## Annual Review

Title: Urban Resilience Programme South Africa
Programme Value £ (full life): £10,000,000		Review date: 14/05/2026
Programme Code: 301487	AMP start date: 14/03/2023	AMP end date: 31/12/2027

Summary of Programme Performance
Year	2023-24	2024-25	2025-26
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003225.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004081.xlsx

SUMMARY AND OVERVIEW

Description of the programme
  1. The Urban Resilience Programme (URP) is providing technical assistance (TA) for inclusive, sustainable, and climate-resilient economic development in South African cities. The programme drew lessons from its predecessor Future Cities programme on local governance, programme delivery models and technical skills gap in municipalities and identified three core pillars guiding programme outputs and outcomes - (1) resilient infrastructure, (2) Inclusive economies, and (3) Urban management and governance
  2. The URP seeks to reduce spatial inequality, alleviate urban poverty, and improve public access to affordable and reliable infrastructure. This is intended to be achieved through capability building of municipal officials in both primary (metros) and secondary (intermediate) cities. The Business Case (BC) identified the following three broad outputs for this programme, which cut across the three pillars noted above –
- building data-based solutions for urban governance and management to streamline urban services and spatial planning processes
- implementing economic development and infrastructure plans in secondary cities to promote green growth, just transition and sustainable development
- facilitating spatial and economic reconfiguration of township economies to be inclusively planned, governed, and financed to become resilient, productive, and investable local economic nodes that support livelihoods and access to services for marginalised communities
  1. The abovementioned outputs will collectively deliver the following outcomes –
- Improvements in access to service delivery, livelihood support and infrastructure for residents of marginalised urban areas in selected municipalities
- Increased investment in sustainable, socially inclusive climate resilient economic infrastructure or value-chain projects in selected municipalities/urban regions
- Enhanced municipal engagement on data and evidence for inclusive access to urban services, accountability, transparency, and civic participation.

Beneficiaries and TA Recipients
  1. The primary TA recipients of this programme are the selected municipalities across metropolitan and non-metropolitan regions of South Africa. Ten secondary cities were initially shortlisted in consultation with the Government of South Africa (GoSA) using a range of factors including TA need, governance, economic and social impact, and financial stability. However, based on the in-depth project and municipal assessments conducted in 25/26, it was concluded that only 4 municipalities from the original shortlist could be supported as the other 6 were deemed unviable projects in high‑risk municipal environments. A new municipal beneficiary, uMngeni Local Municipality, was added through FCDO partnership with Adopt-a-Municipality initiative of Department of Public Works and Infrastructure (DPWI) and Infrastructure South Africa (ISA). In addition to these partners, several national and provincial departments including National Treasury (NT), Cooperative Governance and Traditional Affairs (COGTA), and South African Local Government Association (SALGA) are indirect recipients of technical support as the strategic stakeholders of the programme. FCDO has agreed a programme governance framework with these stakeholders through a signed Memorandum of Understanding.

  1. The indirect beneficiaries of this programme are the residents in target cities who stand to benefit from improved municipal capacity to govern, promote local economic growth and achieve better service delivery because of programme activities. It is expected that the programme support will deliver benefits for over 1.5 million households across the cities receiving technical assistance.
  2. The programme activities and its target beneficiaries are informed by a gap assessment of the South African economy, in particular the enduring impact of spatial inequalities formalised under Apartheid through an exclusionary policy regime. Income and wealth inequality is the highest in the world, with a national Gini coefficient of 0.63. Covid-19 further weakened the economic and social conditions of a highly urbanised population already experiencing unemployment and poverty. Industrial decline and poor service delivery has further worsened quality of life in non-metro regions in economically non-dominant provinces like Limpopo and Mpumalanga. This has entrenched spatial inequality manifesting across provincial lines.
  3. As noted in the business case, South Africa needs to tackle urban inequality to create a sustainable, stable, and green economy that also promotes democracy and institutional accountability. Promoting inclusive and economically robust cities can expand value chains and offer greater access to markets and human capital for South African and international businesses. The programme is building capacity at varying scales in cities across the country tackling a range of technical gaps, which allows the programme to achieve a reasonable breadth of impact while building evidence for what works in non-metro regions compared to metropolitan centres.
  4. The programme is also improving alignment of urban infrastructure projects with other priority areas such as just energy transition, climate adaptation and mitigation and gender equality by mainstreaming these outcomes within the programme design and delivery.
  5. The following table provides geographical spread of the programme since its commencement. Some programme activities at national level are designed to indirectly benefit all municipalities across South Africa. Municipalities which received direct TA in 2025-26 are highlighted in green, including those where TA was discontinued after in-depth project and municipal risk assessment.

Province	Gauteng​	KwaZulu Natal​	Eastern Cape​	Limpopo​	Mpumalanga​	Western Cape
Municipalities	Primary Cities (Metros)
	Tshwane	eThekwini	Nelson Mandela Bay	N/A	N/A	Cape Town
	Johannesburg
	Secondary Cities and small towns
	Emfuleni​	Alfred Duma (Ladysmith)​	King Sabata Dalindyebo (Mthatha)	Polokwane​	Steve Tshwete​
	Mogale City​	Ray Nkonyeni​	​	Thulamela ​	Mbombela​
	​	Newcastle​	​	​	Pixley ka Seme
		uMngeni
		Ugu District

Delivery Partners
  1. The programme is delivered through a combination of accountable grants and commercial contracts with local and international organisations. Delivery partners for individual outputs were chosen based on specific expertise, experience and ability to deliver the required quality and meet beneficiary needs. This demanded robust programme governance to achieve cohesive delivery and maintain consistent performance quality across the delivery partners. Recommendations are provided to improve programme coordination in further sections.
  2. The following table provides a summary of the delivery partners and associated projects funded by the programme in 25-26. In 2025-26, two new agreements were signed. A development capital grant of £1million was approved for NEPAD Business Foundation to fund municipal water infrastructure to reduce revenue loss in municipalities, and a £30,000 accountable grant was issued to Isandla Institute to support South African National Treasury’s Just Urban Transition project providing policy assistance for informal settlements upgrading. Previous ARs can be accessed for information on closed projects.
Component	Delivery partner	Contract Type	Contract/ Agreement value	Business Case Outcomes
Data Capability Support in Metros	Open Cities Lab (OCL), South Africa	Accountable Grant (RDEL)	£1,361,000	Improvements in access to service delivery, livelihood support and infrastructure for residents of marginalised urban areas in selected municipalities ​.
Just urban transition approach to informal settlements	Isandla Institute	Accountable Grant (RDEL)	£30,000
Spatialised Economic Activity Data (SEAD-SA)	Human Sciences Research Council (HSRC), South Africa	Accountable Grant (RDEL)	£192,784	Enhanced municipal engagement on data and evidence for inclusive access to urban services, accountability, transparency and civic participation.
Local Economic Development in Secondary/Intermediate Cities	Adam Smith International (ASI)	Commercial Contract (RDEL)	£5,800,000 (URP allocation with total contract value at £9.6million incl. JETP allocation)	Increased investment in sustainable, socially-inclusive climate resilient economic infrastructure or value-chain projects in selected municipalities/urban regions.
Municipal Non-Revenue Water Partnership	NEPAD Business Foundation (NBF)	Development Capital Grant (CDEL)	£1,000,000

Summary supporting narrative for the overall score in this review
  1. This is the third Annual Review of the Urban Resilience Programme. The programme BC was approved in January 2023 with a start date of 1 April 2023. An addendum to the BC was approved in Q3 of 2025 to allocate up to £2 million CDEL budget to the programme to deliver new infrastructure in municipalities over and above the existing pipeline. Across the programme, technical assistance is enabling municipalities to unlock and derisk investment in catalytic infrastructure and land development projects, improve service delivery and decision-making, and expand access to high-quality economic data for policy and planning. In the third year, progress was made on the project preparation assistance for local economic development in secondary cities, including the establishment of a new partnership with ISA and DPWI to support Adopt-a-Municipality initiative. Advisory support is also helping to strengthen infrastructure planning and project packaging processes, reducing the risk of resource wastage for both municipalities and the FCDO on unviable projects. For example, in Newcastle Municipality the TA resulted in a land-use approach based on market sounding study for a major urban redevelopment project, which deviated from the Municipality’s council approved proposal. This has enabled evidence-based city planning prompting the Municipality to consider demand and market appetite instead of promulgating traditional land-use schemes that place disproportionate emphasis on state-led development.
  2. One of the main challenges this year was reallocation of resources towards viable projects in selected municipalities that meet the programme objectives and risk appetite, while maintaining a consultative approach to stakeholder engagement with Cooperative Governance and Traditional Affairs (COGTA) and South African Local Government Association (SALGA) on unviable projects. This resulted in a decision to discontinue TA to high-risk projects and municipalities to ensure the programme continues to deliver good VfM. However, significant time and resources were spent by FCDO to communicate this effectively to strategic partners. At points, limitations in the effectiveness of stakeholder engagement by delivery partners increased reputational risk to the programme; this was managed through timely escalation and engagement with senior leadership within the Government of South Africa. The appointment of a new Technical Lead to the delivery partner consortia in Q2 improved delivery pace by streamlining programme governance, including Task Order redesign and the adoption of a stage-gate delivery approach. Dedicated cross-consortia sessions were also led by the ASI Team Lead on issues and risks to bring a coherent delivery approach to the programme. Through formal escalation, improvements were made by ASI. These are further elaborated in later sections.
  3. Progress in municipalities where projects were identified for TA continued with the establishment of project governance, ways of working and several executive-level presentations to ensure buy-in for the projects. With the FCDO Programme Manager role being filled in March 2025, the risk of insufficient capacity was partially mitigated. Nevertheless, while the programme team is fully staffed, the scale and technical complexity of the programme continue to pose a risk of undercapacity.
  4. Overall, the programme demonstrated substantial progress, even though pace of delivery, especially with communication and handover of unviable projects for some of the cities could have been improved. The programme exceeded expectations for 43% of the outputs. Based on this and the detailed output assessment provided in further sections, the overall Annual Review score for this programme is A.

Major lessons and recommendations for the year ahead
  1. The following table provides an overview of progress made against the recommendations provided in the previous Annual Review.
Recommendations	Implemented (Y/N)	Progress overview
Expand engagement with GoSA to share best practices for urban infrastructure planning and service delivery, especially where existing programme assets and products can be replicated to support new government programmes focussed on dealing with municipal performance.	Ongoing	Programme approach and lessons were presented to several SA-led forums such as SALGA’s National Economic Working Group, and a learning exchange is planned for May/June to share best practice with municipalities for bankable infrastructure projects.
Adjudicate resource allocation and work planning for project preparation support to generate quick wins and illustrative examples of bankable projects. Additionally, explore mechanisms to scale and replicate data assets and tools produced by the programme to support other municipalities with clear demand for TA.	Ongoing	Mijibora, a community of practice led by OCL, successfully shared data strategies and best practice for data governance with several KZN municipalities who leveraged the CoP sessions to independently develop municipal approach to data-drive decisions. A rapid response approach was developed by ASI to enable short-term TA e.g. uMngeni Municipality whereby ASI led a workshop to demonstrate how peri-urban township-based development initiatives can be reframed and packaged for investment. Other tools produced are yet to be tested for replicability.
Subject to funding availability, develop recommendations for potential interventions to support access to affordable housing in townships and other historically disadvantaged areas.	Yes	Recommendations to support policy reform and market-led interventions were developed. These will be shaped further in 26/27 for implementation. Short-term funding to Isandla Institute for policy advisory on informal settlements upgrading will also contribute to housing gaps.
Continue engagement with strategic government partners like National Treasury on economic development where relevant projects are now closed such as Township Economic Development support by Sustainable Livelihoods Foundation. Establish formal/informal methods to advise and support NT to carry forward this project and ensure sustainability. This could include an independent evaluation and roadmap development for township economies.	Ongoing	FCDO continues to maintain a relationship with NT through SEAD-SA and other UK-funded initiatives allowing regular updates on previously funded projects like TED. While an independent evaluation has not been feasible due to funding limitations, NT has carried on delivery of TED interventions.

  1. The main lessons from the third year of this programme are as follows –
- Political Economy –
  - Municipal infrastructure delivery in South Africa is shaped by a fragmented intergovernmental system with uneven autonomy, misaligned incentives and competing priorities across local, provincial and national actors. While URP has partially strengthened coordination—most notably between National Treasury and COGTA on secondary cities—systemic fragmentation continues to constrain cohesive infrastructure planning.
  - Donor-led programmes in South Africa have limited ability to convene and align critical government actors around standardised approaches to project preparation, finance mobilisation and municipal capacitation without a committed national coalition. Emerging evidence shows that achieving system-level change depends on national stakeholders assuming an enabling role, actively distilling and disseminating lessons across government, with targeted support from delivery partners.
  - Delivery has taken place in a volatile institutional context marked by financial distress and increasing political interference, particularly ahead of local government elections, which has reduced the programme’s ability to focus beyond immediate project‑level objectives. However, partners such as Infrastructure South Africa (ISA) have shown that strong governance structures can buffer these risks and actively advance programme objectives, offering valuable lessons on institutional culture and ways of working within GoSA.
- Project Identification –
  - Prioritising local economic development as the main criterion for programme TA led municipalities to propose projects that were policy‑aligned but often lacked commercial viability and should have been market‑led. In some cases, projects progressed through municipal approval processes but remained fundamentally unviable, either due to reliance on poorly managed bulk services or because they were assessed as too high‑risk to attract market interest. Other infrastructure proposals demonstrated potential to catalyse investment but remained at an early conceptual stage, making them unsuitable for technical assistance within the programme’s three‑year delivery timeframe and level of ambition. In addition, experience showed that some municipalities not originally classified as secondary cities—notably uMngeni—presented a stronger and more viable project pipeline than several municipalities included in the initial secondary city cohort.
  - This lesson resulted in the development of a revised project selection criteria in late-2025 emphasising investment readiness as one of the key parameters to help the programme rapidly screen viable projects and reduce resource wastage on commercially unfeasible and conceptually weak projects.
- TA Sustainability–
  - The programme continues to deliver in a challenging municipal environment characterised by limited capacity and insufficient technical skills to plan complex economic infrastructure projects. Some of these constraints stem from structural issues beyond the scope of the programme, resulting in delivery that is necessarily focused on achievable project‑driven outcomes.
  - Moreover, the misalignment of FCDO’s risk appetite with that of its national and sub-national stakeholders has led to challenges in co-developing TA scope that provides VfM for the programme while mitigating reputational risk to FCDO. For example, in municipalities where institutional instability would reduce the effectiveness of TA, the programme handed over project recommendations to officials for further development under national government guidance and without FCDO funding. The programme stakeholders were initially unreceptive to this approach and preferred the programme to continue investing in TA in spite of the known risks and issues. However, through senior engagements a systemic handover process was eventually agreed.
  - The main lesson from this is that sustaining VfM in high‑risk municipal environments requires willingness to withdraw TA and formalise handover, rather than prolong support that cannot deliver sustainable outcomes, and ensuring clear risk boundaries are established upfront with beneficiaries.

  1. Recommendations for the year ahead –
Recommendations	Responsibility			Due
	Lead	Implement	Consult
With only two years of delivery remaining, refine the programme’s objectives to focus on intermediate outcomes that rapidly enable activities within the programme’s risk appetite. This includes sourcing new projects from municipalities where FCDO holds existing and productive relationships, and prioritising core economic infrastructure projects for project preparation without duplicating other FCDO programmes. Any new activities and/or beneficiaries being considered for programme funding must be able to show noticeable progress towards the higher order outcomes by March 2028.	FCDO	FCDO and delivery partners	GoSA Stakeholders and Beneficiaries	Ongoing
Minimise stakeholder engagement with municipalities until a project is screened for viability to manage expectations. Ensure the risk appetite is clearly communicated to beneficiaries and strategic programme partners.	FCDO	FCDO and delivery partners	GoSA Stakeholders and Beneficiaries	Ongoing
Where possible, leverage existing and new strategic relationships, both at municipal level and the wider urban development ecosystem, to pivot towards influential, convening actors such as National Treasury to unblock and sustain momentum, and ensure FCDO’s Value for Money framework is clearly communicated to prevent misalignment of objectives.	FCDO	FCDO	GoSA Stakeholders and Beneficiaries	By March 2027

THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Validity
  1. The original BC Theory of Change (ToC) remains largely as is with minor changes applied to the outputs to streamline monitoring and reporting process and strengthen the link between partner activities and programme outcomes. Some milestones were increased due to additional activities delivered through the BC addendum.
  2. The programme can realise the long-term impact of resilient urban economies with higher socio-economic productivity, reduced poverty and inequality, inclusive growth​ and sustainable urbanisation through the broad outcomes of – 1. Improvements in service delivery and livelihood support; 2. Increased investment in inclusive economic infrastructure; and 3. Enhanced municipal engagement on data and evidence.
  3. The ToC outlines a set of intermediate outcomes within the municipalities as outlined below, which are achievable within the programme’s life through appropriate output delivery and will increase the confidence in programme’s ability to deliver on long-term outcomes mentioned above.
    1. Increased capability to expand service delivery and economic activity to marginalised urban communities through public and/or private investment in low-income, vulnerable, and historically spatially excluded urban areas such as townships and informal settlements.
    2. Institutionalisation, municipal buy-in and delivery of integrated local economic development plans and projects thereof for targeted urban/peri-urban areas in metros and intermediate cities with climate, gender equity and social inclusion benefits.
    3. Strengthened data ecosystem and evidence-driven planning approach within selected municipalities and increased civic engagement through public access data platforms such as SEAD-SA and Service Delivery Simulator.
  4. These intermediate outcomes are important because they show whether the programme’s overall approach is working. All delivery partners have worked to secure buy‑in from government institutions so that the programme’s outputs are accepted and used. The support provided is designed to build practical skills within municipalities, with officials involved throughout so they can take ownership of the work. Where challenges arose—such as limited capacity, changing priorities, or lack of commitment—the programme adjusted its approach to stay on track at output and intermediate outcome level, with outcome‑level effects expected to materialise beyond the programme timeframe.
  5. A capital grant through NEPAD into the non-revenue water fund is an investment in systemic interventions that will improve municipal capability to support existing and future development by increasing revenue collection that can be reinvested into municipal infrastructure maintenance. Supported municipalities have, in return, signed an agreement to implement their water management strategies to ensure the investment can deliver the desired revenue and service delivery benefits.
Evidence
  1. Validity and limits of assumptions: There is strong global and South Africa‑specific evidence supporting the programme’s Theory of Change, and key assumptions (such as institutional stability, political economy dynamics, and municipal ownership of TA) remain broadly valid. However, the core assumption that municipalities will independently adopt and sustain infrastructure planning, delivery and financial reform practices introduced through FCDO‑supported projects has not yet been fully validated.
  2. Sustainability of capacity building: Evidence from ASI’s market studies suggests that it remains uncertain whether programme tools and methodologies will be replicated by municipalities without external support to drive systemic change. While specialist functions (e.g. engineering, environmental assessments and contracting) are expected to remain outsourced, the programme has demonstrated potential to strengthen municipal officials’ ability to oversee consultants effectively and reduce the risk of inefficient or improper use of municipal budgets.
  3. TA Effectiveness and Institutional Adoption: The programme aims to tackle severe and deeply rooted municipal challenges and further evidence was gathered by delivery partners on how the current TA delivery model is resulting in improvements in institutional skills and infrastructure. FCDO also conducted various site visits and beneficiary engagement throughout the year to assess progress and collect stakeholder feedback. All outputs had sub-indicators measuring level of adoption of technical outputs and total funding secured for project implementation. Stakeholder interviews conducted by ASI, verified by FCDO, showed a high degree of relevance and quality of TA for the municipalities with some municipal officials remarking on the programme’s ability to bring in specialist skills which the municipality could not afford. As most projects remain in early business case stage, the impact of institutional adoption of programme outputs is yet to be assessed.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
  1. The programme is currently on track to deliver on the intended impact of inclusive and climate-resilient economic development in cities by way of investment and improvements in livelihoods support and socially inclusive value chain projects. For example, the Polokwane Agri- and Logistics Hub, a project supported through the local economic development component of the programme, supports inclusive growth by lowering barriers for smallholder farmers and emerging agri-businesses to access markets through shared processing, storage and logistics infrastructure. By focusing on agro-processing and downstream services, the project helps diversify the local economy beyond primary agriculture and strengthens regional value chains. Through the programme’s support, Polokwane municipality was able to test various scenarios for the Hub’s development, prioritising commercial viability, municipal revenue and inclusionary benefits.
  2. In 2026-27, the programme will prioritise the delivery of pipeline developed by ASI in partnership with ISA, COGTA and SALGA, and may also consider expanding support to other spatial and data reforms in National Treasury. The programme scope continues to work towards the outcome targets to support 1.5 million households across the municipalities receiving technical assistance by way of enabling improved services and decision-making. The overall assessment of outcomes will be conducted in the final year of programme delivery.

  1. The following table outlines main progress and actions in 25-26 associated with each output that remains in delivery. Outputs achieved or closed in previous years are not included.

Outputs	Progress Update and Key Actions
Selected metro and secondary/Intermediate city municipalities benefit from technical capability and investment to enable local economic development and improved service delivery	Despite delays due to insufficient municipal data and protracted project assessment of infrastructure pipeline, this output is now progressing well; and subject to municipal responsiveness to technical support, it is expected to make noticeable progress against the programme outcomes and impact in the year ahead. New project selection criteria and stage-gate approach is helping streamline decision making ensuring issues and risks are escalated appropriately. Capital investment in 4 municipalities through NEPAD fund further contributed to water infrastructure implementation which will result in improved services. / Action: Programme should continue to actively manage resource allocation across the portfolio and prioritise low risk, higher return projects to ensure the TA is able to leverage a reasonable amount of funding to advance projects through to implementation while building municipal capability for project preparation and packaging. Disbursement of the CDEL grant will continue to be monitored against the project level logframe to ensure it is directed towards agreed targets.
Municipalities equipped with data-driven planning and decision-making tools, data strategies and processes	Both HSRC and OCL-led projects have closed successfully. Key use cases that optimise municipal decision-making process, asset management, and planning of water and sanitation services were concluded. Lessons from the metros were shared with other municipalities in KZN province through a community of practice to inform their data governance and strategies. HSRC gathered large amounts of SARS and Stats SA datasets to refine the SEAD-SA platform and conducted extensive awareness campaigns to increase the uptake of this granular socio-economic data in municipalities. The second Cities Economic Outlook Report was published on 31 March 2026 highlighting latest trends in urban productivity and growth which is expected to inform municipal planning. / Action: Drawing lessons from these projects, shape the next phase of support to Mzansi Exchange in National Treasury.
Strategic workshops to develop action plan based on policy and practice defined by National Treasury for a just urban transition in informal settlements	Isandla Institute conducted a series of engagements in partnership with National Treasury to socialise the key findings of NT’s Just Urban Transition for Informal Settlements report. The workshops conducted will result in action plans that dictate the role played by various actors in transforming informal settlements towards better service delivery, improved livelihoods and decent housing. / Action: Project closed, however, some of the learnings will shape future support to NT on human settlements policy as part of Operation Vulindlela Phase II reform.
Summary
A new output was added to record the delivery by Isandla Institute. The CDEL contribution to NEPAD resulted in additional results achieved against Output 2 capturing the total value of investment in municipal infrastructure. The logframe review notes that the output indicators remain relevant with the need to add new outputs and refine the indicators to the programme should there be an expansion of scope to support Mzansi Exchange and spatial reform initiatives.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
  1. The programme continues to offer good value for money for the UK based on its targeted impact and outcomes of reducing spatial inequality and improving infrastructure planning, which can create jobs and boost livelihoods while generating opportunities for private sector investment. The programme has also unlocked opportunities to engage other government stakeholders who have the mandate to improve local government services such as, DPWI and ISA, whereby technical products from this programme can be replicated to assist with the delivery of cross-government priorities.
  2. The initial municipal infrastructure pipeline assessment offered important lessons that shape effective approach to project packaging and investment mobilisation in low-capacity municipal environments; and it has provided FCDO with valuable tools to engage municipalities in future to increase infrastructure bankability such as market sounding studies, investor mapping and multi-criteria decision analysis tool to test project viability. The identified programme levers of digital governance, infrastructure planning and catalytic investment are well positioned to deliver on the strategic objectives articulated in the programme Business Case. It is recommended that the programme should continue, and the recommendations provided by this Annual Review are duly adopted by relevant programme stakeholders.

DETAILED OUTPUT SCORING

Output Title	Selected metro and secondary/Intermediate city municipalities benefit from technical capability and investment to enable multi-sectoral local economic development in key urban nodes through inclusive infrastructure planning and project packaging for Paris and GEDSI aligned investment.
Output number:		2	Output Score:	A
Impact weighting (%):		65%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
Percentage of local economic development/infrastructure projects identified by the programme in secondary cities with proven financial viability and ability to deliver climate and GEDSI benefits	50%	Met (50%) / This includes one urban development project in Newcastle and 4 non-revenue water projects to be delivered through NEPAD. In total, there are 10 projects in delivery that provide climate and GEDSI benefits. More projects will be added to the pipeline in 26-27)
Total value of bankable project pipeline with proven viability and ability to deliver climate and GEDSI benefits	£12,250,000	Met (£12,250,000) / ASI and NEPAD have proven viability for infrastructure with capital value of £12,250,000 to date, with a further £56,000,000 worth of projects in pre-feasibility or feasibility stage)
City of Cape Town is equipped with international best practice in Sector Prioritisation modelling of Energy, Water and Sanitation sectors.	N/A (Project Closed)	N/A (Achieved in 24-25)

Briefly describe the output’s activities and provide supporting narrative for the score.
  1. This output encapsulates improvements in municipal capability to plan and mobilise investment for local economic development through industrial planning, land development and basic infrastructure services. The main activities undertaken in 2025-26 to deliver this output include TA to test viability and develop business case for selected projects in non-metropolitan municipalities. Six projects across five municipalities were identified for project preparation with four more projects receiving capital grant to implement water management interventions to help recover lost revenue from water services in municipalities. The total capital value of projects currently receiving TA is estimated to be over £65 million based on early-stage assessment. However, this may change as the projects go through further stages of financial feasibility review. The milestone for this output will be adapted to reflect emerging data from the programme. NEPAD contribution from the programme has resulted in an investment into water infrastructure with total capital value of £1million, adding to the bankable pipeline created by ASI of £11,250,000.
  2. Delivery pace picked up in 2025–26 but remained unsatisfactory due to limited municipal responsiveness and delays in securing institutional approvals. For example, while the urban development project in Newcastle is financially viable, progress remains dependent on municipal council approval of the proposed alternative land-use plan. Delivery was further affected by weaknesses in the Phase 1 pipeline developed by PwC, which prioritised inclusive growth, climate and GEDSI alignment, but lacked sufficient assessment of financial and institutional viability due to limited data and delivery timeframe. After assuming responsibility for the pipeline, ASI assessed 24 projects and confirmed that only five met the criteria for full TA, with the handover of unviable projects absorbing considerable time and resources. Moreover, FCDO’s need to balance reputational risk against programme VfM hindered swift decision-making on the handover process. A stronger pipeline anchored in investment readiness is expected to improve delivery efficiency and cost-effectiveness over the remaining programme period.
  3. The development capital grant to NEPAD’s non-revenue water fund resulted in direct investment in four municipalities increasing the results achieved against the output indicator of total value of bankable projects and helped the programme meet its milestone for 2025-26.
  4. All output milestones noted in the logframe were achieved by the end of the review period despite the institutional constraints within beneficiary organisations. Therefore, the output is scored an A due to a successful delivery of critical programme outputs.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
  1. The output indicators were not changed however one of the milestones corresponding to the total value of bankable projects was increased to capture new results delivered through NEPAD CDEL contribution of £1million. Based on this Annual Review, some revisions may be necessary to the output and indicator definition as well as targets to effectively align the scope of work delivered through ASI as more projects are added to the pipeline.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
  1. In line with the previous year’s recommendations, the programme output and outcome indicators were refined to align with the pipeline targets determined through ASI’s assessment of project and municipal data. The programme governance structure with COGTA and SALGA was also revised by redefining the steering committee as the National Advisory Committee (NAC). This is to ensure that it remains a platform to share progress updates and key findings instead of a decision-making forum, except where stakeholder input is sought to agree external communication. For example, the NAC assisted in agreeing the handover process for unviable municipalities resulting in improved coordination across the stakeholders including ASI.
  2. Lessons – Value of capital investment (public and private) in municipal projects depends on factors such as land value, market appetite and wider state of municipal services and fiscal health. Though it is logical that the programme measures value of mobilised investment as a success metric, it remains challenging to establish a target without detailed financial modelling of selected projects. Additionally, the ability of this output to translate into wider improvements in municipal services and livelihoods (outcome) is underpinned by the assumption that necessary institutional reforms will be implemented to incentivise private sector investment and efficient use of NT grant funding. While municipalities were selected based on expressed demand at BC design stage, the resulting cohort proved only partially aligned with the programme’s intended ambition, reducing outcome confidence where deeper systemic constraints fell outside the scope of TA. Going forward, prioritising support to municipalities that are showing improvements in fiscal health and have minor political instability risk would offer the best outcomes for the programme.
  3. Recommendations – Output indicators and milestones should be refined in line with data emerging from the review of project pipeline instead of setting an upfront target with limited evidentiary support. Project selection should continue to be based on outcomes that are within the programme’s ability to influence, directly or indirectly. TA should be prioritised in fewer municipalities where projects are capable of reaching financial close within the programme’s duration.

Output Title	Municipalities equipped with data-driven planning and decision-making tools, data strategies and processes aimed at achieving integrated, efficient, and inclusive urban planning, governance and management including public access to reliable, accurate and up-to-date datasets through dashboards such as Strat Hub and Spatialised Economic Activity Data-SA (SEAD-SA)
Output number:		3	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
Completed data strategy for eThekwini Municipality including technical interventions to integrate existing data platforms such as Start Hub and ISIMS	Completed and endorsed Data Strategy	Achieved / OCL developed a draft Data Strategy and implemented the use cases to assist eThekwini Municipality to operationalise data strategy independent of additional technical assistance.
Number of sensitisation workshops conducted with internal AND external stakeholders, especially marginalised communities, on data assets and application (disaggregated by gender, age, disability, and other characteristics as applicable)	24	Exceeded (25) / This includes use case engagements, advisory support; capacity building through community of practice sessions by OCL. HSRC facilitated provincial training in the Eastern Cape, an awareness session at the World Bank Urbanisation and Development Conference and online seminars ahead of the Cities Economic Outlook.
Number of economic and other municipal datasets, toolkits, and assets accessible to municipal departments and public (where applicable) in usable format	15	Exceeded (20) / Toolkits: Data Strategy toolkit, AI governance models, Training content for municipal leadership and the Spatial tax (SEAD_SA) website. / Data assets: ETK CR Tool, CCT EAM tool and130 Spatial Economic Datasets from SARS and Stats-SA accessible through SEAD-SA platform / Data strategies: 7 municipalities were supported to develop and enhance data strategies, one of which has been council approved (Ugu) / Cities Economic Outlook report 2026 / 5 Policy briefs by SEAD-SA

Briefly describe the output’s activities and provide supporting narrative for the score.
  1. The purpose of this output is to achieve improved urban planning, management, and governance through the provision of valuable data infrastructure and capabilities in municipalities and national government.
  2. This output is delivered through two projects with separate delivery partners (HSRC and OCL) targeting different aspects of data related capacity building in local government – access to spatialised economic data (SEAD-SA) and application of data in municipalities to inform service delivery decisions, respectively. Collectively, the two projects aim to address upstream access to consolidate spatial data and downstream capability to embed complex datasets in day-to-day sub-national operations.
  3. The HSRC project closed on 31 March 2026 with the publication of second Cities Economic Outlook Report. OCL also concluded the majority of support to municipalities with some outstanding actions on Mzansi Exchange, a National Treasury initiative. A no-cost extension to 30 April was approved for OCL to effectively close the project in line with the agreed workplan.
  4. With increased spatial accuracy for employment and firm-level data, especially for non-metro regions, SEAD-SA has matured into a trusted, high impact public data infrastructure supporting evidence based and inclusive local economic policy. Some examples of its success include Western Cape Spatial Economic Dashboard which integrated SEAD-SA as a key source for its planning decisions; training workshop for nearly 100 participants from Eastern Cape provincial government on how to embed SEAD-SA in operational decisions; and a policy brief highlighting the correlation between jobs, firms and spatial inequality to provide recommendations for improving inclusive economic growth in regions facing economic decline.
  5. Access to SEAD-SA database has also enabled improved analysis across the programme, for example, spatial data for uMngeni Municipality over the last few years showed a pattern of growth correlated to improved governance and political stability in comparison to its neighbouring municipalities. This helped validate one of the key assumptions of the programme that institutional stability is critical for infrastructure investment and inclusive development.
  6. SEAD-SA also supported the National Treasury’s Secure Data Facility by enabling reliable and faster data production that can be embedded within wider cross-government data sharing platforms.
  7. In some cases where technical outputs provided to the municipalities were limited, Mijibora, a Community of Practice led by OCL, helped raise awareness and advocacy for data-driven planning and was widely credited with shifting how institutions think about data—from siloed reporting to strategic, integrated assets. In addition to learning dissemination, OCL support resulted in strong uptake by operational staff, improved collaboration between technical and line departments, exposure to agile ways of working, and concrete use of data outputs in planning and operational analysis.
  8. While the output exceeded its milestones, OCL-led project delivery faced challenges such as uneven coordination between technical advisors and municipal counterparts, reliance on a small number of officials causing bottlenecks, and sensitivities around data‑sharing where governance arrangements for project set-up were weak. These issues were largely mitigated through escalation and trust‑building, and they informed lessons on delivering complex, innovative interventions in unfamiliar institutional contexts.
  9. Given that the partner’s deliverables resulted in nationally embedded data assets and uptake beyond the original target municipalities through the MijiBora Community of Practice, this output exceeded expectations and is therefore scored an A+.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
  1. The targets for this output were changed during the past year with the inclusion of Mzansi Exchange support through OCL.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
  1. The previous AR recommended that the programme identify opportunities to share scalable data assets and tools with municipalities that have limited ability to access technical expertise. This has been achieved through Mijibora, a community of practice established by OCL, which resulted in uptake of data strategies and replication of several use cases focussed on service delivery based on programme support to eThekwini and City of Cape Town.
  2. Lesson – If left unaddressed, inconsistency in local government capability and data maturity between metros and non-metros can heighten the digital and spatial divide with respect to municipal decisions that directly impact service delivery. Through this programme, smaller municipalities were exposed to innovative tools for data and evidence-led planning. Even so, they require a strategic shift in how to use data science and consistent technical support to transform municipal services, both of which are not within the scope of this programme.
  3. Given SEAD-SA was primarily led as a research project with extensive focus on metro data, reflections from programme beneficiaries note the need to shift research agendas towards municipality‑driven problem statements, while peer learning from stronger metros should be used systematically to build confidence and trust in weaker municipalities. Mzansi Xchange is expected to address this issue with increasing number of municipalities taking the initiative to build internal data and digital infrastructure.
  4. Recommendation – FCDO should continue to support the development of digital public infrastructure by leveraging national policy momentum and strategic leadership. As public funding for these initiatives increases, targeted FCDO support drawing on UK and international best practice can significantly enhance the impact of GoSA’s data and digital strategy.

Output Title	Strategic workshops to develop action plan based on policy and practice defined by National Treasury for a just urban transition in informal settlements
Output number:		5	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of strategic engagements with relevant government / departments/structures delivered	5	Met (5) / 2 roundtables for CSOs and municipalities exploring how CSOs can continue to fulfil a supportive intermediary and advocacy role in advancing local practice, and municipal realities, capability requirements for scaling participatory upgrading and urban reform needs. / 1 in-person multi-stakeholder roundtable on governance and urban reform. / 2 Strategic engagements with the Presidential Employment Programme and CoGTA discussing recommendations related to public employment programmes for informal settlement upgrading.
Written documentation summarising the findings and recommendations from the workshops	2	Met (2) / Thematic report on the potential of public employment programmes to support livelihoods and informal settlement upgrading / Synthesis report on government reform, coordination, capability requirements and partnering)

Briefly describe the output’s activities and provide supporting narrative for the score.
  1. This is a new output added to the programme utilising existing programme funding to support informal settlements upgrading policy. From previous and ongoing FCDO programmes supporting spatial inequality, informal settlements reform remains a key hurdle for inclusive economic growth. Evidence also suggests that any upgrading process should consider livelihoods and climate resilience. Therefore, through the programme Isandla Institute, in partnership with NT, conducted a series of engagements with civil society organisations, private sector, national and municipal departments to validate NT’s policy recommendations. These workshops resulted in the synthesisation of findings highlight how national public employment programmes can support livelihoods through targeting community-led programmes and job funds towards informal settlement upgrading. Additionally, a report was produced to summarise government reform and partnering approach for various actors with vested interests in informal settlement upgrading.

  1. Overall, the output met both milestone targets with well-documented positive feedback from the recipients of knowledge dissemination products. The output is scored as an A.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
  1. This is a new output and has been achieved in 25-26 AR period.
Lessons learned this year and recommendations for the year ahead
  1. This output has relevance for broader spatial reforms to be undertaken by NT and the SA Presidency’s Operation Vulindlela. Should the programme provide support to this theme in 26-27, lessons from the workshops should inform leverage points for further technical assistance.
## D. VALUE FOR MONEY

Key cost drivers and performance
  1. Overall, VfM remains positive but not yet fully evidenced at outcome level. The programme shows good discipline on economy (competitive procurement, use of lower-cost delivery models where possible, and efforts to reduce travel), reasonable efficiency (in moving procurement and mobilisation forward and the use of existing municipal systems and tools rather than creating parallel ones, thus reducing additional licensing/build costs and supporting user uptake), and a strong commitment to equity through GEDSI integration.
  2. The programme continues to benefit marginalised groups with 100% of the programme budget aligned to GEDSI outcomes by supporting job creation and inclusive development in socio-economically weaker cities and regions of South Africa. VfM performance is strengthened by the integration of GEDSI into project design, tool development, use-case selection, and delivery processes.
  3. Performance on cost-effectiveness is promising but some evidence of early adoption of outputs and improved user capability is still emerging. Robust assessment of implementation and long-term effectiveness of technical outputs will take longer than the programme timeframe allows; and this is expected to rely on the municipal-led implementation translating into measurable results.
  4. The programme’s principal cost driver has been staff/consultant time, with expenses remaining secondary. Across the year, reporting indicates that day rates reduced over the life of the programme and then stabilized at about £388 per day, reflecting a delivery model where higher-cost staff increasingly provided oversight while more implementation was undertaken by medium and lower-cost team members. Budget execution has generally been strong, though overall the programme did have an in-year underspend. Expenses were relatively contained in the earlier quarters but increased in the revised Q3 period because of higher logistics, travel and events costs linked to close-out and engagement activity.

VfM Indicator	Benchmark	2025-26	Trend
Economy – Average consultant fee rate for technical experts	£700	£388	↑
Efficiency - Average cost of TA per municipality	£1.3m - £3m	£141k	↑
Efficiency - % of programme costs allocated to management and admin	10%	13%	↑
Effectiveness – % of government departments supported who are reporting improvements in capability to plan and implement infrastructure delivery and attract investment	0	84%	↑
Equity - % of spend directly targeting beneficiaries from marginalised communities or, in historically disadvantage geographies	60%	100%	↑
Cost-Effectiveness – Value of public/private finance leveraged per unit cost of TA	0	N/A *	N/A

* Mobilised funds will depend on the bankable projects identified, and the final amount will be known at the end of the programme.
VfM performance compared to the original VfM proposition in the business case
  1. The original VfM proposition combined commercial delivery with accountable grants to balance flexibility, expertise and scalability. While TA on project preparation through ASI enabled rapid access to a wide-ranging, and otherwise cost-intensive, technical expertise in project finance required by municipalities, the accountable grants delivered strong VfM through adaptive delivery aimed at system-level impacts. For example, SEAD-SA and Open Cities Lab generated national data and digital public goods, and NEPAD leveraged existing municipal partnerships to quickly build investable water infrastructure pipeline to deploy Dev Cap Grant that can generate municipal revenue through financial assets. Collectively, these approaches maximised reach of the programme and reduced duplication of efforts needed to establish relationships with beneficiaries.
  2. Year 2 experience has validated this further with important refinements. The business case expected the evidence of effectiveness to be demonstrated not only through cost control and delivery design, but also through evidence of adoption, institutionalisation and wider impact. The quarterly and annual reporting shows this is partially happening but also highlights practical constraints. Particularly delayed post-deployment assessment, variable municipal readiness, and data availability issues, which mean that effectiveness evidence is still maturing. Many inherited project concepts lacked readiness or viable financing pathways. By strengthening early diagnostics, introducing appropriate decision tools and exiting weak projects, the programme avoided sunk costs and misallocation. Additional VfM was achieved through partnership leverage, co-financing and co-production approaches, increasing the likelihood that TA would inform municipal decisions rather than stand-alone outputs.
Assessment of whether the programme continues to represent value for money
  1. Based on the evidence reviewed, the programme continues to represent good value for money by supporting UKinSA Country Plan objectives, including inclusive economic growth, just transition, and good governance. It delivers value through its contribution to improved urban infrastructure and spatial equity, which are critical to South Africa’s economic development. The programme has also strengthened UK relationships with key government institutions, creating opportunities to influence infrastructure planning and policy reform.
  2. While it is too early to demonstrate investment mobilisation at scale, the programme has delivered VfM by identifying and stopping non-viable project pathways early, strengthening evidence through market testing and feasibility assessments; delivering GEDSI-related benefits across all projects; and learning from early challenges feeding directly into improved sequencing, engagement and resource allocation.
  3. This judgement is qualified by slower than planned mobilisation and implementation constraints, including delayed municipal approvals, stretched municipal capacity, and an underspend earlier in the period before expenditure accelerated. This means VfM remains positive, but stronger evidence of realised efficiency gains and results will be strengthened further as the programme concentrates effort on a smaller portfolio of viable projects, applies disciplined stage-gates, and progresses projects toward feasibility and financing decisions where outcomes become more quantifiable.
## E. RISK
Overview of risk management
  1. Overall, the programme continues to operate at a moderate risk, consistent with the original Business Case risk appetite. Risk is actively monitored through quarterly programme reviews, delivery partner reporting, and ongoing political economy analysis at municipal level.
  2. Given the scale and complexity of delivery across multiple municipalities and partners, risk management focuses on identifying systemic and portfolio-level risks, rather than all individual project-level issues with the latter delegated to delivery partners to manage. Financial, fiduciary, safeguarding and delivery risks are reviewed regularly in line with FCDO requirements, with escalation applied proportionately where risks threaten programme outcomes, reputation, or value for money.
Key risks and mitigation
  1. The most significant risks affecting programme delivery during the review period relate to municipal capacity constraints, political and institutional instability, delivery partner performance, and resourcing pressures within the programme team. These risks are interrelated and are managed through adaptive delivery approaches, strengthened governance, and closer engagement with strategic partners.
  2. While delivery remains feasible within the remaining programme period, risk levels are expected to remain moderate in the short to medium term due to factors largely outside the programmes direct control, particularly municipal capacity and political context. The programme team will continue to prioritise adaptive management, selective pipeline decisions, and proportionate escalation to ensure continued delivery against outcomes while protecting UK reputation and value for money.

RISK REGISTER
Risk category	Risk Description	Mitigation Actions	Residual risk
Policy & Programme Delivery	Municipal capacity constraints / - Limited technical capacity, high turnover and weak systems hinder absorption of TA and project progression	The programme has mitigated this risk by prioritising municipal champions, adjusting delivery scope where necessary, and working closely with national partners where appropriate, though residual risk remains.	Major
Strategy & Context	Local elections and shifting municipal priorities disrupt engagement and timelines	While no significant disruption has yet materialised, early signals indicate potential variations in stability across municipalities. The programme continues to monitor political developments closely and apply political economy analysis to inform pipeline decisions and engagement strategies.	Moderate
Policy & Programme Delivery	Stakeholder engagement, forecasting and delivery consistency risks	These have been addressed through strengthened performance management, revised roles within the delivery team, and escalation through contractual channels where necessary. While performance has stabilised over the review period, delivery pace and forecasting accuracy remain areas requiring continued oversight.	Moderate
Policy & Programme Delivery	Increased portfolio complexity without commensurate resourcing	While current resourcing remains sufficient, new delivery partners and complex grant arrangements have required more intensive management than initially anticipated. This risk is actively monitored and may be mitigated through portfolio prioritisation and decisions on future pipeline scale.	Moderate
Financial & fiduciary	Fraud, misreporting	Financial and fiduciary risks remain well controlled through robust due diligence, quarterly financial reviews, and payments linked to delivery milestones.	Moderate
Safeguarding	SEAH and BHD incidences within partner organisations	Safeguarding risks have not materialised at programme level; however, isolated incidents within partner organisations have reinforced the need for continued vigilance and clearer communication of reporting expectations, particularly where guidance gaps exist.	Moderate

## F. PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Overview of Commercial and delivery partner Performance
  1. Delivery performance across the programme was mixed but showed marked improvement in the latter half of the review period. The accountable grant partners — the Human Sciences Research Council (HSRC) and Open Cities Lab (OCL) — continued to demonstrate strong technical delivery, maintaining momentum on complex multi-year data initiatives. HSRC delivered major enhancements to the Spatial Tax Panel (STP) and increased institutional uptake among provincial and national bodies such as Western Cape provincial government, National Treasury’s Secure Data Facility and CIPC. HSRC also led a successful launch of the Cities Economic Outlook report 2026, which positioned SEAD-SA with a mature, well embedded data infrastructure in government systems. OCL’s performance was similarly strong. The team delivered multiple data assets for Cape Town and eThekwini, strengthened municipal data strategies, and expanded sub-national communities of practice that now attract participation across provinces. OCL also advanced adoption, deepened qualitative evaluation processes and maintained consistent delivery of knowledge products and stakeholder engagements.
  2. NEPAD Non-Revenue Water (NRW) Fund was awarded a £1 million Development Capital Grant to support the programme’s expanded focus on municipal water security. Despite some initial challenges in navigating the CDEL and constructive obligation arrangements as well as contextual issues such as limited municipal capacity, procurement delays, and resource bottlenecks, NEPAD successfully secured Implementing Agents across most participating municipalities and advanced procurement for bulk meters, Pressure-reducing Valves, and data-logging equipment.
  3. The Isandla Institute was another new accountable grant signed in this financial year. The partner delivered two high‑quality national‑level roundtables (Civil Society Organisations + Municipal) and advanced strategic engagements with CoGTA, NT, the Presidential Employment Programme, and other stakeholders. Their work established a shared conceptual and practical understanding of a Just Urban Transition (JUT), producing tailored concept notes, facilitation guides, and a comprehensive framing of JUT for informal settlement upgrading. Delivery quality was consistently high, participation strong, and stakeholder feedback very positive. Where scheduling challenges arose, Isandla adapted quickly and maintained delivery momentum.
  4. On the secondary cities' component, performance improved significantly after a difficult mobilisation period in previous year. During the initial months of Year 2, the supplier’s delivery consistency was weakened by leadership gaps, uneven project structuring, and reliance on assumption‑heavy diagnostics inherited from the previous pipeline. By Q3 of 25-26, a strengthened delivery structure, clearer staging of task orders, and intentional municipal engagement enabled more coherent progress across the six active projects, including viable concept refinement for Mbombela Waste Separation, Newcastle Equarand, Polokwane Agri‑Hub, and uMngeni projects under the Adopt‑a‑Municipality partnership.

Gender Equity Diversity and Social Inclusion (GEDSI)
  1. The programme is designed to reduce gender inequities and improve social inclusion without causing harm to any specific vulnerable or marginalised groups. However, due to the nature of technical assistance whereby programme inputs will only deliver benefits for vulnerable groups beyond the life of the programme, the most appropriate indicator of GEDSI is the extent to which programme activities mainstream actions that intentionally improve outcomes for women, youth, elderly and any other target demographics.
  2. GEDSI mainstreaming strengthened across most delivery partners during the review period, with increasingly explicit frameworks guiding implementation rather than ad hoc inclusion. Both HSRC and OCL integrated gendered and age-disaggregated analysis into their data assets, enabling municipalities to apply finer grain targeting of vulnerable groups. SEAD-SA now incorporates detailed indicators on gender, age and income, supporting analysis of inequalities at sub-municipal level and informing decision-making tools such as provincial dashboards. Isandla Institute centres procedural justice and social inclusion through participatory governance and livelihoods-focused approaches in informal settlements, ensuring interventions reflect the needs of vulnerable groups. NEPAD’s GEDSI specialists targeted service improvements in low-income and informal communities, supported by inclusive employment and procurement requirements, including a minimum 35% participation of women and proactive inclusion of persons with disabilities.
  3. For municipal infrastructure support, the adoption of GEDSI markers within early‑stage project filtering, feasibility work, and concept design contributed to more systematic assessment of social risks and distributional benefits. This approach was applied across core projects, including the Newcastle and Polokwane work, where municipal workshops explicitly engaged on differential impacts on women, youth and informal workers. The Mbombela Waste Separation project integrated a dedicated Social Value & Impact Assessment to map conditions faced by informal waste pickers and identify opportunities for equitable participation in future recovery systems.
  4. GEDSI integration is becoming more embedded in routine technical workflows, though capacity constraints in municipalities limit the extent to which these practices can be institutionalised without continued support. Deeper integration of empowerment‑focused indicators and consistent tracking of gender‑differentiated benefits remain priorities for the next period.

Budget Profile
  1. By 31 March 2026, the programme had utilised over 61% (£6,146,069.67) of the total multi-year budget of £10,00,000 and about 87% of its financial year allocation. The table below outlines budget and actual spend for each delivery partner categorised by geographical coverage.
Delivery partner	2025-26 Budget	Actual Spend	% of total budget	Geographical Coverage	Output
Open Cities Lab	£590,378	£568,077.68	96%	2 Metros (Provinces - KZN and Western Cape)	Output 3
Human Sciences Research Council	£75,635	£75,239.55	99%	Country-wide	Output 3
Adam Smith International (ASI)	£2,200,000.00	£1,682,991.04	76%	10 secondary cities (Provinces - KZN, Western Cape, Mpumalanga, Limpopo, Eastern Cape, Gauteng)	Output 2
NEPAD Business Foundation	£1,000,000	£1,000,000	100%	Polokwane, Nelson Mandela Bay, Pixley Ka Seme, Johannesburg	Output 2
Isandla Institute	£30,000	£30,000	100%	Country-wide	Output 5
TOTAL	£3,896,013	£3,357,078.95	86%

Financial Statements and Forecasting
  1. At the time of this review, audited financial statements for 2023-24 and 24-25 period are available for OCL, HSRC, SLF, and PwC. Following discussions between FCDO and the ASI regarding audit requirements, it was agreed that either an end-of-programme audit or two audits will be commissioned by ASI over the course of the contract. At the time of this AR, these discussions are ongoing and the final decision will be captured in the contract amendment documents. ASI has submitted annual financial statements in the interim. Other delivery partners’ financial Audit statements 25-26 are expected between July and September 2026.
  2. Financial management across partners remained broadly sound. All accountable grant partners (HSRC, OCL, Isandla, NEPAD) continued to meet FCDO’s standards for financial controls. Minor forecasting variances were observed for HSRC due to unanticipated shifts in personnel allocation, however these were promptly addressed, and annual expenditure remained within tolerance.
  3. Within the commercial delivery chain underspend was recorded during the first half of the year due to project delays and adjustments to the delivery team structure. Improved operational stability from Q3 onwards increased expenditure alignment with planned activities. The programme forecast is reviewed monthly based on delivery partners’ reporting. Overall, financial management remains compliant, with risks relating primarily to forecasting accuracy and pace of delivery rather than fiduciary controls.

Commercial Contract Performance (KPIs)
  1. Performance of the commercial supplier was assessed against the agreed KPIs, which are reviewed quarterly and are linked to fees at risk. Performance over the review period showed gradual improvement, particularly in responsiveness and technical engagement. However, persistent weaknesses in financial forecasting and delivery discipline materially affected performance. Forecast accuracy was not met although Q1 variances were within tolerance, material underspends emerged from Q2 and became structural by Q3, exceeding agreed thresholds.

  1. Timeliness of financial submissions was consistently met, with forecasts, quarterly financial reports and annual financial statements submitted within agreed deadlines.
  2. Value for Money monitoring was partially met. While reports were submitted on time, early reporting relied heavily on narrative placeholders and lacked clear baselines, benchmarks and cost-effectiveness metrics limiting the robustness of VfM assurance during the review period.
  3. Quality of deliverables was partially met; technical quality improved over time under URP’s new technical lead. Quality of deliverables improved but was uneven across task orders, with the annual report requiring reworking.
  4. Overall, KPI performance was assessed as between “Mostly Met” and “Partially Met”. In line with the contractual agreement, 10% fee at risk were to be withheld linked to the supplier KPIs; however, upon application of this clause it is now judged to be economically immaterial to the supplier to sufficiently persuade improvements in financial management. It is advised that in future contracts FCDO considers relatively more consequential punitive measures to ensure these are effective in incentivising supplier performance.

SUPPLIER KPIs
KPI	Weighting	Scoring
Timely provision of budget forecasts with high levels of accuracy in quarterly forecasting, efficient spending and maintenance of financial records.	30%	3 (33% of fees at risk paid)
Timely delivery of high-quality quarterly reports, programme deliverables and agreed workplans (including task orders).	60%	2 (66% of fees at risk paid)
Contribution and timely response to FCDO processes including risk reports, MREL and technical enquiries.	10%	2 (66% of fees at risk paid)

## G. MONITORING, EVIDENCE AND LEARNING

Overview of Monitoring and Evaluation
  1. FCDO maintains quarterly and annual reporting cycle whereby the programme is monitored, measured, and evaluated through detailed financial and narrative reports received from the delivery partners. This also includes quarterly tracking of output-level milestone targets against the programme logframe to consolidate partner inputs and outputs. In addition to this, site visits and stakeholder engagements were conducted throughout the year to maintain oversight of programme progress and manage risks. Though the FCDO programme team aimed to conduct quarterly project visits, due to occasional lack of municipal response and availability it remained challenging to maintain a quarterly schedule.
  2. To ensure this AR is based on validated data and evidence of programme progress, interviews with a sample group of beneficiaries were conducted. The Annual Review process was led by FCDO programme team in South Africa, with interviews with key stakeholders held by the PRO and Programme Manager, supported by the SRO. Delivery partners’ annual reports also fed into the evidence base for the Annual Review.
  3. The programme results framework was updated during the review period to increase its alignment with project-level outcomes and strengthen the link between outputs and impact. Where new delivery partners were appointed to deliver additional results, such as NEPAD and Isandla Institute, the logframe was accordingly updated to reflect their contribution.
  4. In this third year of programme delivery, extensive emphasis was placed on intermediate outcomes such as institutional change and adoption of critical programme outputs. This enabled the programme to adapt its delivery approach where necessary to achieve better value for money while maintaining its focus on the original objectives as noted in the programme business case. For example, evidence-based assessment of municipal project pipeline resulted in the decision to discontinue TA where programme would not have been able to deliver the desired outcomes. Additionally, lessons from an initial project assessment informed a refined project selection framework that focussed on 1. investment opportunities; 2. project readiness; 3. risk and 4. Impact and benefits. Each of these criteria was defined by a set of questions that will enable early project screening minimising risk of unviable projects entering the pipeline.

Beneficiary Feedback
  1. In 2025-26, FCDO conducted multiple site visits and undertook formal as well as informal engagements with government stakeholders to collect feedback on delivery partner performance and quality of programme outputs. Feedback from municipalities and national government predominantly highlighted the value of programme communication and formal governance agreed with delivery partners in engaging key government officials to ensure the development process is inclusive. Interviews with project beneficiaries like NT, City of Cape Town and Ugu Municipality highlighted the foundational role of SEAD-SA in catalysing broader reforms like Mzansi Xchange; and the importance of demand-led TA for OCL project to ensure data-led interventions have strategic buy-in and remain aligned to municipal priorities.
  2. One municipal official recommended that where donor-funded initiatives are introduced to new municipalities, drawing on existing municipal partners/beneficiaries to introduce the programme helps build credibility and confidence in the programme. This also mitigates the risk of failure due to lack of stakeholder interest. Some beneficiaries raised the risk of limited impact of upstream initiatives that enable data access without sufficient frontline capability and institutional ownership of data ecosystems. This proves the programme’s logic that both increased access to data and enhanced skills for data-driven decisions is critical for the desired programme outcomes.
  3. Feedback from the previous review resulted in greater rigour in project identification for investment and the establishment of robust governance arrangements, while developing diverse partnerships to increase programme outcome confidence. For example, support to Adopt-a-Municipality initiative through ISA and DPWI contributed to the quality of infrastructure pipeline and pace of delivery. ISA noted that the programme’s approach introduced a disciplined project preparation method that broke complex infrastructure work into manageable, structured steps.

Evidence
  1. A key piece of evidence which emerged in this year for the programme is the Cities Economic Outlook report published as part of the SEAD-SA project. The report offers fresh, data-supported insights for the whole programme that reinforce the linkages between spatial inequality and inclusive growth, which forms the basis for this programme’s Strategic Case.
  2. The report highlights weak job growth in secondary cities—only 10% over the past decade—and their continued difficulty in attracting talent and investment relative to metros, despite severe service delivery challenges in cities such as Johannesburg and Durban. While metros are likely to remain the primary destination for economic migrants, rapid population growth combined with ageing and poorly maintained infrastructure strengthens the case for targeted investment and institutional capacity‑building in secondary cities and small towns. As anchor economies in historically poorer provinces such as Mpumalanga and Limpopo, increased investment in these cities could play a decisive role in reversing regional economic decline.
  3. The analysis also provides examples of investments which align with the programme’s focus, too. This includes – 1. building on existing industrial or logistical bases; 2. supporting niche tradable sectors, rather than low‑productivity local services; 3. avoiding “new city” or artificial decentralisation strategies.

  1. Other emerging evidence is drawn from the delivery of data initiatives in municipalities where FCDO, delivery partners and beneficiaries note institutional readiness as an imperative. The evidence documented by OCL also underscores the need for a three-tiered approach to capacity building that considers municipal data maturity and leadership support. It proposes an incremental TA working through foundation, strategic advisory and intensive support in that order, to ensure systematic transformation of municipal operations.
  2. FCDO also took steps during the review period to improve partner reporting through continuous feedback on key aspects such as VfM, GEDSI and disaggregated data for KPIs. This feedback also included request for evidence of TA effectiveness, and sustainability of programme outputs. Stock-take workshops were conducted with all delivery partners at the start of 2025-26 and towards the end to consolidate lessons, refine logframes and improve programme governance.

Learning
  1. The primary mode of capturing and sharing programme lessons, new evidence, and know-how in 2025-26 was through presentation at partner-led multi-stakeholder sessions, project-level policy briefs and knowledge reports. All delivery partners are expected to embed learning activities and evidence documentation within their deliverables to ensure the programme can adapt based on contextual lessons emerging from its individual project environment. Selected learnings from 2025-26 are as follows -
- Partnering for Influence -
  - The programme addresses multiple, interlinked drivers of spatial inequality, infrastructure underinvestment and urban decay. A key learning from delivery experience is that the effectiveness of FCDO support in this context is constrained where delivery is organised through standalone, FCDO‑owned initiatives operating alongside fragmented institutional mandates and incentives within government.
  - By contrast, anchoring technical assistance within existing GoSA‑owned programmes that align with FCDO objectives, while retaining mechanisms to influence delivery standards, sequencing and reform, has proven more effective. This approach has enabled stronger institutional ownership, faster progression from scoping to implementation, and greater scope to shape practice and policy than parallel delivery arrangements.
  - Partnerships with initiatives such as Adopt‑a‑Municipality, SEAD‑SA and NT’s Just Transition in Informal Settlements demonstrate the value of working through established GoSA platforms to achieve system‑level traction, reduce delivery friction and improve VfM. This learning will inform future programme design by prioritising delivery modalities that leverage government‑led platforms where objectives, incentives and accountability are sufficiently aligned.
- Embedded Support –
  - Programme delivery has highlighted the extent to which outcomes depend on municipal capacity to absorb technical assistance and drive reform internally. Where municipalities demonstrate willingness to engage with new evidence and approaches that challenge established practices—as illustrated by the Mbombela Waste Management project—progress is contingent on sustained senior leadership buy‑in. Securing this buy‑in often requires significant internal advocacy by municipal counterparts, underpinned by both technical credibility and political acumen.
  - While programmes like URP are designed to help address these capability gaps, evidence suggests that private‑sector advisors operating through externally funded consortia may not always command sufficient institutional trust to influence entrenched practices. In such contexts, delivery effectiveness and VfM can be strengthened through the provision of embedded support—where suitably skilled advisors work alongside municipal counterparts, with institutional consent, and are positioned closer to decision‑making processes.
  - Although this model may not be appropriate across all partners or contexts, the use of targeted embedded support has emerged as a valuable complementary approach to traditional TA programmes. This learning will inform future delivery choices, particularly in high‑risk or reform‑intensive environments where institutional change depends on sustained internal leadership and ownership.

Date of last narrative financial report	31 March 2026	Date of last audited annual statement	November 2025