## Annual Review Template

Title: Monitoring, Evaluation, Research and Learning for Yemen (MERLY)
Programme Value £ (full life): £9,000,000.00		Review date: 22/10/2025
Programme Code: 301494	AMP start date: 22/10/2024	AMP end date: 10/11/2029

Summary of Programme Performance
Year	2025
Overall Output Score	B
Risk Rating	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006551.odt
DevTracker Link to results framework:	N/A: Logframe yet to be signed off

A. SUMMARY AND OVERVIEW
Description of programme
This is the first Annual Review of the Monitoring, Evaluation, Research and Learning for Yemen (MERLY) programme. At the time of drafting, MERLY had not yet transitioned to the Implementation Phase and therefore this review is relatively light touch and focuses on the Inception Phase. The next Annual Review will be brought forward to July 2026 and report on progress against the programme logframe indicators in FY 25/26.

MERLY aims to support the Yemen Office Network (YON) to deliver, monitor, and evaluate results against the Yemen Country Business Plan. MERLY’s outputs should inform strategic decisions regarding YON’s diplomatic and development activities, as well as improve accountability and Value for Money (VfM). The programme will provide independent oversight, verify results, support robust risk management, and provide YON with the required evidence to push for humanitarian system reform and influence the broader international response in Yemen.

The MERLY programme has three workstreams; (i) Independent Monitoring, (ii) Research, Analysis and Evaluative Learning, and (iii) Portfolio Learning and Engagement. The proposed approximate split of budget for the Independent Monitoring workstream outlined in the MERLY Terms of Reference (ToR) was 70%. However, in the event that budget allocations are reduced in future years, an even larger percentage of the MERLY budget should be assigned to the Independent Monitoring workstream. MERLY is YON’s key mechanism for monitoring programme risks on the ground in much of the country, to provide verification and assurance of our expenditure and results. Therefore, it is essential that MERLY’s third-party monitoring (TPM) is regular and has an extensive geographical spread, to reflect the wide coverage of YON programme operations.

MERLY is delivered by a consortium of partners, led by Tetra Tech International Development (Tetra Tech). The contract for MERLY was signed with Tetra Tech on 16 December 2024 which initiated the start of the programme’s Inception Phase. The total contract value is up to £9,000,000 over three years, with an end date of 15 December 2027, and the possibility to extend by a further two years and a budget increase of up to £6,000,000. The Inception Phase was planned to last up to 6 months, however, at the time of writing this review, in October 2025, the programme is still in Inception.

Summary supporting narrative for the overall score in this review

The MERLY programme has scored a B in this Annual Review. As explained below, the output section for this review focused on the Inception Phase, which was significantly extended.

It was agreed in the contact that progress to the Implementation Phase would be subject to the MERLY SRO’s approval of the Inception Report. At the time of drafting this Annual Review, the Inception Report had not yet been approved. There are a number of reasons for this delay, some of which were outside of Tetra Tech’s control. These factors included implementing partner reluctance to share data, inaccessibility to sites in north Yemen, delays in agreeing the annual workplan, and changes to the MERLY Team Leader.

Despite this, a number of the management and operational sections of the Inception Report were approved by the MERLY SRO ahead of the initial Inception Phase deadline. Additionally, some implementation activities were able to commence during this period, such as the design phase of the Food Security Safety Net (FSSN) programme outcome evaluation.

The FCDO team felt that the first draft of the Inception Report lacked specific details regarding Tetra Tech’s plan for TPM. FCDO is currently awaiting the revised Inception Report which should include specification of TPM approaches such as the number of sites and beneficiaries targeted, the geographic spread, and TPM visit structure and verification process. It is expected that the report will be signed off within the next four weeks and for the Implementation Phase to begin in November 2025.

Major lessons and recommendations for the year ahead

Following this Annual Review, the MERLY SRO should consider whether it’s appropriate to update the Theory of Change (ToC) to better align with the MERLY ToR and logframe. This should be discussed with the YON Development Director to determine if this constitutes a ‘material change’ and will therefore result in a Business Case Addendum being required.

Throughout the Inception Phase, implementing partners were extremely reluctant to share beneficiary data, and this reluctance increased over time as the security of their staff and offices in Yemen worsened in the north. In some cases, partners may have legitimate concerns, but where there is a blanket reluctance to share data with a new supplier, the presence of FCDO early on might have addressed this issue by compelling partners to explain why they would not share specific data that is required for TPM. However, Tetra Tech did not want to start their relationship with new implementing partners by appearing antagonistic and tried to continue engaging with them in the hope this would address data availability issues.

Tetra Tech should continue to ensure that YON is kept informed of changes to access restrictions and any issues should be raised immediately. As a minimum, risks and access restrictions should be an agenda item of each bi-weekly meeting between Tetra Tech and the MERLY SRO.

Tetra Tech recently launched the recruitment process for a new MERLY Team Leader, and a winning candidate has been identified. In the coming weeks, it should be ensured that the new Team Leader is quickly brought up to speed with MERLY operations to date, including previous issues and delays. They should also receive a thorough introduction to YON, its programmes and priorities.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The MERLY Theory of Change (ToC) as outlined in the Business Case is as follows:

The plans set out in the Business Case were further developed in the MERLY Terms of Reference (ToR). The ToR was created in consultation with Section Heads and programme teams to ensure outcomes and outputs were aligned to the evolving needs of YON, some of which might have changed since the Business Case was drafted. In the MERLY ToR, the ToC activities remained mostly the same, however these were streamlined under three workstreams rather than the four outputs noted above. The workstreams are (i) Independent Monitoring, (ii) Research, Analysis and Evaluative Learning and (iii) Portfolio Learning and Engagement, and the draft logframe outputs have been linked to these.

At the time of this Annual Review, the MERLY logframe was still in draft, but had been endorsed by the MERLY SRO. The logframe would formally be signed off alongside the approval of the Inception Report. In response to recommendations from the Project Completion Review of MERLY’s predecessor, IMEDA, the impact and outcome indicators in the draft MERLY logframe are both quantitative and qualitative in nature. To measure the qualitative indicators, Tetra Tech will conduct an annual survey of YON staff and implementing partners to test aspects such as level of usefulness of MEL services and utilisation of MERLY data and products for decision-making.

Following this Annual Review, the MERLY SRO should consider whether it’s appropriate to update the ToC to better align with the MERLY ToR and logframe. This should be discussed with the YON Development Director to determine if this constitutes a ‘material change’ and will therefore result in a Business Case Addendum being required.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Since MERLY has not yet transitioned to the Implementation Phase and the logframe is still in draft, progress against logframe indicators has not been assessed as part of this Annual Review. During the next review period, implementation should commence and progress towards milestones will be reviewed. Due to the extended Inception Phase, the Implementation Phase of the programme will be shorter than initially planned. Currently, this should not affect the likelihood of MERLY achieving its expected outcomes and impact. However, this should be reconsidered during the next Annual Review.

Planned output indicators remain relevant considering the expected outcomes and impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The MERLY programme should continue implementing activities in the coming year to support the objectives of YON and the broader humanitarian system in Yemen. MERLY provides a crucial oversight, assurance, and risk management function for YON, which is not present in Yemen. MERLY helps to improve the effectiveness, quality, and value for money of our programmes and policies, and provides additional data analyses required to inform strategic decisions about our programmes.

## C. DETAILED OUTPUT SCORING

At the time of this Annual Review, the MERLY programme was still in the Inception Phase and therefore the programme logframe was still in draft and not yet in operation. The output scoring section for this review will focus on the Inception Phase. The next Annual Review will cover progress against the programme logframe indicators in FY 25/26.

Output Title	Inception Phase
Output number:		1	Output Score:	B
Impact weighting (%):		100%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Contract signed	Contract signed	Met: MERLY contract signed on 16th December 2024
1.2 Inception Report signed off	Inception Report signed off by MERLY SRO by 16th June 2025	Not met: MERLY Inception Report still awaiting sign off in October 2025

Briefly describe the output’s activities and provide supporting narrative for the score.
The MERLY programme scores a B in this Annual Review as one of the two milestones was not met.

Following the selection of Tetra Tech as the successful supplier in October 2024, the MERLY contract was signed on 16th December 2024. It was agreed in the contact that the Inception Phase would last a maximum of 6 months and that progress to the Implementation Phase would be subject to the MERLY SRO’s approval of the Inception Report. Therefore, the planned end date of the Inception Phase was 16th June 2025.

To commence Inception activities, Tetra Tech held an initial kick-off meeting with YON to establish a common understanding of MERLY objectives and scope, and to clarify roles and communication protocols. In February 2025, Tetra Tech organised a visit to Amman to meet with YON colleagues in person for detailed deliberations regarding MERLY's proposed activities and programme priorities, in order to begin drafting the workplan for FY 25/26. This included sharing lessons learned of what worked and what didn’t under the previous programme, IMEDA. Following this, Tetra Tech held virtual meetings with YON programme implementing partners where both parties agreed on coordination mechanisms and data sharing needs for the smooth coordination of MERLY. With the intention of speeding up the Inception Report review process, in March 2025, Tetra Tech began submitting management and operational sections of the report to the MERLY SRO for comments. This included a draft logframe, Value for Money (VfM) performance indicator matrix, risk register, and General Data Protection Regulation (GDPR) and ethical policies, which were delivered to a high standard.

As the June Inception Phase deadline approached, it was clear that neither the workplan of annual deliverables nor the Inception Report were near completion. It was initially agreed that the Inception Phase should be extended by one month, after which, it was extended again until the Inception Report was approved. At the time of drafting this Annual Review, in October 2025, MERLY is still in the Inception Phase. There are various reasons for this delay, some of which were outside of Tetra Tech’s control and occurred despite strong mitigations in place.
Firstly, all implementing partners were initially extremely reluctant to share their programme data, such as beneficiary and health facility location data, with Tetra Tech. This reluctance increased over time as the security of their staff and offices in Yemen worsened in the north. The lack of such information made it difficult for Tetra Tech to propose appropriate sampling strategies for data collection and therefore they could not complete the Inception Report and TPM plan to the required standard for approval. Tetra Tech explored Data Sharing Agreements with partners, organised sessions to build confidence with partners and used YON colleagues to reiterate the importance of accessing this data. Eventually, Tetra Tech received the required data from all partners except WFP, who have stated that they will no longer share beneficiary data. Tetra Tech has since developed a workaround to ensure that WFP will still undergo TPM. In some cases, partners may have legitimate concerns, but where there is a blanket reluctance to share data with a new supplier, the presence of FCDO early on might have addressed this issue by compelling partners to explain why they would not share specific data that is required for TPM. However, Tetra Tech did not want to start their relationship with new implementing partners by appearing antagonistic and tried to continue engaging with them in the hope this would address data availability issues.
Secondly, in July 2025, Tetra Tech stated that it would not be possible to conduct in-person data collection in north Yemen through their consortium partners, who had expressed strong reservations on sending in their field staff until further notice, due to severe access restrictions and high security risks. This was a significant concern for YON programme staff, especially at this late stage of Inception, as it was essential that TPM covered as much of north Yemen as possible due to the spread of funding in the north and FCDO’s inability to travel to field sites there. The MERLY SRO contacted the Yemeni TPM firm previously responsible for data collection under IMEDA and discovered that they were still operating across all of Yemen. Tetra Tech was able to subcontract this firm to ensure full coverage of TPM under MERLY. Although successful, this process created delays in Tetra Tech confirming their TPM approach whilst it was unknown whether they would be able to access sites in the north. Going forward, Tetra Tech should ensure that YON is kept informed of changes to access restrictions and any issues should be raised immediately. As a minimum, risks and access restrictions should be an agenda item of each bi-weekly meeting between Tetra Tech and the MERLY SRO.
In addition, it has taken much longer than expected to agree the annual workplan for FY 25/26. Since the beginning of Inception, Tetra Tech held a number of sessions with YON programme teams to discuss their needs for MERLY. As Inception progressed, this list evolved slightly due to changing priorities and the lack of time remaining in the financial year for implementation, which impacted what was possible. It was also discovered that YON should expect to receive a lower budget in FY 26/27, which affected what activities should be undertaken in this year. It is expected that the workplan process for next year should be simpler, due to the full year being dedicated to implementation and because it has already been agreed that the primary focus of the workplan will be TPM, with a few additional reviews if feasible.
Finally, the deployment of the MERLY Team Leader to Amman took longer than initially expected. This was a result of delays to the Jordanian authorities reviewing the contract and visa authorisation and was challenging for Tetra Tech to mitigate as it was largely out of their control. To help facilitate the process, Tetra Tech appointed a Jordanian legal firm to liaise with the Jordanian embassy. On FCDO’s request, the Team Leader relocated to Amman on 10th June 2025 via a temporary visa until the residency was granted. However, unfortunately the visa application was denied by Jordanian authorities, and the Team Leader had to immediately leave Amman. Following this, Tetra Tech began the recruitment process for a new Team Leader. The MERLY SRO was involved in reviewing CVs and interviewing the top three candidates. The preferred candidate was agreed, and Tetra Tech has begun the contract negotiations. In the coming weeks, it should be ensured that the new Team Leader is quickly brought up to speed with MERLY operations to date, including previous issues and delays. They should also receive a thorough introduction to YON, its programmes and priorities.

To limit the gap in MEL services YON received due to the extended Inception Phase, Tetra Tech began work on some implementation activities within this period. Planning for the FSSN Outcome Evaluation begun in June 2025 and the Design Document has since been finalised after going through YON and EQUALS review. Tetra Tech have also started planning the TPM rounds for the Women and Children (W&C) programme and the WFP component of FSSN, Design Documents for both are expected soon. In addition, in April 2025, MERLY took over funding of the Yemen Economic Tracking Initiative (YETI) from the AFFY programme. This online tool is delivered by ACAPS, who are also a MERLY consortium partner.

The first draft of the MERLY Inception Report was submitted to FCDO on 15th July 2025. Following this, the MERLY Steering Committee reviewed and met to discuss comments. The Committee felt that the report lacked specific details regarding Tetra Tech’s plan for TPM, particularly considering the first year workplan for FY 25/26. Tetra Tech had proposed an inception report design where the report would summarise the design of various products and signpost the reader to the details contained in Design Documents due to the variety of work products and because TPM and evaluation designs can change over time. However, FCDO felt that more specific information regarding the plans for FY 25/26 TPM was required upfront. It was agreed that Tetra Tech would revise the Inception Report to respond to FCDO’s comments, which included specification of TPM approaches such as the number of sites and beneficiaries targeted, the geographic spread (North vs. South), and TPM visit structure and verification process.
Currently, FCDO is awaiting the revised Inception Report. It is expected that the report will be signed off within the next four weeks and for the Implementation Phase to begin in November 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the next reporting period, MERLY will be in implementation. The next Annual Review will cover the outputs in the programme logframe, which is currently drafted and awaiting sign-off.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Throughout the Inception Phase, implementing partners were extremely reluctant to share beneficiary data, and this reluctance increased over time as the security of their staff and offices in Yemen worsened in the north. In some cases, partners may have legitimate concerns, but where there is a blanket reluctance to share data with a new supplier, the presence of FCDO early on might have addressed this issue by compelling partners to explain why they would not share specific data that is required for TPM. However, Tetra Tech did not want to start their relationship with new implementing partners by appearing antagonistic and tried to continue engaging with them in the hope this would address data availability issues.

Tetra Tech should continue to ensure that YON is kept informed of changes to access restrictions and any issues should be raised immediately. As a minimum, risks and access restrictions should be an agenda item of each bi-weekly meeting between Tetra Tech and the MERLY SRO.

Tetra Tech recently launched the recruitment process for a new MERLY Team Leader, and a winning candidate has been identified. In the coming weeks, it should be ensured that the new Team Leader is quickly brought up to speed with MERLY operations to date, including previous issues and delays. They should also receive a thorough introduction to YON, its programmes and priorities.

## D: VALUE FOR MONEY

Key cost drivers and performance

As part of the Inception Report, Tetra Tech designed a VfM indicator framework which included agreed VfM indictors aligned to the 5E’s and a process to track progress against the indicators across the lifetime of the programme. Tetra Tech will maintain a comprehensive VfM Journal encompassing all agreed-upon indicators and capturing data throughout MERLY implementation. Data collection will occur at least annually, linked to the Annual Review cycle, and Tetra Tech will include a dedicated section on all VfM indicators in the Q2 and Q4 financial reports each year.

The below VfM indicators will be included in the MERLY VfM Journal and reported on in future Annual Reviews:

	Indicator	Data Source	Means of verification	Rationale	Frequency
Economy	Average value of expenses incurred for each product (disaggregated by product type)	TT data set of all approved products	TT will capture the actual expense incurred for each product produced.	To provide a cost of the expenses required for various products delivered over time and identify trends.	Annual
Efficiency	% of milestones completed within agreed time frame.	TT - Monthly financial reports, deliverable log & workplan	TT will maintain a record of the approved milestones, feedback rounds and approved delivery schedule, noting any variances.	To assess the extent to which the project has been able to deliver MEL activities, in a timely manner against approved workplan	Annual
	Cost saved from collecting TPM data in locations where more than one FCDO IP is implementing activities	TT expense receipts and invoices from various service providers	Expenses will be on actuals so can be verified	To assess extent of costs saved by collecting data in one round for multiple IPs	Annual
Effectiveness	Percentage of FCDO PTs giving a rating score of at least "high" on utilisation of MERLY data and products for decision-making.	FCDO PT online questionnaire	FCDO programme team online survey	To provide a measure of the perceived utilisation of MERLY products over time to FCDO staff; one annual round of feedback to be timed to match the FCDO Annual Review reporting cycle	Annual
	Level of usefulness of MEL services of " High" or better as reported by FCDO PTs and IPs	FCDO and IP online survey questionnaire	FCDO PT and IP online survey	To provide a measure of the perceived utility of MERLY products over time to Implementing partners, one annual round of feedback to be timed to match the FCDO Annual Review reporting cycle	Annual
Equity	% of MERLY products on which sample data is collected on women and other vulnerable groups.	TT reports	A review of every data collection activity will be done to identify coverage of vulnerable groups in the data set.	To assess the extent to which we are collecting data from traditionally underrepresented beneficiary groups	Annual
Cost Effectiveness	Comparison of costs of different work products, and their findings / recommendations which lead to action taken by IPs	Recommendation and actions taken tracker	Annual check of number of actions taken by IPs in response to MERLY findings/recommendations	This is a narrative indicator rather than a quantitative measure capturing intangible effects of MERLY work.	Annual

VfM performance compared to the original VfM proposition in the business case

As MERLY is still in the Inception Phase, no progress against the VfM indicators has been tracked thus far. A detailed review will be included in the next Annual Review once data against the indicators has been collected.

Some suggested VfM indicators were outlined in the MERLY Business Case, and these were used to develop the indicator set listed above. The Business Case also stated that the best balance of costs and benefits will be achieved through:
- Utilisation of a single agreement and competitive procurement process to drive Value for Money. The procurement process will assess the technical and commercial quality of the proposed Supplier, with rates benchmarked and assessed by FCDO PCD.
- Working directly with a flexible consortium of expert suppliers to ensure the highest quality and cohesion of programme and policy-relevant MERL.
- Maximising benefits by engaging across YON to drive improvements in the effectiveness of all YON activities.
- Minimising risks through a robust procurement, governance, and management structure (see Management Case) to ensure that the programme remains relevant to the needs of YON.
- Investing in supplier integration, to ensure linkages between MERLY and YON, internal and external partners, and stakeholders.
- Investing in the generation, dissemination and integration of learning, to drive improvements within and beyond YON. Collaboration with other FCDO programmes and departments will enable MERLY to build on and share innovation.
Tetra Tech was carefully scrutinised by FCDO Procurement in advance of being able to bid for MERLY. The evaluation criteria were designed with support from FCDO commercial experts and included questions related to fee rates. Similar MEL programmes in Syria and Afghanistan were used as reference points when developing the MERLY ToR, to incorporate best practice and lessons learned. The MERLY contract is managed by Tetra Tech as the lead supplier of a consortium which includes various international and local Yemeni organisations. The governance structure of MERLY, which includes quarterly Steering Committee meetings, encourages cross-YON integration to ensure that the programme continues to address the evolving needs and priorities of YON. Tetra Tech also maintains regular communication with programme implementing partners to ensure strong relationship and trust building, which will aid the integration of learning on the back of monitoring or capacity building activities.

Assessment of whether the programme continues to represent value for money

MERLY continues to represent value for money; assuring the YON portfolio, ensuring public funds are spent well, and supporting YON (and wider) decision-making with robust evidence. The programme provides a crucial oversight, assurance, and risk management function for YON, which is not present in Yemen. MERLY helps to improve the effectiveness, quality, and value for money of our programmes and policies, and provides additional data analyses required to inform strategic decisions about our programmes.

E: RISK

Overview of risk management

The risk appetites for the MERLY programme are broadly in alignment with the overall YON programme portfolio appetites, although not entirely the same.

Risk Category	MERLY	YON	MENA
Strategy & Context	Receptive	Eager	Eager
Policy & Programme	Receptive	Eager	Receptive
Public Service & Operations	Minimal	Cautious	Cautious
People	Cautious	Cautious	Cautious
Safeguarding	Receptive	Receptive	Cautious
Financial & Fiduciary	Cautious	Receptive	Receptive
Reputational	Receptive	Receptive	Cautious

Due to the fact that YON has no actual presence in Yemen, the MERLY programme plays a significant role in managing and mitigating risk. As the programme has yet to exit the Inception Phase and the situational context within Yemen is extremely fluid, the full assessment of risk is under constant review. The current overall risk rating for MERLY is considered “Major”.
The ongoing conflict in Yemen restricts our ability to access and monitor our programmes in Yemen, especially in the north of the country where the defacto authority are the FTO designated Houthi organisation. This issue has already become evident during the initial Inception period of MERLY as Tetra Tech had to seek out alternative TPM firms in order to gain access to collect data in the north as the pre-contracted local organisations indicated their inability to provide monitoring services at the current time.

Houthi detentions of UN staff, Israel’s targeted strikes against the sites in Sana’a and bureaucratic delays in obtaining approvals to undertake third party monitoring all contribute to an increased exposure to risk.

Risk	Mitigation	Current Rating
Operating environment becomes dangerous or untenable	Tetra Tech to maintain close contact with local partners to understand situational changes and adapt accordingly. / Ensure no international staff are active locally. / Where necessary utilise alternative methods of data collection.	Severe
TPM activities become impossible to undertake	Work with wider humanitarian response to champion continued access for TPM and humanitarian workers. / Tetra Tech to monitor and revisit their TPM strategy on a consistent and ongoing basis. / Where possible, streamline the permissions process to speed up the process of gaining access approvals and permissions.	Severe
Safeguarding – Potential harm to beneficiaries including SEAH	Ensure all partners have robust and clearly defined safeguarding policies in place and that staff are trained in safeguarding. / Review our Safeguarding strategy with the YON Social Development Advisor on a regular basis to ensure fit for purpose. / Include Safeguarding indicators in all TPM reports	Major
Safeguarding – GDPR exposure exposes beneficiaries to harm	Ensure all partners have robust and clearly defined IT data policies in place and contingency measures in place for unauthorised data access. / Monitor data access policies as standard part of TPM activities.	Major

Water scarcity, drought and flooding are the most significant risks from a climate and environment focus although the MERLY programme has no direct link through funding to any mitigation activities. MERLY will ensure that where possible, digital forms are used for data collection as opposed to paper forms and field visits are clustered to reduce travel emissions.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The initial procurement of MERLY took longer than planned due to a number of factors. MERLY was procured through the Global Evaluation and Monitoring Framework (GEMFA). At the time, there were several other new programmes being procured through the same framework and MERLY was de-prioritised due to its predecessor programme, IMEDA, still being live. FCDO’s commercial team would not run various procurements through the same framework concurrently because this would result in the same small group of suppliers being required to produce multiple bids simultaneously, potentially resulting in reduced bids for MERLY. To reduce the gap in independent monitoring services delivered for YON, the IMEDA Business Case was extended to 31 March 2025, by which time MERLY Inception had begun. The MERLY contract was signed with Tetra Tech on 16 December 2024. The total contract value is up to £9,000,000 over three years, with an end date of 15 December 2027, and the possibility to extend by a further two years and a budget increase of up to £6,000,000.

The MERLY programme is managed via one commercial contract between FCDO and the supplier, Tetra Tech. Tetra Tech then sub-contract a range of international and local Yemeni partners with specific expertise to create the MERLY consortium. The MERLY consortium currently consists of 8 organisations including Tetra Tech.

The templates for quarterly progress and financial reports were agreed between Tetra Tech and the MERLY SRO, and reporting has been received up to June 2025. Communication between the MERLY team and Tetra Tech has remained strong from the outset, through formal bi-weekly meetings and ad-hoc catch ups in between. The Tetra Tech team organised a visit to Amman in February 2025 to facilitate introductions to YON teams and their implementing partners in addition to kicking off workplan planning for FY 25/26. Following this, throughout the Inception Phase Tetra Tech have maintained regular communication with YON teams, to discuss their needs and expectations, via meetings and emails.

Since December 2024, we have paid Tetra Tech £193,633.40. £154,442.83 of that accounts for spend in FY 25/26, against a total budget of £3,000,000 for the year. Spend has been slower than initially expected because the programme has not yet transitioned to the Implementation Phase. However, it was agreed that some vital implementation activities could begin whilst inception was concluding, to limit the gap in coverage that YON has had to manage since March when IMEDA closed. Although spending has been slower than initially hoped, Tetra Tech feel that underspend in FY 25/26 is not likely, so long as the final work products in the workplan are confirmed. Key drivers of this year’s spend are the two TPM rounds for W&C, one TPM round for FSSN and the evaluation of FSSN. These products have the largest scale and associated risk but are already in motion for completion by March 2026 unless there is a drastic development in security on the ground in Yemen.

G: MONITORING, EVIDENCE AND LEARNING

YON employs a mixture of formal and ad hoc methods of monitoring the MERLY programme. The MERLY team and Tetra Tech hold bi-weekly meetings, with ad-hoc catch ups on specific issues in between. The governance structure of MERLY includes quarterly Steering Committee meetings, with attendance from Tetra Tech and each of YON’s team, which encourages cross-YON integration to ensure that the programme continues to address the evolving needs and priorities of YON. The Steering Committee reviewed the draft Inception Report and will be consulted before the final version is approved.

MERLY aims to generate robust, actionable evidence and learning that is capable of informing decision-making across programme, portfolio, and policy levels.

Tetra Tech have incorporated lesson learning from IMEDA where possible to build on the achievements of the previous supplier and try to prevent similar issues occurring. Information on what worked well and what didn’t was shared by the MERLY SRO and gathered from programme teams during Tetra Tech’s visit to Amman in February 2025.

MERLY was designed with a workstream which focused on YON portfolio learning and engagement, which proposed to include activities such as portfolio learning reviews and influencing assessments. In the event of budget reductions, this workstream would be de-prioritised. However, learning should be integrated into all MERLY activities. For example, Tetra Tech will maintain a recommendations tracker to record and monitor partner progress against TPM recommendations.

Date of last narrative financial report	July 2025	Date of last audited annual statement	30th September 2024