## UK PACT Annual Review 2024-25

Title: UK Partnering for Accelerated Climate Transitions (UK PACT)
Programme Value £ (full life): £280m		Review date: November - December 2025
Programme Code : 301495	AMP start date: 1/4/22	AMP end date: 31/3/27

Summary of Programme Performance
Year	FY18-19	FY19-20	FY20-21	FY21-22	FY22-23	FY23-24	FY24-25
Overall Output Score	N/A	A	A+	A	A	A	A+
Risk Rating	Minor / Moderate	Moderate	Major	Major	Major	Major	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005236.odt
Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-301495/documents

A. SUMMARY AND OVERVIEW

Description of programme
UK Partnering for Accelerated Climate Transitions (UK PACT) is a climate mitigation technical assistance (TA) programme which supports partner countries with high mitigation potential to increase their climate ambitions and implement that ambition more rapidly, more effectively and more equitably.

It responds to the critical global need for increased capability to implement and raise the ambition of Nationally Determined Contributions (NDCs) in Official Development Assistance (ODA) eligible countries with high emissions. It leverages the UK’s position as a global leader in tackling climate change to build strong partnerships with priority governments, share expertise and build capacity, and deliver transformational assistance.

Working in partnership with beneficiary governments, UK PACT provides TA support to the following climate mitigation areas: climate governance and policy; energy transition and efficiency; climate finance; sustainable agriculture, nature and forests; and urban mobility and resilient cities.

The programme is managed by the Foreign Commonwealth and Development Office (FCDO) and jointly governed and funded with the Department for Energy Security and Net Zero (DESNZ). It is an ODA funded programme which contributes towards the UK’s £11.6bn International Climate Finance (ICF) commitment.

FY 24-25 marked the first year for UK PACT under a new delivery model and single delivery partner (DP) replacing the previous multi-partner structure. This consolidation was designed to enable greater coherence across the global portfolio, alongside a significant scale-up in operations.

The Annual Review was undertaken in November - December 2025 and covers the period of FY 24-25 although lessons are drawn from programme experience until December 2025. The team interviewed UK PACT Fund Managers, and visited Indonesia to interview Embassy staff, government counterparts, the delivery partner and implementing partners (IPs).

Summary supporting narrative for the overall score in this review

FY 24-25 marked a pivotal year for UK PACT, with the successful mobilisation of a new delivery model under a single delivery partner consortium, led by Palladium in partnership with Arup and Social Development Direct (SDD), replacing the previous multi-partner structure. This consolidation enabled greater coherence and agility across the global portfolio, alongside a significant scale-up in operations: the decision was taken to scale-up in the Philippines, Malaysia and Peru, alongside a significant scale-up of the whole portfolio with overall spending increasing by 73.5% from the previous year’s spend of £26.4m. Final spending was £45,783,850 against an initial budget set at the beginning of the year of £56.1m. While performance was strong overall, challenges in mobilisation (particularly in new countries for the delivery partner), and financial management, required targeted interventions and close collaboration between FCDO and the delivery partner to maintain delivery performance.

For this reporting period, UK PACT launched a new Monitoring, Evaluation and Learning (MEL) framework to enhance accountability, evidence of impact, and programme-wide learning. The approach moved away from a focus on counting outputs to assessing how interventions drive transformational change. Key changes included a revised theory of change and logframe, sector-specific indicators, and the implementation of a case-based results reporting approach. Output wording and indicators were revised to more explicitly focus on recording the direct uptake result of programme activities, outcome indicators are now more closely aligned with ICF indicators with new outcome indicators to measure sectoral performance, and a log frame using the standard FCDO template was implemented. A nested approach for fund and sector-level theories of change was developed, alongside enhanced quarterly and annual reporting, integration of gender equality, disability and social inclusion (GEDSI), and plans for a new Information Management System to streamline data collection. Regional MEL Manager roles were created for quality assurance, and Palladium continued quarterly and annual reporting, including the first comprehensive KPI 15 report for all funds. Internal audit findings prompted improvements such as baseline data, updated templates, and post-project outcome tracking.

The AR score has improved this year from an A to an A+. The programme achieved strong results against its output indicators, meeting or exceeding all output indicator targets where they were present for FY 24-25 except for one indicator with Output 3.1. The results reported for the year was a notable step-change for the programme, with a significant scale-up in outputs reported as well as intermediate outcomes and outcomes achieved. This reflects improved performance as well as results of interventions from earlier years coming to fruition. Over 30,000 individuals and 531 organisations were supported with technical assistance, and UK PACT contributed to 34 new or enhanced climate policies and tools. Projects reported direct emissions reductions of 22,310 tonnes of carbon dioxide equivalent (tCO₂e) and indirect reductions of 415,586 tCO₂e, with a projected lifetime impact exceeding 4.4 million tCO₂e. These achievements reflect the programme’s growing influence in shaping policy, mobilising finance, and strengthening institutional capacity across priority sectors.

Despite these successes, the programme had challenges in some areas. Delays in mobilisation and operational challenges in Asia and Nigeria impacted delivery timelines, and financial forecasting and reporting required corrective action. The DP responded constructively, implementing improvement measures and meeting KPI “Good” ratings in 17 of 19 instances by year-end. The overall score of this review reflects strong delivery of results and progress and resilience in addressing challenges, though the review recognises the need for continued focus on MEL implementation, communicating impact and financial management.

The assessment of performance in this review was supported by interviews with and feedback from UK Civil Servants (UK PACT team members, Embassy staff, DESNZ colleagues) and DP staff whose interviews and feedback supported the assessment of the programme as a high performing centrally managed programme, that has a high level of integration into HMG Post’s strategies, with a strong reputation for quality support with UK PACT’s partner countries and recognition of the flexible offer and work with local partners and networks. Strong feedback on the quality of UK PACT programme support and delivery approach was relayed by all Indonesian government counterparts interviewed, with co-designing of projects, flexibility of support and strength of implementing partners all noted.

Major lessons and recommendations for the year ahead

The lessons and recommendations of this Annual Review primarily focus on overall portfolio and outcome/impact performance, reflecting the importance of maintaining high output delivery whilst strengthening outcome performance. The recommendations for outputs are included under each output section.

No.	Lesson	Recommendation
1	Transformational change & impact / This AR illustrates the programme has improved results at the impact and outcome levels, with year-on-year improvements for the ICF transformational change KPI. / Nevertheless, the programme faces challenges common to ODA TA programmes with achieving transformational change. Achieving such change requires sharp focus on activities that follow strong theories of change at each level of the programme, and these results often take time to materialise and can fall beyond the duration of UK PACT projects; programme activities to strengthen this approach took place in the AR period and have been implemented since then, but further action can be taken to improve transformational impact going forward. / Related to this, partner governments highlight the need to combine TA with downstream investment (including capital expenditure) to maximise impact. This financial assistance is beyond the scope of the programme, so strategic coherence and co-ordination with other programmes and downstream investment is key. Targeting ODA to deliver transformational change and linking TA to investment are two ICF 4 principles.	UK PACT Fund Leads (FCDO and DP) should continue to ensure the new fund and sector level theories of change are used to inform the fund strategic direction and selection of interventions in country, including throughout implementation planning and strategic spend decisions for FY 26-27. / The DP (as part of broader learning on delivering effective Technical Assistance) should develop guidance/recommendations on how the programme can better support transformational change, with the aim of improving the programme’s performance against the ICF KPI. This should include: / a definition of transformational change in the UK PACT context / how activities can be planned, projects selected, and follow-up undertaken to take account of the multi-year timeframe required to achieve transformational change. This will account for and inform the programme’s learning approach. / The role of teams at post in assessing transformational potential and delivering transformational change. / UK PACT should look for increased partnerships with other HMG programmes that are downstream of UK PACT TA to maximise opportunities to scale-up and mobilise finance to achieve transformational change. The programme should pilot a partnership with another HMG programme that supports downstream investment, aiming to develop a pilot partnership by Q2 in FY 26-27 and if successful consider introducing other partnerships over FY 26-27.
2	Sectoral technical expertise and UK policy coordination / There are different ways policy and sectoral technical expertise are applied across the project and programme cycle, and the introduction of thematic leads over the last year has strengthened this approach. However, there are opportunities to integrate this further, particularly at the strategy development and learning stages of the programme. But, this requires time and resources from both the UKPACT team and those with the expertise.	The Programme Management Team and the DP should conduct a review into technical and policy expertise in UK PACT (UK Government and DP), identifying opportunities to strengthen integration. The review should consider: / What type of technical expertise is currently available for the programme and how it is accessed, / How it is used during key points of the fund cycle (development of fund strategies and implementation plans, input and oversight of calls for proposals, project selection and design, and oversight of project deliverables and portfolio strategies, results reporting and learning), / How the short-term technical assistance (STTA) function of the contract is used, / How the programme can better integrate technical and policy expertise on offer from within HMG to inform programme activities and shape UK policy (UK PACT thematic leads, FCDO climate cadres, technical advisors at post and UK PACT public sector partnerships). This review should be concluded by the end of Q1 FY 26-27 / Fund Leads and Regional Leads should ensure that job descriptions and goals for FY 26-27 both in HQ and posts include any required technical elements or areas of expertise. A Regional Lead should oversee this across the programme to conclude by the end of Q1 26-27.
3	Cross programme learning and coherence / Considerable improvements were made to the programme’s MEL approach in this AR year, which have continued since then. / As part of this there has been good progress on learning activities, including thematic reviews, country and portfolio learning events, and work from the GEDSI hub. Nevertheless, cross-fund and intra-regional learning is underutilised, limiting knowledge exchange across the programme and beyond, and weakening portfolio coherence, and there are some missed opportunities for synergies particularly between multi-region funds and country funds.	The delivery partner should finalise the refresh of the learning agenda in Q4 FY 25-26. This should include how lessons learned from the UK PACT programme can best be shared across countries, regions, sectors, at the programme level, and to broader HMG and international audiences. The agenda should include analysis of successes and failures in UK PACT sectors and sub-sectors. / FCDO Regional Leads should consider (by end of Q1 FY 26-27) whether there are opportunities for learning between the two regional funds and countries within these regions and, if so, work with the DP to develop these opportunities into specific learning.
4	Programme management / The UK PACT programme has now completed a full year under the new contract and delivery model, and the programme has scaled up substantially. Though new processes and systems have been established and are working effectively, there is room for improvement and further strengthening including in areas identified by internal audit such as results and risk management.	The Programme Management Team should work with the DP to strengthen financial reporting, including through revised KPIs. These should be agreed by Q4 25-26. / The Programme Management Team and the DP should by the end of Q4 25-26 agree a training plan for FY 26-27 including UK PACT staff at post and covering aid diversion, safeguarding, risk management, and other programme management areas depending on needs. / The Programme Management Team and the DP should agree a KPI linked directly to delivery of outputs and intermediate outcomes. This should be agreed by Q4 FY 25-26. / The Programme Management Team should conclude delivery of actions taken in response to recommendations made by FCDO Internal Audit (e.g. on results and risk management), and confirm this in writing to the Audit team.
5	Communications / UK PACT has an agreed Comms Strategy, but the requirements have shifted. Host market comms was previously prioritised resulting in the strong recognition of UK PACT and its work in many countries. Going forward it will be important to give equal weight to demonstrating programme results and sharing lessons within the programme, across HMG and to international audiences.	The DP should propose an addendum to/update to the Comms Strategy reflecting the latest requirements, and specific comms plans for each fund. This should be agreed by the programme before the start of FY 26-27 and communicated to all teams. / The Programme Management Team and the DP should agree a comms KPI to ensure high quality compelling communications products that clearly demonstrate UK PACT’s results. This should be agreed by Q4 25-26.
6	Integration with a new CNE Centre of Expertise (CoE) / FCDO has committed to establish a new Climate, Nature and Energy (CNE) CoE to provide responsive, demand-driven TA to priority countries in FY 26-27. As the government’s flagship climate mitigation TA programme, UK PACT has considerable evidence and experience that can help shape an effective model. It is anticipated that UK PACT will be part of the new CoE and may be required to adapt to deliver on the CoE vision and objectives.	The SRO, regional team leaders and Programme Management Team should contribute to the design of the new CoE, sharing experience and lessons from UK PACT. / In FY 26-27 the same roles should ensure the smooth transition of UK PACT to fit within the new CoE, adjusting the programme, extended business case and contract as required.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The UK PACT monitoring, evaluation and learning (MEL) strategy and framework was significantly updated in FY 24-25. Following the move to a single delivery partner structure, the DP produced a new MEL framework to replace the framework under the old delivery model. The rapid scaling of the portfolio had challenged the ability of the old MEL framework to direct, track, measure and communicate project and impact pathways successfully. The MEL framework was updated with a new MEL strategy and was adapted to cover a wider range of results and better targeted learning.

As part of the MEL strategy refresh, the programme theory of change (ToC) was reviewed and revised to strengthen and improve it for a scaled-up programme. The new MEL strategy and theory of change were developed and agreed during the FY 24-25. The new strategy identifies how fund and sector level ToCs can be linked to the overarching programme ToC and identifies learning themes. One of the main objectives of the new programme ToC is to capture pathways for transformational change, including promoting the scaling and replication of successful policies and best practices. The ToC also seeks to ensure alignment with UK PACT’s ambition to act as a catalytic programme, building sustainable partnerships that raise climate ambition and accelerate transitions in a fair and equitable way. Development of fund and sector level ToCs was agreed as part of the new MEL strategy in October 2024 and was completed in the following reporting year in FY 25-26, with substantive drafts of fund ToCs in place for 9 of 14 funds by the end of FY 24-25.

The Theory of Change in place from October 2024 was[1]:
[1] See previous Annual Review for the old ToC.

As well as the new programme ToC and nested fund ToCs, the new MEL updates include changes the UK PACT logframe. The logframe was updated to clarify causal pathways from outputs to impact; to update output indicators to improve assessment of TA uptake; align indicators to ICF KPIs; and include sector-specific indicators for outcomes such as finance mobilised, clean energy capacity installed, improved land management, and sustainable mobility. The revised logframe also includes baseline data, annual milestones and end of programme targets for all impact, outcome and output indicators for the programme. The inclusion of baselines, milestones and targets in the programme logframe addresses a key recommendation by the FCDO internal audit of the programme that took place in the reporting year. The revised ToCs at every level codify pathways to transformational change (Lesson 1).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme has demonstrated strong progress, and impact and outcomes results were a notable improvement on previous years. This was the first year the programme assessed sectoral outcomes, and the programme delivered good results against all new outcome indicators, noting that there were not quantitative milestones for the period for new outcome indicators so performance can only be assessed against end of programme targets. This programme has indicators at the impact (2 indicators); intermediate outcome (2); and outcome (5) level.

Over FY 24-25, the programme has demonstrated strong progress and a notable scale-up in achieved results across core outcomes and intermediate outcomes, particularly in countries with established funds and mature portfolios. In terms of impact, the programme has delivered strong results for impact indicator 1 on emissions reductions, and for impact indicator 2 on transformational change (TA KPI 15) the programme reported an improved score compared to the previous year.

For the programme’s intermediate outcome: “Adoption of enhanced models and capabilities that deliver more ambitious, sustained and inclusive action on emissions reduction”, the results reported show the programme making good progress. For the intermediate outcome indicator on climate policy and planning, the programme has reported a cumulative 72 new or enhanced policies, practices, tools or technologies supported - a notably higher number than the target milestone of 40 cumulative achieved by 2025.

The programme has delivered good results against all five new outcome indicators and good progress towards 2027 programme targets, and there were notable results delivered in the key outcomes of mobilising climate finance and influencing policy – key enablers of transformational change. However the outcome indicators did not have quantitative milestones for 2025 as there was not enough available data to set these in the new logframe developed in 2024. The five outcome indicators, with summaries of results achieved this year are:

- Outcome Indicator 1 Finance mobilised: To date, using a revised methodology from FY 24-25 UK PACT technical assistance has contributed to the mobilisation of £3.79 billion of investment for climate action, against a programme target of £1 billion by 2027. £13,243,325 of finance mobilised in support of climate action was reported as being achieved in FY 24-25.
- Outcome Indicator 2 Installed capacity of clean energy: In the reporting period, UK PACT technical assistance is reported to have contributed to the installation of cumulative 4.98 MW of new clean energy generating capacity. An additional 23.44 MW of new installed capacity has been supported indirectly through investment mobilisation in Colombia.[2]
  [2] There were not programme targets for Outcome Indicators 2 and 3 set at the time of this review as the indicators are new and there was not enough available data to set targets. This will be implemented in future years.
- Outcome Indicator 3: Number of people with improved access to clean energy: In the reporting period, UK PACT has supported improved access to clean energy and clean cooking technologies for over 4,200 individuals and one health facility – the Makueni County Referral Hospital in Kenya.
- Outcome Indicator 4: Area of land under improved sustainable land use management, including nature and forests: In the reporting period, UK PACT technical assistance contributed to the introduction or strengthening of sustainable land use management practices over an area of 37,556ha. An additional 375,389ha of land has been supported indirectly through investment mobilisation in Peru.

Outcome Indicator 5: Number and description of cases of improved access to clean and sustainable mobility solutions and more resilient cities: This indicator is measured under a case study indicator. In FY 24-25, one case was reported of where UK PACT has delivered this change, focused on the results of the ‘Future Cities’ portfolio in Indonesia.
Examples of progress towards outcomes include:

- Enhanced skills and capacity driving climate action:
  In Kenya, UK PACT supported the development of Makueni County’s first comprehensive Energy Plan and Investment Prospectus, enabling the installation of a 0.21 MW solar PV system at the county referral hospital. This intervention is projected to save KSh 7 million annually, reinvested into healthcare, and catalyse a £430 million clean energy investment pipeline.
- Policy and regulatory reform accelerating emissions reductions:
  In Brazil, UK PACT supported the launch of the National Bioeconomy Strategy, embedding climate resilience and biodiversity into Brazil’s development agenda. Operationalisation efforts are underway, including the development of Brazil’s first National Bioeconomy and Sociobioeconomy Plans.
- Mobilising green finance and investment:
  Across the portfolio, UK PACT contributed to the mobilisation of £13.2 million in FY 24-25, adding to a cumulative total of £3.79 billion. This includes support for Peru’s first sustainable sovereign bond and forest concession financing in Brazil alongside innovative mechanisms such as carbon taxes and green bonds in Mexico and Colombia.

The programme has reported strong results against its impact targets in FY 24-25, and the programme’s impact on climate mitigation is increasingly visible. For Impact Indicator 1, volume of emissions avoided/reductions supported: Projects to date have reported a cumulative 181,126 tCO ₂e emissions avoided or reduced. The same projects have reported a projected lifetime impact of 4,422,056 tCO ₂e. An additional 983,917 tCO ₂e reductions has been indirectly supported by the programme through the mobilisation of investments into green projects. This is a notable amount higher than the current programme target of 1 million tCO ₂e, and the real emissions reduction impact of the programme is likely to be far higher and early policy results, if fully implemented have the potential to deliver even high levels of impact.

For impact indicator 2 on transformational change (aligned with ICF KPI 15) the programme reported a score of “4 - Partial evidence suggesting transformational change is likely”, this was improvement on the 3.5 score achieved the previous year. This is a step in the right direction, and the programme would expect to see further evidence of transformational change in future years as further evidence of outcomes and impacts are realised. Given the importance of transformational change to climate change TA and the UK PACT programme, this is still a key area of planned improvements to the programme, and this is reflected in ‘Lesson 1’ in this review’s major lessons and recommendations above. The ICF KPI 15 assessment for UK PACT is an average score of an assessment of the six mature UK PACT Funds that had been in delivery for a sufficient amount of time to assess. In future reporting periods the programme will assess how this should be expanded to further funds, and it is important that the assessment of transformational change reflects all of the global programme’s work.

Performance at the outcome and impact level remains lower in newer funds and regions. Mobilisation delays in Asia (India, Thailand, Vietnam) and some operational challenges in Nigeria slowed progress towards intermediate outcomes. The complexity of attributing emissions reductions to enabling actions, combined with the long causal chain from outputs to impact, means that transformational change will take time to materialise. Reported emissions reductions for FY 24-25 (22,310 tCO₂e direct; 415,586 tCO₂e indirect) are strong relative to the programme’s current target of 1,000,000 tCO₂e and projected lifetime impacts exceed 4.4 million tonnes, reflecting that the milestones and targets should be updated to reflect current projections and ambitions.

For the next reporting period, actions for the programme to take forward on several areas are planned, including actions as part of our response the FCDO internal audit of the programme. On MEL, milestones and targets will be updated to reflect current projections and a realistic ambition and the programme will initiate the procurement of an independent evaluation partner in FY 25-26 to provide objective assessments and learning. Updated guidance and planning for the tracking of outcomes post-project closure has been developed and will be socialised with programme funded teams at post in FY 25-26. This Annual Review recommendations will make further improvements to outcome delivery, particularly those related to lessons one, two and three.

There will be several further actions taken forward by the DP. There will be a rollout of the grants and results information management system (IMS), and fund-level indicators will be rolled out by mid-FY 25-26 to improve evidence of outcome-level progress. To enhance financial and risk management, quarterly financial review workshops and regional risk training will be implemented to address persistent forecasting and reporting issues. The use of case studies and digital channels will be expanded to showcase results and strengthen stakeholder engagement, ensuring visibility of UK PACT’s contribution to transformational change. The DP will also implement targeted support for underperforming regions, deploying surge capacity and tailored technical assistance to funds in Asia and Nigeria to stabilise delivery and improve performance.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the evidence, the programme should continue on its own merits and in the context of the wider ECD ICF portfolio. UK PACT remains the UK’s flagship climate mitigation technical assistance and capacity building programme. It is well aligned with FCDO priorities and HMG’s modernised approach to development, and plans for a new CNE Centre of Expertise.

The programme’s results are strong. The programme’s cumulative finance mobilised (£3.79bn vs a £1bn 2027 target), strong progress across all five outcome indicators (notably policy influence, clean energy access, land management, and mobility), and emissions reductions that already exceed the current target (181,126 tCO₂e direct reported to date, 4.42m tCO₂e lifetime projections, plus 983,917 tCO₂e indirectly supported) demonstrate clear value for money and growing transformational potential (ICF “Transformational Change” KPI 15 score improved from 3.5 to 4.0).

Furthermore, the programme team have overseen marked improvements in programme delivery, including good progress on the recommendations from last year’s AR (see Annex for a full assessment).

## C. DETAILED OUTPUT SCORING

Output Title	Skills enhanced and capabilities built to improve climate action
Output number:		1	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	Yes (30%)

Indicator(s) *[3]	Milestone(s) for this review	Progress
1.1) # and description of cases of skills and knowledge enhanced to deliver improved climate action / 1.2) Number of individuals and organisations / supported by UK PACT / (ICF TA KPI 2)	5 cases; and identification of cases for 25-26 reporting.[4] / 66 unique project outputs planned in this category for FY 24-25 / 1.2) A modelled estimate[5] of 20,000 individuals and 50 organisations were predicted to be supported for FY 24-25 based on previous years’ data	10 Cases / 76 Unique project outputs were delivered under this category / 30,280 Individuals, 531 Organisations
[3] To note on the use of case studies in logframe indicators: UK PACT now uses a case study-based reporting methodology in the new MEL Strategy, where case studies are recorded as a core reporting tool alongside the total number of outputs produced under each indicator. Case studies are designed to capture qualitative evidence of change, explain why and how results occurred, and provide actionable learning for replication and scaling. PACT projects are expected to produce at least one case study (which may cover multiple results) during implementation.
[4] Evidence within selected case studies demonstrates progress on capacity and capability building across the programme.
[5] The programme employed a modelled estimate rather than a hard milestone for this indicator, as there were concerns that a hard milestone in this output could create perverse incentives to focus support towards large numbers of individuals, rather than transformational change and emissions reductions impacts.

This output, ‘Skills enhanced and capacities built to improve climate action’ aims to address low capacity and insufficient skills and knowledge to design and implement relevant policies and practices, which in turn drives increased ambition and accelerated climate action. Ten cases/examples spanning six funds and all five priority sectors were recorded, and this was double the amount planned for the milestone target for 24-25. These provided strong evidence of strengthened skills and capacities among a diverse range of stakeholders and showed the scaling up and increased activities under this output this year. The cases detail how over 5,000 individuals, including policymakers, financial professionals, farmers, and community leaders, benefited from targeted capacity-building initiatives.

In FY 24-25, 30,280 individuals and 531 organisations were supported with UK PACT technical assistance, and 76 unique project outputs were delivered under this category. This was over the 66 unique project outputs planned, and above the modelled estimate of 20,000 individuals and 50 organisations predicted to receive support in FY 24-25. For this indicator, the programme used a modelled estimate based on previous years’ data rather than a hard milestone, as there were concerns that a hard milestone for this output could create perverse incentives for support to be directed towards targeting reaching a high number of individuals, rather than focusing on sustainable skills enhanced and capabilities built.

The case studies illustrate how UK PACT projects can work to enhance skills and capacity to deliver climate action:

In India, the programme delivered a green finance capacity building project to strengthen climate risk assessment in India’s banking sector. The support delivered capacity building training equipped 576 finance professionals – 34% of whom were women – from 13 Indian financial institutions with the knowledge and tools to integrate climate-related financial risks into their decision-making processes. Through tailored training modules, workshops, and technical assistance, the project enhanced participants’ understanding of ESG and climate risk frameworks, enabling them to influence institutional practices and support the Reserve Bank of India’s progress toward climate-responsive regulation.

In Mexico, the programme delivered capacity building to advance State-Level climate legislation, supporting public officials across 14 Mexican states. Support was delivered through targeted workshops, participatory legislative drafting, and technical assistance, enhancing their ability to design and implement inclusive climate policies. This support helped advance climate legislation in eight Mexican states and delivered five legal reform proposals, as well as catalysing the creation of the Intersecretarial Commission on Climate Change in Nayarit.

In Indonesia, the programme supported the Indonesia federal government and local authorities to improve energy efficiency in public owned buildings. The programme delivered training and certification of over 100 energy professionals to support the adoption of PP 33/2023, which formalized the role of Energy Saving Superintendents, and provision of capacity building for 378 government staff from 276 institutions across 23 provinces. This support led to the development and adoption of national guidebooks by the Ministry of Energy and Mineral Resources to inform ongoing and future training and led to the development of a community of practice with knowledge sharing and support shared between of energy professionals who have undertaken the training.

#### Changes to this output during the past year and planned changes as a result of this review
#### This output was updated as part of the MEL framework refresh finalised in October 2024. It was changed from three output indicators (counterpart satisfaction rating) to two new output indicators. Indicator 1.1 utilises a case-based reporting (CBR) approach, which was a method adopted as part of the MEL framework refresh. Each UK PACT project is expected to produce at least one case study (which may cover multiple results) during implementation.

No substantial changes to this output are planned, however the programme will update its milestones for future years and end of programme target to more accurately reflect the ambition of the programme.

Progress on recommendations from the previous annual review
Last year’s Annual Review included the recommendation under this output that: “consideration should be given at design stage for how training might be scaled up and/or lessons shared around a defined outcome objective.” This recommendation links to the major recommendation 2.3 from last year’s AR: to design follow up into projects from the start to maximise learning and scale-up of interventions and improve progress against outcomes. New project closure requirements have been built into project contracts to record lessons and opportunities to scale up training. The DP has also implemented a structured project closure process that captures learning and recommendations for follow on work that can secure and scale up project impact. This includes a close out meeting between the IP, the DP, FCDO and post to debrief on results, challenges and future opportunities.

Lessons learned this year and recommendations for the year ahead
The Annual Review field visit found that projects with more activities aligned to this output achieved stronger results and greater scale of impact. Success was highest where partner government counterparts were deeply engaged in the design and delivery of capacity-building activities, a good example of this was the energy efficiency work in Indonesia. In this instance, the federal government was heavily engaged in the project, illustrating strong leadership and coordination. The “training of trainers” model helped create significant reach across local authorities.

For activities under Output 1, Fund Teams should ensure there is a strong partner or interlocuter in the counterpart government, that activities are clearly linked to counterpart government policies, and that project plans contain clear counterpart-led engagement plans to support successful project delivery and uptake of outcomes.

Output Title	Innovative models, including policy, accelerated and/or piloted to deliver improved climate action
Output number:		2	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	Yes (25%)

Indicator(s)	Milestone(s) for this review	Progress
2.1) # and description of cases where new tools, technologies, or best practices to deliver improved climate action have been supported and/or piloted / 2.2) # and description of cases of policy processes that have been informed or supported by recommendations produced through UK PACT	2.1) 5 cases / 2.2) 5 cases / Evidence within selected case studies demonstrates progress on the development and roll out of innovations to deliver improved climate mitigation results across the programme. / 67 unique project outputs planned in this category for FY 24-25, covering both 2.1 and 2.2	2.1) 9 Cases / 2.2) 7 Cases / 84 unique project outputs were delivered under this category in FY 24-25

By supporting the piloting, acceleration and scaling of innovative tools, policy approaches and business and financial models, the programme is supporting counterparts by helping equip policymakers to design and implement more effective, scalable, and adaptive strategies that can lead to reduced GHG emissions and deliver on NDC commitments.

Nine cases reported across five funds in the energy, nature and mobility sectors of new tools, technologies, or best practices to deliver improved climate action being supported and/or piloted (indicator 2.1), exceeding the number of case studies targeted (9 v 5).

Seven cases reported across six funds in the climate policy, green finance, nature and mobility sectors of policy processes having been informed or supported by recommendations produced through UK PACT, (indicator 2.2), again exceeding the number originally targeted (7 compared to 5).

The twelve projects and portfolios assessed through these case studies demonstrate how UK PACT-supported interventions have piloted innovative tools, technologies, and policy approaches while contributing meaningfully to policy and regulatory reform. Some examples are included here:

In Indonesia, in the low carbon transport sector, the programme introduced a range of innovations, digital planning tools, and inclusive urban mobility pilots, while aligning with national strategies and catalysing regulatory engagement. This included the development of the Road Transport Decarbonisation Pathways (RTDP) Tool, which enables dynamic emissions analysis and policy planning. The tool was well received by Indonesian government representatives and has enhanced expertise in emissions estimation and mitigation assessment. This tool is now being adapted for a UK PACT project in Thailand. Low carbon transport projects also made significant contributions to policy and regulatory advances, including supporting the drafting of Jakarta’s Transport Demand Management regulation and Low Emission Zone guidelines, and the integration of transit-oriented development recommendations into regional planning.

In Kenya, through the eCAP programme, UK PACT played a pivotal role in supporting the Government of Kenya to develop two landmark national strategies: the National Cooking Transition Strategy (KNCTS) and the Kenya National eCooking Strategy (KNeCS). This achievement represents a significant step forward in shaping the country’s clean cooking transition. Alongside this, the programme delivered targeted interventions and pilots focused on supply chain development, carbon finance, utility-enabled and innovative consumer financing, and public awareness. These efforts not only informed the strategies but also demonstrated scalable financing and awareness models, providing a strong evidence base for future implementation and clear recommendations for continued research and action.

In Colombia, the programme supported the transformation of cacao cultivation in the Colombian Amazon. UK PACT supported the piloting of a comprehensive, deforestation-free cacao business model across 10 associations, integrating agroforestry, traceability, biodiversity monitoring, and market positioning strategies. The project also supported the development of policy recommendations in collaboration with the Departmental Cocoa Committees and UPRA, leading to the inclusion of nine cacao-related initiatives in the Development Plans of Caquetá, Guaviare, and Putumayo.

#### Changes to this output during the past year and planned changes as a result of this review
For 2024-25, this output has also been updated tracking ‘Innovative models, including policy, accelerated and/or piloted to deliver improved climate action’ instead of ‘Recommendations Proposed for relevant policies, legislation, and regulations on climate change mitigation’. This change was designed to more explicitly focus on the direct result of programme activities, rather than summarising the number of activities undertaken.
Progress on recommendations from the previous annual review
Last year’s annual review has two recommendations under this output. Firstly, it recommended that “Projects within a fund’s portfolio [should] focus on a narrower set of outcome objectives, with projects building on each other to facilitate greater impact and transformational change (linked to major recommendation 2.1 and 2.2). As detailed in the annex, the programme has made strong progress against this recommendation. With only two exceptions, all UK PACT Funds now only operate in a maximum of three sectors, leading to more focused and coherent portfolios in funds. Funds have made strong progress to ‘cluster’ delivery, for example in Malaysia and the Philippines, where clustered delivery approaches were integrated in to Fund Strategy and Sector Case development from the outset, and with collaborative engagement from Post, FCDO and the delivery partner, sets of clustered projects were identified to meet counterpart priorities with the ultimate aim to optimise leveraging further climate finance.

Last year’s Annual Review also recommended that PACT officers at Post should ensure they continue to link up with other UK ICF initiatives such as the Climate Finance Accelerator and the Just Energy Transition Partnerships. UK PACT Funds and officers at Post have generally made good progress against this recommendation. There is very strong join-up between UK PACT and Just Energy Transition Partnerships in countries that have both programmes - South Africa, Indonesia and Vietnam - where the teams work closely together. Programme funded staff at Post have strong relationships with other HMG climate programming, for example in Indonesia where the UK PACT programme is a key part of the MELAJU initiative led by Post, which brings together the HMG climate and sustainable infrastructure programme ‘offer’ into a single coherent package of support.

Lessons learned this year and recommendations for the year ahead
Piloting innovative tools and policy models is most effective when paired with strong enabling conditions—such as policy interaction, financing mechanisms, and inclusive stakeholder participation. Case from FY 24-25 show that technical innovation alone does not guarantee uptake. Success depended on early integration with policy processes, capacity-building for implementing institutions, and alignment with market incentives. Where these elements were missing or delayed, scaling and replication were constrained despite promising technical results. UK PACT Funds should consider whether an assessment of enabling conditions is needed in project plans and grant agreements and prioritise providing support linked to this output as part of a wider package of support that looks at other barriers to policy adoption.

A further lesson was identified from the Indonesia low carbon transport support, where the Road Transport Decarbonisation Pathways (RTDP) Tool developed is now being adapted for use in a project in Thailand, showing the value of for cross-fund learning and where sharing experiences of successful delivery can support impact in other areas of the programme. Lessons and recommendations on learning are elaborated in more detail in the major lessons and recommendations section in this report.

Output Title	Knowledge, evidence and learning generated and shared, and policies and practices informed
Output number:		3	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
3.1) # and description of cases of policy processes or practices linked to climate mitigation that have been supported or informed by UK PACT research, knowledge and evidence generation / 3.2) # and description of cross-project, cross-fund or cross-programme knowledge and communication products generated and disseminated by the programme	3.1) 5 cases; and identification of cases for FY 25-26 reporting. / Evidence within selected case studies demonstrates how new research, knowledge or evidence developed under the programme will be or is being applied to inform climate action. / 145 unique project outputs planned in this category for FY 24-25 / 3.2) 4 products	3.1) 6 cases / A total of 131 unique project outputs were delivered under this category in FY 24-25. / . / 3.2) 6 products developed: case study slide pack for COP29; Adaptation & Biodiversity Taxonomy and Guidance; and four Sector Outcome & Learning Reports in Energy, Green Finance, Nature and Climate Policy.

UK PACT project activities under this output seek to generate evidence and learning and disseminate that knowledge among key stakeholders to inform policies and practices which are then adopted to enhance action on emissions reductions. This type of support helps governments anticipate impacts, allocate resources effectively, and refine strategies based on emerging insights. By promoting the exchange of what works, for whom, and under what conditions, UK PACT also strengthens adaptive programming, fosters collaboration, and supports the scaling of successful interventions.

Six case studies across four UK PACT Funds, across the green finance, energy, and mobility sectors, illustrate how UK PACT has generated new evidence, knowledge, and insights through targeted research and analysis. This is a slight increase on the planned number of cases (5). This work has directly informed the design and implementation of climate policies and strategies, contributing to more effective and inclusive climate action.
A total of 131 unique project outputs were delivered under this category in FY 24-25, which was slightly lower than the 145 planned.
Six knowledge and communication products were generated and disseminated by the programme, in line with what was planned. This included outcome and learning reviews across four priority sectors: climate policy, energy, green finance, and nature. These reviews provided both sector-specific insights and shared lessons on the UK PACT model.
Examples of the case studies developed under the output are:

In Brazil, funded by UK PACT, the Ecological Transformation Plan (ETP) task force conducted a series of sectoral and value chain analyses – covering economic growth, decarbonisation potential, job creation, and investment needs – to identify Brazil’s highest-potential green growth sectors. These findings informed the Ministry of Finance’s policy priorities and investment strategies under the Ecological Transformation Plan.

In South Africa, UK PACT support for the SAREM project generated impactful research and learning through the development of Market Intelligence Reports (MIRs), which provided real-time, policy aligned data and investment insights that informed national strategy, supported solar thermal manufacturing and skills development, and supported evidence-based decision-making across South Africa’s renewable energy sector. The reports were well received by counterpart government officials and ministers.

Changes to this output during the past year and planned changes as a result of this review
#### Output 3 remains focused on ‘Knowledge, evidence and learning generated and shared, and policies and practices informed’, but the indicators were revised to use case studies to more clearly articulate the result of this work, and more explicitly focus on recording the direct result of programme activities, rather than summarising the activities and numbers of products produced
Progress on recommendations from the previous annual review
Under this Output, last year’s Annual Review had the recommendation: “to be of maximum value recommendations/guidance [developed in projects] provided needs to be easily and effectively communicated to the right audience.”

The case study examples detailed above demonstrate good progress on this recommendation. The Brazil ETP project was designed to present, validate and define future analyses together with relevant stakeholders on an ongoing basis, throughout implementation, to ensure the analysis reached the right audience, met their needs and maximised use. In the case of the South Africa SAREM project, UK PACT support enabled the shift to digital, real-time market intelligence reports, making them more useful to investors in need of live data and information.

Lessons learned this year and recommendations for the year ahead
Evidence and knowledge products are most impactful when they are designed for practical uptake and linked to decision-making processes. FY 24-25 case studies demonstrate that research and data generation can influence policy and investment decisions most effectively when complemented by targeted dissemination and stakeholder engagement plans. When designing activities under this output in UK PACT projects, PACT Fund teams and DP teams should continue to ensure that knowledge products are clearly linked to policy development or decision making in counterpart governments and should consider if dissemination plans are needed in project activities.

Output Title	Partnerships and networks established and strengthened
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1) # and description of cases of policy processes or practices linked to climate mitigation that have been supported or informed as a result of UK PACT convening and partnering activities / 4.2) # and description of cross-project, cross-fund or cross-programme convening activities or events delivered by the programme	4.1) 5 cases; and identification of cases for FY 25-26 reporting. / Evidence within selected case studies demonstrates progress on the establishment or strengthening of multi-stakeholder partnerships and networks to deliver improved climate action. / 25 unique project outputs planned in this category for FY 24-25 / 4.2) 4 events delivered: including portfolio cross-learning events/workshops in Kenya, Indonesia, Colombia and Mexico; panel moderation at biodiversity COP16 in Cali, Colombia; and the relaunch of the GEDSI learning and leadership webinar series.	4.1) 7 Cases / 28 Unique project outputs were delivered in this category for FY 24-25 / 4.2) 7 Events

UK PACT projects establish and strengthen climate partnerships and networks both in-country and regionally by convening stakeholders for the exchange of knowledge, evidence and learning, to drive forward increased ambition in action on reducing emissions.

A total of 28 unique project outputs were delivered under this category in FY 24-25, higher than the planned number of 25. Seven case studies across five UK PACT Country Funds in the Green Finance, Climate Policy, and Energy sectors were developed, exceeding the planned number of five. These case studies illustrate how projects have actively convened stakeholders around shared priorities – facilitating collaboration, consensus-building, and the co-creation of knowledge to inform the design and delivery of new climate policies and strategies. The project examples below provide illustrations of relevant activities and their outputs in 24-25.

In Brazil UK PACT supported the design and operationalisation of Brazil’s Ecological Transformation Plan (ETP)by bringing together public, private, and civil society stakeholders through structured dialogues, technical workshops, and high-level forums – including COP29 and New York Climate Week – to co-develop a roadmap for green economic transformation. These engagements validated research, built consensus around priority value chains – such as biofuels, critical minerals, and the circular economy – and directly informed the Ministry of Finance’s policy direction. The project fostered cross-sector alignment, boosted investor confidence, and laid the foundation for future regulatory and financial mechanisms to support Brazil’s green transition.

In South Africa UK PACT supported the South African National Treasury on their green finance taxonomy work. The programme’s support engaged key financial and regulatory stakeholders – including the National Treasury, Financial Sector Conduct Authority (FSCA), and the Banking Association of South Africa (BASA) – through bilateral meetings, a national workshop, and collaborative technical work. These efforts fostered multi-stakeholder dialogue, built consensus on usability challenges, and contributed to the FSCA’s pilot taxonomy initiative and BASA’s position paper to the Treasury, demonstrating early influence on both public and private sector practices.

For the programme-level convening and knowledge sharing (indicator 4.2). Seven events were delivered or supported to foster knowledge exchange and stakeholder collaboration across the programme in FY 24-25, this was three more events that the four planned for this milestone. These included cross-portfolio learning workshops in Kenya, Indonesia, Colombia, and Mexico; a high-profile panel on nature-based solutions at Biodiversity COP16 in Cali, Colombia; and the relaunch of the GEDSI Learning and Leadership webinar series. Each event was designed to surface insights, build synergies, and strengthen partnerships around shared climate and development priorities

Changes to this output during the past year and planned changes as a result of this review
The Output wording has remained the same from the previous MEL framework. Indicator 4.1 was revised to follow to a case study approach and focus on recording the direct result of programme activities, rather than summarising the activities. Indicator 4.2 was also added cover the number and description of convening activities at the programme level.

Progress on recommendations from the previous annual review
Last year’s annual review did not include a specific recommendation on this output. There was a lesson included in this output without a specific recommendation on the importance of Gender, Equality, Disability and Social Inclusion (GEDSI) integration and mainstreaming throughout the project life cycle, which went on to feed into UK PACT’s updated GEDSI strategy and its implementation.

Lessons learned this year and recommendations for the year ahead
This Annual Review and the programme’s performance have shown that strong partnerships and networks are critical for enabling systemic change, and that partnership and networks can accelerate policy reform and unlock investment when they are inclusive and strategically aligned. The programme does not have any further specific recommendations under this output, which has exceeded targets. The programme has identified specific recommendations under the lesson 3 on learning in the major lessons and recommendations, that will take forward development of the programme’s learning approach in the next reporting year.
## D: VALUE FOR MONEY

This internal review assesses the UK PACT programme’s value for money (VfM) performance for FY 24-25, aligned with the refreshed Monitoring, Evaluation and Learning (MEL) Strategy and VfM Framework approved in October 2024. It provides an interim analysis ahead of an independent VfM study scheduled for FY 26-27 following procurement of an evaluation partner. Based on the evidence provided below, the programme is assessed as continuing to demonstrate VfM:

Economy:
- UK PACT maintained strong cost discipline, with supplier costs at 15% of DP programme expenditure well within the contractual 20% cap.
- Proportional/agile resourcing ensures fund management costs remain low during normal operation but flex to accommodate surge periods of work (calls for proposal/project launch), supporting cost-efficiency without compromising oversight.
- FCDO procurement standards including for competitive tendering were applied and cascaded to implementing partners, and expert deployments were sourced from local markets and a centralised roster using benchmarked rates to maximise VfM.

Efficiency:
- Under KPI 1b, which measures the timely delivery of outputs (on time or within 1 month), the programme achieved a success rate of 96% and 100% in in Q3 and Q4 of FY 24-25, exceeding the FCDO’s target threshold of 85%. Adaptive management mechanisms – such as adjustable Fund Implementation Plans, monthly Delivery Meetings, Quarterly Fund Boards, and delegated authority for decision making and oversight – enabled real-time resource reallocation, mitigating delays and optimising delivery.
- Stronger development of pipeline readiness and advanced planning over the course of FY 24-25 meant committed spend for FY 25-26 was projected at 59% against the budget by Q1, compared to 35% at the same point last year.

Effectiveness:
- UK PACT delivered 319 outputs strategically aligned to the programme’s theory of change, exceeding annual targets.
- Over 30,000 individuals and more than 500 organisations received technical assistance in FY 24-25. To date, technical assistance has informed over 70 climate policies and plans and supported mobilisation of £3.79bn in climate finance for the lifetime of the programme, reinforcing the programme’s catalytic role in enabling long-term emissions reductions.
- The programme has shown consistent year-on-year improvements in fund-level scores against the FCDO international climate finance (ICF) KPI 15 which measures how likely interventions are to drive transformational change.
- The refreshed MEL framework (Section G) has strengthened effectiveness by embedding a coherent, impact‑oriented approach, ensuring a clear causal pathway from outputs to impact, guiding the selection of interventions to maximise impact.

Equity:
- UK PACT has a Gender Equality marker of “significant”, and Disability Inclusion marker of “significant”. Equity considerations were embedded throughout the delivery cycle in design, project selection and implementation, as well as through the MEL framework. Gender equality, disability and social inclusion (GEDSI) action plans are mainstreamed across projects and reviewed annually, with 12 GEDSI experts providing hands-on support to fund teams. This has resulted in demonstrable inclusion outcomes, with marginalised groups actively shaping and benefitting from climate action.
- UK PACT’s GEDSI Learning and Leadership Hubs have brought together partners, FCDO staff and GEDSI experts to share good practice and build long-term institutional and individual capacity.
- Several indicators were introduced to measure equity on the programme delivery for FY 24-25. Female representation in the Long-Term Technical Assistance team remained high at 69%, while local nationals filled 97% of country and regional positions, a significant increase from the baseline. Supply chain diversity also improved, with Micro, Small and Medium Enterprises (MSMEs) (75%), national organisations (76%), and women-led organisations (42%), and marginalised-led organisations (17%) making up a slightly larger share of grant applications compared to the baseline.

Overall cost‑effectiveness: The programme delivers high impact relative to the investment made. Through disciplined cost control and efficient delivery, inputs are converted into timely, strategically aligned outputs that catalyse policy change, mobilise resources, build institutional capacity, and embed equity. Performance is consistently improving over time with growing transformational potential.

E: RISK

Overview of risk management
As part of the transition to a single DP and decentralised delivery model, a revised risk management approach was introduced, establishing how risks should be registered and managed at each level of the programme (project, fund, overall programme).

UK PACT operated largely within its defined risk appetite during 2024-25, though several areas required heightened attention. Residual risk ratings generally remained moderate, with mitigation strategies stabilising most risks. Two themes dominated the year: strategic uncertainty and DP capacity.

Key Trends:
- Strategic & Funding Risks: The most significant development was the announcement of ODA reductions, putting future funding and programme continuity at risk. This remained above appetite at year end, though this risk fell within appetite after budgets were received in April 2025. Funds undertook scenario planning to mitigate the impact.
- Delivery Risks: Risks developed into issues with DP mobilisation delays, resource gaps and performance issues in Asia and Nigeria and issues with financial forecasting and reporting (which required a rectification plan). Strengthened governance helped mitigate the risk of programme wide delivery issues.
- People Risks: Recruitment constraints and turnover increased pressure mid-year before stabilising following recruitment and prioritisation. Overseas staffing risks eased after contract extensions.
- Safeguarding & Fiduciary Risks: Fraud and SEAH risks stayed low with enhanced checks and learning sessions.

Lessons Learned:
- Early engagement with senior stakeholders and proactive scenario planning are critical to managing funding volatility.
- Swift mitigating action to address emerging delivery risks are important to prevent these developing into issues.
- Investment in staff capability and sectoral learning supports resilience under decentralised delivery.
An internal audit of the programme in FY 24-25 found controls to be adequate but highlighted some weaknesses in risk management, reflecting the programme being in transition to a single DP and a new decentralised operating model. Actions were taken in this review period and since then to address the findings and recommendations include standardising risks, risk categories and appetites across funds, strengthening oversight of Implementing Partners’ risk management, and introducing a more defined risk escalation process – with further training on risk management to be rolled out across the programme.

Given that the programme successfully mobilised the single DP model and expanded delivery with strong delivery of results, residual risk ratings throughout the year generally remained moderate, and changes have been made to address challenges raised by Internal Audit, this review assesses that the risk rating for the programme overall has fallen from major to moderate.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery Partner (DP) Annual Performance Review
As is set out in the DP Contract, the FCDO and Palladium conducted and Annual Performance Review of FY 24-25. A summary of this is set out below:

“FY 24-25 marked a pivotal year for UK PACT, with the successful mobilisation of a new delivery model and a significant scale-up in operations and geographic reach. The programme met or exceeded its results targets[6], delivering impactful technical assistance to over 30,000 individuals and 500 organisations, and demonstrating strong performance across the majority of KPIs.
[6] This Annual Review assesses that one of the results targets has been missed as one indicator has been missed.

However, the year was not without its challenges. Performance was notably better in countries where Palladium had established teams. Delays in mobilisation and performance issues with staff particularly in newly managed funds in Asia and Nigeria caused impacts on programme delivery. These prompted significant involvement from FCDO and Palladium staff to resolve. Challenges were also experienced in PMU capacity, the development and implementation of the MEL framework and approach[7], and financial and risk management, especially financial forecasting.
[7] In the review, the FCDO acknowledged its role in the delay to development of the MEL framework, where the FCDO’s capacity to engage was initially limited given the scale of other mobilisation tasks

Throughout these hurdles, Palladium engaged constructively with FCDO to address concerns, showing adaptability and a commitment to improvement. As the programme continues the FCDO wishes to see an increasing focus on results, and successful communication of the impact of the programme.”

The findings of the performance review informed the lessons and recommendations in this annual review on financial management, results, and comms.

Key Performance Indicators (KPIs)
Draft Key Performance Indicators were included in the tender and finalised post contract award. Overall, the DP performed well against the KPIs. Of the 19 instances where KPIs were measured, the DP met the KPI ‘good’ criteria in 17 of them. The two instances the good criteria were not met were on financial KPIs. In both cases, the DP improved and met the good criteria the following quarter. One “Inadequate” score prompted the need for a rectification plan, which was agreed with FCDO and then carried out by Palladium.

Strategic Supplier Relationship Management (SSRM) scorecards
SSRM scorecards assessed the DP across dimensions such as governance, delivery, risk management, and collaboration. Results indicated a positive trajectory, with the DP rated as a responsive and constructive partner, particularly in addressing mobilisation challenges and implementing improvement plans. Areas of strength included proactive engagement with FCDO, adaptability during scale-up, and compliance with contractual obligations. However, the scorecards highlighted the need for continued improvement in financial forecasting accuracy and MEL implementation, aligning with issues flagged in KPIs and audit findings.

Financial Management
Financial management remained a key focus in FY 24-25, with challenges experienced and improvements introduced. Early-year issues included one late forecast submission and a forecast variance of 13%, leading to KPI breaches (see above) and financial deductions for the DP. Mid way through the year, the overall budget for UK PACT was reduced by £10m to mitigate underspend risk. New tools to strengthen forecasting and reporting were introduced, alongside additional financial review meetings and clearer invoicing processes. Overall, UK PACT achieved a significant increase (73.5%) in spend from the previous year. Final spending was £45,783,850 against an initial budget set at the beginning of the year of £56.1m, and a revised budget set at the mid-year point of £46.1m (a 99.3% spend). £15,058,000 of this spend was funded by DESNZ, with the rest coming from the FCDO.

Internal Audit
As referenced elsewhere in this review, FCDO conducted an internal audit of the UK PACT Programme with fieldwork taking place in Q3 FY 24-25. The audit found UK PACT to be strategically aligned with HMG climate objectives and supported by effective governance at the portfolio level, but highlighted risks given the programme’s complexity, ongoing transition to a single delivery partner, and gaps in MEL and risk management. The programme followed a plan of work to respond to the issues raised. The final step in this process is for the programme to report to the audit team that this work is complete. The Executive Summary and ratings of the audit report is included at Annex B.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The DP is responsible for overseeing the project Implementing Partners, monitoring delivery of expected results, and collecting and reporting evidence of achieved outputs, outcomes and impacts against the UK PACT results framework. Monitoring includes field visits by DP staff in country, UK PACT officers at Post also attend field visits to see project IPs, as well as engaging with counterparts to determine how successful the intervention had been. The UK PACT Fund Leads (who are based in the UK) also visit their country at least once to meet with government counterparts and IPs and visit project sites, drawing on evidence and learning to influence future strategy.

Under the new delivery model, UK PACT has introduced a refreshed Monitoring, Evaluation and Learning (MEL) Strategy designed to strengthen accountability, improve evidence of impact, and embed learning across the programme. The new MEL Strategy and Theory of Change were developed and agreed during FY 24-25. The changes were mobilised in October 2024.

The new MEL system includes:
- A revised Theory of Change and Logframe: Updated to clarify causal pathways from outputs to impact; updated the outputs to assess uptake of TA; aligned indicators to ICF KPIs; and included sector-specific indicators for outcomes such as finance mobilised, clean energy capacity installed, improved land management, and sustainable mobility.
- Case-Based Results (CBRs)[8]: Introduced as a core reporting tool to capture qualitative evidence of change, explain why and how results occurred, and provide actionable learning for replication and scaling.
  [8] As noted above, UK PACT now uses a case study-based reporting methodology in the new MEL Strategy, where case studies are recorded as a core reporting tool alongside the total number of outputs produced under each indicator. Case studies are designed to capture qualitative evidence of change, explain why and how results occurred, and provide actionable learning for replication and scaling. PACT projects are expected to produce at least one case study (which may cover multiple results) during implementation.
- Nested Approach for Theories of Change: Development of Fund and sector-level ToCs to align with the overarching programme framework, ensuring coherence while allowing for the development of contextualised indicators and targets. These will be used to structure quarterly results reporting at fund level, and to guide reporting and learning activities, including ICF KPI 15 reporting and portfolio learning events. Development of fund and sector level ToCs was agreed in the new MEL strategy in October 2024 and was completed in the following reporting year in FY 25-26, however substantive drafts of fund ToCs were had been developed in 9 of 14 funds by the end of FY 24-25. They will be assessed in the next Annual Review for FY 25-26.
- Quarterly and Annual Reporting: Quarterly reports focusing on progress towards outcomes and intermediate outcomes in addition to outputs. Annual reporting consolidates results at programme level and includes KPI 15 analysis on likelihood of transformational change.
- Integration of GEDSI: Gender Equality, Disability and Social Inclusion objectives are embedded throughout the MEL framework, with disaggregated data and dedicated learning questions to ensure equitable climate transitions.

The new MEL Strategy also included an agreement to introduce a new Information Management System (IMS) to be developed by Palladium, to streamline data collection and reporting, with IPs able to upload evidence directly. The IMS development was finalised after the reporting year in FY 25-26 and will be assessed in the programme’s next Annual Review. The DP also established Regional MEL Manager roles to provide quality assurance and capacity building at fund level, while the central delivery partner MEL team ensures consistency and alignment with programme strategy.

The MEL activities undertaken and processes followed in FY 24-25 were:
- For FY 24-25, Palladium reported quarterly on programme results, and a review of results was held quarterly at the programme’s Quarterly Programme Boards. Palladium also produced an Annual Report summarising programme achievement across all levels of the UK PACT log frame – outputs, intermediate outcomes, outcomes and impact. This was accompanied by a series of case studies capturing results and impact highlights from across the portfolio and separate reports for each of the ICF TA KPIs.
- A separate ICF KPI 15 (Likelihood of Transformational Change) report was submitted in September 2025, covering the FY 24-25. For the first time since the programme began, a report was completed for each fund, including a baselining exercise for the newest funds.
- New theories of change – see point above.
- Quarterly Fund Boards were held for every fund, where quarterly results reporting was discussed. These Boards were chaired by the UK PACT Regional Leads in the UK, and attended by the Fund Leads, officers at Post and the DP.

The FCDO internal audit of the programme also identified gaps in the programme’s MEL approach. The programme has made changes and improvements to address these gaps, many of which were already planned as part of the new MEL Strategy and theory of change. These included:
- The establishment of baseline data, milestones and targets in the UK PACT logframe to enable consistent monitoring and evaluation over the course of the programme. These have since been revised in the following reporting period (FY 25-26) when more data was available.
- Fund quarterly progress report (QPR) templates have been updated to improve results reporting to better serve adaptive programming and strategic decision-making needs of funds.

For undertaking this Annual Review, an in-country visit to Indonesia was carried out for the review team to understand the value and results of the country portfolio, and how it links with HMG strategy in country. This was following the recommendation to carry out in-country visits from the previous annual review, and the programme would recommend this practice continues for future UK PACT Annual Reviews. Last year’s review also recommended considering bringing the timing for the FY 24-25 Annual Review forward to the summer of 2025, however resource constraints and significant staff changes meant moving forward to the summer wasn't feasible, and the Indonesia country visit was planned for November to purposely link it to the DP regional conference with representation of all seven regional funds to provide a stronger evidence base. It was also recommended that the FY 24-25 Annual Review includes staff from outside of the UK PACT team, and the programme secured the support of an independent reviewer this year. However, the independent reviewer was unable to join the visit due political instability at their post, but they have still provided scrutiny and input into the Annual Review process and report.

UK PACT will procure an evaluation partner to undertake independent evaluations of the programme, complementing internal MEL activities. Procurement will commence in FY 25-26.

Learning
The refreshed MEL strategy places learning at the heart of UK PACT’s delivery model. A structured learning agenda was introduced in October 2024, focusing on four priority themes:
1. Programme design and synergies – How to build coherent portfolios that deliver systemic change.
2. Partnering for impact – What drives successful bilateral partnerships and local ownership.
3. Sector transformation – Entry points for catalytic interventions and pathways for scaling.
4. Equitability and sustainability – How to ensure just transitions and sustained behaviour change.

Learning was embedded throughout the project cycle and in core moments of project design, implementation and close out. All projects must outline a learning plan at application stage and are encouraged to report on lessons learned during implementation and actions taken or planned in response through their monthly updates and quarterly reporting. At project close out, a full completion report is undertaken by the IP or expert leading the project documenting project achievements, challenges, lessons learned and future recommendations.

During FY 24-25 a number of core learning activities were undertaken at the fund and programme-level. Portfolio synergy sessions (including at the global gathering) took place, along with thematic expert-led sector outcome and learning reviews across four priority UK PACT sectors, namely energy, green finance, climate policy and nature. These reviews aimed to draw out lessons on best entry points for UK PACT technical assistance in these sectors. The GEDSI learning and leadership hub was also relaunched, bringing together IPs, experts, FCDO and the DP consortium in a monthly forum to share best practices and learnings from GEDSI implementation across a range of sectors. At the fund level, cross-portfolio learning events were held in Colombia (Just Rural Transitions and NDC alignment), Mexico (sectoral roundtables), Kenya (Nature Based Solutions) and Indonesia (energy efficiency and low carbon transport). These events were designed to surface insights, foster synergies, and strengthen collaboration and partnerships around shared climate and development objectives between programme stakeholders. As noted in lesson 3 and related recommendations for this Annual Review, more can be done to strengthen cross-portfolio learning going forward, as identified in the internal audit report and through interviews with UK government officials.

Date of last narrative financial report	May 2025	Date of last audited annual statement

Annex: Detailed Recommendations & Lessons from FY 23-24

Major lessons and recommendations from FY 23-24 and progress made
No.	Lesson	Recommendation	Progress
1	UK PACT remains a highly valued TA programme for climate mitigation action, and benefits from strong engagement and collaboration at Post and link-up with other UK government climate initiatives.	UK PACT should continue to work closely with Post bilateral programmes and CMPs, as it has in SA with the JETP, to build synergies across programming effort in country and enhance the impact of UK climate mitigation action (date: ongoing). / UK PACT Team to work with DESNZ to deliver the approach agreed at the Programme Board on 7th November 24 to increase collaboration between UK PACT with other ICF TA programmes; DESNZ to lead (June 25)	UK PACT HQ colleagues work closely with Post, who have a role in signing off strategies and projects and sit on quarterly boards. / There is regular engagement at all levels, including regular catch-ups between senior Post UKB and regional team leads. Post teams were engaged on 26-27 fund prioritisation, and the programme has established ‘Across the Network’ meetings to share priorities and perspectives. / Ongoing engagement and synergies have been created with CMPs and post bilateral programmes. / At post, examples are: the Melaju transport platform in Indonesia, EcoInvest in Brazil and South Africa energy projects integrated into the JETP. / At HQ, engagement with CMPs and CoEs examples are: GCIP, GCIE, and collaboration on NDC partnership through UK PACT thematic lead on climate policy and governance. / There is strong collaboration with DESNZ via governance structure. / Good coordination with DBT on Philippines Offshore Wind inward UK study visit. / UK PACT leads design of new CNE CoEs, positioning as a central TA programme and embedding lessons learned.
2	In some Country Funds interventions are spread too thinly contributing to lower than anticipated portfolio outcomes in some cases undermining significant impact. This is because of UK PACT’s large scope, the limited budget per country, and the prioritisation given to demand-led interventions.	Fund[9] teams, as a default, should prioritise a maximum of three sectoral areas and reduced number of sub-sectors (date: from March 25 onwards with progress to be reviewed in early 2026). / Fund teams should look for opportunities to ‘cluster’ delivery of complementary projects which work to achieve a shared desired outcome, and thus more significant impact. Projects that have transformation impact should receive greater prioritisation in the project selection process. Teams should draw on evidence of what works well to inform project scoping within sectors (date: from March 25 onwards with progress to be reviewed early 2026 view). / Follow up should be designed into projects from the start to maximise learning and / or the scaling up of interventions and improve progress against outcomes. Follow up activity to be included in fund level plans and reporting and to feed into learning products. Also to be included in objectives and work plans of FCDO (Post) fund leads (date: from March 25 onwards with progress to be reviewed early 2026). / The delivery partner to deliver programme level guidance to teams on how best to conduct, communicate and report on follow up activity (date: by June 25). / Whilst each Fund should look to limit the number of sectors and sub-sectors, the programme should maintain the flexibility to allocate funding to respond to requests that emerge mid-year from counterparts, without the need for a full sector case. For example, an occasional expert deployment outside of the main sector cases should remain possible (date: from March 2025, progress reviewed in early 2026).	Actions taken / Fund strategy limits: New UK PACT fund strategies signed off now have a maximum of three sectors (e.g., Mexico, Malaysia, Philippines). Exceptions in ASEAN, Indonesia, Brazil which are larger funds with complex delivery challenges / Theory of Change (ToC) have been rolled out at portfolio and fund level to clarify intervention pathways, including Fund and sector level ToCs. / Learning Resources: Sector learning documents and MEL strategy include sector transformation themes. / Parallel Strategy/Sector Case Development: Now rolled out. Malaysia and Philippines strategies developed in parallel with sector cases, ensuring clustered delivery and shared fund-level outcomes. / Examples of clustered delivery: / Nigeria: 6 CET projects clustered around Rural Electrification Agency with complementary expert deployments. / Philippines: Focused on offshore wind & microgrids. / Malaysia: Energy & nature priorities linked to sustainable finance roadmap. / Project Closure Process: The delivery partner have implemented structured closure process with learning capture and follow-on recommendations; guidance developed for systematic follow-up. / Flexibility for responding to counterparts maintained in the programme: For example, Indonesia introduced climate governance work as a support area following government change. / Actions planned / Sector Reduction: The programme is considering further reductions in sectors in line with 26-27 prioritisation (e.g., Nigeria dropping AFOLU) / MEL Approach: Finalise 2026 learning themes and learning plan / Outcome Tracking: Guidance on post-project outcome tracking has been produced, and will be disseminated with post staff / Spending plans for 26-27 to be analysed against Logframe and fund ToCs
3	Whilst flexibility and responsiveness to counterpart’s requests are key to UK PACT’s success, UK PACT should move to being more ‘demand informed’ than ‘demand-led’, with a greater emphasis on shaping the demand from counterparts.	When scoping new areas of work, FCDO Fund Leads should seek advice from xHMG experts to better guide portfolio priorities and projects, developing the approach hand in hand with UK PACT PFPs. Specifically, FCDO Fund Leads should provide advice, informed by consultation with xHMG sector experts, to UK PACT PFPs on the types of interventions to promote in discussions with counterparts. (date: from April 25 onwards, progress to be reviewed in early 2026).	The programme’s guidance documents (Master Slide Deck, Sector Case and Strategy guidance) have been updated to incorporate this recommendation on being demand informed. / The programme has established thematic leads for key sectoral areas to coordinate HMG expertise, for climate policy and finance; AFOLU; climate finance, and energy transition. And the programme draws on DESNZ support on Emissions Trading Schemes / Carbon Pricing. / The Thematic Leads help the programme understand the UK's policy priorities, provide technical advice on strategies and project selection, share updates on other relevant programming, and learning from UK PACT interventions. / All relevant country and sector strategies shared with Thematic Leads for their advice, and they advise on investment panel decisions.
4	UK PACT has a thorough approach to scoping and setting strategy for each fund, but the process is resource intensive which reduces time for the delivery of interventions and can undermine fund level programme coherence. Similarly, co-design of projects with counterparts is a USP of the programme but can also reduce the time for programme delivery.	The programme team should explore with the Delivery Partner ways to condense and better sequence the scoping, country strategy and implementation plan processes (date: plan in place by April ’25). / Country strategies should be focussed on key issues, and the programme (through the DP) should consider options for maximising efficiency. For example, can sector cases be completed at the same time and can calls for proposals encompass multiple sectors? (date: plan in place by April ’25). / Similarly, consideration should be given to how the co-creation process could be made more efficient (date: plan in place by April ’25).	Actions taken / Streamlined Strategy & Sector Case Approach: The revised approach was implemented in early January and applied to Malaysia, Philippines, and Mexico strategies. Country and sector strategy templates were reduced to focus on key issues. For Philippines and Malaysia, sector and country strategies developed concurrently to speed up and reduce resource intensity. / Call for proposals efficiencies: In Mexico, all calls for proposals (CfPs) were developed concurrently to maximize project synergies and speed up the process. In Kenya’s nature based-solutions CfP, the market engagement stage removed due to strong market response. / Improved Scoping Times: Project timelines were reduced in Malaysia and Mexico (~16 weeks vs. 18-week average), and in the Philippines (14 weeks) / Co-creation activities moved into inception phase: Rolled out Oct/Nov 2024 after trials in Brazil (2022/23). This has had the benefits of quicker mobilisation, better counterpart engagement, equitable for IPs, MEL and GEDSI resourcing aligned early. / Actions planned / Reduction of timeframes during selection and contracting, including: removal of market engagement stage where appropriate, further analysis of CfP and ED processes to identify opportunities for refinement across scoping, selection, and co-creation. / Portfolio alignment workshop post-GA signing to harmonize projects if CfPs are staggered closely.
5	The programme’s MEL approach should continue to pivot towards being more outcome focussed, which should facilitate better articulation and demonstrate of impact and sustainability of effect.	The Theories of Change developed at fund level and sector level should be finalised by the delivery partner and reviewed by FCDO Fund and Regional Leads before the end of the FY, in order to strengthen the programme-wide approach for selecting interventions in the coming FY. A ‘golden thread’ linking fund interventions together and to the overarching programme TOC and the Post Country Business Plan should be clear (date: April ’25). / Quarterly Boards and Reporting should be focused on progress towards outputs and outcomes, rather than project updates (which should be covered in Monthly Delivery Meetings or other check-ins). The DP should submit updates on output, outcome and impact performance in quarterly reporting at fund and programme level, detailing progress made and a comparison against the expected results. Quarterly reports at fund and programme level should also set out the expected results for the next quarter. The DP will also submit a report summarising output, outcome and impact performance for the whole of the FY (starting with FY 24-25) (date: April ’25). / FCDO (Post) Fund Leads and the delivery partner Fund Leads should be required to conduct regular field visits (at least once every six months) with IPs to better track progress towards outcomes, as well as more effectively identify risk or safeguarding concerns. PFPs should also be required more systematically follow up to collect information after projects have finished. (date: from April 25, progress to be reviewed in early 2026).	Actions taken / Development of Theories of Change (ToCs) The delivery partner partially completed ToCs for all countries and sectors; workshops held with all fund teams and ToCs included in Fund QPRs (August). / Integration into Prioritisation ToCs were used in 26-27 prioritisation plans to assess impact of budget cut proposals. / Results Reporting Shift: Fund and programme-level quarterly reports and Boards now cover progress against results framework. The delivery partner’s Annual Report (July) focused on results reporting, showing a step change in results reporting. / Monitoring & Assurance; Role responsibilities have been updated and budgets allocated for field visits and post-project monitoring. Risk monitoring incorporated into the UK PACT Risk Framework. Checklist, safeguarding training, and field visit report template have been developed / Actions planned / A working group has been created to refine QPR and Fund Board process by Feb 2026 (updated guidance for February cycle). / Fund ToCs are being made “reporting ready” (mapped with indicators) February QPRs to include results narrative against ToCs. / Post-project follow up guidance has been developed by the delivery partner – and will be implemented on discussion with staff at post. / The delivery partner is planning training for field visits for staff. / Approach for FCDO staff field visits will be designed, including templates.
6	The expansion of the programme from 6 Country funds to 10, and 2 regional funds, makes it challenging to manage the programme centrally and has increased the importance of programme management excellence.	The role of the DP Country Fund Managers and PFPs should have a greater emphasis on programme management, with job descriptions updated (as necessary) and training rolled out across the team as required (date: from June 25 onwards, progress to be reviewed in early 2026). / To ensure consistency, the programme must continue to embed a standardised approach to how the core of UK PACT is managed at fund level and consistently reported up to Programme Level, including delivering the recommendations of the recent IAD (date: ongoing).	Actions taken / Guidance: Programme Activity Manual (PAM) Developed in March 2025 as the delivery partner’s overarching guide for activity management. Standardised approaches have been implemented across workstreams in line with PMU policies (PAM, MEL, GEDSI, Risk, Finance). / The delivery partner team training: UK PACT processes, end-to-end activity management, MEEs, CfPs, risk, safeguarding, fraud, financial management, GEDSI, and MEL have all been implemented. / Role Clarity and Capacity Building: RACIs have been developed for each workstream to clarify responsibilities and regional trainings delivered on RACIs and expectations for staff. / Job descriptions for Fund Manager and Fund Associate have been updated to include project management tasks / Model/template objectives for Programme Funded Post Staff have been developed. Master Slide Deck sets out responsibilities at each level. / Onboarding: Internal and FCDO-facing onboarding induction deck deployed to professionalise onboarding. / Governance and Risk Management: Monthly programme-level delivery meetings introduced in Oct 2024; fund-level meetings started Jan 2025 with standard agendas (delivery, finance, risk). / Risk Framework was rolled out during mobilisation in 2024, introducing structured risk identification, management, and escalation. Risk training between Delivery Partner (DP) and FCDO rolled out in May; refresher planned for December. / Actions Planned / Confirm PFP job descriptions and objectives align. / Agree training plan for 2026
7	The in-country visit to South Africa was extremely useful for the review team to understand the value and results of the country portfolio, and how it links with Post’s Country Plan. / This year’s Annual Review took place several months after the review period, during which time the delivery model had changed and many programme staff had moved on which impacted the value of the findings.	Recommend conducting in-country visits as part of future Annual Reviews (date: ongoing). / Bringing the timing for future Annual Reviews, including the FY 24-25 Annual Review forward to the summer (date: August 25). / Recommend that the FY 24-25 Annual Review includes staff from outside of the UK PACT team (date: ongoing).	Significant staff changes meant moving forward to the summer wasn't feasible, and Asia country visit in November to purposely linking it to the delivery partner regional conference to provide a stronger evidence base for the AR. AR should be complete a month before last year's review. / AR included country visit covering Asia Funds as not examined before as part of the AR - Indonesia, ASEAN / Independent reviewer unable to join due political instability at their post, but they are scrutinising and providing input into the report
[9] Country Programmes were renamed as Country Funds in April 2024.

ANNEX B – EXECUTIVE SUMMARY OF AUDIT RATIONALE