## Explainer
UK PACT Results Framework
The following document summarises: - The UK PACT Results Framework, including log frame with output, intermediate outcome, outcome and impact indicators, and cross-cutting reporting and learning milestones which will be delivered by the programme. These are accompanied by brief definition and disaggregation notes (more details will be included in the individual indicator reference sheets). - Milestones and targets are cumulative - Learning themes and questions which will guide activity in this area through programme monitoring, evaluation and reporting. - A Log Frame checklist. - A Change Log to track updates to the Results Framework over programme implementation. Reporting on the UK PACT Results Framework will take place on a quarterly and annual basis, and feed into the FCDO Annual Review cycle. The UK PACT reporting cycle runs from April 1st to March 31st, following the UK Fiscal Year. A detailed set of methodologies, assessment and verification tools, trainings and guidance notes will be developed to accompany the Results Framework and facilitate measurement and reporting of progress against log frame indicators, and will be available to consult on the UK PACT SharePoint.

## Log Frame
PROJECT NAME | UK Partnering for Accelerated Transitions (UK PACT)
IMPACT | Impact Indicator 1 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Definition & Disaggregation | Assumptions
Accelerated emissions reductions which support equitable just transitions, and contribute to poverty reduction and resilient economic development | Volume of emissions avoided / reductions supported by UK PACT (ICF TA KPI 5)* | Planned | 158,809 tonnes CO2 eq | 100% of projects identified as being able to report against this indicator have a completed TA KPI 5 report | 100% of projects identified as being able to report against this indicator have a completed TA KPI 5 report | 1,000,000 tonnes CO2 eq | As it is challenging to attribute specific outcomes to TA support specifically, this indicator does not attempt to determine a specific volume of emissions reductions that ICF TA has causally influenced or that can be directly attributed to UK Government. Instead, it measures the contribution of ICF TA to emissions abatement: the total volume of emissions reduced or avoided that have been supported by ICF TA. This is a broader measure than the volume of emissions reductions that may be directly attributable to ICF TA (which is not possible to identify in many cases of TA provision). | • There are no major economic, social, or political shocks in-country which could outweigh emission reduction and just transition efforts. • There is sufficient funding available to implement enhanced policies and practices.
|  | Achieved |  | Direct: 451,141 tCO₂eq Indirect: 713,902 tCO₂eq
Source
Evaluation workstream - TA KPI 5 methodology
| Impact Indicator 2 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Takes into consideration socio-economic transformations, including poverty alleviation, empowerment of women and marginalised groups, and reduced impacts of climate change on the most vulnerable. Will consider how and where UK PACT has contributed to accelerating NDC implementation or enhancing NDC ambition in target countries.
| Extent to which UK PACT has contributed to likely transformational change in countries supported by the programme (ICF KPI 15)* | Planned | 3.5 (rounded to 3) – not enough evidence yet to assess, or the balance of evidence is inconclusive | Completion of KPI 15 report for relevant Funds - Brazil, Colombia, Mexico, South Africa, Kenya, Indonesia | Completion of KPI 15 report for relevant Funds - Brazil, Colombia, Mexico, South Africa, Kenya, Indonesia, India, Thailand (TBC) | At least 5 Funds scoring a 4 or above (partial or substantial evidence suggesting transformational change is likely)
|  | Achieved |  | Programme aggregate score of 4 - partial evidence that suggests transformational change is likely
Source
Annual ICF KPI 15 report
OUTCOME | Outcome Indicator 1 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Approximates ICF KPI - unable to attribute results from TA programme. Disaggregation following ICF methodology (GEDSI elements in review). Projections made at project agreement/inception stage and reviewed at least once at project completion stage. | Assumptions
Implementation of models (policies, practices, tools and technologies) that deliver accelerated and ambitious emissions reductions and facilitate inclusive and resilient economies | £ Finance mobilised in support of climate action (approximates ICF KPIs 11 & 12)* | Planned | £1.026 billion* *Relates to previous indicators for finance accessed/leveraged and finance invested | 100% of projects identified as being able to report against this indicator have a completed outcome projection report | TBD | $1 billion |  | • Recipient counterparts have the lasting power to develop and implement relevant policies and practices. • Host governments and institutions retain policy priorities, commitment, and motivation around emission reductions and allocate financial and human resources accordingly. • Embassy teams continue to support stakeholders in the adoption and implementation of outputs beyond the completion of specific interventions or project support. • There is sufficient funding available to implement enhanced policies and practices.
|  | Achieved |  | £3.79 billion
Source
Adapted ICF KPI methodology - Annual Fund reporting and analysis
| Outcome Indicator 2 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Approximates ICF KPI - unable to attribute results from TA programme. Disaggregation following ICF methodology (GEDSI elements in review). Projections made at project agreement/inception stage and reviewed at least once at project completion stage.
| Installed capacity of clean energy (MW) (approximates ICF KPI 7) | Planned | N/A - new indicator for 2024 | 100% of projects identified as being able to report against this indicator have a completed outcome projection report | TBD | Not enough data yet to set target
|  | Achieved |  | Direct: 4.98 MW Indirect: 23.44 MW
Source
Adapted ICF KPI methodology - Annual Fund reporting and analysis
| Outcome Indicator 3 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Approximates ICF KPI - unable to attribute results from TA programme. Disaggregation following ICF methodology (GEDSI elements in review). Projections made at project agreement/inception stage and reviewed at least once at project completion stage.
| Number of people and social institutions with improved access to clean energy (approximates ICF KPI 2) | Planned | N/A - new indicator for 2024 | 100% of projects identified as being able to report against this indicator have a completed outcome projection report | TBD | Not enough data yet to set target
|  | Achieved |  | 4,252 individuals 1 social institution
Source
Adapted ICF KPI methodology - Annual Fund reporting and analysis
| Outcome Indicator 4 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 | Target (date) | Approximates ICF KPI - unable to attribute results from TA programme. Disaggregation following ICF methodology (GEDSI elements in review). Projections made at project agreement/inception stage and reviewed at least once at project completion stage.
| Area of land under improved sustainable land use management, including nature and forests (approximates ICF KPI 17) | Planned | N/A - new indicator for 2024 | 100% of projects identified as being able to report against this indicator have a completed outcome projection report | TBD | 50,000 Ha (subject to revision when new data becomes available)
|  | Achieved |  | Direct: 37,556 ha Indirect: 375,389 ha
Source
Adapted ICF KPI methodology - Annual Fund reporting and analysis
| Outcome Indicator 5 |  | Baseline (2024) | Milestone 1 | Milestone 2 (2026) | Target (2027) | Clean and sustainable mobility solutions includes low or no-emissions transportation, including active mobility solutions. Disaggregation by age, gender, disability or marginalised status (context specific) as available. Projections made at project agreement/inception stage and reviewed at least once at project completion stage.
| # and description of cases of improved access to clean and sustainable mobility solutions and more resilient cities | Planned | N/A - new indicator for 2024 | 1 - case study capturing the results and impact of the closing Future Cities portfolio in Indonesia | 1 | 3 - case studies capturing the outcomes of the India, Indonesia and Thailand sustainable mobility portfolios
|  | Achieved |  | 1 - case study capturing the results and impact of the closing Future Cities portfolio in Indonesia
Source
UK PACT case study that includes contribution assessment to capture the influence of UK PACT support.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO (%)
INPUTS (HR) | FCDO (FTEs)
INTERMEDIATE OUTCOME | Intermediate Outcome Indicator 1 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Definition & Disaggregation | Assumptions
Adoption of enhanced models (policies, practices, tools and technologies) and capabilities that deliver more ambitious, sustained and inclusive action on emissions reduction. | # and description of new or enhanced policies, practices, tools or technologies with a projected emissions reduction or climate change mitigation impact, where there is a demonstrable contribution from UK PACT (includes ICF TA KPI 3)* | Planned | 28 | 40 | 50 | 60 | Should include indication of sustainability of adoption of TA outputs: e.g. a policy signed or ratified, new or enhanced practices, tools and technologies which have been adopted within standard operating procedures or organisational guidelines or processes, etc. Should document GEDSI and poverty alleviation impacts. Projections made at both project agreement/inception and project completion stage. | • The programme’s outputs remain applicable, relevant, and useful to their intended beneficiaries in their intended contexts. • Recipients of the programme’s outputs have the necessary authority, access, resources and motivation to enable output adoption within new policies and practices. • Embassy teams continue to support stakeholders in the adoption and implementation of outputs beyond the completion of specific interventions or project support.
|  | Achieved |  | 72 (53 TA KPI 3)
Source
Project reporting and UK PACT case study that includes contribution assessment to capture the influence of UK PACT support.
| Intermediate Outcome Indicator 2 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (date) | Capacities may relate to institutional and technical knowledge, governance, management capabilities, external relations and stakeholder engagement, GEDSI capabilities, financial resources and/or human resources. Requirement for institutional capacity assessments at project baseline and endline.
| # and description of cases of organizational or institutional change in capacities where there is a demonstrable contribution from UK PACT | Planned | N/A - new indicator for 2024 | Establishment of institutional capacity assessment scorecard | 5 | 10
|  | Achieved |  | 5 cases of institutional strengthening reported across 5 Funds
Source
Institutional Capacity Assessment Scorecard and UK PACT case study that includes contribution assessment to capture the influence of UK PACT support.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Definition & Disaggregation | Assumptions
Skills enhanced and capacities built to improve climate action | # and description of cases of skills and knowledge enhanced to deliver improved climate action | Planned | N/A - new indicator for 2024 Under previous logframe, 491 unique project outputs were reported in this category | 5 cases; and identification of cases for 25/26 reporting. Evidence within selected case studies demonstrates progress on capacity and capability building across the programme. (*66 unique project outputs planned in this category for FY24/25) | 10 cases; and identification of cases for 26/27 reporting. Evidence within selected case studies demonstrates progress on capacity and capability building across the programme. (*36 unique project outputs planned in this category for FY25/26) | 20 cases Evidence within selected case studies demonstrates progress on capacity and capability building across the programme. (*22 unique project outputs planned in this category for FY26/27) | Skills or knowledge enhanced as a result of the programme’s support through trainings undertaken, and considering individual responses given in follow-up training questionnaires. Should document GEDSI and poverty alleviation considerations. Cases projected at project agreement/inception stage. Cases selected for reporting each year based on maturity of project, significance of the result and learning potential, and ensuring representative coverage across Funds/geographies, project type (grant or expert deployment) and sectors. | • Assumes post have ability to effectively engage counterparts and that demand is correctly identified. • Technical expertise are sufficiently skilled, resourced, and supported to deliver value. • There is a sufficient ecosystem of organisations to collaborate with and deliver effective projects. • In-country actors work cooperatively and complement each other.
|  | Achieved |  | 10 case studies spanning six Funds and all five UK PACT priority sectors provide evidence of strengthened skills and capacities among a diverse range of stakeholders. (76 unique project outputs delivered in this category in FY24-25)
Source
UK PACT case study that includes contribution assessment to capture the influence of UK PACT support.
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Disaggregated by gender, geography, age, disability and organisation type.
25 | Number of individuals and organisations supported by UK PACT (ICF TA KPI 2) | Planned | 119,024 individuals (55,823 male; 47,005 female; 16,196 unknown) 456 organisations | 140,000 individuals 500 organisations (not targets - estimates based on previous years results) | 160,000 individuals 550 organisations (not targets - estimates based on previous years results) | 175,000 individuals 600 organisations (not targets - estimates based on previous years results)
|  | Achieved |  | 30,280 Individuals 531 Organisations
|  | Source | [5 empty] | RISK RATING
Project milestone reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Definition & Disaggregation | Assumption
Innovative models, including policy, accelerated and/or piloted to deliver improved climate action | # and description of cases where new tools, technologies, or best practices to deliver improved climate action have been supported and/or piloted | Planned | N/A - new indicator for 2024 Under previous logframe, 76 unique project outputs were reported in this category | 5 cases; and identification of cases for 25/26 reporting. Evidence within selected case studies demonstrates progress on the development and roll out of innovations to deliver improved climate mitigation results across the programme. (*67 unique project outputs planned in this category for FY24/25) | 10 cases; and identification of cases for 26/27 reporting. Evidence within selected case studies demonstrates progress on the development and roll out of innovations to deliver improved climate mitigation results across the programme. (*35 unique project outputs planned in this category for FY25/26) | 20 cases Evidence within selected case studies demonstrates progress on the development and roll out of innovations to deliver improved climate mitigation results across the programme. (*26 unique project outputs planned in this category for FY26/27) | Tools, technologies or best practices applicable in the public, private or third sectors. Should document GEDSI and poverty alleviation considerations. Cases projected at project agreement/inception stage. Cases selected for reporting each year based on maturity of project, significance of the result and learning potential, and ensuring representative coverage across Funds/geographies, project type (grant or expert deployment) and sectors. | • Assumes post have ability to effectively engage counterparts and that demand is correctly identified. • Technical expertise are sufficiently skilled, resourced, and supported to deliver value. • There is a sufficient ecosystem of organisations to collaborate with and deliver effective projects. • In-country actors work cooperatively and complement each other.
|  | Achieved |  | 9 cases reported across five Funds in the energy, nature and mobility sectors of new tools, technologies, or best practices to deliver improved climate action being supported and/or piloted. (84 unique project outputs delivered in this category in FY24-25)
Source
UK PACT case study that includes contribution assessment to capture the influence of UK PACT support.
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Policies are defined as any law, rule, or regulation created to reduce, or that can contribute to reducing, carbon emissions in the public sector. Should document GEDSI and poverty alleviation considerations. Cases projected at project agreement/inception stage. Cases selected for reporting each year based on maturity of project, significance of the result and learning potential, and ensuring representative coverage across Funds/geographies, project type (grant or expert deployment) and sectors.
35 | # and description of cases of policy processes that have been informed or supported by recommendations produced through UK PACT | Planned | N/A - new indicator for 2024 Under previous logframe, 416 unique project outputs were reported in this category | 5 cases; and identification of cases for 25/26 reporting. Evidence within selected case studies demonstrates how recommendations produced under UK PACT are set to influence or inform climate policy development across the programme. (for unique project outputs in this category see output indicator 2.1) | 10 cases; and identification of cases for 26/27 reporting. Evidence within selected case studies demonstrates how recommendations produced under UK PACT are set to influence or inform climate policy development across the programme. (for unique project outputs in this category see output indicator 2.1) | 20 cases Evidence within selected case studies demonstrates how recommendations produced under UK PACT are set to influence or inform climate policy development across the programme. (for unique project outputs in this category see output indicator 2.1)
|  | Achieved |  | 7 cases reported across six Funds in the climate policy, green finance, nature and mobility sectors of policy processes having been informed or supported by recommendations produced through UK PACT (for unique project outputs in this category see output indicator 2.1 above)
|  | Source | [5 empty] | RISK RATING
UK PACT case study that includes contribution assessment to capture the influence of UK PACT support.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Definition & Disaggregation | Assumptions
Knowledge, evidence and learning generated and shared, and policies and practices informed | # and description of cases of policy processes or practices linked to climate mitigation that have been supported or informed by UK PACT research, knowledge and evidence generation | Planned | N/A - new indicator for 2024 Under previous logframe, 470 unique project outputs were reported in this category | 5 cases; and identification of cases for 25/26 reporting. Evidence within selected case studies demonstrates how new research, knowledge or evidence developed under the programme will be or is being applied to inform climate action. (*145 unique project outputs planned in this category for FY24/25) | 10 cases; and identification of cases for 26/27 reporting. Evidence within selected case studies demonstrates how new research, knowledge or evidence developed under the programme will be or is being applied to inform climate action. (*87 unique project outputs planned in this category for FY25/26) | 20 cases. Evidence within selected case studies demonstrates how new research, knowledge or evidence developed under the programme will be or is being applied to inform climate action. (*29 unique project outputs planned in this category for FY26/27) | Tracks the development and dissemination of new research, evidence and knowledge to support climate mitigation and adaptation policy and action. May include research papers, reports, feasibility studies, evidence reviews, and so on. Should document GEDSI and poverty alleviation considerations. Cases projected at project agreement/inception stage. Cases selected for reporting each year based on maturity of project, significance of the result and learning potential, and ensuring representative coverage across Funds/geographies, project type (grant or expert deployment) and sectors. | • Assumes post have ability to effectively engage counterparts and that demand is correctly identified. • Technical expertise are sufficiently skilled, resourced, and supported to deliver value. • There is a sufficient ecosystem of organisations to collaborate with and deliver effective projects. • In-country actors work cooperatively and complement each other.
|  | Achieved |  | 6 case studies across four UK PACT country funds—spanning the Green Finance, Energy, and Mobility sectors—illustrate how UK PACT has generated new evidence, knowledge, and insights through targeted research and analysis. This work has directly informed the design and implementation of climate policies and strategies, contributing to more effective and inclusive climate action (131 unique project outputs delivered in this category in FY24-25)
Source
UK PACT case study that includes contribution assessment to capture the influence of UK PACT support.
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Tracks the development and dissemination of learning-focussed knowledge and communication products by the UK PACT programme, that capture and communicate learning and case studies on best practices across multiple projects, funds and/or sectors in support of further replication, scaling or investment. Contributes to Contract KPI 5 on Learning.
20 | # and description of cross-project, cross-fund or cross-programme knowledge and communication products generated and disseminated by the programme | Planned | N/A - new indicator for 2024 | 4 | 8 | 12
|  | Achieved |  | 6 products developed: case study slide pack for COP29; Adaptation & Biodiversity Taxonomy and Guidance; and four Sector Outcome & Learning Reports in Energy, Green Finance, Nature and Climate Policy.
|  | Source | [5 empty] | RISK RATING
Quarterly and Annual Fund and Programme Reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Definition & Disaggregation | Assumption
Partnerships and networks established and strengthened, and policies and practices informed | # and description of cases of policy processes or practices linked to climate mitigation that have been supported or informed as a result of UK PACT convening and partnering activities | Planned | N/A - new indicator for 2024 Under previous logframe, 159 unique project outputs were reported in this category | 5 cases; and identification of cases for 25/26 reporting. Evidence within selected case studies demonstrates progress on the establishment or strengthening of multi-stakeholder partnerships and networks to deliver improved climate action. (*25 unique project outputs planned in this category for FY24/25) | 8 cases; and identification of cases for 26/27 reporting. Evidence within selected case studies demonstrates progress on the establishment or strengthening of multi-stakeholder partnerships and networks to deliver improved climate action. (*15 unique project outputs planned in this category for FY25/26) | 12 cases Evidence within selected case studies demonstrates progress on the establishment or strengthening of multi-stakeholder partnerships and networks to deliver improved climate action. (*18 unique project outputs planned in this category for FY26/27) | Convening and partnering activities may involve developing new partnerships and networks or strengthening existing ones. Reporting supported through a collaboration quality assessment scorecard. Should document GEDSI and poverty alleviation considerations. Cases projected at project agreement/inception stage. Cases selected for reporting each year based on maturity of project, significance of the result and learning potential, and ensuring representative coverage across Funds/geographies, project type (grant or expert deployment) and sectors. | • Assumes post have ability to effectively engage counterparts and that demand is correctly identified. • Technical expertise are sufficiently skilled, resourced, and supported to deliver value. • There is a sufficient ecosystem of organisations to collaborate with and deliver effective projects. • In-country actors work cooperatively and complement each other.
|  | Achieved |  | 7 case studies across five UK PACT country funds in the Green Finance, Climate Policy, and Energy sectors illustrate how projects have actively convened stakeholders around shared priorities—facilitating collaboration, consensus-building, and the co-creation of knowledge to inform the design and delivery of new climate policies and strategies (28 unique project outputs were delivered in this category in FY24-25)
Source
UK PACT case study that includes contribution assessment to capture the influence of UK PACT support.
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Counts the number of learning and communication focussed activities and events that bring together multiple projects, portfolios and/or funds, delivered by the UK PACT programme. These may also involve the participation of stakeholders external to the UK PACT programme (e.g. from other HMG programmes). Contributes to Contract KPI 5 on Learning.
20 | # and description of cross-project, cross-fund or cross-programme convening activities or events delivered by the programme | Planned | N/A - new indicator for 2024 | 4 | 8 | 12
|  | Achieved |  | 7 events delivered: including portfolio cross-learning events/workshops in Kenya, Indonesia, Colombia and Mexico; panel moderation at biodiversity COP16 in Cali, Colombia; and the relaunch of the GEDSI learning and leadership webinar series.
|  | Source | [5 empty] | RISK RATING
Annual Fund and Programme Reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
* will be included in FCDO ICF indicator data
* unique project outputs calculated on an ongoing basis as new projects enter into the portfolio

## Non-LF Indicators
CROSS-CUTTING INDICATORS | Cross-Cutting Indicator 1 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Definition & Disaggregation | Assumption
Additional programme indicators monitoring strategic fund design and implementation objectives. | # of fund strategies active through associated implementation plan (corresponds to ICF TA KPI 1) | Planned |  | 12 | 15 | 15 | Fund Implementation Plan and Costed Workplan which have been agreed with FCDO. | • Assumes post have ability to effectively engage counterparts and that demand is correctly identified. • Technical expertise are sufficiently skilled, resourced, and supported to deliver value. • There is a sufficient ecosystem of organisations to collaborate with and deliver effective projects. • In-country actors work cooperatively and complement each other. • Implementing partners and experts are provided with clear guidance and support on output and delivery expectations.
|  | Achieved |  | 12
Source
Fund reporting data
| Cross-Cutting Indicator 2 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (2027) | Aligns with contract KPI 1B. 'Effective progress' rated green - green/amber or above on project delivery progress. Disaggregated by Fund.
| % of grant-funded projects rated as “making effective progress” against milestones (corresponds to contract KPI 1B) | Planned |  | >85% | >85% | >85%
Achieved
Source
Fund reporting data
| Cross-Cutting Indicator 3 |  | Baseline (2024) | Milestone 1 (2025) | Milestone 2 (2026) | Target (date) | Assessed and rated on the UK PACT GEDSI continuum at project agreement/inception stage. Re-assessed at project completion.
| % of projects rated as GEDSI empowering or transformative | Planned
Achieved
Source
Fund reporting data

## ICF KPIs
ICF KPIs – where they are located in the results framework
ICF KPI | RF area
KPI 15 – Extent to which contributes to likely Transformational Change | Impact
TA KPI 5 – Volume of emissions reductions avoided or supported by ICF TA | Impact
KPIs 11 & 12 – Public and private finance mobilised (approximate) | Outcome
KPI 2 – People and social institutions with improved clean energy access (approximate) | Outcome
KPI 7 – Installed capacity of clean energy (approximate) | Outcome
KPI 17 – Land brought under improved sustainable management (approximate) | Outcome
TA KPI 3 – Climate policies informed by ICF TA | Intermediate Outcome
TA KPI 1 – Countries supported by ICF TA | Cross-Cutting Indicator
TA KPI 2 – Individuals and organisations informed by ICF TA | Output 2
https://www.gov.uk/government/publications/uk-climate-finance-results

## LF checklist
UK PACT
AR due date | 2025-07-01
Lead | Aline Moore
Do the milestones align to the Annual Review due date? | Yes
Are all sections complete, including FCDO inputs, assumptions etc? | FCDO inputs to be completed.
Is there a change log? | Yes
Is the logframe consistent with the Theory of Change? | Yes
Is the Results chain clear and logical? | Yes
Do the impact indicators measure long term goals to which the project contributes? | Yes. Impact Indicators included to measure GHG emissions, contribution to acceleration of NDC implementation or increase in NDC ambition, contribution to transformational change.
Do the outcome indicators measure what will change and who will benefit? | Yes. Outcome indicators are a mix of qualitative and quantitative indicators, reflecting the downstream impacts of policy and practice implementation, and the need for amplification of UK PACT results through replication and scaling pathways in order to contribute to transformational change goals. The adoption of new policies and practices is captured under an Intermediate Outcome category, given the relatively large jump between UK PACT output and outcome areas.
Do the output indicators measure the tangible services or facilities (results of your activities) that will be delivered by the project? | Yes. Output indicators capture results of activities delivered both by projects (grants and expert deployments) and by the programme itself (fund design, management, learning and collaboration).
Are all indicators relevant to the results chain? | Yes.
Are all indicators clearly defined and measurable? | Yes. Detailed methodology and verification templates to be developed during pilot phase.
If relevant, can you include indicators which contribute towards ICF reporting? | ICF TA KPIs 1, 2, 3 and 5 and ICF KPI 15 are all included in the logframe. Approximate indicators for ICF KPIs 2, 7, 11, 12 and 17 are also included.
Have you considered using standard indicators / best practice indicators / learning from other projects? | Yes. Methodologies for potential sub-indicators (case study data points) related to sustainable mobility and green jobs will draw on best practices from ITDP, EC, ILO and UN reporting.
Are baselines included for all indicators? | Baselines, milestones and targets TBD
Are the targets and milestones realistic and achievable? Do the targets take into account time for project mobilization? | Baselines, milestones and targets TBD
Is the logframe useful for assessing the VfM of the programme as a whole? If not what is missing and should be monitored elsewhere at Annual Review? Are there economy VfM indicators | A draft VfM approach has been outlined in the M&L strategy, and is reflected in the learning agenda and benefits tracker. Additional VfM indicators will be developed to track economy criteria.
Is the logframe gender / equality sensitive? Is data disaggregated by sex or other relevant variables (age, disability, inequality, migratory status, geographic area, other) to support progress on Leave No-One Behind? | Yes - disaggregation has been included wherever possible. Specific indicators measuring GEDSI results have also been included.
Is source information clear and based on robust data sources, including data periodicity and availability, who will collect and report? [nb flag if government data is used to report on any indicators] | Yes. Detailed methodology and verification templates to be developed during pilot phase.
Are qualitative indicators used where appropriate? [nb Think about how the results / targets incentivises the programme implementers] | Yes, qualitative case-based reporting is used throughout the logframe in order to capture learning and reflect the nuanced nature of capacity building and policy support work.
Comments, any actions taken and next steps | First draft completed July 2024. Detailed methodologies and verification templates to be completed once approved for implementation.

## Change log
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | Rationale | AUTHOR | DATE
1
2
3
4
5
6
7
8
9
10