## Annual Review – FINAL WITH REDACTIONS

Title: Ukraine Humanitarian Response Programme
Programme Value £ (full life): FY 21/22: £54m; FY 22/23: £166m; FY 23/24: £137m. Total (FY 21/22, 22/23 & 23/24): £357m		Review date: / 15 September 2024
Programme Code: 301497	AMP start date: 24/02/2022	AMP end date: 31/03/2025

Year	2023	2024
Overall Output Score	A	A
Risk Rating

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301497 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301497 Documents (fcdo.gov.uk)

Contents

A Summary and Overview
B Theory of Change and Progress towards Outcomes
C Detailed Output Scoring
Output 1	Ensuring protection and prioritisation of the most vulnerable by using our funding and advocacy to drive effectiveness in the international humanitarian response
Output 2	Promoting access, inclusion and respect for IHL by working diplomatically and via technical engagement with the humanitarian system
Output 3	Promoting sustainable recovery by developing humanitarian-development synergies to ensure we build government capacity to respond
Output 4	Developing a more localised response, harnessing Ukrainian capacities by more equitably balancing funding of the international response with support to local actors
Output 5	Maintaining flexibility, scanning the horizon, and adapting to evolving priorities and emerging risks should humanitarian needs spike
Output 6	Moldova

D Value for Money
E Risk
F Programme Management: Delivery, Commercial and Financial performance
G Monitoring, evidence and learning
ANNEX A: Recommendations
ANNEX B: Breakdown of funding by partner
A. SUMMARY AND OVERVIEW

Context

A year after Russia’s full-scale invasion of Ukraine, the frontline extended over 1,200 kilometres, cutting across the Kherson, Zaporizhzhia, Donetsk, Luhansk, and Kharkiv oblasts. The much-anticipated Ukrainian counteroffensive, launched in June 2023 and continuing through December, fell short of reclaiming Russian-occupied territories in the south and east. The conflict has evolved into a war of attrition, marked by entrenched defensive lines on both sides. Drones, electronic warfare, artillery, trenches, and extensive minefields dominate the battlefield. The battle for Bakhmut, which ended in May 2023 after more than a year of fighting and soldier fatalities estimated to be in the tens of thousands, stands as one of Europe’s bloodiest confrontations since World War II. Humanitarian access across the frontlines remains severely restricted, particularly in Russian-controlled areas.

The destruction of the Kakhovka Dam in June 2023 – widely attributed to Russian forces – has devastating humanitarian and environmental consequences, underscoring the ongoing risk of high-impact incidents. The reporting period concluded with a renewed wave of large-scale Russian attacks targeting Ukraine’s energy infrastructure. By June 2024, 73% of Ukraine’s thermal power plants and 20 hydroelectric units were rendered inoperative. At the time of writing, the prospect of a just and sustainable peace remains distant.

The civilian toll of the war remains severe. As of January 2024, the United Nations estimated that 14.6 million people – around 40% of Ukraine’s population – needed humanitarian assistance, with $3.1 billion USD requested to support 8.4 million of them. Frontline communities were identified as the most acutely affected, though signs of growing hardship were evident across the country. Nearly 4 million people remain internally displaced, with over 100,000 of the most vulnerable residing in collective centres. Humanitarian need in Ukraine is now protracted. The number of Ukrainian refugees in Europe has remained relatively stable at 6.4 million. Moldova, one of Europe’s poorest countries, continues to host approximately 127,000 registered refugees, many of whom are among the most vulnerable.

Despite the ongoing war, Ukraine’s economy showed signs of recovery in 2023. Following a sharp 29% contraction in 2022, GDP grew by 5.3% in 2023. However, the scale of recovery and reconstruction needed remains daunting. According to the World Bank’s updated Recovery and Reconstruction Needs Assessment, the total cost is now estimated at $486 billion. The most pressing challenges are in housing, energy, commerce, livelihoods, and agriculture. Education and healthcare services remain disrupted. While the Ukrainian government continues to provide social protection and essential services, these systems are under immense strain and heavily reliant on external fiscal support.

The programme

Following ministerial approval to extend the programme, Year 2 saw a refinement of both activities and geographic scope. The programme shifted from broad-based appeal funding across Ukraine and the wider region to a more focused set of tailored partnerships operating exclusively in Ukraine and Moldova. While the overarching objectives – delivering life-saving assistance and protection to the most vulnerable and at-risk populations – remained unchanged, a dedicated programme strategy was developed to guide implementation. This strategy balances structured planning with the flexibility needed to adapt to a highly dynamic and unpredictable context. The expected outcomes of the programme remained consistent with those set in Year 1. Further details on the Year 2 strategy and the rationale for partner selection are provided in Section B.

Total spend for the programme in this review period was £137,481,528 GBP. Headline results are set out at paragraph 29. A simplified overview of spend by partner is set out in the table below:

Partner	Spend (£M)
WHO (including Humanity & Inclusion)	2.7
Women’s Peace & Humanitarian Fund (WPHF)	3
OCHA & Ukraine Humanitarian Fund (UHF)	37.1
Red Cross Movement	40.1
Standby Partnerships	0.4
Nonviolent Peaceforce	7.4
IOM	17.8
STAAR	1.3
Mercy Corps	16.5
ACAPS	0.7
WFP (Moldova)	3
UNFPA (Moldova)	3
UNICEF (Moldova)	4.5

In October 2023 a further – and final – extension was approved by Director EECAD for a further financial year (FY24/25). This was to provide a bridge to a multi-year programme which was under development. The new business case was endorsed by Ministers in August 2024 and the new programme is expected to commence in October 2024.

Overall score and summary supporting narrative

This review examines the second year of FCDO humanitarian programming at scale in Ukraine. While no longer operating in the emergency context which characterised year one, the trajectory of war in Ukraine has remained difficult to predict. For example, less territory was reclaimed by Ukraine than was hoped in the counter-offensive; the unanticipated destruction of the Kakhovka Dam, as well as the renewal of mass attacks on Ukraine’s energy infrastructure, meant adopting a flexible approach as needed to respond spikes in needs. This, and the substantial changes in geographic focus and the move away from appeal-based funding detailed above, means it is difficult to make a meaningful comparison of performance between years one and two. Progress was made in further establishing standard programming tools, such as a unified logframe, but these are not yet mature enough to support a more scientific and holistic assessment of achievement across the programme.

The review was conducted by the programme team drawing on evidence from ongoing partner engagement, partner reporting, FCDO monitoring visits where these were possible, and third-party monitoring. Security restrictions have prevented the programme team from interviewing beneficiaries in Ukraine as part of this review, but this has been mitigated by the third-party monitoring which was designed with these restrictions in mind. An external reviewer brought additional constructive challenge and outside perspective to strengthen conclusions. The programme was also examined by FCDO’s Internal Audit Department and by ICAI in its rapid review of HMG’s non-military support to Ukraine. This review has drawn on those findings.

The overall score awarded for the second year of the programme is ‘A’. This reflects that implementation is on track, with all outputs meeting or exceeding expectations. Detail on the performance against targets and achievements is set out in the output summaries in Section C. Critically for a context which continues to be characterised by uncertainty, the programme has proven agile and adaptive against new threats.

Major lessons and recommendations for the year ahead

Lessons learned and recommendations can be found at the end of each section, which are then consolidated in Annex A. For the purposes of this section, more holistic programme lessons are captured. Key lessons and areas for strategic reflection, with a focus on Ukraine, are as follows:

- Further strategy development is needed to support a gradual and sustainable transition from humanitarian assistance to recovery and development, where conditions allow. Humanitarian need in Ukraine is now protracted, and sustainable solutions are needed. The UK is already advancing programmes in Ukraine focused on economic growth and social recovery, now in late design or early implementation stages. To maximise impact, FCDO should invest in shaping a clear, forward-looking vision for supporting vulnerable populations through both Ukrainian government systems and inclusive economic development. This vision must be realistic about timelines, institutional capacity, and critical dependencies. Experience of the Perekhid Initiative highlights the complexity of this transition. Success will depend on coordinated action across donors and Ukrainian institutions, spanning multiple sectors and strands of programming. A shared strategy and unified direction will be essential to ensure coherence, avoid duplication, and deliver meaningful results in the shortest possible time.
  [note] The Perekhid Initiative is a technical assistance program in Ukraine that aims to set the foundation for the transition of humanitarian cash to delivery through Ukraine’s social protection systems. Its goal is to make sure that people affected by the war—especially vulnerable groups like pensioners, people with disabilities, and low-income families—receive long-term, coordinated support by gradually shifting emergency aid into more stable, government-run assistance programs.
- In Moldova, the humanitarian - development nexus transition should continue to focus on ensuring appropriate integration of refugees with Temporary Protection or other legal status into the Government of Moldova’s national systems and service provision. This will be particularly important for Social Protection, Education, and Health, where strengthening national systems can pay dividends in improving support to both vulnerable Moldovans and Ukrainian refugees. Building shock-responsiveness into national systems, especially Social Protection, will help to bolster Moldova’s resilience to future crises or spikes in need.
- As funding declines, the humanitarian response must prepare for tougher choices and sharpen its priorities. In 2022 and 2023, the response in Ukraine benefited from exceptionally strong donor support. This enabled humanitarian actors to extend beyond traditional life-saving activities into areas of recovery and poverty alleviation. While this expansion has brought clear benefits, it also raises concerns about sustainability and the expectations it has created. Looking ahead to 2025, the funding outlook is far more uncertain, with major donors expected to significantly scale back their contributions. This calls for immediate reflection on how to operate with fewer resources and a realistic acknowledgment that substantial cuts will likely require a step back from recovery-focused programming.

Humanitarian actors must refocus on core mandate, prioritising life-saving and harm-reduction interventions over broader efforts. At the same time, a coordinated dialogue with development actors is essential to ensure continuity of support and that no one is left behind. Within the humanitarian sphere, there must be a deliberate effort to make the cash-based response more sustainable and better aligned with national social protection systems. Rationalisation of the response will also be necessary - a reduction in the number of operational actors is inevitable.

The tension between the ambition for localisation and the realities of delivery remains a persistent challenge. Despite strong commitments, most funding continues to flow through traditional international humanitarian channels. FCDO has faced difficulties in advancing direct funding to local actors – partly due to stringent risk management requirements, but also because of the limitations imposed by short programme and budget cycles. Annual or shorter implementation timeframes have significantly constrained progress on this agenda. Nonetheless, within these constraints, FCDO has made meaningful strides. Partnerships with Mercy Corps and the HAVEN consortium, as well as support for the development of the Alliance of Ukrainian CSOs as a leadership and advocacy platform, represent important steps forward. Unlocking multi-year budgets remains the critical enabler for strategic progress on direct funding. In the meantime, FCDO should strengthen its approach by improving metrics – particularly tracking how funding reaches Ukrainian NGOs – and by investing in evidence generation and learning to inform future localisation efforts.

Accountability to Affected Populations has a low profile within the response. There is a prevailing assumption that advancing localisation will automatically lead to more accountable and inclusive aid delivery. However, evidence from other contexts suggests this is not guaranteed. One notable issue is the proliferation of feedback mechanisms – an audit identified 33 hotlines operated by INGOs alone, many of which are reportedly overstretched. This raises not only VFM concerns but also fundamental questions about the coherence and effectiveness of the response, particularly given the proliferation of organisations involved in delivering aid and cash assistance. These challenges highlight the urgent need for: more consistent and strategic attention to AAP across the response; rationalisation of cash actors and modalities, to reduce duplication and improve coordination and; streamlined and accessible feedback channels, ensuring affected populations can meaningfully engage and be heard.

While the programme has made some progress in streamlining, it still involves a large number of partnerships, many of which operate through multiple layers of sub-partners. This structure supports the localisation agenda - especially given the challenges of establishing more direct partnerships - and allows for breadth of interventions. However, the VFM of this model should be reviewed, particularly in light of the transaction costs associated with long delivery chains. As some Ukrainian NGOs grow in capacity and scale, continuing with such a complex structure will become harder to justify. There is also a need to further prioritise and consolidate partnerships. For example, the Women’s Peace and Humanitarian Fund - a new partnership this year - has faced delays in disbursement with programme team capacity too strained to provide timely constructive challenge. This highlights the importance of aligning the number of partnerships with available resources to ensure effective management. Delivery chain mapping can help identify further opportunities for rationalisation.
[note] This should extend beyond the humanitarian programme. In the course of this review it was identified another programme in the embassy was funding Women CSOs through another modality albeit with different objectives. More systematic sharing of information across programmes will help with deduplication and decision-making that preserves strategic intent.

The establishment of a unified logframe marked progress; however, target setting across partners was overcautious, the logframe was overly long, and it lacked outcome-level indicators. These issues partly reflect the significant differences between Year 1 and Year 2 of the programme, shorter implementation timeframes than initially anticipated and the challenges of setting targets in a fluid context where much was unknown. The strategic framework (outlined Section B), which guided Year 2 activities and informed the logframe, was more effective as a planning tool than as a results framework. A key constraint was limited team capacity during the logframe’s development, which coincided with the future business case design, an ICAI review, and an Internal Audit. Future logframes should build on this year’s learning by focusing on a smaller set of well-defined targets - including outcome indicators - that are regularly reviewed and updated.

Travel beyond Kyiv for programme staff has remained highly restricted. During the review period, only one visit was conducted to the east, in Poltava, despite the majority of interventions taking place in frontline oblasts. This limited access presents several challenges. While third-party monitoring helps mitigate some of these risks, it is not a substitute for direct oversight. To address these constraints while maintaining staff safety in an active conflict zone, FCDO should consider adopting approaches used in the Middle East and Africa - such as enabling travel facilitated by the Red Cross or UN agencies.
[note] For example: operational issues may go undetected; alignment with plans and standards is harder to verify; greater reliance on partner self-reporting increases the risk of bias or incomplete information; risks such as misuse of funds or safeguarding concerns are more difficult to identify; opportunities for learning and adaptation are missed, especially from community feedback; assessing outcomes and impact becomes more challenging

As the Ukraine and Moldova Humanitarian Assistance and Recovery Programme (HARP) is set to launch shortly after the completion of this Annual Review, the insights and recommendations derived from the review will directly inform and guide its implementation.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Theory of change

This business case was set up on emergency rules following the full-scale Russian invasion of Ukraine in 2022. The trajectory and presentation of humanitarian need in Ukraine has proven difficult to predict given the multi-faceted expression of Russian aggression. In Autumn 2022 Ukraine was both amid a successful counteroffensive which was reclaiming land which had been occupied by Russia and experiencing significant damage to energy infrastructure as a result of Russian mass missile and drone attacks. Assessments differed on how long Ukraine would need humanitarian support and how this should be balanced over the longer term with support for recovery and reconstruction.

Recognising this, a one-year extension to the programme was proposed as the most prudent option to avoid a break in vital humanitarian support and allow for the development of both a non-military aid strategy for Ukraine and a full business case for a future humanitarian programme (if judged necessary). Ministers agreed the recommendation on 25 April 2023.

As a programme predicated on emergency rules, the theory of change remains relatively simple aiming for outcomes of a) the basic and protection needs of people affected by the invasion in Ukraine and the region were met and b) humanitarian workers and agencies were afforded access to conflict affected populations and detainees. The original outputs were to provide life-saving assistance, protect people from violence and support the international system to coordinate the response working closely with the Government of Ukraine and regional governments.

Without deviating from what Ministers had agreed within the business case, the programme team developed a strategy to guide efforts in the second year of programming. This was undertaken as part of the transition away from crisis operations and intended to ensure the continued relevance, and increase the impact, of UKAid. The strategy was developed through a series of technical meetings to canvas inputs; external consultation with humanitarian actors and donors; and internal consultation with subject matter experts in Ukraine and the region, teams working on nascent recovery and reconstruction support, and penholders for the overarching HMG strategy toward Ukraine.

Through this process five strategic priorities, sitting within the existing theory of change, were identified. These are set out below.
- Ensuring protection and prioritisation of the most vulnerable by using FCDO funding and advocacy to drive effectiveness in the international humanitarian response.
- Promoting access, inclusion and respect for IHL by working diplomatically and via technical engagement with the humanitarian system.
- Promoting sustainable recovery by developing humanitarian-development synergies to ensure we build government capacity to respond.
- Developing a more localised response, harnessing Ukrainian and Moldovan capacities by more equitably balancing funding of the international response with support to local actors.
- Maintaining flexibility, scanning the horizon, and adapting to evolving priorities and emerging risks should humanitarian needs spike.

These strategic objectives acknowledged that there remains a substantial population in Ukraine that needs humanitarian assistance and that Russian attacks continued to pose protection risks to civilians across Ukraine. Equally, the UN-led humanitarian response in Ukraine, established from an almost standing start but now operating at scale, would need to consolidate and become more efficient and effectives as funding levels normalised. A focus on access, inclusion and respect for IHL was identified in recognition of ongoing violations of IHL by Russia and their almost complete denial of access to the most vulnerable populations, as well as risks to populations who are close to a kinetic 900km frontline. Finally, a focus on inclusion was prioritised in recognition that populations in need tended to be women, children, people with disabilities and the elderly.

Objectives on promoting sustainable recovery and developing a more localised response were aimed at setting the foundation for transition to longer-term solutions – understanding that humanitarian can be a bridge to development, but not a substitute. The strategy recognised that as a middle-income country – albeit one under significant economic stress – Ukraine has comparatively capable government institutions centrally and regionally, and saw the risks of allowing parallel systems to become entrenched. Equally, it also acknowledged that as the lines of conflict had become concentrated in the south and east, it was possible for some regions in Ukraine to move rapidly toward stabilisation, recovery and reconstruction.

Supporting a more localised response was also selected as a priority in line with the principle of ‘as local as possible, as international as necessary’. This recognised that local actors are key to increasing the reach and effectiveness of humanitarian responses – as well as a nascent but growing evidence base on the opportunities to realise significant cost savings through working through them. Beyond this, the strategy discerned the significant potential in Ukraine to advance localisation given an already active and capable civil society. With an eye toward typical trajectories of funding in humanitarian crises (i.e. declining and the overall underfunding of humanitarian responses) bolstering the efforts of local actors would help put the response on a more sustainable footing over the longer term.
[note] many of these CSOs had already pivoted their efforts to humanitarian response early and quickly established themselves as a key part of the response, particularly in last mile delivery to the most vulnerable populations.

The final objective, around maintaining flexibility and responding to emerging risks, understood that a level of uncertainty – largely relating to how Russia would execute their warfare – would persist. As such UK programming would need to retain the capability to pivot to renewed emergency response.

This strategy saw the evolution of UK support toward more targeted interventions in the second year of the programme. Geographically, focus was switched from middle-income European countries (such as Poland) and to countries, specifically Ukraine and Moldova, which would be ODA eligible over the longer term and where vulnerabilities were much higher.

Partner selection
A broad summary of the high-level shifts in the programme that resulted from the adoption of these strategic priorities is set out below.

Ukraine
Move from broad-based support to all populations in need to prioritising frontline areas where needs are most severe (primarily in the South and East of Ukraine)
Recognising risks to protection of civilians and access will endure, invest in organisations who can reach these populations and deliver specialist inclusion and protection services
Given long-term aim of delivery through Ukrainian national systems, support transition of humanitarian cash to shock responsive and inclusive social protection. In parallel, seek delivery of more humanitarian support through Ukrainian-led organisations to increase the reach, effectiveness and inclusion of the response.
Understanding the majority humanitarian funding will be channelled through a wider UN-led response, UK support to strategic enablers to reinforce overall coordination and influence aggregate humanitarian spend.

Moldova and the region
Given refugee displacement in Moldova will be long-term and the host community is vulnerable, focus on investment to strengthen national social protection systems to facilitate sustainable and integrated provision of quality of services supporting both communities.
Recognising that nearly 70% of refugees being women and girls, continue specific support to these needs, while working to ensure social protection is more inclusive and strengthening service provision to survivors of GBV.
As with Ukraine, but at a lesser scale, support to strategic enablers to reinforce overall coordination.

Existing partnerships were carefully reviewed. Some (WFP Ukraine, UNICEF Ukraine, UNHCR, International Solidarity Fund) were brought to a close. These decisions were made following consideration of fit with the emerging strategy, but also reducing geographic focus and, in some instances, a recognition that these organisations were well funded by other major donors. Partnerships with Mercy Corps (as a grant funding mechanism to support local actors) and Ukraine Red Cross Society were scaled up as part of the increased focus on localisation.
[note] The Ukraine Red Cross Society is one of the oldest humanitarian organisations in the country with an ability to respond to emergencies nationwide and an auxiliary to government. The programme team judged URCS will endure in Ukraine over the long term.

FCDO also developed a consortium (HAVEN) through Nonviolent Peaceforce with Acted and XXXXXX. This pilots models of area-based coordination which better supports coordination for local actors in specific geographies, supports the safety of volunteer collectives delivering assistance and civilian protection in areas under attack, and delivers IHL training and better data collection on contested areas. This was aimed at supporting delivery of both localisation and access strategic aims, as well as bolstering response to the most vulnerable in Ukraine.

A technical assistance initiative (PereHid) to help prepare for the transition of humanitarian cash to delivery through social protection systems was stood up in partnership with the EU and US. A similar focus on bolstering social protection – through a technical assistance initiative (Moldova and Region Technical Assistance Facility – MRTAF), alongside support through WFP, UNICEF and UNFPA – was undertaken in Moldova. IOM were also retained as a partner in Ukraine, beyond their emergency response remit, in recognition of their ability to blend support for basic needs with recovery activities. To strengthen focus on inclusion, in addition to efforts to mainstream these considerations throughout partnerships, FCDO partnered with WHO, and their downstream partners Help Age, and pledged support to the Women Peace and Humanitarian Fund, run by UN women.

Finally, to maintain flexibility to respond to contextual changes, flexibility was built into key partnerships (XXXXXX, Ukraine Red Cross, IOM and Mercy Corps) including through rapid response mechanisms. The UK also supported the OCHA-led Ukraine Humanitarian Fund which is able to fill critical gaps in the response - smoothing against the risks of earmarking – as well as respond fast to spikes in need. This modality, with support and advocacy from the UK, has been able to greatly increase support to local organisations and undertaken initiatives through them to better deliver in contested areas.

A summary of partnerships in this year of the programme, their focus and geographies and funds received from FCDO is set out Annex B.

Outcome delivery
The programme is considered to have achieved its objectives and desired outcomes. The 2024 ICAI rapid review on aid to Ukraine judged that UK ‘humanitarian support has been rapid and flexible, effectively targeting vulnerable groups and working well alongside national social protection systems’ and ‘performed well’. A selection of results reflecting this delivery are as follows:

- Nearly 400,000 people in Ukraine and Moldova receiving cash support for general or specific (sectoral) needs.
- Approximately 48,000 children supported with non-formal education and assistance to improve access to education in Ukraine and Moldova.
- In Moldova 15,764 beneficiaries from the refugee and host community benefitting from GBV safe spaces, static and mobile services and help to access GBV services. In Ukraine, 15,764 benefitting from support to tackle GBV.
- Systems strengthening support to hospitals in Ukraine, particularly for rehabilitative pathways, which have prospectively benefitted nearly 500,000 patients.
- Slightly over 3,000 livelihoods grants in Ukraine to help people affected by the war, often internally displaced, to move out of dependency.
- More than 80,000 people benefitting from in-kind support, primarily to bolster winter support and help repair damaged homes from aerial attacks.
- Repair to damaged water infrastructure that has helped clean water to be provided up to 500,000 people living in communities across the frontline.
- Mental health and psychosocial support to 32,758 beneficiaries in Ukraine and Moldova to help those managing trauma.

Future of the programme
In Autumn 2023, Director EECAD (Programmes & Recovery) agreed a no-cost extension of the programme to end FY24/25. This was agreed in recognition of the time needed to develop a successor programme and the approval timelines this entails. The successor programme will build on the lessons and recommendations captured within this review.
[note] The successor humanitarian business case is being developed alongside planned UK support for economic recovery, social recovery and reconstruction. Development in parallel has allowed for holistic planning and to maximise complementing effort across interventions.

The decision to continue with UK support for humanitarian needs in Ukraine and Moldova, at least in the near term, recognises the direct correlation between Russian aggression and warfare with humanitarian need in Ukraine. In the absence of a cessation of hostilities and a just and sustainable peace, humanitarian need will persist in Ukraine and continue to impact poor countries, such as Moldova, in the region where Ukrainian refugees are hosted. We judge that humanitarian action is needed not only to bolster Ukraine’s (and Moldova’s) resilience in the short-term but also to manage strategic risks, including those posed by an uneven or stalled recovery.

Continued support for humanitarian dovetails with UK efforts, with allies, to scale up recovery and reconstruction in Ukraine. Progress on this agenda is unlikely to be linear nor even, especially in frontline areas in the South and East of Ukraine which remain under frequent attack. Humanitarian actors, who can act fast and reach into more difficult areas, can not only meet essential needs but also promote early recovery and protect the space for more broad-based recovery when this is possible, preserving vital human capital. In parallel, programming needs to be able to adapt rapidly to changing realities and respond quickly to both improvements and deterioration of the situation on the ground. Humanitarian actors, alongside stabilisation efforts, are able to offer this.

## C. DETAILED OUTPUT SCORING

Note on Scoring Methodology
Building on the framework used to select partners, the programme team developed a unified logframe. This took each of the refreshed strategic aims (see section B, para 17) as outputs which contribute to the desired outcomes in the original business case. These outcomes are that a) the basic and protection needs of people affected by the invasion in Ukraine and the region were met and b) humanitarian workers and agencies were afforded access to conflict affected populations and detainees.

The refreshed outputs still sit within, and deliver, the original outputs agreed by Ministers. Put simply these are to: provide life-saving assistance; protect people from violence; and support the international system to coordinate the response working closely with the Government of Ukraine and other governments in the region. The determination sitting behind the new outputs is to deliver the original outputs more efficiently and effectively, while contributing where possible to a longer-term more sustainable response to vulnerability in Ukraine.

In the new scoring framework, each output – one to five – refers to a strategic objective. Outputs have been scored on the basis of results across a range of contributing partners. Some partners have contributed to multiple outputs. For the purposes of this review, Moldova has been scored as a separate output, while working broadly to the same strategic aims as the Ukraine partnerships.

The table below sets out the outputs and their weightings which were determined by advisers reflecting broad considerations of how much budget was invested to deliver under each output, but also the significance of the activities within these to delivering the desired outcomes.

	AR outputs	Weighting
1	Ensuring protection and prioritisation of the most vulnerable by using our funding and advocacy to drive effectiveness in the international humanitarian response	37%
2	Promoting access, inclusion and respect for IHL by working diplomatically and via technical engagement with the humanitarian system	14%
3	Promoting sustainable recovery by developing humanitarian-development synergies to ensure we build government capacity to respond.	9%
4	Developing a more localised response, harnessing Ukrainian capacities by more equitably balancing funding of the international response with support to local actors.	18%
5	Maintaining flexibility, scanning the horizon, and adapting to evolving priorities and emerging risks should humanitarian needs spike	12%
6	Moldova	10%

In assessing performance, the programme team and advisers have drawn on partner reporting, third party monitoring, reflections from the ICAI rapid review, field visits where possible and meetings with partners in support of Annual Review. A Humanitarian Adviser from the wider department travelled to Ukraine to support the Annual Review to offer independent challenge and external scrutiny, leading particularly on Outputs 1 and 4 and offering overarching recommendations on the programme.

The approach taken, while an improvement on the prior year, has some limitations. The strategic framework (outlined Section B), which guided Year 2 activities and informed the logframe, has proven more effective as a planning tool than as a results framework. Further to this a number of partnerships had a shorter implementation timeframe than initially intended. This was a result of both the timing of confirmed allocations of ODA for Ukraine and the region and strains on programme management capacity in the early stages of the financial year. These factors, and the differing design requirements across partnerships, resulted in a phased approach to mobilisation. Consequently, partner level logframes are not standardised across partners and do not consistently map onto a programme level framework.
[note] The programme team was initially staffed through expression of interest exercise. To stabilise resourcing for the longer term, the team were obliged to undergo recruitment for permanent staff. Given that departmental demand exceeded supply for programme managers, these roles had to be recruited externally with the time entailed for onboarding and security clearances. This exercise coincided with the destruction of the Kakhovka dam and obliged a short-term period of crisis response to these needs which further pressured available programme management resources.

Equally, the setting of indicators has proved challenging more generally due to the fluidity of the context. The war was one year old when indicators were set, and much was unknown. There has been some caution in indicator-setting which has seen a trend of overperformance across outputs. Where there was clear over-performance due to over caution we have moderated results downward. As partnerships and the overall response matures, FCDO and partners will be better placed to set more stretching targets which create impetus for more efficient and effective delivery.

Selected indicators in the logframe go some way toward expressing level of effort and partner performance but are not exhaustive. There are programme partnerships not captured within the logframe which have contributed to delivery of desired outputs and outcomes. Under relevant selections evidence from these partnerships have been included but do not contribute to output scoring.

Where we have continued unearmarked funding to appeals or pooled funds, we have not set targets in line with general practice for these modalities. In this annual review, this includes partnerships with the Ukraine Humanitarian Funds, the Women’s Peace and Humanitarian Fund and XXXXXX. Achievements, beyond those captured in the logframe, will be captured in the narrative under relevant outputs to the extent possible and more fully in the Project Completion Report. Finally third-party monitoring, humanitarian deployments and Standby partnerships have not been scored.
[note] This will be published by Summer 2025.

A note on assessments of IOM within this review
IOM were unable to provide final reporting for the period of the review in line with the FCDO-IOM MoU. According to the agreement these reports were due 30 June 2024. An extension to 13 September 2024 was offered by FCDO but the deadline was not met. IOM have explained the reason for the delay being (at the time of writing) an ongoing response to an audit which includes a forensic review of all project financials for a period which falls within the timeframe of FCDO’s annual review.

Given that IOM’s results are unconfirmed, only some indicative results are available, and the ongoing response to the internal audit which may see further adjustments of results, no indicator from IOM has been awarded more than an ‘A’ (meets expectations) even if there is reasonable evidence of overperformance. Where no indicative results have been received a grading of C (substantially did not meet expectations) has been awarded.

An addendum will be included with the Project Completion Report, which will anticipate will be published Summer 2025, will include finalised results under this partnership. FCDO programme team is engaged with IOM on the ongoing response to the internal audit findings and taking appropriate action in relation to the lapsed reporting.

Recommendations
1	Governance and logframe / Review and rationalise logframe for FY24-25 and identify a shorter set of more focused objectives. Lessons from the FY23-24 logframe to inform HARP logframe development. / Building on the IAD audit of the programme, and in preparation for the mobilisation of the successor business case, review and refresh programme governance.	March 2025 (Logframe) / October 2025 (Governance review)	Senior Programme Leads

Output Title	Ensuring protection and prioritisation of the most vulnerable by using funding and advocacy to drive effectiveness in the international humanitarian response
Output number:		1	Output Score:	A
Impact weighting (%):		37%	Weighting revised since last AR?	N/A

Indicators	Planned	Achieved	Score
1.11 [Mercy Corps] Total value of cash or vouchers for basic needs distributed to vulnerable participants in conflict affected areas in Ukraine	£7.1m	£7.4m	A
1.12 [Mercy Corps] % of MPCA participants who are over the age of 50 / *17,666 out of 37,034 MPCA recipients were over the age of 50.	20%	48%	A+
1.13 [Mercy Corps] % of partners working in South / East Ukraine that successfully applied agreed upon vulnerability and targeting criteria	80%	100%	A +
Indicators	Planned	Achieved	Score
1.21 [URCS] # of people reached with Mental Health Unit (MHU) services	13,333	1,673	C
1.22 [URCS] # of people covered by URCS' winterisation relief assistance	750,000	824,525	A+
1.23 [URCS] # of people supported through Ministry of Temporary Occupied Territories centralised payments in the retaken territories from Russian Federation	33,333	90,280	A+
1.24 [URCS] # of IDPs assisted with cash for shelter (Prykhystok) by household/family unit and number of IDPs assisted.	2129 HH / 5439 IDPs	79,785 HH / 206,055 IDPs	A+
Indicators	Planned	Achieved	Score
1.31 [IOM] # of individuals who received multi-purpose cash transfers disaggregated by age, gender and disability	10825	14063	A
1.32 [IOM] # of individuals who receive sustenance grants, disaggregated by age, gender and disability	3000	2989	B
1.33 [IOM] # of households reached with solid fuel	1000	TBC	C
Indicators	Planned	Achieved	Score
1.41 [IOM] # of individuals who receive MHPSS support, disaggregated by age, gender and disability	3000	15205	A
1.42 [IOM] # of individuals reached with health activities	1500	TBC	C
1.43 [IOM] # of individuals provided with protection assistance	400	421	A
Indicators	Planned	Achieved	Score
1.51 [ACAPS] % of survey respondents confirm that the product was useful/informative/shaped their decision making or work processes	70	82	A
1.52 [ACAPS] # of reports and datasets published / # people reached through dissemination of each product via ACAPS email campaigns and social media (people per product)	10 / 350	9 / 400	A
1.53 [ACAPS] # of joint analysis sessions held	3	2	B

Output description
This output, in simple terms, is about identifying the most vulnerable in Ukraine and meeting their most basic needs through a range of partners. During the period of the review most partners under this output have prioritised frontline areas in the South and East of Ukraine where needs are most severe, although Ukraine Red Cross had activities country wide. Support included cash and in-kind assistance to meet basic needs (including winter specific needs), small scale agricultural livelihoods support, provision of health and MHPSS services, protection case management, shelter and WASH assistance. Partners were selected for their ability to respond rapidly, flexibly and at scale to changing and emergency needs in a volatile context.

The identification and prioritisation of the most vulnerable groups were grounded in a robust evidence base, supported by specialist analysis from ACAPS (through a partnership with the British Red Cross), Mercy Corps’ internal analysis unit, IOM’s Displacement Tracking Matrix, and REACH via the HAVEN consortium. In line with FCDO’s emphasis on an inclusive and protection-sensitive response, deliberate efforts were made to enhance the inclusion and monitoring of vulnerable populations. This was achieved primarily through the selection of specialist downstream partners and by expanding access to hard-to-reach frontline areas via an increased number of local partners. For example, partnering with the Ukrainian Red Cross Society enabled national coverage through its extensive branch network, while Mercy Corps’ granting mechanism facilitated funding for local NGOs with deeper access to vulnerable communities.

This output has been scored overall an A ‘met expectations’.

Review of Indicators
The indicators under this output demonstrate a generally positive level of progress, though there are notable instances of both underachievement and overachievement. These variances are primarily due to the need to adapt activities in response to shifting needs and fluctuating resources within a volatile operational context. While such adjustments would typically be reflected in the logframe, the dual pressures of constrained programme resourcing and the urgency to respond to rapidly evolving needs have made timely updates challenging. Consequently, the overall performance assessments presented in the table above have been moderated, where appropriate, to account for these contextual factors. The following paragraphs provide further detail on specific areas of under- and over-performance.

Mercy Corps overachieved its indicators 1.11,1.12, and 1.13. The overachievement on volume of MPCA was due to savings from sub-awards (due to shorter durations of support) as well as gains through exchange rate fluctuations. Sharing the contract of the online portal for the NGO platform with other actors also generated some savings. The shifting of some workshops online, rather than in person, due to security constraints led to further savings which were then reallocated to MPCA. Mercy Corps also overachieved in the reaching people over the age of 50 with MPCA. In this instance the target was set too low given the agreed targeting criteria.

URCS significantly under achieved indicator 1.21. This was the result of a change in planned support to 11 mobile health units (MHUs) in Zakarpattia following a needs assessment which showed that the number of IDPs settling in remote areas of the oblast had significantly reduced with a consequent decrease in demand for mental health services. Part of the funding earmarked for MHUs was therefore channelled to the Kakhovka Dam response and the remaining to winter support activities. This accounts for slight overachievement in indicator 1.22.
[note] Beyond Zakarpattia programme supported two mental health units in Kyiv region. Further provision of such units in other locations in Ukraine were provided from other donor funding

Similarly, the URCS indicator 1.23 shows as significantly overachieved because the target used was set in error, it should have been 90,280 people. Indicator 1.24 was significantly overachieved because the target was set before the budget for winterisation activities received an uplift which allowed more IDPs to be supported with cash for shelter

IOM only provided indicative reporting against some indicators by the agreed deadline. As such no result has been scored more than an A. Indicative results suggest IOM overachieved the MPCA target indicator 1.31. This is likely due to the transfer of underspend on other budget lines and a reallocation agreed with FCDO. The large overachievement of the target 1.41 was possible due to a higher-than-expected demand for the MHPSS support hotline, as well as IOM’s local implementing partners being able to reach more individuals in their communities than initially anticipated, within the available budget. In this instance overachievement suggests good performance but targets will need to be revised upwards for any future support. Whilst figures were provided in the indicative reporting for activities represented by IOM indicators 1.33 and 1.42, it was not clear what the final result for each was – so these have been left as TBC.
[note] After the final extension to the reporting deadline, IOM provided an updated logframe and final report that confirmed the majority of final indicator results. IOM explained in this that they had substituted solid fuel distributions to cash for winter. They distributed cash to 3,700 households (11,349 individuals) across Dnipropetrovska, Donetska, Kharkivska, Sumska, Khersonska, and Zaporizka oblasts. IOM explained that these additional cash distributions were funded through savings from other programme sectors. It should be noted that this was not a change that FCDO authorised in advance as such the assessment for this indicator remains graded C. Discussions with IOM are ongoing and appropriate corrective action has been taken.

ACAPS exceeded targets on the percentage of survey respondents confirming that products were useful and slightly underachieved on the number of reports published and slightly overachieved number of people reached through dissemination of each product via ACAPS email. ACAPS underachieved on the number of joint analysis sessions held, but this has been rectified through a no cost extension after the period of this review.

Assessment of performance
Under this output, FCDO’s partners have delivered a comprehensive, multi-sectoral response that effectively targets the most vulnerable populations across a complex and volatile operational environment. By concentrating efforts in conflict-affected areas and prioritising access to hard-to-reach communities, the relevance and impact of UK humanitarian assistance in Ukraine have been significantly strengthened. The expansion of partnerships with local actors across the programme has further enhanced both the reach and quality of aid delivery. In addition to maintaining consistent support, partners demonstrated strong capacity to scale up emergency responses when needed and to adapt flexibly to heightened needs during the winter period and in the immediate aftermath of aerial attacks.

MPCA remains a cornerstone of high-quality support in humanitarian responses, enabling vulnerable individuals to meet urgent basic needs in a flexible and dignified manner. Mercy Corps, URCS and IOM delivered MPCA to 140,814 of the most vulnerable conflict-affected individuals through UK support, either through three-month support packages or rapid one-off payments in response to emergency shocks. The Cash Working Group standard allowance of UAH 2,200 per family member per month was revised in October 2023 to UAH 3,600 per family member per month for newly registered beneficiaries. This adjustment aligned with the updated Minimum Expenditure Basket and addressed concerns regarding the adequacy of the previous amount following significant inflation in Ukraine following the full-scale invasion – increasing the ability for households to meet their basic needs, and therefore quality of UK support.

However, this increase of support does present challenges. The overall cost of the response has increased and the gap between provision of support between social protection systems and humanitarian actors has widened as the Government of Ukraine cannot afford to adjust their payments. Equally with anticipated declines in funding for humanitarian, it is not clear whether this approach will be sustainable over the long term. More comprehensive coverage for a smaller caseload, or more modest transfers for a larger population, will need to be considered.

Similarly, there is a need for strategic reflection on the provision of cash and in-kind in both FCDO partnerships and the response. Trends in Ukraine illustrate a continuing proliferation of cash actors and, concerningly, indications in a decline in the use of MPCA despite its well evidenced benefits over in-kind support and sectoral cash. FCDO will need to, working with donors and its partners, ensure that efforts centre the beneficiary and what their needs and preferences are vs a supply-led approach. Equally, in terms of maturing effort on cash and improving the quality of assistance and project design, do more to evaluate impact of assistance on beneficiaries over the longer-term drawing on efforts from other contexts.
[note] For example, CAMEALEON in Lebanon tracks the impact of multipurpose cash assistance on Lebanon across a range of metrics: household expenditure, food security, shelter, WASH, education, employment, health and decision-making. The study measures the impact of providing short-term (less than 12 months) and long-term (more than 12 months) MPC assistance as well as discontinuation from it. The situation in Ukraine is far from analogous to Lebanon being much more geographically vast with continuing waves of displacement and short-term need, but such research and evaluation efforts will be needed to support better delivery for beneficiaries.

On inclusion, clear efforts have been made by FCDO and partners to mainstream protection and reach vulnerable groups including persons with disabilities, Roma and LGBTQAI+ as well as isolated individuals who require home based care. Mercy Corps partnered with local organisations Voice of Romni and Alliance Global, who targeted Roma and LGBTQAI+ communities respectively. Both partners worked to access these hard-to-reach communities, helping to register individuals for MPCA and provided tailored psychosocial support sessions. This has been recognised in the ICAI rapid review and there is opportunity to share learning. But there is further to go in making FCDO funded partnerships, and the humanitarian response writ large, accountable to affected populations. This means strengthening efforts to include affected communities in project design and adaptation, and ensure their preferences inform choices on modality e.g. cash, vouchers, or in-kind. Future FCDO humanitarian partnerships should also examine in more depth whether feedback mechanisms are accessible.

There is potential to strengthen the uptake and use of analysis products, and to strengthen the expansion of the analysis space to local actors drawing on their expertise. Strategic engagement from FCDO on thematic areas for analysis can support use in policy engagement and response design. Equally, reporting from partners in this annual review captures the delivery of assistance but stops short of showing the impact of that assistance, as set out above more focus is needed on developing MEL tools but this needs to be complemented by designing longer-term interventions where impact can be more easily measured.

Recommendations
2	Strategic alignment and use of analysis / ACAPS should deepen its engagement with local analysts and coordination platforms, such as the Alliance of CSOs, to foster local analytical capacity and relevance with the goal of enhancing analytical sustainability within the response.	31 March 2026	31 March 2026

Output Title	Promoting access, inclusion and respect for IHL by working diplomatically and via technical engagement with the humanitarian system
Output number:		2	Output Score:	A
Impact weighting (%):		14%	Weighting revised since last AR?	N/A

2.1 Sub output: Safety and security of local volunteer groups are increased while their humanitarian efforts are sustained.
Indicators	Planned	Achieved	Score
2.11 [Nonviolent Peaceforce] % of community members reporting safer access to essential humanitarian services	95%	100%	A+
2.12 [Nonviolent Peaceforce] % of downstream front-line service providers reporting an increased ability to deliver essential humanitarian services and facilitate civilian evacuations.	95%	100%	A+
2.2 Sub output: Improved access to training for military and military adjacent groups on International Humanitarian Law and humanitarian principles and norms.
Indicators	Planned	Achieved	Score
2.21 [Nonviolent Peaceforce] Percentage of local CSOs, volunteer groups, local administrators, and XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX / XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX / XXXXXXXXXXXXXXXXXXXX.	100%	70%	B
2.3 Sub-output: Support the development and implementation of more effective support for local entities involved in humanitarian response in frontline areas which can created linkages between humanitarian and early recovery work, and linking them to other support where needed
Indicators	Planned	Achieved	Score
2.31 [Nonviolent Peaceforce] % of CSOs demonstrating improved knowledge of protection	70%	94%	A+
2.32 [Nonviolent Peaceforce] % of employees and volunteers of selected local administration bodies in need of training on protection mainstreaming who participated in adequate training sessions	80%	83%	A+
2.4 Sub-output: To support and influence the Movement’s advocacy and communications at a national, regional and global level
Indicators	Planned	Achieved	Score
2.41 [URCS] # of external Movement events that engage stakeholders or public on the importance of the Red Pillar for Ukraine's response	5	5	A
2.5 Sub-output: Technical leadership provided to UN and humanitarian community to develop and implement a disability inclusion framework
Indicators	Planned	Achieved	Score
2.51 [WHO] Guiding framework available with technical implementation support	1	1	A
2.6 Sub-output: Support provided at community level for improved access to humanitarian health and protection services for people in need including persons with disabilities at oblast and community level.
Indicators	Planned	Achieved	Score
2.61 [HI] # of Target communities (e.g. hromadas) where steps have been taken to identify, activate or strengthen local resources that support psychosocial well-being and development.	5	7	A+
2.62 [HI] # local disability actors supported to maintain and increase capacities within disability-inclusive humanitarian action and the response in Ukraine.	1	0	C
2.7 Sub-output: Development actors supported to ensure increased disability-inclusive humanitarian action
Indicators	Planned	Achieved	Score
2.71 [HI] # of personnel of UN agencies/INGOs and NGOs have been trained to increase inclusion of persons with disabilities into humanitarian action programming	75	258	A++
2.8 Sub-output: Partner CSOs, both new and existing, are provided strategic, tailored trainings and support that enable them to respond to the essential needs among highly vulnerable population groups in Ukraine
Indicators	Planned	Achieved	Score
2.81 [Mercy Corps] Percentage of supported CSOs that are promoting gender equality and/or social inclusion,	65%	82%	A+
2.82 [Mercy Corps] Percentage of staff who understand the five key principles of protection mainstreaming.	80%	80%	A
2.83 [Mercy Corps] Percentage of pooled funds allocated to protection programming	25%	10%	B
2.84 [Mercy Corps] Number of localised GESI assessments conducted in southern and eastern Ukraine, informed by Women Led Organisations/ Organisations of Persons with Disabilities	2	2	A

Output description
Ukraine is an active war zone with extreme Russian aggression through, but not limited to, frequent shelling, and missile and drone attacks on urban centres and civilian infrastructure, as well as kinetic frontline that extends more than 900km. Access to the most war-affected areas in Ukraine is vital for the people living in the most war-affected areas; many of whom cannot easily move and have complex needs. Inclusion ensures the most socially marginalised or physically disadvantaged, often those with the deepest needs, do not miss out. Compliance with International Humanitarian Law will minimise harms to civilians and other non-combatants.

UN humanitarian response plans continue to highlight that the needs of individuals residing near the front lines and in areas under the temporary occupation by the Russian Federation are among the most acute. Humanitarian access within territories controlled by the Government of Ukraine remains generally open with the exception of kinetic frontline areas, although NGOs have noted some minor bureaucratic challenges, such as delays in issuing visas to aid workers. NGOs have also expressed increasing concern on the impact of tightened of conscription laws on humanitarian delivery – this is not a challenge that is unique to NGOs. In stark contrast, during the period under review, the Russian Federation continued to almost entirely deny humanitarian access to the areas it controls. As of April 2023, approximately 174,000 square kilometres of land were assessed to be contaminated by landmines - an area larger than the combined size of England, Wales, and Northern Ireland - with a particularly high concentration in the Kharkiv region, further complicating access efforts.

Partners contributing to delivery under this output include:

- Mercy Corps, the Ukrainian Red Cross Society, XXXXXXXXXXXX. All work at the front line, with diverse groups of people. They are well-placed to tackle issues of access and inclusion.
- WHO and Humanity & Inclusion who focus on a specific and growing population that is often excluded: the disabled.
- The HAVEN Consortium, led by the Non-Violent Peace Force. This intervention delivers a range of activities designed to support better access and adherence to IHL through a range of members. For example, ACTED provides inclusive assistance in conflict-affected areas, XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. This was a new partnership that started June 2023.
  [note] Members of the HAVEN consortium in 23/24: Nonviolent Peaceforce (Lead), Acted, XXXXXXXXX and IMPACT
- XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

This output has been scored an A overall.

Review of indicators
Most targets were achieved or exceeded. In some cases, targets have been substantially exceeded (e.g. Humanity & Inclusion’s training to increase inclusion exceeded targets by 340%) due to higher than anticipated demand from protection cluster actors. Three targets were not fulfilled. The first by XXXXXXXXXXXXX 2.21, as XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXX. The second, 2.62 by Humanity & Inclusion was not met because the partnership agreement was drafted but not yet signed. The collaboration entailed by the agreement was however well underway. In general, where targets have been exceeded, the reason is generally down to the fluidity of the context. The third, 2.83 by Mercy Corps, as the most common protection activity among new partners are trainings for psychologists or individual counselling. These activities are generally cheaper than in-kind distributions, which account for the majority of activities. The war was one year old when indicators were set, some interventions were in their first year of implementation, and much was unknown. There was a degree of caution in indicator-setting. As partnerships and the overall response matures, FCDO and partners will be better placed to set more stretching targets which create impetus for more efficient and effective delivery.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.
[note] XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Assessment of Performance
Examining performance against the key three components of this output – access, inclusion and IHL – we judge these have largely been achieved, albeit within realistic parameters.

In regard to humanitarian access this is a function of the conflict and largely out of the control of FCDO and its partners. Over the reporting period humanitarian access has declined, most notably as a result of Russian advances and taking of territory, but also because of an increasingly kinetic frontline, significant levels of mining and the high use of drones in frontline areas - some of which have killed aid workers. Russia continues to deny access to the territory it occupies.

Advocacy for improved humanitarian access from within Ukraine cannot be decisive in tackling these problems as the root cause remains Russia’s failure to comply with IHL. Little short of a strengthened and sustained diplomatic effort at the highest levels, or significant Ukrainian success on the battlefield, humanitarian access to the most severely in need will continue to be constrained and may well diminish further.

There are opportunities for more impactful advocacy within Ukraine to the government of Ukraine on the bureaucratic burdens faced by aid operators, a facet of access considerations, but donors have not yet successfully coalesced to support NGO asks in these areas. This is largely a consequence of bandwidth limitations in large complex crisis.

Examining programmatic efforts in this output, these have been more successful, particularly where they have built off findings in FCDO Third Party Monitoring. Monitoring identified a lack of security, shortage of Personal Protective Equipment, poor roads, and lack of vehicles as blockers to humanitarian access. The HAVEN consortium has given local groups personal protective equipment, fuel vouchers and training, and Mercy Corps has provided Hostile Environment Awareness Training for its partners. These help partners operate more safely when near the frontlines. Humanity & Inclusion mobile teams have also adapted their operations to redeploy when there are access problems. More broadly, the nationwide network of the Ukraine Red Cross Society and their volunteers have been well-placed to help in hard-to-reach areas. The Ukraine Humanitarian Fund, to which the UK was the biggest donor in 2023, has been able to advance some small-scale interventions in territories occupied by Russia – largely hawala style cash support – but these interventions remain complicated, high-risk and are difficult to bring to scale.

The most successful aspect of Output 2 has been on promoting inclusion. Third Party monitoring shows that all FCDO partners are making a genuine effort, but that sometimes circumstances make full inclusion difficult. To wit, limitations in time, access and resources, and the difficult circumstances in which partners are operating, make it difficult to apply the level of nuance necessary to be fully inclusive, particularly when there are multiple levels of exclusion. This is most evident in aid operations on the frontlines.

Regarding respect for International Humanitarian Law, this remains deeply challenged given how the Russian Federation continues to execute its illegal full-scale invasion of Ukraine. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Nevertheless, partners under this output (XXXXXX, Ukraine Red Cross and XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX) have and continue to advocate for adherence. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Ukraine Red Cross have developed a strong partnership with the revitalised National IHL Commission and are working with on voluntary IHL reporting with the Ukrainian Ministry of Defence. This is in close collaboration with the UK IHL Commission, through experience sharing and peer-review support. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

One area for reflection is whether training can do more to tackle the issue, highlighted by FCDO’s Third-Party Monitoring, that illustrates that some small local organisations do not distinguish between military and civilian aid. This can put aid workers and civilians at risk. Understanding on the importance of independence and impartiality of humanitarian assistance has risen markedly since February 2022 but requires continuous dialogue with responders.

Lessons
Despite the overwhelming challenges it is right that the FCDO programme team continue to make efforts on securing humanitarian access and promoting adherence to IHL. To not do so, particularly on access, would be, in effect, to abandon the most vulnerable. Advocacy on the greatest challenges to these agendas, the appalling conduct of the Russian Federation, has not born fruit. The upcoming appointment of a new UN Emergency Relief Coordinator may offer opportunity to reignite diplomatic efforts. Local advocacy could be stronger on bureaucratic impediments facing aid organisations in Ukraine – with due respect to the fact that overall access picture in the territory controlled by Ukraine being very good. Concerns on conscription remain challenging for member states to engage on, as the Ukrainian Armed Forces seek to increase the number of people serving.

Understanding constraints on making progress on access, FCDO invested in increasing local partnerships, primarily through HAVEN, Mercy Corps and the Ukraine Red Cross. This has paid dividends because local actors and volunteers have better access, particularly to communities living near the frontline. Given access challenges will continue, the programme team should continue to invest, and examine the merit, in expanding these partnerships.

On promotion of IHL through the programme, training and dissemination of information is a worthy endeavour. The next step, and a difficult one, is to assess the impact of training. How do people put their new skills into practice? What has been the impact? This is not easy, particularly with IHL, but it would be an excellent progression in the next phase. FCDO should also consider how it can work through its partners to promote better understanding on the distinction between military and humanitarian assistance and why this is important to reduce risks to aid workers.

The emphasis on inclusion in programme design consolidated through ongoing partner engagement has paid dividends. But in the dynamic and dangerous environment where FCDO’s partners work, it will continue to be difficult to get an accurate picture of needs and social exclusion. Vulnerability can change rapidly and assessors do not always have the time to undertake thorough analyses. All humanitarian actors will benefit from more work to monitor tensions in communities, which will inevitably rise as the war continues. FCDO will need to think carefully about the balance between blanket and nuanced targeting. This could be thought through by developing an approach paper on inclusion which can then guide future programming.

Recommendations
3	Advocacy on IHL / Through partner organisations (XXXXXXXXXXXXXX and URCS, but others too) deliver advocacy on humanitarian access and protection and observance of IHL. Supplement this with diplomatic engagement through BEK and FCDO. Specifically, FCDO to map: types, range, and channels of IHL, access, and protection advocacy; and to include 1-2 case studies of advocacy in action in the second HARP annual review.	30 June 2026	Humanitarian Adviser working with EECAD

Output Title	Promoting sustainable recovery by developing humanitarian-development synergies to ensure we build government capacity to respond
Output number:		3	Output Score:	A
Impact weighting (%):		9%	Weighting revised since last AR?	N/A

Sub output: Technical, coordination, piloting support to MoH and MoSP at national level on developing and implementing strategic reforms of rehabilitation and long term care services.
Indicators	Planned	Achieved	Score
3.11 [WHO] # strategic reform directions / initiatives supported with coordination, assessment, and piloting.	1	3	A +
3.2 Sub output: Technical support provided to rehabilitation facilities and partner organisations, in oblasts in eastern Ukraine
Indicators	Planned	Achieved	Score
3.21 [WHO] # oblasts supported with dedicated staff training and equipment support	6	18	A +
3.3 Sub-output: Technical support and guidance to prevent clinical complications following traumatic injury and promote improved clinical outcomes through rehabilitation and AT interventions
Indicators	Planned	Achieved	Score
3.31 [WHO] # facilities of critical national relevance supported by WHO	15	14	A
3.4 Sub-output: Creating an evidence base, which improves GoU awareness on the humanitarian-development situation, and providing advice and options for next steps which is inclusive (gender, age, disability and marginalised groups) and results in shifts in skills, behaviours and relationships.
Indicators	Planned	Achieved	Score
3.41 [STAAR] Submission and approval by the Steering Committee of the Situation Analysis, the Transition Options Analysis, Policy Recommendations, and Strategic Roadmap & Operational Framework.	All submitted and approved	Not met	B
3.42 [STAAR] Core, Ukraine-based positions filled within 12 weeks of agreement of Terms of Reference with attrition rate of no more than 33 percent and uninterrupted presence of the Team Leader in Ukraine.	100%	100%	A
3.5 Sub-output: Improved evidence-based programming and policy making by embedding data analytics consultants into the Ministry of Reintegration of Temporarily Occupied Territories.
Indicators	Planned	Achieved	Score
3.51 [IOM] # of Government of Ukraine IDP case management systems supported	1	1	A
3.6 Sub-output: To ensure disaster management preparedness across Ukraine
Indicators	Planned	Achieved	Score
3.61 [URCS] # of Disaster Risk Management (DRM) policies/procedures/ tools developed, enhanced and completed.	3	1	C
3.62 [URCS] # of regions reached on preparedness and risk reduction and recovery dissemination activities.	5	5	A
[note] Documents are in advanced stages of drafting but not submitted or approved.

Output description
Given the impacts of the full-scale invasion will extend far beyond the scope and timescale of humanitarian support, which is by its nature short-term and tactical in its emphasis, this output aims to build synergies between humanitarian support and longer-term recovery. More specifically it aims to bolster Government of Ukraine capacity to respond to the long-term vulnerability. This outcome also reflects the prioritisation of localisation in the execution of the programme and the importance of strong capacity of strengthening national systems within that agenda.

This outcome includes FCDO funding to four specialist partners WHO, IOM, URCS and STAAR. Funding was intended to:

  1. strengthen Ukrainian capacity to respond to physical rehabilitation needs of the population (WHO);
  2. provide effective case management for internally displaced people (IOM);
  3. develop robust disaster risk management preparedness policies and plans (URCS), and;
  4. support synergies between humanitarian cash responses and national social protection programmes (STAAR).

Partners were chosen for their specialisms within their respective fields and existing relationships with relevant ministries. STAAR was chosen as FCDO’s centrally manged programme for supporting Grand Bargain commitments on social protection and humanitarian cash linkages.
[note] The Grand Bargain is a 2016 agreement between major donors and humanitarian organisations aimed at improving the efficiency and effectiveness of humanitarian aid by reducing bureaucracy and increasing transparency. It committed to better linking humanitarian and development efforts.

This output has been scored an A, meeting expectations.

Review of indicators
Most indicators were achieved or overachieved, with the exception of two indicators which were moderately underachieved.

WHO overachieved on two indicators, 3.11 and 3.21, and narrowly underachieved on one 3.31. This is testament to their global and in-country leadership on the rehabilitation agenda but also reflects the challenge of developing – and delivering against - targets for activities dependent on multiple stakeholders in a complex context.

WHO provided coordination support to the Government of Ukraine with three strategic events on rehabilitation and disability inclusion [3.11]. This included a WHO-facilitated conference and Ministerial level meeting to identify further regulatory steps to develop government policies on rehabilitation and assistive technologies for 2024-26. In 2024/25, WHO supported the Ministry of Health to develop 9 new policies including on provision of assistive products for adults and children, standardised tools for assessing disability and a national strategy on deinstitutionalisation for adults in Ukraine. WHO also supported to two Summary Meetings of the Barrier-Free Council, Ukraine’s First Lady-led initiative to improve inclusivity and accessibility. The results against this indicator do not fully reflect its breadth, as support to piloting reforms was not provided.

Rehabilitation facilities in 18 oblasts were supported with dedicated staff training and equipment [3.21]. Highlights from this support included capacity strengthening of Nikopol Regional Children Rehabilitation Centre and Zaporizhzhia Children Oblast Hospital at the request of the Ministry of Health to support children with injuries and disabilities. Activities included training for rehabilitation professionals on paediatric physical therapy for children and provision of 90 hospital beds to two children’s hospitals in Dnipro and Cherkasy.

WHO also worked in collaboration with the Ministry of Education and Science and the Alliance of Public Health to deliver a pilot to provide individualised community rehabilitation support to 12 people with acquired vision loss and their caregivers. The result was an improvement of individual capacity to adapt to the environment and increase functional capacities in daily life activities. WHO supported the Ministry of Education to incorporate learnings from the pilot to inform the development of a short-term educational and support program for persons with vision loss and their families/accompanying persons. This will be incorporated into longer-term service development at the community level. In support of [3.31], WHO assisted 14 nationally critical healthcare facilities by establishing a network of non-specialised in-patient rehabilitation departments at supercluster and cluster hospitals. This was achieved through capacity building and the provision of rehabilitation and medical equipment, hospital beds, assistive products, and IT equipment. One hospital could not be supported due to ongoing reconstruction and changes in leadership – factors beyond WHO’s control.

DAI achieved indicator 3.42 through successful recruitment and retention of three members of the Perekhid Initiative Technical Assistance Facility (TAF), supporting them with onboarding, duty of care and programme management throughout the reporting year. The TAF’s Situation Analysis, the Transition Options Analysis, Policy Recommendations, and Strategic Roadmap & Operational Framework were drafted but not finalised nor submitted to the Steering Committee for approval, meaning [3.41] was only partially achieved. Delays in submission were the result of delays to recruitment of other non-FCDO funded key TAF roles, time required to respond to and resolve substantial (sometimes conflicting) feedback from the Perekhid Initiative’s Working Group members, and limited Ministry of Social Policy capacity to engage with the analysis.
[note] DAI or Development Alternatives, Inc are a global development organisation.
[note] The Perekhid Initiative is a technical assistance program in Ukraine that aims to set the foundation for the transition of humanitarian cash to delivery through Ukraine’s social protection systems. Its goal is to make sure that people affected by the war—especially vulnerable groups like pensioners, people with disabilities, and low-income families—receive long-term, coordinated support by gradually shifting emergency aid into more stable, government-run assistance programs.

IOM indicative reporting suggests strengthened the Ministry of Reintegration of Temporarily Occupied Territories’ IDP case management system [3.51] through procurement of case management software and training for staff on software usage. This enables staff to efficiently systematise, and process IDPs assistance requests received through the Ministry’s call centre and to conduct in-depth analysis of the most urgent needs and concerns of vulnerable populations. Additionally, IOM has contracted the software provider to provide two years of technical maintenance to the Ministry to promote longer-term support and sustainability.

URCS supported five regions (Chernivetska, Ivano-Frankivska, Khmelnytska, Kirovogradska and Mykolaivska) with preparedness and risk reduction and recovery dissemination activities [3.62]. From a target of three, only one Disaster Risk Management policy/procedures/tools developed, enhanced and completed by URCS [3.61]. URCS struggled to onboard new staff members and have undertaken a review of their salary scale and benefits to become more competitive as an employer. A number of workstreams were delayed as a result of these recruitment challenges including these tools. However, during the reporting period URCS developed and signed off regulations on the Emergency Operations Centre and further developed role descriptions for key roles in the centre who will now take this work forward.

Aside from the indicators listed above, other partners across the programme have strengthened synergies between humanitarian and sustainable recovery efforts. For example, through the HAVEN consortium, ACTED have been supporting the Relief Coordination Centre in Kharkiv, which works closely with local authorities to coordinate requests for support. A further example is IOM’s scoping study on Government capacity to produce and publish official statistics in compliance with concepts, methodologies and technical standards employed by EU member states – a requirement for EU membership. IOM also seconded technical data advisors to the Ministry of Social Policy to support and strengthen efforts to facilitate a sustainable transition from a humanitarian emergency response to one focused upon recovery, reconstruction and strategic resilience, as enshrined in the framework of the Perekhid Initiative.

Assessment of Performance
In crisis or conflict contexts collaboration between humanitarian and government actors can be challenging and time intensive. These challenges are compounded in Ukraine due to the protracted shock of the invasion and reduced capacity of the government to engage with the proliferation of humanitarian actors and programmes, whilst simultaneously supporting the war effort and delivering an ambitious package of government reforms. Despite this, FCDOs humanitarian partners under this output have built synergies by establishing relationships and commitments for ongoing collaboration (in some cases underpinned by MoUs or formal agreements) with key government counterparts, humanitarian and recovery partners.

Activities to build capacity to meet the most acute needs via existing government systems and institutions, notably rehabilitation of injured populations via existing healthcare facilities and case management support to IDPs via existing Ministry departments, have already begun to have a direct impact on affected populations. Reforms to government policy and procedures, as well as humanitarian policies and processes have proven more challenging to implement in the reporting period. This is symptomatic of the time, engagement and consultation necessary to complete such reforms and indicative of the need for longer-term programming to continue these processes.

In the case of the Perekhid Initiative reports, limited capacity of the Ministry of Social Policy and other recovery/development actors to engage has resulted in a skewing of the recommendations in the drafted reports towards making the humanitarian cash response more social protection-sensitive, rather than on facilitating a transition from humanitarian cash towards a shock-responsive social protection system. This, combined with the need to build consensus amongst humanitarian actors engaged in the initiative has limited the extent to which evidence and advice has been used by the Government of Ukraine, donors and agencies to inform policies, practices and programmes at this point in time.

WHO’s support for long-term care services was also delayed as initial scoping and consultation with government officials proved more complex than the partner had anticipated. However, as part of WHO’s 2024-25 activities, WHO will be collaborating with the Ministry of Social Protection in two oblasts to establish pilot projects on reorienting institution-based long-term care models towards community-based solutions, focusing on case management, multi-disciplinary work and integration between primary care and community-based long-term care to support internally displaced older persons and people with complex long-term care needs.

Lessons learned
A key lesson under this output is the importance of investing in developing strong relationships with government counterparts and the time required to understand their needs and priorities. Flexibility in approach, timelines and activities is essential to ensure that national capacity is developed in a needs-based, sustainable manner that will support sustainable recovery in the long term. This requires compromise and prioritisation of longer-term objectives (quality) over short-term outputs (quantity), which can be challenging under the funding cycles and reporting frameworks of humanitarian programming.

Arguably the initial expectations, delivery within one year, of the Perekhid Initiative were unrealistic. Such a transition in the current circumstances is a very complex endeavour that will take years. It was also inevitable that requirement to engage a large number of diverse stakeholders would create inertia. FCDO Advisers working on this output have made good progress in pushing the agenda forward, but this has required significant management behind the scenes and much convening.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Monitoring and evaluation of capacity and synergy building activities has proven challenging, limiting opportunities for course correcting and understanding the effectiveness and sustainability.

Recommendations
4	Design of capacity building interventions / Design future capacity building to factor in the need for in depth consultation to ensure alignment with government needs and priorities as well an enable flexibility to adapt to changing capacities and priorities.	April 2026	Social Development Advisors

Output Title	Developing a more localised response, harnessing Ukrainian capacities by more equitably balancing funding of the international response with support to local actors
Output number:		4	Output Score:	A+
Impact weighting (%):		18%	Weighting revised since last AR?	N/A

Sub output: Safety and security of local volunteer groups are increased while their humanitarian efforts are sustained.
Indicators	Planned	Achieved	Score
4.11 [Nonviolent Peaceforce] % of front-line service providers receiving operational support and capacity building	95%	100%	A+
4.12 [Nonviolent Peaceforce] % of staff and volunteers of front-line service providers reporting an increase in their safety and security.	95%	100%	A+
4.2 Sub output: Support the development and implementation of effective support for local entities involved in humanitarian response in frontline areas can create linkages between humanitarian and early recovery work, and linking them to other support where needed.
Indicators	Planned	Achieved	Score
4.21 [Nonviolent Peaceforce] % of beneficiary coordination structures, local CSOs, volunteer groups, and local administrations reporting better ability to identify and fill humanitarian needs and improved coordination in prioritised locations.	80%	88%	A+
4.22 [Nonviolent Peaceforce] # of pre-existing local coordination structures supported and strengthened through capacity development	1	1	A
4.23 [Nonviolent Peaceforce] # new local coordination structures set up to further pilot novel coordination methods and strengthen local responses	2	2	A
4.3 Sub-output: Partner CSOs, both new and existing, are provided strategic, tailored trainings and support that enable them to respond to the essential needs among highly vulnerable population groups in Ukraine
Indicators	Planned	Achieved	Score
4.31 [Mercy Corps] Number of tailored capacity plans delivered	4	8	A+
4.32 [Mercy Corps] Number of individuals accessing non-MPCA or RRM services offered by CSOs (without double counting across services)	33,800	93,800	A+
4.33 [Mercy Corps] Number of sub-grants disbursed to CSO partners	8	17	A+
4.4 Sub-output: To support URCS' long-term national society development
Indicators	Planned	Achieved	Score
4.41 [URCS] # of humanitarian staff and volunteers using renovated premises (total)	600	0	B

Output description
FCDO is supporting localisation of the response in Ukraine, taking a broad interpretation of the concept to include a focus on supporting interventions of local actors who are closest to communities, while supporting local authorities and national government structures where possible. This approach has been mainstreamed as much as possible throughout the programme. This output offers an assessment of these efforts at a relatively nascent stage, recognising that while Ukraine boasts significant local capacity, the response in Ukraine (through a metric of funding) is dominated by four UN organisations: WFP, UNICEF, UNHCR, and IOM. This is typical of humanitarian responses worldwide and ultimately reveals the aggregate of donor preferences.

In Ukraine, local actors embedded within their communities are essential for reaching those most in need, especially in frontline areas. Looking ahead, Ukraine presents significant opportunities for advancing localisation. As humanitarian funding is expected to decline, strengthening local capacity is key to ensuring a more sustainable response. However, building the capabilities of Ukraine’s often small local NGOs—and shifting donor practices—will take time. In response, FCDO has adopted a holistic approach to localisation, aiming to increase both the proportion and quality of funding to local organisations, whether directly or through intermediaries. This strategy also seeks to amplify local voices in response planning and invest in long-term capacity building. Importantly, it enhances inclusion and accountability to affected populations, as many local actors are specialised organisations serving marginalised or hard-to-reach groups, such as LGBTQIA+ and Roma communities.

FCDO supports local civil society organisations primarily through partnerships with Mercy Corps and the HAVEN Consortium. Mercy Corps operates a grant mechanism that funds 17 national NGOs, while the HAVEN Consortium,has supported 115 civil society organisations and volunteer groups working in frontline areas. Additionally, ACTED has strengthened four locally led coordination structures in Kharkiv, Zaporizhzhia, Mykolaiv, and Kherson. The Ukrainian Red Cross Society—a key national actor and auxiliary to the Ukrainian government—is also a partner, alongside the OCHA-managed Ukraine Humanitarian Fund and the UN Women-administered Women’s Peace and Humanitarian Fund, both of which provide grants to local actors.

Under this output Mercy Corps, Ukraine Red Cross Society and Nonviolent Peaceforce (as the grant holder for the HAVEN Consortium) are assessed. Efforts to strengthen national systems is captured in the previous section. The Ukraine Humanitarian Fund and the Women Peace and Humanitarian Fund were not set indicators in the logframe under this output (largely a consequence of a set reporting cycle that does not match FCDO’s) but some commentary is offered in this section on their success at localisation.

Under this output all indicators were achieved or over-achieved. The significant overachievement in Mercy Corps indicators is a consequence of the lack of clarity on the number of civil society organisations that would be onboarded through a call for proposals which made it difficult to set stretching targets. The pressures on the programme team in the period of the review, limited capacity to revise targets. Nevertheless, these results have now informed targets for 24/25 which should be more realistic.

This output was scored as an A+, exceeding expectations.

Assessment of Performance
All targets under this output were met or exceeded except for [4.41]. Renovation delays at the shared office meant URCS couldn’t meet its target for moving staff into the building. These delays were due to a strict procurement process, slow hiring in the procurement team, and time needed to get renovation permits. The work was finished in the next reporting period, and by August 2024, URCS and partner national societies had moved in.

FCDO has made positive progress towards its objective of promoting a more localised response working within restrictions which has made direct funding deeply challenging. This year the programme has evolved its partnerships towards an increased balance of support to local civil society actors. While not funding local partners directly, the programme expanded the CSO sub-granting mechanism with Mercy Corps, as well as establishing the HAVEN Consortium which supports a locally led, coordinated and delivered response in conflict affected areas, and the partnership with key local actor Ukraine Red Cross was added. The approach taken by FCDO’s INGO partners in working towards partner-led programming, equitable partnerships and sharing risk, as well as demonstrating flexibility, was appreciated by their partners as demonstrated in reporting and partner testimonies.

FCDO’s emphasis on localisation has enhanced frontline response capabilities and strengthened inclusion across operations. By prioritising duty of care and supporting local actors in risk mitigation, the approach has enabled safer and more effective responses in areas frequently affected by conflict within an international armed conflict context. This has also contributed to progress toward establishing common minimum standards across the response as good practice has been replicated by the Ukraine Humanitarian Fund and other programmes. Another area of success was the work through the HAVEN consortium to pilot models of area-based coordination – widely praised across the response.
[note] For example, ACTED through the HAVEN consortium supported the Relief Coordination Centre (RCC) in sustaining its coordination hub in Kharkiv and launching a new one in Zaporizhzhia. RCC coordinates humanitarian aid by working with local organisations, INGOs, the UN cluster system, and local authorities. In Kharkiv, RCC has become a key source of coordination data, widely used by humanitarian actors. ACTED’s support included training in financial and information management, enhancing RCC’s capacity and effectiveness.

Moreover, the inclusion of local actors - particularly those serving hard-to-reach populations or groups requiring specialised services - within the Mercy Corps partnership has further reinforced the portfolio’s inclusivity. Additional details on these developments are provided under Output 2.
[note] Some specific examples from the Mercy Corps examples follow. Alliance Global supported over 1,200 LGBT+ individuals through MPCA registration, psychosocial support, temporary shelter, and employment assistance. Voice of Romni provided tailored aid to Roma communities and vulnerable women, improving access to essential services for over 800 households. DOSVID distributed combined food and hygiene kits to more than 500 people with disabilities in Zaporizhzhia. Gender Club Dnipro trained 30 psychologists in bereavement care and delivered psychological support to 142 women affected by conflict-related loss.

Continued FCDO support and advocacy with the Ukraine Humanitarian Fund (UHF) to adopt a localisation strategy has yielded tangible results. A significant share of UHF funding is now directed to local actors, alongside meaningful efforts to simplify the application process for smaller organisations. In 2023, UHF allocated $36 million directly and $57 million indirectly to 13 national NGOs - over 30% of its total $181 million allocation for the year, marking an 8% increase from 2022. Additionally, a contextualised capacity assessment (a pilot intended to reduce the barriers for applying to the fund) enabled 15 more Ukrainian NGOs to access direct funding for the first time, with grants capped at $250,000.

Support provided through the Ukraine Red Cross led to the establishment of the Alliance of Ukrainian Civil Society Organisations, which has amplified the voice of local leadership within the international humanitarian response. The CSO Alliance UA has played a central role in advancing localisation in Ukraine, notably through a strategic session in December 2023 and the 2nd Annual Ukrainian Aid Leadership Conference in March 2024. These efforts culminated in a nationally endorsed localisation strategy aimed at empowering local actors in both crisis response and recovery. Continued advocacy from FCDO—with response leadership, international partners, INGOs, and UN agencies—will be essential to sustaining and reinforcing this progress.

Lessons
FCDO has to balance support to more equitably balancing funding of the international response with support to local actors with internal capacity to manage an upscale in partners. The approach taken by working through intermediaries and pooled funds has enabled this. However future funding may consider longer term deeper investments with fewer partners to build more strategic partnerships. Doing so with a greater proportion of local actors will be contingent on Ministers committing to budget certainty, most likely through the next Spending Review.

While increasing the funding share to local actors is only one metric of localisation, it would be useful to track consistently across partners to measure progress over time. Similarly comprehensive mapping of downstream partners and which partners are supported by more than one part of the portfolio e.g. through UHF and an INGO partner and will be useful in drawing out insights, particularly for the future multiyear programme. Budget visibility from UN partners is essential to understand funding flows, which should be requested in institutional partnership discussions. A short external review of localisation efforts, successes, challenges and risks in the portfolio should also be considered to inform future programming and advocacy.

FCDO’s current constraints on providing multiyear funding, coupled with occasional delays in disbursement, have resulted in subcontracted partners receiving grants with durations (sometimes significantly) shorter than one year. This has placed pressure on partners to deliver rapidly, limiting opportunities to establish longer-term, strategic partnerships and hindering efforts to support sustainable organisational development. To enhance the effectiveness and sustainability of future programming, as well as unlock more strategic progress on localisation, it is recommended that these limitations be addressed.

There is significant potential to enhance the sharing of learning on localisation and partnership approaches across FCDO humanitarian partners. This includes coordination among donors—particularly where multiple donors are funding the same local actors—and across BE Kyiv, extending beyond the humanitarian sector. Strengthening these linkages would help ensure consistent messaging on localisation is delivered both internally and externally, across all components of the response.

Learning on localisation in this programme has been built into the future HARP business case where a longer-term approach to localisation has been articulated.

Recommendations
5	Localisation / Set out headline learning on localisation in Ukraine, enablers and barriers, and BEK approach. / Discuss with Humanitarian Department (FCDO) during inward visit of BEK partners. / Track and capture in one place how funding flows through FCDO intermediaries to local actors. / Finalise comprehensive review of FCDO’s efforts on localisation across the portfolio to draw out further learning, inform future partnerships and strengthen advocacy, and present this to FCDO senior officials.	September 2025 (approach paper) / November 2025 (discuss findings) / December 2025 (funding flow tracking) / January 2026 (comprehensive paper and presentation to senior officials)	Lead Advisor and PRO

Output Title	Maintaining flexibility, scanning the horizon, and adapting to evolving priorities and emerging risks should humanitarian needs spike
Output number:		5	Output Score:	A
Impact weighting (%):		12%	Weighting revised since last AR?	N/A

5.1 Sub output: To ensure disaster management preparedness across Ukraine
Indicators	Planned	Achieved	Score
5.11 [URCS] # of Disaster Risk Management (DRM) policies/procedures/ tools developed, enhanced and completed.	3	1	B
5.12 [URCS] # of regions reached on preparedness and risk reduction and recovery dissemination activities.	5	5	A
5.2 Sub output: Lifesaving, appropriate, and timely assistance is provided to individuals in newly accessible locations. (Rapid Response Mechanism)
Indicators	Planned	Achieved	Score
5.21 [Mercy Corps] Number of households provided with NFI Kits through RRM	2250	3491	A+
5.21 [Mercy Corps] Number of individuals provided with Ready-to-Eat (RTE) Food Rations through RRM	2250	3570	A+
5.21 [Mercy Corps] Percentage of RRM interventions completed within 14 day of the completed rapid needs assessment	80%	78%	A

Output description

The humanitarian context in Ukraine is highly dynamic, with the potential for sudden shifts and spikes in needs throughout the programme’s duration. In response, the programme design in the second year of implementation sought to equip FCDO teams and partners with the tools to monitor and analyse evolving conditions and adapt their response accordingly.

The programme demonstrated strong adaptability during the review period, leveraging a combination of robust data sources and flexible response mechanisms to address evolving needs across Ukraine. Information and analysis were drawn from tools such as the IOM Displacement Tracking Matrix, REACH assessments, ACAPS secondary data reviews, Mercy Corps Data Analytics, and Palladium HSOT. These insights were paired with agile response modalities—including IOM, Mercy Corps LIVES, URCS, and OCHA’s UHF—to enable timely and targeted interventions. Most of these data and analysis services are publicly accessible, supporting broader humanitarian planning and decision-making. Collectively, these efforts aimed to ensure an evidence-based response that reflects the needs and preferences of affected communities.

In the reporting period, as well as ongoing humanitarian operations, partners also responded to the destruction of the Kakhovka Dam (June 2023), missile attacks across the country, prepared for and responded to humanitarian impacts of attacks on critical national infrastructure and compounding impacts of winter, understanding reducing humanitarian access in frontlines and sought to understand and highlight risks on the reducing household economic resilience.

This output was scored an A ‘meets expectations’ overall.

Assessment of Performance
Partner indicators against this output have mostly been achieved or overachieved, with one underachieved indicator and one narrowly missed.

Mercy Corps exceeded targets on two of three indicators and narrowly missed the third, completing 78% of Rapid Response Mechanism interventions within 14 days—just below the 80% target. Of the 41 activations during the reporting period, nine exceeded the timeframe due to security and access challenges in frontline areas, which should not be considered a fault of the implementing partners. The two overachieved indicators—distribution of NFI kits and ready-to-eat food rations—were set before partners finalised their activities. A larger number of partners opted for in-kind support rather than service-based assistance, resulting in a higher number of people reached. Mercy Corps plans to revise its results framework in future cycles to better align with actual partner activities. These minor deviations, whether over- or under-performance, had no significant impact on the quality or efficiency of the assistance delivered.

Mercy Corps reported overachievements on the satisfaction of assistance, with the target set at 80% and MPCA achieving 90%, the RRM 97% satisfaction and in-kind assistance 99%. The team undertook corrective actions for underperforming on programme participants knowledge of the LIVES feedback mechanism, particularly for RRM where only 38% of people knew how to use their CARM system, conducting analysis which identified a lack of familiarity of complaints and feedback processes.

Ukraine Red Cross Society worked to strengthen its internal capacity for disaster risk management (DRM) and response, successfully supporting preparedness and risk reduction activities in five regions. However, progress was limited by recruitment and retention challenges, resulting in the development of only one new DRM policy or procedure out of the three initially planned. In response to these ongoing staffing issues—common across the organisation—Ukraine Red Cross reviewed and adjusted its salary scale to better align with market rates, aiming to improve recruitment and retention.

More generally Ukraine Red Cross branch development has been central to building decentralised emergency response capacity, enabling close coordination with local authorities and regional State Emergency Service of Ukraine (SESU) teams. This network played a critical role in responding to nearly all spikes in humanitarian need during the reporting period. Since Russia’s full-scale invasion, URCS’s expansion must be supported by continued investment in regional and branch-level development to ensure high-quality response and effective management of large-scale operations nationwide.

With FCDO funding, URCS delivered training in disaster risk management, emergency response, and crisis communications for staff and volunteers, and distributed 200 disaster risk reduction kits across Kharkiv, Sumy, and Zaporizhzhia. Additionally, the URCS Emergency Response Fund—of which FCDO contributed £2,769,913 out of a total £10 million in 2023—provides flexible resources that can be mobilised by central and regional teams. This capacity was demonstrated following the destruction of the Kakhovka Dam, when URCS partnered with the State Emergency Service to deliver evacuation services.

The OCHA-managed Ukraine Humanitarian Fund (UHF) remains a vital mechanism for enabling rapid response to emerging needs and sudden crises in Ukraine. While there were some delays in disbursements due to headquarters-level approval processes, the fund demonstrated flexibility and responsiveness in key moments. Following the destruction of the Kakhovka Dam, UHF used its expedited top-up mechanism to allocate an additional $3 million, allowing partners already active in Kherson and Mykolaiv to scale up their operations. The same mechanism was also used to boost winterisation funding.

UHF’s efforts to expand access for Ukrainian organisations—through increased national partner engagement and the introduction of funding envelopes tailored for smaller organisations—enabled a broader range of actors to respond effectively. This flexibility supported the fund’s goal of reallocating resources to where they are most needed as the context evolves.

The combination of UN-led planning processes, supported by high-quality analysis from partners such as REACH and ACAPS, and the ability to trigger reserve allocations, allows humanitarian actors to mobilise proactively—whether for seasonal preparedness, such as winter planning, or in response to sudden shocks like the Kakhovka Dam incident. However, while the sector-based structure of the fund enables targeted, gap-filling interventions, it presents challenges for supporting integrated, multi-sector responses.

Good quality data, information and analysis underpins a quality response, and partners ACAPS (through BRC), REACH (under the HAVEN consortium) and IOM’s DTM contributed to horizon scanning and understanding the evolving context and risks. REACH national multi-sector needs assessment underpins annual planning processes, while their Joint Rapid Assessments and Rapid Needs Assessments enables cluster and operational actor planning.

Response in focus: Destruction of Kakhovka Dam

On 6 June 2023, the destruction of the Nova Kakhovka Dam caused widespread flooding, displacement, and land contamination in Kherson Oblast and surrounding regions. In response, the programme rapidly pivoted existing support, released contingency funds, and accelerated planned assistance. New agreements were signed to contribute £10 million to the International Committee of the Red Cross appeal and £5 million to the Ukraine Humanitarian Fund, providing partners with the flexibility to scale up their response. Additionally, £1 million in planned programming with IOM was redirected to support those affected, primarily through cash transfers.

Following a request from the SESU, FCDO initiated an in-kind response through Palladium, its humanitarian logistics partner. Items were verified for relevance and appropriateness, and the first trucks—carrying boats to support SESU’s response—arrived in Lviv on 13 June. Between 13 June and 12 July, a range of equipment was delivered, including water pumps capable of removing 200 million litres of water per day, tankers able to support over 9,000 people with clean water per load, and boats and waders to enhance SESU’s search and rescue capacity. Many of these items will remain useful for future emergencies – not least because of Ukraine’s other dams which could be hit in ongoing Russian aerial attacks/

To address the widespread loss of access to safe water, IOM distributed over 87 water tanks (5,000–10,000 litre capacity) to affected communities, providing vital emergency water points. IOM, designated by the Ministry of Reintegration as the lead humanitarian cash partner, supported 1,410 flood-affected individuals with multi-purpose cash assistance through FCDO funding. While 1,533 payments were processed, the discrepancy reflects individuals who registered but were unable to collect their payments, likely due to displacement.

IOM also collaborated with SESU to deliver essential supplies—including boats, lifejackets, pumps, hoses, and safety ropes—to SESU’s Lviv warehouse for onward distribution to affected areas. These resources enabled safe evacuations and the removal of floodwaters, helping residents begin recovery.

Overall, we judge that FCDO’s partnerships over this period have demonstrated strong agility, clearly pivoting to spikes in need.

Lessons learned
FCDO must remain clear-eyed about the importance of maintaining flexibility within its partnerships, while recognising the trade-offs this entails. Further investment in contingency planning and scenario development—particularly in the next business case—will strengthen preparedness. While the current programme team benefits from strong crisis experience, it is essential to broaden crisis response capabilities across the wider team and institutional systems to avoid over-reliance on a shrinking pool of experienced individuals.

FCDO should apply a high threshold for deploying in-kind support from its own resources, given the heavy transactional burden involved. Greater efficiency and value for money are likely to be achieved by channelling support through partners. Additionally, FCDO must be more willing to conclude its own in-kind interventions once the immediate phase of a crisis has passed. While many items may have future utility, their value for money diminishes rapidly after the initial emergency—whereas the management burden remains constant.

Recommendations
6	Crisis and scenario planning / Develop scenario planning for humanitarian risks with the development of triggers. Ensure the future programme portfolio contains actors who have capacity for large-scale shock responses.	31 December 2025	HARP SRO, PRO, and Lead Advisor

Output Title	Activities in Moldova
Output number:		6	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

6.1 Sub output: Inter-Agency GBV Coordination is strengthened through coordination and capacity building efforts of all actors in line with the GBV working group agreed Work-Plan
Indicators	Planned		Achieved		Score
6.11 [UNFPA] Proportion of Annual GBV Sector Working Groups targets achieved.	95%		95%		A
6.2 Sub output: Existing 28 static and mobile Women, Youth and Older Persons Safe Spaces for January-March 2024 are sustained.
Indicators	Planned		Achieved		Score
6.21 [UNFPA] Number of beneficiaries reached with GBV static and mobile services by end of March 2024.	15000		15764		A
6.3 Sub-output: Households are better able to meet their basic needs as they define and prioritise them.
Indicators	Planned		Achieved		Score
6.31 [WFP] Number of women, men, boys and girls receiving cash-based transfers (residents/refugees)	200,000 & / 3000		91593 & / 4395		B
Sub output: Ministry of Labour and Social Protection (MLSP) has improved capacity to increase coverage and efficiency of the national social assistance programme for vulnerable families with children in delivering Child Protection and GBV services.
Indicators	Planned		Achieved		Score
6.41 [UNICEF] Number of refugee and vulnerable Moldovan children having access to child protection services in Moldova [Children/ caregivers]	60,000 / / 15,000		65,643 / / 23,809		A+
6.42 [UNICEF] Number of social workers acquired enhanced knowledge on case management, including identification, referral and services provision to UASC and provision of effective child protection within the Temporary Protection mechanism.	450		549		A+
6.43 [UNICEF] Availability of costed minimum package of social services to vulnerable refugees and host communities in Moldova mainstreamed in the national Social Policy reform.	Completed		Partially		B
6.5 Sub output: Strengthening the implementation of the National Program for Preventing and Combating Violence Against Women and Girls and Domestic Violence 2023-2027 is advanced
Indicators		Planned		Achieved		Score
6.51 [UNFPA] Integrated services package for GBV survivors developed through technical assistance of UNFPA and in coordination with the MLSP and civil society experts.		-		Partially – implementation ongoing		B
6.52 [UNFPA] GBV case management model and methodology developed and piloted.		-		Achieved		A
6.53 [UNFPA] Number of people reached through awareness raising and communication activities for prevention of violence against women and girls.		500,000		3,100,000		A+
6.6 Sub-output: Number of national policies, strategies, programmes and other system components contributing to Zero Hunger and other SDGs enhanced with WFP capacity strengthening support Target: 1 Social Protection System component enhanced (digitalisation of available platforms and databases)
Indicators		Planned		Achieved		Score
6.61 [WFP] Number of people engaged in capacity strengthening initiatives facilitated by WFP to enhance national stakeholder capacities contributing to Zero Hunger and other SGDs		3353		5347		A+
6.62 [WFP] Number of capacity strengthening initiatives facilitated by WFP to enhance national stakeholder capacities to contribute to Zero Hunger and other SDGs		1		2		A+
6.7 Sub output: Support the reform of the administrative structure of social protection delivery between central government and local government levels. Improve coordination of development partner support. Support the decision-making process in evaluating services through a Value for Money framework. Help to create and integrate an approach to Risk Management including prevention, checks, controls and safeguards.
Indicators		Planned		Achieved		Score
6.71 [STAAR] Setting up of a Deconcentrated Social System for Territorial Social Assistance Agencies (ATAS): draft regulations and HR matrix developed.		100%		50%		B
6.72 [STAAR] Improvement of Social Assistance Funding Mechanism and Redefining the Role of Social Funds: draft key result indicators for reengineered social services developed. Draft data collection format developed		-		Completed		A
6.73 [STAAR] Revision of Social Services Classification and Improvement of Quality Management: draft quality assurance framework; quality standards; risk framework for social benefits/social services and curriculum developed.		Completed		75%		A
6.8 Sub output: National healthcare system has improved capacity to sustain access to quality maternal and child healthcare (MCH) services for vulnerable refugee children, adolescents, and their caregivers.
Indicators		Planned		Achieved		Score
6.81 [UNICEF] Number of refugee children and their caregivers benefiting from healthcare services including nutrition (Infant and Young Child Feeding - IYCF) and routine immunisation with support from UNICEF.		8,000		7,300		B
6.82 [UNICEF] Number of parents and caregivers benefiting from health promotion and information services, including information on accessing services available through the implementation of Temporary Protection mechanism in Moldova		12000		37500		A+
6.83 [UNICEF] Percentage of Youth Friendly Health Service (YFHS) professionals and service providers trained in provision of GBV		80%		90%		A+
6.9 Sub-output: National education system has strengthened capacity to ensure quality of teaching and learning for refugee children and adolescents in Moldova
Indicators		Planned		Achieved		Score
6.91 [UNICEF] Number of refugee children and adolescents accessing and enrolled in formal and non-formal education and learning in Moldova in accordance with the provisions of Temporary protection mechanisms [Accessing/enrolled]		25,000 / / 5,000		25,000 / / 2,314		B
6.92 [UNICEF] Availability of functional National hub for youth NGOs and students' councils		National hub is functional		Completed		A
6.93 [UNICEF] Number of youth NGOs and students' councils nationwide accessing and implementing different forms of non-formal and informal education and skills development initiatives for refugee and vulnerable Moldovan students.		70		100		A+
6.94 [UNICEF] Number of teachers and educational professionals benefiting from UNICEF supported trainings on MHPSS, GBV, Social and Emotional Learning and Psychosocial First Aid		1000		1302		A+
6.10 Sub output: Strengthened social inclusion of older people from refugees and host communities leading to increased resilience and social cohesion
Indicators		Planned		Achieved		Score
6.101 [UNFPA] Number of recreational daily centres strengthened to empower the older population to have a healthy and active life.		2		2		A
6.102 [UNFPA] Number of vulnerable older persons capacitated with digital skills to access online social and other public services platforms.		1000		1000		A
[note] Unaccompanied and Separated Children
[note] Data collection, analysis Gap Analysis finalised and shared with MLSP but not fully mainstreamed into national social policy.
[note] Regulations developed and submitted to Ministry. HR matrix not developed as not requested by Ministry.
[note] All developed and submitted to Ministry except the curriculum - not developed as deprioritised by Ministry.

Output description
Interventions in Moldova followed the same programme strategy and shifts as outlined in section B, tailored to a refugee response where the host community had a level of entrenched poverty and vulnerabilities to shocks. Interventions took a dual approach. First, direct support to refugees and extremely vulnerable Moldovans, delivering a tailored needs-based targeted response of the most vulnerable in this group – women and girls. Second, a focus on social integration through investment in strengthening national social protection systems to facilitate sustainable and integrated provision of quality services to which support both communities. This approach is in line with the framework established by the Global Compact on Refugees 2018 and aims at a sustainable approach to what is now a protracted displacement.

In FY23/24, the UK provided £11.3 million in humanitarian funding to support response efforts in Moldova. This assistance was delivered through established partnerships with UNICEF (£4.5 million), WFP (£3 million), UNFPA (£3 million), and STAAR (£822,000). FCDO did not engage new partners during this period, instead continuing collaboration with trusted organisations that had already demonstrated strong programmatic, technical, and operational capabilities. In designing the interventions for this financial year, the programme team used the prior year’s annual review recommendations as a starting point and consulted with other donors to complement their interventions.

The interventions successfully achieved their intended outputs, earning an overall performance score of A.

Assessment of Performance

WFP
WFP provided daily hot food to refugees living in Refugee Accommodation Centres. Meals were nutritiously designed and were prepared in line with Moldovan food hygiene safety standards. FCDO monitoring visits to RACs found a high quality of food storage and preparation, and high levels of beneficiary satisfaction with the support. Although costly, this intervention is judged to be an essential food security provision for this vulnerable population.

During the winter period, WFP provided cash assistance to vulnerable Moldovan individuals, with targeting lists developed in collaboration with the Ministry of Labour and Social Protection (MLSP). Priority was given to pensioners, families with children and/or adults with severe disabilities, and breastfeeding mothers. Cash assistance also supported Moldovans hosting Ukrainian refugees, reflecting the compact approach referenced above. The use of Posta Moldova enabled broad geographic coverage and facilitated home deliveries for individuals with limited mobility. Post-distribution monitoring indicated high levels of beneficiary satisfaction.

However, the number of individuals reached was significantly lower than originally planned, primarily due to a revision in the average household size, reflecting the high proportion of pensioners living alone. In addition, WFP’s expenditure on cash assistance was lower than anticipated, with a larger share of the budget allocated to technical assistance for the MLSP. While FCDO funding can, and should, be flexible to evolving circumstances and improved data this change should have been communicated prior to implementation. FCDO did also have concerns about risks to the perceived independence of humanitarian targeting for a second round of cash assistance distributed to a small group of beneficiaries in March 2024, which risked accusations of politicisation. FCDO’s concerns were flagged and discussed with WFP in April 2024. WFP and FCDO agreed that the supported group were eligible for assistance according to the agreed targeting criteria and identified vulnerabilities, however FCDO requested earlier consultation on considered risks in advance of distribution.
[note] This expectation has been reinforced to WFP as part of the Annual Review process with adjustments to ongoing engagement to improve scrutiny.

WFP did not collect data on the percentage of households reporting utility affordability as a serious issue, as the cash transfer was a one-time intervention. This limits our ability to assess the effectiveness of the support in meeting critical winter needs. Enhanced outcome-level reporting will be essential for future interventions of this nature.

FCDO support to WFP has also contributed to Moldova’s RESTART reform against an objective of strengthening systems and developing shock responsive social protection. This included capacity building by delivering training on data management for budgetary and policy frameworks and integrating cross-functional approaches to address GBV within social assistance programming. Targets were exceeded. UK support also enabled WFP to complete a performance review of Ajutor Social, MLSP’s social cash transfer programme. Based on this review, WFP developed reform recommendations aimed at improving the programme’s impact on poor and vulnerable populations. These recommendations have been submitted to the Minister and have helped identify key areas for continued collaboration with MLSP, including cash assurance, risk management, digitalisation, capacity building, and strategic communications. This was complimented by WFP support to an evaluation of MLSP’s information systems, contributing to the design of a more citizen-centric digital service architecture. Given the long-term nature of the change, it is difficult to assess impact at this juncture, but progress will be monitored in the next programme cycle.

UNFPA
Through FCDO funding UNFPA supported 32 static and mobile Safe Spaces for women, youth, and older people. The services, which benefit both refugee and host communities, are coordinated with local authorities and delivered by social workers to ensure long-term sustainability. Monitoring visits and an independent UNFPA evaluation found these Safe Spaces to be effective in providing vulnerable women refugees, including women from Roma groups, with safe access to information and GBV services. To mitigate the risk of exclusion of elderly people - a significant proportion of Ukrainian refugees in Moldova, UNFPA increased the accessibility of services and inclusion of this group. Monitoring visits observed Safe Spaces to be effective at engaging older people, especially within refugee accommodation centres. Active Aging Centres provided a similar level of engagement within wider communities.

Complementing the safe spaces, support is also provided to the GBV sub-working group, as part of the Refugee Coordination Forum, and for systems strengthening with MLSP to improve national action against GBV. Through this support, FCDO improved coordination among humanitarian actors and with the government – primarily through aligned indicator reporting and referral pathways. UNFPA also facilitated training to service providers on preventing and combating GBV against people with disabilities, and trained people with disabilities on how to identify and report cases. UK funding has also supported MLSP in the development of a national programme to combat GBV working with survivors (including refugees), perpetrators and civil society aimed to develop an integrated services package and SOPs. The package has been endorsed by the MLSP and is being actively advanced for implementation. Because of the ongoing nature of this process, the metric is considered a partial achievement. Finally, UNFPA implemented a communications campaign to raise awareness about violence against women and girls, with a strong focus on digital violence. The campaign significantly exceeded its initial outreach targets, influenced by the strategic engagement of national celebrities. It is too early to determine whether this has led to changes of behaviour.
[note] National Program for Preventing and Combating Violence Against Women and Girls and Domestic Violence (2023-2027)
[note] The campaign was designed to raise awareness and understanding of what constitutes GBV and rights and not aimed at distinct behaviour changes in this phase. Behavioural change efforts are planned in future phases of the campaigns.

UNICEF
UK support to UNICEF in Moldova was aimed at improving nationally led child protection services to which both Ukrainian refugees and vulnerable Moldovan children have access. Targets under these indicators were moderately exceeded. We judge working with MLSP enabled wide reach, as well as being a more sustainable platform on which to deliver improved services. Specific training for child protection specialists was delivered to improve case management. There is evidence of gradually improving the knowledge base of workers delivering child protection. Work is ongoing to determine methodologies to measure improvements in quality of service delivery. Quantitatively there are positive indications (number of cases opened) being seen in coverage of services.

Through the programme FCDO has also aimed to improve Ukrainian refugee enrolment in education and participation in non-formal education. Activities include back to school campaigns and investment in 81 EduTech Labs. We judge there has been reasonable uptake of non-formal education among vulnerable groups and the capacity development for youth workers, teachers and representatives of pupils’ councils has improved delivery through increased technical knowledge and application of this. Enrolment for Ukrainian refugee children in Moldovan schools remains concerningly low. Parental reluctance, intentions to return, a lack of awareness on options, and language difficulties are significant, and difficult to overcome, barriers. We assess that efforts to tackle barriers have been technically sound, albeit they have not unlocked significant enrolment increases.

Further efforts through FCDO’s partnership with UNICEF to improve the welfare of vulnerable children in Moldova include reimbursement to the National Health Insurance Company of Moldova for the cost of health care services provided to 7,300 refugee children and women (children’s caregivers), and a wide-reaching health promotion campaign. This has improved access to vital healthcare, improved community awareness of immunisation, and represented good VFM by benefitting from the economies of scale afforded by using an existing national platform. Complementing UNFPA efforts on GBV, UNICEF through FCDO funding has sought to improve GBV service provision in 41 Youth Friendly Health Clinics – through a training programme which has benefited 138 clinical staff and development of SOPs. A clinic monitoring visit demonstrated good technical knowledge of staff.

Finally, UNICEF has contributed to MLSP’s Social Protection Reform, which aims to ensure fairer access and better quality of social services and cash transfers and thereby reduce child poverty in Moldova. In this period activities included cost-efficiency gap analyses and development of social investment plans. UNICEF also initiated an analysis of fiscal space for the financing of social protection which will feed into the 2025 budget development for submission to the Ministry of Finance. UNICEF’s support has been effective in supporting the MLSP to tailor their efforts to identify sustainable financing for social assistance and social protection programmes, including for refugee integration efforts. Whilst there is still some way to go in reaching financing needs, the support has proved useful in shaping asks and requirements.

Moldova Regional Technical Assistance Facility
The facility is a UK funded team of Social Protection experts embedded within MLSP, supporting their social protection system reform. The reform has introduced a new Ministry-managed territorial service delivery structure with the goal of ensuring equitable access to quality social protection services. Although the MRTAF team had planned to develop draft regulations and an HR matrix for the decentralised system, shifting ministerial priorities limited progress against these indicators.

Despite this, the MRTAF team made significant contributions across several other areas. On the digitalisation of social service delivery processes, efforts have enhanced automation, accountability, and management, and informed the design of a future digital services architecture. On social protection cash assistance, the team’s analysis has contributed to strengthening risk management, case management, and linkages between service and cash provision. To support service quality, the team developed a briefing paper outlining five generic service standards and a concept paper linking quality assurance to performance management. This work has guided MLSP in conceptualising quality standards, including the Metabook and Curriculum. The MRTAF team played an active role in the RESTART Working Group on Capacity Building, preparing a comprehensive strategy for professional development in social protection. This strategy aligns with the EU’s modular credit accumulation framework, supporting competency-based progression toward formal qualifications. The team’s technical outputs have been relevant and of a good quality, recognised by the MLSP and other actors supporting the reform process. The team’s agility was also an added value. However, it did take some time for the team’s role to be recognised and clarified within the MLSP, which hampered progress in the early months.

Lessons
 The UK’s humanitarian efforts in Moldova have effectively met their intended objectives, albeit it is difficult to judge at this stage the impact of longer-term initiatives to social protection and services strengthening. Importantly, the UK’s investments, alongside allies, have helped Moldova to support a significant per capita population of refugees despite an existing poverty challenge and vulnerability to shocks. Moldova has shown and continues to show impressive hospitality to the refugee community, including integrating them to the extent afforded by temporary protection to national systems. This has allowed a dual-targeting strategy reaching Ukrainian refugees and vulnerable Moldovans that has enhanced efficiency and avoided the creation of parallel humanitarian systems. In addition to the scales of economy this approach affords, as well as sustainability, this approach has helped reduce the risk of social tensions. Importantly, support has been relevant to the needs of the most vulnerable, focusing on meeting basic, protection, and health needs, tackling GBV, and improving access to education.
[note] According to UNHCR’s 2023 Participatory Assessment for Moldova, social cohesion between Ukrainian refugees and host communities remains strong, with no significant changes since 2022.

Multiple partnerships in the Moldova programme have contributed to addressing GBV and social protection systems strengthening. We are confident approaches have been complementary. The priority in future years will be on ensuring the sustainability and entrenchment of reform efforts supported by technical assistance, especially given the high ongoing reliance of the MLSP on external support and consultants to push through change. In addition, a clear roadmap for continued refugee integration into national systems will be necessary. A broader, and shared, theory of change is needed to ensure strategic intent is maintained and that due is focus is given to broader, more political, enablers and links to other set-piece areas of support, particularly EU support, which could set strong incentives for inclusion and focus on the most vulnerable. Efforts to enhance shock-responsiveness of social protection are at an early juncture but the desired end state will not be delivered by technical assistance alone.

As it stands this programme is not responding substantively in Transnistria where there are vulnerable populations, including Ukrainian refugees, who rely on the provision of Russian gas which transits through Ukraine. This is a complex operating environment which has the potential to see rapid spikes in humanitarian need and displacement. FCDO will need to invest in contingency planning in advance of winter and monitor developments on the provision of Russian gas closely.

D: VALUE FOR MONEY

Key cost drivers and performance
For most partners, the primary cost drivers were related to the procurement of items essential for programme activities. For instance, UNFPA in Moldova incurred significant costs procuring medical equipment for perinatal centres, while WFP (Moldova), Mercy Corps, and IOM focused in the main on distributing cash and vouchers to beneficiaries. In contrast, partners such as STAAR and ACAPS reported that their main expenditures were operational, i.e. rent and staffing.

Overall, programme performance relative to these cost inputs has been acceptable. For example, during the in-kind response to the Nova Kakhovka dam incident, Palladium procured bundled items—such as water tankers with tap stands and boats with lines—to enhance usability for the State Emergency Services of Ukraine. This approach enabled immediate deployment and reduced the need for additional purchases. Similarly, WFP in Moldova distributed food vouchers, which proved more cost-effective than catering services, allowing the programme to reach a greater number of refugees with hot meals.

However, there have been instances of suboptimal performance in relation to cost inputs. While the technical assistance provided by consultants contracted through STAAR provider DAI has been strong, the value for money of DAI’s support teams is less evident. It has been difficult to assess the deliverables associated with certain budget lines—such as knowledge management, monitoring and learning, and communications—despite repeated requests for clarification from DAI, which holds the STAAR contract.

Performance compared to the original VFM proposition in the business case
In this review we have assessed delivery against the core components of humanitarian VFM - speed, cost and quality. The first year of the programme, particularly in the emergency phase gave priority to speed and the relevance of support with a strong emphasis on ‘do no harm’ principles. As the programme has evolved, more consideration has been given to costs in parallel with speed, relevance and quality.

Speed: The programme responded swiftly and effectively to the destruction of the Nova Kakhovka dam, delivering timely and appropriate assistance through both partners and direct in-kind support. In preparation for winter, the FCDO team proactively reprioritised available programme resources, directing them to partners best positioned to meet the needs of the most vulnerable populations during that period. Throughout the year, the programme has consistently demonstrated agility in responding to evolving needs. For example, in August 2023, following emergency evacuations from Kupiansk, HAVEN requested to reallocate funding under the ‘safe accommodation’ budget line—from providing hotel rooms for evacuees to supplying materials for the Kharkiv collective centre as a quicker, lower cost and more sustainable solution. This request was turned around at pace underlining strong relationship management.

- Cost: The team has been consistent in scrutinising budgets and payment requests, encouraging efficiencies, managing costs down and ensuring savings were effectively reprogrammed. For example, HAVEN secured an insurance policy that was significantly less expensive than initial quotations received during budget development phase following dialogue. Savings made on this were flexibly re-programmed in accordance with needs, specifically on the procurement of PPE for volunteers and civilian evacuations.
- Quality: Programme quality is primarily monitored through regular third-party monitoring. Feedback from these visits is shared with partners and used to drive continuous improvement. For example, feedback has led to enhancements in the accessibility of downstream partners’ project sites, such as the installation of ramps and the provision of information in braille. In addition to third-party monitoring, FCDO staff have conducted field visits – albeit more in Moldova than in Ukraine where significant security restrictions remain. In Moldova, site visits have included Refugee Accommodation Centres, Safe Spaces, and EduTech Labs across the country. During these visits, staff engage with both implementing teams and service users to assess the quality and relevance of interventions. Beneficiaries from both refugee and Moldovan host communities have consistently expressed positive feedback on FCDO-funded assistance. In Ukraine, the team conducted one monitoring visit east of Kyiv, to Poltava. This verified the relevance and quality of mental health and psychosocial support activities and anti-trafficking messaging delivered under IOM’s protection programming. The quality of modular housing support provided in Year 1 was also assessed. Beneficiaries were surveyed in the visits and provided positive feedback on the quality of assistance, with mental health support being particularly valued.

Alongside monitoring, partners have undertaken VFM evaluations. Mercy Corps commissioned Key Aid Consulting to assess the cash component of the LIVES 1.0 programme in Ukraine and Poland. This concluded that the intervention was efficient and effective, exceeding its planned caseload within a condensed timeframe. The study also produced a set of recommendations, set out in the table below, which Mercy Corps has incorporated into the design and delivery of LIVES 2.0.

Longer programmatic commitments to help build capacity of partners.
Consolidate activities in one country at a larger scale to deliver better VFM – noting that the inclusion of Poland has proven costly and time consuming.
Advocacy to the Cash Working Group to increase the transfer value of MPCA to mitigate the erosion impact of inflation.
Examine due diligence assessments on implementing partners to remove low value add areas of examination while maintaining rigour on risk management
Consider diversification of delivery mechanisms and potential financial service provider to increase equity through simplifying the method of assistance for recipients with specific vulnerabilities.

There is a tension between quality and sustainability with cash transfer values. There was an increase in the cash transfer value in Ukraine during the period of the review to reflect sharp rises in inflation after the full-scale invasion, but this has increased the disparity with social protection payments, the challenges in aligning and increased the risk of entrenching a parallel system. The question on how to maintain quality and how this links to the number of people who can be helped, will be an enduring question in the Ukraine response.
[note] The cash transfer value also draws on the Minimum Expenditure Basket as a reference point. Many humanitarian responses draw on the Survival Minimum Expenditure Basket. FCDO will need to carefully monitor the trajectory of humanitarian funding to monitor whether this approach is sustainable.

As outlined in the business case addendum, the programme has increasingly integrated activities that advance equity. In its second year of implementation, the programme has placed greater emphasis on localisation and inclusion to advance equity, acknowledging from the first Annual Review, “a key consideration for the programme’s future value for money will be its effectiveness in supporting localisation and strengthening national systems.” Notable examples of this shift include:

The HAVEN project, which has supported locally led coordination of humanitarian aid and evacuation efforts and strengthened the volunteer response structure through provision of PPE, insurance, fuel stipends and first aid training. This has leveraged the knowledge of local actors on their communities and ensured more of the very most in need, often elderly, are reached in frontline areas.

The WHO project, which supports the strengthening of current rehabilitation systems through the provision of assistive technology and training for medical personnel. WHO have also worked with Humanity and Inclusion to improve disability inclusion more generally in the response, through engagement with and funding of OPDs.

Support to the PereHid Initiative via STAAR, which provides analysis on how to complement the national social protection system and opportunities for more shock-responsive social protection, an investment in longer term solutions to vulnerability in Ukraine and improved quality of provision.

Similarly, strengthening the Moldovan national social protection system through provision of technical and material assistance from partners UNICEF, WFP, UNFPA, and STAAR in support of the Ministry of Labour and Social Protection’s RESTART Social Protection Reform.

Mercy Corps, LIVES 2.0 programme continued to deliver strengthened localised aid through providing systematic, tailored capacity-building support to national actors, growing their knowledge and skills to lead humanitarian response. Through sub-grants, CSOs became empowered to deliver protection services and address basic needs to a broader more diverse population in need.

Recognising the need for further progress on localisation and inclusion, the team developed partnership principles. These outline key expectations on localisation and GESI, which will be further incorporated into the final year of this programme.

Progress has been mixed against the VFM recommendations from the prior period. A lack of ability to directly monitor in Ukraine (due to security restrictions), resource constraints and the ongoing pace of the response are barriers which the programme team have struggled to overcome. Positively there has been progress over the review period to stabilise management of partnerships, pushing for greater reporting and information sharing than in the initial phase of the response, refining our third-party monitoring approach and planning for the future of the FCDO’s humanitarian programming. While a VFM strategy is to be developed the team plans to transition to the 5Es model in the next phase of programming and establish a mechanism to further develop a more extensive evidence base. This challenge is not unique to the UK and reflects that responses at this scale in Ukraine are relatively nascent.

Recommendations:
7	Value for money / Define a value for money strategy and indicators for successor programme based on lessons learned from the first two years of programming at scale. Efforts should be made within this develop a standardised 5Es assessment criteria across interventions and better beneficiary data disaggregation.	31 March 2026	HARP PRO

E: RISK

The risk rating for the programme is severe. This has not changed since the previous annual review, reflecting the fact that operating in Ukraine continues to entail a high level of risk for all actors, especially those seeking to deliver humanitarian assistance to the most vulnerable people in need – typically those in frontline areas. The risk appetite for the programme, shown in the table below, is higher than the departmental and British Embassy Kyiv risk appetites across all categories. This is typical of a humanitarian programme given delivery was focused in war-affected areas and given the higher risk nature of humanitarian operations.

FCDO and British Embassy Kyiv have decided to support the programme understanding the risks entailed, agreeing the programme risk appetite aligns with the realities on the ground and the level of risk required to deliver an innovative and effective humanitarian response in this context.

Risk Category	FCDO risk appetite	BE Kyiv risk appetite	Programme risk appetite
Financial and fiduciary	Receptive	Cautious	Receptive
Reputation	Receptive	Cautious	Receptive
Safeguarding	Cautious	Cautious	Receptive
Strategy & context	Cautious	Eager	Eager
Policy and programme delivery	Cautious	Eager	Eager
Public service delivery & operations	Cautious	Cautious	Receptive
People	Cautious	Receptive	Receptive

Five risks had severe gross risks (pre-mitigation) at the end of March 2024, detailed below:

		Risk	Likelihood	Impact	Gross Risk
Ukraine	1	Black swan events: Black swan events create significant spikes in humanitarian need that risk overwhelming response capacity, leading to potential for dire unmet humanitarian need and to further undermine perceptions of humanitarian actors.	Possible	Severe	Severe
	2	Access to Russian controlled areas: As humanitarian access in Russian-controlled areas becomes increasingly constrained and Ukrainian retaking of territory slows or stalls, this prevents humanitarian organisations from reaching those populations in need, leaving significant parts of the Ukrainian population with no or limited humanitarian support.	Almost Certain	Major	Severe
	3	FCDO staffing: Short tour lengths and work pressures, alongside continued use of consultants with short notice periods, lead to increased churn within the team and potential for burnout with negative impacts on continuity of effective staffing within the BEK Humanitarian team.	Almost Certain	Major	Severe
Moldova	4	Political change: Change in government from pro-reform to a pro-Russian party halts reform processes, resulting in reduced civic space, opportunities for diplomacy, reduced humanitarian access (including administrative and logistical constraints/ impacts on people) and programmes stalled, with impacts on refugee inclusion (legal, access to service provision, and general acceptance of refugees in host communities) and effectiveness of FCDO-funded interventions, specifically curtailing our ability to work with or through government systems.	Possible	Severe	Severe
	5	Increased refugees: Black swan events or a significant escalation in conflict trigger a massive refugee influx into Moldova which overwhelms government and humanitarian capacity to respond in Moldova and Romania and renders our existing programming ineffective, insufficient and inappropriate to the nature of response needed. This raises political and media attention on the refugee crisis and increases the potential for them to go further into the EU and the UK.	Possible	Severe	Severe

All risks had a post mitigation strategy of “major”, due to the strategies employed by the FCDO team. For risk one, mitigation focused around holding contingency funding to respond to spikes in need and close engagement with FCDO’s Humanitarian Department. For risk two, mitigations included FCDO support to XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Support to the HAVEN consortium has helped maintain interventions in contested areas through innovations such as the PPE lending scheme. For risk three, the severe rating was due to ongoing vacancies for multiple key team positions: however, recruitment rounds have since concluded. For risk four, mitigations included continuing support to the Government of Moldova reforms via the work of STAAR, and continuing UK diplomacy efforts through the BE Chisinau political team. Finally, risk five was mitigated through engagement on humanitarian response contingency planning.

Separate risk registers were held for Ukraine and Moldova, which were reviewed and updated monthly by the programme team. All residual risks have remained in appetite during the review period with no escalations. Partner-level issues are raised and noted on the register – some examples are noted below:

IOM Third Party Monitoring reported a potential risk of aid diversion, owing to a previous theft at a project site and ongoing security concerns. This was reported to IOM, who engaged the local partner running the site to ensure proper security measures where taken to secure project assets. Recent reports of potential diversion at scale, also reported by IOM, have resulted in a decision to pause FCDO funding while facts are established. Investigations are ongoing.

HAVEN: When artillery fire worsened in Kherson, Nonviolent Peaceforce flagged the increased risk and their mitigation measures: moving staff accommodation to a more secure location, and requesting permission to purchase an armoured vehicle to improve the safety of staff movements.

STAAR: Operational continuity with uncertainty surrounding the continuation of contracts for the technical experts embedded in the STAAR projects in Ukraine and Moldova when waiting for the FCDO ODA 2024/25 allocation. A change of personnel can undermine relationships with the respective Governments. To mitigate this, FCDO worked closely with the contractor, DAI, to understand their time scales for renewing technical assistance contracts and sought budget allocation exemptions so that contracts could be renewed.

WHO and HI: During the Third-Party Monitoring process, FCDO partner Ecorys also reported a possible risk of burnout of healthcare workers and staff members due to the intensity of their work. WHO engaged with this recommendation positively and has planned to implement MHPSS support for staff members in the new project. This component has been included in the new GLOA for HI, and more generally across our grants, with self-help activities and trainings coordinated with the MHPSS Unit.

Mercy Corps: To mitigate increased risk from aerial attacks and work undertaken in war affected locations Mercy Corps ensured a robust security and crisis analytics presence that is very close to programme operations. Mercy Corps also reinforced standard operating procedures among partners through participation in a security forum.

Ukraine Red Cross: Key risks reported to us through the duration of the programme relate to fraud/aid diversion, safeguarding, the lack of financial management and staff being impacted by conflict escalations. Recognising the risks posed by the rapid expansion of the Ukraine Red Cross following the full-scale invasion, British Red Cross provided and will continue to provide bilateral support in key areas. FCDO usually funds national societies via BRC as they can commit to pre-agreed aspects of assurance and accountability, including risk management and escalation.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Whilst all partners have reported on risks during regular meetings (typically monthly or bi-monthly) with FCDO, generally only NGO partners have formally reported on risks using a risk register, as part of their quarterly reporting cycle. Lighter-touch approaches have been taken with UN partners, where standard agreements with FCDO do not stipulate the requirement for a risk register. To note, in Moldova, UN partners UNFPA and UNICEF have both submitted risk registers to FCDO as part of final reporting.

Due diligence has also been utilised to manage partner-level risks. Through due diligence interviews and follow up on key findings UNFPA has introduced a new Enterprise Risk Management policy in April 2022 (software updated in June 2024) to increase risk literacy and strengthen risk culture. Additionally, during follow-up on the due diligence assessment Nonviolent Peaceforce, lead of the HAVEN consortium, has refreshed several internal policies (including anti-fraud, conflict of interest) which were more than 3-5 years old.

During the review period, this programme was audited by FCDO’s Internal Audit Department as part of an audit on the Eastern Europe and Central Asia Department. This review found that the controls in the programme, ‘has developed adequate controls to operate in a challenging environment’. A number of follow up actions were identified to further strengthen controls which the team is now working through.

Lessons
Risk monitoring remains challenging in Ukraine. The programme continues to rely heavily on third party monitoring. While this offers good coverage and insights, and a degree of risk management, it is not a panacea or analogous to what direct team monitoring can achieve. Direct team monitoring, in combination with third party monitoring, is necessary to have more confidence that risks, particularly around aid diversion are being appropriately tracked. The programme team will continue to press on this, and FCDO is considering carefully how to balance its duty of care to staff with discharging its obligations to protecting taxpayer monies. One way forward would be to replicate FCDO practice in Africa and the Middle East and travel with the UN and Red Cross Movement to benefit from their access and security.

A key reflection coming out of this review has been on the need to deepen our understanding of risk in Ukraine now the humanitarian response is stabilised. Within this is the recognition on the need for reflections on the assumptions made on risk in the emergency phase. For example, there is a default assumption that working with the UN is inherently lower risk than local partners. A more nuanced assessment it that all organisations that receive a significant influx of funding in an emergency (and beyond) will have their systems strained. This applies to the UN as much as it does an NGO and with the UN agencies receiving most of the funding in the response, the risk is clearly concentrated in these organisations. To ensure that are risk analysis is up to date the team will need to refresh and deepen due diligences – with accompanying dialogue on how funds flow in the intervention and how risk is mitigated throughout, as well as staffing for core risk management positions.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Programme governance and resourcing
For the majority of the review period, the programme SRO was the Deputy Director EECAD in London. With the appointment of a Development Director in July 2023, EECAD and BE Kyiv agreed to transition responsibility and day-to-day management of Ukraine humanitarian programming. In recognition of the significant scale-up of programming effort at post it was agreed the transition would be phased with the ambition to transfer the SRO role to post by April 2024. Ahead of this, in August 2023, the programme part of the then Ukraine Humanitarian Team was transferred to post structures, with the head of team moving to the line management of the Development Director, while continuing to report, alongside the PRO and Senior Programme Lead (Operational Excellence) to the SRO.

Throughout the review period most staff were based in London, with only two members based in Kyiv and one based in Moldova. Staffing was particularly challenged at the start of the period but stabilised over time albeit turnover has been high. The pace of work has been demanding throughout the period and team capacity regularly stretched. Many pressures were beyond the control of the team but in hindsight, more interrogation was needed on the number of partnerships taken on as a factor the team could control. For example, while funding the Women’s Peace and Humanitarian Fund has been a net positive, the team struggled to give it the attention required to unblock problems as they arose – particularly around the fund’s disbursal times. A similar point was raised by the Quality Assurance Unit to the team on as part of their review of future plans.
[note] Within this review period the team were part of an enhanced response to the destruction of the Kakhovka Dam, the development of a successor business case within a condensed timeframe, responded to an internal audit and participated in an ICAI review.

Humanitarian Advisers and programme team members were able to travel regularly to Ukraine and Moldova marking significant progress in team representation in post, as well as the ability to engage more directly with partners. Travelling beyond Kyiv, to the South and East of Ukraine, proved difficult with only one visit to Poltava in January 2024. Additional visits towards the South and East have not been possible due to security concerns, impacting the team’s ability to assess spend, delivery and conduct asset checks.

In the second year of the programme, the team has implemented a more stable and “business as usual” approach to partner management and reporting. Upon signing new agreements or amendments with partners for FY 2023/24, FCDO negotiated more regular reporting schedules using standard FCDO humanitarian templates, including reporting on risks and delivery chains. Improved staffing capability has facilitated more regular and in-depth dialogue with partners, allowing better understanding of key issues and challenges and a more consistent risk management approach.

Overall, the direct partners to this programme provided positive feedback on their relationship with FCDO, with Nonviolent Peaceforce noting the ‘partnership’ feel and support given to ensure the HAVEN consortium is strengthened and successful. For example, early in the partnership the FCDO team developed an agreement on budget flexibility, with a clear simple process to request budget changes – key to allowing HAVEN to provide emergency responses in a timely manner. At the last Partner Day in-country Moldovan partners, WFP, UNICEF and UNFPA, collectively noted their appreciation of the FCDO’s openness to dialogue, proactive engagement, and thought partnership. Beyond warm relationships the programme team acknowledge there is further to go to ensuring consistent practice in approach to managing partnerships across the team and ensure the right balance of working level effort with senior visibility and strategic reflection. This will be picked up through a refresh of programme governance for the successor programme.

Ambiguity in FCDO planning and transience of staffing have had an impact on partnership management. For example, changes in FCDO staffing during the reporting period, which included advisory and programme support, did impact the quality of engagement and communication with WHO. More formal training for new staff members and better knowledge sharing amongst team members would have ensured a smoother handover of duties on the partnership. Late confirmation of country allocations at the beginning of the period was disruptive to NGO partnerships, particularly Mercy Corps. This was beyond the control of the immediate team. Feedback has been given to central teams on the importance of budget certainty to achieving vision and VFM.

Given the wide range and number of partners involved in the portfolio, performance has naturally varied. Due to the nature of the programme and restrictions in travel, there is a heightened need for high-quality, accurate reporting to effectively communicate programme delivery, including successes and challenges. FCDO recognises the operational difficulties in this context and the demands placed on those working in Ukraine and the surrounding region. Despite these challenges, most – but not all – partners have consistently provided timely and detailed narrative and financial reports. This consistent communication has offered visibility into the programme’s achievements, risks, and financial status. Reliable reporting allowed FCDO to effectively monitor delivery, expenditure, and results, helping to mitigate the risks of underperformance or underspending.

There were examples of where partners did not provide consistently accurate reporting or reports were significantly delayed – most notably IOM. The team continues to engage with partners to resolve gaps and the SRO has reinforced expectations where necessary.

Throughout the reporting period partners generally engaged well with FCDO programme and advisory staff’s recommendations and requests. Specifically, all partners, when requested, provided updates to due diligence recommendation implementation and delivery chain maps. Multiple partners fully cooperated with FCDO audits and external reviews.

Funding Arrangements
The programme is made up of different funding arrangements, primarily unearmarked appeal funding and softly earmarked funding with UN agencies under Memoranda of Understanding and earmarked funding with NGOs through Accountable Grant Agreements. Commercial partnerships include Ecorys, to deliver the programmes third party monitoring activities and Palladium, who are contracted to support the delivery and subcontracting of in-kind support, deployments (advisory capacity) and Standby Partnerships.

The programme has drawn on multiple central FCDO contracts in the year under review. Although the team is not responsible for contract management directly, they have been able to work well with suppliers to effectively steer and direct the work as needed. The quality of invoicing has varied under commercial partners, with some invoices containing errors or charges without a clear explanation. The team has applied robust scrutiny and dedicated programme and senior resource to the review and quality assurance of such invoices.

Assets
In-kind donations and assets procured through Palladium were transferred to the Government of Ukraine or the relevant agency, mainly through Transfer of Ownership agreements administered by Palladium.  For NGO partners, assets registers submitted to FCDO were reviewed by the programme team. Although physical checks have yet to occur given access constraints to areas of programme operation, the programme team should consider how future site visits and virtual asset checks can be used to ensure proper asset management.

Financial performance
The original Business Case approved funding of £357m, notionally split across financial years as follows: FY 21/22 (£60m), FY 22/23 (£160m), FY 23/24 (£137m). Final spend against the publicly announced £357m Business Case budget in the reporting period was £356,661,857. In February 2024, a decision was taken to reallocate around £8.5 million, consisting of potential underspend and unallocated funds reserved for contingencies, to other components to ensure as full spend as possible.

Following discussions with finance colleagues, all £137m of programme budget in 23/24 was categorised as programme resource budget. Final spend against the publicly announced £137m was £137,481,528.

Audit
No partner audits commissioned by FCDO took place during the reporting period. The programme was audited by FCDO’s Internal Audit Department through February to March 2024. Some partners have commissioned their own audits and shared findings, most notably IOM.

G: MONITORING, EVIDENCE AND LEARNING

Internal Monitoring
Internally, performance of the programme has primarily been monitored through logframes. Where FCDO has provided earmarked funding (all partners excluding OCHA, XXXXXX and the Women’s Peace and Humanitarian Fund) individual logframes have agreed and a schedule of reporting against the agreed indicators. These are then discussed in meetings between the partner and the FCDO programme team with a designated Humanitarian Adviser and Programme Manager. These meetings are documented and include follow-up actions. The intent of these meetings is to drive the best possible performance for FCDO funding, working through problems as they arose, monitoring risks and surfacing opportunities. This way of monitoring performance was an advance on the prior year of the programme where only a few interventions had dedicated logframes – reflecting the origins of the programme in a crisis setting.

Sitting above the partner level logframes is the overarching logframe – the approach to which is detailed in Section C. As noted there, this took longer than anticipated to finalise, a consequence of a staggered mobilisation of partnerships which had shifted significantly from the prior year and later than typical confirmation of annual allocations to FCDO bilateral budgets. While a positive step forward, the programme team were not able to monitor performance against this logframe until this Annual Review. This reflects constraints on team capacity but also the need to further evolve the governance structure of the programme to include a regular review of overarching progress across review period. This will be aided in future by the delegation of the SRO-ship to BE Kyiv but is a clear area for improvement.

Supporting regular monitoring of individual partner logframes, partners to FCDO have conducted their own monitoring, sharing this to inform our judgements and support learning. For example, UNICEF in Moldova shares overall findings from their regular meetings with beneficiaries, social media listening, focus group discussions and community and youth engagement. Where partners, such as ACAPs work with organisations rather than individuals as their beneficiaries, feedback on their products was collected online. This enables the team, in this instance, to identify the most pressing information and analysis needs.

Where possible the FCDO programme team have directly monitored programme activities, checking these are as communicated in partner reports, adhere to response standards, are conducted in a way that delivers on FCDO’s safeguarding and fraud/diversion expectations and, as part of this, speaking directly to beneficiaries on their needs and the support received. This has been most successful in Moldova. In the period of the review, approximately monthly monitoring visits in took place in Moldova. These visits directly informed ongoing management of the programme.

As noted earlier in the review, direct monitoring in Ukraine has been subject to significant constraints. There has been one visit for the programme team outside Kyiv City to Poltava in the east with other visits taking place in the Kyiv and Lviv.
[note] Opportunities for monitoring in Kyiv city are limited. FCDO were able to visit Okhmatdyt Children’s Hospital in Kyiv which included seeing some of WHO’s rehabilitation work, as part of their Inclusive System Strengthening project and meet beneficiaries.

FCDO Internal Audit review March 2024
As noted in prior sections, the programme was also reviewed by FCDO’s Internal Audit in March 2024. This examined the programmes controls in their design and operation, and reviewed how these were applied in some of the partnerships in the programme. The overall conclusion was that the programme team have developed adequate controls to operate in a challenging environment. The recommendations made by FCDO’s Internal Audit Department will be taken forward by the programme team to further improve programme controls and management of risk.

Expectations of partner monitoring
Spot checks are embedded into their grant conditions with downstream partners for program monitoring. For example, the HAVEN consortium conducts regular asset checks on downstream partners holding FCDO-funded PPE kits. Post-distribution monitoring is also employed by several partners. In Moldova UNFPA requires regular reports from their downstream partners including beneficiary feedback and regularly visits implementation sites. Similarly, WFP in Moldova has used phone and physical monitoring for cash to vulnerable Moldovans.

Annual Review
This Annual Review has been taken forward primarily by the programme team. To increase the rigour of the assessments within, a Humanitarian Adviser from the wider department joined the review team, leading the assessment of delivery under outputs 1 and 4 and offering overarching recommendations which have been represented in Section A. The approach taken to assessments under other outputs, has also benefitted from a degree of impartiality. Lead authors for these sections, all Humanitarian Advisers, assessed a broader range of partnerships, beyond the ones they led directly on. To inform their assessments they drew not only on third-party monitoring but also conducted meetings with partners to review evidence on performance over the period of the review and ask questions to test this and surface recommendations for improvements.

This process has been aided by the input of programme managers. Finally, the SRO for the programme has reviewed each section of the AR to ensure consistency of approach.

Third Party Monitoring in Ukraine
The programme team draws on a central contract implemented by Ecorys for monitoring and evaluation of the programme. During the annual review reporting period two rounds of monitoring were implemented via Ecorys. Field work visited project sites in the East and South of Ukraine and included the monitoring of tier one partners i.e. those directly funded by FCDO. Partners monitored included Mercy Corps, Ukraine Red Cross Society, WHO, IOM, Humanity & Inclusion, HAVEN, and the Women’s Peace and Humanitarian Fund. Ecorys sub-contracted field-monitors from the Kyiv International Institute of Sociology to visit 85 project sites supported by seven partners.

To select sites, partners were asked to compile a list of project sites listed in hard-to-reach areas of Ukraine within the East and South. From this list, sites were selected according to the following parameters: geographical spread, different types of services and assistance, and safety of field-work staff. Monitors conducted interviews with project site staff and collected feedback from beneficiaries on relevance, efficiency and inclusiveness of support; managing risks and protection of beneficiaries and; accountability to affected populations. Field-visits were further supported by in-depth key informant interviews of partner-staff, local CSOs, government authorities.

Findings were summarised in reporting and submitted to the FCDO. Findings are disseminated to partners to help improve delivery for beneficiaries or to raise issues. For example, WHO on the potential risk of burnout among healthcare professionals due to the intensity of their work. WHO responded positively and have included MHPSS support for staff and healthcare professionals in their 24/25 project.

While the Ecorys TPM has been an asset to FCDO in Ukraine, further reflection is warranted on whether it can go further in the essential tasks of monitoring the risks of fraud and diversion, in addition to the important questions put to beneficiaries on the quality of support. As the review was being compiled, FCDO was informed of a potentially significant diversion in some of IOM’s support, funded by the UK and other donors, which was uncovered through monitoring by OCHA. A comparative examination of the respective monitoring undertaken by Ecorys and OCHA on IOM can help identify areas for improvements for future rounds of FCDO’s third-party monitoring.

Monitoring in Moldova
Partners UNICEF, UNFPA and WFP in Moldova have been subject to multiple site monitoring visits by FCDO staff which negates the need for third-party monitoring. Visits have included review of project implementation, discussion on situational updates, speaking to beneficiaries and the local communities, and dialogue with any relevant downstream partners and post-visit reporting. Where areas for improvement have been identified these have been raised with partners and through them, communicated on to downstream partners.

Learning – Ukraine
Learning has occurred both at partner level and programme level in Ukraine. At programme level, the team hosted partner days to aid learning. These allowed the programme team to engage with partners, including those working downstream, to understand better delivery of activities, the realities facing implementers, areas for improvement in the over-arching response and the trajectory of needs and risks in the response. In turn these events have been used to disseminate learning to partners from wider programme assessments, share FCDO thinking and analysis (including from other contexts) as well as reinforcing expectations on safeguarding and management of risks of fraud and diversion.

A key takeaway from these events was the need for equitable partnerships with local actors throughout the delivery chain. FCDO has progressed this by developing a set of partnership principles, outlining how the programme expects direct partners to engage with downstream partners. These principles have been reviewed by local partners to ensure relevancy reinforcing the importance of this type of engagement and learning.

At the partner level partners have engaged in learning across the review period, both within the FCDO-funded projects, across their organisations as a whole and alongside FCDO. Some examples are:

Mercy Corps through post distribution monitoring for winterisation assistance. Here a multipurpose cash assistance top-up to the most vulnerable households in winter months, showed that in certain locations close to the frontline not all essential goods were available for purchase – including winter clothing and fuel. In these instances, both cash and in-kind support are needed. These learnings will be incorporated into LIVES 3.0 winterisation preparations to improve support in Winter 24/25.

Humanity & Inclusion conducted training with community-based medical staff and humanitarian workers on rehabilitation and MHPSS services. Participants agreed the training topics, including Psychological First Aid, Stress Management Training and training on providing assistance to those with low mobility, were relevant and important for their work. On average, participants improved their knowledge by 24% for rehabilitation training, and 19% for the MHPSS trainings.

WHO delivered a briefing to FCDO on their Winter Risk Assessment, which analysed the potential effects of winter on vulnerable populations in Ukraine. This highlighted the significant vulnerabilities of older persons and persons with disabilities, informing both FCDO programme design but also the overarching response.

Learning – Moldova
The FCDO programme team have also hosted (early 2024) a partner day with Moldovan implementers. This was used to discuss project synergies, contextual overlaps, areas for improvement and to obtain feedback. This provided a productive opportunity for partners to share and discuss lessons learnt, as well as to identify further areas for collaboration.

In the Moldova context reflective exercises, sometimes through FCDO facilitated roundtables, have helped strengthen discourse on humanitarian-development-peace nexus approaches and strengthening national systems for service delivery to meet the needs of refugees and vulnerable Moldovan groups. This is important as longer-term more sustainable solutions to vulnerability are better delivered through national systems rather than humanitarian actors where funding will inevitably decline.

In Moldova the programme team plans to capture learnings from partners, and other contexts, to develop a roadmap to guide the transition of humanitarian interventions, over a period of time, into the development space. Moldova has potential to provide learning on how humanitarian response efforts can be delivered through, and in support of, national systems, and further the evidence base on the cost value of shock-responsive social protection systems which could be applied in other contexts. There is scope for learning on how the national social protection system can be further supported to enable the inclusion and integration of refugees into the host community, whilst contributing to social cohesion efforts.

Summary
This period illustrated good progress on aspects of the MEL approach, mostly on monitoring. Further work is needed to bring up performance on evaluation and learning. This is not unique to FCDO’s humanitarian work in Ukraine and applies to many programmes, most of which are at a relatively early stage of genesis or now operating in a vastly changed context. BE Kyiv is currently developing a successor monitoring programme and a holistic approach to evaluation. The Humanitarian team will dock into these efforts.

Prior sections have relevant recommendations on monitoring. A refreshed MEL approach will be picked up in the implementation of the successor programme.

ANNEX A: Recommendations

	Recommendation	Target	Owner
1	Governance and logframe / Review and rationalise logframe for FY24-25 and identify a shorter set of more focused objectives. Lessons from the FY23-24 logframe to inform HARP logframe development. / Building on the IAD audit of the programme, and in preparation for the mobilisation of the successor business case, review and refresh programme governance.	March 2025 (Logframe) / October 2025 (Governance review)	Senior Programme Leads
2	Strategic alignment and use of analysis / ACAPS should deepen its engagement with local analysts and coordination platforms, such as the Alliance of CSOs, to foster local analytical capacity and relevance with the goal of enhancing analytical sustainability within the response.	31 March 2026	ACAPS
3	Advocacy on IHL / Through partner organisations (XXXXXXXXXXXXXX and URCS, but others too) deliver advocacy on humanitarian access and protection and observance of IHL. Supplement this with diplomatic engagement through BEK and FCDO. Specifically, FCDO to map: types, range, and channels of IHL, access, and protection advocacy; and to include 1-2 case studies of advocacy in action in the second HARP annual review.	30 June 2026	Humanitarian Adviser working with EECAD
4	Design of capacity building interventions / Design future capacity building to factor in the need for in depth consultation to ensure alignment with government needs and priorities as well an enable flexibility to adapt to changing capacities and priorities.	April 2026	Social Development Advisers
5	Localisation / Set out headline learning on localisation in Ukraine, enablers and barriers, and BEK approach. / Discuss with Humanitarian Department (FCDO) during inward visit of BEK partners. / Track and capture in one place how funding flows through FCDO intermediaries to local actors. / Finalise comprehensive review of FCDO’s efforts on localisation across the portfolio to draw out further learning, inform future partnerships and strengthen advocacy, and present this to FCDO senior officials.	September 2025 (approach paper) / November 2025 (discuss findings) / December 2025 (funding flow tracking) / January 2026 (comprehensive paper and presentation to senior officials)	Lead Adviser and PRO
6	Crisis and scenario planning / Develop scenario planning for humanitarian risks with the development of triggers. Ensure the future programme portfolio contains actors who have capacity for large-scale shock responses.	31 December 2025	HARP SRO, PRO and Lead Adviser
7	Value for money / Define a value for money strategy and indicators for successor programme based on lessons learned from the first two years of programming at scale. Efforts should be made within this develop a standardised 5Es assessment criteria across interventions and better beneficiary data disaggregation.	31 March 2026	HARP PRO

ANNEX B: Breakdown of funding by partner

Partner	Activities funded by FCDO	Geographies	Total funding received in the period of the Annual Review
WHO (including Humanity & Inclusion)	System Strengthening Rehabilitation Support / MHPSS / Disability Inclusion	Ukraine - Nationwide	£2,669,794
Women’s Peace & Humanitarian Fund (WPHF)	Capacity Building for WROs/WLOs / GBV response / MHPSS / Legal assistance / Vocational/professional training / Socio-Economic Recovery / Shelter	Ukraine - Nationwide	£3,000,000
OCHA & Ukraine Humanitarian Fund (UHF)	Shelter/NFIs / Protection Assistance / Food Security / Health / WASH / MPC / Mine Action / Education / GBV / Child Protection	Ukraine - Nationwide	£37,100,000
XXXXXX	XXXXXXXXXX / XXXXXXXXXX / XXXXXXXXXX / XXXXXXXXXX / XXXXXXXXXX / XXXXXXXXXX / XXXXXXXXXX	XXXXXXXXXX	XXXXXXXXXXXXXXXXX
Standby Partnerships (UN via HSOT)	Staffing costs	Ukraine –Nationwide / Poland / Latvia / Romania	£374,036
Nonviolent Peaceforce / HAVEN	Protection / IHL Training / In-kind support / CSO support/training / Data Analysis / Evacuation support	Odesa / Mykolaiv / Kharkiv / Kherson / Zaporizhzhia	£7,440,059
IOM	MPCA / Livelihood support / Critical Infrastructure Support / MHPSS / Data Analysis / WASH	Ukraine - Nationwide	£17,750,000
STAAR	Research and Analysis to strengthen Social Protection and Humanitarian Cash and Services linkages	Moldova and Ukraine	£1,330,677
Mercy Corps	MPCA / In-kind assistance / PSS / CSO training / Shelter / Legal and employment support	Donetsk / Kherson / Dnipro / Kharkiv / Zaporizhzhia Mykolaiv / Sumy / Zakarpattia	£16,475,000
Ukrainian Red Cross (via British Red Cross)	MPCA / In-kind assistance / Disaster response and recovery / Shelter / Healthcare and rehabilitation / Humanitarian Diplomacy	Ukraine - Nationwide	£13,753,001
ACAPS (via British Red Cross)	Data analysis	Ukraine - Nationwide and wider region	£688,961
WFP	System strengthening - shock prevention Cash / Food and nutrition Refugee services	Moldova	£3,000,000
UNFPA	Social protection and system strengthening GBV prevention and response Health - emergency services for women, girls and elderly Refugee services	Moldova	£3,000,000
UNICEF	Social protection and system strengthening Healthcare - maternal and child, mental health Education Refugee services	Moldova	£4,500,000
[note] Implementation of activities in 24/25 FY
[note] FCDO funding not attributable – activities listed from partner’s Annual Report, not donor specific.