Programme Completion Review
FINAL

Title: Ukraine Humanitarian Response Programme (UHRP)
Final Programme Spend £ (full life): / Total (full life): £418m	2021/22: £53m, / 2022/23: £167m / 2023/24: £137m / 2024/25: £62m	Review Date: 30/06/2025
Programme Code: / [AMP ID#] 301497	Start Date: / 24/02/2022	End Date: / 31/03/2025

Summary of Programme Performance

Year	2023	2024	2025
Programme Score	A	A	A
Residual Risk Exposure Rating

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/D0005124.odt / https://iati.fcdo.gov.uk/iati_documents/D0006054.odt
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-301497/documents
DevTracker Links to Annual Reviews (2023 and 2024):

Contents

## A. Summary and Overview

Description of the programme

The Ukraine Humanitarian Response Programme was initiated following the Russian full-scale invasion of Ukraine in February 2022 on an emergency rules basis. It was the largest ‘no regrets’ commitment of humanitarian support made by HM Government at the outset of a crisis.

The programme, supported by broader advocacy efforts, aimed (i) to provide protection and life-saving assistance to the most vulnerable and at-risk populations, including internally displaced persons, people with disabilities, women and girls and older people, across Ukraine and the surrounding region; (ii) to work with allies to ensure the international humanitarian system delivered an effective (well-coordinated and well-funded) response; and (iii) to call out malign activity and press for respect for International Humanitarian Law, particularly access.

The programme initially operated in multiple geographies primarily in Ukraine, but also countries in the region where Ukrainian refugees fled. Support was streamlined in the second year of the programme to focus on Ukraine and Moldova only. In July 2022, the original Business Case retrospectively approved up to £220 million for activity in financial years 2021/22 and 2022/23. An additional £199 million was approved in January 2023 under a Business Case Addendum. A no-cost extension was subsequently granted, taking the programme end date to 31 March 2025 and allowing for the transition to a new multi-year humanitarian programme which commenced in October 2024.

The programme’s original outputs were to provide life-saving assistance, protect people from violence and support the international system to coordinate the response working closely with the Government of Ukraine and regional governments.  From year two, the programme team iterated a more developed strategy sitting under the outputs and the programme in Ukraine and Moldova was shaped around five strategic priorities. Output-level assessments in this Review are based on these strategic priorities in line with a refinement in the theory of change[1].
[1] This shift is fully detailed in the 2024 annual review.

Activities and project partners have evolved significantly from the initial response through to the end of the programme as the programme moved from broad-based emergency appeals, both country and regional, to bilateral partnerships. Between 2022-2025, the programme delivered support through 19 partners, as well as providing in-kind assistance through bilateral programme CDEL (first year only) and RDEL budgets, and funding standby partnerships[2]. A full list of partners and spend can be found at section G.
[2] Standby partnerships are funding for short term humanitarian expertise embedded into United Nations organisations.

The initial emergency response prioritised meeting urgent needs at speed, working through trusted partners to ensure delivery and adherence to FCDO compliance standards. In-kind and logistics support were delivered primarily through Palladium, with other support provided though the Red Cross and UN. The programme subsequently increased its focus on quality, transitioning towards activity supporting greater localisation, inclusion and resilience, and from a focus on in-kind to cash support. Throughout the programme, a significant volume of funding has been allocated through pooled funds.

The programme has scored an ‘A’ overall for outputs in 2024/25 demonstrating that implementation was on-track. The programme also achieved an ‘A’ in both the first and second years of operation. Output indicators over the three years have shifted considerably as activity has adapted by necessity to contextual shifts making a year-on-year comparison of performance difficult. In all three years, outputs objectives have been generally met, delivering impact across the three original programme objectives, with a clear demonstration of programme agility, praised in the ICAI rapid review. There have been notable challenges in maintaining respect for International Humanitarian Law, achieving humanitarian access to territory controlled by the Russian Federation, and some aspects of monitoring.

Humanitarian context

By April 2025, more than three years after the full-scale invasion, 3.7 million people remained internally displaced in Ukraine, and 5.1 million continue to seek refuge in Europe. Two-thirds of internally displaced persons (IDPs) had been displaced for over two years. There were over 1,000 Collective Sites hosting IDPs across the country, struggling to meet the needs of the high rates of people with disabilities and older people that they were receiving. Compared with 2023, 2024 and 2025 saw rising casualty rates due to the intensity of frontline attacks; increased use of long-range missiles and loitering munitions; and attacks using aerial bombs on larger cities[3]. Year-on-year humanitarian needs have increased in severity across all sectors of the humanitarian response[4]. Throughout 2024 and into early 2025, rates of incidents involving violence against humanitarian personnel, assets or facilities increased, with worsening humanitarian access in many areas[5].
[3] 2025-03-21 OHCHR Report on Children's Rights in Ukraine.pdf
[4] REACH Ukraine Calibration Assessment 2024-2025 (March 2025) - Ukraine | ReliefWeb
[5] Ukraine: Humanitarian Access Snapshot (January to February 2025) [EN/UK] - Ukraine | ReliefWeb

As the programme closes, the humanitarian situation remains severe, with around 12.7 million people – one in three Ukrainians – estimated to require humanitarian assistance in 2025[6]. The suspension and reduction of funding by key donors (including USAID) in early 2025 created significant additional unmet needs; the 2025 Ukraine Humanitarian Needs and Response Plan (HNRP) remains less than one-third funded at the end of June 2025. With protracted humanitarian needs and diminishing global commitments, we must maximise the VfM of the FCDO’s humanitarian programming, balancing immediate humanitarian impact with longer-term resilience and system strengthening. Lessons and recommended actions set out in this Review can support this goal.
[6] Ukraine: Summary of the Humanitarian Needs and Response Plan and the Regional Refugee Response Plan (January 2025) [EN/UK] | OCHA

Reflections and recommended actions

This section captures six strategic reflections from the programme. Some of these strategic reflections include one or more recommendations for action, which focus on areas not already taken forward within the successor humanitarian programme or through FCDO’s broader policy, influencing and advocacy.

Localisation

Advance efforts to further localise humanitarian response efforts to i) ensure continued to support needs in frontline areas where international actors are unable to operate and ii) longer-term enable Ukraine to meet the basic needs of its population and address future shocks. Investing in local capacity is a more sustainable model for humanitarian response in Ukraine over the long term, recognising that international funding for humanitarian will continue to decline. Consider:

Adopting ‘local first’ (or ‘if not local, why not’) approach to FCDO humanitarian strategy and programming in Ukraine, underpinned by political and institutional support. Unlocking this fully may require shifts from traditional models of FCDO programming.

ACTIONS:
1. Agree a benchmark (%) for the amount of funding to be channelled directly toward local partners under the new humanitarian programme by end of FY 25/26 (owner: PRO).
2. Directly fund a local partner and/or consortium by end of FY 25/26 (owner: SRO).
3. Enhancing monitoring and evaluation of our support to local actors to better understand, and communicate, how this is impacting quality and VfM. Commission TPM provider and/or other resource to conduct evaluation by end FY 26/27 (owner: PRO).

Resilience and recovery

1. Develop a clearer strategy and theory of change regarding the contribution of our humanitarian programming to resilience and recovery efforts in Ukraine. Set out how our funding will strengthen systems, including social protection, and ensure integration with the wider FCDO portfolio. This will help ensure our programming remains adaptive and relevant to an evolving, protracted crisis. Consider:
2. Pursue greater alignment with other FCDO programmes (e.g. SPIRIT and Programme for Resilient Ukraine) working on recovery, resilience and system strengthening. Work toward collective outcomes and Theory of Changes.

ACTION:
Agree collective strategy and ToC by end of March 2026, to align humanitarian with other relevant programmes (owner: SRO).

Reaching the most vulnerable

Ensure that our future programming in Ukraine delivers targeted, high-quality assistance that is tailored to and inclusive of the needs of the most vulnerable. This will ensure we maximise the impact of our funding, as well as addressing persistent issues across the humanitarian response in Ukraine relating to poor quality assistance and accountability to affected populations. Consider:

Develop a monitoring and results framework which is better able to track and assess key metrics relating to support to vulnerable groups across all future programme outputs. This should cover measures included in the British Embassy Kyiv Humanitarian Partnership Principles. Include qualitative metrics to track and assesses feedback from beneficiaries as to the quality of assistance received.

ACTIONS:
1. BEK Monitoring and Evaluation Adviser to support programme team in reviewing and refreshing M&E and results framework by November 2025 (owner: PRO).
2. Conduct an evaluation of the quality of assistance provided by our partners to test whether our partners are implementing an inclusive approach, by June 2026 (owner: PRO and SDA).

Coordination

Utilise FCDO programming, thought leadership and influence to strengthen coordination efforts, especially around cash, across the response. Tackle persistent coordination issues and the risks these pose to the effective delivery of our aid, and to our reputation, as well as to the wider response.

ACTIONS:
1. Develop an internal cash strategy, providing series of policy and programmatic recommendations and underpinning work plan, by end of January 2026. As part of this consider use of benchmark (%) programme spend to be via cash interventions. Promote and track progress against principles from the ‘Common Donor Approach to Humanitarian Cash Assistance[7] (global guidance endorsed by FCDO centrally) (owner: SRO).
  [7] https://www.calpnetwork.org/publication/common-donor-approach-to-humanitarian-cash-assistance-2025/
2. Implementing recommendations from the PereHID initiative, adjust our humanitarian response to strengthen linkages between humanitarian cash assistance and enabling an effective national social protection system (aligning with SPIRIT). Agree, internally, which PereHID recommendations to take forward, and develop an implementation plan as part of internal cash strategy development, by end of January 2026 (owner: SRO).

Monitoring and evaluation

Revamp and bolster monitoring and evaluation across humanitarian programming in Ukraine, including enhancing results frameworks (including logframes) and value for money assessments, to more clearly demonstrate and communicate the collective impact and VfM of our funding. The programme team should consider the following

ACTIONS:
1. Secure dedicated evaluation advisory capacity to support the design of the monitoring and results framework for the successor programme, Humanitarian Assistance, Recovery and Protection Programme (HARP). Ensure the programme’s Theory of Change can articulate the intended totality and impact of all outputs/partners’ activities. Target: November 2025 (owner: PRO).
2. Secure dedicated resource to conduct comprehensive VFM assessment and to support VFM design/strategy for HARP – by March 2026 (owner: PRO).

Compliance

Ensure we remain compliant with FCDO Programme Operating Framework rules and other processes; retain strong oversight of our programme and are enabled to make effective decisions.

ACTION:
Work towards normalising and stabilising programme processes following three years of emergency rules (whilst acknowledging challenges in FCDO operating model, predictability in funding, and staff resources) (owner: PRO).

How this Review was conducted

The objective of this review was to provide an assessment of the full performance of the programme since inception, based upon (i) an assessment of output performance against targets for the final year of the programme (2024/25), through a review of logframe indicators for the six programme outcomes (five for Ukraine and one for Moldova); and (ii) outcome and impact narratives at output level and at programme level since programme inception.

The review was conducted by members of the programme team, with significant input from an external reviewer to challenge and strengthen conclusions and recommendations. The review team drew upon evidence from ongoing partner engagement, partner reporting, reports from TPM, previous annual reviews, and targeted interviews with partners, UN agencies and donors. Security restrictions once again prevented the team from interviewing beneficiaries in Ukraine outside of Kyiv as part of this review, however TPM reports providing beneficiary testimony were reviewed.

Actions following approval of this report

The review identifies reflections and lessons learned through programme implementation. This learning will be used to inform future humanitarian programming in Ukraine. Following the review, the review team will share lessons learned across the FCDO, and as appropriate, with programme partners, to improve future performance, delivery and efficiency.

Audited financial statements will be provided by partners in line with the requirements set out in project agreements. These will be provided within 18 months of the end of the programme, in line with programme closure deadlines. Submission of some final financial reports will take place after the publication of this review. Final reports received after publication will be reviewed by the programme team, and feedback provided to partners. As of 30 June 2025, there are four open cases of aid diversion, which are being closely monitored. They are expected to be concluded by the end of the programme closure period (September 2026).

## B: Theory of Change and Outcome Assessment

Reflections: approach and outcomes, UHRP 2022 – 2025

This section provides an overview of key reflections on the evolution of the programme between February 2022 and March 2025, appropriateness of the approaches taken, and key outcomes. Year 1 of the programme (2022/23) represented a huge scale up in funding, at pace across multiple contexts, and from a standing start, with no pre-existing FCDO humanitarian programme in place in Ukraine and limited international presence in-country. The programme was founded on a “no regrets” approach, given the scale and unpredictability of the crisis, resulting in much of the UK’s funding being unearmarked and channelled through UN Red Cross and Disasters Emergency Committee (DEC) appeals. This focussed on blanket coverage and speed of support rather than targeted assistance.

This was the appropriate strategy at the outset of the crisis given the type of shock and the scale and volatility of the emergency. The UK’s support helped to kick-start humanitarian operations in Ukraine, and regionally, and our flexibility in approach, including the wide range, and number, of partners and use of unearmarked funding, enabled the provision of life saving assistance and protection support (the intended outcomes), covering multi-sectoral needs in Ukraine and the wider region. It should be noted, however, that the international response, particularly the UN, has been criticised for a perceived issue with speed of response and effectiveness of delivery in the early stages of the crisis. This was, in part, due to limited preparedness and anticipatory funding made available by donors ahead of Russia’s full-scale invasion but is also reflective of a very fluid situation as the frontline, and associated access, shifted and the sheer scale of need and population movements across borders. The UN and XXXXXXXXXXXX have faced significant challenges to their mandates and operating models in Ukraine, a context in which the multilateral system is under serious challenge.

While Ukrainian capacity and resilience at all levels of government and civil society is widely acknowledged, relying on government systems and/or supporting local CSOs to deliver humanitarian assistance in the first year of the crisis would have been unrealistic, and directing our support through international actors was the appropriate channel. Ukraine faced a shock of such magnitude and speed that systems – national and local, were overwhelmed, and needed time to reorganise and reestablish themselves. A more important lesson for FCDO, and the wider international community, was to have funded anticipatory action for international humanitarian actors to be better placed to scale up response efforts.

The significant scale-up of funding in the first year of the crisis, and associated plethora of humanitarian actors operating in Ukraine, has contributed to issues regarding the coordination of aid and the targeting, quality and delivery of assistance. This significant funding injection, coupled with pressure from donors to spend quickly, disincentivised the humanitarian system in Ukraine to coordinate in an effective manner and there are persistent issues regarding the duplication of aid and the relevance (type and timing) of assistance provided by some actors. There remains limited reference to accountability to affected populations across the response implying that interventions were not people-centred and were instead largely supply, rather than demand driven. Cash coordination is perhaps a microcosm of these issues. Assistance does not consistently follow global guidance and commitments regarding multi-purpose cash.

The second and third year of the programme represented a clear evolution and adaptation in our humanitarian strategy and the programme. This includes a rebalancing of our partnerships, with reduced support to UN agencies and greater weighting toward INGOs and, indirectly, local actors, while continuing support to the Red Cross movement partners. The programme has developed a more targeted approach, focused on bilateral partnerships, earmarked funding and niche issue-based/thematic-focused programming alongside closing out support in refugee hosting countries except for Moldova. This represents an adaptive, responsive programme, that is relevant and tailored to the needs it is attempting to support and the context within which it works.

As part of this more targeted approach, protection has been prioritised. This includes a range of protection interventions delivered by programme partners to prevent, mitigate and address conflict-induced harm. This is an appropriate strategy given the response in Ukraine is fundamentally a protection emergency. This approach presents a key area of added value for FCDO and the wider humanitarian system, particularly in light of global funding cuts which will hit protection and inclusion programming and partners the hardest.

Demonstrable progress has been made towards a more localised response, both within the programme and through influencing of wider response efforts, delivering on a key recommendation within the Independent Commission for Aid Impact’s review 2023 of UK aid in Ukraine. The establishment of the HAVEN consortium, support to Mercy’s Corps sub-grant and locally led cash model, and bolstering Ukraine Red Cross Society capacity are examples of good practice in localising response efforts. FCDO has utilised its funding, and its place on the advisory board, to advocate for UHF to channel a greater level of direct funding to local organisations.

This approach is vital given it is local actors that are able to access the hardest to reach areas and almost solely manage last mile delivery in front-line areas where needs are most severe (contributing to both Outcome 1 and 2 of the programme). This has enhanced the VfM and impact of FCDO funding, as well as presenting a more sustainable approach to humanitarian programming through bolstering Ukrainian capacity and resilience.

As the programme has evolved, greater emphasis has been placed on the use of multipurpose cash assistance (MPCA) to respond to emergencies and as the key modality to support basic needs. Partners have been in part selected based on their ability to deliver cash assistance to a high standard (e.g. Mercy Corps). Other partners have been pressed to enhance, and scale, their cash interventions (e.g. URCS). The prioritisation of cash assistance is an appropriate approach given the Ukraine crisis is defined by a diverse set of multi-sectoral needs and an evolving context, requiring both the provision of immediate as well as longer-term assistance in response to both conflict-induced and deteriorating socio-economic conditions. This represents an efficient and cost-effective way to provide support, and more adequately responds to preferences and needs by empowering crisis-affected people to make choices as to what they the need the most (in support of Outcome 1). This drives VfM and maximises the impact of UK funding. MPCA support of basic needs is also contributing to Ukrainian household resilience to shocks and supports early recovery efforts by strengthening local economies. Ukraine is a protracted emergency, displaying many of the hallmarks we see in other long-term crises.  It is increasingly characterised by socio-economic shocks as well as conflict shocks, with needs deepening and likely to become more complex for many years to come. Ukraine is unlikely to be able to meet the needs of its population in the short- to medium-term; development actors and the private sector are unlikely to be able to fully plug the gap. UK support should plan for and adapt to this, acknowledging and building upon the resilience and recovery activities already delivered through the programme.

Overall assessment of programme outcomes

The original emergency rules business case, providing the basis for an evolving and responsive programme, included two outcomes but no outcome indicators. Considering the two outcomes (provided in the table below) in turn:

- Outcome 1: the programme has consistently performed strongly in delivering impact in supporting and responding to the protection needs of conflict affected people in Ukraine, providing the flexibility in funding and partnerships to adapt to changing needs across the lifetime of the programme.
- Outcome 2: Access has remained a challenging issue for the programme and our partners. Access for most partners to occupied and frontline areas, and to detainees, has been contested and limited. This issue remains largely outside of the scope and control of the programme.

	Starting point	Final result
Budget	£220m	£419m
Timeframe	13 months, 13 days	3 years, 1 month and 13 days
Outcomes / (Descriptive only – no outcome indicators available.)	The basic and protection needs of conflict affected people in Ukraine and the region are met. / Humanitarian workers (and agencies) are afforded access to conflict affected populations and detainees.	Strong performance against Outcome 1 / Outcome 2 removed: challenges largely outside of the scope of the programme, although significant efforts made to maximise access within available security and partner capacity constraints.

Programme outputs have met expectations in all three years of the programme, resulting in the overall Programme Score, “A”, and supporting the achievement of Outcome 1, the meeting of basic and protection needs. Though output indicators demonstrated some positive progress on access, full achievement of this Outcome ultimately fell out with the scope of the programme.

Almost all output indicators were achieved in line with targets and within the original (and subsequently extended) timeframe and budget. There were some notable exceptions:
- The withdrawal of funding to IOM in 2024 led to no delivery against sub-output 1.2 in the final year of the programme. (Please see Detailed Output Assessment for Output 1).
- There was consistent, moderate overperformance against output indicators in activity in Moldova, which may be partly attributable to effective Government-donor-civil society coordination.

VfM and Sustainability

VfM for this programme focussed on the speed of the response as the key VfM consideration, with an increasing focus on quality as the response progressed. As is typical in a crisis response, initial programme design did not include VfM indicators and it is therefore not possible to compare the VfM of the programme as a whole to the VfM proposed in the business case. As noted above, the programme performed strongly against Outcome 1; VfM was enhanced through choices about interventions and modalities, such as the emphasis on localising the response and expanding MPCA to support basic needs demonstrating strong evidence of cost-effectiveness.

Regarding equity, the programme exceeded targets for the enhancement of CSO capacity to respond to essential needs of highly vulnerable populations, including through the promotion of gender equality and social inclusion and the allocation of funding to protection programming. The programme also delivered effectively on goals to better incorporate disability inclusion into the humanitarian lifecycle. Further detail on equity and inclusion can be found in the detailed output assessment for Output 2. A more detailed account of programme VfM can be found in section E, Value for Money.

Much of the activity over the programme lifetime – particularly in year 1 – was the provision of emergency assistance. Continued Russian aggression means that humanitarian needs will persist. Continued support to local actors and vulnerable conflict-affected communities, and system strengthening to support social protection provision and prevent the persistence of parallel protection systems, have increased the sustainability of the response in the short- to medium-term. The increased focus on sustainable recovery in years 2 and 3 sought to lay the foundations for transition to longer-term solutions in regions less intensively affected by ongoing conflict.

Theory of change and results framework

1. The overarching objective of the programme was “to help ensure that lives are saved and the most vulnerable people are protected in Ukraine and in the neighbouring region.” The theory of change statement supporting this is below.
  If the international humanitarian system is coordinated, well-funded and localised, and works closely with the Government of Ukraine/regional governments then it is possible to effectively:
  - Provide conflict affected people in Ukraine and the region with life-saving assistance that is adapted to the specific needs of different groups such as children, women, the elderly, detainees, internally displaced people and refugees.
  - Protect people from violence (including protecting against GBV and supporting survivors).
  - Enhance the skills and capacity of humanitarian workers (and agencies) to advocate for freedom of movement to access people in need.
  FCDO’s support to the outputs above then contributes to meeting the overall immediate basic and protection needs of people affected by the conflict (food, shelter, water, cash etc.).
2. Key assumptions were as follows:
- Implementing partners spend in line with Humanitarian Response Plan (HRP) and other donor commitments realised.
- Response structures and humanitarian actors can adapt to a fluid context.
- Sanctions do not impede ability to support humanitarian action.
- Political, military and security situation does not deteriorate to the extent that humanitarian actors cannot operate effectively, and the Government of Ukraine continues to operate.
- FCDO can hold space for principled humanitarian action commensurate with the scale and severity of needs.

The assumption that capacity, coordination and advocacy would unlock access to people in need has not universally held; many areas remain inaccessible and the solution to this lies beyond the programme mandate. Risks to other key assumptions were either not realised, or broadly managed by the programme team, donors and partners. Coordination also presented challenges for donors and partners, and in engagement with Government, although an increased focus on empowering local actors led to improved coordination and responses at local levels.

FCDO’s flexible approach supported partners in adapting to the changing context and to learning from initial phases. The programme was designed with the expectation that its response structures and partners would be able to flex to the changing context and needs. The evolution from the strategy, activity and partners pursued in the initial response to those deployed in subsequent years demonstrates significant agility in the programme. Within partner agreements, the team also demonstrated considerable flexibility in approving changes within, and sometimes between, agreed activities in response to partners’ assessments of need and evolving understanding of what works.

The results system for the initial response focussed on tracking (i) Life Saving Assistance; (ii) International Humanitarian System coordination and funding and support to government; (iii) Humanitarian Protection and Access. 72% of the initial £220 million committed through the programme was unearmarked funding to UN agency appeals, which significantly limited results data in year 1 to that provided by UN self-reporting. The results framework was expanded in years 2 and 3 to introduce logframes and allow for the collation of data on beneficiaries reached on a sector-by-sector basis for both Ukraine and Moldova. Data was not consistently disaggregated to enable analysis of how FCDO funding was improving outcomes for specific vulnerable groups across the whole of the response.

## C: Detailed Output Scoring

Note on Output Scoring Methodology

Each output in this section refers to a strategic objective within the final Ukraine Humanitarian Response Programme logframe. Outputs are scored on the basis of results from partners who contributed to that objective in 2024/25. Partners operating in Ukraine may contribute to multiple outputs. Moldova is a separate output, organised by the strategic objectives within the Moldova programme logframe. All Moldova partners are scored under this output.

The outputs table sets out the programme’s six outputs and their weightings for 2024/25, alongside the score allocated for activity in 2024/25. Score descriptions are also provided. The weightings were derived from the proportion of programme budget allocated to Moldova (10%), and the weighting of each strategic objective agreed in the Ukraine logframe. This weighting was used to calculate the overall scoring of the programme in the 2024/25 review period.

Outputs	Weighting (%)	24/25 score
1. Ensuring protection and prioritisation of the most vulnerable by using our funding and advocacy to drive effectiveness in the international humanitarian response.	38%	A
2. Promoting access, inclusion and respect for international humanitarian law (IHL) by working diplomatically and via technical engagement with the humanitarian system.	13%	A
3. Promoting sustainable recovery by developing humanitarian-development synergies to ensure we build government capacity to respond.	8%	A+
4. Developing a more localised response, harnessing Ukrainian capacities by more equitably balancing funding of the international response with support to local actors.	18%	A
5. Maintaining flexibility, scanning the horizon, and adapting to evolving priorities and emerging risks should humanitarian needs spike.	13%	A
6. Activities in Moldova.	10%	A+

Scores have been included for appeal/unearmarked funding to UHF and XXXXX however, these are based on qualitative assessments of partners’ performances, due to the absence of targets. UHF and XXXXX results are not 100% attributable to FCDO, as UK contributions are pooled with funding from other donors.

## D: Detailed Output Assessment

This section reviews the six programme outputs in more detail. For each output, there is:
- A table showing output indicators and targets for 2024/25 against final results, with a score allocated for each indicator.
- An output description.
- A 12-Month Review, describing delivery partners, activities, performance and achievements in 2024/25; and providing an output score for the final year’s activities and justification for this score.
- A three-year strategic review of the programme’s performance under the output themes, providing reflections, lessons learned and recommendations for future programming.

Output Number and Title	1: Ensuring protection and prioritisation of the most vulnerable by using our funding and advocacy to drive effectiveness in the international humanitarian response.
Output Score	A (Outputs met expectations)
Impact weighting (%)	38%	Impact weighting revised since last AR?	Impact weighting increased from 37% to 38%

Output Indicator	Target	Final Result	Difference	Score
Sub Output 1.1 - Vulnerable individuals are targeted through an inclusive mechanism and supported in meeting basic needs through cash assistance (MPCA, Winterisation)
1.11 [URCS; Mercy Corps] # of people receiving multi-purpose cash.	6,097 / 18,750	9,568 / 25,910	+57% / +38%	A
1.12 [Mercy Corps] % of participants reporting satisfaction with assistance (INDEX; contents, quantity, quality, appropriateness).	90%	97%	+8%	A+
Sub Output 1.2 - Critical humanitarian support reaches the most vulnerable populations in Ukraine.
1.21 [IOM] # of individuals who receive sustenance grants, disaggregated by age, gender and disability.	4,212	0	-100%	C
1.22 [IOM] # of households supported with non-food items (NFIs) via the Common Pipeline, disaggregate by ages, genders, veteran status and disability status.	6,500	0	-100%	C
Sub Output 1.3 - Humanitarian Response Coordination and Planning.
1.31 [OCHA] OCHA Ukraine Office meeting its strategic objectives.	n/a	n/a	n/a	n/a
Sub Output 1.4 - Quality assessments and information products produced and disseminated to relevant and engaged audiences to increase use of analysis for decision making.
1.41 [ACAPS] Use in decision making / % of survey respondents confirm that the product was useful/informative/shaped their decision making or work processes.	70%	90%	+29%	A+
1.42 [ACAPS] Engagement/active participation / # of joint analysis sessions held / # of INGOs and NNGOs attending joint analysis sessions / training.	9 / 50	9 / 50	- / -	A
Sub Output 1.5 - Multi-sector humanitarian support.
1.51 [UHF] Number and percentage of targeted people in need reported to have been reached by partners through the Fund’s allocations (standard/reserve) disaggregated by gender, age, sector and geographic area.	No target set	266,000 / 1,400,000*	-	n/a
1.52 [CBPF] Efficient prioritisation – CBPF funding is prioritized in alignment with the HNRP.	No target	Allocations launched in line with HNRP	-	A
1.53 XXXXXXXXXXXXXXXXXXXXXXXXXXX / XXXXXXXXXX.	XXXXXXXXX	XXX	X	XXX

*UHF report on a calendar year basis. UK funds into the pooled fund are not earmarked. Unspent funds from previous years roll over into subsequent years. For these reasons, attribution of results to UK funding can only be an approximation. 266,00 is a 19% proportion (based on UK contributions in 2024) of the total result for people reached (1.4M) through the Fund in 2024, as reported in the Ukraine Humanitarian Fund Annual Report 2024.

Output Description

This output is about identifying the most vulnerable in Ukraine and meeting their most basic needs through a range of partners. Support has been provided through various forms of assistance, including cash, in-kind, service provision, livelihoods support, case management, shelter and water, sanitation and heating (WASH) assistance. This has included the provision of assistance to frontline areas in the South and East of Ukraine, where needs have been most severe, as well as support across the rest of Ukraine and, in year 1, in neighbouring states. This response was supported through effective humanitarian response coordination and planning, and based upon quality evidence and assessments of need to enable effective decision-making. The response put an emphasis on inclusion and the monitoring of the needs of and support to vulnerable populations.

12-Month Review for Output 1

Introduction

Partners under this output provided humanitarian assistance to the most vulnerable in Ukraine, often in hard-to-reach areas close to the front lines. This output included both earmarked, project specific funding and pooled funding to humanitarian funds and appeals. This output has been scored overall an A for 2024/25, “output met expectation”.  This reflects the meeting and exceeding of all indicator targets with the exception of Sub Output [1.2]

Sustenance grants were to be provided to 4,212 people by IOM during the reporting period, however this activity, and the distribution of NFIs, was cancelled due to FCDO’s decision in October 2024 to suspend project funding in response to reported allegations of potentially significant aid diversion within IOM. The funding suspension was in line with FCDO rules governing aid spend, to safeguard UK taxpayers' money. This resulted in the targets for sub-output 1.2 not being met. IOM subsequently restarted the distribution of NFIs, using funding from a different donor (thus enabling achievement of target 1.22; the final result for this activity shown in the table above is nil due to the withdrawal of FCDO bilateral funds). Seventy-eight per cent of the funding allocated to IOM in 2024/25 was returned to the FCDO and/or reallocated across the programme.

Cash Assistance

Cash remains the most dignified, flexible, and cost-effective way to meet people’s basic needs, and in most cases is what people in Ukraine prefer to receive. Continuing from 2023/24, several FCDO partners provided cash assistance to beneficiaries in 2024/25 to support them with their basic needs, and with specific winter top ups to help households meet additional costs in colder months, and in the expectation for attacks on Critical National Infrastructure and energy black outs. This included URCS and Mercy Corps through earmarked funding, and UHF and XXXXX through their multi-sector humanitarian support (see below).

In 2024/25, Mercy Corps reached 25,910 programme participants with cash transfers, including rapid cash. While Mercy Corps have exceeded their target significantly, this was due to receiving an additional top-up of £1 million, designated for MPCA distributions only. Targets were not adjusted as the top-up was provided after the logframe had been finalised; accordingly, this sub output has been allocated an “A” despite exceeding the targets set. Partners such as Mercy Corps gathered beneficiary feedback on cash assistance and exceeded their target with 97% of all beneficiaries reported being satisfied with the assistance they received.

URCS also provided cash assistance through winter cash, and through targeted interventions for households where someone has acquired a disability or financial support to vulnerable families whose relatives are missing due to military action. URCS significantly exceeded their target with 9,568 people receiving cash assistance. In line with PereHID Initiative recommendations, URCS worked with the former Ministry of Reintegration of Temporarily Occupied Territories to utilise government lists of vulnerable households, aiming to leverage the scale and knowledge of the government.

Following a request from local authorities, additional households were reached with cash for winterisation in Mykolaiv and Kharkiv Oblasts through utilising exchange rate savings and savings across other budget lines. Of respondents of the post-distribution monitoring for winterisation relief, 93% indicated that the waiting time between registration and delivery of assistance was appropriate and 99% were satisfied with the overall participation in the programme. More than 75 % of respondents confirmed that all or most of their winterisation needs were met after receiving cash assistance through URCS’ programme, a further 20% confirmed some of their needs were met[8]. Utilities, medication and clothing were the top three areas that beneficiaries spent the money on.
[8] The basic needs that households were unable to meet after receiving winter cash included: medicines, utilities and health services. URCS recommended that further needs assessments could be conducted in these regions to identify exisiting gaps and address specific sectoral needs.

Multi-sector humanitarian support

In 2024/25, FCDO continued to provide funding for multi-sector humanitarian support for the most vulnerable, war affected people in Ukraine, in line with the 2024 HNRP. UHF provided $162 million in targeted and coordinated multi-sectoral humanitarian assistance, including $4.8 million for MPCA, $77.9 million for Shelter and NFIs and $19.8 million for Protection.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Mobile health care is essential in areas close to the frontline, where vulnerable populations including older persons and persons with disabilities may struggle to access health facilities.

Analysis and decision-making

Identification and prioritisation of the most vulnerable was informed by a strong evidence base, supported by ACAPs, who conducted nine joint analysis sessions [1.42]. Seventy participants attended in total: 50 from INGOs and UN agencies, 15 NNGOs, four donors, and one local government representative.

These joint analysis meetings provided insights from local responders, allowing ACAPS to ground-truth theories and explore possible scenarios. They encouraged organisations to conduct analysis which benefits their work and planning capabilities, helping them to understand the importance of different types of analysis on their work. The sessions also brought together different organisations, fostering relationships and collaboration.

From a survey conducted in March 2025, 90% of respondents advised that they found ACAPs’ information products useful for decision making processes. ACAPS produced several thematic reports across key themes and analytical briefing notes in response to major events/changes to the context. These reports incorporated the voices of affected communities and responders, such as Ukrainian NGOs and volunteer groups. By amplifying this ground-truth data, the needs of the most vulnerable were communicated to key decision makers.

Coordination

FCDO began funding OCHA in March 2022 under UHRP to support coordination [1.3] of the humanitarian response in Ukraine. For 2024/25 funding continued but switched to the new humanitarian programme (not UHRP). This 2024/25 funding will need to be reported in reviews of this new programme, in due course. The earlier funding is captured in this document.

Three-year Strategic Review for Output 1

Overview

Partners ensured the protection and prioritisation of the most vulnerable in Ukraine through a multisector humanitarian response that combined advocacy with action to drive effectiveness. The response has sought to draw upon available data to identify and target specific vulnerable groups-including the elderly, persons with disabilities and those in conflict affected or recently liberated areas. Partners then worked to prioritise the most affected regions and hard to access communities, often under dire circumstances. Crucially, under this output, partners worked in close partnership with local organisations, enhancing both outreach and community trust. Through integrated efforts across sectors – ranging from cash, in-kind support for winterization and protection services – the response remained flexible and responsive to evolving emergencies. Flexibility facilitated response to emergencies to meet winter needs and respond to attacks on energy and infrastructure, for example in the response to Khakovka dam. As a result, assistance was adapted to the real and immediate needs of those most at risk.

Cash Assistance

One of the essential tools of the humanitarian response has been the provision of MPCA, which helps households facing shocks meet their basic needs in the way that they deem best. This has consistently been the preferred modality of households[9] and additionally helps support or revive local markets, particularly in newly de-occupied or frontline areas. In 2022, six million individuals were reached with MPCA, followed by 5.3m in 2023, marking it as one of the largest humanitarian responses globally.
[9] Ukraine: Multi-purpose cash assistance and sectoral outcomes assessment - Examining cash assistance and its impact on households in Ukraine (April 2025) - Ukraine | ReliefWeb

The programme’s approach to MPCA evolved over the three years: initially contributing to UN appeals and subsequently to WFP’s cash programme and the development of the Government of Ukraine’s Unified Information System of the Social Sphere to enable better information sharing between government, citizens and humanitarian responders. This led to the establishment of the PereHID Initiative, a multi-stakeholder project to develop an evidence base to work better with Government of Ukraine social protection provision, alongside investments in locally-led cash assistance through the Mercy Corps LIVES project and UN and Red Cross provision of winter cash with UNHCR.

MPCA targeted prioritised groups such as internally displaced persons, households with children, elderly-headed households, families whose relatives were missing, persons with disabilities and other individuals with specific needs. Cash proved to be an effective modality, offering recipients flexibility and dignity and allowing them to prioritise their immediate needs. Surveys consistently identified the main expenditure of cash assistance as food, rent and utilities, hygiene and health, clothing and winterisation, healthcare, education and housing repairs. The approach also stimulated local markers and economies. Feedback from beneficiaries indicated a strong preference for cash over in-kind assistance citing its adaptability to individual circumstance.

Vulnerable individuals were supported to meet winterisation needs through cash, and in-kind support such as heating, shelter and provision of essential supplies. FCDO guided partners prioritised the most vulnerable focusing on internally displaced persons particularly those in collective shelters lacking adequate insulation, older persons and persons with disabilities and frontline communities that often experienced severe infrastructure damage and limited humanitarian access. Our partners provided food parcels and kits, hygiene kits, water and other essential items. Specific support for winter was also provided by several partners, which included solid fuel, firewood, heaters, blankets and cash.

Challenges – cash: Despite overall success, cash assistance encountered several challenges. Digital access barriers – particularly the reliance on online platforms for registration and distribution – excluded some vulnerable groups, particularly older people. Coordination issues emerged, including difficulties in balancing cash and in-kind assistance and in distinguishing between multi-purpose cash and sector-specific cash support. While these challenges remain unresolved, FCDO has taken a leadership role in improving coordination by convening expert meetings and spearheading the publication of Common Donor Messaging on Humanitarian Cash Assistance in Ukraine (October 2024), which promotes donor alignment around cash-first approaches, local leadership, and responsiveness to affected populations’ preferences. Efforts to link cash assistance with national social protection systems have been a key focus for FCDO, though data-sharing constraints with government counterparts continue to pose obstacles.

Protecting vulnerable populations

Partners made efforts to mainstream protection and reach and include vulnerable groups including persons with disabilities, Roma and Lesbian, gay, bisexual and transgender people (LGBT+) as well as isolated individuals who required home based care. Under this output, partners delivered a multi-sector response targeting the most vulnerable populations in a large and volatile context. Efforts focussed on conflict affected areas and prioritised reaching the most vulnerable and those in hard-to-reach areas increasing the efficiency of the response. Working in partnership with numerous local partners enhanced reach and access to the most vulnerable. Identification and prioritisation of the most vulnerable groups was informed by a strong evidence base supported by specialist analysis.

Ensuring an inclusive and protection sensitive response was a priority for FCDO. Partners increased inclusion of marginalised groups through delivering services via specialist downstream partners, as well as strengthening access to hard-to-reach front line areas through an increased number of local partners.

Challenges – protection: Despite improved efforts over the years, several reports indicated that those with limited mobility, the elderly and persons with disabilities continued to be left behind as assistance failed to target them or was not inclusive and accessible to them.

Humanitarian Response Coordination and Planning

FCDO provided funding to OCHA’s office in Ukraine £1.5 million in March 2022, £0.5 million in April 2022, and £2.0 million in November 2023 (FCDO provided £1.4 million in December 2024 but this was through the new programme, HARP, rather than UHRP). OCHA does not do activity-based funding. Donors’ contributions are pooled and spread across OCHA’s operation. Overall, the funding supported their critical humanitarian coordination mandate at the national and subnational level and the strategic enablers that they can bring to bear, such as civ-mil coordination, data and analysis, and negotiations on access. Throughout the response, OCHA played a pivotal role in coordinating organisations to implement a ‘Humanitarian System-Wide Scale-Up’ a considerable achievement given that Ukraine, prior to the invasion, was one of the smallest humanitarian responses globally.

OCHA improved liaison throughout the period with the Government of Ukraine on key areas of work, thereby improving the overall relationship between the latter with the UN. These included areas such as humanitarian focused legislation, operationalising convoys to frontline areas with local government and general humanitarian co-ordination.

Challenges – coordination: Although OCHA swiftly deployed emergency personnel in the immediate aftermath of the full-scale invasion, some of the broader scale-up was slow, drawing criticism until improvements were made in late 2022 with the establishment of three sub national hubs. There remain significant staffing gaps at national and subnational levels, i.e. in civil-military coordination roles. Coordination with, and adequate inclusion of local response actors, remains a challenge. Cluster reviews are underway to improve efficiency, and there is an ongoing initiative to enhance area-based coordination. OCHA have continued to provide an information management function and coordination of HRNP processes has been strong. Expectations over the extent to which OCHA provide deeper analysis of humanitarian needs remain unclear. OCHA sit reps are limited in detail.

Assessments and Analysis

In the initial phase of the response FCDO funded a Standby Partnership position dedicated to supporting the establishment of the Assessment and Analysis Working Group – recognising that this was essential to give data and analysis work a higher profile across the response, and to support coordinated and collaborative data and analysis work processes. In year two FCDO’s programme extended to include REACH and then ACAPS – two organisations dedicated to providing humanitarian needs data and analysis. While REACH focus more on primary data collection nationwide, and the production of assessment reports, ACAPS provide analysis that supports users make sense out of existing data. FCDO have also provided support to a dedicated analysis function within Mercy Corps team (more on the role of analysis in the programme under Output 5).

Challenges – assessments and analysis: Humanitarian needs assessments and analysis projects are often uncoordinated – this has resulted in information gaps in some areas and duplication in others. This is often a result of organisations defining their deliverables independently and this then being what drives momentum. While the humanitarian data landscape is rich, partners report that there is too much to adequately absorb, which may limit the extent to which it can practically support decision makers. FCDO continues to encourage more analysis of existing data to better bridge the gap between data and decisions. The Assessment and Analysis Working Group continues to operate and is an important space for bringing together data and analysis actors across the response – it is however limited in function - members often update one another on respective workflows rather than it operate as a true space for joint analysis and shared planning, as initially intended. Conversations between members, are ongoing to turn this around.

Multi-sector humanitarian support

Widespread and indiscriminate attacks across Ukraine resulted in mass displacement, civilian casualties, the destruction of infrastructure, and the breakdown of essential services. The scale and complexity of the crisis meant that affected populations faced multiple, overlapping vulnerabilities. Displaced families required urgent support across a range of sectors, including shelter, food, water and sanitation, healthcare, education, and protection. At the same time, host communities and public service systems were under immense strain. In many oblasts—particularly in the east and south—core services such as health, education, and water supply collapsed entirely. To effectively address these interconnected needs, avoid duplication, and maximize the impact of the humanitarian response, a coordinated multi-sectoral approach was essential.

UHF played a critical role in enabling this response. It allowed for rapid, flexible funding to meet emerging needs through three key mechanisms: Standard Allocations, aligned with strategic priorities; Reserve Allocations, activated in response to specific developments; and top-up funding for existing partners to scale up operations. The early decision to support the UHF reflected a strategic recognition of its value in enabling partners to respond swiftly and at scale. The fund not only enhanced coordination but also ensured that essential, yet often underfunded, aspects of the response were adequately supported. It facilitated the timely flow of resources to local and national actors and allowed for agile, context-driven adjustments.

Notably, the UHF saw the largest expansion and scale-up of any humanitarian country-based pooled fund to date. Its investments significantly increased the number of Ukrainian partners involved in the response. By introducing dedicated funding envelopes for smaller organizations, the UHF broadened access to resources and enabled a more diverse range of actors to participate. This flexibility allowed the response to adapt more effectively to shifting needs on the ground—realizing the fund’s core objective of directing resources to where they are most needed as the context evolves.

Decentralised partners such as URCS played a vital role in delivering a flexible, multi-sector response across Ukraine. With a wide-reaching branch network, URCS was well-positioned to respond rapidly to emergencies in coordination with local authorities and regional State Emergency Services of Ukraine teams. The URCS Emergency Response Fund—supported by a £2.77 million contribution from FCDO out of a total £10 million—enabled the organisation to reinforce local branch capacity with centrally managed resources that could be deployed quickly through regional and national emergency teams.

This adaptable model proved critical during major crises, such as the destruction of the Kakhovka Dam. In response, URCS worked alongside State Emergency Services of Ukraine to provide evacuation support and deliver essential services to affected communities. The Emergency Response Fund allowed URCS to scale up operations swiftly, mobilising personnel, supplies, and logistical support where they were most needed. In parallel, the URCS Emergency Pooled Fund—also supported by FCDO—further enhanced the organisation’s ability to respond to evolving needs across sectors, reinforcing its role as a key national actor in Ukraine’s humanitarian architecture.

Under this output, the Mercy Corps programme continued to strengthen localised humanitarian aid in Ukraine by providing grants to local organisations, enabling them to lead and implement activities tailored to the needs of their communities. A subset of these partners also received tailored capacity-building support to enhance their ability to lead effective humanitarian responses. Over the years, the programme significantly expanded its reach, increasing the number of local partners from six to seventeen, including women-led and women’s rights organisations. Local partners delivered a wide range of services in frontline and hard-to-reach areas, including psychosocial support, temporary shelter, legal aid, advocacy, employment assistance, education, and the distribution of food and non-food items.

In support of broader localisation efforts, Mercy Corps also contributed to the development of an online portal for the NGO Forum. This platform will enhance transparency and accountability by enabling INGOs to self-report funding flows and share information with Ukrainian civil society. It complements existing financial tracking systems by capturing indirect funding and capacity development support to local actors.

Challenges – multisector humanitarian support: Delays in the disbursement of UHF funds, primarily due to approval bottlenecks at headquarters level, have sometimes hindered the mechanism’s responsiveness. Additionally, the cluster system’s sector-specific planning approach limits ability to implement integrated, multi-sector responses. While there has been impressive progress toward localisation, the full potential of pooled funds like the UHF to support local actors is not yet realised, highlighting the need for continued advocacy and structural reforms.

Monitoring and evaluation of this output has varied. TPM was carried out by Ecorys for Mercy Corps, IOM and URCS, including monitoring of cash assistance activities. Due to the nature of their work and our funding, TPM was not conducted for ACAPs, XXXX, UHF or OCHA. FCDO team members participated in UHF site visits where possible. In 2024, FCDO retained their seat on the UHF Advisory Board, which allowed us to provide feedback on allocation strategies, results and new funding initiatives.

Lessons

- Early planning and timely disbursal are crucial; delays in procurement and planning impacted the timely delivery of winterisation support. Delays in fund release reduced the impact of otherwise well-designed mechanisms. Mechanisms like UHF and URCS Emergency Fund enabled agile responses, underlining the effectiveness of flexible funding.
- Local civil society is vital: engaging local actors improved outreach, responsiveness, and sustainability.
- Multi-sector coordination is essential: integrated approaches are necessary to address overlapping vulnerabilities. But despite efforts, inclusion gaps remain, with vulnerable groups – especially those without digital access (often older people) – often left behind.

Output Number and Title	Output 2: Promoting access, inclusion and respect for IHL by working diplomatically and via technical engagement with the humanitarian system.
Output Score	A (Outputs met expectations)
Impact weighting (%)	13%	Impact weighting revised since last AR?	Yes. Reduced from 14% to 13%.

Output Indicator	Target	Final Result	Difference	Score
Sub output 2.1 - Frontline communities receive essential humanitarian services and necessary tools to keep themselves safe while local response mechanisms and duty-bearing institutions increase their coordination efforts.
2.11 [Nonviolent Peaceforce (NP)] # communities in priority areas report increased and safer access to services – inclusive of NP and/or its local partners.	28	23	-18%	B
Sub output 2.2 - Improved access to training for military and military adjacent groups on International Humanitarian Law and humanitarian principles and norms.
2.21 XXXXXXXXXXXXXXXXXXXXXXXXXXX / XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX / XXXXXXXXXXXXXXXX.	XXX	XXX	XXX	X
Sub output 2.3 - Through protection mainstreaming, capacity building, and NP-supported mentoring initiatives, local organizations have increased capacity to identify and directly address community protection concerns; with a heightened focus on people living with disabilities and vulnerable populations.
2.31 [NP] % of selected partners reporting an increased ability to identify, and engage, protection concerns.	100%	100%	-	A
2.32 [NP] # of humanitarian referrals actioned by NP to specialised services and/or assistance to prevent, mitigate, or respond to protection risks.	90	116	+29%	A+
2.33 [NP] # of local volunteers and staff trained on thematic protection issues and protection mainstreaming.	1500	1850	+23%	A+
Sub Output 2.4 - Disability inclusion is included in key processes in the humanitarian project cycle (i.e. Multi-Sector Needs Assessment, HNRP, Inter-Cluster Working Group meetings/processes, etc.), including via the participation of UN Liaison officers in relevant UN mechanisms.
2.41 [WHO] # of processes supported, including workshops for Organisations of persons with disabilities	8	9	+13%	A
Sub Output 2.5 - Partner CSOs, both new and existing, are provided strategic, tailored trainings and support that enable them to respond to the essential needs among highly vulnerable population groups in Ukraine
2.51 [Mercy Corps] % of supported CSOs that are promoting gender equality and/or social inclusion.	65%	93%	+43%	A
2.52 [Mercy Corps] % of pooled funds allocated to protection programming.	25%	34%	+36%	A

Output Description

This output is about securing access to the most conflict affected areas to support the provision of protection of people living in these areas; about ensuring the inclusion of vulnerable, marginalised groups and those with complex needs; and about building greater compliance with International Humanitarian Law to minimise harms to civilians and other non-combatants.

12-Month Review for Output 2

Introduction

Under this output, the programme sought to improve access to frontline communities in Ukraine and those leaving the temporarily occupied territories. Respect for and compliance with IHL was promoted. This output also sought to mainstream inclusion across the response, to ensure the most vulnerable were reached and supported with dignity. The work by earmarked partners HAVEN, Mercy Corps and WHO is assessed below. XXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXX. Despite challenges in accessing frontline communities and in measuring and disseminating knowledge of IHL, there was strong delivery across the output, which has been scored overall an A for 2024/25, “outputs met expectations”.

Performance against indicators

Over 2024/25, NP-led consortium, HAVEN, met or exceed their indicators for improving safer access, civilian protection and IHL compliance. Under sub-outputs [2.1] and [2.3], NP conducted direct protection activities, and built the capacity of local actors in civilian protection to expand the network of protection actors in frontline Oblasts. This work includes ensuring respect for IHL: for example, the Kharkiv team advocated for reduced military presence at a newly opened transit site in Izium, Donetsk, minimising potential risks to evacuees. The exceeded targets for sub output [2.3] are due to the high level of interest and demand from local actors for capacity building on protection, as well as the effective engagement strategies used by NP with local actors and communities to improve awareness on protection.

Over 20 coordination meetings facilitated by NP have allowed them to provide 116 referrals to specialised services. Only 23 of the target 28 communities reported safer access to services [2.1], as only 23 communities could be reached due to evolving security dynamics in Kherson, specifically the increased use of first-person view drones. This limited the ability of NP to consistently deliver services and access communities as planned.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Ninety-three per cent of Mercy Corps’ downstream partners promoted gender equality and social inclusion (GESI) through their activities [2.5]. Mercy Corps’ GESI team held a two-day, online training session, “Integrating Gender Equality and Social Inclusion Minimum Standards into Programme Activities,” in January 2025 to reinforce core principles, emphasise relevance, and strengthen assessment of projects through a GESI lens. The session also covered GESI minimum standards, and intersectional vulnerabilities including age, disability, displacement, and gender.

During the reporting period, Mercy Corps scaled up its contribution to the Humanitarian Diplomacy Initiative, XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. In September, Humanitarian Diplomacy Initiative members, led by Mercy Corps, travelled to New York and Washington, D.C., where they conducted a series of briefings to provide situational updates and present key recommendations on humanitarian access. These discussions continued, focusing on strategies and incentives for engaging conflict parties on issues related to access and civilian protection. In the final quarter of 2024/25, Humanitarian Diplomacy Initiative members, alongside representatives from the CRC and OCHA participated in the Riyadh International Humanitarian Forum. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

WHO have continued work to ensure that persons with disabilities in Ukraine can access humanitarian assistance by including disability in key processes in the humanitarian project cycle. This has included participation in Humanitarian Programme Cycle workshops, contributions to the HNRP and Ukraine Winter Response Plan to reflect the needs of persons with disabilities and technical support to the Age and Disability Technical Working Group and Gender in Humanitarian Action Working Group.

Three-year Strategic Review for Output 2

Overview

Between 2022-2025, FCDO partners have made significant strides in enhancing protection and humanitarian access for frontline communities in Ukraine. HAVEN played a pivotal role in delivering direct protection services and building local response capacity. Through a combination of strategic training, mentoring, and operational support, CSO partners were equipped to deliver inclusive, protection-sensitive assistance to some of Ukraine’s most vulnerable communities. Local organisations have significantly enhanced their ability to identify and respond to protection concerns within their communities. Meanwhile, WHO have played a central role in guiding the humanitarian community in integrating disability inclusion into key processes.

Despite the challenging context, HAVEN has promoted respect for IHL across all sectors involved in the humanitarian response, ensuring that both military and civilian actors are better equipped to uphold humanitarian standards in complex operational environments. XXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXX.

Protection

A major programme achievement was the expansion of local protection networks through targeted training and capacity building. Local staff, partners and volunteer groups were equipped with essential knowledge and tools on protection mainstreaming and humanitarian principles, enabling safer and more effective operations in high-risk areas. Training sessions and mentoring initiatives helped embed protection principles into daily operations, while also fostering a culture of accountability and resilience among frontline responders. Protection mainstreaming was complemented by strengthened data collection practices, ensuring that activities were informed by disaggregated data and responsive to the needs of different population groups.

Nonviolent Peaceforce (NP) provided a comprehensive “duty of care” package to frontline responders, including personal protective equipment (PPE), first aid kits, and volunteer insurance; they also provided communication and operational support, including training in first aid, psychological first aid, and distribution safety. As a result, all frontline service providers reported improved safety and security. NP’s consistent communication and operational support – including training in first aid, psychological first aid, and distribution safety – further enhanced partner capacity. Their volunteer resilience programme, offering mental health support, contributed to the sustainability of the response. This approach to duty of care has influenced broader humanitarian practices, informing responsible partnership principles and encouraging donors to include such provisions in funding allocations.

In many areas, coordination emerged as a key strength. The HAVEN consortium, including ACTED and NP, played a central role in establishing and reinforcing local coordination structures. ACTED partnered with the Relief Coordination Centre (RCC) to maintain and expand area-based coordination hubs. RCC now serves as a key source of coordination data, working closely with local authorities and humanitarian actors. ACTED supported RCC’s institutional development, providing training in financial and information management and standardised data collection. Partner-facilitated meetings enabled effective referrals to specialised services, strengthening the link between frontline responders and the broader humanitarian system.

In collaboration with People in Need and the Legal Development Network, ACTED also established a new coordination platform in other regions. This platform streamlined communication between humanitarian actors and local stakeholders, enabling a community-centred approach to identifying and addressing needs. Peer-to-peer learning between RCC and Legal Development Network / People in Need has further strengthened local coordination. As a result, in HAVEN’s first year, 88% of local coordination structures and stakeholders reported improved capacity to identify and meet humanitarian needs – surpassing an 80% target; and in the second year, a similar indicator achieved 99%, surpassing the 80% target.

HAVEN members also collaborated to enhance impact. For example, in response to a request from regional authorities, RCC and NP improved civilian protection at a major railway station by refurbishing underground shelters and enhancing WASH facilities. XXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Together, these efforts contributed to a more localised, sustainable, inclusive, durable and accountable response, enabling local actors to identify and address protection risks, and to do so in a way that respects the dignity and rights of the people they serve, and to continue their work despite the challenges of operating in conflict-affected areas.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Challenges – Protection: Ongoing conflict and poor infrastructure continue to limit access to some areas, delaying or preventing the delivery of essential services (see more on access below). Limited outcome tracking has made it difficult to assess long-term impacts of our interventions. Finally, coordination gaps persist in some regions: national coordination mechanisms are not always inclusive of local actors or present in all oblasts, creating fragmentation in the response.

Access

Since the onset of the full-scale invasion in 2022, humanitarian access in Ukraine has remained a persistent challenge, particularly in frontline and non-government-controlled areas. Despite the adoption of various strategies (e.g. advocacy, decentralised response models, and operational adaptations) access has continued to deteriorate. As of mid-2025, the situation remains critical. Escalating hostilities, especially in the east and south, have displaced hundreds of thousands and severely disrupted essential services. Humanitarian actors face a range of access barriers, including active conflict, damaged infrastructure, security risks, and administrative delays. TPM has also identified shortages of PPE, limited vehicle availability, and bureaucratic hurdles as key impediments to access.

Two main approaches have emerged to navigate these constraints:
Negotiated Access: XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Local-level negotiations by actors such as URCS, HAVEN and Mercy Corps LIVES partners have improved access in hard-to-reach communities under Ukrainian control. URCS, as an auxiliary to the government with a nationwide branch network and embedded volunteers, has been particularly effective in reaching vulnerable populations.

Operational Adaptation and Risk Mitigation: More tangible success has been seen through efforts to enhance partner safety and operational flexibility. HAVEN has equipped local groups with PPE and training, while Mercy Corps has provided Hostile Environment Awareness Training and enabled costs for security (e.g. PPE) for its partners. These measures have enabled safer operations near frontlines. Organisations like Humanity & Inclusion have adopted mobile team models that redeploy based on security conditions. Mercy Corps partners also procure and store equipment locally to ensure continuity during access disruptions.

Challenges – Access: Despite these efforts, an estimated 1.5 million civilians in non-government-controlled areas remain largely cut off from humanitarian assistance. CSOs working in frontline areas continue to face significant challenges related to security, logistics, and resource limitations. Even in accessible regions, the scale of need continues to outpace available resources. Advocacy has had limited impact as an enabler of humanitarian access in this context.

Inclusion

Inclusion has been a central principle of the humanitarian response in Ukraine, aligned with Guidelines on the Inclusion of Persons with Disabilities and other at-risk groups. Humanitarian actors have made genuine efforts to ensure that assistance reaches all those in need, particularly the most marginalised. However, the operational context has presented significant challenges to fully inclusive programming.

All FCDO partners have integrated inclusion into their programming and advocacy. Some partners, like Humanity & Inclusion, focussed on specific groups, while others adopted a broader approach, incorporating inclusive practices across targeting, recruitment, and service delivery. Mercy Corps worked with local partners to ensure that protection services were accessible to those most at risk. This included targeted outreach to marginalised groups such as Roma communities, LGBT+ individuals, and people with chronic health conditions. Capacity building workshops brought together organisations of persons with disabilities and humanitarian actors to explore inclusive approaches across sectors such as WASH, cash assistance, food security, and accountability. Humanity & Inclusion delivered targeted support at the community level, including rehabilitation and mental health services, as well as training on protection and disability inclusion. TPM confirmed that partners were actively tailoring support to be more inclusive, even under difficult circumstances.

Guidance from WHO on disability integration, working closely with UHF, included shaping funding and implementation methodologies, contributing to strategic planning, and supporting technical working groups focused on age, disability, and gender. These efforts helped ensure that the needs of persons with disabilities were increasingly recognised and addressed in both strategic frameworks and operational plans.

Encouragingly, there have been shifts in societal attitudes. Partners report a decline in prejudice against certain marginalised groups, as individuals from these communities have taken active roles in the war effort. Operationally, inclusion has been supported through practical measures such as the provision of PPE and Hostile Environment Awareness Training for local partners, enabling them to operate more safely and reach underserved populations, including in frontline areas.

Despite strong efforts, several barriers persist leading to uneven inclusion of vulnerable groups. These include time and security constraints in high-risk, hard-to-reach areas and in situations where the need to act quickly for personal and community safety can result in less nuanced targeting, in spite of improvements in duty of care and operational support; documentation Issues, with many individuals lacking the necessary identification to register for assistance, leading to exclusion from formal aid systems; tensions in targeting approaches, with debate between blanket targeting (which is faster and perceived as more equitable) and focused targeting (which aims to reach the most vulnerable); and the challenge of addressing the full spectrum of exclusion for those with intersectional vulnerabilities. Regarding disability inclusion, some partners continued to lack the tools and technical capacity to fully integrate disability inclusion into their programming, and the limited engagement of disability focal points at the local level constrained the operational impact of inclusion frameworks.

Setting of targets, monitoring and evaluation also presented challenges: some targets were either too ambitious or not adjusted in response to changing needs and contexts, making it difficult to accurately measure progress; feedback systems were not always accessible to all groups, particularly those with disabilities or limited literacy; and the lack of consistent outcome monitoring made it difficult to assess whether increased capacity had translated into improved protection for vulnerable populations.

Respect for International Humanitarian Law

Since the onset of the full-scale invasion in 2022, the application and respect for IHL in Ukraine have been under intense scrutiny. While Ukraine has taken action to demonstrate its commitment to IHL, the broader operational environment remains fraught with violations, limited accountability, and challenges in implementation. In this challenging environment, the programme has had some notable successes:

Ukraine’s Ministry of Defence submitted a voluntary report on IHL implementation in early 2025 – the first of its kind by a country in active conflict. This initiative, signalling a strong political commitment to uphold IHL standards. was supported by URCS. URCS has also played a key role in institutional strengthening, revitalising the National IHL Commission and supporting IHL dissemination efforts across government and military institutions. XXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Trainees showed improved attitudes toward IHL, reflecting a shift in perception and openness to its principles. TPM reports encouraging results in terms of participation and performance during training sessions. In the first year of the programme the whole-of-community response to the full-scale invasion risked blurring between humanitarian and military support. Significant investment was made in contextualising training and awareness raising among CSO responders on the importance of neutral and independent humanitarian response, thus improving understanding of humanitarian principles.

Challenges – IHL: While training outcomes are promising, assessing the real-world application of IHL by armed forces remains difficult. FCDO and its partners lack the mandate and access to monitor compliance on the battlefield. There also continues to be some indications of a blurring of Humanitarian and Military Aid with some small local organisations reportedly failing to distinguish between military and civilian aid, increasing risks for both aid workers and civilians. The broader conflict context – particularly violations by Russian Federation forces – has contributed to a global perception of declining respect for and erosion of IHL norms. This has led to growing scepticism among civil society and former prisoners of war about the effectiveness of IHL in practice. Reach and sustainability of engagement have also proven challenging. Maintaining consistent engagement with military and military-adjacent groups requires ongoing effort, trust-building, and adaptation to the realities of conflict dynamics. And despite efforts, not all relevant actors have been reached or were able to fully engage with training due to operational constraints and competing priorities.

XXXX

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Lessons

- Local actors are critical: Local organisations and volunteers embedded in communities are often the only actors able to consistently access and serve frontline and hard-to-reach areas. Their presence and trust within communities are essential for effective humanitarian delivery. With capacity building support, they are well-positioned to identify and respond to protection concerns and to ensure the relevance of interventions. They are also often better positioned to engage with military-adjacent communities and facilitate training.
- Equitable partnerships are foundational: Feedback has highlighted the importance of fostering equal, trust-based relationships between international and local actors. FCDO’s partnership principles have been a positive step in setting expectations. Tailored support has enhanced localisation: context-specific capacity building has enabled CSOs to deliver more inclusive and responsive assistance. Participatory approaches (allowing CSOs to define their own priorities) have proven particularly effective. Duty of care has enabled a more sustained response: providing frontline responders with PPE, training, and mental health support significantly improves their safety and ability to continue operating in high-risk environments. Flexible programming is key: the ability to redeploy mobile teams or shift operational focus in response to changing security conditions has proven essential for maintaining service delivery in volatile areas.
- Inclusion is improving but remains a work in progress: continued effort is needed to adapt to evolving vulnerability profiles and access constraints. Disability inclusion is most effective when integrated across all stages of the humanitarian project cycle, rather than treated as a standalone concern. Sustained advocacy and leadership are essential to ensure disability inclusion is prioritised and mainstreamed.
- Engagement with authorities enhances legitimacy: collaboration with national institutions, such as the Ministry of Defence and the National IHL Commission, has strengthened the credibility and reach of IHL training efforts. Coordination improves when locally led: Locally established coordination structures, supported by partners like NP and ACTED, have strengthened the ability of local actors to identify needs and respond more effectively.

Output Number and Title	Output 3: Promoting sustainable recovery by developing humanitarian-development synergies to ensure we build government capacity to respond.
Output Score	A (Outputs met expectations)
Impact weighting (%)	8%	Impact weighting revised since last AR?	Yes. / Revised down from 9% to 8%.

Output Indicator	Target	Final Result	Difference	Score
Sub Output 3.1 - Support Ministry of Health and Ministry of Social Policy in framing modern rehabilitation, assistive technologies and long-term care services for healthcare and beyond.
# of regulatory documents developed, passed public discussion and approved by leading state agency.	3	9	+200%	A+
Sub Output 3.2 - Monitoring system to align mapped activities with rehabilitation staff capacity of healthcare facilities delivering rehabilitation services.
# of operational partners on rehabilitation reporting to the mapping tool.	8	12	+50%	A+
Sub Output 3.3 - Technical support and guidance to improve capacity of Ukrainian health facilities to support outcomes for rehabilitation patients.
# of facilities supported	61	80	+31%	A+
# of people trained	1070	1242	+16%	A+
Sub Output 3.4 – Technical assistance facility evidence and advice used by donors and agencies to inform policies
# of policies, practices and programmes informed by technical assistance facility evidence and advice	5	9	+80%	A
Sub Output 3.5 - To ensure disaster management preparedness across Ukraine
# of Disaster risk management policies/ procedures/ tools developed, enhanced and completed		8	-	A

Output Description

This output is about building synergies between humanitarian support and longer-term recovery. It aims to bolster Government of Ukraine capacity and strengthen national systems to respond to the long-term vulnerability created by a protracted crisis. It aims to build capacity and support for the localisation of programme delivery.

12-Month Review for Output 3

Introduction

This output aimed to build synergies between humanitarian support and longer-term recovery to bolster Government of Ukraine capacity to respond to the long-term needs of the population. This outcome encompasses FCDO funding to four specialist partners to a) strengthen Ukrainian capacity to respond to physical rehabilitation needs of the population (WHO); b) provide effective case management for internally displaced people (IOM); c) develop robust disaster risk management preparedness policies and plans (URCS) and; d) to support synergies between humanitarian cash responses and national social protection programmes (STAAR). Partners were chosen for their specialisms within their respective fields and existing relationships with relevant ministries. STAAR was chosen as FCDO’s centrally-managed programmatic vehicle for supporting commitments on social protection and humanitarian cash linkages. Overall, partners achieved or moderately exceeded their targets. Some of these targets could have been set at a higher level at the outset, so this output has been scored overall an A for 2024/25, “Outputs met expectations”.

Health system strengthening

During 2024/25, WHO supported the Ministry of Health and the Ministry of Social Policy with the development of nine regulatory documents on modernising rehabilitation and long-term care services in Ukraine. This included policies on provision of assistive products for adults and children, standardised tools for assessing disability and a national strategy on deinstitutionalisation for adults in Ukraine. These policies are critical to ensuring the rehabilitation system is equipped to support the recovery of Ukrainians affected by the war, increasing their ability to play an active role in Ukraine’s socio-economic recovery, as well as supporting Ukraine’s pathway to EU accession.

To support the coordination of humanitarian actors in the physical rehabilitation sector, WHO developed a mapping tool, hosted on the Ministry of Health website. Currently 12 operational partners from the Rehabilitation Working Group are reporting to the tool regarding their ongoing activities. The tool shows information on classification of health facilities, numbers of beds, and numbers of patients. This will strengthen humanitarian-development synergies by assisting with calculating the workload for each rehabilitation department, avoiding duplication between humanitarian actors.

WHO provided technical support and guidance to 80 Ukrainian health facilities to improve their capacity and support outcomes for rehabilitation patients. This included providing assistive technology such as walking frames and wrist and knee orthoses to non-specialised rehabilitation departments. In collaboration with UNICEF, WHO also supported children’s hospitals through provision of paediatric rehabilitation equipment.

WHO provided capacity-building training to 1242 Ukrainian healthcare professionals on rehabilitation activities including training for wheelchair providers, clinical trainings for multidisciplinary rehabilitation teams and workshops on modern rehabilitation principles for healthcare administrators and leadership. WHO employ the training of trainer approach to capacity building trainings to ensure that participants can replicate trainings in future.

Social Protection

In 2024/25, the number of policies, programmes and practices informed by STAAR’s technical assistance facility’s evidence increased. However, these were skewed more to humanitarian-development synergies than to building government capacity to respond, due to limited government capacity to engage with the initiative and competing reform priorities. Policies include the inclusion of social protection and humanitarian cash linkages in the 2025 Humanitarian Needs and Response Plan, a government decree on financial assistance to internally displaced persons and other Ukrainians affected by Russian aggression, and the State Social Services Strategy. Several pilot programmes were also funded by donors as a result of engagement in the PereHID initiative, including vertical expansion of key social protection programmes by WFP and UNICEF, alongside UNHCR’s role in bridging critical gaps from evacuation, displacement, or the aftermath of aerial attacks until people can access national social assistance schemes, thereby complementing the Government’s programmes.

Shifts in practice are harder to attribute directly to technical assistance facility evidence, partly due to delays in publishing and the fact that many organisations were already referring beneficiaries to the social protection system, using government lists and vertically expanding social protection programmes. These shifts are more likely a result of sustained donor interest in the humanitarian cash and social protection linkages, regular PereHID coordination meetings and actor engagement with PereHID product drafting processes. Several technical guidelines were subsequently produced by the technical assistance facility to underpin these practices and guide future approaches. Evidence, analysis and recommendations produced by the technical assistance facility on strengthening the social protection system will be used to shape and define the reform priorities supported under FCDO’s SPIRIT programme.

Disaster Management Preparedness

URCS continued to act as an auxiliary to the Government of Ukraine, leading on improving the disaster risk management preparedness through close collaboration with government systems. During the 12-month period, URCS developed/enhanced/completed 8 disaster risk management policies/procedures/tools which includes Memorandums of Cooperation between State Emergency Services of Ukraine and URCS regional organisations and regulatory framework for the inclusion of the URCS branches to the Unified State Civil Protection System (USCPS).

Monitoring and Evaluation

TPM was conducted for both WHO and URCS over the life of the programme. In addition, site visits for senior officials were organised to Ohmatdyt Children’s Hospital[10] in Kyiv and XXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX, to highlight UK support for children’s healthcare and persons with disabilities through our partnership with WHO.
[10] Ohmatdyt Children’s Hospital is the largest children’s hospital in Ukraine. Despite being a medical facility, it was severely damaged during a Russian Federation missile attack in July 2024. This highlights the live challenges that programme partners face.

Three-year Strategic Review for Output 3

This output reflects both the prioritisation of working through the Government of Ukraine and of strengthening national systems in the business case, and commitment to use humanitarian interventions to lay the foundations for sustainable recovery. The increase in progress against outputs in the final year of the programme is indicative of the time investment required to support humanitarian-development synergies and to build relationships with government to effectively strengthen national systems. Whilst this is true across all contexts, challenges are compounded in Ukraine due to strained government capacity to engage in reforms whilst sustaining the war effort and the proliferation of humanitarian actors both international and national. Multi-year programming has therefore been essential in maintaining progress on key reforms and capacity development initiatives, but delays in confirming extensions between calendar years and the restrictions of have also limited the scope of activities to delivery within business case timelines

This output was also underpinned by assumption that the war would not last as long as it has. Decisions to discontinue system strengthening initiatives in the subsequent Ukraine Humanitarian Business Case were based on a honest assessment of team finite capacity and greater priority being given to other lines of effort. There remains the potential for wider British Embassy Kyiv recovery programming to continue effort in these sectors or indeed other donors.

Whilst the logframe measures key outputs, it does not capture the long-term impacts of interventions, which will extend far beyond the lifetime of the programme. This is particularly the case for the WHO intervention, which has concurrently supported the Government of Ukraine to meet acute humanitarian health needs as well as to develop a modern rehabilitation system fit for the needs of Ukrainians affected by the full-scale invasion. This intervention also contributes to broader British Embassy Kyiv objectives on supporting veteran integration and the development of a disability-responsive society, under the Government of Ukraine’s “Barrier-Free” strategy. Though not funded by FCDO, the engagement of the Collaborative Cash Network with the PereHID Initiative has contributed to a revised understanding of vulnerability in Ukraine, by identifying sub-sets of the population excluded from both social protection and humanitarian cash targeting. This understanding should be used to inform revisions of targeting criteria across the humanitarian response and the social protection system.

Lessons

Working with partners with existing relationships with government ministries and mandates across humanitarian and development facilitates system strengthening. This is reflected in the differences in access and engagement experienced by WHO and the PereHID Initiative Technical Assistance Facility, for whom UNICEF played a key role in facilitating engagement. That said, the independence of the PereHID Technical Assistance, together with the multi-agency membership of the initiative, facilitated discussions on humanitarian-recovery synergies in a way which was able to transcend agency politics.

- Levels of government engagement also reflect different capacities of ministries and political imperatives on the urgency of the system strengthening reforms. In the case of PereHID, the continued presence of a parallel humanitarian cash system also reduced the urgency of government reforms on shock-responsive social protection.
- Data sharing policies and lack of interoperability between digital systems can prevent humanitarian-recovery synergies and limit the ability of humanitarian actors to fully leverage social protection systems to reach vulnerable populations with humanitarian cash.
- A shared understanding of humanitarian actors’ role in supporting people to meet their basic needs via social protection systems is required to avoid tensions around the difference between “meeting basic needs” and “poverty reduction” being used to justify parallel systems.
- Flexibility is required when designing interventions to support transitions from humanitarian to government or recovery interventions, particularly in conflict affected contexts. The PereHID initiative Terms of Reference, based on a premise that the war would end quickly, placed over-emphasis on a “transition” of humanitarian caseloads to the social protection system, rather than on how humanitarian actors can leverage and strengthen the system to enable it to better respond. Although this shift in approach was achieved in the final year, a revision of the terms of reference based on the context and understanding of overlap within the social protection and humanitarian caseloads earlier in the initiative could have accelerated progress.
- Whilst humanitarian programmes can be effective vehicles for laying the groundwork of system strengthening interventions, sustained development programming vehicles are required to transition activities and ensure longer term sustainability. More broadly across the response, siloed coordination structures, including for donors, has limited the establishment of humanitarian-development synergies and the ability to combine collective expertise, experience and resources to strengthen the government of Ukraine’s ability to respond.

Output Number and Title	Output 4: Developing a more localised response, harnessing Ukrainian capacities by more equitably balancing funding of the international response with support to local actors.
Output Score	A (Outputs met expectations)
Impact weighting (%)	18%	Impact weighting revised since last AR?	No.

Output Indicator	Target	Final Result	Difference	Score
Sub Output 4.1 - CSOs are provided strategic, tailored trainings and support that enable them to respond to the essential needs among highly vulnerable population groups in Ukraine.
4.11 [NP] # of local CSOs and volunteer groups report an increased and safer ability to deliver essential humanitarian services as well as address and identify protection needs.	25	25	-	A
4.12 [Mercy Corps; ACAPS] # of tailored capacity plans and trainings developed	12 / 4	12 / 4	- / -	A
Sub Output 4.2 - To support URCS' long-term national society development.
4.21 [URCS] # of humanitarian staff and volunteers using renovated premises	600	422	-30%	B
Sub Output 4.3 - Continue to drive localisation agenda and make improvements to the accessibility of the UHF to local NGOs and CSOs.
4.31 [UHF] % of allocation disbursed directly to national and local humanitarian partners.	No target	45%	-	-
4.32 [Mercy Corps] Number of subgrants disbursed to CSO partners		15	-	A
Sub Output 4.4 - Initiatives of women’s rights/led organisations in women, peace and security and humanitarian action funded.
4.41 [WPHF] # of CSOs supported to implement initiatives	17	22*	-	A
4.42 [WPHF] # of projects/grants implemented in humanitarian assistance, protection of women and girls and peacebuilding	14	23*	-	A

*Reflects CSOs and projects/grants funded by FCDO who implemented activities in 2024 calendar year, to align with WPHF’s reporting timelines. A further 13 proposals were approved for funding in December 2024 with FCDO funding, but results were out of scope for this indicator as their implementation began in the 2025 calendar year. Additional funding was also provided in February 2025, to support WPHF in the aftermath of the US Aid cuts, but results for this are out of scope due to project implementation timelines.

Output Description

This output is about how the programme contributes to a more locally-led response in Ukraine, enabling Ukrainian civil society actors to develop their expertise and skills and use this to inform the humanitarian response according to their understanding of communities and their needs. It also supports organisations to lead the design and implementation of emergency interventions, and to ensure that frontline organisations can work as safely as possible.

12-Month Review for Output 4

Introduction

Under this output, the programme continued to support the localisation of the humanitarian response in Ukraine. Whilst there was a focus on representative community-level programming with local actors, the programme also supported local authorities and national government structures where possible.

This output has been scored overall an A for 2024/25, “output met expectation”.

Increasing localisation

Through a range of partnerships with UN and large NGOs, the proportion funding to local and national actors in the portfolio increased this year. For example, in the 2024 calendar year, 45% of UHF’s total funding allocation (58.2% of net funding – i.e. received directly or indirectly) was provided directly to national and local humanitarian partners, an increase from 20% (32% net funding) in 2023. Importantly, of the three allocations launched by UHF in 2024, only one of these was open to UN Agencies. In addition, their Second Reserve Allocation, for a total of $19.6 million, was only open to National NGOs.

Duty of Care

As the programme, and the wider response, increased funding to local actors, there was an increasing need to establish a duty of care minimum standard. The extreme risks faced by aid workers, particularly in frontline regions, has lead to efforts to prioritise duty of care for these workers, ensuring their safety, mental health, and operational support. Under the programme, ACAPS produced a report highlighting the duty of care challenges humanitarian workers face; this report recommended ensuring that staff welfare is embedded into budgets with NNGOs; improving coordination across the response, and institutionalising duty of care practices.

NP provided a comprehensive duty of care package to 25 HAVEN subgrantees (CSOs and volunteer groups), all of whom reported an increased ability to safely deliver essential humanitarian services to frontline communities as a result. The package included PPE, insurance and access to psychosocial support. NP responded to feedback on the support provided: e.g. when CSOs questioned the quality of helmets provided, NP arranged independent testing of the PPE to ensure its quality as life-saving equipment.

Through their LIVES programme, Mercy Corps ensured that local CSO partners could access the minimum “duty of care package”. This minimum package included life and health insurance and was available to all partners operating in high-risk areas. By ensuring the programme invested in local partners’ safety and well-being, we helped to build mutual respect and trust, which in turn increased the flow of accurate, timely insights into evolving protection needs on the ground.

Equitable partnerships

Over one-fifth of Mercy Corps’ budget was allocated to sub-awards for a network of 15 partner organisations delivering vital humanitarian assistance through various modalities, including cash, in-kind support, and livelihoods programming. Continuing the approach from the previous year, Mercy Corps prioritised equitable partnerships with these small to medium-sized CSOs. TPM reported that partners consistently described their relationship with Mercy Corps as equal rather than hierarchical, with one partner stating: “We feel like a partner and not just a sub-contractor.” By fostering strong, equal relationships, Mercy Corps created a trust-based environment where partners felt comfortable providing honest feedback. This feedback was actively captured and integrated into future project planning and decision-making. For example, under the LIVES 3.0 programme, sub-awards were extended to longer durations wherever possible.

Capacity building

Through our range of partnerships, the programme contributed to continued localisation by building the capacity of small-medium Ukrainian-led CSOs. In 2024/25, Mercy Corps developed 12 tailored capacity-building plans where Ukrainian CSOs received targeted training in accountability, emergency response, support functions, and monitoring techniques. These efforts empowered local partners by expanding their organisation skillset, and enabling greater ownership and decision-making authority. All partners self-reported improvements in their organisational capacity, highlighting the effectiveness of a flexible, partner-led approach to capacity strengthening. Local partners were especially complimentary of the monitoring techniques and needs assessment training sessions. The result was significantly increased evidence feeding into needs assessments for the communities that they were supporting, and much improved MEL engagement for their ongoing programmes. As a direct result of this training, organisations such as Responsible Citizens successfully secured funding from additional donors, demonstrating increased confidence, capability, and sustainability.

ACAPS also played a role in building the analysis capacity of CSOs, by delivering four humanitarian analysis trainings, primarily targeting national NGOs. Each training session was oversubscribed indicating high demand amongst national organisations to improve analysis skills. The ACAPS team responded to direct feedback from local organisations to tailor trainings to meet their needs – for example, seeking training on context analysis to support local NGOs in developing funding proposals. ACAPS was the only organisation supporting capacity building training for local actors that focussed on improving qualitative analysis skills. In the evaluation of the analysis training, the feedback was overwhelmingly positive, with 90% of respondents agreeing that it had been directly supportive to their work. This training covered local responders’ analysis gaps and ensured they could use these skills to draft proposals for funding from donors.

Promote Accountability to Affected Communities

This year, the programme ensured decisions were community-led to ensure efforts are responsive, respectful, and relevant to the needs and rights of the people they aim to support. Through UK funding, WPHF have supported 22 local women’s rights and women-led organisations in Ukraine since 2023/24. This partnership enabled the implementation of targeted projects across humanitarian assistance, protection of women and girls, and peacebuilding. By working directly with women-led organisations, the programme ensured that women could actively participate in humanitarian coordination mechanisms, decision-making bodies and advocacy platforms at local, regional and national levels. In addition, local women’s organisations and CSOs coordinated efforts to advocate for and implement interventions to protect women’s and girls' rights and end GBV in conflict settings.

Three-year Strategic Review for Output 4

Over the three-year programme cycle, the programme has made significant steps in advancing a more localised humanitarian response in Ukraine. The programme consistently met or exceeded its output indicators, with notable achievements within limits of increasing funding to local and national actors, enhancing the capacity of CSOs, and promoting equitable partnerships. The programme has delivered strong performance across all localisation-related outputs. Capacity-building targets were exceeded, with 100% of partners reporting improved organisational capacity, and local actors were empowered to lead programming, with increased access to funding and leadership roles in coordination mechanisms.

The programme’s success lies in its twin-track approach: equitable partnerships and support to Ukrainian actors’ interventions, and systemic influence on international funding and coordination mechanisms. This has positioned FCDO as a leader in operationalising localisation in a complex humanitarian context. However, challenges remain. Despite progress, the humanitarian system in Ukraine remains UN-centric, and access to funding, particularly flexible funding that allows for adaptation, for local actors is still constrained. The programme’s influence on policy and coordination structures has been impactful but requires sustained advocacy. Over the duration of the programme activities were introduced to support government leadership and systems strengthening– a key component of FCDO’s localisation approach in Ukraine, which are captured in Outcome 3 ‘Promoting Sustainable Recovery’.

The first-year allocations were largely unearmarked contributions, so it is not possible to quantify the number of Ukrainian actors supported nor the amount of funding. In the second year of the programme 133 Ukrainian CSOs were directly supported through FCDO partnerships and up to 25% of funding went to Ukrainian actors. There was an increased emphasis on the quality and depth of our engagement with and support to local Ukrainian actors. As a result of enhanced capacity building and support to their leadership efforts, some CSOs were able to become fully-fledged consortium partners (e.g. RCC, within HAVEN) or were successful in applying for direct funding from UHF in 2024/25.

Advocacy efforts from within the UN, local partners and donors has contributed to an overall increase in the proportion of funding from key humanitarian pooled funds going to Ukrainian CSOs. For example, within UHF, the proportion of funding received directly by Ukrainian CSOs grew from 12.6% in 2022, to 45% in 2024. UHF partnered with 25 national NGOs in 2024, and net funding (direct and indirect) to national NGOs was $93.3 million[11] (57.6% of total allocated funds).
[11] Figure for total UHF funding, from all donors including the UK.

Working with those closest to communities enables more equitable access to assistance: Local communities and CSOs are the first responders in every emergency, and the full-scale invasion of Ukraine was no exception. Ukrainian civil society were and continue to move first and furthest, being among the only organisations working in very dangerous frontline areas, with UN agencies and INGOs relying on them for the riskiest work. Over the years of the programme, partners were introduced both to sustain the responses of Ukraine’s first responders, and to enable the programme to meet the needs of specific groups of people. T

The Mercy Corps LIVES project started in the first year of the programme and FCDO supported the Women’s, Peace and Humanitarian Fund introduced in the second year, in particular supporting women-led, LGBT+, Roma and disability representative groups. The HAVEN consortium was introduced in the second year to support CSOs and volunteers with protection, evacuation, and recovery efforts in high-risk areas. These partnerships improved accessibility of UK assistance according to groups’ unique experiences and needs. FCDO’s TPM found a “commendably proactive approach” to supporting vulnerable groups, while feeding back to partners groups at risk of being excluded for consideration.

The programme’s main vehicle for supporting the shift to a locally-led response have been the Mercy Corps LIVES project (granting, emergency response, locally-led cash and supporting CSO leadership/capacity), HAVEN (frontline CSOs/volunteer groups, safety and security, local area-based coordination), the British Red Cross/URCS partnership (URCS delivery, branch development, CSO leadership Alliance Ukraine network) and through two UN-led funds; UHF (increasing funding to CSOs, contextualising due diligence, piloting area-based allocations) and Women, Peace and Humanitarian Fund (flexible funding to deliver humanitarian aid, promote women’s leadership in crisis response). DEC, while being an INGO-oriented mechanism, contributed to thought leadership on supporting local leadership at the outset of the response (Localisation scoping exercise; Christian Aid). Other partners may have worked with Ukrainian organisations but without specific localisation/equitable partnership objectives built in, so are not listed here.

Supporting local leadership and coordination: Alongside access to funding and equitable partnerships, supporting enhanced Ukrainian leadership in policy engagement and strategic and operational coordination is key to a transition to Ukrainian ownership of the humanitarian response. For example, UK funding supported the establishment of the Alliance Ukraine network through the British Red Cross partnership, which has represented Ukrainian civil society in national and international fora, such as the annual Senior Officials Meetings. CSOs have also been supported as they participate in national leadership; for example Mercy Corps LIVES partner Alliance Global participated in the 17th National LGBT+ Conference, which resulted in a national roadmap for LGBT+ rights and inclusion in 2025.

The programme has also transitioned leadership and decision-making power to Ukrainian partners as experience and knowledge has grown. In the Mercy Corps LIVES partnership two local partners, Sonce UA and The Tenth of April, took over full responsibility for activating and managing their Rapid Response Mechanism. They conducted 64 activations in Q3 of 2024/2025 alone, responding to emergencies such as shelling and infrastructure damage. Their ability to independently manage procurement, needs assessments, and distribution significantly improved response speed and localisation of emergency aid.

HAVEN has made significant strides in advancing locally-led coordination in Ukraine by embedding local actors at the heart of humanitarian planning and response. Through RCC, the programme supported coordination across Kharkivska, Zaporizka, and Donetska oblasts, co-chairing key sub-clusters and supporting evacuations and recovery planning. RCC, in collaboration with other HAVEN partners, ensured that local level planning was grounded in local data and community input. The LINK platform, developed by Legal Development Network and People in Need, further enhanced coordination by connecting local needs with international actors in real time, reducing duplication and increasing transparency. NP’s area-based coordination pilot and its leadership in the HAVEN Evacuation Taskforce exemplified how localised, proactive coordination can drive timely and effective humanitarian action. This crucial groundwork and leadership of Ukrainian CSOs will pay dividends in enabling a shift to a more contextualised model of coordination in Ukraine.

WPHF also supported women’s leadership in humanitarian and crisis settings through leadership and advocacy trainings and campaigns to increase public awareness. Training participants included IDP and Roma women, women living with HIV and women and girls with disabilities.

Advancing research and evidence on localisation in Ukraine

The humanitarian response in Ukraine is often looked to as an opportunity to achieve long-held commitments on localisation, so gathering good practice and evidence is key to sharing lessons and successes. The programme has therefore also prioritised contributing to the growing evidence base on localisation and good practice; either through funding or partners’ access to information. For example:
Access to data from UHF supported the study "Passing the Buck: The Economics of Localizing Aid in Ukraine". This study assessed that local actors could deliver aid up to 32% more cost-efficiently than international intermediaries, primarily due to lower overhead and salary costs, even when adjusted to a ‘fair share’ of overheads and market-benchmarked salaries; that LNGOs were capable of managing larger grants and conducting procurement at comparable quality and cost to UN agencies, challenging assumptions about their capacity.
The programme also supported the March 2025 study, "No More Excuses: Prioritising Local Leadership in Cash Assistance in Ukraine," by Ground Truth Solutions and Open Space Works Ukraine, highlighting that while local CSOs are deeply embedded in communities and uniquely positioned to deliver aid effectively, they remain largely sidelined in leadership roles. Only 3.4% of cash assistance funding in 2024 was managed by local or national organisations, despite their proven ability to reach marginalised groups, navigate bureaucratic systems, and respond swiftly to crises.

Over the course of the programme the output has been monitored through a range of means. Programme managers and advisors have held regular meetings with partners to hear updates on implementation, with formal quarterly reports providing updates on agreed logframes. TPM on HAVEN, Mercy Corps and WPHF provided the majority of field-based monitoring for the output, with TPM partner Ecorys speaking to for example the Mercy Corps supported local partners to explore how Mercy Corps’ efforts to strengthen safeguarding standards, risk management, and localisation contribute to downstream partners’ sustainability and their ability to manage aid independently. Increased ability to travel to partner sites would enhance the monitoring and evaluation capacity for this output through FCDO colleagues being able to meet downstream partners directly.

Lessons

- Equitable partnerships build trust and improve quality of delivery. Partnerships are strongest where CSOs are considered equals and empowered to make adaptations based on what they see, not sub-contractors to fulfil a pre-defined activity. Flexible, partner-led capacity building works: tailored support based on self-assessment (e.g., ASPIRE model) leads to meaningful organisational growth.
- Duty of care is foundational: providing safety and psychosocial support to frontline responders is essential for sustainable localisation.
- Combine programming and influencing aims: complementing localisation-oriented programming with influencing has seen the best results.
- Coordination must be localised: locally led coordination structures are more responsive and trusted by communities and authorities.

Output Number and Title	Output 5: Maintaining flexibility, scanning the horizon, and adapting to evolving priorities and emerging risks should humanitarian needs spike.
Output Score	A
Impact weighting (%)	13%	Impact weighting revised since last AR?	Yes. Revised up from 12%.

Output Indicator	Target	Final Result	Difference	Score
Sub Output 5.1 - Effectiveness of UHF mechanism to respond to spike in need or change of context.
Timely launch of reserve allocations and effectiveness of winter response (UHF).	RA funds disbursed to partners within 30 days of launch		-
Sub Output 5.2 - Forward looking analysis products that consider humanitarian impacts of context developments.
# of times anticipatory analysis features in analysis report (ACAPS).		7	-	A
% of users confirming use of anticipatory analysis to support response activities* (ACAPS).	70%	90%	+29%	A+
RA funds disbursed to partners within 30 days of launch		11.25 days (average for all allocations)	-	A

*Results from ACAPS end of grant user survey

Output Description

This output is about ensuring the programme has the capacity to remain flexible and shift as needed. Situation monitoring and data analysis has been an essential to this – including providing funding support to data and analysis organisations and prioritising our internal analysis capacity to track humanitarian context developments, needs and risk. Additionally, FCDO prioritised flexible funding mechanisms to enable rapid disbursement of resources as required.

12-Month Review for Output 5

Introduction

Under this output, we aimed to ensure our programme remained flexible and responsive to sudden shifts in needs. To maintain this adaptability we have 1) provided funding directly to humanitarian data collection and analysis partners, and 2) remained diligent in monitoring the evolving context through continuous secondary data review / regular engagement with data collection and analysis partners across the response, and producing our own internal analysis to guide discussion / planning. By closely tracking contextual changes and assessing humanitarian needs, we have been able to identify emerging priorities and adjust our programming accordingly — supporting an evidence-based response.

This output has been scored overall an A for 2024/25, “output met expectation”.

Enhancing anticipatory analysis within the broader response

The humanitarian response in Ukraine is rich in data on humanitarian needs. However, there is a widely recognised gap in deeper, interpretive analysis that can make sense of this data. Existing analysis tends to focus on the immediate situation, while anticipatory insights – those that look ahead to potential future developments – are notably lacking. This type of forward-looking analysis is not only a priority for the FCDO but is also frequently cited by other humanitarian actors as essential for effective operational planning. Recognising this gap in the humanitarian data and analysis landscape in Ukraine, we continued our partnership with ACAPS who have strengthened the anticipatory dimension of their analytical work, in accordance with their new analytical strategy launched in 2024.

Over the past year, ACAPS has integrated a dedicated anticipatory analysis component into most of their reports. This approach enables decision-makers to better understand how evolving contextual dynamics may impact humanitarian needs, moving beyond static, point-in-time assessments. ACAPS more qualitative and forward-looking methodology complements the extensive quantitative data already available across the response, offering a more holistic foundation for planning and decision-making. Building on their earlier scenario work, ACAPS held new scenario workshops in February 2025, bringing together analysts and humanitarian experts from across the response. Feedback from the workshops was very positive. As a direct outcome, International NGO Safety Organisation invited ACAPS to co-develop and deliver a training on contingency planning for local actors, using the 2025 ACAPS scenarios as a foundational tool. Via ACAPS’ end of grant survey, 90% of users confirmed use of ACAPS’ anticipatory analysis to support response activities and inform key decisions. E.g. within the International Federation of Red Cross and Red Crescent Societies (IFRC) 2025 Q2 Impact Forecast, they cited ACAPS’ analysis report on the funding reduction implications[12] as a key source.
[12] ACAPS. (2025, March 31). Ukraine: Implications of the US foreign aid cuts on humanitarian, development, and government-led programmes. https://www.acaps.org/fileadmin/Data_Product/Main_media/20250331_ACAPS_Thematic_report_Ukraine_Implications_of_US_foreign_aid_cuts.pdf

There are continued concerns about the sustainability of ACAPS work in Ukraine, due to a reliance on a small pool of international donors.

Activation of contingency funding

Through partnership with UHF, our programme contributed to reserve allocations that are designed to provide rapid and flexible funding in response to emergencies. UHF uses three types of mechanism which are activated in response spikes in need or emerging priorities as detailed in the HNRP: Standard Allocations, through routine funding windows; Reserve Allocations, activated by the Resident and Humanitarian Coordinator in response to a specific issue or development; Funding top ups to existing partners.

During the 2024 calendar year, the UHF launched three funding allocations: a Standard Allocation, a Winter Response Reserve Allocation, and a Second Reserve Allocation. The $66.6 million Winter Response Reserve Allocation supported time-critical and high-impact activities identified in the 2024-2025 Winter Response Plan launched in July 2024. Partners were pre-selected to allow rapid disbursement of funds and funds were restricted to the Shelter/NFI Cluster and the Camp Coordination and Camp Management Cluster to address the most important needs during the winter months. In 2024, the UHF’s Reserve allocation processes were conducted within an average of 21.5 days. The average disbursement timeline across all three allocations, including the Standard Allocation, was 11.25 days.

Three-year Strategic Review for Output 5

Overview of operational flexibility within FCDO’s programme

The FCDO’s first clear response to the surge in humanitarian needs came with the launch of its programme following the full-scale invasion in February 2022. Within two weeks, assistance was being delivered on a “no regrets” basis. Initially, the programme partnered with multilateral organisations capable of rapid fund disbursement to meet urgent needs. Over time, the portfolio evolved to include both emergency response and early recovery, while retaining flexible, unearmarked partnerships to ensure continued rapid response capacity. To better anticipate shifting needs and adapt to a fluid humanitarian landscape, FCDO has prioritised investment in analytical capacity.

Ensuring capability of partners to respond to shifting context

Over the three years of the programme, flexibility was maintained through the allocation and release of contingency funding. Setting aside a portion of contingency funds each year, ensured our programme could respond to new or unforeseen requests for targeted support, including requests from the Government of Ukraine, or to supplement existing partner funding where required. Specifically, within our partnerships, we ensured all partners had the flexibility to adapt and respond to sudden shifts in context. Across our portfolio, we worked with a mix of UN partners who received softly earmarked or unearmarked funding, allowing them to rapidly reallocate resources in response to shocks and address the most urgent needs and priorities. XXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Several key flexible funding mechanisms were utilised across our partners, and these are summarised below:

During 2023/24, Mercy Corps improved their ability to conduct quick, systematic evaluations following sudden shocks through the establishment of their Rapid Response Mechanism (RRM). Within the first 24–72 hours of a shock, Mercy Corps conducts a rapid needs assessment, collecting critical information which will determine whether the RRM should be activated, and the type of assistance needed urgently. This continued into 2024/25, where the RRM was activated 185 times, quickly disbursing life-saving cash and in-kind assistance to frontline areas. Through tailored capacity building plans, Mercy Corps’ downstream partners Sonce UA and The Tenth of April assumed responsibility for procurement and activation of the Rapid Response Mechanism for in-kind assistance. Out of the 185 RRM activations, 91% of interventions were completed within 14 days of the finalised rapid needs assessment, exceeding Mercy Corps’ target. For example, on 4 April 2025, a residential neighbourhood in Kryvyi Rih was struck by a cluster "Iskander" missile. This resulted in the loss of 18 lives, over 70 residents injured and left significant damage to civilian infrastructure. Mercy Corps’ downstream partner Sonce UA conducted a rapid needs assessment the following day, which identified emergency shelter kits, financial assistance, stoves, portable burners, flashlights, hygiene items, and blankets to be priority needs. The day after Sonce UA distributed 40 emergency shelter kits (non-UK-funded) to provide protection from the cold weather.

Unearmarked Funds

UHF reserve allocations have evolved into a highly responsive and strategic tool for responding quickly to sudden shifts in context. Over the past three years, UHF has used reserve allocations to rapidly respond to emerging crises, such as intensified conflict, winter and large-scale displacement. These allocations are not pre-planned but triggered by real-time needs assessments, field data, coordination with humanitarian clusters and local authorities. For example, in September 2024, UHF launched a $66.6 million reserve allocation to support winter preparedness, focusing on heating, shelter repairs, and cash assistance for utilities in areas facing harsh conditions and ongoing hostilities. The fund also emphasises localisation, increasingly channelling resources to national NGOs and civil society organizations that can access hard-to-reach areas and deliver tailored, inclusive aid. By aligning with the HNRP and leveraging pre-positioned partnerships, UHF ensures that its reserve allocations are both timely and impactful, adapting fluidly to the evolving humanitarian landscape.

Across the two years, our programme contributed to URCS’ Emergency Pooled Fund, a mechanism which allows donors to pool their contributions into a single, unearmarked fund to support local humanitarian efforts. This enables Red Cross humanitarian partners in Ukraine to deliver timely, coordinated, and principled assistance and enabling URCS to react quickly to needs in the communities through a timely decision-making process and with more flexible planning and reporting guidelines.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

Key examples of partner response in accordance with specific context developments

The Nova Kakhovka Dam disaster

1. Following the destruction of the Nova Kakhovka Dam, humanitarian needs surged. Over 700,000 people across southern Ukraine were left without access to safe drinking water, and thousands of homes sustained significant damage. The flooding disrupted essential services, heightened health risks, and exacerbated protection concerns, including mine contamination, as floodwaters dislodged and redistributed explosive remnants across affected areas.
2. Support to the response is covered in detail in the 2024 annual review of this programme. The experience of responding to this incident led to team learning that supported flexing the programme in response to the evolving humanitarian situation.

Winter

Over the past three years, humanitarian needs have surged each winter as temperatures plummet well below zero and relentless Russian attacks on Ukraine’s energy infrastructure leave millions without reliable access to power, water, and heating. These conditions have posed recurring challenges for the humanitarian response, though the nature and severity of needs have varied year to year. Guided by data and anticipatory analysis, particularly on the projected impacts of winter, our programme remained agile, adapting to evolving needs through the use of flexible funding.

The first cold season in the response (2022-2023) had multiple challenges, including large displacement with high numbers of civilians living in collective centres which were not fully prepared for winter. Ahead of the 2023-2024 winter season, we applied lessons learned from the previous year to strengthen our preparedness and adapted our response based on the updated priorities and urgent needs. We provided additional top-up funding to key partners to enhance their winter readiness. Notably, our programme increased funding to UHF by £20 million in support of their targeted winter appeal, enabling funding for a broad range of national and international NGOs, as well as UN agencies, to address strategic gaps identified through the inter-cluster coordination process. We also allocated £7.35 million to WHO, Mercy Corps, URCS, and IOM. These top-ups enabled us to meet our original beneficiary targets despite adjustments to the cash transfer value. We also provided an additional cash top-up to the most vulnerable households to help cover increased utility bills and purchase essential winter items. Moreover, this increased funding ensured that persons with disabilities, older people, and institutionalised populations were reached through inclusive health and rehabilitation services, contributing to greater equity and broader system strengthening.

The most recent winter response demonstrated improved coordination and a shift towards a more data-driven and pro-active rather than reactive approach. Through analytical partners, including ACAPS and REACH, we received early reports anticipating damage to energy infrastructure and the subsequent impact on living conditions during the cold season. Drawing on this analysis, alongside other sources, we proposed several reallocations across the portfolio to address urgent and emerging needs. While most new partnerships were supported through a separate business case, we provided an additional top-up to HAVEN. This funding was disbursed ahead of winter, enabling partners to mitigate the anticipated effects of harsh seasonal conditions. The support facilitated the provision of solid fuel to heat community facilities in vulnerable areas, as well as generators and fuel for collective centres hosting IDPs.

Rising humanitarian needs due to escalating conflict and increased use of long-range weapons

In 2024, Russian forces escalated their attacks on civilian infrastructure, increasingly deploying missiles, guided bombs, and drones in densely populated areas. Compared to 2023, there was a marked rise in the number of health care and educational facilities damaged or destroyed, alongside a 30% increase in civilian casualties. Damage to residential property in urban areas became increasingly commonplace. Notably, a growing share of these incidents occurred far from the frontlines. Meanwhile, conflict also escalated along the frontline, deepening needs in these areas, and triggering a notable increase in displacement in the final quarter of the year. This deteriorating security environment significantly affected humanitarian operations in frontline Oblasts with a rising number of access incidents reported.

In response to the deteriorating security environment, we prioritised continued funding for the Ukraine Red Cross Society and Mercy Corps—key partners in delivering rapid emergency assistance following attacks on civilian areas. Their support has included immediate shelter, health care services, psychosocial support, and the distribution of hot meals to affected populations. We also maintained our support for HAVEN, with a particular focus on their duty of care initiatives, which have been vital in sustaining local NGOs operating under increasingly challenging conditions. In parallel, our funding to ACAPS enabled the production of a comprehensive report on duty of care issues across the humanitarian response. This report was widely recognized by other actors and donors as a valuable advocacy tool. Additionally, we raised duty of care as a priority issue at the Senior Officials Meeting and played a leading role in encouraging the adoption of the Duty of Care Minimum Package (which our partner, Mercy Corps, was central to developing and socialising) across the response.

Severe humanitarian needs in IDP Collective Sites

Multiple humanitarian assessments have highlighted severe gaps in services and infrastructure within IDP Collective Sites, which are ill-equipped to meet the needs of a highly vulnerable population. These sites accommodate a large proportion of older people and individuals with disabilities, many of whom live with chronic health conditions, lack economic independence, and have no support networks. Conditions in most Collective Sites remain substandard. Few are adequately prepared for winter, and most do not offer services that are accessible to people with disabilities. In August 2024, displacement intensified in frontline oblasts, leading to a rise in evacuations to Collective Sites, including in central and western regions. We maintained our support to UHF, which designated 10% of its 2024 allocation to Collective Sites — recognising this as a strategic priority in light of shifting displacement trends and the growing urgency to expand shelter capacity.

Prioritising data and analysis to support understanding of evolving humanitarian context

Dedicated support to data and analysis organisations has been a core part of FCDO’s programme – this includes support to REACH, ACAPS and Mercy Corps.

REACH: FCDO began supporting REACH in June 2023 under HAVEN. This funding has supported REACH in conducting their core data collection and analysis work – notably their regular Humanitarian Situation Monitoring assessment which tracks evolving needs along the frontline and in non-government held areas, their Joint Market Monitoring, and the nationwide Multi-sector Needs Assessment that provides much of the data behind the HNRP 2024 and 2025. These assessments provide some of the most critical data across the response and are central to our ability to monitor needs. Over time, REACH expanded their portfolio of work to include more localised assessments in frontline areas – notably their Local Responder Area Profile assessments, designed to support our understanding of what local organisations require in specific frontline locations, and Rapid Needs Assessments, e.g., in response to evacuation spikes (in collaboration with IOM). The findings are shared with operational actors, including the Inter-Cluster Working Group and the Area Managers.

ACAPS: FCDO began supporting ACAPS in October 2023. This funding has allowed ACAPS to produce a range of qualitative analytical products, maintain four regularly updated datasets on access incidents, infrastructure damage, and key humanitarian indicators, and deliver analytical training aimed at building local capacity. Over the course of the partnership, the approach has shifted from general support to a more focused effort to align ACAPS’ work with identified analytical gaps and needs in the response. ACAPS have improved the strategic relevance of their analysis and ensure it is shared in appropriate forums. This has led to increased referencing of their products by other actors and high demand for their training sessions. ACAPS has contributed to making sense of the large volume of data in the response, using qualitative analysis and a network of local informants to help contextualise findings. Their scenario-building work, prioritised by FCDO in 2023 and 2024, has been acknowledged by others as a useful tool for collective analysis across the response. This analytical work supports FCDO and the wider response to better monitor the evolving humanitarian situation and respond accordingly. Measuring the impact of specific pieces of analysis remains a challenge. For analysis to be successful we need to understand the impact it has on influencing work processes, including decision making at programmatic and/or strategic levels, and in informing advocacy. Therefore, indicators that monitor the number of reports published are not sufficient. To more accurately assess the impact analysis work we have pushed ACAPS to track key indicators that include active engagement from intended users, feedback received, secondary references to ACAPS work.

Mercy Corps: Through our partnership with Mercy Corps, we supported the establishment of the Ukraine Crisis Analysis Team (UACAT). Over the past two years, UACAT have provided continuous contextual analysis to the Mercy Corps programme team to ensure that programming corresponded to the situation on ground and programme adaptations as needed. This support included biweekly context planning sessions, publicly available thematic and flash reports, and reports with limited distribution, such as UACAT’s report on the challenges of frontline aid delivery.

Lessons

- We need to be ready to flex programmes at short notice. This can involve a shift from emergency to recovery mode as well as vice versa. Programmes with longer time frames and flexible internal arrangements (like Mercy Corps’ RRM mechanism) reduce FCDO’s workload and improve partners’ ability to respond to spikes in need.
- Assessment data and analysis are key to shaping evidence based and targeted programming, but strong coordination is needed to avoid multiple partners working on the same topics. The wealth of data and analysis products available in the Ukraine response also made it difficult to absorb and utilise these towards better decisions, so synthesis products and strong dissemination are key.
- Without diversified funding sources and broader external demand for their products, analysis partners become reliant on donor funding. Greater efforts should be made by partners to ensure sustainability through a focus on building up wider research uptake.

Output Number and Title	6: Support to the Government of Moldova through provision of humanitarian aid and protection services to vulnerable refugees and Moldovans affected by the crisis, whilst strengthening local and national capacities to be shock-responsive through support to system reform.
Output Score	A+ (Outputs moderately exceeded expectations)
Impact weighting (%)	10%	Impact weighting revised since last AR?

Output Indicator	Target	Final Result	Difference	Score
Number of individuals reached with multisectoral GBV response services (UNFPA).	6,030	8,071	+34%	A+
Number of people receiving assistance unconditionally or conditionally (WFP, in complementing other agencies’ activity (UNICEF, FAO, WHO)).	61,500	87,066	+42%	A+
% targeted communities with a functioning referral system for children at the community level (UNICEF).	100%	100%	-	A
Proportion of trained service providers who exhibit competence in providing survivor-centred care to GBV survivors (disaggregated by type of response service and government/CSO service providers) (UNFPA).	70%	84%	+20%	A+
% emergency affected children and youth (5 - 18 years old) attending learning spaces/schools in affected areas (UNICEF).	25%	15%	-40%	B
% of refugee children receiving quality primary health care services (UNICEF).	22%	36%	+64%	A+

Output Description

The UK’s humanitarian response programme in Moldova has, in close collaboration with the Government of Moldova, ensured the provision of life-sustaining assistance, delivered protection support for vulnerable Ukrainian refugees and Moldovan community members, and supported national social protection system strengthening. Achievements have been monitored through reporting, programme visits, and evaluation meetings with partners and wider stakeholders.

12-Month Review for Output 6

Introduction

FCDO has continued to deliver a comprehensive programme of interventions in Moldova, meeting immediate humanitarian needs alongside delivering system-strengthening support to the country’s national social protection system for sustainable support that will continue to deliver for vulnerable households into the future. This output has been scored overall an A+ for 2024/25, “Outputs moderately exceeded expectation”.

UNFPA

UNFPA exceeded its target for the number of individuals reached with multisectoral GBV response services, achieving a total of 8,071 beneficiaries against a starting target of 6,030. This success is attributed to the operation of 32 static and mobile Safe Spaces across Moldova, which provided comprehensive GBV prevention and response services. These spaces offered psychosocial support, legal aid, and referral services, with a strong focus on inclusion—particularly for refugees, persons with disabilities, and Roma communities. Notably, 82% of GBV response service recipients were refugees, highlighting the programme’s relevance and reach.

In addition to service delivery, UNFPA invested in capacity building, training 977 community social workers and over 600 specialized service providers. These trainings focused on survivor-centred care, disability inclusion, and technology-facilitated GBV. As a result, 84% of trained service providers demonstrated competence in delivering survivor-centred care—surpassing the 70% target.

UNFPA also played a key role in policy advocacy and system strengthening, supporting the development of Moldova’s first National Compendium of GBV Indicators, advancing legislative reforms on technology-facilitated GBV, and piloting a technology-facilitated GBV detection system using AI. Furthermore, the organization co-chaired the GBV Sub-Working Group, enhancing coordination among over 65 partners and leading the development of the 2025–2026 GBV Sector Plan. These achievements reflect a comprehensive and sustainable approach to GBV prevention and response, combining direct service provision, institutional capacity building, and policy reform.

UNICEF

UNICEF’s interventions focused on strengthening national systems to provide protection, education, and health services to vulnerable Moldovan and refugee children. The organization met or exceeded most of its targets, with a few exceptions. UNICEF successfully ensured that 100% of targeted communities had functioning referral systems for children, meeting its target. This was achieved through extensive capacity building, including the training of 559 professionals and the deployment of 149 child protection specialists at the community level. A notable success was the integration of these 149 child protection specialists into Ministry of Labour and Social Protection (MLSP) payrolls within the planned timeframe, demonstrating the willingness and ability of the MLSP to take management and financial responsibility for the added capacity within their workforce. These specialists supported over 24,000 children using a case management approach.

In health, UNICEF exceeded expectations by reaching 36% of refugee children with quality primary healthcare services, surpassing the 22% target. This was facilitated through partnerships with the National Health Insurance Company and targeted reimbursements to health facilities.

However, 15% of emergency-affected children and youth attended learning spaces or schools, falling short of the 25% target. Despite this, UNICEF made significant strides through the EduTech Labs and Play and Learning Hubs, reaching over 2,000 children with non-formal education and 6,121 children with early learning activities. The organization also launched large-scale social behaviour change campaigns, reaching over 330,000 children and 266,000 parents to promote inclusive education and school enrolment.

WFP

WFP programming has delivered hot food in Refugee Accommodation Centres (three meals per day), reaching 2,103 Ukrainian refugees (including 189 with disabilities). In addition, WFP provided border snacks for 1,181 refugees (46 with disabilities). This intervention reached those most vulnerable Ukrainians least able to move from humanitarian accommodation into rented or family hosting, primarily the elderly or those with disabilities. The delivery of cash assistance for refugee hosting households has supported Moldovan families providing direct assistance to refugees (who could not afford to integrate into the rental market), thus easing the burden on these households and helping to offset the increased costs of hosting families. This support reached 16,089 individuals.

Complementary winter cash assistance for 67,693 vulnerable Moldovans, especially to the poorest category of pensioners and families with severely disabled members, has provided urgently needed financial support to those struggling to meet basic needs in a cost of living and energy crisis caused by Russia’s full-scale invasion of Ukraine. The provision of assistance to vulnerable Moldovans alongside Ukrainian refugees has been particularly important in mitigating against a risk of rising social tensions, especially over a tense political period in Moldova categorised by significant Russian interference and spreading of disinformation. WFP has taken an active lead in provision of technical assistance to the RESTART Reform and social protection system strengthening, including in shock-responsive social protection, including in delivering training to 2,107 individuals.

Moldova Regional Technical Assistance Facility (MRTAF)

The MRTAF team of technical consultants was embedded within the MLSP from July 2023, with the aim of supporting the MLSP’s RESTART Reform of the National Social Protection System. The MRTAF team successfully provided advice to the MLSP on the targeted technical areas including: support for the development of a performance management dashboard, developing a Risk Pilot Project, providing learning resources for social services and social transfers, and developing a communication strategy for the reform. There was evidence of Ministerial uptake of MRTAF developed outputs, and advisory papers were provided including on Capacity Building, Case Management, and Recruitment of Child Specialists. Despite these achievements, the timing of the team’s work and the ‘firefighting’ environment of the early phases of the Reform meant that obtaining MLSP buy-in and approval was slow and often challenging. Advice papers were not consistently actioned, and the team's provision of technical expertise was not always capitalised on, with the MLSP prioritising immediate over medium/long term ambitions for the reform.

Three-year Strategic Review for Output 6

Across the three years of programming, significant achievements have been made in output and outcome achievements, with only a small number of areas underachieving on planned targets. The programme has continuously demonstrated early and effective transitioning from humanitarian to durable solutions programming through the implementation modalities utilised, and strong buy-in from the Government of Moldova has bolstered this approach.

The response has evolved from an initial focus on meeting emergency and life-saving humanitarian needs, to a holistic, durable solutions focussed response delivering humanitarian assistance with sustainable and complementary social protection system-strengthening interventions benefitting both Ukrainian refugees and vulnerable Moldovan communities. The success of this response was possible due to the hugely positive efforts from the Government of Moldova to facilitate humanitarian provision through their national systems, recognising and actively encouraging international assistance in areas where these needed bolstering. This has led to systematic improvements in Social Protection, Health, and Education provision for both Moldovans and Ukrainian refugees, with roadmaps drafted for refugee integration in each of these sectors.

Lessons:

- Delivering through the national system. The programme has, as far as feasible, been delivered through efforts to strengthen national systems, simultaneously working to improve capacity to deliver quality social and protection services, be shock-responsive, and to integrate Ukrainian refugees. This approach has been facilitated by the positive approach of national authorities towards refugee integration, maintained value for money, and will ensure longer-term sustainability than could have been achieved through delivery of a fully parallel humanitarian response effort. Whilst funding has been primarily channelled through UN agencies, efforts in Moldova have incorporated strong partnership and capacity building components with MLSP in particular, complemented by activities implemented by a diverse group of UN-supported CSO downstream partners (e.g. Artemida, Homecare, and Ave Copii), allowing a focus on the national (and local) systems to be maintained. There was however scope within the programme for additional focus on ensuring local, community-level systems were sufficiently supported to complement national, government-led service provision.
- Supporting vulnerable Moldovans alongside Ukrainian refugee communities. This approach has enabled the programme to uphold social acceptance and mitigate tensions between communities, ensure needs-based targeting of conflict- affected communities regardless of status, and deliver services with value for money across geographic localities in Moldova, including in harder to access, rural areas (e.g. through Mobile Safe Spaces). Ukrainian and Moldovan communities can access many of the same services (including Safe Spaces, Youth Friendly Health Centres, and EduTech Hubs), helping to uphold generally accepting attitudes amongst both groups. Given the high rates of poverty across Moldova and pre-existing weaknesses in quality and access to services, exacerbated by the impacts of the conflict in Ukraine and subsequent refugee crisis, complementary support to both communities has been imperative. This has resulted in a high number of Moldovan beneficiaries reached, reflecting the chosen modality of delivering through national assistance and joint service provision, focussed on sustainable and inclusion focused approaches.
- Delivering a humanitarian intervention with a social protection lens. The UK focussed delivery in priority areas from early on in the response – emergency protection, GBV, and social protection system-strengthening. This ensured the programme’s delivery of tangible and complementary results across partners (not stretching the remit too wide), and has allowed the UK to position itself as a lead donor and strategic partner in these technical areas. The focus on social protection has enabled early identification of opportunities for humanitarian exit strategies and complementary nexus and development funded interventions for medium- to long-term support. It is notable however, that the provision of social protection technical assistance to the MLSP was more effective when it was accompanied by practical tools and close ongoing support: the technical assistance delivered through UN agencies (UNICEF and WFP) which was complemented by tangible as well as technical support, had greater impact than the independent team of technical experts embedded within the MLSP through MRTAF/STAAR.

## E: Value for Money

It has not been possible to make a single statement on the VfM of this programme as there was no programme-level VfM statement adopted against which to set performance. The approach to VfM shifted, appropriately, between the first emergency-response phase and subsequent years’ activities. The high-risk, no-regrets nature of the response and commitment to piloting new approaches to strengthen localisation, equity and coordination led to impactful interventions representing high VfM.

VfM Approach

The greatest VfM gains for rapid response to unpreventable catastrophes lie in resilience measures and preparedness[13] (on average, for every $1 invested in emergency preparedness, $2.6 is saved in the next crisis[14]). Various factors limited such preparedness activity ahead of the Ukraine crisis despite the projected risk of conflict. A Humanitarian Advisor was deployed ahead of the full-scale invasion to undertake scoping activity for a possible response.
[13] DFID (2017) VfM Guidance: Humanitarian: rapid response and emergency preparedness
[14] DFID (2019) Best Buys in Humanitarian Contexts

The original business case, developed during the early stages of a rapid-onset crisis response, recommended the adoption of the humanitarian VfM triangle of cost, quality and speed (rather than the framework of the 5 ‘Es’[15]). This was in line with departmental VfM guidance at the time, for humanitarian rapid response. No specific value statement was adopted, although the prioritisation of speed was proposed, with quality (responding to the right needs in the right way) and cost to be considered in the later stages of the programme. Noting the absence of a pre-response VfM assessment, a full-scale cost analysis was proposed for delivery at the end of the programme, with partners to submit VfM analysis centred on the three criteria of cost, quality and speed. High-level metrics were suggested for measuring these. The business case addendum maintained this approach to VfM, while increasing the focus on equity.
[15] The 5 Es of FCDO’s value for money framework are: economy, efficiency, effectiveness and equity (including gender equality and disability), and overall cost-effectiveness.

The Grand Bargain (and Grand Bargain 2.0) identified options for improving VfM in humanitarian rapid response, including delivery through local actors, scaling-up cash transfers, innovative use of technology, reducing earmarking, increasing transparency and accountability, improving consistency and harmonisation amongst donors and increasing “nexus” funding (including in the field of social protection). The programme’s annual reviews highlighted these linkages through identifying and encouraging the use of high-value and best-buy[16] approaches. Whilst not expressly set out in a VfM framework, the programme team have made distinct choices throughout the programme lifecycle, including in design, funding reallocation decisions and delivery modalities, that reflect a commitment to these goals (see examples below).
[16] DFID Humanitarian ‘Best Buys’ Analysis [January 2019 Revision]

Measuring and monitoring VfM

Activities changed significantly throughout the life of the programme. The approach to indicators and the measurement of results was also inconsistent. The programme had no logframe for year 1, due to the imperative to move quickly to implementation; there were separate logframes for years 2 and 3, again reflecting the changing activities and focus. Results trackers were available but not always routinely updated; they also lacked data disaggregation (see section B). Full implementation of annual review recommendations made on the programme’s approach to VfM was undermined by team overstretch and resourcing gaps (see section G), the volatile context, and the responsive, adaptive nature of the programme’s activities. These factors combined with the emphasis on speed of response created challenges in the assessment of VfM performance. TPM (see section G) was deployed to increase understanding of programme delivery, impact, and VfM, and allowed identification of some areas for improvement.

Consistent challenges in securing adequate resourcing of the programme team significantly limited their ability to fully develop proper compliance frameworks and monitoring tools – exacerbated by the dynamic, complex and novel context, limited information and very limited access to partners’ activities for monitoring. The programme team also lacked reliable access to an economist or MEL expert.

There were positive intentions to require partners to give “due regard to VfM in reporting”, however VfM was only formally included as a question in the FCDO reporting template in the final year of the programme. Some partners proactively provided review annually against the VfM assessment set out in their initial project proposal; findings and recommendations were then implemented in subsequent years. For example, in July 2023 Mercy Corps published a VfM study following the first year of the LIVES project and its recommendations were implemented across subsequent years.

Ultimately, qualitative and ad hoc approaches were adopted by the programme team to monitor and drive-up VfM performance. Examples of these efforts against the humanitarian VfM triangle of cost, quality and speed:

SPEED
- Strengthening localisation including working through URCS from early in the response allowed for the rapid scaling-up of response networks and speed in ensuring support reached areas where it was needed most. These networks and local organisations enabled delivery when markets stopped functioning (efficiency).
- Moving towards greater levels of local procurement in late 2022 further reduced costs and delivery times (increasing economy and effectiveness), as well as delivering benefits for the Ukrainian economy (cost-effectiveness).
- Ensuring the procurement of items for emergency response that were both relevant and interoperable with local and state systems increased impact and reduced delays in deploying these items (economy).
- In responding to winter needs, funds were deployed to those partners best able to quickly meet the needs of the most vulnerable (demonstrating economy and equity).
- Partners’ successful ability to reallocate funds between activity lines allowed for rapid adaptation of responses to meet real-time needs, as well as increasing relevance and thus impact (efficiency, effectiveness and equity).

QUALITY
- Relevance of the response was supported by the FCDO’s flexible funding approach, allowing partners to course-correct towards more relevant, impactful interventions as the situation and needs changed and as they were able to gather real-time feedback from downstream partners and beneficiaries (effectiveness and equity).
- Relevance and utility of assistance was also strengthened through the emphasis on providing cash and voucher assistance in place of in-kind support after the initial stage of the response (see below on use of MPCA) (effectiveness and equity).
- Coordination at local, regional and national levels; with government and between donors had mixed success (section D: three-year Strategic Review for Output 1). FCDO decisions on prioritisation sought to support the HNRP for Ukraine (efficiency and cost-effectiveness).
- In addition to targeted interventions under Output 2 (promoting access, inclusion and respect for IHL), adherence to humanitarian standards was mainstreamed through partner interventions (cost-effectiveness).
- The availability of in-house technical experts to provide guidance to the programme team throughout the response ensured the right support was provided at the right time and to the right people and prevented decisions representing poor VfM (supporting effectiveness).
- The PereHID (Ukraine) and STAAR (Moldova) initiatives are examples of programme-funded interventions representing comparatively weaker VfM: though designed to respond to identified needs, review suggests they did not do so in the “right” way, seeking to develop technical capacity before the political will and absorption capacity to sustain these were established, and using unrealistic assumptions about the external context in the theory of change. This led to lower impact and sustainability (and lower effectiveness).

COST
- In the early stages of the response, use of a commercial logistics partner for the procurement of in-kind assistance supported VfM through smarter navigation of supply chains, negotiation of competitive prices and timely delivery (demonstrating economy). This approach became less competitive as the response progressed and once other actors had set up supply chains providing support at scale.
- In the later stages of the response, efficiency was considered on a cost-per beneficiary basis where costs were comparable, for example in delivery of MPCA. There was downward pressure on distribution and procurement costs where networks were established, and economies of scale achieved (economy).
- Capacity-permitting, delivery through local partners and state systems presented opportunities to decrease costs (as compared with UN delivery) and increase sustainability and wider VfM (economy and cost-effectiveness). Some partners initially lacked experience and capacity which also reduced the ability to drive efficiency.
- Partners’ operating costs (rents, staffing) faced pressures in part due to the rapid scaling-up of the international response, which reduced opportunities and incentives for efficiency.
- Portfolio-level monitoring allowed for the timely and effective reallocation of underutilised funds (ensuring greater cost-effectiveness).

Examples of supporting and bolstering the VfM through thematic / policy decisions:

Supporting localisation

Localisation is widely accepted to be more cost-effective (costs less and can have greater impact – see references in Output 4 to building the evidence base on benefits) than delivery through international actors[17]. Though rigorous evidence supporting this is lacking, recent analysis points to savings of 32% compared to using international structures. Significant efficiencies were found when comparing both UN and INGO budgets to local budgets in the Ukraine context (Refugees International, 2024)[18]. Through the programme:
[17] DFID (2019) Best Buys in Humanitarian Contexts
[18] Refugees International (2024) Passing the Buck: The Economics of Localizing Aid in Ukraine

- Bolstering capacity of the Ukraine Red Cross Society supported longer-term localising of response and disaster preparedness efforts in Ukraine.
- The HAVEN consortium empowered downstream partners to choose implementation approaches that worked for their specific contexts, operating models and beneficiaries. HAVEN also strengthening volunteer response structures and provided local coordination.
- HAVEN partners’ approaches to strengthening protection through IHL training focussed on working with non-state actors’ behaviours and norms, as well as on knowledge gained through training, thus increasing the effectiveness of these interventions.
- Mercy Corps’ sub-grant model allowed for locally led procurement and activation of the Rapid Response Mechanism for in-kind assistance.
- Through the British Red Cross, the programme supported the formation of the Alliance of Ukrainian CSOs, whose role was to advocate for greater local leadership in the aid sector in Ukraine. The Alliance emphasised the urgent need for structured, sustainable, and inclusive humanitarian responses, equitable partnerships with international stakeholders, and an expanded role for Ukrainian CSOs beyond emergency aid, including recovery, development, and civil defence.
- In May 2025, the Embassy’s humanitarian team received an award recognising their commitment to localisation through their advocacy efforts and programming decisions.

Use of cash support

Approximately a third of humanitarian activities in Ukraine (2022-2024) were delivered through cash and voucher assistance (Ukraine Cash Working Group, 2025)[19]. The UK is an advocate for the use of MPCA in humanitarian crises wherever it is appropriate (FCDO, 2025)[20]. Evidence shows that delivering assistance as cash is more efficient than in-kind, with cash being as much as 2-3 times cheaper to deliver than food aid, as well as improving outcomes and generating significant benefits to local economies. Cash assistance is considered a “Great Buy” in FCDO’s internal Humanitarian ‘Best Buys’ Analysis. The VfM potential of cash assistance increases when cash is multi-purpose and delivered through a single transfer. Where feasible (through functioning local markets, availability of technology to assist transfers and reduce fraud, etc), MPCA gives recipients more dignity and flexibility to meet their needs. Cash-based responses are feasible in the Ukraine context, however efforts are ongoing in moving towards a single transfer of MPCA. Through the programme, FCDO:
[19] Ukraine Cash Working Group (2025) Cash and Voucher Assistance (CVA) - Ukraine 2024 Response Analysis Snapshot
[20] FCDO (2025) Humanitarian Guidance Note: Cash in Emergency Contexts

- Increased support for the use and driving-up standards in the delivery of MPCA to respond to emergencies and support basic needs in Ukraine.
- Advocated with donors and partners on the collective need to enhance and scale cash interventions, thus supporting local economies and empowering crisis-affected people to make choices as to what they the need the most.
- Made continued efforts to improve coordination in the delivery of MPCA.

Increasing the use and impact of pooled funds

Evidence demonstrating the cost effectiveness of country based pooled funds (CBPF) compared with bilateral funding of UN or multilateral programmes is lacking[21]. However, the significance of CBPFs in enabling rapid scale-up of the humanitarian response, and the FCDO’s proposed focus on increasing the proportion of donor funding being channelled through CBPFs[22], places a premium on ensuring we use our funding position to leverage approaches which support the VfM of CBPF. This includes ensuring CBPFs respond at pace; achieve the best possible impact for affected persons; promote IHL compliance; align with localisation commitments; protect the financial resilience of downstream partners, and champion transparency.
[21] K4D (2018) Country-based pooled funds for humanitarian financing
[22] FCDO (2025)

- 17 % of the programme funding was channelled through pooled funds. In total, £67.1 million was unearmarked.
- The OCHA-administered UHF directed almost 60 per cent of its funding to local and national partners in 2024 – higher than the global average[23].
  [23] OCHA (2025) Country-Based Pooled Funds and Regional Humanitarian Pooled Funds 2024 in Review
- FCDO leadership and advocacy in UHF improved the direction and impact of this fund, for example through contributing to the UHF localisation strategy, and providing feedback on allocation strategies as a member of the Advisory Board. The programme team also worked closely with the FCDO OCHA and Country Based Pooled Fund Institutional Leads to provide country-level feedback on issues such as staffing, governance and risk sharing.

Ensuring equity and inclusion

With a strategic commitment to reach the most vulnerable, the programme focussed on disability and gender inclusion (see section D: Output 2). This included:
- Voluntary adoption and proactive dissemination of “Partnership Principles”, outlining key expectations on localisation and gender equality and social inclusion minimum standards.
- Utilising standby partnerships to support the UN and national governments to increase understanding of and good practices in inclusion. In Moldova, this was successfully further disseminated through the NGO sector.
- Working with WHO to strengthen rehabilitation systems, train medical personnel and improve disability inclusion (working with organisations of persons with disabilities).
- Funding through WPHF provided capacity building and institutional support to local women’s rights and women-led organisations.

Lessons:

- The scale, complexity, novelty and inaccessibility of programme interventions, and rapid pace of set-up, presented significant challenges to the building and adopting of a VfM statement and framework, even after the development of the retrospective, emergency-rules business case. The programme team adopted speed as the initial primary driver of VfM. This was justifiable given the context. Despite some improvements in results tracking towards the end of the programme, beneficiary data did not consistently include inclusion markers (to allow disaggregation by age, sex, disability etc) reducing the ability to demonstrate equity quantitatively.
- There is an opportunity for organisational learning for Ukraine and wider contexts from new approaches piloted under this programme to strengthen localisation, equity and coordination.
- It was beyond the capacity of the team to complete the full-scale cost analysis at the end of the programme.

## F: Risk

Programme Risk

Risk management has been formalised over the programme lifecycle, with regular risk update meetings that reduced from a monthly to quarterly basis when the initial emergency response phase of the programme scaled down in late 2023. Risk appetites have remained high over the programme life, exceeding FCDO’s set appetites. This is to be expected in a programme that operated predominantly in frontline regions of an active conflict, that has sustained in fighting since the full-scale invasion in early 2022. At programme closure, the risk appetites (agreed by SRO and Development Director Kyiv) were as follows:

Risk category	Humanitarian appetite
Financial and fiduciary	Receptive
Reputation	Receptive
Safeguarding	Receptive
Strategy & context	Eager
Policy and programme delivery	Eager
Public service delivery & operations	Receptive
People	Receptive

Risks with negative trends that threatened programme success included: aid diversion, partner performance, access, and energy poverty. IOM’s announcement of the first large-scale case of aid diversion across the Ukraine humanitarian response, and lack of clear reporting on the involvement of donor funding created an increasing risk to the programme. Mitigation measures such as pausing funding and reporting to the Internal Audit and Investigations Directorate helped minimise the impact of the risk Engagement with IOM and recovery of funds is ongoing. Further details on this case can be found in the 2023/24 Annual Review.

Partner performance was specifically an increasing risk as local male staff were mobilised to join the Ukrainian armed forces during the programme. This meant staff would often feel unable to work outside their homes, creating a risk for programme delivery. For this risk specifically, given UK Government's political support to the Government of Ukraine during this conflict there were few mitigating measures that could be put in place.

Access was an increasing risk and concern during the programme. The Russian Federation’s territorial gains meant fewer people were accessible to project partners. There were sustained attacks on humanitarian workers. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Additionally, when the Sumy border crossing point between Ukraine and Russia was destroyed following the Ukranian incursion into Kursk, this significantly reduced the routes for Ukrainians in the temporarily occupied territories to return to Ukraine. The programme had few levers to mitigate this risk.

Finally, in Moldova, the end of the gas pipeline agreement increased the risk of widespread, severe energy poverty in Transnistria. This risk was escalated to the programme’s SRO, with re-allocations made to support partners to address related energy needs amongst vulnerable populations. Through these mitigation measures, where possible, as well as the high-risk appetite – the programme has been able to deliver within appetite over its lifetime.

With the successor programme, HARP, most risks will continue to be relevant. Reflections on the risk management process have been made with recommendations on how to improve this for the HARP process. It was noted that escalation processes could be more dynamic: with the time taken to update seniors, risks risked becoming issues. It was also unclear how risks fed into portfolio level and cross- BE Kyiv risks. On risk mitigation, it was noted that no system was in place to ensure agreed actions were carried out, and external challenge and support to hold the programme to account and ensure mitigation strategies were effective was lacking. Equally, it was felt management of partners risks – ensuring they was managing these effectively – could be stronger.

A key risk mitigation tool that was not employed by the programme is regular monitoring of partner activities. The security restrictions in place on internal travel to South and Eastern Ukraine, where the vast majority of the programmes funding is spent, meant programme monitoring by the team was not possible. Direct programme monitoring by UHF was what alerted the wider humanitarian community that the risk of large-scale aid diversion had become a reality, and led to the programme pausing funding to IOM to ensure protection of taxpayer funds . In a high-value, high-risk programme, it is essential that the team can conduct programme monitoring, and efforts should continue to secure permissions for this.

Update on Partnership Principles

Our Partnership Principles in Ukraine were developed in response to the Alliance’s Ukraine strategy for a locally-led humanitarian response and in consultation with our direct implementing partners – in particular Mercy Corps, HAVEN partners (NP and ACTED) and IOM. The Principles focus on donor best-practise for supporting and strengthening localisation. Downstream partners commended and endorsed the Principles and provided feedback and advice on how to use them in practice.

During the last year of the programme, evidence that the Principles had been integrated into our programmes included implementing partners strengthening and supporting leadership of their local partners in local coordination efforts and providing Ukrainian language as a medium of communication at various conferences, workshops and seminars for partners. Partners now include the percentage of overheads for local partners into programme budgets and budget for duty of care related expenses such as PPE, fuel for evacuation, and certain insurance costs for staff working on the front-line.

The majority of our evidence on the effectiveness of these Principles is anecdotal from partner reports. As we develop our future programme we will seek to integrate the Principles into our programme logframe to ensure regular tracking of indicators, as well as set up M&E mechanisms to collect evidence on whether the Principles are being used effectively in practise.

## G: Programme Management: Commercial & Financial Performance, Monitoring & Evaluation

Programme Team structure and performance

Set up on emergency funding rules, the programme responded initially to a difficult to predict trajectory of need. The diversity of partners and contractual arrangements captured in this programme, meant there was a heavy lift of programme management during the first year to put in place structures, systems and processes. The time, effort and resources this required was, at times, underestimated. The emergency funding basis meant that many routine programme processes and documents (including annual reviews and programme-level logframes) were delayed and developed retrospectively as staff capacity began to improve in 2023/24.

Despite this effort to normalise processes, persistent overload[24] on the team saw delays in completing some core programme processes. Significant staffing issues (a lack of appropriately experienced staff coupled with staffing gaps) and the complexity of the programme and context were also contributing factors. Many programmes in Ukraine which were being stood up at pace faced similar challenges. Resourcing needs were communicated but took time to be worked through. A point of reflection remains for FCDO in how to ensure departmental priorities are effectively and efficiently resourced – to secure enough people, and with the right skills, to enable us to meet our oversight obligations whilst also standing up high-value programming at pace.
[24] E.g. in the period from October 2023 to March 2024 the team responded to a ICAI review, an IAD audit, developed a £500m business case in addition to implementation of the existing programme in an uncertain and changeable context. 15 DDAs were developed and signed off in the first 18 months of the programme – a large number for a single programme.

The programme’s governance structure has undergone significant changes since the beginning of the response. The initial phase of the programme in 2022 was designed and managed by the FCDO’s Humanitarian Response Group crisis structure. This evolved into a standalone Ukraine Humanitarian Team in June 2022 with the programme placed under leadership of a Programme SRO based in the FCDO’s Eastern Europe and Central Asia Directorate. In 2024/25, SRO leadership for the programme shifted to the British Embassy Kyiv.

Throughout the life of the programme, most programme team staff have been based outside of Ukraine (in London or working remotely from other locations), with team members making trips to the region where security and capacity permitted this. The number of UK team members permanently based in British Embassy Kyiv increased during 2024/25 to three as platform space in the Embassy increased. Opportunities for travel beyond Kyiv have been severely limited by security considerations, with only a handful of short visits being made beyond Kyiv (e.g. to Poltava in January 2024 and to Mykolaiv in October 2024). Advisory capacity was significantly impacted throughout the programme due to difficulties in recruiting advisers internally which obliged reliance on external contractors with a high turnover. In 2024/25 these problems became acute due to a shift in the management of the central contract for securing external advisors. Staffing throughout the programme was a reoccurring issue (as flagged above) and was captured in the programme’s risk register, rated as severe and subsequently escalated to Eastern Europe and Central Asia Directorate directors. Resourcing issues persisted through to programme closure.

Overall partnership performance

The programme consisted of different funding mechanisms. This included unearmarked appeal funding and softly earmarked funding with UN agencies under Memorandum of Understanding, and earmarked funding with NGOs through Accountable Grant agreements. As a result, there was not one consistent approach to partner management across the programme. Overall, partners funded under the programme performed well despite the challenging and volatile context. Staffing and recruitment were reoccurring issues for many partners. URCS struggled to secure and retain staff across the two years and subsequently undertook a review of their salary scale and benefits to enable them to become more competitive as an employer.

Reporting

There was a trend of increased frequency and quality of reporting over the life of the programme, due to increased staffing in the team and increase in earmarked funding agreements. During last 12 months, overall partners provided quarterly or biannually narrative and financial reporting in a timely manner and to a high quality. Reporting frequency for UN and Red Cross partners were pre-agreed at institutional level, and took a lighter approach compared to NGOs who provided regular quarterly reports. Ukrainian Red Cross via British Red Cross experienced delays in producing biannual 2023-2025 One Plan narrative reports for their 2024/25 funding due to URCS staff capacity. However, to monitor progress British Red Cross produced quarterly financial reports and produced in depth monthly meetings presenting progress against the programme’s targets. The quality of reporting across partners has varied with ACAPS and STAAR’s initial reports lacking detail; however, the ACAPS team has consistently responded constructively and made necessary adjustments. Whilst some improvements to STAAR’s reporting were made, these were minor and not consistently applied across the lifespan of the project.

Overall partners’ financial management was strong across the programme (with the notable exception of IOM) despite the rapid implementation and expansion of their operations. The majority of partners provided timely and accurate financial forecasts with some delays caused by staff capacity. Notably, URCS’ financial management significantly improved over the programme’s three years which is testament to the investment in building their management capacity.

Risk management

All programme managers ensured regular proactive risk discussions with partners including updates to partner level risk registers. During the programme, a few partner risks were escalated. One risk that was escalated to senior leadership team, was the impacts of the changes to the mobilisation legislation and the impact it potentially could have on URCS and NGO staff. The change in law saw URCS no longer fully exempt and had the potential to cause significant staffing issues and therefore impact their ability to operate as many in frontline delivery roles were males of conscription age (e.g. 70% in URCS’ emergency department).

Delivery chain mapping

Most partners provided regular updates to their delivery chain mapping, however level of detail provided varied. With the scale of local partners supported by the HAVEN consortium, for example, the partners did not provide highly detailed information such as exact implementation locations for each partner. Pooled fund and appeal partners did not need to provide this due to the inability to distinguish donor funding and subsequently publish partners online.

Assets

NGO partners provided quarterly asset register updates. Multilaterals were not obliged to share asset registers as through central agreements, assets will be purchased, managed, and disposed of according to their rules and procedures.

Aid Diversion

The first major case of alleged fraud in the Ukraine humanitarian response was communicated in July 2024 when IOM privately briefed donors on possible fraud and diversion of aid funds under their management. Alleged issues concerned staff misconduct (including supply chain conflict of interests; procurement irregularities; negligence, and delivery of low-quality winter kits). IOM referred these allegations to the UN’s Office of Internal Oversight, which initiated a series of investigations. FCDO received written confirmation from IOM in October 2025, at the conclusion of the investigations, that no FCDO bilateral funding to IOM Ukraine was impacted by the 21 cases investigated.

Partner performance issues such as late reporting and lack of staff capacity at IOM Ukraine to engage with FCDO should have served as early warnings that all was not right. A refresh of the due diligence assessment for IOM Ukraine is required before future funding could be disbursed, to be assured that issues raised – particularly around their management of procurement – have been addressed.

Commercial

In the early stages of the programme, bilateral in-kind assistance was provided through FCDO’s central contract with commercial partner, Palladium. The contract was also used for deployments (advisory capacity) and Standby Partnerships. The number of standby positions funded by the Ukraine Humanitarian Team has significantly reduced since the start of the programme, from 31 positions in 22/23 to 1 position in 24/25. Total expenditure on Standby Partnerships over the programme was around £2.3 million. Palladium’s performance in relation to invoicing and reporting has improved since 2023/24. Through retained staffing and knowledge, the team established better working relationships with Palladium project staff, contributing to improved communication.

Performance management issues within DAI impacted delivery. Late reporting meant a lag between project implementation and formal updates to FCDO. Despite repeated feedback from FCDO, the quality of reporting improved only minimally over the project lifetime. In conclusion, whilst DAI implemented operational aspects of the project well, their value-add in delivering the technical assistance was unclear – both in practice and reporting.

Financial Performance

The original Business Case approved funding of £220m, notionally split across financial years as follows: 2022/23 (£60m), 2023/24 (£160m). This was followed by a Business Case Addendum which was approved to increase the budget to up to £419m and extend the programme end date to 31 March 2024. A no cost extension was then approved to extend the programme end date to 31 March 2025.

Final spend against the £419m Business case budget was £418,398,124. Reallocations took place in each financial year to address partner’s changing needs and fill gaps in funding, using funding held for contingencies and unspent funds from other partners. Throughout 2024/25, over £8.5 million of funding was reallocated, including £4.5 million held for contingencies. These reallocations supported partners to prepare for winter activities and mitigate the effects of the US Aid funding pause.

Of the total business case value, £4 million was capital budget and £415 million was programme resource budget. The capital components were largely made up of in-kind assets procured and donated to the Government of Ukraine in the early stages of the response.

Table A: Partners and spend across programme:

Code	Partner	Component Description	Total programme budget (£)	Total spend to programme end (£) / (At 31 March 2025)	% spend (Against total budget)
101	XXXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXXXXXXXX	XXXXXXXXX	XXXX
102	Standby Partnerships	Short-term humanitarian expertise embedded into United Nations organisations working in Ukraine and neighbouring countries	£2,865,255	£2,397,462	83%
103	OCHA/UHF	Support to the Ukraine Humanitarian Fund (UHF) and strengthened humanitarian coordination in Ukraine	£72,500,000	£72,500,000	100%
104	UNHCR	Support to the Ukraine Regional Refugee Response Plan	£25,000,000	£25,000,000	100%
105	IFRC	Humanitarian Preparedness and Response Support to Ukraine and the region	£15,000,000	£15,000,000	100%
106	DEC	Aid Match funding to provide food, cash, water, medical care, and psychological support to people in Ukraine and refugees in the region.	£25,100,000	£25,100,000	100%
107	Palladium	Humanitarian experts deployed to work on the Ukraine response	£2,882,479	£2,520,814	87%
108	Bilateral CDEL	Provision of items in-kind for the Ukraine Humanitarian Response (Capital Expenditure)	£3,691,089	£3,691,089	100%
109	UK-Med	Primary health care provision, capacity building and Health Assessments in Ukraine	£321,926	£321,926	100%
110	Bilateral RDEL	Provision of items in-kind for the Ukraine Response (Resource Expenditure)	£5,298,507	£5,298,507	100%
111	UNICEF Moldova	Assistance and Protection for Women and Children in Ukraine and Moldova	£28,825,000	£28,824,928	100%
113	World Food Programme (WFP)	Emergency food assistance, cash and social protection system strengthening in Ukraine and Moldova	£22,500,000	£22,500,000	100%
114	ISF	Emergency Shelter Assistance and Energy support for Communities in Ukraine	£9,997,986	£9,997,986	100%
115	Mercy Corps Europe	Locally led, Inclusive and Versatile Emergency Support to Conflict Affected Populations in Ukraine (LIVES)	£44,462,131	£44,381,742	99.8%
116	International Organization for Migration (IOM)	Inclusive humanitarian and resilience support to people in need within Ukraine and across the region	£46,750,000	£35,492,157	75%
117	UNFPA (Moldova)	Supporting the reproductive health needs of people in emergencies	£8,450,000	£8,450,000	100%
118	Ecorys	Programme Monitoring and Assessments	£1,798,654	£1,738,479	97%
119	World Health Organisation (WHO)	Inclusive System Strengthening, Building Resilience of Rehabilitation Services and provision of Technical Support in Ukraine	£9,575,199	£9,380,604	98%
401	British Red Cross	Supporting a localised humanitarian response to build resilience in Ukraine	£22,270,988	£22,232,951	99.8%
402	NP	Humanitarian action through volunteers, enablers and networks (HAVEN) in Ukraine	£18,728,886	£18,728,886	100%
403	STAAR	Support the transition of humanitarian caseloads into inclusive social protection systems in Ukraine and Moldova.	£3,000,000	£3,000,000	100%
404	WPHF	Supporting women’s organisations in Ukraine to deliver humanitarian and protection activities.	£6,855,593	£6,855,593	100%

Audit

An internal audit took place at the beginning of 2024/25, which reviewed the Ukraine Humanitarian Response Programme in 2023/24. The audit focused on the overall management of the programme, with a deep dive into three specific FCDO funded partnerships: UHF, administered by the Office for the Coordination of Humanitarian Affairs (OCHA), Mercy Corps and British Red Cross. The net risk rating of the programme was assessed as Severe, but the review found that the programme had developed adequate controls to operate in a challenging environment. All recommendations from the audit were implemented or are ongoing.

No partner audits took place over the life of the programme, however Due Diligence Assessments were refreshed for UNFPA Moldova to improve assurance. Audited financial statements will be requested from partners as part of programme closure.

Programme-level approach to monitoring and evaluation

Our Monitoring and Evaluation approach focused on two areas: 1) regular partner reporting and meetings – as agreed within each partner agreement, and 2) five rounds of TPM over the course of the programme from an independent supplier (Ecorys). Due to the security situation, the programme team was unable to make regular visits to partner sites. Travel constraints also limited the team’s ability carry out direct engagement with beneficiaries.

Our TPM covered areas of Ukraine that FCDO staff could not regularly travel to. Each round aimed to monitor the quality and quantity of activities conducted, assess the knowledge of staff on the ground in key technical and compliance areas, accountability to affected populations, risk management and protection of programme participants and to conduct spot-checks in key compliance areas, i.e. asset spot-checks, beneficiary lists.

The monitoring methodology evolved over the course of the programme, incorporating diverse data collection methods to ensure a comprehensive assessment of aid delivery. These included: 1) field verification visits to humanitarian delivery sites, where monitoring teams engaged directly with staff and beneficiaries to observe operations firsthand; 2) Key Informant Interviews (KIIs) with implementing partners, government officials, NGOs, UN agencies, and other humanitarian actors to gather qualitative insights; 3) Computer-Assisted Telephone Interviews (CATI), to systematically capture recipient feedback; 4) document analysis of project reports and operational frameworks and policies to verify compliance with humanitarian standards; and 5) thematic studies, such as the localisation study in round 3, which assessed the role of Ukrainian NGOs in aid delivery.

Following Round 3, FCDO also shifted from a one-size-fits-all questionnaire set to tailored questionnaire sets per partner. This led to more in-depth and individualised reporting and follow-up. After each Round Ecorys presented key findings and recommendations to FCDO and implementing partners. Ecorys produced a synthesis report of all five rounds and concluded the programme had been highly relevant and inclusive and adapted to evolving needs. It also outlined key recommendations for HARP, for example developing more flexible approaches to better reach marginalised groups, and stronger feedback mechanisms to ensure that community input leads to meaningful programme adjustments.

Results from each TPM report were shared and discussed with FCDO colleagues and partners. Whilst there was no systematic process to track progress on implementation of every recommendation, the reports gave FCDO higher level assurances on delivery effectiveness and partners’ management of risk.

Weaknesses in our MEL approach should be addressed in future programming:
- Severe limitations on access for the programme team to partner locations largely prevented direct monitoring.
- Both TPM and regular partner reporting and engagement focused mainly on individual partner level monitoring and activity rather than how these interventions delivered collectively against outcomes and impact in our theory of change.
- The absence of a MEL strategy meant that potentially useful recommendations captured through ad hoc MEL approaches on individual projects were less able to feed through systematically into strengthening the wider programme.

Date of last narrative financial report	30/09/2025	Date of last audited annual statement	31/12/2025