## TEFOS Programme Annual Review

Title: TEFOS (“Territorios Forestales Sostenibles” in Spanish which translates as “Forests, Communities and Sustainable Growth” in English).
Programme Value £ (full life): £64m		Review date: April 2024 – March 2025
Programme Code: [301502]	AMP start date: 01.04.22	AMP end date: 31.12.2027

Summary of Programme Performance
Year	20/21	21/22	22/23	23/24	24/25
Overall Output Score	N/A	B	B	A	A
Risk Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301502 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301502 Documents

## A. SUMMARY AND OVERVIEW

Description of programme
TEFOS (“Territorios Forestales Sostenibles”) is a £64m sustainable forest programme that aims to reduce deforestation in conflict-affected areas of Colombia. TEFOS works predominantly in 20 conflict-afflicted municipalities, and in an additional 15 municipalities. Collectively, these municipalities account for nearly half of all deforestation in the Colombian Amazon region, as of 2022. Tackling deforestation in the Amazon region requires a holistic approach that addresses complex drivers, such as land tenure insecurity[1], illegal drivers of deforestation[2] and limited access to sustainable livelihood opportunities for local communities.
[1] This can also help with legal drivers behind land grabbing such as cattle ranching, mining, industrial agriculture and infrastructure.
[2] such as land grabbing, cattle ranching in protected areas, illegal mining, illegal wildlife trafficking
To tackle these challenges, TEFOS has three Pillars: Pillar 1 (2021-26) supports the rollout of the Multipurpose Cadastre (MPC) in target municipalities as part of the Colombian Government’s (GoC) National Development Plan (2022-2026). TEFOS also promotes interoperability between the cadastre with other environmental data systems while building the capacity of government institutions to use this data to tackle deforestation. Pillar 2 (2021-26) strengthens the capacity of Colombian agencies to prevent, prosecute and sanction environmental crimes. Pillar 3 (2024-26) operates at a local level, supporting communities to develop sustainable livelihoods to reduce incentives and pressures that create an enabling environment for deforestation.
All three Pillars are expected to work in tandem in target municipalities where deforestation and the implementation of the Peace Accords are key challenges and priorities for the GoC. In this context, Pillar 3 has been strategically focused on promoting sustainable land use in geographic areas with the highest rates of deforestation, which also experience challenging security conditions linked to the presence of illegal armed groups. This approach reflects a conscious balance between programme delivery considerations and the opportunity to achieve meaningful impact in priority areas. It is expected that TEFOS will support tangible reductions in deforestation by fostering behaviour change in the local communities and institutions. With improved information about land administration and land use, clarity over land tenure, and stronger institutional capacity to investigate environmental crimes, land users are disincentivised from engaging in illegal deforestation. At the same time, rural communities have more opportunities to pursue legal and sustainable livelihoods.
However, the TEFOS programme is being implemented within a context of highly volatile deforestation rates at the national level, with the highest rates in the Amazon region. Deforestation is related to the expansion of illicit economies including forest to pasture conversion for cattle ranching, land grabbing and illicit crops. This expansion has been facilitated by the construction of over ~1,100 kilometres of illegal roads, which was identified as the main driver of deforestation in 2024 and early 2025.[3] Although 2024 showed an increase in deforestation of 36% compared to 2023, there has been an overall downward trend in deforestation rates in the last decade[4]. While deforestation is occurring across all TEFOS municipalities, it is not distributed equally amongst all jurisdictions.
[3] Procuraduría General de la Nación (2025)
[4] Ministerio de Ambiente y Desarrollo Sostenible (2024)
Figure 1 – Timelines of TEFOS pillars
Pillar	Phase 1		Phase 2
	2020	2021	2022	2023	2024	2025	2026
1	Strengthening & supporting the Government of Colombia to update the multipurpose cadastre and incentivise sustainable land management. (£43m).
2		Building capacity in multiple agencies to investigate environmental crime, focussing on illegal activities that are driving deforestation, such as land grabbing. (£10m).
3					Promote sustainable economic activities and conservation incentives appropriate for conflict-affected, deforestation hotspots. (£9.9m).

Summary supporting narrative for the overall score in this review
After two consecutive “B” scores during the first two years of the programme, followed by the implementation of a robust Improvement Performance Plan – IPP, the TEFOS programme started to deliver consistent and significant results against log frame targets obtaining an “A” score in 2023-24. The programme receives a consecutive “A” score during this fourth implementation year (April 2024 – March 2025). Most of the actions from the IPP remain in place and have become good practices within the programme. Although not contributing directly to the overall score, indicators at the intermediate outcome and outcome level also showed significant progress, providing evidence that the programme is on track to deliver expected impact.
Table 1 – Scoring calculation
Output number​	Output Description​	Impact Weight (%)​	Output Performance​	Impact Weighted Score​
1​	Land users (men and women) are aware of the multipurpose cadastre and have greater knowledge of land rights, restrictions and responsibilities​	14.3%​	Outputs substantially exceeded expectation (A++)​	21.4​
2​	Regional/local government increase capability to use multipurpose cadastre in decision making including land use planning​	14.3%​	Outputs moderately exceeded expectation (A+)​	17.9​
3​	Cadastral information of municipalities with deforestation hotspots is updated ​	14.3%​	Outputs met expectation (A)​	14.3​
4​	Multipurpose cadastre data interoperable with SIAC (Environmental National Information System). ​	14.3%​	Outputs moderately did not meet expectation (B)​	10.7​
5​	Targeted state institutions at local & regional level improve interagency coordination and cooperation, as they strengthen their skills to enforce environmental rule of law​	21.4%​	Outputs met expectation (A)​	21.4​
6​	Targeted institutions have increased knowledge and expertise to prevent and investigate illegal drivers of deforestation and tackle its financial chain​	21.4%​	Outputs moderately exceeded expectation (A+)​	26.8​
Annual Review Score​: A		100%​	Outputs met expectation (A)​	112.5​

Due to differences in the timing and scope of the three Pillars, it has not been possible to align delivery across the same locations on the ground, in particular as Pillar 3 is set to begin one year later than initially planned. Nevertheless, together, the three Pillars present a holistic approach to tackling deforestation, and there have been recent examples of cross-pillar working. For example, integration of cadastral information from Pillar 1 with environmental information from local body, SINCHI[5], in Cuemaní where Pillar 3 operates. TEFOS’ implementation years have offered multiple learning opportunities. In particular, changes in Colombia’s political and legal context have influenced programme delivery by affecting implementation timelines, institutional coordination and approval processes, requiring adjustments to sequencing and delivery modalities across the Pillar.
[5] SINCHI: Instituto Amazónico de Investigaciones Científicas SINCHI – Colombian entity that is in charge of researching the Amazon in relation to conservation and sustainable development, exploring local bioeconomies and integrating ancestral knowledge systems. SINCHI is the environmental leader of Cuemaní, are where Pillar 3 of TEFOS is taking place.
Pillar 1, implemented by the World Bank (WB), advanced significantly against milestones: 75% of output targets were met or exceeded (ref. Section C for details). Targets for cadastral updating and conservation agreements were exceeded, and capacity-building efforts significantly strengthened local environmental authorities. The most significant milestone for Pillar 1 during FY 24/25 was the initiation of activities in 25 of the 32 UK targeted municipalities, including eight located within Paramillo and Puinawai National Parks.
TEFOS cadastre work is directly implemented in 20 municipalities and two National Natural Parks (PNN Paramillo and PNN Puinawai). As these National Parks partially encompass 12 additional municipalities, TEFOS reaches a total of 32 municipalities. During this reporting period, the initial list of municipalities was adjusted to include the rural areas of Peque and Ituango, beyond the partial area within PNN Paramillo, to maximize the efficiency of a joint operation with Catastro Antioquia. As shown in the Table 2 below:
Table 2 –Group of municipalities under Pillar 1
#	Municipality	Department	Financial approach
1	CALAMAR	GUAVIARE	Group of municipalities financed mostly with resources from UK Cooperation.
2	MIRAFLORES	GUAVIARE
3	PUERTO RICO	CAQUETA
4	LA MACARENA	META
5	MAPIRIPÁN	META
6	PUERTO CONCORDIA	META
7	URIBE	META
8	VISTAHERMOSA	META
9	EL RETORNO	GUAVIARE
10	CARTAGENA DEL CHAIRÁ	CAQUETA	Group of municipalities financed mostly with Local Contribution.
11	SAN VICENTE DEL CAGUÁN	CAQUETA
12	SOLANO	CAQUETA
13	SAN JOSÉ DEL GUAVIARE	GUAVIARE
14	TAME	ARAUCA
15	MESETAS	META
16	PUERTO GUZMÁN	PUTUMAYO
17	LEGUÍZAMO	PUTUMAYO
18	SAN JOSE DE URE	CORDOBA
19	(ANM)[6] PUERTO COLOMBIA	GUAINIA
20	INÍRIDA	GUAINIA
21	CAREPA	ANTIOQUIA	Municipalities that overlap with the Paramillo National Natural Park (PNN) and the Puinawai National Natural Park (PNN). Intervention in the Formalized Ethnic Territories is mostly funded with resources from UK Cooperation.
22	CHIGORODÓ	ANTIOQUIA
23	MUTATÁ	ANTIOQUIA
24	TIERRALTA	CORDOBA
25	MONTELÍBANO	CORDOBA
26	(ANM) MORICHAL	GUAINIA
27	(ANM) PANA PANA	GUAINIA
28	EL BAGRE	ANTIOQUIA	Group of municipalities with cadastral operations by Catastro Antioquia. Financed mostly by resources from UK Cooperation.
29	SEGOVIA	ANTIOQUIA
30	ZARAGOZA	ANTIOQUIA
31	PEQUE	ANTIOQUIA
32	ITUANGO	ANTIOQUIA
[6] ANM - non-municipalized areas (Areas no municipalizadas in Spanish) refer to those areas located in Amazonas, Guainía and Vaupés departments that do not coincide with the territorial levels defined in the Constitution, therefore their management depends of the department to which they belong.

The strong progress against milestones resulted in cadastral updating of ~6.5 million hectares, exceeding over three times the agreed upon milestone (2 million hectares) and surpassing several intermediate indicators such as conservation agreements and training programs. These advances were complemented by regulatory progress, notably the issuance of Decree 462/2025, funded mainly through TEFOS, and enabled operations in Indigenous territories under the Free, Prior and Informed Consent (FPIC) framework[7].
[7] Decree 462 of 2025 regulates the implementation of the Multipurpose Cadastre in Indigenous territories and territorialities, under a differential and intercultural approach. The decree is the result of a prior consultation process carried out through the Permanent Roundtable for Consultation with Indigenous Peoples. It ensures that cadastral information respects Indigenous territorial rights and autonomy and supports territorial planning and environmental protection.
In addition, interoperability between cadastral and environmental data systems was strengthened through pilot projects[8], which will allow environmental authorities to use cadastral data for planning and conservation purposes for the first time. Institutional capacity was also strengthened via structured training programs for environmental authorities and local governments. These actions collectively represent a major step towards securing land tenure, improving territorial governance, and reducing deforestation pressures in strategic areas.
[8] Cadastral–Environmental Integration Pilots, led by MinAmbiente, in coordination with IGAC, SINCHI, ANT, National Natural Parks, CARs, NIRAS and local governments, aim to develop strategies that integrate environmental and cadastral information in order to promote territorial rights. This approach seeks to generate alternatives for land use and access, primarily in forest reserve areas established under Law 2 of 1959, while advancing a new proposal for defo Cadastral–Environmental Integration Pilots, led by MinAmbiente, in coordination with IGAC, SINCHI, ANT, National Natural Parks, CARs, NIRAS and local governments, aim to develop strategies that integrate environmental and cadastral information in order to promote territorial rights. This approach seeks to generate alternatives for land use and access, primarily in forest reserve areas established under Law 2 of 1959, while advancing a new proposal for deforestation containment.
Building on this success, next year’s (FY25/26) priorities will focus on accelerating cadastral operations in Indigenous territories under the FPIC framework, finalising strategic contracts with Catastro Antioquia and ethnic organizations, and further enhancing interoperability between cadastral and environmental data systems. These actions will consolidate gains and ensure the programme continues to deliver inclusive, sustainable outcomes aligned with its theory of change.
Pillar 2, implemented by UNODC, delivered expected results for FY24/25 (ref. Section C for details), with timely delivery of support to beneficiary entities. During this fiscal year, Pillar 2 strengthened inter-institutional coordination and enforcement capacity at local and regional levels through joint work involving the National Land Agency (ANT) and the Procuraduría General de la Nación (PGN), Colombia’s oversight body for the conduct of public officials. This contributed to more coherent and effective prevention and enforcement responses in priority territories, including actions addressing the financial drivers of deforestation. A total of 623 institutional actors were trained in a range of areas to help tackle environmental crime, from investigation and prosecution to community-based approaches. Evidence from post-training assessments indicates that learning outcomes exceeded the expected threshold.
Pillar 2 faces important sustainability challenges, including the high turnover of trained personnel across beneficiary institutions. Therefore, the final year of implementation should prioritise consolidating and institutionalising the most relevant tools, methodologies and capacity-building processes developed throughout the programme, rather than creating new interventions. This includes supporting partner institutions to formally adopt and continue using key products such as specialised training modules, investigative methodologies, inter-institutional coordination mechanisms, the Judicial Observatory of Environmental Crimes (OAJ), and the TEFOS virtual learning platform beyond the programme lifecycle.
Pillar 3, implemented by NIRAS through a consortium of three partners: NIRAS, ONF Andina and GITEC, faced delays in the inception phase during this reporting period, following the signing of the contract in May 2024. The inception report was submitted as planned in November 2024, but required three rounds of review by FCDO, Colombian Ministry of the Environment and Sustainable Development (MinAmbiente)[9] and SINCHI ahead of approval on 11 June 2025. The Work Plan also required protracted negotiations with the GoC and local communities, including around a change of scope from two geographies to one and volatile security situations with illegal armed groups around the Total Peace negotiations between the GoC and dissident groups n Amazonian region. Furthermore, uncertainty around UK government ODA cuts announced in February 2025 created additional delays to necessary contract adjustments ahead of the implementation phase. Implementation of Pillar 3 was therefore delayed to the following reporting period, ultimately beginning in October 2025.
[9] Ministerio de Ambiente y Desarrollo Sostenible/Ministry of Environment and Sustainable Development - Institution serving as the technical implementer of Component 5 on Multipurpose Cadastre, leading Subcomponent 5.1 Institutional Strengthening of Environmental Authorities and Subcomponent 5.2 Development of Information and Communication Technologies (ICT) and strengthening of the Environmental Information System of Colombia (SIAC).
During this reporting period NIRAS focused their efforts on building partnerships and identifying the families that would be supported[10] by the programme to ensure rapid implementation once the contract was amended and the final budget was approved. This has resulted in strong alliances with stakeholders key to community buy-in and provision of technical assistance. NIRAS also responded to recommendations from the inception phase, such as strengthening their conflict sensitivity approach and strengthening coordination with SINCHI. As required, Pillar 3 implemented an adaptive project management approach to building alliances with key stakeholders such as SINCHI, ASOJUNTAS[11], COGANCHAIRÁ[12] and the MinAmbiente. These partners and potential subcontractors will play an essential role in securing community buy-in and delivering technical assistance under the three components of Pillar 3 (detailed in Annex 2). A positive development was coordination between NIRAS and Pillar 1 to develop a pilot for the formalisation of rural property for some households in the Forest Development and Biodiversity Nuclei of Cuemaní[13], where Pillar 3 is located. This will allow TEFOS to partly test assumptions and relationships between Pillars as per the Theory of Change.
[10] The characterisation process includes surveying the property area and collecting socio-environmental and productive information through surveys conducted jointly with families and local experts. Based on this information, the elements and areas to be targeted—such as productive reconversion, conservation, and/or restoration—are agreed upon and formalised in a Conservation Agreement with the families leading the change process.
[11] Asociación de Juntas de Acción Comunal - A second-tier organization in Colombia that brings together Community Action Boards (JACs) from a specific territory (locality, commune, district) to coordinate efforts, represent their interests, and implement projects for the benefit of the community. It is a non-profit entity of a civic and social nature.
[12] Comité de Ganaderos de Cartagena del Chairá – Local committee in charge of improving the production systems of cattle ranching in Cartagena del Chairá.
[13] The transition from Active Deforestation Clusters (NAD) to Forest and Biodiversity Development Clusters (NDFyB) is a commitment to territorial socio-ecological transformation for peace with social and environmental justice, in which the protagonists of this change are the peasant, indigenous, and Afro-descendant

Major lessons and recommendations for the year ahead
See detailed recommendations in Annex 1.
Pillar 1
Ensure the Multipurpose Cadastre delivers inclusive and equitable outcomes for ethnic communities
The programme should prioritize the effective inclusion of Indigenous and Afro‑descendant communities as beneficiaries of the Multipurpose Cadastre, ensuring that cadastral approaches, institutional arrangements and implementation pathways are adapted to ethnic communities’ social, cultural and territorial realities. This is essential for strengthening legal tenure security, environmental governance and trust in public land administration in TEFOS municipalities.

Strengthen programme governance, financial oversight and delivery capacity to ensure effective implementation
Implementing institutions and partners should reinforce coordination, contract management and financial oversight mechanisms to mitigate delivery risks, ensure value for money, and maintain implementation momentum, particularly in areas with high operational complexity and during periods of institutional transition.

Safeguard the sustainability and institutionalization of results beyond the life of the programme
The World Bank and national counterparts should focus on embedding the programme’s key results—technical, institutional and capacity‑building—within permanent national and local government systems, budgets and mandates. Particular attention should be given to maintaining trained human resources, interoperable data systems and inter‑institutional coordination mechanisms to ensure long‑term impact after programme closure.
Pillar 2
Address the sustainability challenge by embedding Pillar 2 interventions within permanent institutional systems
A central challenge for Pillar 2 is ensuring that its interventions remain viable once external support ends. To address this, greater emphasis should be placed on institutional ownership and long‑term adoption, ensuring that capacities, tools and ways of working developed under the Pillar are fully integrated into existing mandates, systems and standard practices of partner institutions (e.g. the Attorney General’s Office could progressively integrate TEFOS-supported investigative methodologies and inter-agency coordination practices into permanent operational and training structures. Likewise, the Judicial Observatory of Environmental Crimes (OAJ) could serve as a long-term institutional mechanism within the Judicial Branch for managing and analysing environmental crime information. ).

Protect and consolidate the impact delivered by Pillar 2 through sustained inter‑institutional collaboration
The impact achieved under Pillar 2—particularly in strengthening responses to environmental crime—depends on continued collaboration between environmental, justice and security actors. Consolidating inter‑institutional coordination as an ongoing and operational way of working is essential to ensure that progress achieved under the Pillar translates into lasting results beyond the programme’s lifetime.
Pillar 3
1. Place inclusive and participatory engagement at the centre of Pillar 3 implementation
   The effectiveness and sustainability of Pillar 3 depend on meaningful participation of local communities and organisations. Strengthening inclusive mechanisms that amplify community voices in decision‑making—particularly in conservation, livelihoods and territorial governance—will reinforce local ownership, legitimacy and the programme’s ability to operate safely and effectively in high‑conflict environments.
2. Secure long‑term sustainability through strong alignment and buy‑in from local and national institutions
   Pillar 3 should continue prioritising early and sustained alignment with local governments, relevant national authorities and strategic partners to ensure institutional ownership and continuity beyond project closure. Clear alignment with public policy priorities, combined with selective engagement with additional partners, is essential to anchor results and enable longer‑term uptake and scaling.

Deliver Pillar 3 through robust adaptive management and sound programme oversight
Given the complexity of the volatile security situation on the ground, Pillar 3 requires strong adaptive management to balance scalability, flexibility and risk management. Maintaining clear financial oversight, conflict‑sensitive implementation and evidence‑based learning will be critical to ensuring timely delivery, safeguarding staff and resources, and maximising the programme’s contribution to conservation and sustainable livelihoods.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

TEFOS assumes that a holistic and demand-led approach is required to reduce deforestation in post-conflict/conflict affected, rural areas of Colombia. This includes tackling key deforestation drivers: illegal economies and environmental crime, uncertainty in land rights and land titling, and the lack of alternative livelihoods. The combination of activities delivered via TEFOS will bring economic, environmental and social benefits through incentives and opportunities for communities to sustainably manage land and reduce pressure in forest areas. The overarching theory of change for the programme is summarised in the figure below.

Figure 2 - TEFOS summarised theory of change

TEFOS’ theory of change comprises of multiple types of interventions involving a range of public institutions Political and governance dynamics create challenges in driving  synergies towards a common goal, such as halting deforestation. The British Embassy seeks to build bridges and facilitate engagement across key TEFOS stakeholders.
This year (FY24/25), TEFOS made important progress in aligning its interventions with the theory of change, with individual Pillars achieving results. Total convergence across the three Pillars remains a challenge in terms of timelines. However, the systemic articulation envisioned by the theory of change on linking cadastre, enforcement, and livelihoods in the same territories, was tested between Pillars 1 and 3 through cadastre-environmental integration pilot exercises in the same territory.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
See detailed information per outcome indicator in the annex 2.
Pillar 1 is partially on track to deliver its expected outcomes related to strengthened land governance, improved tenure security, and enhanced territorial planning in deforestation hotspots. During FY24/25, the Pillar advanced key enabling conditions, including improved interoperability between cadastral and environmental information systems, the use of conservation agreements as incentive mechanisms, and expanded access to multipurpose cadastre information at municipal level. Progress has been particularly strong at an area‑based level, enabling municipalities and environmental authorities to use cadastral and geospatial information for planning and management even before parcel‑level updates were completed. However, outcome‑level progress remains constrained by delays in parcel‑level cadastral updating.
Implementation timelines were affected by prolonged procurement processes, complex fiduciary requirements, institutional transitions, and external challenges such as security risks, logistical constraints, and socio‑environmental sensitivities. Despite these constraints, Pillar 1 continues to provide integrated territorial interventions under TEFOS, including pilots linking cadastral and environmental planning processes. A non‑cost extension is likely to be required to complete outstanding commitments. In the next reporting period, priorities will focus on accelerating cadastral operations in targeted municipalities (including Catastro Antioquia, refer to Table 2) and Indigenous territories, finalising key contractual processes, strengthening interoperability between cadastral and environmental data systems, scaling up capacity‑building for local authorities, and reinforcing risk‑management measures to ensure compliance with social and environmental safeguards and a do‑no‑harm approach.
Pillar 2 is on track meeting most output and outcome milestones and reinforcing the pathway that improved enforcement capacity prevents illegal drivers of deforestation. A marked increase in law-enforcement activity and expanded access to environmental, geospatial and judicial information point to strengthened operational performance and greater uptake of analytics tools for institutional decision-making. In addition, two planned initiatives were completed under CONALDEF[14], strengthening coordination between the environmental sector and law enforcement entities. Training activities contributed to positive improvements in institutional knowledge and skills. Taken together, these achievements constitute important enabling conditions and signals of increased institutional capacity and deterrence, although their sustained impact will depend on territorial, economic and governance measures, as well as on ownership and continuity by national entities.
[14] CONALDEF (National Council for Combating Deforestation and Other Environmental Crimes) is an inter-institutional coordination body led by the MinAmbiente and composed of entities from the environmental, security, justice, defence and land sectors involved in preventing and addressing deforestation and related environmental crimes.
The results of Pillar 2 contribute towards the systemic conditions for mitigating environmental crimes, including deforestation, but the materialisation of this impact will also depend on territorial measures, such as the control of illegal armed groups, as well as the sustainability of the implementation of policies to improve the social and economic conditions of the populations inhabiting these regions.
Pillar 3 has not delivered outcome‑level results during FY24/25, as implementation remained at inception stage following delays to contract amendments and scope adjustments. The Pillar is designed to contribute to reduced deforestation by enabling land users in deforestation hotspots to adopt sustainable economic activities that increase incomes while reducing pressure on forests, including through improved sustainable land use management and increased revenues for supported households and organisations.
Looking ahead, planned actions include accelerating MPC rollout and activating the indigenous operator and MPC in areas surrounding Paramillo National Park tracks under Pillar 1, consolidating sustainability and knowledge transfer in Pillar 2 as part of the closing year of the Pillar, and finalising the contract amendment with NIRAS to fully implementing Pillar 3’s productive partnerships and conservation agreements. A revision of the theory of change and log frame is advised by MEL partner to reflect operational realities and embed adaptive learning, ensuring that the programme remains focused on delivering integrated, durable outcomes in its final phase.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
From the analysis of progress and achievements this year, there is clear evidence that TEFOS is having a positive impact on tackling deforestation and should continue. The programme’s theory of change continues to offer a comprehensive framework to address deforestation drivers through integrated interventions in land governance, law enforcement, and sustainable livelihoods. While differences in timelines and operational scopes across pillars have limited full convergence, cross-Pillar coordination has improved significantly, and the start of Pillar 3 enhances the potential for the ToC to materialise on the ground. The Cartagena del Chairá pilot represents a critical opportunity to demonstrate how these components work together, generating lessons that can inform future initiatives in Colombia and across the region. However, the planned closure of Pillar 2 in the following financial year may constrain the ability to further deepen and consolidate this materialisation of the ToC, particularly given that this period was originally envisaged as the only phase in which all three Pillars would be operating simultaneously, something that, in practice, was only partially achieved.
TEFOS is strongly aligned with national priorities, including the National Comprehensive Plan to Contain Deforestation, Integrated Rural Reform, and the implementation of the 2016 Peace Agreement, and complements other UK and donor programmes. The cross-sectorial nature of the TEFOS programme, has enabled interinstitutional dialogues and therefore integrate agendas. For instance, through the pilot in Cartagena del Chaira, it is planned that parcel[15] information collected by SINCHI through the Conservar Paga Programme in Cuemaní is shared with IGAC to enable a more efficient cadastral operation process. This has positioned this programme as a strategic platform for the GoC to reinforce systemic change rather than isolated actions even beyond the UK F&LU portfolio in Colombia. Overall, TEFOS has demonstrated progress toward its objectives and remains highly relevant to Colombia’s policy landscape – this is the first time that Colombia’s land is being fully mapped in the country’s history - and the UK’s climate and biodiversity goals. Continuation is recommended, with a focus on accelerating implementation, consolidating sustainability, and leveraging cross-Pillar pilots to maximise impact and inform future programming.
[15] The parcel is the basic unit of the cadastre and is defined as a real estate asset—land with or without constructions—identified in its physical, legal, and economic dimensions. It constitutes the main object of cadastral records, has legally defined boundaries, and may have its own land registry (matrícula inmobiliaria).

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Pillar 1: Multipurpose cadastre MPC update in environmental strategic areas

For FY 24/25, the analysis focuses on the indicators agreed during the restructuring process, finished on December 2023. As part of this restructuring, the GoC and the WB revised the log frame targets and introduced additional indicators to capture more detailed progress in cadastral operations.

Output Title	Land users (men and women) are aware of the multipurpose cadastre and have greater knowledge of land rights, restrictions, and responsibilities
Output number:		1	Output Score:	Output substantially exceeded expectations (A++)
Impact weighting (%):		10%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of people that increased their knowledge through communication strategies	Cumulative to date: 810 / (FY24/25: 283)	Output substantially exceeded expectations (A++): 1,140 / (FY24/25: 618)

During FY 24/25, MinAmbiente successfully implemented 14 workshops across four departments and twelve municipalities, reaching 1,549 participants. These activities focused on promoting understanding of the MPC, land-use restrictions, environmental governance, and deforestation containment strategies. The methodology combined participatory dialogues, social mapping, and tailored edu-communication tools, supported by culturally adapted materials. Pre- and post-workshop surveys confirmed that 1,140 participants (73%) improved their knowledge, surpassing the milestone for this FY and the end-of-programme target of 1,904.
Output 1 substantially exceeded its target, demonstrating the effectiveness of the redesigned approach informed by lessons learned from the initial workshop phase in 2022. Implemented during FY24/25, this phase recorded near-universal positive feedback (approximately 99%) in terms of participant awareness and perceived usefulness, confirming the validity of the methodological refinements. Key implementation challenges—namely complex inter-institutional coordination, logistical constraints in remote locations, and initial community scepticism related to environmental restrictions and potential tax implications—were effectively addressed through adaptive delivery modalities, culturally appropriate materials, and clear, consistent communication.
No changes to targets or indicators are proposed, as the component has met its objectives. Planned actions focus on consolidating lessons learned, producing case studies, and reinforcing risk communication strategies to address persistent concerns about conservation incentives and fiscal impacts.

Output Title	Regional/local government increase capability to use multipurpose cadastre in decision making including land use planning
Output number:		2	Output Score:	Output exceeded expectations (A+)
Impact weighting (%):		10%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 # regional/local government officials and relevant government agencies/entities trained on cadastral systems on e.g. tenure rights, land tenure restrictions, and responsibilities (including land administration, environment, planning and parks authorities; disaggregate by type of organisation, sex, age, ethnic group)	Cumulative: 283 / (FY24/25: 75)	Output exceeded expectations (A+): 284 / (FY24/25: 76)
2.3 Number of individuals and organisations supported by technical assistance under pillar 1 (ICF Technical Assistance KPI 2)	-	762

Output 2 has delivered significant progress toward strengthening institutional capacity for MPC use in territorial decision-making. During the reporting period, three major training cycles were completed, culminating in two diploma programs (managerial and technical) developed with the University of Medellín. These programs targeted environmental authorities and technical staff, focusing on governance, interoperability, and integration of cadastral and environmental information. In total, 284 environmental sector staff were successfully trained, meeting the intermediate target, and 762 individuals were reached through technical assistance and communication strategies, contributing to ICF TA KPI2 (International Climate Finance, Technical Assistance KPI2: Number of individuals and organisations informed by International Climate Finance technical assistance).
Authorities such as CDA, CorpoAmazonía, Cormacarena, and Corporinoquia are already applying MPC inputs (i.e., territorial diagnostics, homogeneous zones, legal territorial objects) despite incomplete parcel-level processes, signalling improved evidence-based planning. Coordination between IGAC, MinAmbiente, and other actors has improved, and the SAT[16] framework is being recognized as a flexible, fit-for-purpose approach to land administration.
[16] The Territorial Administration System (SAT) is a Colombian government initiative led by the DNP that integrates land, environmental, and planning information to support territorial decision-making, shifting from a traditional land administration model to a comprehensive territorial management approach that links rights, land uses, and restrictions, with the Multipurpose Cadastre serving as its technical backbone by providing the country’s core geospatial and land information.
The main change was the introduction of diploma programs to deepen institutional engagement and technical capacity, reflecting a shift from short courses to structured, competency-based learning. This approach aligns with programme objectives and strengthens sustainability by embedding knowledge within environmental authorities. No major underperformance was observed, and the output remains on track to meet end-of-programme targets.
Output 2 has exceeded expectations. No changes to indicators or targets are proposed, as the activity achieved its objectives. Planned actions for the next FY include coordination in TEFOS areas, in particular pilot 3 in San José del Guaviare and SAT.

Output Title	Cadastral information of municipalities with deforestation hotspots is updated
Output number:		3	Output Score:	Outputs met expectation (A)
Impact weighting (%):		10%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 # registry offices with information in digital format	Cumulative: 10 / (FY24/25: 3 ORIPs with information in digital format)	Output has not met expectation (B): 9 / (FY24/25: 0)
3.2 # of parcels with updated data in the Multipurpose Cadastre System	Cumulative: 48,116 / (FY24/25: 46,358 parcels updated)	Output has not met expectation (B): 38,349 / (FY24/25: 36,591 parcels updated)
3.3 Area within project municipalities with updated cadastral and property information through cadastral management processes [Ha]	Cumulative: 2,000,000 / (FY24/25: 1,811,415 Ha updated)	Output substantially exceeds expectations (A++): 6,726,983 / (FY24/25: 6,538,398 Ha updated)

During FY 24/25, indicator 3.1 led by the Superintendence of Notaries and Registry (SNR)[17], showed a cumulative progress that remains at nine ORIP[18]s digitised, with no additional offices completed. The SNR decided that, with the available resources, it would expand the scope for next FY to include digitization of Old System Books (LAS) in Segovia and Montería and Registry Records (AR) in San Martín and Puerto Asís, all located in UK-targeted municipalities. Additionally, migration from LAS to the current Property Registration System (FMI) was initiated in four ORIPs (Apartadó, Ituango, Dabeiba, and Montelíbano). These processes aim to consolidate registry information and support the implementation of the MPC. Progress during the FY was primarily contractual, including preparation of TORs and procurement adjustments for hiring 21 consultants to support sequential updating and data validation.
[17] Superintendencia de Notariado y Registro / Superintendence of Notaries and Registries - Institution serving as the technical implementer of Component 5 on Multipurpose Cadastre.
[18] Oficinas de Registro e Instrumentos Públicos /Registry Office - Registers real estate properties by processing the filing, thereby legalizing and making public the designation of ownership.
For Indicator 3.2, a 27% increase of the target was reached during this FY, with 38,349 parcels updated against 48,116 planned. This reflects partial cadastral formation[19] and updating[20] in eight municipalities, covering 6.51 million hectares and 35,285 parcels (partially in the municipalities of Miraflores, Calamar, Cartagena del Chairá, Puerto Leguízamo, San Vicente del Caguán, Solano, San José del Guaviare and Tierralta), plus 3,064 parcels through cadastral maintenance[21] processes in 11 municipalities (Mapiripán, Puerto Rico- Caquetá, Vista Hermosa, La Macarena, El Retorno, Puerto Concordia, Uribe, Cartagena del Chairá, Puerto Leguízamo, Tame, San José de Uré). Cartographic inputs advanced significantly: orthoimages and digital terrain models were completed for rural areas across six departments (Guaviare, Caquetá, Meta, Putumayo, Antioquia, and Arauca) and two national parks (Paramillo and Puinawai) with a total coverage of 16,540,688 ha, while urban cartography was finalized for 200 built-up areas (7,979 ha). Cadastral Operational phase has progressed averages 32% across 25 municipalities, with notable advancement in Solano (97.8%), Cartagena del Chairá (81.9%), and Tierra Alta (71.8%). Challenges such as security risks, restricted territorial access due to social unrest, limited availability of trained local personnel, poor connectivity, and delays in contracting logistics and temporary services operators have collectively slowed parcel-level progress in nine UK-funded municipalities, despite the project’s technical achievements.
[19] Cadastral formation is performed for those municipalities that do not have a cadastre
[20] Cadastral updating takes place for those municipalities that already have an initial base.
[21] Cadastral maintenance (conservation in Spanish) refers to the identification, collection and incorporation into the cadastral database of changes in the physical, legal, and/or economic information of conformed real estate. Although the information processing is done by IGAC as part of the contribution of the GoC, the inputs used to update the registry information in the ORIPs were made with the resources of the UK donation, WB loan and local contribution
Before the issuance of Decree 462/2025 (22 April 2025), IGAC adopted an alternative approach to advance operations in Indigenous territories despite compressed timelines and regulatory delays. While full deployment was initially contingent on the decree, IGAC leveraged the exception provided under Law 2294/2023 to activate a transitional model for cadastral incorporation. This involved preparing cadastral inputs, conducting pre-recognition activities, and designing operational plans aligned with FPIC agreements. In coordination with ANT, IGAC developed a “Special Procedure for the Incorporation of Indigenous Territories into the Cadastral Database”, enabling the update of reserves in Solano (Caquetá) and Puerto Leguízamo (Putumayo) ahead of schedule. These measures allowed progress in ethnic areas while ensuring compliance with social safeguards and maintaining dialogue with Indigenous organizations (ONIC and OPIAC), laying the groundwork for the expanded scope of operations covering 94 reserves and over 4.2 million hectares.
Indicator 3.3 achieved outstanding progress, surpassing the end-of-program target by a large margin. A total of 6,726,983 hectares were updated against a target of 2,000,000 hectares, representing 240% achievement. This result reflects the accelerated rollout of cadastral operations in prioritized municipalities and protected areas, including both formation and updating processes, as well as maintenance in strategic zones. The overachievement is largely explained by the incorporation of complementary resources from the National General Budget and funding sources[22], which expanded coverage beyond what was originally planned under UK financing. However, this strong technical performance contrasts with delays in contractual execution and operations in ethnic territories, caused by the late issuance of Decree 462/2025 and the complexity of inter-institutional agreements. While the indicator is well above target, risks remain regarding the completion of procurement processes to progress in Indigenous areas and National Parks, requiring operational adjustments and possibly a time extension to ensure compliance with social safeguards and commitments.
[22] The cadastral operation in targeted UK municipalities has been financed with several sources, including funding from PGN for base personnel at the national and territorial levels; Fondo Colombia en Paz for areas in Mesetas municipality, Inírida, and Puerto Colombia located within Puinawai PNN; USAID funding for rural areas in San Vicente del Caguán, Cartagena del Chairá, and Solano, which are located within Chiribiquete PNN; and some of the base personnel contracting has been financed through the UK-funds.
The significant overachievement in Indicator 3.3 (area updated) compared to the modest progress in Indicator 3.2 (parcels updated) is primarily due to differences in scope, funding, and operational complexity. The area indicator benefited from large-scale cadastral formation and updating processes financed through multiple sources, which allowed extensive rural zones and protected areas to be incorporated into the system. In contrast, parcel-level progress depends on detailed, parcel-by-parcel work in municipalities funded by the UK funds, which faced delays in contracting logistics and temporary services companies, as well as challenges in ethnic territories requiring compliance with FPIC and social safeguards. These processes are inherently more time-consuming and resource-intensive, involving individual property validation and community engagement. As a result, while technical progress on area coverage exceeded expectations, parcel updates remain off track and will require accelerated implementation and strengthened inter-institutional coordination to meet end-of-program targets. Coordination between IGAC and Pillar 3, through MinAmbiente, is likely critical to advancing parcel-level information sharing during household characterization processes.
Overall Output 3 met expectations. Changes during the year include the adoption of a sequential updating strategy, expansion of digitization scope to additional ORIPs, and activation of FPIC-aligned instruments through Decree 462/2025. Planned changes involve completion of pending cartographic inputs, installation of CORS in Indigenous reserves, and initiation of sequential updates in at least ten ORIPs. These adjustments aim to accelerate delivery and realign progress toward end-of-programme targets. To meet commitments and uphold social safeguards, a no cost extension is recommended by the MEL partner.

Output Title	Multipurpose cadastre data interoperable with SIAC (Environmental National Information System).
Output number:		4	Output Score:	Outputs have not met expectation (B)
Impact weighting (%):		10%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of Legal Territorial Objects modelled and standardised within the framework of the Environmental Information System (SIAC) strengthening.	10	Output has not met expectation (B): 4
4.1.1 Number of Legal Territorial Objects standardized and accessible through environmental entities	5	Output has not met expectation (B): 1
4.2 New tools and studies leading to improve territorial administration systems management (AF restructuring target)	19	Output met expectation (A): 19

For FY 24/25, progress on MPC and SIAC interoperability has been uneven. The RDM[23] continues to serve as the core IGAC-led tool to consolidate cadastral and registry data at the national level, including links with SIAC under MinAmbiente. RDM was deployed and tested on SNR infrastructure, and a test successfully integrated cadastral and registry data. Technical architecture was strengthened through updated guidelines and consultations with technology providers. Additionally, 21 registry offices were migrated to the centralized system, consolidating data system, consolidating data for 168 municipalities and over 1.8 million property folios.
[23] Repositorio de datos maestro/Master Data Repository - It is a technological platform that integrates the country’s cadastral and registry information under the LADM_COL standard. The RDM centralizes Cadastre and Registry data, eliminating separate work between entities and creating a single source of information for decision-making.
Despite these achievements, indicator 4.1 is off track regarding end-of-program targets for Legal Territorial Objects (LTOs)[24]. Only 4 of the planned 10 LTOs were modelled by MinAmbiente[25]. Similarly, for indicator 4.1.1, only one LTO (Protected Areas) was successfully disposed and published by PNN, however, the remaining three modelled LTOs could not be made accessible due to the pending implementation of the required solutions architecture and technological environment to ensure interoperability with SIAC and IGAC’s Master Data Repository. These delays were driven by prolonged procurement processes, institutional transitions, and the need for technical adjustments to align with MinAmbiente’s IT standards. For FY25/26, the plan is to finalize this architecture, deploy the necessary infrastructure, and publish all standardized LTOs to ensure they are available for consultation and use by environmental entities and other stakeholders.
[24] Objetos Territoriales Legales /Legal Territorial Objects - They are defined portions of territory with legal effects, either public or private. Their existence, boundaries, and measurements originate from a law or an administrative act of the State or from a private title. This information is produced by entities responsible for generating, maintaining, and providing access to the data.
[25] The fours LOT modelled are "Áreas Protegidas" (Protected Areas), managed by PNN; and "Ley 2da" (Law 2nd), "Reserva Forestal Protectora Productora" (Productive Protective Forest Reserve), and "Reserva Protectora Nacional" (National Protective Reserve), the latter three produced by the MinAmbiente.
For indicator 4.2, MinAmbiente progressed on producing three tools including: SIAC reconceptualization, Systematization of the experience “Knowing to Conserve with the Multipurpose Cadaster” and registry code analysis, which will support environmental planning and integration for 168 municipalities and over 1.8 million property folios.
Output 4 have not met expectations. Activities under this output, such as interoperability between the MPC and SIAC, deployment of the Master Data Repository, and modelling of LTOs, are actions that still require important progress in the Next FY.
Progress on recommendations from the previous AR for Pillar 1, lessons learned this year and recommendations for the year ahead
All recommendations from the UK Annual Review 23/24 have been addressed. Actions included maintaining regular monitoring of key contracts, strengthening IGAC–MinAmbiente coordination, implementing security protocols for fieldwork, and ensuring timely financial reporting for value-for-money analysis. Progress was also made on FPIC agreements and grievance mechanisms aligned with FCDO safeguarding standards. These measures have reinforced governance and operational efficiency in complex territorial contexts.

Recommendations	Progress 24/25
Recommendation 1. FA and IGAC to continue reporting to FCDO on the monthly follow-up meetings, the progress of the cadastre roll-out in accordance with the intervention strategy, which must also be complemented by a provisional timetable for the start and completion of cadastral operations.	Delivered - Progress on the cadastral roll-out has been reported during the monthly follow-up meetings. IGAC provided an estimated start date for field operations, so the timetable will be updated once key strategic contracts are awarded and signed. It is recommended to maintain this practice.
Recommendation 2. The WB and FA continue monitoring the strategic contractual processes, red flags and bottle necks in monthly catch ups and design timely strategies to overcome contractual and legal barriers.	Delivered - WB in coordination with FA is conducting weekly follow-up meetings with IGAC to monitor the progress of key contracts and address contractual and administrative bottlenecks. In addition, during the monthly follow-up meetings, FA presents fiduciary alerts for implementing partners to take timely action.
Recommendation 3. The WB and FCDO in coordination with DNP should engage with implementing partners to better understand the approach that is used to identify, monitor and react to security risks for the cadastral operation by Q4 2024/2025.	Partially delivered - As part of the safeguards workshop organized by DNP in April 2025, IGAC presented the security protocol applied during cadastral fieldwork, including self‑protection measures, risk reporting and response pathways, and operational procedures for high‑risk contexts. This exchange contributed to a clearer understanding of IGAC’s approach to managing security risks. However, further structured engagement involving WB and other implementing partners, including discussion of ongoing risk monitoring mechanisms and adaptive response measures across implementing partners, is still needed to fully meet the recommendation. / .
Recommendation 4. The WB and FCDO to encourage greater articulation between the Ministry of Environment and IGAC by the second half of 2024, to strengthen the contributions of the cadastral information to the environmental agenda.	Delivered - Coordination between IGAC and MinAmbiente has been strengthened through the development of the following three pilot projects: i) Cartagena del Chairá municipality, aimed at harmonizing planning tools and environmental data to support the MPC; / ii) Developing a protocol of environmental guidelines for cadastral operations in AEIA; and iii) San José del Guaviare, where interoperability mechanisms between cadastral and environmental data (SINA) are being implemented. / In addition, coordination has been evident in the implementation of activities under component 5.2, supporting communication workshops, and under component 5.5, which involves the strategy to provide information and support to CARs in using it for cadastral purposes, as described throughout this report.
Recommendation 5. FA to provide financial reports to the FCDO on the committed and executed budget per component and implementing partner. Based on this, the WB will report in the quarterly strategic meetings on budget progress and execution scenarios, outlining strategic actions that contribute to project advancement.	Delivered – FA presented the committed and executed budget during the monthly follow-up meetings. Based on this information and progress in key contractual processes, WB presented in August and December 2024 an overview of project progress and challenges, along with financial execution projections under moderate and worst-case scenarios, outlining the associated risks for each.
Recommendation 6. FA and the GoC institutions to work together to provide information required for the value for money analysis of pillar 1 as well as to the Improvement Plan led by FCDO in agreement with the WB.	Delivered - In 2024, FA submitted a report based on the methodology agreed with the British Embassy, which assessed financial and physical progress (as inputs for VfM) linked to the outcomes and intermediate results indicators of the UK Grant. The annual reports include a financial section with a qualitative analysis addressing the management of the 4Es (economy, efficiency, effectiveness, and equity). Regarding the improvement plan, the progress presented during missions, monthly follow-up meetings, and the weekly updates on key strategic contracts serve as inputs for the British Embassy's Improvement Plan.
Recommendation 7. WB to follow up agreements reached in the protocolized FPIC, particularly actions related to cadastral operation and capacity generation of indigenous organizations through intercultural schools	Delivered - FPIC agreements are documented in the official record of protocolization. The official follow-up is carried out by the GoC through the Ministry of Internal Affairs, at the request of either party (government agencies or IPs). The implementation of the agreements has been monitored within the framework of the semi-annual report and during missions, where the WB Indigenous Affairs Specialist requests updates on overall progress, identifies any delays in commitments and their causes, and provides recommendations. Additionally, when required, engagement is carried out with Indigenous organizations to address the technical and informational requirements necessary to advance agreements or contracts with IGAC. This report includes actions related to cadastral operations in Indigenous reserves (para. 36), capacity-building efforts through intercultural schools, and follow-up on FPIC processes.

Lessons learned
The implemented actions in response to the UK Annual Review recommendations provided valuable insights for strengthening program delivery:
- Enhanced Monitoring Mechanisms: Regular weekly and monthly follow-up meetings proved critical for early identification of bottlenecks and timely resolution of contractual and operational challenges.
- Strategic Interinstitutional Coordination: Joint initiatives between IGAC and MinAmbiente demonstrated the importance of aligning cadastral and environmental agendas to maximize impact and foster integrated territorial governance.
- Financial Transparency as a Trust-Building Tool: Timely and detailed financial reporting facilitated value-for-money analysis and informed strategic decisions, reinforcing donor confidence.
- Inclusive Engagement and Safeguarding: Continuous dialogue mechanisms and grievance redress systems, aligned with FCDO safeguarding standards, ensured community participation and compliance with social and environmental safeguards.
- Adaptive Planning in Complex Contexts: Flexibility and proactive mitigation strategies were essential to address delays caused by administrative processes and contextual risks, ensuring continuity of implementation.

Pillar 2: Strengthening capacities for environmental rule of law

Output Title	Targeted state institutions at local & regional level improve interagency coordination and cooperation, as they strengthen their skills to enforce environmental rule of law
Output number:		5	Output Score:	Output met expectation (A)
Impact weighting (%):		15%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 # plans/strategies/guidelines/protocols implemented to strengthen the PGN and CARS capacity to carry out preventative, punitive and disciplinary functions and improve coordination with other environmental authorities	Cumulative to date: 39 / FY24/25: 11 plans/strategies/guidelines/ protocols)	Output moderately does not meet expectation (B): 38 / (FY24/25: 10 plans/strategies/guidelines/ protocols were implemented)
5.2 Number of plans, strategies, guidelines, protocols implemented to strengthen the capacity of environmental authorities/pertinent entities in their preventive, punitive and disciplinary functions and improve coordination with other environmental authorities.	Cumulative to date: 39 / (FY24/25: 14 plans/strategies/guidelines/ protocols)	Output met expectation (A): 39 / (FY24/25: 14 plans/strategies/guidelines/ protocols were implemented)
5.3 # prevention actions related to deforestation in deforestation hotspots in programme municipalities.	Cumulative to date: 21 / (FY24/25: 2 prevention actions)	Output met expectation (A): 21 / (In FY24/25: 2 prevention actions were implemented)

Output 5 demonstrated strong progress towards strengthening interagency coordination and cooperation at local and regional levels, while enhancing institutional capacities to enforce environmental rule of law. Under Indicator 5.1, 10 out of 11 planned protocols and coordination mechanisms were implemented, reinforcing collaboration between the Public Prosecutor's Office (PGN) and environmental authorities through national and territorial roundtables, technical guidance, and anti-corruption tools. Indicator 5.2 fully achieved (and slightly exceeded) its target, delivering over 14 instruments that strengthened the National Land Agency’s (ANT) capacity to manage land-related drivers of deforestation and improved coordination across sectors, including financial investigation actors. Indicator 5.3 was fully achieved through targeted prevention actions in deforestation hotspots, combining field-level coordination and operational support. Overall, these results reflect enhanced inter-institutional cooperation, improved technical and legal capacities, and stronger coordinated responses to enforce environmental rule of law across territories.
In addition to the above, it is worth highlighting the strengthening of anti-corruption capacities for prosecutors and municipal attorneys against drivers of deforestation through the development of a practical guide. The guide strengthens technical, scientific, and legal capacities to investigate and sanction disciplinary misconduct and acts of corruption associated with deforestation, standardizing investigative criteria and promoting more robust and coherent institutional responses. All these actions facilitated the consolidation of a more strategic, coordinated, and focused state-level response to environmental crimes.
Output 5 met expectations. Only one activity under Output Indicator 5.1 was rated as “moderately does not meet expectation,” relating to the development of the training module for SINA public officials. While the content was successfully formulated, the module was not fully operationalised within the reporting period, as its virtualisation and integration into the TEFOS learning platform were delayed due to pending validation by the Public Prosecutor's Office (PGN) and the Institute of Public Ministry Studies (IEMP). This limited its immediate institutional uptake. To address this, activities planned for the next financial year include a dedicated consultancy to develop virtual learning environments and thematic modules on strengthening environmental authorities and combating deforestation, which will be integrated into both the TEFOS platform and beneficiary institutions’ systems.

Output Title	Targeted institutions have increased knowledge and expertise to prevent and investigate illegal drivers of deforestation and tackle its financial chain
Output number:		6	Output Score:	Output exceeded expectation (A+)
Impact weighting (%):		15%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
6.1 # interventions delivered that increase institution capacity	Cumulative to date: 57 / (FY24/25: 22 interventions delivered that increase institution capacity)	Output met expectation (A): 57 / (FY24/25: 22)
6.2 # officials trained in use of tools and protocols	Cumulative to date: 1,570 / (FY24/25: 1,098)	Output substantially exceeds expectations (A++): 1,947 / (623 – unique count) / (FY24/25: 1,558 officials)
6.3 % of public officials, judicial servants and members of civil society who show increased knowledge and understanding of environmental crime post-training*	70%	Output exceeded expectation (A+): 86% (The average score of the post-training evaluations administered to officials who participated in training on environmental crimes was 86%).

Output 6 consolidated a substantive and measurable strengthening of institutional capacities to prevent, investigate, and prosecute the illegal drivers of deforestation and their financial chains. From a strategic perspective, the following actions stand out: (i) The consolidation of the 'Follow the Money' approach by building specialised capabilities to investigate the financial chain of deforestation. This was achieved through advanced training in agricultural accounting, money laundering, asset forfeiture (extinción de dominio), financial analysis, and the use of specialised tools. (ii) Similarly, technical assistance and strategic mentoring were provided to key institutions, sustainably strengthening investigative, judicial, and analytical capacities in prioritized deforestation hotspots. (iii) Regarding the deforestation information and monitoring system, strengthening was achieved through structured mentoring and technical support for the design and implementation of the National Registry of Deforested Areas (RNAD), alongside the development of inter-institutional data governance frameworks, enabling more robust, interoperable systems and supporting evidence-based judicial and operational decision-making. In addition to the above, verifiable learning results were achieved through the training of 1,558 officials—including judicial operators, security forces, environmental authorities, and civil society—showing an average 86% (corresponds to the average score of the post-evaluations for the personnel from Criminal Investigation Section, Office of the Attorney General, and Superior Council of the Judiciary who attended the trainings) improvement in knowledge and competencies related to criminal investigation, prosecution, environmental sustainability in judicial decisions, and financial prosecution. Consequently, a clear shift was observed toward an increase not only in individual capabilities but also in the establishment of structural and sustainable capacity to address deforestation as an organized and financial crime phenomenon, aligned with the Program’s strategic objectives and producing medium- and long-term impacts. Output 6 exceeded expectation.
Progress on recommendations from the previous AR for Pillar 2, lessons learned this year and recommendations for the year ahead
Recommendations	Progress
Recommendation 1. UNODC to consider how its final planning cycle during FY24/25 can strengthen an exit strategy for the final year and present it in the steering committee in February 2025. This will involve defining key cross-cutting lines of work that can create lasting outcomes and are developed in a coordinated interinstitutional effort. It should also include alternatives to ensure the sustainability of previous years actions and knowledge retention among the institutions.	Delivered – During the FY24/25 annual planning process, UNODC presented to the High-level Committee (February 2025) a sustainability-oriented approach for Pillar 2. This approach outlined criteria to prioritise sustainability through the transfer of knowledge and operational tools—such as the TEFOS platform—to beneficiary institutions. The proposed transition aims to move away from direct mentoring towards greater institutional ownership, while identifying potential donor funding opportunities to support the continuation of selected processes beyond the formal closure of TEFOS.
Recommendation 2. UNODC and FCDO to map out how the different components of pillar 2 will contribute to TEFOS theory of change outcomes to prioritise the activities with the most impactful potential.	Delivered – UNODC, TEFOS programme team, and beneficiaries conducted participatory planning to prioritize theory of change-aligned activities. These efforts focus on Pillar 2 objectives Additionally; annual planning is complemented by weekly monitoring through technical and budgetary evaluations conducted in follow-up sessions. This dynamic process enables the adjustment of priorities and the timely enhancement of strategic lines with the greatest programmatic impact. This process is the result of sustained strategic engagement and technical coordination evidenced through a Annual Planning Report and its budget
Recommendation 3. UNODC should reform its communication processes with the Colombian entities to ensure stronger alignment and coordination on timelines, budgets and hiring decisions. A follow-up system for queries from entities should be established by Q2 2025 to ensure timely responses as well as the evidence of socialization of the procurement and recruitment processes with the recipient institutions.	Partially Delivered – UNODC strengthened operational communication and coordination with beneficiary institutions through joint definition of terms of reference and technical specifications, continuous bilateral engagement with institutional focal points, and regular technical and financial monitoring. These practices improved alignment on hiring needs, facilitated timely information sharing, and supported risk mitigation during implementation. Strategic coordination was further reinforced through mechanisms such as the High-Level Committee (February 2025) and the lessons learned review exercise (June 2025). However, the recommendation’s intent to formally reform communication processes and establish a structured, traceable follow-up system for institutional queries by Q2 2025 was only partially addressed, as evidence of a standardised and documented system applicable across institutions remains limited.
Recommendation 4. UNODC to outline a communication strategy to be implemented in FY25/26 to enhance the culture of mutual recognition between the institutions and to create a sense of ownership over pillar 2 outcomes and results. UNODC should also highlight the importance of cooperation and joint achievements in reports going forward, as well as the appropriate recognition of TEFOS as a UK cooperation programme.	Partially Delivered – UNODC implemented a series of communication activities to disseminate Pillar 2 results, reinforce institutional recognition, and highlight joint achievements in addressing deforestation and environmental crime. These efforts were further formalised through the inclusion of Communication focused activities in the FY25/26 Log frame (Activity 2.2), supporting sustainability, knowledge transfer, institutional ownership, and the visibility of UK cooperation under TEFOS. Interinstitutional dialogue was strengthened through multiple international forums, including a dedicated event to showcase collective achievements. However, while these actions contribute meaningfully to the recommendation’s objectives, evidence of a clearly articulated, comprehensive communication strategy for FY25/26 remains limited, supporting the assessment of partial delivery.

Lessons learned
- Anchor products to existing institutional frameworks such as institutional plans, regulatory instruments, already adopted indicator frameworks, etc., and make it explicit which product is incorporated into those frameworks and who is institutionally responsible for mobilising it (not just the focal point).
- Incorporation of products into institutions: Define the ‘nature’ of each product (guidance vs. adoptable) from the design stage and require that all deliverables include: (i) purpose, (ii) target users, (iii) formal incorporation decision (if applicable), (iv) internal approval route, (v) minimum evidence of ownership (pilot, internal circular, inclusion in POA, etc.).
- Ensure socialisation beyond the focal point: dissemination plan by mission, legal, planning and internal control areas; and ‘landing’ sessions focused on how the work changes (procedures, formats, flows) and not just on technical content.
- Digital tools: Involve those responsible for technology from the outset of processes involving products in this area; this reduces rework and improves adoption times.
Pillar 3: Promoting sustainable alternative livelihoods in deforestation hotspots
In this FY24/25, as a result from the inception phase, progress was made defining to detail the outputs and indicators to measure the impact according to the theory of change. Nonetheless, the implementation hasn't begun (as explained in section A), and thus there is no milestone progress reported yet for the indicators (N/A). NIRAS’s ability to rapidly begin implementation will determine FCDO’s confidence in the implementing partner’s ability to meet the output goals and indicator values. So far, FCDO recognises the adaptive planning and management that NIRAS has done to contribute towards the outputs.
Detailed updates are nevertheless provided against each output area.
Output Title	Public-private partnerships in place to promote commercialisation and market access of sustainable products & services
Output number:		7	Output Score:	N/A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
7.1 # of sustainable value chain models developed in intervention area (models developed for four of five supported products incl. cacao, copoazu, cacay, dairy, timber)	N/A	N/A
7.2 # of strategic upstream partners demonstrating increased interest in supported value chains (letter of interest)	N/A	N/A
7.3 # of commitments/instruments made by upstream actors to purchase products through supported value chains (letter of agreement/intent between actors in value chain ecosystem)	N/A	N/A
7.4 % of households supported by value chain capacity building activities (goods production, business management, etc.) reporting increased knowledge related to sustainable value chains	N/A	N/A

During this reporting period no quantifiable progress was expected for Output 7 as the inception phase was still ongoing, However, NIRAS has laid a foundation for milestones to be achieved in the next year as a result of multi-stakeholder alliance building, successful private sector engagement, and the identification of beneficiary households under the program.
Specifically, upstream private sector partners such as Casa Lúker, Natura, Amazonía Emprende, and Agrosolidaria, have signed letters of interest for all target value chains. Public and international cooperation sector partners have collaborated in the design and delivery of regional workshops geared towards sustainable value chain management. These are GIZ, Swisscontact and the Goverment of Caquetá. NIRAS expects to report quantifiable progress against these indicators in the upcoming FY, once implementation begins and the final budget is approved.
Additionally, two productive partnerships have been secured in close coordination with the Rural Development Agency. Firstly, COGANCHAIRÁ reached an agreement with NIRAS to promote the transition from traditional cattle ranching productive systems to silvopastoral systems, as well as securing infrastructure and technical assistance investments for 200 households in the dairy value chain. Secondly, Chocaguán agreed to strengthen the cocoa value chain in the region through improving its sustainability and building market linkages with specialized markets at a national level.
Furthermore, ASOJUNTAS agreed to identify an initial group of 250 households as direct beneficiaries of the programme. Together with the planned workshops and technical assistance, as well as with early identification of families prior to implementation, quantifiable progress is anticipated in the upcoming year. SINCHI has also meaningfully contributed to identifying the producer families, which will directly contribute to indicator 7.4.
Output Title	Sustainable land use and forest management plans developed and operationalised, including social inclusion and empowerment initiatives
Output number:		8	Output Score:	N/A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
8.1 Progress against four-step model for the development of a technical roadmap for the implementation of a farmer-led forestry concession model	N/A	N/A
8.2 Progress against eight-step model for the development and submission to relevant authority of a proposal for the farmer-led forestry concession through forestry management plan in Cueimaní.	N/A	N/A
8.3 Development of socially inclusive sustainable forest management frameworks to support operationalisation (i.e. sustainable forest management plan, business plan, extraction model, etc.)	N/A	N/A
8.4 % of planned farmer concession members receiving sustainable forest management training reporting increased knowledge in sustainable forest management	N/A	N/A

During the reported period no quantifiable progress was expected for Output 8. However, NIRAS has laid a foundation for milestones to be achieved in the next year as a result of qualitative progress made through close collaboration with MinAmbiente on the implementation of a Community Forest Concession (CFC)[26] in Cuemaní, as well as through the delivery of numerous multi-stakeholder workshops to align the methodological framework of the CFCs to ensure their replicability and scalability.
[26] Community (campesino) forest concessions will aim at the sustainable use and conservation of forests and biodiversity in deforestation containment areas identified and prioritized by MinAmbiente. Concessions will promote: 1. The community forest economy and biodiversity through sustainable forest management of timber, non-timber, wild flora, and ecosystem services, including, among others, activities related to the processing and marketing of products obtained from value chains, as part of the solutions promoted, based on nature and the bioeconomy. 2. The development of activities for the recovery, restoration, and productive ecological rehabilitation of forests and/or other natural ecosystems for future developments in the community forest economy and biodiversity. Ref. Decree 0057/2025.
More specifically, SINCHI, Corpoamazonía, MinAmbiente and NIRAS reached an agreement to design and draft the guide for the implementation of CFCs in the Amazonian region of Colombia following a participatory approach. This effort is directly related to NIRAS’s support towards MinAmbiente’s Directorate of Forests, Biodiversity and Ecosystem Services. On forest management, NIRAS and the consortium partner ONF Andina have developed a forest management plan for a 10,000-hectare polygon in the Cueva del Jaguar. This plan directly contributed towards MinAmbiente’s regulatory framework for CFCs.
Finally, SINCHI and staff members of the MinAmbiente’s Directorate have provided key technical inputs for the design of a national-level CFC methodological guide. Progress has been made in relation to the production of a first draft of the guide which includes key content elements and technical priorities. No progress has been made that directly relates to indicator 8.4. as farmer concession members have yet to be determined.

Output Title	In prioritised areas, supported communities adopt conservation practices aligned to the identified incentive requirements
Output number:		9	Output Score:	N/A
Impact weighting (%):		10%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
9.1 # of productive restoration system models developed	N/A	N/A
9.2 % of households in intervention area signing conservation agreements as managers of change	N/A	N/A
9.3 # of technical conservation knowledge outputs (i.e. land surveys, socio-environmental mapping, GIS assessments, carbon feasibility studies) developed for intervention area	N/A	N/A
9.4 % of supported households reporting increased knowledge of conservation schemes following capacity building activities	N/A	N/A

During the reported period no quantifiable progress was expected for Output 9. NIRAS has progressed the least on this output compared to 7 and 8. However, some milestones have been achieved.
Firstly, SINCHI, ASOJUNTAS and COGANCHAIRÁ have formally agreed to support in the identification of households that will be considered as part of the incentive program ‘Conservar Paga’. NIRAS estimates that 657 households will be supported through SINCHI, and an additional 474 households will be supported through ASOJUNTAS and COGANCHAIRÁ. Priority will be placed on ensuring that those identified do not overlap with existing work performed by ASOJUNTAS but rather introduce new households to the incentive programme.
Additionally, NIRAS worked closely with SINCHI and MinAmbiente to design the selection criteria for ‘change maker’[27] families to implement the productive restoration systems. NIRAS has pre-emptively identified approximately 350 ‘change maker’ families with the help of MinAmbiente, SINCHI as well as UNDOC.
[27] Change maker families, or ‘gestores del cambio’, refer to the community members in the local area that support the implementation of the Comprehensive Plan to Contain Deforestation 2023-2026 (PICD). This method reflects a community-based deforestation management strategy in line with MinAmbiente’s deforestation containment strategy. Change maker families are campesinos and indigenous communities.
Finally, NIRAS advanced in the conceptualisation and design of productive restoration models under Agroforestry and Silvopastoral Systems for cacao and copoazú. These models were designed with the participation of SINCHI and MinAmbiente, as well as COGANCHAIRÁ.
Progress on recommendations from the previous AR for Pillar 3, lessons learned this year and recommendations for the year ahead

Recommendations	Progress
Recommendation 1. During the inception phase NIRAS, with the support of the FCDO, should establish communication channels with the institutions that are relevant for pillar 3 implementation. This includes the Ministry of Environment, SINCHI and the local institutions.	Delivered – Despite an extended inception phase and a delayed start to the implementation of Pillar 3, NIRAS was successful in establishing communication with key institutional players at the national, departmental and local level. To date, NIRAS has direct communication with MinAmbiente, the Governor’s office of the Department of Caquetá, as well as the local mayor’s office and other local institution such as SINCHI, ASOJUNTAS and COGANCHAIRÁ. During the 2024-2025 period, NIRAS advanced in establishing partnerships and alliances with the local institutions that will identify the target families for the implementation.
Recommendation 2. NIRAS to outline the implementation plan the best aligns with the political interests of the GoC referred to the environmental, the agricultural and the peace agendas.	Partially delivered – NIRAS has strengthened coordination with MinAmbiente and local institutions to secure institutional buy‑in for the inception report and agreed workplan and has begun aligning implementation with key environmental priorities of the GoC. This includes identifying specific policies and regulatory instruments to support, such as Resolution 57 of 2025 on Community Forest Concessions and its pilot in Cuemaní. However, the implementation plan does not yet fully articulate alignment with the agricultural and peace agenda, nor does it clearly outline how political interests across sectors will be managed during the 2025–2026 electoral cycle. Sustained collaboration between NIRAS, FCDO and conflict sensitivity advisor will be essential to maintain institutional ownership and adapt implementation to potential shifts in political priorities, to fully meet the recommendation.
Recommendation 3. FCDO to ensure articulation between the NIRAS team and other relevant UK programmes and stakeholders that can leverage Pillar 3 ambitions.	Delivered – During the inception phase FCDO ensured articulation between UK-funded projects from the Forest and Land Use portfolio and UK Pact projects with pillar 3 activities related to sustainable cattle ranching in Caquetá. Key articulation was made with the Peace Programme to ensure actions were complementary in relation to conflict sensitivity approach in Caquetá and strengthening NIRAS proposal in this aspect. / After the approval of the inception report in June wider portfolio from UK-Pact projects, Science and Innovation and Biodiversity and Oceans about Cacay, Cacao were aligned.

## D: VALUE FOR MONEY

Key cost drivers and performance
The TEFOS value for money proposition as stated in the Business Case, recognises the importance of the complementarity of the pillars to unleashing the potential of transformational change of stated impacts. However, it also recognises that the differing timeframes and each pillars interventions makes it difficult to identify individual pillar contributions to outcome and impact-level results. The uncertainty in measuring the causality and attribution of interventions requires the FCDO to adopt a flexible approach to evaluating value for money (Vfm) by combining quantitative and qualitative indicators and giving relevance to the learning and adaptation processes demanded by the challenging circumstances and changing risks in which the programme operates.
This year’s assessment addresses a recommendation made by the FY23/24 TEFOS Annual Review: “The MEL partner to provide concrete directions to FCDO and DP’s about how to improve the VfM report and the adjustment of VfM indicators with the inclusion of qualitative information for the next AR.” This VfM assessment thus builds on VfM frameworks redeveloped for Pillars 1 and 2 during FY25 with more appropriate indicators. The evaluation is based on the FY25 MEL and DPs Annual Report.
It should be noted that due to the complexity of the new data reporting requirements, Pillar 1 and 2 reported with the information they had and are currently testing these requirements to prepare for a more comprehensive view of the indicators for the 2025/26 report. As part of this, indicators will be further refined to ensure feasibility and shared interpretation of reporting. Additionally, Pillar 3 hasn’t started their implementation, which also limits ability to assess VfM.
The assessment encompasses the 4 E’s of FCDO’s value for money framework – economy, efficiency, effectiveness, and equity, and overall cost-effectiveness, by the definitions outlined below:
- Economy: Evaluates the value of inputs and how they are managed during the programme delivery.
- Efficiency: An efficiency assessment considers the costs per unit of inputs and outputs at the required quality.
- Effectiveness: Measures how outputs are turned into intermediate outcomes and outcomes.
- Equity: UK Government spending cannot deliver VfM if not conducted in an equitable manner leading to equitable outcomes. This is why equity forms part of the VfM assessment.
Pillar 1
From the issuing of the WB’s Promissory Note until March 2025 (USD 55,000,000 representing £42,970,000), the UK has disbursed £27,090,000 (USD 34,266,442) to the Multi-donor Trust Fund. This represents around 63% of the total amount committed. Expenses incurred by the WB up until and through March 2025 amount to USD 4,104,570 including administrative fees and expenses (USD 2,148,744) and, total direct costs (USD 1,955,826) which include staff costs, consultants, travel expenses, media workshop and other. This represents around 12% of the disbursed amount and 7.5% of the total commitment.
Up to March 2025, the WB has allocated USD 14,519,000 to FA of which USD 13,000,422 (90%) has been spent. As a result, the WB had a positive balance of USD 17,645,694. FA has committed USD 19,138,406.35 based on the approved 2025-2026 Operations Plan and Procurement Plan, for this reason a fourth encashment for £12,900,000 (USD 16,317,353) was made early April 2025.
By July 31 2026, Pillar 1’s closing date, it is expected that an additional USD 26,418,983.92 will be spent, amounting to a 92% cumulative expenditure. Therefore, it is estimated that USD 3,555,474.91 from the total donation agreement with FA (USD 42,970,000) will remain unspent, corresponding to: i) the final payment for the software contract (MinAmbiente), ii) resources for the ethnic operator (excluding OPIAC), and iii) pending resources programmed by IGAC. Moreover, it is anticipated that the project, through the Ministry of Finance, will request a restructuring project to extend the project closing date to achieve the Project Development Objective targets. According to the regular financial follow up meetings between the WB and the TEFOS team, by the end of the programme there will be remaining resources (around USD 9.5m) at the Trust Fund, the destination of these funds will be agreed in the next FY according to the Administration Arrangement between both parties and FCDO’s strategic priorities.
Based on this information, the Programme team has reiterated to the WB the need to modify the payment schedule in the Administration Arrangement. In addition, the Programme team raised a concern with the WB, and implementing partners, about the chances of executing the full budget within the project timeframe if delays in the contracting processes continue. This situation poses a risk particularly for those activities that require a longer implementation time (such as the Catastro Antioquia contract and contracts with ethnic operators).
In regard to the 4Es assessment developed by the MEL Partner review, Pillar 1 delivers good value overall at this stage of the programme, but room for improvement remains. The Pillar needs to focus on catching up on some of its output and intermediate outcome milestones to enhance its efficiency and effectiveness as well as providing greater transparency of its budget allocation decisions taken within the reporting year.

Principle	Value for Money assessment
Economy	Pillar 1 executed project activities valued at $5,057,224 against a planned annual budget of $5,203,297, resulting in an execution rate of 97% and underspend of 3%, a low variance within the 5% tolerance, denoting good economy delivered. It was evidenced that with their shift in implementation plans within the year, funds are carefully reallocated where spend capacity is greater than anticipated.
Efficiency	Pillar 1 has met or exceeded 55% of its output level milestone targets for FY24/25. As noted under economy, it has delivered these results within the budget allocated to it annually. By this measure, the Pillar delivered poor value, as half of its output indicators did not progress as much as expected, even though all the outputs that did not meet expectations did see notable progression (ref Section C). Nonetheless, several strategies have been implemented to deliver outputs efficiently, three early case studies stand out: (1) support to the Intercultural School of Geography for Life[28], in partnership with IGAC and GIZ; (2) support to the operationalisation of the Master Data Repository (RDM); (3) IGAC’s experiences in San José del Guaviare were noted where innovative environmental governance had allowed the MPC roll-out to take place under volatile conditions, with added risks due to the presence of armed groups.
Effectiveness	Pillar 1 has met or exceeded 2 out of 3 (or 66%) of its intermediate outcome level milestone targets for FY24/25. As noted above under economy, it has delivered these results within the budget allocated to it annually. By this measure, the Pillar delivered moderate efficiency. While one of the intermediate outcomes was not met, another one outperformed its milestone target by 30%. On the other hand, with five CARs reported by MinAmbiente to uptake cadastral data by government institutions for sustainable land use planning or environmental management, the indicator for this year was exceeded, as the target was 4. By this measure, the Pillar has been strongly effective.
Equity	Equitable participation for women, indigenous communities, and youth has been embedded systematically in the MPC and other Pillar activities. At least five cases of sustainable integration of these groups into the implementation have been identified in the reporting period: (1) Successful integration of gender and ethnic inclusion protocols into IGAC’s cadastre methodologies and the environmental sector’s adoption of safeguards in conservation agreements; (2) IGAC’s safeguards team developed and disseminated the Social and Environmental Management Plans (PGAS) for cadastral update projects guide; (3) Indigenous and Afro-descendant organisations have been meaningfully engaged in participatory processes; (4) the WB coordinated and delivered a national workshop on social and environmental safeguards; (5) the WB and the TEFOS team at the British Embassy actively participated in the coordination and facilitation of the Gender Roundtables convened by IGAC. These actions support a strong equity rating.
[28] The IGAC Intercultural Schools “Geography for Life” are a community‑based territorial training strategy. They aim to strengthen the participation of rural, Indigenous, and Afro‑descendant communities in the Multipurpose Cadastre through dialogue between technical and local knowledge. They promote territorial understanding, conflict prevention, and informed decision‑making with an intercultural and equity focus.

Pillar 2
From April 2021 to March 2025, the UK has disbursed £7,744,365 to UNODC out of the £10,000,000 allocated for the entire life of the Pillar. Based on the annual evaluation, UNODC has spent an average of 98% of the total allocated funding each year showing a good level of budget execution. The remaining annual balance, considered underspent, is carried over to the next FY to continue operations and integrated into the last year's planning cycle. In addition, proactively UNODC provides information on the activities that cannot be carried out and submits a formal request to the British Embassy anytime a reallocation of the budget is required. The UNODC also noted that the underspend is used to cover any potential delay in receiving next year’s payment.
In the AR period (April 2024/March2025) the UK approved a budget of £2,367,532 (ICF funded) and the reported spending was £2,325,832 resulting in an underspend of 2% (that matches UNDOC´s corporate practice).
In regard to the 4Es VfM assessment developed by MEL partner, Pillar 2 delivered good value during the reporting period, achieving a positive rating of 6 out of 9 indicators. Compared to FY23/24, the pillar has improved significantly its performance on economy, lowering the variance between executed and planned budget from 17% to 2%. This signifies both good financial management and the ability to deliver the project in line with partners’ needs. The achievement of key milestones continues to be at or above expectations. However, as Pillar 2 enters the final year of implementation, evidence of areas for improvement remains in proving the additionality of the support provided to institutions, identifying and articulating transformative change, and raising further ambitions on equity and inclusion principles.

Principle	Value for money assessment
Economy	Pillar 2 executed project activities resulted in an execution rate of 98% and underspend of 2%. This is a significant improvement compared to the FY22/23 and FY23/24 periods when the average variance was 17%, denoting accurate forecast predictability and a satisfactory ability to meet the needs of stakeholders. All procurement processes met the UNODC compliance requirements, ensuring fairness, transparency and competition, and institutions are satisfied with 100% of the support provided, which indicates that procurement processes have been effective in delivering good economic value.
Efficiency	UNODC has reported meeting or exceeding 96% of its output milestones, the unmet targets reflect unspent balances. Pillar 2 support is perceived as valuable and useful by the relevant institutions. Some constraining factors that limit the added value of Pillar 2 have been identified, such as capacity building and data.
Effectiveness	Out of the 7 Intermediate Outcome and Outcome indicators targeted by the Pillar, 6 targets were met or exceeded. In most cases, achievements were significantly above expectations, supporting a rating of strong effectiveness. Based on the positive participation of the institutions in the Pillar’s activities as well as reported successful risk mitigations measures, the Pillar has been strongly effective. Pillar 2 has achieved three key transformational changes already from support to key institutions: (1) capacity building for ANT to enforce landowners’ environmental obligations and land-use restrictions in areas of ecological significance of the property by adopting legal, environmental, and social parameters proposed by Pillar 2 and issuing first resolutions to initiate the process of asset forfeiture; (2) consolidation and legitimisation of CONALDEF as the main government body in charge of the coordination and articulation for planned interventions against environmental crime; (3) strengthened regional coordination through the Amazon Cooperation Treaty Organisation (ACTO).
Equity	The Pillar has proposed eight separate tools or processes embedding equity and inclusion principles. Nonetheless, institutional stakeholders did not report being aware of methodological tools designed to operationalise gender equality and social inclusion. The Pillar lacks a structure component aimed at institutionalising the GEDSI approach within the beneficiary organisations.

Pillar 3
From April 2024 to March 2025, the Uk has disbursed £668,359 out of £1,033,202.60 corresponding to milestone 1 and 2 from the inception phase. Current contract with NIRAS is up to £9,900,000. The financial planning for the next FY will depend on the start of the implementation phase.
Pillar 3 is well set up to deliver good value for money once in full implementation. As the pillar was in early stage of operation in the reporting period, it has been reported only on selected VfM indicators.
Principle	Value for money assessment
Economy	Indicators point to good economy being delivered, as average fee rates remained within the tolerance margin of 5%, procurement processes were followed, and the quality of technical consultants has been assessed as high.
Efficiency	The main output in the period has been the inception report, which was delivered with some delay caused primarily by improvements in programme scope agreed with UK and Colombian Government counterparts, and uncertainty due to the broader UK ODA landscape.
Effectiveness	Strong relationships with government stakeholders and ownership of the Pillar were evidenced, which now need to be leveraged during implementation. The Pillar targets improved sustainable land use over 10,780.08 ha in the Cuemaní cluster (Outcome Indicator 3.1), against a total planned budget of approximately £10m, reflecting an intensive approach to sustainable land use. At the same time, the Pillar also targets activities with stakeholders in Bogota and Florencia and Cartagena del chairá and aims to have demonstrative effects through the Cuemaní pilot that other clusters in Colombia could learn from and replicate; as such its value cannot be defined only by the quantifiable impact on sustainable land use in Cuemaní.
Equity	Limited evidence due to the status of the implementation. Based on the GEDSI strategy the pillar is well set up to produce equitable outcomes and impacts.

Assessment of whether the programme continues to represent value for money

This year, TEFOS has maintained a strong trajectory toward up-to-the-mark Value for Money, with Pillars 1 and 2 delivering sustained results and reinforcing the programme’s multiplier effect. Achievements at both output and outcome levels demonstrate that TEFOS is not operating in isolation but leveraging partnerships with government and other stakeholders in foreign assistance and the private sector to amplify impact. Improved articulation and coordination with stakeholders, alongside strengthened relationships with institutions, have enabled more integrated and cost-effective delivery. These synergies continue to enhance the overall VfM of the grant by ensuring that resources generate broader systemic benefits rather than isolated outputs.

The programme team’s efforts to improve reporting from implementing partners have resulted in richer quantitative data, allowing for a deeper analysis and more informed VfM assessments. While gaps remain, the MEL report notes that qualitative approaches can complement these limitations. Current examples provided by partners are still fragmented, but a more structured qualitative methodology could transform these insights into meaningful evidence of efficiency and effectiveness. Overall, TEFOS continues to represent good value for money, provided that future reporting cycles strengthen VFM analysis and integrate qualitative evidence systematically to capture the full scope of programme impact.

E: RISK

Overview of risk management

For FY 24/25, the programme operated within FCDO’s risk appetite across five of seven risk categories, and kept a sustained pressure in Financial & Fiduciary, Strategy & Context, and Policy & Programme Delivery risks are due to security volatility, delivery delays and funding uncertainty. Overall, residual risk levels have remained stable or reduced, reflecting strengthened mitigation measures, closer TEFOS Programme oversight, and improved coordination with delivery partners. Where risks remain moderate, this reflects inherent programme characteristics, particularly delivery in conflict-affected deforestation hotspots areas, and the complexity of multi-pillar implementation rather than faults in risk management.
When it comes to main trends in risk exposure and response:
Policy and Programme Delivery: Delivery risk have been the most material category, driven by delays in prior consultation processes (i.e. pillar 1), high staff turnover across GoC institutions and delivery partners and interdependencies between pillars, particularly the impact of Pillar 1 delays on overall programme delivery.
Over the last year, the programme has strengthened governance structures and inter-pillar coordination meetings on strategic topics like communications, and programme results and pilots, embedded secondees and advisors within MinAmbiente to mitigate interface risk and revised delivery timelines and run three pilots to materialise integrated impacts across pillars. Residual delivery risk was assessed as moderate and improving though the complexity of the programme continues to require active management.
Financial and fiduciary risks have been a persistent area of pressure particularly related to delays in procurement and contracting processes under Pillar 1 and 3; and uncertainty around ICF budget allocations. While gross risks in this category were assessed as major to severe, residual risks have been reduced to moderate or minor through enhanced financial monitoring by Post and implementation of Performance Improvement Plans.
Overall, fiduciary risk is stable but continued monitoring remains essential.
Strategy and context, security and contextual risks increased during the review period due to resurgence of armed group activity in TEFOS municipalities and territorial restrictions while cadastre operation is taking place. Despite this, the programme remained deliverable through continuous coordination with Embassy political and security teams and adaptive territorial engagement strategies.
Residual strategy and context risk remains moderate, reflecting inherent operating conditions rather than programme underperformance.
Equality, safeguarding and SEAH assurance
Safeguarding risks remained low, with no reported SEAH or child safeguarding incidents during the period. Key actions included contractual safeguarding obligations for all delivery partners, a TEFOS-wide GESI assessment and the development of a programme-level GESI strategy, ‘do no harm’ approaches particularly in indigenous and conflict-affected territories and clear anti- harassment guidance aligned with FCDO standards for Pillar 1 cadastre activities.
Monitoring of gender and inclusion indicators is embedded within MEL processes, and safeguarding risks are assessed as minor and within appetite.
Climate and environmental risk
The programme’s objectives are fully aligned with the Paris Agreement, with climate and environmental outcomes at the core of TEFOS. Climate and environmental risk have been assessed and judged to be low, given that the programme is specifically designed to address deforestation drivers and strengthen sustainable land‑use systems, thereby mitigating rather than exacerbating climate and environmental risks.
Update on Partnership Principles
Although programme funds are not channelled through government systems, delivery partners maintain regular engagement with public institutions to ensure alignment with sectoral policies and regulatory frameworks. Given this interaction, the Partnership Principles (PPs) have been applied as a risk management strategy and governance framework rather than as formal conditions for disbursement.
During the review period, no significant concerns were identified regarding the four PPs, poverty reduction and the SDGs, respect for human rights, financial management and anti-corruption, and domestic accountability, within the scope of programme activities. However, recognising that collaboration with government entities can expose the programme to reputational and operational risks, we have incorporated elements of the PPs related to financial management and anti-corruption into our risk matrix and maintained dialogue with delivery partners to ensure compliance with international standards.
Going forward, the PPs will continue to play a partial role in programme monitoring, focusing on the early identification of risks in areas such as human rights, transparency, and accountability. This approach ensures that any deterioration in these principles can be addressed promptly through adaptive management measures, without imposing rigid conditionality on non-governmental delivery partners.
Due diligence approach
All key risks identified through partner Due Diligence Assessments are reflected in the programme risk register. Over the financial year no material deterioration in partner risk profiles has been observed, fiduciary and delivery risks associated with partners remain proportionate to the programme’s risk profile and no immediate DDA refreshes are required though periodic reviews will continue in line with FCDO guidance.
The programme has largely delivered within risk appetite, although sustained management attention has been required in financial, delivery and contextual risks. Looking ahead, priority risk management actions should include continued close financial oversight to avoid underspend or misalignment and ensuring delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Implementation agreements for Pillars 1 and 2 are formalised through promissory notes with the WB and UNODC, respectively. Therefore, the evaluation under commercial terms is not applicable to this FY report. Commercial evaluation only applies to the commercial contract signed between NIRAS and FCDO in May 2024.
According to the Administration Arrangement (AA), the WB is responsible for the programme management and administration activities for the Trust Fund, including programme governance, planning and executing work plans and budgets, managing communications and reporting, monitoring and evaluating activities. The Bank is also in charge of providing implementation support to recipient-executed activities. Fondo Acción[29], selected as the recipient entity for Pillar 1, oversees the management of the project and assumes part of the responsibility for implementation. FA signed an interinstitutional agreement with the implementing partners who are the local government institutions responsible for the activities, in accordance with the rules and procedures established in the Operational Manual of the pillar.
[29] Fondo Acción (FA) is the fiduciary agent responsible for managing the funds of pillar 1 of TEFOS
FA and the WB apply procurement and financial standards and exercise full control over the corresponding procedures for Pillar 1, ensuring full alignment with FCDO rules and requirements. They prepare updated information on contracting processes and financial performance that is presented at monthly catch-up meetings coordinated by DNP. On the other hand, since technical management is largely in the hands of implementing partners[30], the WB is responsible for reporting on performance during these meetings. The implementing partners are quite independent in applying their technical criteria, however, these criteria are sensitive to several factors, such as staff turnover, technological lock ins or Government priorities, which may risk the coherence of the project activities.
[30] These are the local partners corresponding to the public agencies that participate in the project (IGAC, Ministry of Environment, Registry office, National Natural Parks)
FCDO continued some actions of the Improvement Performance Plan set for FY2023-24 related to financial management of Pillar 1. Semi-annual meetings with WB were held to review timelines and financial risks associated to underspend. Weekly procurement meetings with WB, FA and IGAC were held to follow up on key procurement processes. Although large procurement processes are on track, the MEL team suggested further actions to ensure effective use of remaining resources in the context of a potential extension.
The agreement for Pillar 2 determines that the funds and activities are managed directly by UNODC, in accordance with the financial regulations and rules of the United Nations, also aligned with the FCDO standards. This includes the procurement of staff, equipment, supplies and services and the contracting processes. While the implementation of activities is carried out with around 16 government agencies, UNODC exercises a hands-on approach through individual consultants (“mentors”) who play a technical advisory role in the implementing institutions. This helps to ensure alignment with the activities and the budget agreed. UNODC reports on progress in the monthly catch-up meetings with FCDO.
The commercial contract with NIRAS to deliver Pillar 3 started on May 2024, and at the time, it was expected that the inception phase would finalise by November 2024. The mobilisation of the inception phase happened as planned, nevertheless the third milestone (FCDO’s approval of the inception report) took longer than expected, as outlined in sections above and Annex 2. Social dynamics related to total peace negotiations were unstable and two additional rounds of comments were needed ahead of June 2025 when the report was approved by the SRO. From December 2024 to June 2025 the NIRAS team worked on formalising key geographic and technical agreements with the GoC, improving conflict sensitivity, adaptive management, and delivery chain map sections of the report.
As above, the contract amendment process faced delayed in part due to the ODA cuts announcement and was ultimately finalised in October 2025.
Delivery partners (WB, UNODC and NIRAS) submit their annual reports which feeds into the MEL report provided by the MEL partner, including the information and data needed for the programme evaluation. This year all partners submitted their reports around mid-year, and one round of adjustments were made. Overall, the quality of all reports has been improved including qualitative information regarding cross cutting issues such as VfM, GESI and safeguarding.
According to the MEL partner, Pillar 1 has advanced in embedding GEDSI and safeguarding into land governance reforms by promoting equitable participation of women, youth, and ethnic communities, integrating gender and inclusion protocols into cadastral methodologies, and facilitating institutional dialogues such as Gender Roundtables. It has also strengthened safeguards through Social and Environmental Management Plans and national workshops, though challenges remain in ensuring representation in technical decision-making and consistent disaggregated data. Pillar 2 has adopted inclusive practices in training, participatory methodologies, and safeguards for risk prevention, but lacks systematic GEDSI tools, structured methodologies, and monitoring mechanisms, limiting institutional uptake and impact measurement. Efforts are underway to expand participatory spaces and virtualize technical content with a differential approach, yet the absence of operational instruments persists. Pillar 3 stands out for its comprehensive GEDSI Strategy, which integrates gender, disability, and social inclusion across all phases, promotes equitable participation in conservation agreements, and applies intercultural approaches. It also prioritises tools for awareness, disaggregated data, and inclusive local development, aiming to institutionalise equity and safeguard principles throughout implementation. However, the NIRAS’s staff does not include a GEDSI expert to support the MEL team. FCDO suggests incorporating a technical GEDSI team member to ensure that the strategy is successful.
The Cartagena del Chairá pilot, integrating Pillars 1 and 3, is the programme’s main opportunity to validate the theory of change at the local level. It combines cadastral updates from Pillar 1 with sustainable livelihood interventions from Pillar 3, aiming to link land tenure security and environmental planning with economic alternatives for communities in deforestation hotspots. FCDO should continue enabling this pilot by ensuring timely coordination among IGAC, MinAmbiente, and NIRAS, supporting documentation of all phases, and promoting cross-pillar learning. This will generate evidence for scaling integrated approaches and inform the revision of the theory of change and impact evaluation.
The TEFOS programme team will seek to enhance its effectiveness by improving communication with Delivery Partners regarding reporting requirements, particularly on technical and financial aspects to ensure clear direction and efficient use of partners’ time. Additionally, FCDO’s commercial team should adopt a more proactive role in advising the post on contract management and ensuring staff availability to offer guidance and support for key processes.
The contract with the MEL partner is, for now, the only one subject to a scorecard performance assessment. Requests to evaluate NIRAS performance haven’t been received, though contract KPIS will be agreed with NIRAS as part of the contract amendment. The latest assessment, for Tetra Tech conducted during the period from October 2024 to March 2025, yielded an overall score of 87% across the delivery, responsiveness, quality, resources, capacity, value and innovation and risk management criteria. FCDO highlighted the supplier’s strong performance, flexibility and diligence in meeting the programme requirements, including transparency. The programme team continuously receives valuable feedback from Tetra Tech and support in decision-making processes and will work closely during the revision of the ToC. As points for improvement, the programme team has indicated Tetra Tech improving the documentation of calculations related to Log Frame.

G: MONITORING, EVIDENCE AND LEARNING

Tetra Tech, as the MEL partner, provides constructive guidance to ensure that the Pillars of TEFOS are working together effectively to realise the desired outcomes, playing a key role in the execution of the overall programme. Tetra Tech engages with the programme’s implementing partners and FCDO by:
1. Providing monitoring during implementation to inform evidence-based programme management and allow learning to take place to enable continuous improvement of programme implementation and more effective realisation of the programme’s lifetime objectives.
2. Supporting strong programme-level reporting, monitoring and provide critical constructive guidance to ensure that the three separate Pillars of the programme work together coherently to realise the desired outcomes.
3. Undertaking an ex-post impact evaluation to provide evidence of TEFOS’ impact, and to provide lessons for future international forest and land use programmes.
To meet these objectives, the MEL Supplier is:
1. Taking the Programme Team’s feedback and carrying out for the first time a new way to evaluate the performance of the Pillar 2 through a Quality Assessment.
2. Creating a baseline that will enable to measure the impact of Pillar 3 work during and after implementation.
Addressing a recommendation made by the 2024 TEFOS Annual Review “The MEL partner to provide concrete directions to FCDO and DP´s about how to improve the value for money (VfM) report and the adjustment of VfM indicators with the inclusion of qualitative information for the next AR.”
1. Regularly evaluating and reporting to FCDO to support programme management, decision taking, annual reviews and results collection through interviews with main stakeholders.
2. Regularly communicating with the programme team and delivery partners in the evaluation process and explaining how the pillars are being measured and reported.
3. Constantly discussing with the DP and programme team about the indicator setting and creating strategies to improve the reporting progress.
TEFOS’ implementation years have offered multiple learning opportunities. For instance, Colombia’s political and legal situation has determined the way TEFOS has been implemented. Due to the changes in the timings of Pillar 1 and Pillar 3, this has impacted the outcome chain envisaged at the beginning of the programme design and thus limited on the ground integration across pillars. This has projected different challenges pointed out by the Tetra Tech team and pushed the programme team towards creation of additional strategies such a semestral cross pillar meeting that were continued to be carried out during this year. The MEL partner also considered revising its Theory of Change and Log frame to reflect reality of the three Pillars working at different levels (local/community, regional, national) and over different timelines to what had been anticipated in inception. This will be evaluated in the context of an expected TEFOS extension of Pillar 1, fund availability for Pillar 3 and preparation for the impact evaluation.
The Qualitative Assessment of Pillar 2 provided a more in-depth understanding of its impact with key findings to recognise the strengths and opportunities for improvement that were crucial for the evaluation. The enhanced coordination and capacity have led to a more cohesive response to illegal deforestation and environmental crimes, with institutions now working together more effectively than before Pillar 2 intervention. On the other hand, identifying combined recommendations for the FCDO, UNODC, and the GoC, has strengthened the project management and delivery.
Tetra Tech conducted the VfM assessment of this year under a redeveloped framework of indicators and qualitative information for Pillars 1 and 2, to address the recommendation made on the previous annual review and strengthen the information obtained from the DPs regarding the topic. The new framework was used for the assessment even though the VfM refresher workshops held with the MEL partner, DPs, and the Embassy took place outside the reporting period. The reporting of	Pillars 1 and 2 didn’t have all the information required and the DPs are currently testing these requirements to prepare for a more comprehensive view of the indicators for the 2025/26 report. As part of this, indicators will be further refined to ensure feasibility and shared interpretation of reporting. Additionally, Pillar 3 indicators for VfM assessment were established and reported, considering NIRAS started its operation in 2024 and hasn’t started implementation.
This annual review was made based on annual reports of Delivery Partners (WB, UNODC, and NIRAS) and the MEL annual report of Tetra Tech. The annual reports of DPs describe the state of each pillar throughout the year, including but not limited to, contextual situations impacting the project and its outcomes, institutional arrangements, performance, project monitoring, risk analysis, financial progress, lessons learned and strategic actions for the year ahead. Considering Pillar 3 started operating in May 2024 and the inception phase was extended until June 2025, its report focuses on the work plan and preparation for implementation rather than performance. These inputs were validated by the MEL team and supplemented with semi-structured key informant interviews, carried out with over 40 stakeholders from 14 different organizations participating in the programme. Regarding Pillar 3, interviews have been held predominantly with the NIRAS team themselves rather than stakeholders or institutions they will be working with due to the state of progress. With this information Tetra Tech generated their MEL annual report where they consolidated the progress assessment, progress against KPIs, value for money and generate recommendations for the year to come.
Date of last narrative financial report	April 2024	Date of last audited annual statement

## ANNEXES
Annex 1. Technical recommendations
Pillar 1
Ensure the Multipurpose Cadastre delivers inclusive and equitable outcomes for ethnic communities
1. IGAC, with support from the World Bank, should continue strengthening the community‑based training model under the Intercultural School of Geography for Life – Multipurpose Cadastre, consolidating Geographic Communities[31] as ongoing spaces for learning and local capacity building, with active participation of Indigenous and Afro‑descendant populations in TEFOS municipalities.
  [31] Geographical communities, according to the IGAC’s institutional approach, are groups of people who live in and interact with a specific territory. They hold local knowledge about the land, its boundaries, uses, and spatial relationships. This knowledge contributes to the production of geographic and cadastral information and to territorial decision‑making.
2. IGAC should advance the structuring and implementation of contracting mechanisms with Indigenous operators, building on the training processes already established and making use of the physical and virtual spaces provided by the intercultural schools.
3. In its role as cadastral authority, IGAC should consider adopting an extended Land Administration Domain Model (LADM) to better represent ethnic communities within the Multipurpose Cadastre.
Strengthen programme governance, financial oversight and delivery capacity to ensure effective implementation
1. With respect to the Land Tenure Objects (OTLs) modelled by the Ministry of Environment, IGAC is encouraged to publish these datasets through the Colombia en Mapas platform, in line with ICDE standards, enabling integrated access to cadastral and environmental information.
2. The World Bank should support dialogue between IGAC and Indigenous organisations to facilitate both the structuring and implementation of contracting processes, ensuring that engagement spaces (espacios de interlocución) are aligned with IGAC’s cadastral procedures.
3. The Superintendence of Notaries and Registry (SNR) should complete the digitization of its archives to enhance interoperability with cadastral and land administration systems.
4. SNR should also develop and implement alternative service delivery mechanisms for areas with limited connectivity, including municipalities covered by TEFOS.
5. The World Bank, Fondo Acción and FCDO should maintain close financial oversight to anticipate potential underspend risks or the need for programme extensions toward the end of implementation.
6. The World Bank and Fondo Acción should continue weekly monitoring of key contractual processes led by IGAC and the Ministry of Environment, identify bottlenecks through regular coordination spaces, and put in place timely mitigation strategies to address legal or contractual constraints.
Safeguard the sustainability and institutionalization of results beyond the life of the programme
1. The World Bank and the National Planning Department (DNP), in coordination with implementing partners, should identify early on sustainability measures to ensure that the project’s main outputs and approaches are absorbed into permanent institutional arrangements.
2. Specific support should be provided to manage transition risks associated with the change of government, including continuity of key technical and managerial functions.
3. IGAC, with support from the World Bank and Fondo Acción, should define and communicate a clear and time‑bound implementation plan for the Multipurpose Cadastre in Antioquia, the main region still pending coverage.
4. The Ministry of Environment, IGAC, SNR, National Natural Parks (PNN) and Fondo Acción should ensure the continuity of qualified personnel for contract supervision, technical and financial monitoring, and reporting through pillar closure, to guarantee timely delivery of reports to donors and strategic partners (World Bank, FCDO and Tetra Tech).
5. The World Bank and British Embassy in Bogotá, should proactively engage with IGAC and other key land sector institutions on scenario planning ahead of the elections to identify critical risks, transition arrangements and practical mitigation measures, with the aim of safeguarding the continuity of land registry and cadastral functions and protecting programme gains during and after the change of government.
Pillar 2
Address the sustainability challenge by embedding Pillar 2 interventions within permanent institutional systems
1. UNODC to establish clear institutional transition plans (adoption routes) for key products and capacities, recognising the current reliance on external mentors and training. These plans should be jointly defined with partner institutions from the design stage, ensuring ownership by the relevant institutional areas. They should support the progressive transfer of knowledge, tools and responsibilities to internal technical teams, the institutionalisation of priority methodologies and products, and their integration into standard operating processes. Digital learning platforms, such as the TEFOS-ROCOL[32] Virtual Campus, should be embedded as part of this approach to consolidate learning and support long-term capacity retention.
  [32] These acronyms refer to the Regional Office for Colombia and the Atlantic Cone, which is the regional headquarters of the United Nations Office on Drugs and Crime (UNODC), based in Bogotá, Colombia, and responsible for coordinating activities in Colombia, Argentina, Chile, Paraguay, and Uruguay.
2. MinAmbiente to consolidate SIAC’s interoperability with the justice and security sectors, with UNODC deepening its support for MinAmbiente through a government-led sustainability and transition roadmap, as well as a post-programme cooperation plan that helps maintain and further strengthen the progress achieved under Pillar 2.
Protect and consolidate the impact delivered by Pillar 2 through sustained inter‑institutional collaboration
1. UNODC to follow-up on interinstitutional mechanisms supporting environmental crime investigations, for example the Observatory of Environmental Crimes. Pillar 2 should provide technical assistance to support the operational follow-up of interinstitutional actions or commitments, ensure the follow-up and fulfilment of commitments made in coordination spaces, and develop traceability tools to monitor progress on joint actions.
2. UNODC to proactively engage with partner institutions to improve incorporation of GEDSI activities within Pillar 2. This includes developing GEDSI tools and technical guidance specific to institutions to enable them to effectively integrate equality and inclusion principles into their core mandates and ensure sustainability of UNODC's GEDSI interventions in the final year of the programme.
Pillar 3
Place inclusive and participatory engagement at the centre of Pillar 3 implementation
NIRAS to expand participatory mechanisms to engage with community organisations like ASOJUNTAS and COGANCHAIRA to strengthen ownership, particularly in family characterisation, conservation agreements, and productive value chains. Deeper inclusion of community voices will reinforce legitimacy and sustainability, involving a wider range of local actors in decision-making. The engagement of local organisations can also serve as a political and social strategy to access the territory in a high-conflict environment. Furthermore, the use of assemblies and broader forums should be promoted to enhance legitimacy and involve a wider range of community actors in decision-making.

Secure long‑term sustainability through strong alignment and buy‑in from local and national
NIRAS to ensure that the programme technically aligns with the priorities of the governments of Cartagena del Chairá and Caquetá, as well as the Directorate of Forests from MinAmbiente, to secure institutional buy-in in the long run and support sustainability after project closure. Priority should be given to early and continuous coordination with key institutional partners, without compromising the overall timing of the implementation and delivery of Pillar 3. Identifying key policy areas at multiple levels of government, as well as building potential private sector partnerships and alliances, would contribute support the strategic alignment of the Pillar.
Deliver Pillar 3 through robust adaptive management and sound programme oversight
1. NIRAS should ensure scalability of the intervention within the timeframe and budget approved, while maintaining adaptability in overall project management and implementation. To do so, NIRAS needs to, firstly, build on previous efforts of other programs such as UKPACT, as well as other advances in the Cuemaní Nucleus such as activities implemented by the SINCHI Institute, and identify, on the onset, the target families for Pillar 3, providing NIRAS with enough momentum to scale implementation once it begins in 2025. Successfully executing NIRAS’s adaptive management approach as proposed in the Inception Phase should be prioritized during the Implementation Phase.
2. NIRAS to strengthen its conflict‑sensitivity approach to ensure safe and effective implementation in complex territorial contexts. This should include the recruitment of a Conflict Sensitivity Adviser, the formalisation of collaboration agreements with trusted local organisations, and the implementation of clear safety and security protocols for staff and partners. Progress should be reported during technical catch-up meetings, documented in quarterly and annual reports evidencing how conflict and security considerations have informed implementation decisions. Additional risk, conflict and security analysis should be elaborated and reported in case of extraordinary situations.
3. NIRAS and FCDO to establish regular communication channels regarding Pillar 3 financials once implementation starts. FCDO requires regular, up to date, information on the financial management of the programme i.e., budget changes, forecast updates. Finally, flexible fund expenses need to be closely tracked and accurately reported on a quarterly basis for FCDO to understand both how the financial flows of the program are being spent, as well as how they are directly contributing to technical activities and overall programmatic outcomes and impact.
4. TEFOS team at post in agreement with NIRAS to have an improved understanding as to what constitutes RDEL and CDEL expenses to ensure that NIRAS can support the Embassy in fulfilling its financial reporting and invoicing requirements to the FCDO
5. NIRAS to prioritise the development of a participatory community biodiversity monitoring system as a transformative tool to strengthen local engagement, reinforce local actors’ ownership, generate evidence for decision-making, and contribute to national biodiversity monitoring systems. This system should be complemented by monitoring tools and adaptive management instruments to capture lessons learned, promote continuous improvement, and reinforce accountability and transparency. The participatory community monitoring systems will be designed in a way that respond to scientific methodologies and at the same time can be appropriated by the community, with initial support from TEFOS Pillar 3’s biodiversity experts, and will serve as a community-based initiative to ensure forest conservation and the development of sustainable livelihoods. This recommendation should be implemented in the last quarter of 2025 and remain in place throughout the entire implementation period of Pillar 3.
MEL
1. FCDO and the MEL partner to consider revising TEFOS’s Theory of change and log frame to reflect reality of the three Pillars working at different levels (local/community, regional, national) and over different timelines to what had been anticipated at inception. This recommendation should be evaluated in the context of an expected TEFOS extension of Pillar 1 and fund availability for Pillar 3, including the preparation for the impact evaluation.
2. The MEL partner to provide concrete directions to FCDO and Delivery Partners (DPs) on how to better report and improve the Value for Money (VfM) report and the adjustment of VfM indicators with the inclusion of qualitative information for the next AR
3. FCDO recommends the MEL partner to have an updated change log of the TEFOS indicators and document discussions and agreements with DPs about any changes to the log frame well documented.
Cross-cutting
1. The WB, UNODC and NIRAS to solve technological arrangement obstacles to meet the contractual requirements of the UK’s transparency act requirement and publish information on IATI standard following FCDO’s guidance.  FCDO should ensure all parties are aligned with the expectations of the transparency act based on the contract clauses and FCDO’s requirements.
2. MinAmbiente, IGAC, and NIRAS should prioritise the piloting experience connecting Pillars 1 and 3 in Cartagena del Chairá, documenting all phases, generating lessons learned for scaling up, and defining the next steps. This should be carried out while building on synergies with Pillar 2 to integrate environmental information into the Multipurpose Cadastre and to link territorial planning with sustainable livelihoods. The TEFOS team at the British Embassy should support the monitoring of the pilots, as well as the dissemination and positioning of achievements at the highest possible levels.
3. The World Bank, UNODC, and NIRAS should maintain a mechanism for continuous dialogue through which indigenous groups and other organisations can raise their concerns, within the channels established by each respective entity. This approach should be monitored by the delivery partners to prevent delays and ensure timely reporting.
4. The TEFOS Programme team should continue to play a role in fostering collaboration between government entities to support a consistent environmental agenda across departments and entities and avoid contradictory policies and duplication of efforts.

Annex 2. Detailed analysis per outcome indicator
Pillar 1.
- Intermediate outcome 1 – Indicator 1.1 # of conservation agreements with vulnerable rural communities located in deforestation hotspots in programme municipalities showed strong performance during FY 2024/25, exceeding expectations By the end of the reporting period, the number of conservation agreements signed with vulnerable rural households in deforestation hotspots surpassed the annual milestone. These agreements were concentrated in areas of Colombia’s Natural Parks (PNN), which helped address initial concerns around fiscal implications and environmental restrictions.
- Intermediate outcome 1 – Indicator 1.2 Area within project municipalities with cadastral and property information updated through cadastral management processes (ha), led by IGAC, showed overperformance in FY 2024/25 against a milestone of 1,811,415 ha for the year, adding 6,538,398 ha, reflecting a cumulative total progress of 6,726,983 ha, equivalent to approximately three times the end of programme target.
This acceleration reflects the expansion of operations to 25 municipalities from the 3215 targeted during FY2024/2025. This significant progress includes areas within Paramillo and Puinawai National Parks and was enabled by UK funding through core cartographic and geodetic investments, including rural orthoimages and digital terrain models, urban cartography for 200 built-up areas, and 16 operational stations contributing to the establishment of the national geodetic network.
Intermediate outcome 3 – Indicator 3.1 # of municipalities with access to, and capacity to use the multipurpose cadastre data for planning and other purposes demonstrated steady progress during FY 2024/25. By the end of the reporting period, with co-financing from the GoC, National Planning Department (DNP)16 ensured that 22 of the 32 UK‑targeted municipalities had operational access to MPC data and were actively using it to inform land‑use planning, environmental management, and governance decisions. Of these, 12 municipalities are financed through the World Bank loan, and 10 through the Territorial Technical Cooperation (CTT) program funded by the Inter-American Development Bank (IDB). The municipalities involved are:
Annex Table 1.
Department	Municipality	Funding
Antioquia	El Bagre	WB
Antioquia	Segovia	WB
Antioquia	Zaragoza	WB
Antioquia	Ituango	WB
Antioquia	Peque	WB
Arauca	Tame	WB
Meta	La Macarena	WB
Meta	Puerto Concordia	WB
Meta	Uribe	WB
Meta	Vistahermosa	WB
Meta	Mapiripán	WB
Meta	Mesetas	WB
Caqueta	Puerto Rico	IDB
Caqueta	Cartagena Del Chairá	IDB
Caqueta	San Vicente Del Caguán	IDB
Caqueta	Solano	IDB
Guaviare	El Retorno	IDB
Guaviare	Calamar	IDB
Guaviare	Miraflores	IDB
Guaviare	San José Del Guaviare	IDB
Putumayo	Leguízamo	IDB
Putumayo	Puerto Guzmán	IDB

Through UK funding key cartographic inputs, territorial characterisations, and homogeneous land area analyses were purchased, which provided municipalities with actionable datasets even before parcel-level updates were finalised.
Intermediate outcome 3 – Indicator 3.2 # of environmental or local institutions conducting analysis of information of the Multipurpose Cadastre for planning and other purposes demonstrated meaningful progress during the reporting period, signalling growing institutional capacity to leverage cadastral data for evidence-based decision-making. By the end of the FY, MinAmbiente trained multiple environmental authorities and local government entities to ensure they actively use MPC information to conduct territorial diagnostics, define homogeneous land zones, and integrate legal territorial objects into planning instruments. This uptake was supported by technical assistance and structured training programs, including diploma courses and interoperability pilots that linked MPC data with environmental systems such as SIAC17.
Cadastral operations started in 25 of 35 UK targeted municipalities, interinstitutional coordination improved through pilot projects18 led by Minambiente integrating cadastral and environmental planning, and regulatory tools, such as the issuance of Decree 462/202519 that enabled operations in Indigenous territories. However, progress has been hindered by delays in key contractual processes, such as the signing of agreements with Catastro Antioquia and operators for ethnic territories which experience prolonged delays in different stages of the procurement process due to complex procurement requirements and fiduciary reviews from the implementing partners, FA and WB. Institutional transitions, including leadership changes within IGAC and adjustments in inter-agency coordination mechanisms, further slowed decision-making impacting planned implementation timelines. Regarding the timelines of the operations already on the ground, these were affected by a combination of external issues: heightened security risks in municipalities like Cartagena del Chairá and Solano limited field access impacting parcel level updating; socio-environmental conflicts emerged around land tenure and conservation incentives, requiring additional rounds of community engagement; and logistical barriers in remote areas, such as poor connectivity and limited availability of trained personnel, delayed cadastral operations and data validation. These constraints collectively narrowed the operational calendar and required adaptive planning, including the adoption of sequential updating strategies and intensified risk management protocols to safeguard progress. Notwithstanding these constraints, implementation has delivered tangible results in several municipalities, with significant progress achieved against the expansion in the number of hectares successfully addressed and validated.
Pillar 2
- Outcome 2 – Outcome Indicator 2.1. Number of new cases opened by targeted state institutions to fight deforestation. Surpassed expectations with the promotion of 18 new cases (target: 8), including four environmental sanctioning processes led by National Natural Parks of Colombia (target: 3) addressing illegal mining, road construction, and encroachment in protected areas, and 14 land recovery and property rights cases advanced by National Land Agency (target: 5), covering over 23,000 hectares and progressing to key procedural stages.
- Outcome 2 – Outcome Indicator 2.2. Number of new environmental sanctioning processes opened to carry out investigations against alleged offenders of environmental regulations (CARs) showed a significant 66% increase in SIJIN-DICAR (Criminal Investigation Division) operations, including major interventions such as the “Taladores II” case, which identified deforestation, illegal timber trafficking, corruption, and document falsification linked to organised criminal networks. These results reflect improved institutional capacity to investigate, prioritise and act against environmental crimes, supported by stronger inter-institutional coordination and the application of replicable legal and operational methodologies.
- Intermediate outcome 3 – Indicator 3.3 % of environmental, justice, and security institutions access the SIAC to consult information related to deforestation. The 2024–2025 measurement shows that 79% of entities across the environment, justice, and security sectors accessed the SIAC to consult deforestation-related information, based on survey responses from 53 institutions (42 reporting access). This represents a 6% increase compared to the previous year and a 29% improvement from the baseline (50%). The results demonstrate continued progress in consolidating SIAC as a key information hub supporting decision-making and operational actions against deforestation across sectors and levels of government.
- Intermediate outcome 3 – Indicator 3.4 Percentage of agencies in the environment, justice and security sectors that access the SIAC that perceive that its environmental data is be useful for their work in the fight against deforestation. Showed that 78.6% of entities accessing the SIAC consider the information useful for fulfilling their mission-related tasks in combating deforestation (33 out of 42 entities). While this represents a slight decrease of 1.9% compared to the previous year, the result still reflects a significant improvement of 28%from the baseline (50%), meaning the end-of-programme target (80%) is close to being achieved.
- Intermediary outcome 4 – Indicator 4.1 Number of planned initiatives completed that respond to deforestation within the framework of the National Council for Deforestation Control and Other Associated Environmental Crimes (CONALDEF). The target of implementing 2 initiatives was fully achieved. During the 2024–2025 period, Pillar 2 provided sustained technical and legal support to CONALDEF through its Technical Secretariat and coordination units, contributing to the strategic repositioning of the Council as a central actor in environmental governance. This support enabled the successful implementation of two planned initiatives: First, the operational and administrative strengthening of the Technical Secretariat resulted in the development of key planning instruments, the delivery of over 135 technical and legal inputs, the formulation of internal regulatory proposals, and the consolidation of regional and national coordination space; and second, the operationalisation of CONALDEF’s technical instances enhanced inter-institutional coordination through targeted sessions and technical meetings, supported case prioritisation, and led to the design and initial deployment of Environmental Unified Command Posts (PMUA) for real-time response to deforestation and environmental crime. Together, these advances have strengthened CONALDEF’s operational capacity, legitimacy, and role as a strategic coordination platform.
Regarding major changes in the last year and their implications for FY24/25, no substantive changes were recorded that would alter the structure of the Pillar 2 results framework or require major adjustments to targets or indicators. This stability reflects strong performance management, with consistent measurement and year-on-year comparability maintained. As a result, the programme has been able to focus its efforts on consolidating the institutional adoption of key protocols and practices, while further strengthening effective inter-institutional coordination under CONALDEF.
Pillar 3
This section focuses on progress in establishing the technical, institutional and operational foundations required to deliver Outcome Indicators 3.1 and 3.2 in subsequent reporting periods
Outcome 3. Land users (men and women) in deforestation hotspots undertake sustainable economic activities that increase incomes and reduce pressure on forests
- Output Indicator 3.1. # ha under improved (sustainable land use) management
- Output Indicator 3.2. % change in revenue/income generated by supported farmers/organisations attributed to TEFOS Pillar 3 support
Scope and geographic focus
During FY24/25, Pillar 3 progressed through the inception phase, clarifying the area of implementation to be prioritised as the Forest and Biodiversity Development Cluster (NDFyB) of Cuemaní, located in the municipality of Cartagena del Chairá, Caquetá.
Technical components of Pillar 3
Pillar 3 is structured around three complementary components. Component 1 – Value chains and bioeconomy focuses on promoting forest￼compatible economic activities by strengthening production, organisational and market capacities, supporting inclusive business models and public￼private partnerships that create economic incentives for conservation while improving rural livelihoods. Component 2 – Sustainable forest management and forestry concessions aims to strengthen the legal and long￼term productive use of natural forests by enhancing technical, organisational and operational capacities of concession holders and local actors, in line with existing regulatory frameworks. Component 3 – Conservation, productive and ecological restoration seeks to conserve priority forest areas and restore degraded land through productive and ecological restoration approaches compatible with local livelihoods, informed by territorial biophysical conditions and the characterisation of beneficiary families to support targeted and sustainable interventions.
Inception phase outputs and refinements
The Inception Report was developed in close coordination with the TEFOS Programme team and refined through multiple review iterations, resulting in several key improvements. These included a strengthened conflict sensitivity approach, consolidation of local institutional arrangements, incorporation of lessons from previous UK, USAID, GIZ and UKPACT interventions in Caquetá, and enhanced clarity of the delivery chain map, particularly regarding funding flows and implementation responsibilities. While these refinements strengthened the technical quality and contextual fit of Pillar 3.
Stakeholder engagement and partnerships
During the reporting period, NIRAS focused on building partnerships and advancing engagement with stakeholders essential for community buy￼in and technical delivery. This included coordination with national and local government entities such as MinAmbiente, SINCHI and IGAC in the framework of National Comprehensive Plan to Contain Deforestation (Plan Integral de Contención a la Deforestación – PICD)[33], as well as engagement with community￼based organisations and local actors. Building on prior interventions by development partners, NIRAS also progressed discussions with potential private￼sector partners and technical organisations to support the design and eventual delivery of productive partnerships under Pillar 3.
[33] As defined in the National Development Plan “Colombia Potencia Mundial de la Vida 2022-2006,” the Comprehensive Plan to Contain Deforestation 2023-2026 (PICD) is the comprehensive and intersectoral management framework led by MinAmbiente and in collaboration with the National Environmental System (SINA), indigenous peoples, black community councils, farmers, and international cooperation organizations. It lays the groundwork for 2026, the 44 Active Deforestation Nuclei (NAD) located in the Amazon, Nariño, Chocó, Catatumbo (Norte de Santander), San Lucas (Antioquia, Bolívar, and Santander), Sarare (Arauca), and Paramillo (Antioquia and Córdoba) will be transformed into 28 Forest and Biodiversity Development Nuclei (NDFyB).
Beneficiary identification and adaptive management
As part of implementation readiness, initial efforts focused on the identification and characterisation of beneficiary families within the Cuemaní NDFyB. NIRAS applied an adaptive management approach during this phase, adjusting activity planning in response to feedback from communities and government counterparts. This included flexibility in refining technical approaches, such as integrating community￼requested practices (e.g. sustainable cattle ranching) and supporting government actors in the development of technical guidelines for instruments such as the Forest Farmer concession. These adaptations informed the design of future interventions but did not yet translate into outcome￼level changes.
Cross Pillar coordination and pilot design
A key technical milestone during the inception phase was strengthened coordination between Pillar 3 and Pillar 1, enabling the joint design of an integrated pilot in Cuemaní[34]. This pilot focuses on linking MPC processes with sustainable livelihood and conservation interventions, including the integration and exchange of environmental information produced by SINCHI to support territorial planning and implementation. The pilot is intended to provide a practical platform for testing assumptions embedded in the programme’s Theory of Change by operationalising convergence between land formalisation and livelihood interventions at territorial level.
[34] By using community-based land parcel characterisations previously developed for restoration and conservation incentive programs, the pilot 1 provides validated land data that can be directly leveraged by IGAC to improve cadastral preparation and execution.
Implementation readiness, risks and next steps
Full implementation of Pillar 3 did not commence during FY24/25 due to delays in finalising contract amendments and confirming the final budget envelope. Programme teams anticipate that implementation will begin following formalisation of the contract amendment, subject to internal approval processes. Delays beyond this point may continue to affect the timeframe available for delivering outcome￼level results and could create risks related to underspend if implementation approaches are not adjusted once budget certainty is achieved. Greater precision regarding resource deployment, scope and delivery expectations will be possible once contractual and financial arrangements are finalised.