## Annual Review

Title: Institutional Strengthening of Policy Implementation to Reduce Educational Disparities in Kenya (INSPIRED)
Programme Value £ (full life): 4.95m		Review Date: June 2025
Programme Code : 301503	AMP Start Date: 05/07/2024	AMP End Date: 30/08/2027

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

Dev Tracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005957.odt
Dev Tracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007373.xlsx

SUMMARY AND OVERVIEW
Description of programme
Kenya has improved education access, but quality is falling behind, with deep educational disparities. 2.5m children aged 4 to 17 years (47% girls & 53% boys), and 707,000 children of the early childhood education (ECE) age (4 & 5-year-olds) are estimated to be out-of-school and majority of these are in the ASAL counties[1]. Additionally, children are not learning the basics, evidence revealed that 57% of children aged 10 years did not meet expectations in reading English text (grade 3) in 2023. This represents a learning poverty rate of 57%[2].
[1] UNESCO (2021): Global Out of School Children Initiative – Kenya Country Study - link
[2] FLANA (2023): Are all Our Children Learning? 1st FLN Assessment Kenya Report - USAWA Agenda – link

The programme aims to improve the quality of ECE and foundational learning (FL) skills for 200,000 children (100,000 directly and 100,000 indirectly) in Wajir and Mandera. It has 3 components: i) support implementation of National Education Reforms based on the Presidential Working Party on Education Reforms (PWPER) (legislative changes, policy development and strengthen capacity); ii) enhance equity through strengthening the delivery of ECE services in Wajir and Mandera (strengthen management at the school and county levels, improve teacher capabilities, and provide age and culturally appropriate teaching and learning materials); and iii) strengthen evidence generation and use in the ECE sub-sector.
The programme is implemented by a consortium led by Education Development Trust (EDT), supported by downstream partners, Aga Khan Foundation (AKF), Sightsavers, Wajir Peace and Development Agency (WPDA), Voice of Peace for All (VOPA) and Research Hub Africa Limited. The programme was co-created and is working alongside government (national and county levels).

Changes in the Operating Context:
Since the programme approval there have been several changes that have impacted the programme.

Political leadership changes at the Ministry of Education (MoE): leadership changes (CS and PS) placed the entire basic education portfolio under a new leadership team, requiring the programme to re-establish relations, rebuild trust and goodwill, and secure buy-in. This impacted the momentum for the ongoing national reforms, causing a 2-month delay in the inception phase.

Termination of the USAID-funded national literacy program: US stopped the recently approved five-year $79m Kenya Primary Literacy Programme (KPLP), and this might potentially regress decades of progress on FL. The programme aimed to improve the national early grade reading instruction in Kiswahili and English in all the public primary schools in Kenya. It was expected to complement the INSPIRED programme’s efforts in Wajir and Mandera.

GoK’s fiscal pressures: In the 2025/26 budget estimates, education received the lions share, with a total allocation of Ksh701.9b. However, 96% of this (Ksh674.3b) is allocated to recurrent expenditure, mainly covering teacher salaries and student capitation grants. Only 4% (Ksh27.6b) is allocated to development expenditure for school infrastructure, teacher training and provision of teaching and learning materials, including textbooks[3]. Additionally, the implementation of the national reforms requires a budget of Ksh972.8m but only Ksh691.3m is allocated, representing a 29% budget deficit[4]. These fiscal pressures may have implications for the programme.
[3] Parliament (2025): - Proposed National Budget Estimates for 2025/26 - Education Sector Spending Plan – link
[4] GoK (2024): Medium Term Expenditure Framework [2025/26 - 2027/28] – Education Sector Report – link

UK’s ODA Budget Cuts: In February 2025, the UK announced the reduction of aid spending to 0.3% of Gross National Income by 2027. This will have implications for the INSPIRED programme. We are discussing restructuring the programme to fast-track delivery and ensure a responsive exit.

Summary supporting narrative for the overall score in this review
The programme’s performance for this period (first AR) has been scored as an A. The activities have only been delivered for five months (due to inception delays). The programme is on track to strengthen MoE’s capacity through providing high-quality Technical Assistance (TA). It played a central role in supporting the development of the draft National Foundational Learning Policy Guidelines (2025), supported the inter-ministerial County Early Childhood Education Committees (CECECs) establishment (Wajir and Mandera), and the development and/or review of the draft policies and legislative frameworks (bills) linked to FL reforms including: i) Basic Education 2024, (ii) Teachers Service Commission (Amendment) 2024, (iii) Kenya National Examination Council (Amendment) 2024, (iv) Kenya Institute of Curriculum Development (Amendment) 2024, and (v) National Education Policy Framework 2024. Upon enactment and effective implementation, these reforms will set the stage for sustained improvements.
Through this TA, the programme provided the technical capacity that was missing, the best available evidence and global best practice, and supported government to establish a strong and structured engagement with stakeholders to secure buy-in and strengthen accountability. TA is most effective and influential when teams work alongside counterparts in government, to address the technical and the evidence-based knowledge gaps, ensuring all outputs are developed in collaboration with government[5].
[5] Annual Review Report (2022): Education Beyond Aid – UK-funded Ghana education programme - link

Other achievements include the procurement and the dissemination of ECE teaching and learning materials (books in the first language – Somali & Borana) to 571 schools in Wajir and Mandera; ECE teacher professional development training, including evidence-based teacher training, and continuous school-based teacher coaching and mentoring. A total of 1,281 teachers, 639 school leaders and 84 sub-county officials were trained and coached. These interventions are expected to enhance the teacher’s professional capability, which in turn will improve the school readiness skills of the targeted children. The evaluation of the USAID-funded programme demonstrated that, teacher training alone is not sufficient to significantly improve literacy outcomes. Other factors such as the provision of quality materials, continuous teacher coaching and mentoring support, and a conducive learning environment are also key for success[6].
[6] USAID (2020): TUSOME External Evaluation Study – Endline Evaluation Report - link
Feedback from an ECE teacher at the Catholic Integrated ECE centre in Wajir / “I thank the INSPIRED programme for the teacher training and coaching provided to me and my colleagues. I have not received any formal in-service training on Competency Based Education (CBE) in the last 4 years. The training taught me new skills and new pedagogical approaches. I learnt to develop teaching and learning materials using the locally available resources. The training has improved my lesson planning and classroom management skills. Currently, I’m developing most of my classroom teaching and learning materials using the locally available resources.”

This feedback corroborates the wider views recorded from teachers and head teachers in Wajir, the challenge highlights a disconnect between the pre-service training of ECE teachers and the required in-service refresher. The programme will build capacity at the county-level (Wajir and Mandera) to enhance consistency and improve the quality of the county in-service teacher professional development.
Major lessons and recommendations for the year ahead
Key Lessons:
Influencing takes time and requires technical assistance: building trust and consensus among key stakeholders to secure buy-in and support takes time. Policy and co-creation workshops are an integral part of this process.

Leveraging wider partnerships and collaboration can strengthen collective efforts and increase resources. In the current ODA dynamics, more partnerships should be harnessed. As such, the programme’s partnership with TIKKA (Turkey Development Agency) has improved the school infrastructure in Wajir, complementing the programme’s efforts to improve learning outcomes. Whilst this partnership is in the early stages, it has been flagged as “a model for trilateral collaboration that ensures that others are invested and influenced to work together towards global development goals in the framework of modernised partnerships”.

Political influence is critical to achieve sustainable reforms. Progress in the implementation of the national education reforms often stalls at the political level, reflecting the need for more understanding of the key actors, the power relations, the available resources, priorities and the key interests underpinning the delivery of the education sector reforms in Kenya. This was visible during the recent senior government leadership transition.

UK’s role in the education sector is visible and impactful. The UK role in the sector has been lauded by GoK (national and county), downstream partners, and beneficiaries. The UK has improved discussions and engagement on sector reforms and the need to improve efficiency, data and prioritisation (critical due fiscal pressures), for example, through the donor coordination mechanism. The UK should continue to play this vital role.

Recommendations
	Recommendation	Description	Responsible	Timelines
1	Lobby TIKKA to expand their school infrastructure support to more schools in Wajir under the UK-TIKKA partnership.	TIKKA agreed to provide additional school infrastructure support in Wajir, through a phased approach over the lifespan of the programme. However, in view of the programme restructuring, there is need to follow up with TIKKA to ensure they align their support to any changes made to INSPIRED.	INSPIRED programme team.	December 2025
2	Encourage MoE to prioritise and adhere to the agreed / Harmonized Donor Principles.	There is need to encourage MoE to prioritise and adhere to the agreed harmonised donor principles. This will enhance accountability and transparency of public finance and promote effective and efficient use of education sector resources, including the development partner assistance.	EDT and INSPIRED programme team	Ongoing
3	Restructure the programme to ensure a responsible exit.	With the recent ODA reduction to 0.3% of GNI and considering the need to avoid a cliff-edge situation and maximise impact, the programme will need to restructure to bring forward its end date by six months to ensure a responsible exit and maintain the critical relationships with GoK.	INSPIRED programme team	July 2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programmes theory of change, including any changes to outcome and impact indicators from the original business case.

The ToC and the assumptions continue to hold true. The ToC remains valid.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
At the outcome level, the programme aims to strengthen the foundational learning policy environment at the national level and increase access to quality early childhood education services in Wajir and Mandera, with a reduction in gender disparities. In view of the progress made against outputs, and the contextual changes, the programme is on track to increase access to quality ECE services in Wajir and Mandera. Similarly, the programme is on track to strengthen the FL policy environment. However, although notable progress has been made at the policy level, the ultimate test will be the extent to which MoE will effectively implement the policies at the school-level to benefit Kenya’s children.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme is still in the early stages of implementation hence most achievements are processes and activities setting a firm foundation for success. The programme successfully completed the inception phase, which included mobilisation of teams and co-creation of the programme with key GoK officials. The endorsement of the final programme deliverables by the Principal Secretary for Basic Education confirmed that the programme ToC is valid, and the overall ambition is well-aligned with GoK’s strategic priorities. Based on these, we recommend the continuation of the programme.

Output Title	Enhanced capacity within GoK to deliver improved and equitable ECE and foundational learning policy reforms.
Output number:		1		Output Score:		A
Impact weighting (%):		40%		Weighting revised since last AR?		No

Indicator(s)			Milestones / for this review		Progress
Process indicator: 1.1 Number of GoK officials trained /participating in coaching sessions to strengthen the implementation of ECE & foundational learning policy reforms at the national and county government levels.			66		Exceeded expectations – a total of 72 government officials (national and county level) were trained and coached on using evidence and global best practice to develop and review policies and legislative frameworks linked to FL reforms.
1.2 Number of instances that evidence capacity improvement in GoK systems, processes, and tools for managing and monitoring the delivery of ECE and foundational learning policy priorities as a result of INSPIRED programme intervention.			GoK systems review survey undertaken and completed.		Achieved – the assessment of the gaps in the MoE’s system for managing and monitoring the delivery of FL reforms was completed.
1.3 Number of learners enrolled in ECE centres directly benefiting from INSPIRED interventions in Wajir and Mandera.			62,000		Exceeded expectations – a total of 63,777 ECE children are currently benefiting from the INSPIRED programme interventions in Wajir and Mandera counties. Please see comments in the details below.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme has started to deliver the foundational aspects to influence policy reforms. For example, several Bills and policies have been drafted, reviewed and some submitted for approval. As the BC noted, these reforms if implemented, will be critical to achieve changes and increase government capacity. Interviews with MoE officials suggested that the TA is demand-based and locally led, with a strong emphasis on capacity strengthening rather than capacity substitution, and its delivery approach is flexible to accommodate the shifting political and operational realities in the MoE. Evidence from the evaluation of World Bank TA programmes suggests that the key factors associated with greater TA effectiveness include the level of government’s receptivity, buy-in, absorptive capacity and continued follow-up[7].
[7] Mergesa (2019): The Effectiveness of Technical Assistance in Middle Income Countries – link
The assessment of gaps in the MoE’s systems for managing and monitoring the implementation of the FL policy priorities identified critical issues which the programme has started to address. In terms of next steps, the programme will support the reactivation of the Ministerial Education Reforms Implementation and Advisory Committee (MERIAC) which will be responsible for providing oversight and leadership in the implementation of the reforms – moving the reform’s implementation leadership, oversight and accountability to senior government levels.
Lessons learned this year:
Consistent political engagement, beyond the high-level commitment and the training of officials, is key to build and maintain progress in the education reforms. INSPIRED succeeded in securing high-level political commitment to education reforms, especially those that relate to ECE. However, the lack of government resources and delays in approving the Bills underscore the importance of continued engagement (supported by FCDO) with key actors within MoE to sustain progress, implementation and ensure that actions lead to changes. This is an area where consistent political economy analysis is required to understand the political challenges around education reform, what motivates key actors, and opportunities that might be available.

Fiscal pressures at county level are constraining ECE progress and accountability. While there is high-level of ambition for ECE, the reality on the ground is different as observed during the field visit in Wajir. Most schools had low ECE enrolment, inadequate ECE teachers, infrastructure, and erratic provision of school meals. The head teachers attributed the low enrolment to competition from the Duksi and Madrassa, the absence or the inconsistent provision of school meals, and the shortage of teaching staff. These challenges have implications for the programme thus it’s important to monitor them regularly.

Output Title	Stronger capacity for teachers, school leaders, and county ECE departments to effectively deliver ECE services in Wajir and Mandera Counties.
Output number:		2	Output Score:			A
Impact weighting (%):		45%	Weighting revised since last AR?			No

Indicator(s)				Milestones for this review	Progress
2.1 Proportion of ECE teachers recording improved pedagogical skills for teaching pre-literacy, pre-numeracy and socio-emotional skills in the targeted ECE schools across Wajir and Mandera counties.				Not measured in Y1.	N/A
2.2 Proportion of ECE teachers reporting improved teacher professional development support and improved school leadership instructional support in the targeted ECE schools across Wajir and Mandera counties.				Not measured in Y1.	N/A
2.3 Number of ECE teachers, school leaders and subcounty ECE officers trained or coached (with support of INSPIRED programme) to improve their professional & technical capabilities.				1,008 / [372 ECE teachers, 570 school leaders, 66 sub-county officials]	Exceeded expectations - a total of 2,004 officials were trained were trained and coached in Wajir and Mandera. / Details: 1,281 teachers (850 male, 431 female) including 51 teachers with disability (39 male, & 12 female), and 639 ECE school leaders (48 female, 591 male), and 84 ECE sub-county officials (64 male and 20 female), including 4 sub-county officials with disability (3 male, 1 female) were trained and coached during this period.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output exceeded expectations. A total of 2,004 officials including 1,281 ECE teachers, 639 ECE school leaders, and 84 ECE sub-county officials were trained and coached in Wajir and Mandera. The programme also supported the procurement and the dissemination of the first batch of ECE teaching and learning materials, workbooks and reading books (provided in the first language – Somali & Borana) to a total of 571 schools across Wajir and Mandera. It has further provided contextualised, continuous school-based teacher coaching and mentoring support, to reinforce the pedagogical improvements in the real ECE classroom setting.

The programme’s three-pronged approach (teacher training, ongoing school-based teacher coaching, and the provision of teaching and learning materials) is laying a firm foundation for improving the school readiness skills of the targeted children. Evidence from the evaluation of the TAYARI early childhood education programme found that - combining teacher training, and ongoing school-based teacher coaching, and the provision of age-appropriate teaching and learning materials is an effective and holistic approach for improving the school readiness skills of ECE learners[8]. Furthermore, the using first language (Somali & Borana) in instruction is enhancing parental engagement. Feedback from the interviewed parents revealed that parents are more likely to engage and support their children when mother tongue is used for instruction.
[8] APHRC (2018): Impact Evaluation of the TAYARI School Readiness Programme in Kenya. See report here

Further discussions with teachers suggested that the provision of continuous in-service teacher professional development support has been erratic and inconsistent in both Wajir and Mandera. This is due to the limited ECE resources, infrastructural limitations (including poor road networks and limited access to technology), environmental factors (including harsh weather conditions), and wider safety and security risks[9]. Additionally, as observed during the field visit, there are fewer female ECE teachers in Wajir and Mandera. Insights from discussions with teachers and religious leaders revealed that this challenge is underpinned by cultural norms that discourage female mobility and safety concerns, coupled with retrogressive traditional gender roles and limited access to quality education among the marginalised girls. Furthermore, female teachers’ presence in the classroom is generally associated with expanded educational opportunities and attainment for girls[10]. The programme should monitor the impact of fewer female teachers on girl’s educational outcomes.
[9] UNESCO (2024) International Institute for Capacity Building in Africa: Teacher Professional Development in Emergency Contexts - A Small Sample Exploratory Analysis for Five East African Countries – link
[10] EDT (2024): The necessity of female teachers for girls’ education in crisis settings – link

Lessons learned this year:
Strong engagement with community and religious leaders is key for effective integration of Duksi and formal ECE in Wajir and Mandera. Feedback from the religious leaders in Wajir reveals a guarded sense of support for ECE integration, but under very specific conditions. Therefore, the programme has an opportunity to leverage religion not just as a key demographic variable, but also as a strategic entry point for advancing ECE in a manner that respects, reflects, and reinforces the community's spiritual priorities and beliefs.
Feedback from a religious leader in Wajir / “The ECE integration approach should prioritise the use of a hybrid timetable, where Duksi lessons happen early in the morning and the formal ECE lessons happen thereafter. Let us ensure this integration does not remove or water down the Quranic teachings.”

Co-created programmes are essential for success. Engagement of strategic and decision-making stakeholders during the inception phase delivered results. For example, in Wajir county, officials contributed to ensure the programme provided ECE teaching and learning materials in line with the county needs. However, it’s important to maintain an honest and open discussion to manage expectations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following a request from Wajir County official to increase the number of ECE teaching and learning materials provided to public ECE schools, the programme took the decision to reduce the number of schools supported by 150 schools (721 to 571 schools). This resulted in a cost-saving of £10,000, which was reinvested in the procurement and dissemination of additional materials.

Output Title	Stronger evidence in the national & the ASAL county's education policy dialogue on "what works" in the delivery of ECE interventions in resource limited settings.
Output number:		3	Output Score:			A
Impact weighting (%):		15%	Weighting revised since last AR?			No

Indicator(s)				Milestone(s) for this review	Progress
3.1 Progress on the production of evidence products (supported by the INSPIRED programme) to inform wider education policy dialogue at the national & the county government level.				Evidence mapping undertaken to identify and agree the policy-relevant evidence gaps.	Achieved - Evidence mapping undertaken and included in the inception report of the recent implementation research study.
3.2 Number of instances where the evidence, research and data generated through the INSPIRED programme is utilized/quoted in the development of key national & county government foundational learning policies or strategies.				Not measured in Y1.	N/A
3.3 Number of GoK officials trained/ participating in mentorship sessions on collection, analysis & the effective uptake of ECE evidence at the national & county government levels in Kenya.				Not measured in Y1.	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.
Research Hub Africa (RHA) was competitively selected as the independent external evaluator. During this period, they reviewed and identified the policy evidence gaps linked to the delivery of ECE services particularly in the low resource settings. The implementation of the research study will contribute to the evidence base on “what works” and “how it works” in the delivery of high quality ECE services. This will inform policy decisions in the marginalized and underserved regions.

While globally[11][12][13], there is a strong body of evidence on the effectiveness of ECE interventions in improving school readiness skills and long-term learning trajectories in urban contexts, there is less evidence on rural and resource-constrained areas like the ASALs. Therefore, the upcoming Implementation Research (IR) study will seek to bridge this evidence gap.
[11] World Bank. (2022). Quality Early Learning: Nurturing children’s potential (Early Learning Partnership Brief). Retrieved from here.
[12] UNICEF. (2020). UNICEF Annual Report 2020. UNICEF. Retrieved from here
[13] RTI International. (2019). Longitudinal midterm report for the Tayari Early Childhood Development and Education Programme. Retrieved from here

D: VALUE FOR MONEY
Key cost drivers and performance
The key cost drivers for the programme include the cost of teacher training, continuous teacher coaching and mentorship, and capacity building initiatives targeting school leaders and various county and national government officials. 30% of spent budget was invested to support the key cost drivers.

VfM performance compared to the original VfM proposition in the business case
VfM / Dimension	Approach and strategies to achieving VfM	Indicators	Achievements
Economy	Economy focuses on minimising input costs while maintaining quality. Strategies include optimising key cost drivers such as staffing and technical assistance (TA).	Programme management & procurement costs as a percentage of total costs. / Component-wise cost allocation & budget execution rate.	Achieved significant cost savings by repurposing funds originally allocated for the procurement of a vehicle (GBP 39,000) by using a vehicle transferred from other programme resulting in operational efficiency while reducing capital expenditure. / Recruitment of full-time ECE and Communications & Advocacy Officers at lower remuneration rate replaced the need for costly and less reliable technical assistance thereby optimising staffing costs. / Programme management and procurement costs remained within the acceptable threshold, demonstrating efficient use of resources aligned to VfM principles.
Efficiency	Examining the conversion of inputs into outputs, ensuring that resources are allocated effectively to achieve the intended reach.	Cost per ECE teacher trained/mentored / Cost per GoK staff receiving capacity support & Cost per event/policy dialogue	The cost per teacher trained is Ksh154.1 (this includes cascade trainings: training of coaches, ECE teachers training and HT sensitization) – there was no baseline. / The programme successfully secured $100,000 from TIKKA to support the infrastructure of six schools during the programme lifespan in wajir. Two schools, a total of 4 classrooms and 6 toilets, have been completed. In addition, TIKKA will provide toys and play materials. Additional schools are planned for the next year. / EDT invested $11,880 to provide internet connectivity support in 6 schools in Wajir & 5 in Mandera as part of their corporate social responsibility. This investment will complement the programme enhancing efficiency at the school-level.
Effectiveness	Focus on component outcomes and consider findings from MERL evaluations of results chain hypotheses. / E.g. did meeting targets on outputs lead to the predicted change in component outcomes?	Cost per GoK staff who reports improved capabilities; Cost per ECE teacher with improved professional competencies; Cost per event/policy dialogue that can be linked to improved evidence uptake	Capacity improvement assessment will be conducted in December (we have only conducted the baseline capacity assessment as the trainings only started in May).
Equity	Data will be collected on sex, locality (urban/rural), disability, gender and SEN to identify equity of allocation, process, performance. Equity considerations will be made in planning activities and reported on.	ECE school readiness results disaggregated by sex and relevant marginalization factors; ECE TPD capabilities results disaggregated by sex and relevant marginalization factors & % of female ECE TPD staff trained.	A total of 1,281 teachers (850 male, 431 female) including 51 teachers with disability (39 male, & 12 female), and 639 ECE school leaders (48 female, 591 male), and 84 ECE sub-county officials (64 male and 20 female), including 4 sub-county officials with disability (3 male, 1 female) were trained and coached during this period.
Cost- Effectiveness	Cost-effectiveness evaluation will take the above factors into account to give an overall assessment of the programme’s ultimate impact on improved FL, relative to the inputs invested.		This will be conducted as part of the endline evaluation

Assessment of whether the programme continues to represent value for money
The original vfm proposition in the business case stands. The programme is delivering vfm as outlined throughout this review.

E: RISK

Overall risk rating: Moderate
The overall programme risk has not changed since the approval.  The programme’s net risk rating remains as moderate despite the new risks outlined in this review.  FCDO Kenya’s risk appetite for the programme is receptive which is within FCDO’s risk appetite. The programme team monitor risk at partner bi-weekly meetings, and changes to existing risks (or new risks) are recorded in a risk register, updated quarterly.  Additionally, risk registers are maintained for Safeguarding and Fraud risks. No risks outside of appetite were identified during this period.  Security remains a key constraint in Mandera, as a result we selected a local partner with strong local presence. FCDO staff have not been able to visit Mandera due to security risk.

All the risks identified in the due diligence assessment have a mitigation action and the team is monitoring closely.  FCDO Kenya undertook full due diligence on the lead partner, EDT, who in turn conducted due diligence assessments for all the Consortia partners Aga Khan Foundation (AKF), Sightsavers, Wajir Peace and Development Agency (WPDA), Voice of Peace for All (VOPA) and Research Hub Africa Limited.

Risks assessment (including emerging risks) and mitigation
Risk Category	Risk Appetite	Rationale and Mitigation Measures
Strategy and Context	Receptive (moderate)	The security situation in Mandera is fluid with incidents reported from time to time due to frequent attacks by terrorist groups as well as clan-based conflicts. / Implementing partner is working with the local delivery partner (CRIMETEC) which provides security intelligence and advisories to ensure to ensure day today security for seamless programme implementation though sharing security reports on a weekly basis.
Policy and Programme Delivery	Receptive (moderate)	Changing political landscape and dynamics, with expectations, demands and interests from the MoE, Council of Governors (CoG) and the two county Governments against the limited budget and competing priorities. / Implementing partner, in consultation with local leaders and stakeholders, continues to manage this through co-creation and joint prioritisation based on the available budget and programme mandate. Work plans are reviewed regularly to ensure they remain the instrument to influence and support the decision-making process.
Budget cuts- UK ODA budget cuts	Cautious (moderate)	Materialized - The reduction in ODA (to 0.3%) might impact this programme. / Programme team is now considering options to ensure the programme delivers its objective, a responsible exit while maintaining the critical relationships with GoK.
Financial and Fiduciary	Cautious (moderate)	Fraud, corruption and misuse of FCDO funds leading to loss of funds. Due diligence assessments were conducted for the lead and downstream partners and identified weaknesses were actioned; no funds were channelled directly to national or local government; rigorous financial controls, and reporting were applied. No Fraud case was reported during the year under review.
Safeguarding	Cautious (moderate)	The possibilities of Sexual Exploitation, Abuse and Harassment (SEAH) issues, given the context and the nature of the programme, safeguarding policies need to be monitored to ascertain how they are implemented on the ground. / EDT due diligence demonstrated that they have a zero-tolerance policy against actual or attempted acts of all forms of exploitation, abuse, and harassment, including SEAH, perpetrated by employees toward members of its workforce, beneficiaries, and community members. Partners staff were taken through safeguarding sessions to sensitize them on the safeguarding issues, reporting procedures, and reporting procedures. / No cases of sexual abuse, harassment and exploitation were reported during the period under review.
Foreign Exchange losses	Cautious (moderate)	Foreign Exchange losses GBP to KES exchange rates fluctuation affecting available funds for activities. / The lead implementing partner EDT has been monitoring the trends with the banks that have informed regular updates and discussions with FCDO.

Partnership principles: The programme does not provide financial aid to government directly.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners
The delivery consortium was selected through a competitive process. FCDO signed an accountable grant with EDT, the lead partner, in August 2024 to start the inception phase. Downstream partners are AKF, Sightsavers, WPDA and VOPA and Research Hub Africa Limited (joined in January 2025). FCDO’s relationship with all the partners has been positive and productive. Coordination is key when working with a wide range of partners and stakeholders, thus FCDO coordinates and ensures joint partner meetings bi-weekly.  These meetings have proved useful in getting programme updates, sharing experiences among partners and resolve issues immediately where they arise (EDT change in personnel).

Performance is monitored through a set of workplans alongside quarterly meetings that focus on progress, risks and financial management. In addition, EDT provides quarterly reports that are scrutinised and discussed. Issues are addressed immediately in the meetings, and risks escalated to SRO and DD as required.

The lead partner successfully established a strong governance structure that facilitated effective coordination and communication among all stakeholders. This structure was designed to maintain transparency and ensure that every participant was aligned with the program’s goals and timelines. Other structures were put in place to support the program's smooth operation, including the Programme Steering Group, Programme Control Group, and Programme Leadership Team. These structures help ensure that coordination between the Ministry of Education (MOE), Council of Governors (CoG), County Governments and the INSPIRED Programme is continuous and effective, allowing for swift decision-making and problem resolution.

Recommendation
Change of Senior Programme Leadership: EDT changed a senior team member immediately after the contract award temporarily disrupted implementation, though this was quickly resolved. This should have been done gradually, at the appropriate time, and with careful consideration of the wider implications to the programme.

Financial: The total budget for INSPIRED programme is £4.95m.

The following table shows funds disbursed to the programme partner to date:
Partner	Total budget (£)	Disbursed to date	Balance
Education Development Trust (EDT)	4,399,956	1,227,660	3,171,936
Education Adviser	450,000	0	450,000
Inception Phase	100,000[14]	100.000	0
[14] These funds were used as part of the design funds to support evidence gathering.

EDT met FCDO’s quarterly narrative and financial reporting requirements; however, they did not meet FCDO forecasting requirements. To support EDT, FCDO programme team developed and shared a narrative and financial reporting template and introduced a monthly tracking tool and meetings to help track monthly spend – this should reduce the variations.

Recommendation:  EDT will need to improve on its forecasting to ensure that it is within a variance of +/- (10%).  Going forward, FCDO to continue to monitor finances closely and consider further capacity building on financial performance.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
This period focused on developing key monitoring documents and data collection tools to support routine program monitoring. A comprehensive monitoring and evaluation (MEL) framework and updated log frame were developed. FCDO programme team monitors the programme through bi-weekly management meetings with all partners. Through these meetings the programme has adjusted to respond to needs, i.e. to decrease the number of schools in response to county request. Two field visits were undertaken, one jointly with TIKKA. Some observations included, selecting schools for TIKKA support, and discussions with government officials and teachers about the challenges observed: lack of classrooms (some classes were delivered under the trees), lack of water, challenges with madras timings, lack of material, etc.

Evidence
A comprehensive baseline survey was undertaken to establish the baseline across the outcomes. It employed a mixed methods approach, qualitative and quantitative data using both primary and secondary approaches that were participatory in nature. A total of 157 schools formed the baseline sample, comprising 120 intervention schools (60 from each county of Wajir and Mandera spread equally across rural and urban schools) and 37 comparison schools (19 in urban and 18 in rural set-ups). Garissa county was the source of the comparison group. In total 1,884 households (1,440 intervention and 444 comparison) were reached. Key findings include:

Enrolment Trends: intervention schools had higher mean enrolments across all grades (PP1, PP2, and Grade 1), particularly in urban ECE centres. Rural schools, particularly those in ASALs faced challenges due to smaller populations and limited access, resulting in lower enrolment. A notable gender disparity was observed, with boys consistently outnumbering girls, especially in rural areas, the gap was narrower in urban areas. There is a gender balance between boys and girls that will be tracked.

Teacher Support for Foundational Learning: several insights into teacher support as a key factor in foundational learning. Challenges related to teacher presence, training, classroom facilities, lesson planning, and literacy environments were identified. The absence of teachers in intervention classrooms was minimal (0.7%), though even small absences could disrupt consistency, particularly in rural areas where teachers often juggle multiple roles. Although most teachers had basic training, refresher training rates were low in ASALs.

Learning Outcomes: notable differences in ECE outcomes across various domains, including numeracy, problem-solving, communication, literacy, and health & nutrition. Urban areas consistently outperformed rural areas, particularly in emergent numeracy and literacy. This trend is linked to disparities in resource allocation, access to qualified teachers, and infrastructure quality. Children in urban areas and those with access to school readiness activities at home performed better. Gaps were also noted between boys and girls. Communities broadly valued education, but perceptions of ECE remained narrow, with many viewing it primarily as religious or moral training - Madrassa attendance was often prioritised over formal ECE.

Barriers to Accessing Early Childhood Education: Several identified: socioeconomic conditions, infrastructure deficits, and cultural factors. High poverty levels, food insecurity, and inadequate access to basic needs such as clean water and healthcare were reported by many households, particularly in rural areas. Over half of rural intervention households reported not having any income for over 10 days each month, highlighting the deep economic insecurity. The distance to ECE centres also posed a barrier, with 25.1% of children in rural areas walking more than 30 minutes to reach an ECE centre – contributing to absenteeism and low enrolment. Safety concerns exacerbated the problem. Economic barriers, such as the inability to afford school fees, were also prominent, with 41.0% of intervention households reporting they could not afford ECE fees, compared to 28.8% in comparison areas.

Overall Implications for the Programme - the findings reveal that while the foundational commitment to ECE exists at both household and institutional levels, systemic inequities, capacity gaps, and contextual barriers constrain progress. These insights offer FCDO, EDT and county governments an evidence-based starting point for targeted interventions under component 2, to build capacity and sustainably improve teaching quality and enhance inclusive learning environments.

Learning
The programme plans to support learning through tailored knowledge products, including:(i) technical evidence papers for policy-level audiences, (ii) policy briefs and policy digests for wider policy-level audiences, (iii) community & school feedback reports to share learning with key school leaders and key community stakeholders, and (iv) webinars and roundtables for real-time dissemination of evidence and peer exchange. The external evaluator will work with all the relevant partners to develop and disseminate most of these knowledge products during the programme’s lifespan.

Date of last narrative financial report	March 2025	Date of last audited annual statement	N/A (partner financial year runs from 1 Sept 2024 - 31 Aug 2025)