Business Case – May 2025

Summary Sheet

Country Plan Summary / This programme supports Kenya Country Plan (2023 – 2025) delivery and achievements against campaign goal (6) on Open Societies, Democracy and Human Rights, where the UK aims to support the evolution of Effective Institutions and to promote Transparency and Accountability to tackle corruption and reduce illicit finance.
Title: Kenya Institutional Strengthening Programme (KISP)
Programme summary / The UK will deliver up to £14m over five years to support Kenyan institutions to erode incentives and opportunities for corruption and improve trust in Kenya’s political system. This will be achieved through strengthening government institutions and systems of accountability, enhancing skills and resources that will enable political parties and politicians to focus on policies that improve the daily life of Kenyan citizens and working with citizens to hold leaders accountable.
What is the rationale for UK International Development spending? / Kenya suffers from deeply rooted, systemic corruption that results in loss of public funds, increasing debt, poor service delivery and reducing Foreign Direct Investment (FDI). / An adaptive approach and high-risk tolerance of KISP will allow the programme to move at pace, proactively respond to contextual changes and opportunities, and develop interventions as illicit finance and political corruption risks alter. The UK is a trusted development partner to Kenya and has a track record of providing technical assistance that strengthens institutions to improve accountability, electoral integrity and counter illicit financial flows. / Kenya is an influential lower middle-income country, central to the delivery of UK geopolitical, trade, and economic growth interests - its transparency, openness, and stability matters. It is an anchor of stability and of increasing prosperity and innovation in an unstable region that is a high priority to the UK.
Programme Value: up to GBP 14M		Country: Kenya
Country Office confirmation of review processes		Reviewed and cleared by: Strategy, Accountability and Results Team; Programme Board; Country Board and Development Director
Contact name		DGP Team, BHC Nairobi
Threshold for final approval of Business Case: Head of Mission
Date of Approval of Concept Note:	15/04/2024	Name and role of Approver / Deputy Foreign Secretary, FCDO
Date of Approval of Business Case:	15/05/2025	Name and role of Approver / Development Director, BHC Nairobi
Programme Code: 301505	AMP Start Date: 23 / 05 / 2025	AMP End Date: 22 May 2030
Overall programme risk rating:	Major

## Strategic Case

WHY UK INTERVENTION IS NEEDED
Kenya has the largest, and most diversified modern economy in East Africa. Its human capacity, entrepreneurial energy and available capital give it huge potential to create jobs and reduce poverty and inequality among Kenyans. However, this potential is not being met. Kenya suffers from endemic corruption and high poverty levels.  Kenya also has a history of political violence and impunity stemming from aggressive political competition, with the intensity increasing dramatically during election periods.
[note] Although economic growth remains competitive in the region.
[note] In 2024, Kenya’s CPI score marginally increased to 32 out of 100 (its 2022 score), from 31 in 2023, ranking 121 out of 180 countries. This score was still below the global (43) and Sub-Saharan (33) averages. A score below 50 signals serious public sector corruption.
[note] Despite a GDP per capita is US$2099 (Kenya | Data (worldbank.org)), 53% of the population lives in multi-dimensional poverty (deprived of services, rights and basic needs), while 36% is monetary poor (Comprehensive Poverty Report - Kenya National Bureau of Statistics (knbs.or.ke), 2020)

Kenya’s economic growth is strong, but the high debt to GDP ratio crowds out development expenditure: growth averages around 5% of GDP per annum, inflation is now below 5%, and the Shilling stabilised against the dollar in 2024. However, Kenya’s debt-to-GDP ratio is almost 66%, compared to a sustainability threshold of 55% enshrined in law. Debt servicing continues to crowd out space for development expenditure, taking up over two-thirds of revenue in 2024 year and over 50% until at least 2028.Fiscal consolidation is required to set debt on a sustainable path, a key condition of Kenya’s IMF programme. There remains opportunity to set debt on a more sustainable trajectory, but this requires difficult political decisions to be taken to reduce the fiscal deficit and to increase domestic revenue mobilisation. If these are not taken quickly there is a likelihood that Kenya’s debt sustainability will continue to deteriorate.
[note] The IMF-supported program aims to help Kenya reduce its debt vulnerabilities and strengthen its ability to align spending with revenues. It also supports the government's broader reform and governance agenda, addressing weaknesses in state-owned enterprises, strengthening anti-corruption efforts, bolstering the Anti-Money Laundering and Combating the Financing of Terrorism (AML/CFT) framework, improving central bank operations, and advancing policies for sustained and inclusive growth.

The relationship between development and corruption is complex and multifaceted: corruption can hinder development progress, for example through instability or by preventing reforms needed to improve the competitiveness and productivity required to produce higher-value goods; or development can provide the resources, technical capacity, and political will necessary to combat corruption effectively. Kenya must address corruption to avoid the middle-income trap, where failure to progress economically is often tied to persistent corruption and poor governance.
[note] Vandenberg, Poot, and Miyamoto: “Economies get caught in the [middle-income] trap when they are no longer competitive in producing low-value goods, and yet do not have the capacity to produce higher value ones. Our analysis suggests that to develop productive capabilities requires a number of supporting factors including good governance, investment in R&D, high savings and investment levels, an educated workforce, reliable infrastructure, and moderate inequality”

Kenya’s grey-listing in February 2024 by Financial Action Task Force (FATF) underscores the urgent need for the Kenyan Government to strengthen its Anti-Money Laundering, Countering the Financing of Terrorism, and Combating Proliferation Financing frameworks (AML/CFT/CPF). These measures are critical to changing its financial infrastructure to reduce the risk of Kenya being a haven for dirty money and an exporter of instability. Enacting these reforms will demonstrate a serious commitment to addressing illicit finance activities that threaten national stability and integrity.

1. Increase in Illicit Finance (IF): Kenya’s position as East Africa’s regional financial, legal and transport centre; together with significant cross border trade, use of cash and community links across porous borders mean that Kenya has become a “destination, origin or transit jurisdiction for money laundering and illicit finance purposes, for countries in the region”. Gold, minerals, precious metals and other resources are moved on behalf of corrupt actors, organised crime and terrorist groups in the wider region.
  [note] Funds or assets which have been illegally acquired, illegally transferred, illegally obfuscated, and/or illegally used
  [note] Burundi, DRC, Ethiopia, Somalia, South Sudan, Tanzania and Uganda
2. Corruption and illicit finance are symbiotic with politics: Kenya’s elections are one of the most expensive globally and the economy can no longer afford the cost of politics. Major corruption scandals have occurred in the run-up to closely fought election campaigns. It exacerbates winner-takes-all politics as office holders use their positions to support co-ethnic communities or pay back allies, it deepens both regional and vertical inequality between the wealthy and the poor and fosters ethnic distrust which works against investment in public services. This political culture gives tribal elites political and economic power that has resulted in exclusion, impunity, and limited incentives to address poverty, and other forms of inequalities.
  [note] The cost of politics in Kenya the average cost of managing elections per voter in Kenya is estimated at $ 12.5 which surpasses both Africa’s average of $4.50 and the global average of $2.10. Devolution of 47 sub-national governments has also contributed to unsustainable wage bill and administrative costs.

OPPORTUNITIES FOR TACKLING CORRUPTION & IMPROVING ELECTIONS INTEGRITY IN KENYA

As a growing middle-income country, Kenya is entering a phase where progress on corruption may be becoming more feasible. The table below illustrates that economic development is positively associated with lower perceptions of corruption. This relationship isn’t automatic – development doesn’t automatically eliminate corruption – but it is not possible to sustain chronic corruption and achieve high-income per capita GDP.
[note] This a World Bank classification that refers to countries with a GNI per capita of $1036 and $12535
Table 1.

Tackling corruption is a high priority for Kenyan citizens, Kenyan businesses and investors. In the 2016, 2019 and 2021 Afrobarometer surveys, corruption was either the first or second most important priority for Kenya citizens. Kenyans also want greater democratisation. Afrobarometer’s 2023 survey found that 78% of Kenyans support regular, open, and honest elections as the best way to choose their leaders. Thus, few things matter more to Kenyans than tackling corruption or improving democracy. Tackling corruption is crucial, not only as a moral imperative but necessary to create the conditions - e.g. a quality education, good infrastructure, moderated inequality – for sustained economic growth.

Two new dynamics are now present in the 2022-2027 electoral period: 1) a small shift in citizen’s voting patterns towards issue-based voting; and 2) citizen-led mobilisation to demand accountability from political leaders. The democratic gains made from 2022 elections are nascent. There are opportunities to protect these gains and evolve the political system towards issue-based politics backed by resilient electoral institutions.

The August 2022 elections were marked by a lack of immediate violence and a change in voting behaviour, representing a small window of opportunity to further towards to issue-based politics. The slim win for William Samoei Ruto – of just 220,000 votes – was driven in part by a mobilisation of voters on class/economic lines rather than ethnic lines. Citizens’ voting patterns shifted from ‘particularist’ (how is my group/network going to benefit?) to ‘universalist’ (how are we all going to benefit/it’s unfair just for one group to benefit). Significantly, there is a tax related connection: when tax becomes more broad-based, the accountability relationship changes – a wider cross-section of citizens paying tax expect more from government; so government is incentivised to satisfy a broader (not narrow) constituency. When the opposition failed to accept the presidential result, there were several weeks of anti-government protests in early 2023. To quell the protests the Government and opposition agreed to hold a bipartisan dialogue (National Dialogue Committee (NADCO)) that resulted in recommendations to reform the electoral legal and policy framework, and a rapprochement between the political camps which led to Government support for opposition leader Raila Odinga’s (unsuccessful) African Union Chairperson campaign.
[note] Both domestic and international observation missions highlighted significant improvements in the electoral process that resulted in better administered elections, and despite concerns, the elections were largely peaceful.

The new wave of protests by Kenyan youth in July 2024 continued this focus on issue-based politics and offers an opportunity for change. In June/July 2024, Kenyan youth (GenZ) took to the streets across the country to demand good governance and accountability from the government. The protests were unusual in the Kenyan context due to their lack of political leadership. As protests moved from the national to local level, the offices and homes of local political leaders were targeted and youth took direct coordinated action against individual leaders. The protests, likely infiltrated by paid thugs, became violent and were met with a violent police response – in which over 50 people lost their lives. Their grievances which were initially triggered by the passage in parliament of the Finance (Amendment) Bill 2024 seeking to raise taxes. In response to citizen demands for accountability the President dissolved his Cabinet and formed an inclusive government in which four members of the Orange Democratic Movement (ODM) opposition party took Cabinet Secretary positions.

Overall, the “Gen Z” grievances share a common theme: the cumulative failure of ruling elites and political institutions to meet expectations of accountability, while expecting citizens to pay increased taxes without seeing improved service delivery. The youth are frustrated with glaring systemic corruption and economic inequality. This emerging movement wants to see change in systems that feel outdated, broken, and non-responsive to citizen needs. This movement for change is likely to face challenge because it is outside of the current political elite formation but is likely to sustain in the medium term given Kenya’s youth bulge. Since July 2024 the movement has been less vocal, the extent to which it becomes a force in the 2027 elections is currently difficult to predict. Nonetheless, the conditions present new opportunities for KISP to facilitate reforms to tackle political corruption in Kenya. This implies that there is the capacity, opportunity and, possibly, motivation, to change behaviours within Kenyan public institutions and political leadership to address corruption and strengthen electoral integrity.
[note] Youth aged 15-34 estimated at 35% (19.8M) of total population (projected at 57M by 2025) according to National Council for Population and Development.

STRATEGIC FIT AND RATIONALE FOR UK INTERVENTION

The UK–Kenya strategic partnership (2020-2025) objective on security and stability mandates that the UK and Kenya work together on Kenya’s anti-corruption drive and strengthen democracy and inclusion in Kenya. It also provides a framework for collaboration on illicit finance, organised crime and global terrorism. Kenya is a strong regional partner with whom we can achieve meaningful results. It has significant influence across the continent and on the global stage and is an important regional security player. The Prime Minister and Kenya’s President have agreed to a new 5 year Strategic Partnership.

Supporting the evolution of effective institutions, promoting transparency and accountability, tackling corruption and reducing illicit finance all contribute to the delivery of the Kenya Country Business Plan. KSIP will directly deliver against campaign goal (6) on Open Societies, Democracy and Human Rights. In addition, KISP will have indirect positive impacts on other Campaign Goals, since corruption and electoral fragility negatively impact UK strategic objectives more broadly, mitigating risks across the Country Business Plan.

Putting economic growth and jobs at heart of UK foreign policy: Tackling political corruption and strengthening legal and institutional frameworks in Kenya will contribute to a more predictable and transparent enabling environment for the private sector. This will contribute to mutual growth (Kenya and the UK), by attracting both domestic and foreign direct investments. Strong governance systems underpin success across all areas of human and economic development.
[note] FCDO (2020), ‘Governance Best Buys’ details how strong governance systems underpins success across all sectors of development

KISP directly supports several UK strategies to tackle corruption and illicit finance. First, on 21 November 2024, the Foreign Secretary launched the Illicit Finance Campaign to deliver a government-wide agenda to tackle corruption and illicit finance at home and overseas. Second, the International Illicit Finance Strategy (IIFS), Objective 1 seeks to “ensure that international standards remain comprehensive and reflect changes in illicit finance threats, vulnerabilities and methods, and that they are being effectively implemented.” Finally, the UK International Development White Paper (2023) stresses the importance of tackling corruption and illicit finance and provides a steer, align with the design of KISP, on how this should be approached; “Greater resilience to corruption and illicit finance in country systems is needed. Technical assistance alone is not sufficient. Compliance needs to be complemented by building institutional capability and resilience.” Modernising the UK approach to development suggests faster reform to the global financial system is required to tackle unsustainable debt and kleptocracy, and to unlock finance for development.

UK COMPARATIVE ADVANTAGE
The UK has a track record of support to Kenya on strengthening institutions. Previous relevant programmes include the Elections Management and Security Programme (EMAS) (2012-13), the Drivers of Accountability Programme (DAP) (2010-15), the Deepening Democracy Programme (DDP) (2016-19), Kenya Anti-Corruption Programme (KAP) (2020-24) and the Kenya Elections Support Programme (KESP) (2020-25). These programmes have delivered well against their objectives. We have learnt from these programmes and adjusted our new interventions accordingly.
[note] All programmes scored an ‘A’ in Project Completion Reviews and ‘A’ in recent Annual Reviews, except KAP, that scored ‘B’.

The UK is a trusted development partner, given our unique experience in election support and anti-corruption programming in Kenya. The UK also supported the National Dialogue Committee (NADCO) mediation process that enabled stability in the country after the 2022 elections, and continue to support electoral reforms, making the UK the only donor to use the electoral cycle approach.

The UK has a position from which to work on complex political issues, the FCDO brings together diplomatic and development expertise. Through KISP we will leverage both our diplomatic engagement and programming expertise to deliver the most impactful results. We are able/willing to take risks, which increases our potential for impact. An adaptive approach to our programming implies a higher risk appetite and a capability to ‘fail fast, learn quickly and adapt.’ This provides us the ability to respond to the rapidly changing political climate and leverage opportunities as they arise. However, an adaptive approach also requires a systematic analysis of potential risk and impact of each activity and identified risk will be mitigated through careful theory formulation and iterative evidence collection and theory refinement.

Our ability to convene other partners and leverage/influence other sources of funding is an added advantage. The UK will engage with and shape the work of the World Bank, the EU and others to ensure our objectives are mutually reinforcing.

KEY ELECTORAL REFORMS & ANTICORRUPTION PROGRAMMING LESSONS & GAPS IN KENYA

The UK has a track record of contributing to electoral reforms and anticorruption interventions in Kenya. Key achievements from previous programming include:
- Strengthening electoral institutions (electoral commission, judiciary, national police, Registrar of Political) which contributed to the delivery of a more credible and more peaceful 2022 general election: described by domestic and international observers as a better managed electoral process, meeting the credibility threshold; a peaceful transfer of power at the national and sub-national levels of governance, with no reported deaths of civilians from security services.
- Public oversight institutions improved the execution of their mandates: for example, through UK support, the Office of the Auditor General has improved audit quality, technical capacity to audit Integrated Financial Management System (IFMIS), and data usage, leading to a reduction in the timeline for finalising audit reports.

Key lessons learnt from previous FCDO-funded anti-corruption and election support programmes in Kenya include:
- To tackle the complexity of anti-corruption and electoral support in a changing environment requires a coordinated and strategic approach that uses a range of strategies and diplomatic tools.
- Elections in Kenya and elsewhere are a process, not an event. Early programmatic and diplomatic support is most effective in building relationships and credibility, allowing the UK to engage as a strategic partner, rather than just offering tactical assistance. It is critical that the UK can think and work politically, use its combined expertise, and adapt to changing processes.
- Election support programmes have not tackled the systemic drivers of corruption in the political system – manifest especially in the prohibitive costs of election campaigns and post-election patronage, including tackling the social norms like gifting. It requires having an understanding and addressing issues of social norms and behaviour change to address such systemic drivers.

To address these gaps, KISP will:
- Take a whole-of-government approach, as per the UK White Paper and in partnership with members of the international community. For instance, the European Union and GIZ have ongoing programmes on anticorruption and are currently designing new programmes on democracy and elections, but these are not focussed on the structural drivers of political corruption and do not bring the two areas together systematically – and they are delivered largely as development interventions rather than in routine coordination with their agencies’ political sections.
  [note] International Development in a Contested world: A white paper on International Development. Although a product of the previous UK Government, this paper had broad cross-party support
- We will learn from past UK interventions in Kenya, where political engagement and (development) programming efforts have not always been aligned and understanding and programming for behaviour change has not always been explicit. We will develop an advocacy and influencing strategy to be delivered by British High Commission (BHC) Nairobi’s senior leadership, to complement programme delivery.
- We will use an adaptive programming approach to enable us to test, learn and adapt strategies and interventions to tackle the evolving dynamics around political corruption and elections. This will require:
  - Political Economy Analyses (PEA) to identify potential entry points, an initial theory of change development (with the aid of network analysis and / or systems mapping), and iterative theory refinement throughout the programme based on the ongoing collection of evidence.
  - Activities will be piloted and subject to regular review (possibly 3-6 monthly) with the option to adapt, drop or add new interventions at these review points.
  - This approach will allow KISP to identify public institutions where opportunities arise to: change their behaviour and strengthen their integrity; address regulatory and legal loopholes which allow for corruption; identify key policy issues where political actors and citizens come together; and support electoral reform policies and processes where there is a critical mass of support by the public and from political leadership.

PROPOSED UK INTERVENTION

KISP is designed to spend up to £14m over five years. However, the programme budget will remain flexible to respond to the new ODA reduction landscape over the years.

The expected impact of the programme is: Reduced corruption and illicit finance in Kenya’s political system.

To achieve this impact KISP will deliver two outcomes:
1. Opportunities and incentives for corruption and illicit finance are reduced.
2. Kenya's political system increasingly utilises an issue-based politics model where policy benefits the broader public (rather than specific ethnic or social groups).

Outputs
1. Strengthened legal & policy frameworks, processes that tackle corruption & illicit finance
2. Improved governance & integrity of electoral processes & practices
3. Civil Society (incl. private sector) increasingly mobilised & empowered to engage in policy making and hold those with power to account
4. Politicians and political parties have increased access & are able to use better quality evidence to understand voters & their preferences.

The complexity and difficulty of addressing these issues means that programme implementation must place monitoring, learning and action research – and political economy analysis at its centre. In line with available budgets, KISP will prioritise interventions which have the biggest potential impact and probability of success (based on theory and available evidence) and generate additional evidence throughout implementation to understand what works best in reality.

Anti-corruption efforts are unpredictable, complex, context sensitive and hard to evaluate. Approaches which aim to deliver a clear set of activities which are decided upon at the start with little flexibility in implementation, don’t work well as they are vulnerable to politicisation and there is little contextualised evidence of what works. Evidence indicates an adaptive approach may be more successful. An adaptive approach emphasises learning, and the development practitioner (i.e. the KISP Managing Agent) can adjust their actions to find workable solutions to problems that they may face to deliver agreed programme objectives.

The below sections set out proposed interventions to deliver the outcomes, the intention is that these are further refined, amended, stopped or added to throughout implementation, based on real time learning.

Component A delivers a set of activities which build on existing evidence, strengthening accountability through a set of interventions similar to those which have been delivered in previous FCDO programmes. Component B tests a new approach for which there is little existing evidence, focussing on enhancing issue-based politics. Component C includes a reserve fund that will enable FCDO to respond to emerging opportunities that may not be up taken quickly by the management agent. All the components are linked to the outcomes and intermediate outcomes. The narrative which follows outlines the prioritised activities and outputs for year 1. These will be refined during inception.
[note] Examples include the UK funded Drivers of Accountability Programme (DAP 2013 – 2015) and the Deepening Democracy Programme (DDP 2016 – 2019)

Component A

This component will deliver on outputs 1-3 by strengthening the legal and regulatory and accountability frameworks that govern a small number of thematic areas – including elections. It will complement this by mobilizing citizen groups to engage in policy-making processes and other forms of political participation to hold government to account for commitments they have made or standards they have pledged to uphold. KISP will start with a focus on countering illicit financial flows, electoral integrity and improving integrity in public service. Decision on interventions will be made based on an agreed set of criteria, which could include for example: strength of evidence, risk, potential impact, probability of change (identified incentives of actors to change behaviour – see annex B), value for money and FCDO influence, costs, counterpart absorptive capacity and the availability of the required technical expertise. Working with targeted government institutions and citizens, civil society and the private sector, KISP will test, learn and adapt.

Examples of interventions in the three areas are:

Countering illicit finance
[note] Illicit financial flows in Kenya manifests in many ways, often involving complex schemes that exploit weaknesses in regulatory frameworks, financial systems, and governance structures. High-profile case examples include - Eurobond scandal issued in 2014, with questions about the transparency and accountability of how the funds were utilized, the National Youth Scandal (NYS) involving the theft of billions of shillings through fraudulent procurement processes in the NYS. Investment in high-value real estate to launder illicit gains is common.
FATF grey listing in February 2024 means Kenya is now subject to increased international scrutiny of its financial transactions. KISP will support government to achieve compliance with FATF Standards: enact and enforce relevant legislation, improving regulatory frameworks, and ensure effective implementation (e.g. regulation of high-risk sectors such as lawyers and real estate); build capacity to identify and act upon money laundering risks and coordinate across government. KISP will increase compliance with beneficial ownership requirements and the inter-operability of the beneficial ownership register with other government databases.

KISP will equally support civil society including the media to engage in investigative journalism to uncover illicit finance activities, create awareness for the public to understand the scale and impact of illicit financial flows on development and service delivery, hold government accountable, exposing regulatory loopholes and advocate for policy change.

As part of this programming design, civil society will be mobilised to form coalitions for change consisting of public and private sector stakeholders. Coalitions will work either by gaining support and building on momentum from pro-reform elements within the government, or by changing power relationships and incentives within the ruling elite. The key idea of issue-based programming will be to focus development interventions on specific tangible issues or problems, around which local stakeholders are supported to mobilise and drive reform. Success hinges on engaging diverse stakeholders, building trust incrementally, and framing interventions within local contexts to address complex, non-linear challenges effectively.
[note] Case studies described from Malawi, Nigeria, Ghana, Bangladesh, and Tanzania where Issue based programming has been used for governance programmes highlights the importance of adaptive, flexible, and politically informed programme designs in governance initiatives.

Improving electoral integrity

KISP will also work with the key electoral institutions to protect the progress made in the 2022 elections (for example improved elections operational efficiency, better logistics management on the elections day, better transparency of results transmission process through a public open portal), continue to enhance their resilience against political interference, support effective implementation of new legal, operations and administrative reforms, and guard against any decline against democratic standards. Noting that implementation of the Elections Campaign Finance law which aims at regulating the amount of funds politicians can use on political campaigns has not been implemented to date, KISP will invest in political economy analysis to inform approaches to elite negotiation, building a wider reform package on campaign financing and taking a gradual approach towards implementation.

Enhancing integrity of public service
The Constitution of Kenya, under Chapter Six, outlines integrity standards for persons holding or intending to hold public office in both elective and appointive positions. It’s one of the legally available measures that citizens, and civil society organisations can rely on to stop candidates with outstanding issues of integrity (corruption, abuse of office and fraud) from being cleared to participate in elections or gaining appointment to public office. Kenya is in the process of rolling out an electronic Government Procurement system (eGP) which is to be mandatorily adopted by all MDAs. This system is intended to enhance integrity in the public service by reducing opportunities for corruption, create verifiable audit trails and ensure equitable access to public services. The programme will support the development of a change management strategy building coalitions for change across government, the private sector and civil society, to facilitate efficient adoption of the electronic Government Procurement system (eGP). The programme will also develop a ‘think piece’ on the transformative opportunity of electronic Government Procurement to be shared with government.

Partner institutions are likely to be: the legislative (National Assembly and Senate) and judicial branches of government; and the independent oversight commissions which report to Parliament such as the Independent Electoral and Boundaries Commission (IEBC), Office of the Auditor General, Public Service Commission, and Ethics and Anti-Corruption Commission (EACC), which hold the executive branch of government to account via laws, rules and sanctions for violations, and “demand side” partners will include the media, Civil Society Organisations, business associations or private sector umbrella bodies like Kenya Private Sector Alliance (KEPSA) and trade unions to demand accountability from government. Other agencies could include Financial Reporting Centre, Business Registration Services, Register of Political Parties and political parties.

Component B
This component delivers output 4 which will ensure politicians and political parties have increased access & are able to use better quality evidence to understand voters & their preferences. This will encourage the nascent shift from clientelist to issue-based politics by encouraging and enabling voters, think tanks, the media, politicians and political parties to propose policies that benefit a wider range of people and to implement them (if they win elections). KISP seeks to address among other issues: party policies not backed up by clear data; inactivity of political parties between elections; weak connection between politicians, parties, and citizens at the local level; superficial party structures and restricted spaces for dialogue and collaborative policy formulation.

An adaptive programme approach will enable 1) identification of actors already engaged in this shift towards issue-based politics or open to exploring opportunities to move from clientelist to issue-based politics. 2) identification of potential for coalitions of actors engaged on the same issue where KISP may encourage collective action. The approach to supporting a shift towards issue-based politics would also benefit from Thinking and Working Politically (TWP) as it encourages a more politically aware approach, makes active use of ongoing political economy analysis of this shift and the actors involved, and provide evidence-based insights to encourage adaptation when opportunities or motivations for a shift arise.

Component C
1. Component C allows KISP a degree of flexibility to deliver in the event of 2 types of scenarios.
  1. In the event that unforeseen shifts in the context, providing KISP with new opportunities to take action, and where it is impractical or impossible for the implementing partner to respond on FCDO’s behalf.
  2. To respond if, and when KISP identifies opportunities to “design out corruption” by tackling corruption in sub-sectors, without directly taking responsibility for that implementation itself.

Table 2: Indicative activities for year one

Due to reduced ODA funding and uncertainties in the outer years, we have selected priority activities to be implemented in year one, indicated in table 2 below.
Component	Indicative year one activities
PEA	Conduct analyses to guide and inform delivery: e.g. problem driven PEA targeting specific problems that the programme could address in subsequent years. These will include: i) barriers to regulating Election Campaign Financing and identifying specific pathways for change; ii) political parties adopting issues-based politics; iii) implementing existing vetting processes for appointed officials. A baseline survey on citizen trust and engagement in policy processes will be undertaken to enable the programme to track progress.
Component A – / Countering Illicit Finance	Review legal sector regulation and supervision to provide politically feasible recommendations for improved governance of the sector (professional training, licensing, complaints and sanctions procedures) that is an enabler and preventor of corruption and illicit finance. / Increase beneficial ownership transparency through improving inter-operability of beneficial ownership register, increasing compliance with beneficial ownership register requirements by the private sector, developing legal/regulatory/registration framework for trusts, improving sanctions process for non-compliance with BO register.
Component A: Enhancing integrity of public service	Lead in developing a change management strategy that combines internal performance incentives, public recognition and building of coalitions of non-state actors to enable efficient adoption of the eGP (transparent procurement) system. A key focus on behaviour change, targeting entrenched procurement practices. / Development of a strategic narrative paper on the transformative opportunity of eGP, stating why public procurement reforms matter technically, politically, socially and economically and linking eGP to national priorities like economic growth and anti-corruption. This would help secure political buy-in shape political narratives, attract investment interest and mobilize local and international stakeholders. / Review the legal and policy framework for vetting those seeking elected and appointed positions, including the wealth declaration process, identifying political challenges and opportunities for reform.
Component A: improving electoral integrity	Comprehensive Induction of IEBC Commissioners to build their credibility and confidence to lead the 2027 election process. / Supporting IEBC to develop Election Operations Plan (EOP) to guide 2027 election. / Targeted technical assistance to strengthen elections operations – for example cleaning the voter register, risk management and mitigation plans, strengthening strategic communications​ and IEBC corporate governance protocols​.
Component B: Issue based politics	Develop a clear understanding of the GenZ networks and assess the opportunities for use of digital media and AI in the election and issue-based policy space. / Engage research institute to generate data on citizen policy preferences including their intention to participate in the election and to inform policy propositions by political parties. / Provide data to civil society groups, such as trade unions, business associations or the international community.

Table 3: What long-term success looks like
	What success looks like
Reduced opportunities and incentives for corruption and illicit finance in Kenya's political system	Improved understanding of money laundering risks by Government entities, the private sector and civil society. / Increased sanctions for financial institutions and designated non-financial businesses and professions for non-compliance with money laundering legislation. / Increased supervisions of financial institutions and designated non-financial businesses and professions for non-compliance with money laundering legislation, including improved guidance for the sectors. / Compliance rates of the beneficial ownership register increased indicating improved behaviour within private actors. / Legal persons or arrangements are prevented from misuse for money laundering and information on their beneficial owners is readily available to competent authorities. / Public officers declare interests and wealth in a register indicating improved behaviour in public institutions and actors being more transparent and accountable. / Campaign finance regulations enacted and implemented / More effective collaboration between government agencies and the private sector to detect and prevent illicit finance both locally and internationally. / Improved behaviour and integrity in public service as evidenced by effective vetting process for public servants and politicians that prevents individuals tainted with corruption concerns from taking office. / Reduced wastage and loss of public resources as reported by the Office of the Auditor General. / Key accountability institutions increase their independence and hold the Government to account, eg. auditor general’s office, Ethics and Anti-Corruption Commission. / Political parties to adopt robust internal vetting mechanisms during party primaries indicating improved behaviour and political integrity.
Kenya's political systems increasingly utilizes issue-based politics model where policy benefits the broader public / (rather than specific ethnic or social groups)	At least 5 main Political parties and their leadership prioritize clear and consistent policy-oriented agenda as evidenced by their party manifestos and policies. / Politician and political parties are better equipped to campaign and govern on policy platforms that attract support from across traditional ethnic and social dividing lines. / Shifts in the political system / culture that reflects move away from the behaviours and social norms which tended to be ethnic, personality based, clientelist and transactional politics to issues-based politics focused on policies to improve service delivery. / Transparent, accountable, and inclusive political culture focused on clear, evidence-based policies begin to emerge. / Politicians begin to display rule following behaviour. / Citizens and other interest groups demand reforms and accountability of service delivery by government. / Citizens, media and political parties begin to shape government incentives to foster more inclusive and participatory development. / Resistance to electoral and anticorruption reforms begin to reduce. / Improved citizen trust and confidence in Kenya institutions and political system. / An inclusive political system as evidenced by access levels and participation of women, youth and people living with disability.
Electoral integrity	Increased independence of key electoral institutions as evidenced by increased levels of citizen trust. / Sustained capacity of electoral institutions to deliver credible elections as evidenced by both domestic and international observer group reports. / Effective electoral legal and operational framework leads to credible elections in 2027 and beyond. / The electoral system makes it hard for election of corrupt politicians through more effective integrity rules. / Improved trust levels in electoral institutions as measured by citizen perception surveys. / Use of money in politics is better regulated as per reviewed laws. / The electoral system continues to evolve, over time encouraging cleaner and more constructive (policy-based) political competition, relative to the current dominance of clientelist dynamics.

ASSURANCE OF COMPLIANCE WITH UK LAW
Gender Equality and Public Sector Equality Duty: This programme will be compliant with both the UK Gender Equality Act and the Public Sector Equality Duty. During the inception phase, a gender analysis will be carried out to ensure that the interventions take gender differences and needs into account. The programme will generate evidence on gender exposure and vulnerability to corruption to expose gender specific vulnerabilities to corruption / corruption-gender nexus and consider specific interventions where women are disproportionately impacted by the consequences of corruption but are less likely to pursue complaints. KISP will ensure equality in opportunity throughout all levels of its delivery and avoid negative impact due to age, disability, gender reassignment, pregnancy and maternity, race, religion or belief, sex and sexual orientation. We will include women, youth and other marginalised groups in the processes of strengthening accountability in government.

Counter terrorist financing: The risks of terrorist financing in this programme are low and acceptable. The programme’s illicit finance focus will aim to reduce terrorism finance. A thorough risk management framework will be applied to all partner staff recruitment and downstream partner selection. In addition, FCDO Kenya will ensure: all implementing partners are aware of UK Counter Terrorism (CT) legislation; due diligence and audit of all downstream partners; and inclusion in all down-stream partner agreements and contracts, details of their obligations of all relevant terrorism legislation (and a recorded audit trail). Collaboration across government and reporting of any suspicions to the Counter Fraud and Whistleblowing Unit (CFWU) and National Crime Agency.

Climate and environment: KISP is not eligible for International Climate Finance funding. KISP does not have activities that directly target climate and environmental interventions, though commits to be rooted in “Do No Harm” approach to nature in order to ensure compliance with the Green Finance Strategy criteria of Paris alignment. The programme will not invest in fossil fuels or other activities that may undermine commitments to reducing carbon emissions.

Partnership principles: The programme does not provide direct financial aid to Government of Kenya. Implementing partners will work in partnership with line ministries, departments and agencies. It is expected that technical assistance will be offered through some of the supported interventions. The FCDO programme team will follow HMG Partnership Principles and guidance on working with Government.

Disability: The programme will contribute to implementation of the FCDO Disability Inclusion Strategy. This includes ensuring persons with disability are not excluded from programmes, and that proactive measures are taken by HMG Kenya and partners to maximise inclusion.

Safeguarding: The programme will adhere to HMG’s safeguarding policies, referenced under Contract Condition 50 in FCDO’s standard terms and conditions for suppliers and within the Code of Conduct Annex. During the mobilisation phase, HMG Kenya will conduct enhanced Due Diligence assessments of all proposed implementing partners. First tier implementing partners will work closely with FCDO to ensure that any downstream implementing partners are compliant with the safeguarding rules. Application and monitoring of these policies will be regularly reviewed and tested throughout the programme lifecycle.

## Appraisal Case

KISP THEORY OF CHANGE

The ToC brings together thematic areas traditionally thought of separately:
    1. Electoral integrity and;
    2. Countering political corruption and illicit finance flows.

In doing so the theory recognises that not only must political leaders be incrementally better regulated by rules, but that Kenya’s political system must incrementally generate incentives that make it feasible to adhere to those rules.

Figure I: KISP Theory of Change

KISP Theory of Change narrative
Problem identification – what KISP will address

As set out in the Strategic Case, Kenya is now a middle-income country, with good prospects for continuing economic growth and diversification. In structural terms, this should theoretically create an increasingly favourable environment and incentivise governance reforms: the consequences of economic transformation (urbanisation, higher education levels, a wider tax net, diminished traditional social structures) are positively associated with governance improvements. Evidence suggests that there is also a positive relationship between growth and a state’s ability to control corruption, but results vary widely, with some states are unable to progress growth higher because of corruption i.e. the “middle income trap”. Programmes therefore need to assess feasibility of interventions on a country-by-country basis due to this high degree of variation.
[note] Ping Ang and Dong, 2023
[note] Voss, 2020

The problem KISP will address is a systemic one, with multiple, inter-related components, and broadly unfavourable incentives for reform: those in power work within, and benefit from, the existing system. A clear understanding of this system, the behaviours of political elites and institutions, and these incentives is an essential first step.

How change might happen

Context: As set out in the Strategic Case, the theory of change is based on the premise that recent events (including peaceful elections, changes in voter behaviour, increased citizen mobilisation) are all indicators of a broader shift in the political landscape of Kenya. Through KISP, FCDO aims to catalyse on this shift, ensuring the direction of change persists, and it delivers longer-term, transformative change towards better governance, accountability and issue-based politics, which reduces corruption and illicit finance.

Theory of Change: Since some Kenyan citizens are increasingly shifting towards issue-based politics: IF the opportunity for corruption by those in power decreases (closing loopholes via regulation, policy, processes), AND voters and civil society are empowered to hold those in power to account and continue to engage in policymaking along issue-based lines, and the capacity of politicians and political parties to understand voter preferences is built, THEN politicians and political parties will be less motivated to campaign along ethnic or other socially dividing lines since they won’t gain electorate support, OR engage in corruption for fear of retribution. As more politicians and those in power realise this, more extensive behaviour change and social norms related to clientelism, patronage and entitlement will be addressed.
Activities and outputs: In line with FCDO guidance on adaptive programmes, this Business Case does not identify all specific activities and outputs. Initial analysis (or “diagnosis”) will help to identify issues, and root causes of corruption and inform interventions. This approach has been taken since there is no one way to fight corruption and it is still unclear as to which specific anti-corruption strategy works best in a particular context. The Basel Institute have developed ‘strategic anti-corruption guidelines for development agencies’ that suggest anti-corruption programmes should start with a good diagnosis that covers two broad areas:
[note] PrOF Guide: Top tips – How to design and manage adaptive programmes (nov 2023): “Where there is uncertainty about what activities or outputs will achieve the desired outcomes, programmes should be cautious about defining success in terms of specific outputs.”
[note] Vilanueva 2020

1. Identifying key corruption issues in that country or context that are hindering sustainable development.
2. Understanding root causes: identify underlying drivers of those problems, (such as social norms, or state capture through powerful networks of elites) to ensure projects are grounded in reality. Strategic approaches to anti-corruption will be based on this diagnosis so that activities are – at the very least – relevant, feasible, sustainable, and mindful of risks and unintended consequences.
  [note] Camargo 2021

Impact: Reduced corruption and illicit finance in Kenya’s political system.

Outcomes: The programme will contribute to two long-term outcomes:

1. Opportunities and incentives for corruption and illicit finance are reduced.
2. Kenya's political system embraces an issue-based politics model where policy benefits the broader public (rather than specific ethnic or social groups).

While progress against either of these outcomes would be significant and worthwhile, focussing on both attempts to interrupt the political-financial cycle (see figure II above) at various points, taking a more systematic rather than piecemeal approach. However, even taken together these two outcomes are necessary but not sufficient to achieve the intended impacts – see assumptions below.

Intermediate outcomes: There are two intermediate outcomes:

Intermediate Outcome I: Strengthened Accountability
  - Horizontal accountability, whereby independent institutions hold those with power/leaders to account via laws, rules and sanctions for violations.
  - Vertical accountability, whereby voters hold Government to account through periodic elections.
  - Diagonal accountability, where civil society groups, such as trade unions, business associations or the international community, hold those with power/leaders to account

These outcomes will be delivered through a set of broadly defined interventions and outputs (largely component A, but with some contribution from components B and C) which will be more narrowly identified during programme inception (and consecutive programme adaptation and re-design). Through this intervention approach, the programme will look for where there is evidence of potential change (‘windows of opportunity’) within institutions to identify specific actors and issues which are then linked to mechanisms for further behaviour change, i.e. public institutions are incentivised to satisfy a broader constituency and possibly a focus on longer-term policies and institutional change.

The programme will do this not just by working from the ‘top-down’ with senior officials, not only from the ‘bottom-up’ working with the media or civil society groups but instead will work with whichever combination of actors (working as coalitions) appear to have the power and the incentives to make progress. This will be underpinned by a thinking and working politically approach and may take the form of technical advice, although the programme will also seek to use resources to build coalitions and create the space for deliberation, using the offer of technical advice as an entry point.

Intermediate Outcome II: Issue based politics increasingly adopted by politicians. Politicians and political parties respond (campaign and govern) on policy platforms that attract support from across traditional ethnic and social dividing lines. This intermediate outcome focusses not on government systems, but on the skills and resources political parties and political leaders must have, to conduct forms of issue-based politics. This will include data generated by think tanks and other research institutions and sustained pressure from organised citizen groups demanding for responsive policies and services.

Assumptions

There are several important assumptions underpinning the proposed ToC. These assumptions will need to be regularly tested by the programme, to inform adaptation.

Kenya’s economy continues to grow and diversify, incrementally increasing the attractiveness of rules-based governance for businesses and citizens. There is also an underlying assumption that Kenya’s political economy is creating relatively favourable conditions for reform. This speaks to a double assumption: firstly, that such a proposition is correct; and secondly that these changing conditions will continue to emerge over the course of the programme.
[note] Although the debate on this proposition is not settled, the theoretical case in favour is well made by Khan, Andreoni and Roy in their Briefing Paper “Anti-corruption in adverse contexts: strategies to improve implementation”, produced under the FCDO-funded SOAS Anti-Corruption Evidence Programme (see Introduction)

A broadening tax base continues to change the nature of state-society relations. Where the tax base is small and narrow, the wider population is effectively investing less in state-building. When states expand the tax base, citizens tend to demand a greater say in the use of those resources. Kenya has a pressing need to raise taxes and as it does so this it will increase pressure on the state to be responsive to taxpayers newly caught in the net. The ToC assumes this will continue and will create opportunities/pressure for greater accountability and democratic control.
[note] This is known as the ‘governance dividend’ theory of taxation. It is not always the case that the governance dividend is automatically realised as the tax net deepens and broadens. Governments can, for example, use selective tax exemptions to improve their bargaining position vis a vis taxpayer groups, avoiding demands for greater public accountability (at least for a while). Nonetheless, it is still widely accepted that broader and deeper taxation is more likely to encourage accountability when compared with narrow tax regimes, such as those dependent on land or natural resources. For a critical treatment of the theory, see “Tax and the Governance Dividend”, Mick Moore, ICTD Working Paper 37.

The capability of the state to deliver core functions and public services continues to improve. Politicians often perpetuate clientelist practices because that is what citizens expect of them. These expectations persist because issue-based promises (e.g. to improve healthcare or invest in infrastructure) are not considered sufficiently credible, given the weak capability of the state. The conditions that enable a shift away from this equilibrium include the steady improvement of state capacity, so that campaign promises to deliver particular policies, are increasingly credible.
[note] In “Formalizing clientelism in Kenya: From Harambee to the Constituency Development Fund”, UNU WIDER Working Paper 2021/147, Ken Opalo concludes “Overall, high state capacity and institutionalized environments are conducive to programmatic politics; while the obverse conditions render targeted clientelism the most credible currency in the political market”

The essential conditions for a change in the behaviour system are present in Kenyan political and electoral system. The three essential conditions in the behavioural system are capability, opportunity, and motivation which, combined together, overcome the deep-rooted challenges faced with endemic political corruption, especially during elections, and social norms.

KISP will adopt approaches which build on learning from previous programmes:
Adaptation: An adaptive approach is the most suitable approach for KISP as it allows for flexibility within a politically contentious and fragmented context and addresses the issue of limited evidence. It goes beyond working with the grain, by identifying and responding to opportunities and constraints and considers actors first and issues second, and it understands that people (both those being influenced and those who are influencing) matter most in tackling political corruption. KISP also needs to have a more narrowly defined focus on a key set of actors and institutions to be influenced and act as influencers, whilst create synergy between programmatic and diplomatic efforts in influencing behaviour change.
[note] See https://www.ids.ac.uk/publications/adaptive-programming-in-fragile-conflict-and-violence-affected-settings-what-works-and-under-what-conditions-the-case-of-perl-nigeria/

Combining ‘supply-side’ and ‘demand-side’ approaches, with opportunities identified according to prior ‘political economy analysis’: Possible interventions for tackling corruption include improving public finance systems, improving integrity within public service, supporting audit processes, strengthening the media, amongst many others. All have merit in the right circumstances, but many are dependent on an assumption that it is in the interests of the Government to tackle corruption, and therefore Government (at least at the centre) will put in place the measures necessary – so called ‘supply side’ governance reforms. But the problem identification analysis above shows why this is, in large part, an unrealistic assumption to make.

When operating on an assumption that Government overall will be either disinterested or actively hostile to measures that target political corruption, many aid programmes in the past have tried a ‘demand-side’ approach instead of a supply-side approach. This has involved mainly supporting civil society groups campaigning against corruption, as well as the media sector. However, evidence of the effectiveness of these approaches is limited.
[note] In FCDO’s 2020 ‘Governance Best-Buys’ evidence review, 5 ‘demand-side’ approaches were reviewed. All were classed as either ‘mixed’ or ‘low’ evidence or ‘bad buys’, with the exception of participatory budgeting, which was classed as ‘high potential’ but with major caveats: “[only where there is] government willingness to sanction it in the first place, and typically only applies to a small share of municipal (rather than national) budgets”

Consequently, most recent programming seeking to tackle corruption or improve political governance more broadly has sought to combine ‘supply-side’ and ‘demand-side’ approaches, with opportunities identified according to prior ‘political economy analysis’ and supported with skilled, locally connected implementing partners. This approach has come to be known as ‘thinking and working politically’ which is considered by FCDO-funded research as intrinsic to a successful adaptive approach, and was assessed as a ‘best buy’ in the 2020 Governance Best-Buy evidence review. This creates a second ‘given’, in addition to being adaptive: KISP should combine demand-side and supply-side interventions in a ‘thinking and working politically’ approach.
[note] https://www.ids.ac.uk/projects/adaptive-programming-for-empowerment-and-accountability/
Table 3: Evidence for a “thinking and working politically” approach
Case Study: II. Findings from a thematic evaluation of BHC support to the 2022 elections
Evidence generation, diplomatic engagement, and targeted behavioural strategies enhance programme effectiveness. A thematic evaluation of BHC support to the 2022 elections found KESP to have made strong contribution towards improving elections management and improved electoral dispute resolution. The evaluation identified two enabling factors which are relevant to the design of KISP as an adaptive programme: / i. investment in evidence generation and learning processes, and / ii. synergy between programming and diplomatic influencing.

Behaviour change approach: Given the problem analysis has identified deep-rooted issues related to negative social norms and behaviours underpinning political corruption and weakness in the electoral system, KISP needs to take a behaviour change approach. This includes taking a strategic approach to purposefully influence behaviour change which takes into account motivation (a COM-B framework was recommended as a lens for programme design, implementation and measurement), Building on the evidence of what works in recent FCDO governance programmes in Kenya and more widely (for example, in FCDO’s election monitoring work in Nigeria), KISP will adopt a COM-B model as set out in the theory of change (see also Annex B) to understand and influence behaviour change in such a complex and challenging context of political corruption in Kenya. This model articulates a “'behaviour system' involving three essential conditions: capability, opportunity, and motivation”. As used in the REINVENT review, it provides a basis for designing interventions aimed at behaviour change, making it an ideal model or framework through which to understand a programme like KISP where it is critically important to support behaviour change interventions. It fits well within an overall adaptive approach drawing upon elements of thinking and working politically and political access and influence.
[note] See Annex B for more details on the COM-B model for behaviour change
[note] Michie, S., van Stralen, M.M. & West, R. The behaviour change wheel: A new method for characterising and designing behaviour change interventions. Implementation Sci 6, 42 (2011). https://doi.org/10.1186/1748-5908-6-42
Table 4: Evidence for a behaviour change approach
Case Study: II. REINVENT
The key lesson learnt was that REINVENT was effective, however it only made medium contribution towards reducing elections-related violence by delivering security sector support, community engagement and diplomacy. A review in 2024 emphasised how REINVENT needed to place behaviour change at the heart of the programme and make efforts to enable adaptation. Diplomatic engagement steered mediation with key actors to address hate speech and destabilising forces.

With these ‘givens’ design work identified three different ways in which (over the medium-to long-term) political corruption in Kenya might eventually come to be better controlled. These three theories form the basis of the options appraised below.

Gender Equality Approach

Attaining gender equality will be a significant focus of this programme. There is not much evidence about the interaction of illicit financial flows /corruption and gender. Nonetheless, we have arrived at the following broad understanding:

1. Corruption disproportionately impacts women and girls in its negative effects – the overall argument is that corruption/illicit finance distorts legitimate sources of income at international, national and community levels both in terms of access to legitimate sources of income (they become fewer/are only available if you have means to corrupt) but also in terms of service provision and opportunity that might benefit women/girls (tax returns are distorted and State ability to meet education/health/employment needs are reduced – this further entrenches gender inequality). Strengthening controls against illicit finance/corruption would contribute to reversal of these dynamics allowing more women and girls to benefit.
  [note] Addressing the gender dimensions of corruption, United Nations 2021
2. Corruption mechanisms are less likely to be used by women and girls – there is evidence that women and girls are less likely to avail themselves of formal complaint mechanisms to denounce corruption. This could be due to a lack of understanding of the mechanisms; because they are male dominated (potentially also already corrupted) and therefore do not welcome approaches or; because of a lack of time/opportunity (women still disproportionately cover domestic work etc). Building out more gender sensitive reporting/complaint mechanisms to corruption would improve this.
  [note] Transparency International 2024 - Impact of corruption on women and their role in preventing it, Transparency International 2024

There is some evidence of the risk that pursuing IFFs might see women playing minor roles and who ultimately have less/little criminal responsibility being swept up in enforcement actions whilst males (who – it is argued - are more likely to be directing corrupt actions) escape. An example is that predominantly female secretaries are asked to sign off documents committing fraud/corruption by male seniors, often when they don’t know the true purpose of the documents. The secretaries are then the first arrested by law enforcement as they are the easiest to identify).
[note] Gender-and-IFFs-2019.pdf (transparency.org); The gendered dimensions of illicit financial flows (u4.no)

Based on the above theories, KISP will invest in research and analysis to identify how election corruption / corruption of politics predominantly benefits male politicians compared to females. KISP, in tackling corruption, would seek to reverse this dynamic and, in re-opening the political arena making it fairer and more transparent, allowing for a greater diversity of actors to participate. The programme will seek to support civil society movements arguing for greater diversity in political participation. This would indirectly contribute to loosening (male-led) corruption’s grip over politics. Other interventions would include strengthening reporting mechanisms to be gender sensitive when someone suspects political corruption; working with law enforcement/regulatory agencies to make sure their investigation strategies are gender-aware; and facilitating reform within political/election institutions, to ensure diversity in human resource processes; comms strategies; training offers etc and making sure diversity is respected.

DELIVERY OPTIONS FOR APPRAISAL AND THE PREFERRED OPTION

The below sets out the possible approaches which could be used to deliver the outcomes, and their relative strengths and challenges. Note that the counterfactual / do-nothing option has not been included in the appraisal below, since the rationale for intervening is strong (including, but not limited to potential for high impact, generation of useful evidence and FCDO’s unique strengths and experience in this area). At the same time, the possible modes for delivery are multiple and warrant deep consideration in this business case.

Option A (component A in the theory of change)
Through this option, political corruption would be tackled by seeking to strengthen the legal and regulatory frameworks and other accountability mechanisms that govern elections and public administration in Kenya. This would entail HMG providing support to strengthen:
- ‘Horizontal’ accountability, whereby independent institutions hold those with power/leaders to account via laws, rules and sanctions for violations;
- ‘Vertical’ accountability, whereby voters hold Government to account through periodic elections; and
- ‘Diagonal’ accountability, where civil society groups, such as trade unions, business associations or the international community, hold those with power/leaders to account

The problem traditionally associated with this approach is that in countries with highly unequal distributions of power the powerful will regularly ignore the rules and can do so because those responsible for setting or enforcing rules owe their jobs and their future careers and protection from prosecution themselves to those powerful individuals. Thus, in Kenya, as in many other middle-income countries, rule-avoiding behaviour cannot be forced to become rule-following behaviour just by hoping one or other agency, if sufficiently strengthened, will suddenly have power it has not hitherto had. An understanding of this type of behaviour, and the opportunities for and motivations of powerful elites, including how they could be incentivised to change, would need to be considered in any programme aiming to strengthen accountability.

This is not to say that improvements in accountability are not possible in Kenya - such improvements have and continue to take place, for example in election administration (including with UK support). Sometimes opportunities to strengthen accountability arise as a result of top-down leadership (for example, from a Chief Justice or Chief Election Administrator, or particular Minister). And sometimes they come following pressure (for example from influential civil society groups, from organised citizen groups as was recently the case with GenZ / youth anti-government protests in Kenya, because of media exposure or following scrutiny by a Parliamentary committee). Most often it is a mixture of both (and this is how the approach would work – building coalitions of actors inside and outside the state).
Table 5: Case study examples of diagonal accountability
Case Study: II. Reducing Insecurity and Violent Extremism in the Northern and Coastal regions of Kenya programme
(REINVENT) combined police training and guidelines with multi-stakeholder approaches including hotspot mapping and conflict management through community security intelligence committees.
Case Study: I. Nigeria PERL (Partnership to Engage, Reform and Learn) - service delivery.
This adaptive governance programme demonstrated the benefits of connecting government and citizens groups to address governance challenges. Keeping a focus on the stakeholders and retaining flexibility to switch between issues ensured the programme was able to effectively deliver.

Table 6: Case study example of horizontal accountability
Case Study: II. Ghana Strengthening Action Against Corruption in Ghana (STAAC).
The programme provided support to the drafting of the Companies Act 2019, addressing Beneficial Ownership Transparency (BOT) and paving the way for the creation of the public register.

Whilst difficult to measure, there is some evidence suggesting that tailored electoral integrity measures that facilitate greater political competition or effectively target certain forms of electoral corruption such as political finance violations and vote buying can help combat corruption. The literature indicates an increase in electoral integrity can lead to greater control of political corruption such as cronyism and undue influence, but its effects on administrative corruption remains understudied. However, specific conditions seem to include political finance measures such as subsidies and financial disclosure laws, building the capacity of election management bodies and the presence of an open media environment. Diverse definitions electoral integrity and corruption in the literature, as well as types of electoral systems, complicate cross study comparisons and make it difficult to draw general conclusions. In some contexts, voters may fail to sanction candidates linked to corruption due to factors such as partisan bias, the provision of benefits to voters and levels of economic growth.
Table 7: Case study example of electoral integrity measures
Case Study: II. Kenya Electoral Elections Programme – the importance of taking a systemic approach
Technical assistance to independent election management bodies can also improve the transparency and quality of elections management. The main shortcoming of KESP was that it did not improve integrity of the electoral process due to failure to, for example, control excessive use of money in Kenyan politics.

As a behaviour change approach is suggested, it should also be possible for KISP to be innovative by applying an in-depth understanding of Kenyan social norms to establish what reforms may attract more or less social – and therefore political – support and, critically, design interventions which can support specific reforms, institutions and other actors advocating for change.

Nonetheless, opportunities to make progress are likely to be hard to come by, hard to take advantage of and subject to reversals, since they will often be going against the grain of the underlying political equilibrium. Much will depend on the quality and use of political economy analysis, the quality of political relationship building/coalition building and our/the partners’ willingness to avoid spending where chances of progress are low.

Option B – (Component B in the theory of change)
Many countries reduce corruption not by tackling corruption head-on, but by adopting reforms and policies favouring integrity and impartiality. These changes reflect a shift from clientelist system, where specific groups such as tribes, clans, ethnic or linguistic groups often trump those of the wider public); to one that is more issue-based or ‘universalist’ (where citizens expect political parties to propose and be able to implement in government policies that benefit a wider range of people). An adaptive approach would enable a programme like KISP to identify and act on specific areas of reform and issue-based policies where there is support from the broader public.

Universalist governance models, often based on wide-spread taxation (that make most citizens taxpayers) discourages corruption by making favouritism to be seen as deeply unfair, or corrupt (rather than just ‘the way it works around here’). In contrast, clientelist systems treat resource allocation to specific groups as normal (in some circumstances), encouraging politicians to prioritise their own networks. This weakens impartial laws, administration and rule-of-law.

Kenya, like most middle-income countries, reflects both universalist and clientelist politics. Arguably the 2022 demonstrated some progress with the successful Presidential candidate focusing on a broad economic agenda that appealed across tribal lines targeted at an emerging working class. To encourage this shift, efforts should encourage voters, the media, civil society and politicians and political parties to see the costs of clientelist policies and the benefits of universalist policies. Examples include:
[note] See “Hustlers versus Dynasties? The Elusive Quest for Issue-Based Politics in Kenya”, Ken Ochieng’ Opalo, Georgetown University, 2022
[note] For the evidence base underlying this, see for example “The Quest for Good Governance: How Societies Develop Control of Corruption” 2015, by Alina Mungiu-Pippidi; and “The Quality of Government: Corruption, Social Trust, and Inequality in International Perspective” 2011, by Bo Rothstein
  - Analysing and publicising the impacts of policies (e.g. through think tanks and the media),
  - Engaging diverse citizen groups together to deliberate on possible reforms (e.g. within a local government),
  - Supporting political parties to create and target inclusive policies (e.g. using polling data or focus groups).
These efforts are more likely to encourage behaviour change within the political leadership and public institutions, justifying a behaviour change model. These efforts are more effective when taxpayers are a broad group, as a narrow tax bases concentrates power and allows elites to maintain support through the distribution of patronage.

Three potential problems with this approach include:
  1. Limited evidence: the evidence-base for international aid having much impact on powerful social/political dynamics such as this is very limited.
  2. Broad sweeping change: The second is that this describes very broad, sweeping changes (e.g. tax and public administration reform) that makes it difficult to focus on a limited, manageable number of interventions –and many of these interventions will take decades to bear fruit..
    [note] See Ken Opalo above
  3. The third problem is that not all corruption in Kenya results directly from clientelism; indeed, political leaders pursuing non-ethnic support may still offer more material benefits to voters, to compensate for the presumption that voting for a co-ethnic is more likely to bring direct benefits than voting for a non-co-ethnic. So, the effect of a shift away from ethnic- or kinship-networks may not reduce corruption in the short or medium term. However, it could pave the way for long-term public-sector reforms
Option C – (Component C in the theory of change)

“Designing out” corruption would require detailed political economy analysis of sectors or policy issues to identify possible reforms or opportunities for collective action. These would not only would reduce or eliminate corruption affecting that sector/issue but are politically feasible because some influential-enough group of stakeholders stands to gain from the reform and their latent support/influence could be mobilised given the right type of external support.

For example, in Bangladesh, the School of Oriental and African Studies (SOAS)- Anti-Corruption Evidence programme found that when small infrastructure projects financed by climate funds had a dual-use that benefitted local landowners, corruption associated with those projects diminished. This suggested a straightforward reform: to require all climate-fund infrastructure projects to have a dual use, testing different dual-use proposals to see which attracted the most support from locally influential groups.

The problems with this approach are that (a) it requires significant expertise and resource to research and identify potential areas where corruption can be ‘designed-out’; and (b) even where such opportunities are realised, they tend to be quite far downstream in particular sectors, with little impact on the upstream systems of corruption that have the most impact. Of course, that is the point - this approach is built upon the assumption that expecting such strategic-level reforms is naive in most contexts.
 Table 8: Case study example of “Designing out” corruption
Case Study: II. Malawi Traction Programme – Seed verification.
The Malawi Traction Programme tackled counterfeit seeds by uniting public and private sectors. This programme demonstrated how accountability can be woven into specific sectors, in this case agriculture, resulting in beneficial outcomes. By bringing together different stakeholders from the private and public sector and securing collective buy-in for a verification system, the problem of counterfeit seeds (which were of lower quality) was addressed in the Malawian agricultural sector.

Analysing the options

Table 9 appraises each of these three options against five criteria:
- Would it work? How much confidence does the evidence give us?
- Is it a ‘good fit’ for the UK? Does it align with our comparative advantages and our priorities?
- Are other partners engaged? Is there merit in an additional UK contribution?
- Is it affordable and feasible? What practical factors speak in favour or against this option?
- Is it risky? Are the issues that make this option relatively risky compared to the others?
Table 9. - Multi-criteria scoring appraisal of the options
	Option A. Strengthen accountability	Option B. Support programmatic politics	Option C. ‘Design-out’ corruption
Would this work? / How much confidence does the evidence give us?	If top-down leadership can be found (with the capability, opportunity and motivation to change), the evidence is strong this approach can work. But this leadership is likely to be sporadic at best. Score: 3	Conceptually this approach is as strong as the others but is innovative and therefore significantly less tested and evaluated. An adaptive approach would however be appropriate. Score: 2	This approach is increasingly well-tested and if implemented well can be expected to deliver meaningful change, albeit at a ‘downstream’ level within sectors. Score: 3
Is it a good fit for the UK? / Does it align with our comparative advantages and our priorities?	This approach represents an evolution of our previous work, which has been praised and welcomed by interlocuters. It suits HMG on illicit finance and elections and fits HMG strategy and an adaptive approach which FCDO is known for. Score: 5	This approach builds on UK comparative advantage in elections and anti-corruption; and leverages the UK’s ability to work on sensitive areas of policy, and in Thinking and Working Politically. But it is not traditional ground for any development partner. Score: 4	A radically different approach from HMG’s previous work. Entails no work on elections or illicit finance, areas of UK comparative advantage. Benefits would be seen downstream in sectors, not upstream in governance institutions. Score: 1
Other partners engaged? / Is there merit in an additional UK contribution	EU, Denmark already implementing or in the process of designing some new accountability programmes but not enough to cover all sectors. Score: 2	No other partner implementing programmes to support programmatic politics. Score: 4	This would depend on the sub-sectors chosen, but by design this approach would avoid areas where there would be conflict with other programmes. / Score: 4
Feasible? / What practical factors speak in favour or against this option?	The availability of skills and experience (including in adaptive programming) in the market suggests there would be good competition for this work and reasonable confidence of quality delivery. Score: 4	As this is a relatively unconventional approach, the market may not offer much choice. Although the market can offer how they could apply an adaptive approach. Score: 2	While increasingly well-tested, this approach requires very high capabilities in political economy analysis and sector understanding. This may be hard to find in the market. Score: 2
Risky? / Are the issues that make this option relatively risky compared to the others?	This is a low-risk approach, except in one important respect: without top-down leadership from within GoK, and genuine agency for change, there is a risk of failing to achieve impact. Score: 3	This approach brings some (manageable) risks of perceptions of partisanship. Benefits are also likely very long-term and difficult to quantify. Score: 2	This is a low-risk approach, since the method involves selecting political feasible areas of engagement: Score: 4
Total Out OF 25	Option A Total = 17	Option C Total = 14	Option B Total = 14

For each of the five criteria, each option is scored from 1 (weak) to 5 (strong).

This multi-criteria appraisal results in the following scores for each of the options:

- Strengthen accountability – scores 17 out of 25
- Support programmatic politics – scores 14 out of 25
- ‘Design-out’ corruption – scores 14 out of 25

This implies that Option A is preferable, but the scores are close. This suggests it is worth considering whether any combination of the above options helps to produce a better balance of advantages and disadvantages. To appraise this, we scored each possible combination against two criteria:

1. Coherence. Does this combination require complementary skills (as indicated in Table 10) and focus on similar areas? Or would it require differently skilled-implementing partners and pull HMG resource in different directions?
2. Practicality. Given any combination requires spreading resources compared to focussing on one option, would the implementation of this option still be practically possible?

Again, against the two criteria each possible combination was scored from 1 (weak) to 5 (strong).

Table 10. - Multi-criteria scoring appraisal of possible combinations of options
Option	Coherence	Practicality
A+C	These are very different approaches, likely requiring differently skilled implementing partners, engagement with different counterparts, etc. / Score: 2	Both approaches would require a significant commitment of resources to be credible. / Score: 2
A+B	Both approaches, while different in theory, are focussed on elections and anti-corruption. They both lend themselves well to an adaptive approach. / Score: 4	Potentially option B could be a ‘junior’, or smaller, partner to a better-funded option A / Score: 4
B+C	These are very different approaches, likely requiring differently skilled implementing partners, engagement with different counterparts, etc. / Score: 2	Potentially option B could be a ‘junior’, or smaller, partner to a better-funded option C / Score: 4
A+B+C	Combining all options would cover all bases, but risk coherence. / Score: 2	Combining all options would spread resources very thin. / Score: 1

This multi-criteria appraisal results in the following scores for each of the options:
- Option A+C – scores 4 out of 10
- Option A+B – scores 8 out of 10
- Option B+C – scores 6 out of 10
- Option A+B+C - scores 3 out of 10

Overall, this analysis suggests a preferred approach combining Option A and Option B, and this is largely the preferred option described below. But two further issues were raised during consultations on design that required further deliberation.

Firstly, whether FCDO needs to retain the ability to respond to unforeseen events or opportunities that arise during the programme, where it is impractical or impossible for the implementing partner to respond on FCDO’s behalf. Some examples considered were grants to civil society organisations (such as election observer groups) in advance of the 2027 election, or contributions to multilateral programmes that held significant promise or would benefit significantly from a UK contribution. In both cases it is possible to imagine the objectives of an adaptive programme being well served by such grants/contributions, but the implementing partner would not be able to make them.

Secondly, whether the programme can retain some capacity to enable an ‘option C’-style approach to tackling corruption in sub-sectors, without directly taking responsibility for that implementation itself. Examples raised here included expertise to understand and consider responses to corruption in the use of FCDO-supported climate funds, FCDO-funded health or education support programmes or in County Governments that request such support. Again, this lends itself to an adaptive programming approach.

In both cases the design team concluded that while these possibilities did not invalidate the preferred approach, they did warrant enough flexibility being built into the final design.

Preferred Option

The preferred option incorporates a core programme, focussed on Options A and B described above, plus reserved budget lines for:
- Sub-sector corruption analysis (enabling other HMG teams to ‘design-out’ corruption in their sectors/programmes as per Option C described above).
- A responsive fund for unforeseen events or opportunities.
- Other programme costs, such as programme-funded staff.

Table 11. - Programme outline
Component	Approximate % of programme resource
Core programme
Option A	52%*
Option B	25%*
Reserved budget lines
Sub-sector corruption analysis (Option C)	4%
Responsive fund	10%
Other costs	9%
[note] Including monitoring and evaluation costs, programme design costs and a programme-funded post – further details in management and financial cases

* These allocations are notional since funding for the core programme is intended to be flexible and adaptive: see further detail in the financial and management cases

Value for Money
The KISP programme will develop a VFM matrix at the inception phase to determine key VfM considerations, indicators and benchmarks. These will be built on the KISP log-frame and indicators will be finalised at the design stage. All contracts and agreements with implementing partners will include VFM considerations from the outset, explaining how costs and cost drivers will be captured and monitored over time, using benchmarking from similar programmes where appropriate. Individual indicators for the different programme components set out in the KISP log-frame will be tracked and reported quarterly and annually. KISP will also develop an evaluation strategy which will enable FCDO to dig deeper into questions around efficiency and effectiveness. This strategy will ensure lessons learned to improve VFM in programme delivery will be captured and applied in ‘real-time,’.

An adaptive approach means that the programme must effectively manage uncertainty and experimentation. This means providing a thorough assessment of perceived risk and potential impact when piloting interventions. While upmost care will be taken to ensure efficiency and economy in delivering outcomes, the approach will not be able to guarantee that all outputs are economical and efficient, with instead a greater focus on effectiveness and an appetite for failure. An emphasis will also be placed on how learning has been used to enhance programme effectiveness. Decisions on success against these markers will be informed by:

Economy (buying our inputs at the right price). All KISP implementing partners will optimise economy whilst maintaining quality service provision through:

- FCDO centrally managed open and competitive procurement of service providers, premised on the highest technical competency and the most competitive financial bid that will:
  - Scrutinise financial bids to ensure unit costs for consultancy fees, expenses and administrative costs are benchmarked and as low as is appropriate in each context.
  - Ensure management costs (programme management and overhead) maintain a standard industry percentage of overall costs.
  - Scrutinise travel costs as a proportion of management costs.
- The KISP programme team will ensure:
  - Utilisation of local staff to lower transport costs and build local capacity.
  - Lessons learning and capturing examples of synergies and operating efficiencies which have reduced programme management and running costs.
  - Monitoring cost inputs throughout the programme lifecycle through regular reporting and programme team meetings. Efforts will be made to reduce unit costs during implementation where possible, either through economies of scale and/ or leveraging off other programmes operating in the same context to reduce staffing, equipment, transportation costs etc.

Efficiency (how well are our inputs converted into outputs). Effectiveness will be tracked through:

- Adaptive delivery mechanisms and a mix of service providers.
- Monitoring, evaluation and learning to determine inputs required to reach expected results in each context, at what cost, and at what speed. It will also seek to determine any trade-offs between risks and potential impact of interventions at the design stage.
- Deployment of the right skills, expertise and implementation modalities to consider political contexts in delivery.
- The overall quality of outputs.
- Satisfaction of local government and partners with the assistance provided.
- Appropriate consideration of gender, disability and marginalised communities within delivery of outputs.

Effectiveness (how successful are outputs in achieving outcomes).

- Engagement of a wide range of stakeholders in political engagement.
- £ leverage ratio - amount of finance that is leveraged or mobilised because of programme activities.
- Number of new partnerships established as a result of programme activities.
- Utilisation of lessons learning across and within projects.
- Uptake of new systems-based approaches by other donors (value of aid spending influenced).
- Increased service delivery, including improved quality and increased access for the vulnerable and disadvantaged groups.
Ensure that outputs “do no harm” to vulnerable groups, climate and environment and put in place structures to ensure that any losers are appropriately compensated.

Equity (spending fairly). KISP will deliver on UK's entrenched commitments to ensure that benefits are distributed equitably and that the impacts on vulnerable groups and hard-to-reach populations are appropriately considered through:

- Ensuring gender balanced teams at all levels within delivery partners.
- Supporting gender-sensitive policies in elections and public service.
- Ensuring outreach to high vulnerability clusters, where the poorest and most marginalised populations live.
- Inclusion of marginalised voices in political conversations
- Ensuring programme data is disaggregated, inclusive and that participatory approaches are utilised.

Table 12: Examples of Adaptive VFM indicators/ criteria that will be applied to KISP

Aspect of VFM	Indicator/criteria	Why this is appropriate
Economy	Comparison of costs spent on management and administration relative to technical delivery. / This indicator will be combined with qualitative reflection on whether the ratio is appropriate considering the programme’s delivery model, implementation stage, context, and objectives.	This indicator will be used by the programme team to reflect on whether they are spending money on the rights kinds of inputs needed to support testing, learning and adapting.
Efficiency	Comparison of total expenditure on intervention-scoping relative to the number of interventions progressed, paused or dropped based on evidence and learning. / This indicator will be combined with qualitative reflection on whether the decisions were taken in a timely manner, based on reliable, well-triangulated information or research, and without committing more time or other resources than was justified reasonably by the information available at the time. / This could include reflection on how quickly workstreams are dropped if they are not having the intended effect, and how quickly the team is able to evidence that learning from these processes is being fed back into programming	KISP will deliver good VFM by using scoping, lesson-learning and feedback mechanisms to identify, pilot and scale up successful interventions, whilst quickly identifying and scaling down, stopping or adapting interventions that are not showing results. / Tracking the numbers of issues or workstreams progressed, paused or dropped, and reflecting on the pace and the rigour of the processes through which this happens, will help indicate how efficiently the programme is strategically allocate funds to those areas that are most promising.
Effectiveness	Number of issues where the programme has made a significant contribution to outcome level change. / This indicator will be combined with qualitative reflection on the nature and extent of the programme’s contribution to change in selected results, an estimate of the costs spent to achieve the result, and an evaluation of why those costs were or were not reasonable considering the results achieved.	In complex change processes, effectiveness should be based on a reasonable assessment of the contribution that a programme is making to outcome-level changes. Drawing on qualitative results stories rather than (or in combination with) cost-benefit or cost-effectiveness calculations will help mitigate the risk of the programme focusing on easily measurable but potentially less important areas of work.
Equity	Comparison of the number of target marginalised group members reached by an intervention relative to expenditure. This indicator will be combined with qualitative reflection on the nature of the benefits experienced as described in beneficiary feedback, and an assessment of whether and how the programme could reach target group members more economically, efficiently, and effectively.	KISP will learn and adapt based on knowledge and understanding gained about and from different marginalised groups. This measure is designed to capture the fact that – in principle -adaptive programming provides an opportunity for beneficiaries to shape the programme’s approach and spending.

## C. Commercial Case

What are the preferred delivery routes and funding instruments for this intervention?
To maximise results and Value for Money, KISP will use a flexible and adaptive approach and robust programme, financial and risk management processes and systems. An adaptive programme should maintain the ability to change activity (beneficiaries/methodology, etc.) to adjust to different scenarios and reflect learning.

1. The preferred delivery option incorporates:
  1. A core programme, focussed on Options A - (52% of programme resource) and
  2. Option B - (25%), and
  3. A reserved budget line for:
    1. Option C - Sub-sector corruption analysis - enabling other HMG teams to ‘design-out’ corruption in their sectors/programmes. (4%)
    2. A responsive fund for unforeseen events or opportunities (10%)
  1. Programme-funded Governance Adviser plus FCDO MEL (9%)

Given the adaptive approach and requirement for ongoing evidence generation embedded within the programme, MEL will be delivered by the main managing agent, either directly or via an embedded consortium partner. The MEL provider will require experience of delivering research on governance, adaptive programming and PEA expertise. All delivery partners will have high technical expertise, thorough knowledge of the context, including influential relationships and credibility with the Government of Kenya and key local stakeholders and a track record of working adaptively. The ideal funding mechanism should allow quick mobilisation and subsequent amendments to the agreement, mechanisms to incentivise achievement of outcomes, and provide lessons on how to do this in the most economic and efficient ways. The Kenyan political system presents a challenging operating environment with levels of uncertainty and risk. With a novel programming approach, closer involvement by FCDO is necessary.

Non-contract delivery options such as MOUs or Accountable Grants will ideally allow for quick mobilisation and amendment of agreements, and greater control of allocation of inputs by FCDO.

Finally, FCDO programme-funded Governance Adviser is the proposed PRO for KISP and will lead implementation of the adaptive approach including - designing and adjusting meaningful results frameworks, providing thought leadership, logging lessons and decisions, informing key stakeholders, and disseminating lessons. The PRO will also coordinate cross mission collaboration while leveraging political and diplomatic influencing. They will engage in political influencing and collaboration with other development partners, government, private sector and other relevant stakeholders to influence policy positions. The PRO will be supported by two subject matter technical advisers (elections and anti-corruption), FCDO MEL adviser, FCDO contracted independent MEL consultant (5%) and the PMEL programme (20%).

Table 13 below assessed viable delivery routes and funding instruments, setting out requirements for success, pros, cons, and mitigation strategies.
Table 13: KISP delivery routes and funding instruments

	Requirements for success	Implementing partner best suited to deliver & why	Preferred Delivery Mechanism	Pros	Cons	Mitigations	Alternative delivery mechanisms discounted & why
Component A	(i) This component includes work on illicit finance and political corruption, and accountability through civil society. Ability to operate in a high-risk environment, where results are unpredictable. Flexibility to start, stop, drop workstreams. Provider needs to be insulated from political pressure. (ii) Includes strengthening electoral integrity and campaign finance. Requires relevant experience, track record & expertise in electoral operations, legal reforms and strengthening electoral integrity.	Commercial contract - expertise to handle complexities around countering illicit finance flows and the link to political corruption; and experience to handle political dynamics around elections.	Commercial contract	Access to highly specialised technical assistance (national and international), with experience in other similar contexts, and with adaptive programming Greater ability (than with all other funding instruments), to incentivise partners to deliver results - over relying on organisations' intrinsic motivation. Reduces fragmentation of workstreams if all are implemented under one agreement.	High cost (especially on fees and profits). Standard contract models are highly rigid, as legally binding and needing to align to UK procurement laws. More FCDO staff time required	We propose a hybrid contract structured to incentivise supplier to focus on outcomes, delivery, and to increase willingness to share risks with FCDO. Strong M&E component should run alongside it. Willing to trade off higher costs if this increases chances of successful delivery. Will conduct early market engagement during the procurement process to test	Non-contract funding options (AGs and MoUs) - limited organisations with combined experience of adaptive programming combining illicit finance, anticorruption and civil society engagement). Challenging to incentivise NGOs to stretch and deliver against objectives in case of dips in performance - no mechanism to link payments to results. NGOs usually not set up in a manner that allows them to price in and therefore take the scale of risk that may be needed on this programme.
Component B	Ability to work with political parties, politicians and citizens to focus on issue-based politics. Requires expertise in use of data to inform policy, and experience /knowledge of local political context and access to local political actors.
Component C - Design out corruption	This is sector-specific analysis - sectors where key FCDO programmes operate e.g. health, education, public service. Requires sector expertise, some ability to support implementation of the 'design-out analysis outcome', within an FCDO programme. Requires ability to mobilise sector specific expertise and systems analysis.	Consultancies with ability to mobilize diverse expertise in systems analysis to combat sectoral corruption.	Mix of low value contract and non-contract arrangements, including spending through other FCDO sector programmes	Allows FCDO adequate control, and ensures clear access and collaborative working with FCD sector programmes	Increases management burden for FCDO	Keep programme team, as described in the management section intact to the extent possible, for the duration of the programme. (i.e. 1*SRO, 1*PRO, 2*TA, 2*PM + TL, DTL, IF adviser)	Funds to be managed by managing agent under commercial contract above, or separate AG/MOU - not feasible as high degree of collaboration (potentially on sensitive issues) between KISP and other FCDO programme will be required.
D - Reserved fund	The fund should be easy to call on, to get new implementing mechanism. Likely small bits of work starting/stopping. Requires, high degree of control by FCDO preferred.	NGO - to enable flexibility and control by FCDO	Mix of low value contract and non-contract arrangements	Allows for FCDO decision-making on how funds will be spent; allows us to fund for work that is most appropriately funded by FCDO than by partners, including short-term catalytic support to unblock issues, or urgent pieces of work.	Increases management burden for FCDO	Some agreements could be transitioned to management by the commercial supplier above.	Funds to be managed by managing agent under commercial contract above, or separate AG/MOU - not feasible as some strands of work - especially around political access and influencing, most efficiently administered by FCDO. Also best to keep decision-making on the use of this fund within FCDO

A commercial contract, with reserved fund, is the preferred delivery route to implement the KISP programme through a flexible and adaptive model. Contracting a single managing agent (who can potentially lead a consortium/partnership to ensure the right technical expertise e.g. on adaptive MEL & PEA) will allow streamlined management of KISP to respond flexibly to the evolving demands of multiple and varied stakeholders and differing political economy contexts of different parts of the Kenyan political system. The reserved fund of £1.5M will be held by BHC Nairobi. This fund will allow further flexibility in delivery by enabling funding of ad hoc projects as the opportunity is presented.

Routes to market
The managing agent will be procured through a mini competition under the Global Development Delivery (GDD) framework agreement. The call-down contract will include a Terms of Reference setting out the results required, a financial proforma with a breakdown of costs, start and end dates, and copy of the Suppliers technical proposal.

Each bid will undergo a technical and commercial evaluation. Technical criteria will prioritise suppliers with expertise and capability to design and undertake an adaptive programme, operate in lower middle-income countries and deliver UK’s comparative advantage on political corruption programming and election support in Kenya. The ability to work flexibly, adapt to the different contexts and offer a range of innovative solutions and approaches to address Kenya’s systemic challenges will be critical. An outline criterion the Managing Agent will be assessed against is shown in Table 14.

Table 14: Outline criteria for selecting Management Agent
Criterion	Description
Geographic fit	Track record of designing and delivering high quality governance programmes in lower middle-income contexts with an emphasis on political corruption and election support. Track record of working in Kenya and understanding of its political economy and key actors related to anti-corruption and election integrity. Experience working with FATF grey-listed countries.
Technical expertise	Evidence of working in politically smart ways, including Thinking and Working Politically. A demonstrated ability to be flexible, responsive and adaptive with experience of designing, implementation and monitoring and evaluation of adaptive programming. Expertise in designing, implementing and measuring behaviour change is essential.
Leadership expertise	Within the leadership team – and in particular the Team Leader – a strong capability in understanding and engaging with the donor client, national government actors and key stakeholders. Expertise in participatory facilitation, strategic communications, collaboration and relationship building, ability to learn from failure, and a strong sense of adaptation and flexibility.
Complementarity	An ability to understand and ensure complementarity with FCDO country strategy, policy and programming. Compliments and extends the scope of existing UK and other development partners programming in Kenya. Builds on the achievements and lessons of past and recent governance and conflict-related programmes in Kenya. Draws on best practice from other programmes related to anti-corruption and election support.
Catalytic potential	Evidence of working on similar initiatives that have led to tangible ‘investment ready’ project pipelines of political corruption projects. Ability to identify opportunities and be innovative in programming, partnerships and MERL (monitoring, evaluation, research and learning). Equally, an ability to advise on areas to ‘drawback’ or ‘phase out’ funding, providing evidence to support decision-making.
Bankability	Track record of designing and implementing political corruption projects from inception to financial close, with credible operational and management models. Evidence of investment attraction/ experience of mobilising other sources of funding.
Operational model/focus	Partner ability to call-down or contact relevant skills at different stages of programme implementation (elections, legal sector, public services).

To strengthen delivery capability, framework suppliers will be allowed (with approval from the FCDO commercial lead) to add new sub-contractors or partners to their consortium for this mini competition. Bidders will be encouraged to engage local suppliers, NGOs or personnel, to enhance delivery, and as part of building sustainable supply chains in the countries where we operate.

The framework agreement includes a pre-agreed pricing mechanism (e.g. ceiling fee rates for specific categories of professional services), which will contribute to cost control. As the original framework award was competed under the procurement regulations, the mini competition will be carried out within significantly reduced timescales, and resource costs. The framework agreement will also have already pre-qualified the supplier(s) technical competence, to an extent. The process from issuing the invitation to tender to identification of the winning bidder should take around 12 weeks. In total it should be possible to award the contract via mini-competition in 16 - 20 weeks.

In parallel, the reserved fund will be implemented through a mix of low value contract and non-contract funding agreements. Specific and appropriate funding instruments and agreements will be used for each organisation (the World bank, UK and international framework organisations, NGOs, CSOs, think-tanks, UN agencies among others. Accountable grants may be awarded through a competitive bidding process, or in response to an unsolicited proposal. Direct awards will be in line with the compliance criteria set out in the PrOF. There will remain some uncertainty over the sourcing timelines and exact levels of disbursements, as these will be opportunity-led.

The programme will have 3 components with indicative budgets as shown in Table 15 below.
Table 15: Programme components and budgets

Inputs	Type of funding Instrument	Estimated Value	Approximate proportion of programme budget
1.1 Component A (RDEL): Strengthen accountability	Commercial contract with a Management Agent plus embedded MEL function	£7.32M	52%
1.2 Component B (RDEL): Support issue-based politics		£3.55	25%
Total Managing Agent Contract		£10.87M	77%
2.1 Component C (RDEL): Design-out corruption.	Fund managed by FCDO, implemented through low-value contract and non-contract options	£0.61M	4%
2.2 Reserved / Opportunistic fund (RDEL)		£1.5M	10%
3.1 FCDO Other (RDEL)	Prog funded GA post & Independent Evaluation)	£1.02M	9%
Total funds managed by FCDO		£3.13M	23%
TOTAL		£14M	100%

* These allocations are notional since funding for the core programme is intended to be flexible and adaptive

Table 16: Finance decision points

		Q1 25/26			Q2 25/26			Q3 25/26					Q4 25/26					Q1 26/27
		Apr	May	Jun	Jul	Aug	Sep	Oct	Nov		Dec		Jan		Feb		Mar		Apr	May		Jun

Decision	Amount
Approve full business case, and only £1m to be committed in FY 25/261.	1,000,000
Quarterly programme steering board - decisions on inputs and activities, approve accountable grants to undertake activities FY 25/26
Approve an additional commitment of 50% of components A & B to be committed in FYs 26/27 onwards.	5,435,000
1st programme steering board strategic review – evidence on contribution to outcomes & decisions on next FY’s strategy and activities
1st programme annual review - decision point2.
Approve commitment of full budget based on PSB strategic review & annual review.	7,565,000
	14,000,000

Given the new ODA constraints, we propose that KISP funding approval be done in stages as follows:
i). Decisions to take immediately in year one:
- Approve up to GBP1M of the reserve fund to finance urgent opportunities to strengthen accountability and issue-based politics. Prioritized interventions can be found in table 2.
- Accountable grants to a limited number of partners to be issued and managed directly by FCDO team.

ii). Decisions to delay to year two (2025/26 FY):
- Consider all components but scope of interventions to be determined by ODA allocations in the next FY.
- Procurement of management agent
- Hiring of the programme funded GA
- Design out corruption component
- Independent Evaluation
- Further future decisions points may be decided in year 2.

Performance Management
The managing agent’s performance will be assessed on their ability to deliver outcomes, rather than outputs. This will provide an overarching framework under which a programme team, implementers and beneficiaries can operate flexibly. Payments will be made via a hybrid model where payments will be pegged on a balance of:
  1. Achievement of outcomes, however, there should also be adequate evidence linking the suppliers’ activity with intended outcomes, which will ensure that there is sufficient incentive for the supplier to achieve results. This will allow adaptation within workstreams.
  2. A proportion of inputs (fees and expenses). While traditionally results-based payments transfer risk to the supplier, under KISP, these will be balanced adequately with input-based payments to maintain suppliers’ willingness to innovate.
  3. Key performance indicators – that will test ‘how’ the supplier is performing rather than ‘what’ results they achieve. These will measure how well the supplier tests key assumptions of the ToC, generates and uses quality evidence, especially being open about where things are not working.
Formal quarterly review points will be built in to ensure that payment milestones are still appropriate.

Payments under the reserve fund will primarily be based on inputs or outputs, as there is likely a higher need for actual cost recovery and outputs will be short-term, straight forward and easier to define. Programme-funded staff will be remunerated in line with FCDO’s pay and benefits policies. The staff will be held accountable for their contribution to the programme through both the FCDO performance management framework (with success criteria related to programme objectives), and through the programme results framework.

1. Reserved Fund operated by FCDO: We will conduct proportionate due diligence on any multilaterals or non-profit organisations before entering into Administrative Agreements (AA), Memorandum of Understanding (MoU) or Accountable Grants (AGs) through call for proposals. The FCDO programme team will oversee any agreements with technical support and advice from a Commercial Delivery Manager and Contracts Officer, with additional guidance from the Commercial team as needed.
2. Continued relevance and effectiveness of the programme is key to continued FCDO funding. The programme VFM framework will be reported against during annual reviews and key findings included in relevant analysis and used to drive improvements. Break clauses will be built into all agreements, at annual points, to allow opportunities to change direction, respond to resource availability, or terminate the programme early if not performing, or if it becomes unfeasible or results are not possible to achieve, or as expected based on evidence generated. Conversely, if with good performance and additional resource, the programme could extend in cost and time by up to 50% of current values. The managing agent’s contract will provide for this.

## D. Financial Case

The proposed budget is drawn from estimates from our experience implementing similar activities in ongoing programmes on elections and anticorruption. The allocation per workstream reflects the relative expected contribution of the workstreams to the outcome and expected levels of effort. The annual profile is based on knowledge of the context and timing of key events for the programme (e.g. spend is expected to peak closer to the 2027 Kenyan general election), the expected absorptive capacity of partners and procurement timescales. The figures will be refined further during the mobilisation, and after the inception phase. None of the funds will contribute to International Climate Fund (ICF) commitments – but the programme will be implemented to avoid contributions to climate change, and to safeguard the environment.

Appropriate break points will be reflected in funding agreements to allow scaling up, down or termination in response to the 0.3% ODA landscape over the next 5 years. An adaptive approach will inform the prioritisation of the workstreams to be scaled up or down in response to budget availability. Interventions will be designed and managed for sustainability, should early closure be necessary. This will include, but will not be limited to, integrating influencing, and collaborating with other donors. Two programmes in the portfolio closed by March 2025, which will also increase the available headroom for spend by KISP.

Table 17 outlines the indicative budgets for each component, which will be updated during the procurement, mobilisation and implementation phase. MEL activities are expected to commence at the start of project implementation.
Table 17: Indicative programme budget

Funds disbursal, reporting and controls on expenditure
For both contract and non-contract funding arrangements, budgets will be reviewed against workplans and milestones; administrative vs programme costs should be proportionate. Commercial contracts will be transparent on fees and profits.

The SRO will ensure that funds are disbursed in accordance with the signed agreements and contracts as per the different funding mechanisms and based on agreed milestones and performance indicators; appropriate risk mitigation; and satisfactory financial management, including forecasting and accounting for variances.
- For contracts, funds will be disbursed monthly or quarterly depending on agreed payment mechanism. We will work with commercial and finance advisers to further define how payments will be made to operationalise the hybrid contract described in section C.6 of the commercial case.
- Funds for non-contract funding modalities (MoU’s or AG’s) will be disbursed quarterly or bi- annually upon submission of a proposal (where applicable), budgets, progress and financial reports and forecasts. The FCDO programme team will conduct performance review meetings to discuss implementation progress, challenges and risks.

The PRO will apply standard financial monitoring, reporting and accounting arrangements to ensure funds are not disbursed in advance of need; and that each tranche is properly accounted for before new disbursements are approved. Implementing partners’ monthly and quarterly reports will include realistic spend forecasts and expenditure. The programme team will reconcile these forecasts against (i) relevant data on the financial management system; (ii) annual work plans and budgets; (iii) previous reports; (iv) annual and quarterly spending trends. As much as possible, partners will be required to adopt resource accounting budgeting to provide a closer link between workplans, forecasts and spend, while aiming for less than 5% variance on monthly and 1% variance on annual forecasts. Exchange rate gains and losses will be monitored by the programme team, and implementers will need express permission by the PRO to re-programme gains or losses.

The PRO will ensure that financial management, transparency and accountability systems of implementing partners meet HMG requirements, and that their risk mitigation measures, including to guard against Fraud and Sexual Exploitations, Abuse and Harassment, are sufficiently robust. Enhanced Due Diligence Assessments will be conducted on potential partners to assess their governance and internal controls, ability to deliver, financial management and stability, downstream delivery, and safeguarding controls. The programme team will take the necessary steps to ensure the programme adheres to the zero-tolerance policy on fraud and the UK Counter Fraud/Bribery and Counter Terrorism legislation and that all incidences of suspected/or alleged fraud is reported immediately to the Fraud Investigation team in the Internal Audit and Investigation Directorate (IAID).

The delivery chain is expected to be short with not more than 3 tiers of delivery, which should minimise risk. However, the programme team will work with suppliers to develop and review a delivery chain map at least quarterly and use it to inform a risk-based approach to managing financial and fiduciary risks. Partners will be required to provide annual independent assurances to FCDO, that funds have been used for the intended purpose through audits or audited financial statements. A rolling programme of spot checks will be conducted by the programme team or through third party service providers.

Partners will be required to maintain an updated register of all FCDO funded assets and provide updated registers annually. Assets acquisition, management and disposal will be done in accordance with the FCDO Programme Operating Framework (PROF) and seek to maximise value for money.

## E. Management Case
Strategic Oversight and Programme Governance
The SRO will work closely with the PRO, specialist advisers and the programme team to manage the programme and oversee its implementation in line with the FCDO Programme Operating Framework (PrOF) requirements. It will be important for the FCDO programme team and diplomatic influencing team work closely together drawing on their collective expertise, knowledge and networks. Applying, measuring and learning from FCDO’s political access and influence (PAI) through the engagement with KISP will add considerable value to the programme.

The governance structure of the programme:
1. A Programme Steering Board (PSB) will meet quarterly, be chaired by the PRO and include the FCDO SRO, MEL Adviser, the implementing partner and an independent contracted expert/ adviser. The role of the independent expert/ adviser will be to provide external challenge. The PSB will focus on immediate results (outputs) but with an eye on potential for longer term change (outcome results). Given the frequency of meetings and the fact that change takes time, it is expected that decisions made by the PSB will be at the level of inputs and activities, rather than outputs or other pivots to the overarching strategy (although the PSB would not be precluded from such if there was strong evidence). The PSB will also review overall programme finances, risks and lessons learned.
2. Once a year, the PSB will convene a more in-depth Strategic Review of the programme, in place of the quarterly PSB. The Strategic Review will be timed so that it can inform the FCDO Annual Review learning process. Participants will consider evidence produced by the programme to understand which activities and outputs are contributing to outcomes and to what extent. Additional participants would include academics, independent experts, FCDO High Commissioner and/ or Deputy High Commissioner, and other relevant FCDO experts as relevant (e.g. to diplomacy). It is possible that civil society organisations and government could be invited to part of the day but noting the issues around vested interests. The Strategic Review could be run over 2 days. The first day would be a broad forum for dissemination, but with lots of opportunity for discussion and suggestions for programme adaptations. The second day would convene only the PSB, who would be responsible for designing the workplan for the following year based on the content of the previous day and any other relevant evidence.

Figure III demonstrates how the governance structure would work in practice:

Process for identifying/ adapting activities and outputs

Figure III: Programme Governance process

The SRO and the PRO will ensure the PSB coordinates with existing platforms, including the anticorruption and elections donor working groups.
Management Roles and Responsibilities
Table 18 sets out who is responsible for what aspects of programme management
Roles	Department
0.2 X G7 Adviser (UK Based) - The 1st Secretary Internal Politics and Institutions will be the Senior Responsible Owner (SRO) - responsible for the programme meeting its objectives, achieving its outcomes and contributing to the Kenya Country Plan Goals on Open Societies and Democracy and to FCDO thematic priorities. The SRO will be responsible for strategic oversight, holding the programme team to account in ensuring effective delivery, and providing overall strategic leadership and high-level political and policy advice, decisions and direction.	FCDO (BHC Nairobi)
1.0 X G7 Programme funded Governance Adviser (CBS) - will be the Programme Responsible Owner (PRO). They will ensure that best practice and compliance are applied throughout the day-to-day management of the programme and will lead on the delivery of the programme outcomes, monitoring achievement of programme results, monitoring annual review and due diligence recommendations. The PRO will be supported by KISP technical advisers while working closely with the MA embedded MEL supplier to ensure evidence generation; communication and coordination; engagement with local stakeholders; and management of multiple levels of results frameworks to enable adaptive programming. The SRO will retain closer oversight to make key decisions and provide challenge on implementation.	FCDO (BHC Nairobi)
Multidisciplinary team of technical advisers including 0.8 X Senior Executive Officer Elections Adviser (CBS); 0.8 X Senior Executive Officer Anti-Corruption Adviser (CBS); 0.6 X G7 Illicit Finance Adviser (UKB); all combined with diplomatic influencing from the political counsellors and the BHC leadership including the deputy high commissioner and the high commissioner to ensure effective delivery of the programme. They will provide oversight and strategic advice to the Management Agent responsible for programme delivery in each of these thematic areas. They will also request specific programme evidence in their areas of interest. They will support the PRO in management of multiple levels of results framework and facilitating learning to enable delivery of adaptive programming.	FCDO (BHC Nairobi)
Two programme managers - 0.5*Senior Programme Officer (CBS, Higher Executive Officer), and 0.25*Programme Officer (CBS, Executive Officer), responsible for contract and day to day programme management. Supporting the PRO to manage finances, risk and compliance, and monitoring and evaluation.	FCDO (BHC Nairobi)
0.2 X Senior Executive Officer (CBS) Portfolio Manager – providing oversight on programme management functions, supporting the SRO, PRO and programme managers to maintain high standards in programme management.	FCDO (BHC Nairobi)
0.3 x Grade 7 Commercial Manager (CBS) during the first four months to provide support on the procurement process.	FCDO (BHC Nairobi)
Additional support to include: / support from FCDO 0.2* SEO MEL Adviser to set-up and lay foundations of MEL framework, provide oversight to the independent MEL advisory and link to the PMEL prog. / support from new FCDO 0.2* MEL Programme (PMEL) to provide data quality assurance. / 0.05* Independent MEL advice (consultancy) to support layout out of the MEL framework and provide independent data quality assurance / Gender Adviser, and the Economist	FCDO (BHC Nairobi)

Figure IV: Programme management structure

The CBS Governance Adviser / PRO will be the only KISP funded role; the rest of the team are a combination of UKB and CBS staff within the BHC.
1. To assist with the adaptive approach, the Management Agent will conduct day-to-day programme monitoring. The PRO, while supported by the Elections, Anti-Corruption advisers and 5% of independent MEL advice (consultancy), will provide oversight of the Managing Agent to ensure it is delivering against milestones and targets. This team will be supported by the FCDO SEO MEL Adviser to set-up and lay foundations of MEL process. The BHC-wide MEL supplier (PMEL) will provide some advisory and light touch review services at key points including data quality assurance throughout the programme. There is also an option to bring in EQUALS here to provide an evaluation quality assurance function.
2. The programme team will solicit beneficiary feedback on programme activities and outputs for robust evaluation and ensure that all parties are aligned on the reporting expectations and intended programme outputs and outcomes. FCDO will commission independent evaluation of the programme at midterm and end of the programme.
Contract and Agreement Management
The SRO and PRO will manage contracts and agreements in consultation with the Commercial Lead and FCDO’s Strategy, Assurance and Results team (StART). The central Commercial team, working with our Commercial Lead, will support on the sourcing for the management agent contract through the GDD Framework and all associated approval process through the Procurement Steering Board while other contract within our delegated authority will be managed locally.
Mobilisation and Start-up
On approval, the programme will commence Management Agent (MA) procurement process. This is expected to last around 12-16 weeks. Signing of contracts and agreements will be done at the appropriate level of delegated authority. It is anticipated that the programme will put in place some agreements by June 2025 and then be fully operational by August 2025 at the latest.

An inception phase will then follow for up to 9 months. The MA will establish itself in Nairobi, initiate relationships and begin delivery of initial activities. FCDO will work closely with the MA to develop an inception work plan, clearly outlining specific activities and milestones to be delivered through the adaptive approach. At the end of the inception phase, the MA will produce an inception report, outlining key lessons learnt, and which will form the basis for the programme implementation phase.

Monitoring, Reporting, Evaluation and Learning plan
1. The Managing Agent will be responsible for the delivery of MEL for learning, either directly or through an embedded consortium/ partnership to bring in the required skills. This will include delivering adaptive MEL (regular theory of change reviews, adaptive analysis as set out in the MEL Approach section below), PEA and/or other research and analysis required to steer the programme and inform decisions. Having the Managing Agent responsible for the delivery of MEL will ensure the focus stays on learning rather than accountability, it will also encourage openness and transparency and brings evidence closer to the implementers. A secondary benefit will be a reduction in transaction costs for the FCDO team and value for money since a separately contracted MEL would restrict budget lines (less flexibility to move budgets between implementation and learning) and potentially higher overhead costs.
2. The FCDO programme team including the PRO (GA), while supported by subject matter advisers (Elections and Anti-corruption), and the FCDO MEL Adviser, will lead MEL for accountability, developing the results framework in collaboration with the Managing Agent (to be finalised after contracting), ToC (reviewed during the inception phase) and value for money assumptions annually. This will be supported by monthly (financial) and quarterly (performance) reports from MA / delivery partners, interviews with key stakeholders and beneficiaries and as appropriate - field visits and generally leading data quality assurance.
3. The FCDO Portfolio Monitoring and Evaluation (PMEL) programme will support KISP MEL operations by providing assurance and evidence on what is working. A 5-days a month independent MEL advisory (consultancy) will be engaged to provide independent data quality assurance and advice. They will be procured through the PMEL programme. The FCDO MEL Adviser will provide oversight to the independent MEL adviser.
4. To ensure progress and effectiveness is independently assessed, a mid-term and endline evaluation will be separately procured by FCDO.
5. The FCDO programme team will provide guidance on integrating Gender Equality and Social Inclusion (GESI) indicators in line with the Equality Act 2010 within the results framework.
6. Apart from the quarterly programme technical board and bi-annual programme strategy board reviews, the FCDO programme team will conduct Annual Reviews and a Programme Closure Review at appropriate milestones during the programme lifecycle. Additional support will be requested through the 10% cadre option as appropriate.

What adaptive programming means for KISP
KISP is designed to be an adaptive programme, meaning that the programme design will evolve during implementation, based on evidence and learning emerging from the implementation. Figure V below shows the different elements of an adaptive programming approach as applied to KISP. This would allow for agility to changing political circumstances or personalities, new priorities or events, and if /how the approaches to TA and capacity building are working with different institutions. Recognising the complexities and uncertainties of tackling political corruption, we will expect the Managing Agent to adopt an approach based on ‘problem-driven iterative adaptation’, which requires: (1) a selective focus on actors and issues with political traction, (2) a clear understanding of the local political economy and networks of actors, (3) a willingness to experiment with a variety of intervention approaches, (4) well developed M&E systems to embed feedback loops and assess and use evidence, learn and results, and (5) strong management systems to adapt the programme design according to lessons learned and the changing political context.

Figure V: Adaptive programming framework
[note] Adapted from Christie, A & Green, D (2019)

KISP Programme Strategy Board Committee (bi-annual)
KISP Programme Technical Board (every quarter)

KISP Management Agent (1-3 months)

KISP FCDO leads
By applying this framework, we can look at the interplay between the different elements in adaptive programmes such as KISP:
- Adaptive delivery is the everyday work undertaken by those on the frontline (i.e. KISP’s Managing Agent TA experts) who are delivering governance programmes. They are working constantly with partners and individuals (particularly in government, political parties and civil society). They need to think and work politically, reacting and acting quickly and opportunistically.
- They are ‘usually’ supported – and possibly directed – by those who are at the Adaptive Programming end; these are usually the senior staff within the management agent at the HQ (e.g. KISP’s programme management based in Nairobi) and play a dual role of being informed by (and advise) the frontline staff and engaging, delivering and managing relations with and the demands of donor(s) and, if appropriate, national governments.
- The third element is Adaptive Governance which is usually the senior responsible officer in the donor agency (i.e. FCDO Kenya) who is responsible for programme funding and reporting upwards to more senior staff in the donor (both national HQ and home-based HQ). One of the critical pressures running through and linking each of these elements is getting the balance between ‘freedom to manoeuvre’ and ‘delivery of results.

MEL Approach
The underlying principle for data collection, analysis and learning approaches that will ensure successful adaptive programming for KISP include - timely and targeted evidence generation, and documenting and sharing learnings of success and failure, what works and what doesn’t. The Managing Agent will be responsible for generating and analysing data and evidence with periodic (quarterly) reviews on each programme workstream with the FCDO programme team (SRO, PRO and advisers). The PMEL programme will also provide data quality assurance. The following methods will be used and combined to support successful adaptive programming:
- Political economy analysis (PEA), that recognises differences in political economy in different though proximate locations at national and subnational levels, and on targeted issues and institutions. The PEA will engage FCDO to take account of FCDO’s unique position of bringing diplomacy and programme resource to deliver outcomes.
- Network analysis and/or systems map which looks on a regular basis, together with the PEA, at the relationship between actors within the overall political corruption ecosystem and a particular system related to a thematic area of focus.
  [note] As a good example of the use of network analysis in anti-corruption programming see ‘Evaluating anti-corruption agencies: learning from the Caribbean’, David-Barrett, Elizabeth et al (2020), https://doi.org/10.1080/19439342.2020.1745869
- Reflection sessions, at planned intervals (quarterly) and ad-hoc, across components and stakeholders.
- Monitoring and testing assumptions, and causal links in the ToC: as these underlying conditions may change rapidly in evolving and uncertain political contexts in Kenya with some links opening up opportunities, and other links being more constrained or broken requiring new thinking and intervention options. It is envisaged that the ToC will be reviewed and, if necessary, reconstructed on at least an annual basis.
- Use of the COM-B model (or an equivalent framework) to measure and demonstrate how the essential elements of behaviour change have occurred or not in key political actors and public institutions. It is important to understand and measure the key elements of behaviour change, in particular motivations of political actors.
- Use of local – and possibly remote – data collection for PEA and monitoring, e.g., civil society at local and subnational level to track different level results.
- Informal approaches and rapid sharing, e.g., for PEA or preliminary evaluation findings.
- Independent mid-term and final year reviews, evaluations / impact assessments that complement the rapid/reflective approaches to evidence generation. A separate independent evaluation provider will be tendered.

KISP will use an innovative approach to results measurement using, possibly, outcome harvesting, a behaviour change framework (i.e. COM-B or equivalent) and change stories (MEL). Outcome harvesting exercise will be conducted to extract results from beneficiary impact stories and quarterly progress reports through identifying the important changes that KISP contributed to and analysing these to show how “supply side” and “demand side” changes were reinforcing each other to drive deeper or more wide-reaching reforms.

KISP will also need to measure the added value of FCDO and BHC staff involved in the programme, both directly and indirectly. This could involve for example measuring the contribution of FCDO’s diplomatic efforts in delivering outcomes, use of evidence generated by KISP in political engagement and policy-making activities, how relationships are developed between Kenyan actors engaged in KISP and FCDO/BHC staff working on issues related to corruption and elections, and how FCDO/BHC are engaging with and influencing other donor partners working on similar governance programmes. KISP will need to use an innovative approach to measuring the UK’s added value of bringing together its programmatic and diplomatic expertise into the programme, possibly through a Political Access and Influence tool for example.

Reporting
Reporting on this adaptive programme will have to be analytical. This means reporting not just on results, but also on:
- the significance of the results (what they mean)
- the contribution of the programme to any changes recorded (in particular, if and how the interventions and outputs contributed to intermediate and long-term outcome-level changes)
- the contribution of the programme to behaviour change(s) in political leaders, political parties and public institutions, measured in terms of capability, opportunities and motivations
- the extent to which social norms related to political corruption have changed, and how the programme has made a difference or not
- the contribution of other agencies or factors, e.g. socio-economic or environmental
- lessons learned and possibly reporting on learning indicators
- measuring the progress towards achieving results (by using markers)
- assessing the robustness of the ToC, its causal pathways and assumptions
- measuring FCDO’s political access and influence on the individuals and institutions targeted by the programme
- required changes to the programme, based on the results and lessons learned, and how evidence has been used to feedback into re-programming; and
- reflecting on the strength and weaknesses of the evidence available
Adaptive Annual Review
Adaptive Annual Review approach – the programme will be assessed and scored against four separate performance areas as contained in table 20 below. The results framework will be designed to align with these four areas. The programme team will ensure that adequate evidence is generated and captured to enable effective assessment.
Table 19: Performance areas
Delivery	Using resources efficiently, and delivering any specific outputs that have been agreed, to the right quality, and in a timely fashion.
Actionable Learning	The generation and use of learning that can guide future action within the programme.
Contribution to Meaningful Change	Contribution to meaningful and sustainable change at different levels from immediate outcomes through to longer-term impact.
Fitness for Purpose	Based on the three other performance areas, an assessment of whether the approach is still the right one to achieve the programme goals.

Communications and Digital
The programme will consider building a digital platform to provide access to evidence and programme outputs suitable for public view. The programme team will consult the HQ Digital team in accordance with HMG guidance.
UK Partnership Principles
This programme does not involve direct payments to the Kenyan Government.
Risk Assessment

1. The overall programme risk is assessed as Major and is within the ’Receptive’ appetite agreed by BHC Nairobi for strategy and context. The programme has agreed the following risk appetites:
2. The overall risk appetite is ‘receptive’. This reflects a volatile operating environment, regional political tensions, and lack of will by the political elites and sub-national governments, that may disrupt programme implementation in some regions. We are willing to consider all programme delivery options and choose the one most likely to result in successful delivery and achieve value for money, even if some options carry a ‘major’ degree of residual risk. All risks are within the programme’s risk appetites in all categories.

The FCDO programme team recognises that residual risks are high for Kenya and require active monitoring, managing and mitigation actions. Each intervention will have a separate risk framework developed and monitored regularly. The risk matrix will be reviewed quarterly together with the implementing partners and adjusted accordingly and considered a living document.

Table 20: Risk Matrix
Description	Gross Risk Rating	Mitigation Strategy	Residual Risk
Strategy and Context: Risk Appetite - Receptive
Kenya’s high debt burden takes up GoK’s budgetary resources thereby Impacting GoKs’ ability to co-implement their Anti-Corruption and elections commitments supported by this programme.	Severe	Assess risks regularly; document and discuss at portfolio and programme meetings. Partners will be informed of FCDOs approach to risk and adapt programme as far as possible to emerging critical risks. / Monitor the context, only engage in activities with political traction, where there is demonstrated commitment by GoK in terms of allocation of financial resources. In parallel, with other DPs and programmes, advocate for budget allocations for critical processes.	Major
Polarised political context erodes government good will both at national and sub-national governments, especially towards 2027 general elections, thereby impeding Anti-Corruption and electoral reforms	Severe	We have started mitigating by collaborating with other Heads of Missions, CSOs, UN agencies and business organisations like KEPSA to push government to initiate reforms early within the electoral cycle. / Programme Team undertake activities to influence dialogue, understanding and shared incentives among local/national government.	Major
Category: Financial and Fiduciary
Weak financial systems and capacity at partner level leads to misappropriation and loss of FCDO funds	Major	We will conduct partner due diligence to ensure partners have effective systems and capacity to manage FCDO resources. / Proper monitoring of budget against the actual spend and monthly financial reports/statements. / Monthly finance meetings. / Partner training on FCDO finance processes (forecasting/ accruals/ pre-payments) to ensure proper reporting. / Delivery Chain required from suppliers to indicate funding cash flow/disbursement to sub-contractors. / MA will be required to conduct assessments on their downstream partners and follow through with outstanding issues for tighter controls. / Regular spot-checks both at MA and downstream partners levels. / Programme audits will be conducted as required. / Conducting regular beneficiary feedbacks.	Moderate
Reduction in ODA Resources does not allow for longer-term programming.	Severe	The programme will remain flexible to scale up or down, in line with funding uncertainties. It will also work within a portfolio of complementary programmes and use diplomatic levers to achieve its objectives to the extent possible under any funding scenario. / Establish relationships with donors, (e.g. World Bank) through contributing finances to their programmes. / Engage with HMT on post-2025 ODA spend early. / Increasingly using influencing approach to effect policy reforms and reducing provision of TA and training workshops.	Major
Policy & Programme Delivery
Due to the complexity of the problem to solve, and the novelty of an adaptive programme, there are risks of improper implementation of a properly adaptive approach.	Severe	We have invested in research and evidence to inform learning and programme adaptation. / We’ll hire 5% MEL consultancy, and a programme funded Governance Adviser with experience in adaptive programming to enhance team capability. This will be backed up by FCDO MEL Adviser and the PMEL programme. / We will form strong partnerships with GoK, other donors, private sector and citizen organised accountability groups to collectively push for reforms and complement each other’s efforts.	Major
Private sector not interested in investing in political reform opportunities due to limited incentives/ awareness of benefits thereby slowing down the reform process.	Moderate	Host meetings to raise awareness of programme objectives and benefits to not only the private sector but to the entire country. / We may consider changing the delivery model and work through AGs and MoUs if there’s no interest from the private sector.	Minor
Safeguarding
Partners have inadequate systems to prevent, detect or report potential safeguarding incidents.	Moderate	FCDO and Implementing Partner to carryout partner due diligence. / Ensure partners have Safeguarding Policy and trained staff on Safeguarding and how to report. / Include safeguarding in the agenda for risk register quarterly discussions/ meetings. / Use Third Party Monitors to carry out verifications of partners system.	Minor
Failure to establish and maintain strong safeguards to prevent harm to beneficiaries of our programmes, staff and those implementing our programmes, the communities where we work, or the environment, resulting in ethical violations and reputational damage .	Moderate	Partners to enforce FCDO aligned SEAH policies across the delivery chain and hold awareness and training workshops as needed where direct contact with vulnerable communities is expected. / FCDO programme team to promptly report any cases to investigation unit for investigation and action. / Ensure Supplier has Code of Conduct outlining measures for minimising and addressing safeguarding risks/cases. / City stakeholders to take initiative to introduce vulnerable communities and to the safeguarding policy and reporting.	Minor
Reputational
Irregular funding results in ad hoc delivery, damaging the UK’s reputation.	Moderate	Protect UK reputation by ensuring funds are available and co-finance programmes with other DP and WB to ensure the delivery is guaranteed. Manage expectations early with key stakeholders.	Minor
Risk of perceived partisanship by working with political parties under workstream on supporting programmatic politics	Major?	Protecting UK reputation by ensuring transparent communication to the public about all our programme activities with political parties. / Our work will target political parties from across the political divide and we’ll not display any form of biasness.	Moderate
People
Programme team have limited capacity to deliver high value impact.	Moderate	During the workforce plan will ensure a proper balance between advisory and programme management support.	Minor

ANNEXES

Annex A: Potential use of the COM-B Model as a key framework for KISP

This model is drawn from the REINVENT review (June 2024) which, as discussed, looked at the REINVENT programme through a behaviour change lens or framework. The following are potential areas as to how it could be applied to KISP together with specific evidence coming from the REINVENT review.

Figure VI: Behaviour Change COM-B Model
Capability – is concerned with how political leaders or heads of public institutions could lead a reform process within their political party or public institution respectively. For KISP, a potential change in capability to enact a behaviour change could be that EACC has developed its capacity to strengthen its independent oversight role in combating corruption or a Kenyan political leader has championed a reform process within his or her own party to restrict gifting practices. An example from the REINVENT programme is how key actors had increased knowledge to engage on people-centred approaches to policing, but their opportunities to speak about police reform were limited to ‘closed’ spaces to engage others as the public or more openly political spaces were more restrictive. Another positive example is how REINVENT enabled key actors to develop strategies and policies that support people-centred policing which in turn provides an opportunity for police reform.

Opportunities – is concerned with what opportunities are present that can enable a change in behaviour. The last elections in Kenya showed a shift towards Issue-based politics and away from clientelist politics, presenting an opportunity for how political parties could operate in the future. For KISP, a potential opportunity to enable a behaviour change could be that the EACC earmarked specific resources to implement rules and sanctions on politicians found to have breached illicit finance legislation or that citizen actions calling for good governance have created a social opportunity for politicians to respond and act favourably to their demands. An example from the REINVENT programme relates to an opportunity showing how state and non-state actors are more willing to work together on issues of security, specifically in relation to developing early warning systems. At a societal level, REINVENT has increased opportunities for victims and defenders of Sexual and Gender Based Violence (SGBV) to discuss issues and create safe spaces for survivors. This could be seen as both a capability (i.e. the capacity of survivors to voice their rights has been built) and an opportunity (i.e. the opportunities for them to have the space and support have been created).

Motivations – these are much more challenging to define but it is recognised that a particular behaviour will occur only when a key actor (or actors) concerned has the capability and opportunity to engage in the behaviour and is more motivated to enact that behaviour than any other behaviours [1]. Motivations can be either reflective involving a conscious thought process (e.g. plans and evaluations) or automatic that involves habitual, instinctive, drive-related and affective processes (e.g. desires and habits). For example, REINVENT showed how key stakeholders (‘champions’) in the Ministry of Interior and their implementing partners are more motivated to take on people-centred, democratic approaches to policing. This could be seen as reflective motivation as well as their improved capability. It is recognised that even with a well-designed behaviour change programme, achieving sustainable behaviour change in Kenyan actors will be a challenge as noted in the REINVENT review. It means identifying key influencers who are Kenyan actors as well as those to be influenced by behaviour change.

Annex B
Possible criteria for selecting interventions could include:
- A clear focus on the opportunity or issue to be addressed and the stakeholders who are involved.
- There are recognised ‘champions’, ‘spoilers’ and ‘influencers’ to reform or change processes.
- The capabilities and motivations of key stakeholders are identified and understood.
- The opportunities presented by the issue to be targeted are identified and understood.
- The ‘champions’ for a change or reform process can be identified, and an analysis of their power and influence.
- The incentives and disincentives for a change are clearly expressed.
- The ‘spoilers’ can be identified, and the ways to influence them or negate their effects.
- There is evidence of internal support within the institution or political party for change.
- There is evidence of external popular support or pressure for a change.
- The ‘influencers’ can be identified, i.e. Kenyan actors who will manage and sustain behaviour change efforts.
- There is an established relationship with KISP; programme staff are known and trusted.
- Solutions proposed are bespoke and locally-led, and not centralised blueprints.
- There are ways to gather evidence, monitor progress and measure impact.
- The role of FCDO/BHC staff and their potential added value in the intervention is recognised.