Basic Information

Programme name	KENYA INSTITUTIONAL STRENGTHENING PROGRAM (KISP)
Programme number	301505
Programme description	The Kenya Institutional Strengthening Programme (KISP) aims to work closely with Kenyan public-accountability institutions and civil-society partners to address political corruption and strengthen governance across multiple fronts. These include anti-corruption, public-finance integrity, transparency, accountability, electoral integrity, and efforts to curb illicit financial flows (IFFs).

Impact

Impact statement	Indicators	Source	Baseline	Target [date]
Reduced corruption and illicit finance in Kenya’s political system.	1. Kenya’s score on key governance indices (Corruption perception index, effectiveness of electoral processes, money laundering)	Periodic TI CPI score reports. / WGI- worldwide governance indictors WGI Kenya – World Bank / Mo ibrahim governance index IIAG Kenya – Mo Ibrahim Foundation / Afro- Barometer - Afrobarometer Kenya / EACC – National ethics and corruption survey / EACC NECS 2024 Report (PDF) / V-Dem electoral democracy index v-dem.net / Basel AML index Basel AML Index OR Basel AML Index Ranking	CPI :31 (2023) / WGI - Voice & Accountability -0.36 (2023) / WGI - Political Stability -1.12 (2023) / WGI - Government Effectiveness -0.35 (2023) / WGI - Rule of Law (-0.61 (2023) / WGI - Control of Corruption -0.72 (2023) / Mo Ibrahim Index (IIAG) 51.0 / 100 (2023) / Afrobarometer - low trust in institutions, rising corruption (2023) / EACC - Bribery Prevalence 52.1% (2024) / EACC - Average Bribe (KES) 4,878 (2024) / V-Dem Electoral Democracy Index Grey zone regime / Score: ~0.45 (2024) / Basel AML Index 6.87 / 10 (High risk) (2024)	CPI score higher (closer to global average), -45 / Systemic efficiency and accountability; Public opinion surveys show majority perceiving government/public servants as more accountable.
Outcome

Outcome statement(s)	Indicators	Source	Baseline	Target / (Mar 2026)	Target / [Long term/ Five years]
Outcome 1. Reduced opportunities and incentives for corruption and illicit finance in Kenya	Kenya’s progress in implementing FATF Standards.	FATF	Kenya currently in the FATF Increased Monitoring List (“grey list”) / FATF evaluations and action plans	Kenya makes progress in grey list Action Plan areas / Improved mechanisms & use of better strategies to deter irregularities, non-compliance & corruption incentives	Kenya’s sustained compliance with FATF Standards. / Risk of money laundering in high-risk sectors (e. legal, real estate, accountants, precious metals) is reduced
	Compliance rate with key public accountability and anti-corruption measures.	Wealth declaration	Low usage and verification of wealth declarations	Increased usage and verification of wealth information by public servants.	Corrupt politicians and public servants losing/blocked from getting jobs. / Wealth Information is being used by citizens and civil society to hold public servants to account.
		Integrity Rules Against Corrupt Politicians	Few actors sanctioned		30% of politicians who violate electoral, or political conduct rules are sanctioned.
Outcome 2. Kenya’s / political system is more issue-based and benefits all citizens	2.1. Number/ type of adaptive shifts in policy priorities, party platforms, or campaign strategies in response to evidence and citizen priorities.	Media sentiment analysis	TBD	Early signs of issue-based discourse; #party responsiveness to citizen feedback or evidence	The Culture of Kenya’s / political system fully embraces issue-based politics
	2.2. % change in citizen trust/confidence in electoral Institutions (including political parties, IEBC, ORPP, Judiciary etc) and processes	Afrobarometer 2022 / Survey-based trust levels (ELGIAs PEA by Infotrack)	IEBC trust-35% / Political Parties-20% / Judiciary-55%	Some improvement in perception surveys to Electoral Institutions / IEBC-40%, Political parties-25%	Higher and sustained trust/confidence in Election institutions across demographics
		Voter registration & turnout levels	64% voter turnout in 2022	TBC
Outcome to impact assumptions	Political will sustained due to FATF pressure. / Civic Pressure is sustained.

Output

Output statement(s)	Indicators	Source	Baseline		Target / (Mar 2026)	Target / [Long term/ Five years]
Output 1. Strengthened legal & policy frameworks and processes to tackle corruption & illicit finance	1.1 Progress in legal and policy reforms initiated, passed, or implemented with KISP support targeting corruption and illicit finance	Parliamentary records	Legal & administrative framework for combating Corruption and illicit finance not achieving results citizens expect.		At least 2 legal and policy reforms progressed with KISP support (trust administration bill and regulation, wealth declarations, Cconflict of InterestI regulations)	Better coordination, adoption of improved mechanisms & use of better strategies to deter irregularities, non-compliance & corruption incentives. / Robust anti-corruption &BO framework fully enforced
		e.GP System	15% procurement digitized		Increased compliance, implementation, and use of eGP system by procuring entities (based on % of public procurement transactions processed via e-GP) / 30% procurement via e.GP	Sustained compliance, (implementation and use of eGP system by at least 60% of procuring entities
		Integrity vetting	Limited vetting of candidates		An Integrity vetting framework that secures buy-in from implementing institutions.	Electoral system consistently blocks corrupt candidates
	1.2. Compliance rate with beneficial ownership standards	FATF MER / National risk assessment on money laundering and terrorism financing of legal persons/ arrangements report / OGP NAP 5	Kenya rated as having low level of effectiveness for IO5 (FATF MER 2022) / User compliance levels with BO laws in Kenya below 50% (OGP NAP 5)		Gradual increase in compliance with BO standards by users and BRS / BO risk assessment tools developed and adopted by BRS and stakeholders / BRS increases its stakeholder engagement initiatives to build awareness on BO standards. / BO register/records management protocols and tools are enhanced and deployed.	Effective BO systems / Real-time access of verifiable beneficial owners’ information by competent authorities. / User compliance to BO standards >70%
	1.3 Actions taken to prevent the misuse of high-risk sectors for money laundering and corruption	National Risk Assessment Report / BRS report / PWC Kenya Digest	Few actions taken		Governance review of high-risk sector completed with recommendations agreed by key parties.	Substantial cumulative progress to implement FATF action plans on BO and high-risk sectors. / Increased number of regulated professionals sanctioned.
	IMPACT WEIGHTING – 20%
Output 2. Improved governance & integrity of electoral processes & practices	2.1. Progress of legal and policy reforms initiated, passed or implemented with KISP support related to improving electoral integrity.	KISP progress reports	Weak enforcement: reforms stalled post 2022		At least 2 Electoral reform proposals drafted with KISP support (campaign finance, vetting framework, boundary delimitation).	Endorsements of Kenya’s electoral governance & practices by both domestic and international observers / Legal and policy frameworks reviewed and enforced including (Election Campaign Finance, Election Offences, Boundary Delimitation, Referendum, Political Parties amendment bills) / Merit based system for appointments that is not politically influenced.
	2.2. Credibility of electoral operations, management, and dispute resolution	PEA (2025) / ELOG report / ELGIA report / IEBC reports / Observer reports	Credibility challenges persist due to limited transparency in processes, inconsistent enforcement, and low public confidence in institutional impartiality.		Comprehensive Training/Induction of new IEBC Commissioners is completed. / 2027 General Elections Operations Plan (EOP) is developed and adopted by IEBC. / IEBC completes and adopts a Comprehensive Election Technology Audit ahead of the 2027 General Election. / Electoral dispute resolution plan developed and adopted by Judiciary Committee on Elections / IEBC MOU with the media reviewed, signed, and adopted. / IEBC communication and stakeholder engagement strategy revised, adopted, and understood by IEBC officials. / IEBC Strategic plan (2024-2029) reviewed and validated. / IEBC 2027 General Election Information and Technology Plan reviewed	Credible 2027 elections endorsed by local and global observers. / Positive assessments of the integrity of elections processes and management / Effective and timely EDR process / Effective public engagement, communication, and meaningful consultation by electoral institutions
	IMPACT WEIGHTING - 25 %
Output 3. Enhanced capacity for issue-based engagement and holding power to account.	3.1. Extent of shift from personality and ethnic-based politics	Perception surveys	Dominance in ethnic/personalised politics		(Shift not likely to happen by March 2026)	Politics largely driven by inclusive, national, and issue-based agendas
	3.2. Number of political parties or candidates that co-create manifestos with citizens and civil society	Political parties’ manifestos	Few/none co-create manifestos		A joint “Issues-Policy brief” for inclusion in the Manifestos of the Political Parties developed.	At least 50% of published manifestos for targeted candidates and political parties/coalitions are citizen informed (a head of 2027 elections).
	3.3. Level of citizens, civil society and private sector engagement in policymaking and demanding Accountability		Fragmented engagements		More frequent and quality youth engagement in economic governance / 1 youth led policy reform proposal submitted to parliament, political parties	Citizens across the demographics drive systemic accountability reforms and policy discourse.
	3.4. Number of KISP’s evidence-based recommendations referenced in parliamentary submissions, committee reports, policy briefs, or manifestos.		0		Key parliamentary committees’ reference at least one KISP supported evidence in policy/ legal reforms.	Evidence driven policy making installed
	IMPACT WEIGHTING - 40%
Output to Outcome assumptions	EACC enforces Wealth declaration on Laws: OAG/COB independence holds. / Procurement reforms not blocked. / Political parties open to reforms / IEBC/ORPP remains independent enough to deliver their mandates / CSO’s sustained civic engagement / Parliament passes key reforms. / BRS has capacity to manage BO register. / Media and CSOs operating environment is not restricted by government / ORPP enforces compliance by political parties. / Parties willing to engage citizens. / Citizens actively participating
Monitoring / evaluation questions	Questions / Anticorruption and countering illicit finance / What unexpected challenges or innovations are shaping anti-corruption efforts? / Are institutions more transparent and accountable? / What factors are influencing shifts in public trust across demographics?			Method / Anticorruption and countering illicit finance / Key Informant interviews with EACC, OAG, CSOs and donors; policy tracking and periodic learning workshops / Review of OAG/COB audit reports, BO compliance data, wealth declaration records; citizen perception surveys; scorecards tracking institutional transparency / Afrobarometer/Infotrack surveys disaggregated by age, gender, region; FGDs with Gen Z, women and PWDs.
	Improved Electoral integrity. / Are political actors shifting toward issue-based platforms? / How are electoral institutions adapting to civic pressure or reform demands? / What new practices are emerging in campaign finance enforcement?			Improved Electoral Integrity / Analysis of party manifestos, campaign speeches, and media coverage; citizen dialogue feedback sessions / Policy reviews; Institutional assessments of IEBC/ORPP; KIIs with CSOs and election observers / policy review of CF regulations; monitoring CF disclosures; studies of enforcement actions
	Shift to Issue-based Politics. / Are citizens and civil society more engaged? / How are Gen Z and other underrepresented groups shaping political agendas? / How are citizens using publicly available data to demand accountability? / What factors are influencing behaviour changes in the political system and institutions			shift to Issue-based politics. / Tracking public participation levels and civic actions developed and submitted. / Analytics of social media campaigns driven by youth (hashtags, online mobilizations) FGDs with SIGs coalitions and tracking Gen Z led civic initiatives. / Usage analytics from civic tech platforms (e-GP, BO register, watchdog apps); case studies of citizen-led accountability campaigns, media coverage analysis

KISP SCORING APPROACH
Performance area	Weighting
Delivery - Using resources efficiently, and delivering any specific outputs that have been agreed, to the right quality, and in a timely fashion.	Output 1- 20% / Output 2 – 25% / Output 3 – 40% / Total = 85%	A++ Substantially exceeding expectations / A+ Moderately exceeding expectations / A Meeting expectations / B Moderately not met expectations / C Substantially not met expectations
Actionable Learningi - The generation and use of learning that can guide future action within the programme. / ** advisable that scoring is restricted to planned structured learning	10%	A++ The programme has effectively generated reliable learning that has been used both within and outside the programme / A+ The programme has effectively generated reliable learning in a regular and systematic way, and has used this to guide action within the programme / A The programme has generated reliable, planned learning to guide action in within the programme / B The programme has not generated planned learning to a sufficiently high standard / C The programme has not generated any actionable learning or has not followed through on plans to generate learning or has made significant changes without using evidence to inform them
Contribution to Meaningful Changeii - Contribution to meaningful and sustainable change at different levels from immediate outcomes through to longer-term impact. / * Measuring progress towards contribution to outcomes	5% / Total = 100%	A++ The programme is substantially above a trajectory to achieve the desired outcomes with a wide range of strong evidence to support the change / A+ The programme is above a trajectory to achieve the desired outcomes with strong evidence to support the change / A The programme is on course to achieve the desired outcomes and has supporting evidence / B The programme is below the trajectory to achieve the desired outcomes and evidence to support change is ad hoc and contradictory / C The programme is substantially below the trajectory to achieve the desired outcomes and weak evidence to show any meaningful change
Fitness for Purpose - Based on the three other performance areas, an assessment of whether the approach is still the right one to achieve the programme goals.		Not to be scored but reflected in AR narrative

Programme Strategies or Activities

Indicative Strategies / activities	Milestones
Output 1: Strengthened legal & policy frameworks to tackle corruption & illicit finance
Technical Assistance to BRS and Legal sector (LSK) / Monitoring BO register usage / Support Advocacy coalitions for reforms. / Facilitate policy reform drives targeting Campaign Finance transparency and oversight. / Policy engagement on transparency in debt procurement and reporting / Development of a communications and change management strategy document on E-GP / Engagement of the CoG on adoption of E-GP by the counties.	At least 3 capacity building sessions held with BRS &LSK; compliance guidelines developed and disseminated. / Annual monitoring reports published on BO compliance; BO data accessed and verified by CSO, /oversight bodies. / At least 2 national-level advocacy coalitions established and actively engaging policy makers. / Draft Campaign finance oversight bill developed and tabled; at least 2 public dialogues held on campaign finance reform. / Resolution by the public debt and investments committee to develop rules for debt reporting. / 1 strategy document on E-GP / Resolution by CoG to work with counties to accelerate adoption of the E-GP platform.
Output 2: Improved governance & integrity of electoral processes & practices and Out put 3: Enhanced capacity for issues-based engagement

Support Chapter 6 vetting framework / Support legal reforms on Campaign finance disclosure. / Support Observer engagement platforms. / Train IEBC/ORPP officials on election Integrity / Conduct comprehensive Training/induction programme for the IEBC commissioners. / Technical assistance to IEBC in development of institutional policies	Vetting framework validated and adopted. / Campaign finance disclosure regulations passed / At least 2 pre-and post-election observer dialogues facilitated. / At least 200 officials trained on Integrity, compliance, and dispute resolution standards. / All the 7 IEBC commissioners undertake the program. / At least 3 IEBC institutional policies developed
Facilitate citizen - party dialogues. / Develop policy briefs for Manifestos. / Develop Digital tools for citizen feedback. / Use of macro-economic analysis to raise economic literacy as a foundation for issue-based engagements. / Media engagements to disseminate KISP program outputs and elevate fiscal policy discourse. / Analysis of budget documents (BROP, BPS & DORB) highlighting insights/proposals towards reduction in corruption, wastages, and fraud, as well as foster public education. / Empower youth with knowledge to engage in public policy discourse and processes to demand for financial transparency and accountability. / Develop a public debt and expenditure clock to enhance literacy on Kenya’s public debt. Support Civic coalitions. / Conduct trainings for media actors on safety and ethical reporting.	At least 10 structured dialogue forums between parties, CSOs and citizens held. / At least 200 youth and Women leaders trained and engaged in political issue-based discourse. / At least 2 evidence-based policy briefs produced and referenced in party manifestos. / At least 1 digital platform/apps launched for real-time citizen feedback and party accountability. / Increased public and CSO discussions on macro-economic issues, evidenced through sentiment analysis and uptake in policy dialogues. / Four op-eds published to shape public discourse and influence policy narratives. / An annual national youth dialogue conference convened to provide a platform for youth-led policy debate and engagement with decision-makers. / At least one youth-led policy reform proposal developed and submitted. / At least 5 coalitions formed/strengthened with clear reform agendas. / At least 4 nationwide accountability campaigns conducted (media, petitions, marches) / At least 100 journalists trained on investigative reporting, safety, and ethical standards.

KISP Pathways for Transformational Change

Anticorruption and Countering Illicit Finance		Improved Electoral Integrity	Shift to Issue-Based Politics

Outcome Challenges
High levels of public funds lost to corruption as flagged by oversight institutions (OAG, COB). / Weak legal and policy frameworks for combating corruption and illicit finance. / Low compliance with public accountability measures, including wealth declaration and procurement transparency. / Limited enforcement of Beneficial Ownership (BO) regulations and misuse of legal persons for money laundering. / Fragmented civil society engagement in demanding accountability and influencing policy. / Limited use of digital tools (e.g., e-GP system) for transparency in procurement.		Stalled or weak enforcement of electoral reforms, especially post-2022. / Low public trust in electoral institutions such as IEBC, ORPP, and political parties. / Limited vetting and disqualification of candidates based on integrity standards. / Few sanctions against political actors violating electoral conduct rules. / Lack of transparency and credibility in elections, as perceived by voters and observers. / Weak campaign finance disclosure and enforcement mechanisms. / Stakeholders and Partners	Dominance of ethnic and personality-based politics over issue-driven platforms. / Low citizen engagement in political discourse, especially among youth and marginalized groups. / Few political parties adopting voluntary integrity standards beyond legal requirements. / Limited co-creation of manifestos with citizens and civil society. / Minimal reference to evidence-based recommendations in political submissions and manifestos. / Low usage of civic tech tools for feedback and accountability in political processes.
Public oversight institutions: Office of the Auditor General (OAG), Controller of Budget (COB), Ethics and Anti-Corruption Commission (EACC) / Legal and regulatory bodies: Parliament, Business Registration Service (BRS), Law Society of Kenya (LSK) / Civil society organizations (CSOs) and media / Donor and development partners / Private sector actors		Electoral institutions: Independent Electoral and Boundaries Commission (IEBC), Office of the Registrar of Political Parties (ORPP), Judiciary / Political parties and candidates / Election observers / Civil society organizations (CSOs) / Media / Citizens / Private sector actors	Political parties and candidates / Citizens (especially youth, women, Gen Z) / Civil society organizations / Media platforms and civic tech tools / Private sector actors
Progress markers
Activity	Expect to See	Like to See	/ Top ambition/Want to See
Anti-corruption and Counter Illicit Finance
BRS and Beneficial Ownership (BO) Compliance	Gradual increase in BO compliance / BO Register is working	Accurate information on their beneficial owners is readily available to competent authorities.	Full transparency and real-time access of beneficial owners’ information. / Legal persons or arrangements are prevented from misuse for money laundering; less incentives to use corporates.
Wealth declaration process	Full compliance and disclosure of complete wealth information with the system, institutions and civil society checking the information, creating literacy around those issues.	Action taken based on wealth declarations; EACC beginning criminal investigations, prosecutions and asset seizures based on wealth information; civil society demanding accountability; people not voting for those individuals; being part of decision-making process of citizen voting preferences people prevented from working in public service; citizens asking about appointments to civil	Corrupt Politicians and public servants are not getting/ losing jobs. / Wealth Information is being used by citizens and civil society told public servants to account. / Discouraging public servants from committing corruption.
Leadership vetting framework	Information from public being utilised for vetting; transparent vetting criteria; vetting system considers all sources of information relating to vetting criteria.	Merit based system for appointments that is not politically influenced.	Appointments credible leaders that uphold integrity and not driven by political factors;
Electronic Government Procurement (eGP) and Public Procurement Reform	Public case for eGP is understood by citizens and public servants.	Less leakage of public funds, increased efficiencies / Proper use of public funds / Full functioning working eGP system. / full compliance, implementation, and use of eGP system by all procuring entities, no manual usage, (advocacy around changing the act so no manual usage), no discretion.	Systemic efficiency and accountability / Improved public service delivery. / People trusting government more. / In every financial year, commitments to pending bills should be budgeted;
Misuse of High-Risk Sectors	Basic understanding of the issues across sectors and how high-risk sectors are contributing to IF/AC in country; recognition within sectors and citizenry that there is an issue. / Initial safeguards introduced in high-risk sectors to prevent money laundering (IF/AC), including for example strengthened system that identifies/ manages use of client money.	High risk sectors demonstrate emerging accountability by adopting risk-based safeguards, initiating compliance protocols and collaboration with oversight bodies to prevent ML / Increased sanctions on private sector actors in the high-risk sectors (e.g. lawyers, accountants, real estate agents) . / Complaints being acted upon through formal disciplinary mechanisms; backlog of complaints reduced. / complaints mechanism incentivizing private sector actors to behave differently. / Private sector actors being proactive in terms of holding their fellow professionals to account.	High risk sectors are accountable, transparent, reliable, integral and don’t participate in money laundering.
Improved Electoral Integrity
Citizen Trust/ confidence in Electoral Institutions (including political parties, IEBC, ORPP, Judiciary etc)	Slight improvement in perception surveys to Electoral Institutions / An effective strategic communication and stakeholder engagement strategy implemented.	Noticeable rise in public trust/ confidence in Election institutions	High and sustained trust/confidence in Election institutions across demographics / Periodic engagement platforms between the commission and the citizens
Legal & Operational Framework	Legal and policy reforms initiated or under review to eliminate loopholes in the electoral process. / An effective operation plan/ framework in place and operationalised	A robust legal and operational framework supports credible 2027 elections.	Sustained legal integrity beyond 2027 elections.
Capacity to Deliver Credible Elections	Basic operational readiness for elections	Positive assessments of the integrity of 2027 elections by observers	Strong endorsements from both domestic and international observers
Integrity Rules Against Corrupt Politicians	A legal framework and rules on vetting process of candidates that prevents corrupt candidates from vying for elective positions	Enforcement of integrity rules- Fewer corrupt candidates elected	System effectively blocks corrupt individuals from office
Campaign Finance Regulation	Draft legislation or discussions	Enactment and partial implementation	Full enforcement and public reporting
Inclusive political participation	Periodic engagement platforms between the commission and the citizens / Organised citizen groups in the electoral process	Increased participation (voter turnout) and representation of women, youth/Gen Z, PWDs in the electoral process	Full inclusion of women, youth/esp. Gen Z, PWDs in decision-making processes
Independence of Electoral Institutions	Corporate governance in decision making and operations show autonomy.	Increased stakeholder and citizen engagement and trust in electoral bodies	Institutions operate independently with high public confidence
Towards issue-based politics
Shift from personality and ethnic-based politics	Early signs of issue-based discourse / Dialogue platforms towards development of issue-based manifestos	Issue based manifestos and campaigns. / Some politicians campaign on issues	Culture fully embraces issue-based politics. / Politics driven by inclusive, national agendas
Evidence- based Political Agendas	At least 5 parties mention evidence generated by KISP in manifestos	Parties develop consistent policy platforms	Leadership prioritizes evidence-based policies
Transparent & Inclusive Political Culture	Initial efforts toward transparency	Inclusive platforms and public engagement	Institutionalized accountability and openness
Rule-Following Political Behaviour	Politicians begin adhering to rules	Increased compliance with political norms	Compliance with rules becomes standard political practice
Citizen Demand for Accountability	Citizens raise service delivery concerns	Organized reform movements emerge	Citizens across the demographics drive systemic accountability reforms
Trust in political system	Slight increase in public confidence	Citizens and civil society engage more in policymaking.	High trust and legitimacy of political system