## 2025 Annual Review - RUSH

Title: Reforming the United Nations System – Humanitarian (RUSH)
Programme Value £ (full life): £324 million		Review date: 01/11/2025
Programme Code: 301509	AMP start date: 03/04/2023	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Logframe

## A: SUMMARY AND OVERVIEW

Context

This is the third Annual Review of FCDO’s Reforming the United Nations System – Humanitarian (RUSH) programme, which began in April 2023, and will conclude in March 2026. There are some important contextual points which should be considered when reading this review:

Humanitarian Situation

Global humanitarian need remains high, driven by conflict, climate change, and governance failures. By the end of 2024, 305.1 million people needed humanitarian assistance, and 78% of civilian fatalities in conflict came in countries with a humanitarian plan or appeal[1]. Around 1 in 5 children in the world – approximately 400 million – are living in or fleeing conflict zones[2]. Conflict and crises are increasingly trapping marginalised people, in particular women and girls, in cycles of vulnerability, leading to high rates of gender-based violence, child, early and forced marriages, exclusion from education and preventable maternal deaths.
[1] Global Humanitarian Overview 2025.pdf
[2] Global Humanitarian Overview 2025.pdf

Global humanitarian funding has not kept up with rising need, and the humanitarian system is under significant pressure; by the end of November 2024, only 43% of the UN’s $49.6 billion USD funding requirement had been met[3]. A number of donors have implemented or signalled future funding reductions during 2025, including the UK[1].
[3] Global Humanitarian Overview 2025.pdf
[1] At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister took the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.

As this Annual Review covers activities in 2024, funding reductions announced in 2025 have not significantly impacted this year’s results. However, agencies have already noted that they may struggle to achieve 2025 milestones with a lower budget. Therefore, we recommend that FCDO and agencies review the 2025 milestones to confirm what can be achieved.

Recommendation 1: FCDO and RUSH agencies review the 2025 logframe milestones, in light of recent humanitarian funding cuts.
Description of programme

This Annual Review covers programmatic activity from January-December 2024 inclusive, where the UK contributed £108 million.

The RUSH programme is designed to provide core funding to five humanitarian agencies of the United Nations (UN). This core funding is the most effective way of supporting these agencies to provide life-saving humanitarian assistance, rapidly and at scale. It aims also to enhance the value-for-money of FCDO bilateral humanitarian programmes and drive priority humanitarian reforms including early and anticipatory action, enhanced quality and transparency of data, protection of the most vulnerable, accountability to affected populations, and inclusion in humanitarian response. Through this programme, FCDO holds five UN humanitarian agencies to account for delivering a more co-ordinated, effective and cost-efficient system. These five agencies are: the International Organisation for Migration (IOM); the UN Office for the Co-ordination of Humanitarian Affairs (OCHA); the United Nations High Commission for Refugees (UNHCR); the United Nations’ Children’s Fund (UNICEF); and the World Food Programme (WFP).

FCDO provides £108 million per year in funding for three years, distributed between the five agencies. 70% of the annual contribution to each agency is unearmarked core funding. Distribution of the remaining 30% is contingent on agencies meeting agreed joint targets aligned with the UK’s reform priorities, under an agreed Payment by Results (PbR) Framework.

All five agencies are scored against their progress on outputs covering a range of topics including anticipatory action, localisation, learning and evaluation, protection from sexual exploitation and abuse (PSEA), gender-based violence (GBV), and inclusion. The programme’s logframe splits indicators into two categories: those which contribute towards Payment by Results, and additional, non-PbR indicators.

This programme follows the “3 P’s” of the UK’s Humanitarian Framework:

Prevent: helping the system better prevent humanitarian crises from worsening through anticipatory action and improving resilience towards and responses to climate change in the UN Humanitarian system.

Prioritise: improving the system’s ability to prioritise funding and assistance to those most in need through better use of data, and incentivising the agencies to be more accountable to affected populations; and

Protect: ensuring protection of the most vulnerable by ensuring that PSEA standards are upheld and that we Leave No One Behind.
Summary supporting narrative for the overall score in this review

Overall, agencies have met or exceeded the majority of performance indicators in this Annual Review, leading to an overall score of A.

Agency Achievements

There are strong individual examples of performance at HQ and field level against the thematic topics which this programme measures. These success stories and highlights in 2024 include:

IOM: Their work on displacement and migration in crises reached over 26.4 million people, including internally displaced persons, refugees, migrants and host communities. Of the beneficiaries surveyed, 89 per cent considered that IOM’s humanitarian assistance had been delivered in a safe, accessible, accountable and participatory manner.

OCHA: Supported humanitarian responses in 51 countries and territories, assisting more than 2,000 humanitarian partners and UN agencies to reach nearly 116 million people with at least one form of life-saving assistance in 33 countries, addressing the impact of extreme weather-related emergencies, food insecurity, disease outbreaks.

WFP: Provided food, nutrition, and cash-based assistance (including 2.5 million metric tonnes of food and USD 2.2 billion in cash transfers and vouchers) to 124 million people, providing emergency response within an average of one day of sudden-onset crises. WFP also reached 38.8 million children with interventions that improved their access to nutrition, health and education services, while 18.8 million pregnant and breastfeeding women and girls, and children under 2 were assisted with nutrition support.

UNICEF: Delivered: clean water and sanitation for 41 million people; measles vaccinations for 24.7 million children; early detection and treatment of wasting and other forms of malnutrition benefiting 109.3 million children under 5 years of age; access to education for 9.2 million children; community-based mental health and psychosocial support services for 22.3 million children and families, and interventions to prevent gender-based violence and support survivors for 17.7 million women and children; humanitarian cash assistance for 3.6 million households; delivery of $1.234 billion worth of humanitarian supplies in 68 countries, with 50 per cent going to Level 2 and Level 3 emergencies.

UNHCR: Assisted 36.4 million people in 2024, including refugees, asylum-seekers, stateless people, internally displaced people, and people who were returning to their areas of origin after being forced to flee. Of these: 18.4 million people received protection services; 1.7 million people benefitted from specialist GBV programmes; 1.5 million children and caregivers received child protection services; over 460,000 people benefitted from livelihoods and economic inclusion; 5.3 million people received cash assistance; 2.6 million people received shelter and housing assistance; 2.1 million people benefitted from education programming; 7.7 million people were supported with access to water and/or sanitation services.

Indicator Scoring

Figure 1. Overall Summary of Scores against Outputs

Output	Output Description	Impact / Weight (%)	Output Performance
1	Prevent and anticipate future shocks and build resilience in long-running crises by tackling the underlying drivers of humanitarian crises (collective)	10%	A+
2	Prioritise humanitarian assistance to people in greatest need and provide them with what they need the most to bounce back from crisis (collective)	10%	A
3	Protect the people most at risk, including from conflict-related sexual violence and address barriers to humanitarian assistance (collective)	10%	A
4	Prevent and anticipate future shocks and build resilience in long-running crises by tackling the underlying drivers of humanitarian crises (individual)	23.3%	A
5	Prioritise humanitarian assistance to people in greatest need and provide them with what they need the most to bounce back from crisis (individual)	23.3%	A
6	Protect the people most at risk, including from GBV and address barriers to humanitarian assistance (individual)	23.3%	A

Of the 44 indicators reported against in 2024, 82% of indicators met or exceeded expectations, scoring an A or A+. This is comparable to 84% in 2023. As with 2023, agencies performed better against PbR indicators, achieving or exceeding 93% of targets (14 of 15), compared to 76% of non-PbR indicators.

This is the final full year of the RUSH programme. This coincides with significant reform in the UN humanitarian system, including the announcement of a ‘humanitarian reset’, announced by the UN’s Emergency Relief Coordinator in March 2025[4], and UN80, a reform initiative announced by the UN Secretary-General[5]. For RUSH’s successor programme, we aim to use PbR to proactively drive delivery of key reform commitments made during these initiatives, in order to maximise the impact of FCDO funding on both delivery and reform.
[4] The humanitarian reset (10 March 2025) | OCHA
[5] Home | UN80 Initiative

Progress on recommendations from the 2024 Annual Review, and major lessons and recommendations for the year ahead

Recommendations from the 2024 Annual Review

Most of the recommendations made in the 2024 Annual Review have been addressed by FCDO and the RUSH agencies. However, all recommendations focussed on the logframe, and some recommended updating the logframe impact and outcome indicators. As this is the final full year of the RUSH programme, and FCDO is currently designing a new logframe for RUSH’s successor programme, it has been decided to not change the impact and outcomes in the final few months of RUSH. Changes will be made to the impact and outcome for RUSH’s successor, which is due to begin implementation in January 2026.

Key Lessons and Recommendations for the year ahead

This Annual Review has identified the following recommendations to take forward in the next year:
#	Recommendation	Action Owner	Deadline
1	FCDO and RUSH agencies to review the 2025 logframe milestones, in light of recent humanitarian funding cuts.	FCDO and agencies	December 2025
2	RUSH Agencies to produce an action plan, covering how they will address continued underperformance against indicator 3.2.1, and both maintain and improve PSEA activities in a challenging funding climate.	RUSH Agencies	March 2026
3	WFP to submit an action plan to FCDO, addressing how it plans to address gaps between achievements at HQ and the field, and how it plans to improve PSEA and GBV-related results.	WFP	December 2025
4	Agencies to present on AA and preparedness coordination in a 2026 RUSH Round Table discussion.	RUSH Agencies	January 2026
5	The logframe of RUSH’s successor programme should include indicators which go beyond processes, and capture the longer-term impact of agency activities, on programme participants and communities.	FCDO/RUSH Agencies	January 2026
6	RUSH’s successor programme should put in place stronger mechanisms for clear assessment of VFM - including but not limited to indicators that monitor programme effectiveness within the logframe.	FCDO	January 2026
7	FCDO to produce a non-PbR guidance note, setting a recommended range for report lengths and a common set of standards	FCDO	March 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Theory of Change (ToC) illustrates how this programme uses multilateral core funding to support five UN agencies to provide life-saving humanitarian assistance, rapidly and at scale. It also enhances the value-for-money of FCDO bilateral humanitarian programmes, cements UK influence within these agencies and in the wider multilateral system, and drives priority humanitarian reforms.

There has been a sharp funding decrease in 2025 from the US with the closure of USAID, and expected decreases from other states. This has precipitated a humanitarian reform process that connects into a wider UN80 reform process. The result is that the final year of the programme is operating in a smaller funding environment to when it was designed. It is also possible the wider operating environment will change as a result of ongoing reform processes, but it is not clear how reforms will affect the agencies included in this programme.
In 2024 the impact and outcomes were achieved. In 2025 it is possible milestones at all levels could be missed. In many cases there will not be certainty until 2026 as data collection for many indicators only occurs after the year has finished.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme impact indicator has not been met, however there are credible mitigating circumstances. Of the four outcome indicators, three have milestones, and two were achieved. The third - providing assistance to SEA victim-survivors - improved marginally from the previous year. The programme outputs scored A and A+ meaning that the programme is broadly speaking on track. To note, two of the four outcome indicators are duplications of output indicators.
Impact Indicator: number of people in need being reached by the global humanitarian system
The 2022 baseline for this indicator was 148 million people reached (59% of those targeted) with a milestone of a year-on-year increase in the number of people reached. In 2024 116m people were reached (72% of those targeted). In the year prior 143m (66% of those targeted). Since baseline the indicator achievement has decreased year on year, rather than increasing. However, the percentage of people targeted has increased. For 2024 there are mitigating circumstances as OCHA conducted a boundary setting exercise to reduce the number of people in need. This was in response to a previously inflated people in need figures as humanitarian response took on an expanded role in development and peace activities.

Outcome Indicator 1: the number of people covered/assisted by collective anticipatory action in 2024.
This indicator is the same as the indicator for Output 1.1.2, which has a milestone of 5.5 million people. In 2024, 6.8 million people were covered/assisted, and the milestone was met. The number of people covered by anticipatory action has remained stable from 2023 to 2024 reflecting the challenges in maintaining coverage in some contexts, against increasing coverage in others. In 2024, 12 collective anticipatory action frameworks were triggered, assisting 4.2 million people across nine countries. A further 2.6 million people were covered by 13 active frameworks which were not triggered.
Outcome Indicator 2: % of the most vulnerable groups/those in most severe need receiving what they needed the most in 2024.
This indicator is designed to report upon the people in need, targeted, and reached by the humanitarian system. In 2023, the baseline for the indicator was 363 million people needed assistance, with 245 million people targeted, and 143 million people reached (66%). In 2024, 323 million people needed assistance, with 198 million people targeted, and 116 million people reached (72%).

Using data sources from outside the indicator - the Food Security Cluster (FSC) targeted 113 million out of the 207 million people in need (for their sector) – 96 million for food assistance, 65 million for livelihood assistance – and reached 78% of the targeted population. Out of the 88 million people reached, 71 million received food assistance and 32 million were provided with livelihood and agriculture support, either in-kind, cash or mixed modalities. Yet, as partners received only US$ 6.6 billion out of the USD 15 billion required, they were forced to prioritize and further target the delivery of assistance.[6]
[6] Annual Report.pdf

OCHA identified two data points in their annual reporting which demonstrated the impact of funding shortfalls - 4.7 million people received crop production assistance at an average cost of $150 per household. This support enabled households to produce $468 million worth of food, meeting their own needs and sustaining their communities for months. If the Food and Agriculture Organization (FAO) had received full funding for crop its interventions under the GHO 2024, an additional 25.9 million people could have produced over $2.58 billion worth of food in 2024—four times the original funding request.

Also - in Egypt, under the Sudan Regional Refugee Response Plan, more than 50,000 recently arrived, vulnerable Sudanese refugees received bi-monthly Multi-Purpose Cash (MPC) assistance. With full funding, an additional 93,800 vulnerable Sudanese refugees on the waiting list could have received this vital support.[7]
[7] 2024 in review: humanitarians delivering under attack | Global Humanitarian Overview 2025 | Humanitarian Action
Outcome Indicator 3: % of HCTs (Humanitarian Country Team) that have undertaken collective advocacy actions on critical protection priorities or issues identified in HCT Protection Strategies or through Protection Cluster briefings, messaging and analysis in 2024.

This indicator is the same as the updated version of Output 3.1 and now reads:
1. % of HCTs who have received and been sensitized on the benchmarking tool to facilitate its use.
2. % of HCTs that undertook collective protection advocacy.
Results met the milestone and achieved 28% for a) and 72% for b), however the latter is a decrease from 86% in the previous year. The first sub-indicator reflects the roll out of a new tool and seeks 75% achievement in 2025. Once rolled out it will require maintenance as HCT members change. The current level of progress is marginally ahead of plan. The second sub-indicator reported that in 22 out of 29[8] HNRP contexts, the HCT conducted collective protection advocacy. This is less than the previous year as the indicator is not cumulative and requires new action to be taken every year. As this indicator is a duplicate of 3.1, further information can be found in that section.
[8] Afghanistan, Burkina Faso, Cameroon, Chad, Colombia, DRC, Ethiopia, Haiti, Lebanon, Mali, Mozambique, Myanmar, Niger, Palestine, Philippines, Somalia, Sudan, Syria, Ukraine, Venezuela, Yemen, Ukraine
Outcome Indicator 4: Increased number of sexual exploitation and abuse (SEA) allegations and % of SEA victims receiving timely and adequate assistance in 2024.
An increase in the level of reporting of SEA can indicate better controls and more accessible reporting mechanisms:
1. an increase in the number of SEA allegations from the baseline
2. at least 40% of SEA victims to have received timely and adequate assistance.
As of 2024, 2,555 allegations were recorded on I-Report for the five UN agencies and their implementing partners which is an increase against the baseline and 2023 total of 1,842. Of these 1,788 were by implementing partners of which 50% had assistance rendered, and 767 by UN personnel of which 28% had assistance rendered. Of the implementing partner case half that did not have assistance rendered, 36% was because the victim declined, did not seek assistance, could not be identified (bulk – 33%), or was unreachable. This leaves 15% of cases as unknown or TBD. Of the UN personnel case 72% that did not have assistance rendered, 58% was because the victim declined, did not seek assistance, could not be identified (bulk – 19%), or was unreachable. This leaves 16% of cases as unknown or TBD (note – iReport totals 101.6%). The assistance rendered figures are concerningly low and this demonstrates a crucial gap for unknown or TBD cases, as well as issues in identifying and contacting at risk populations. The availability of data has changed, and it is no longer possible to determine if this assistance is timely and adequate. Based upon this data, the outcome indicator has been missed and demonstrates only a marginal improvement on the previous year. This forms part of FCDO’s wider concerns about PSEA-focussed indicators being missed, which has led to the request for a PSEA-focussed action plan. (see recommendation 2 above).
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

As reflected in the scoring of the programme, RUSH continues to meet expectations and progress can be seen in all the areas of reform on which the programme focuses. The ToC remains relevant as the gap between humanitarian needs and available resources continues to grow, agency reforms are more needed now than ever. However, there is a risk that achievement in 2025 will be lower than expected. Core funding continues to provide a useful complement to direct funding to UN agencies in crisis contexts, allowing them to strengthen their systems and processes, fulfil their global roles in upholding global norms and standards, and supporting them to operate more quickly and flexibly where and when need arises. For these reasons we assess that the programme should continue.
Recommendations for the year ahead:
FCDO to ask partners to estimate whether they are on track to achieve 2025 milestones (see Recommendation 1 on page 2).

## C. DETAILED OUTPUT SCORING

Output Title	Prevent and anticipate future shocks and build resilience in long-running crises by tackling the underlying drivers of humanitarian crises
Output number:		1	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Achievement	Progress against Milestone
1.1.1: # of frameworks for climate-related hazards developed or reviewed (including in complex emergencies)	12	16	Moderately exceeded expectation
1.1.2: # of people covered /or assisted by collective anticipatory action	6.5M	6.8M	Met expectation
1.1.3: # of publications or events on anticipatory action learning and knowledge management	8	9	Moderately exceeded expectation
1.2.1: # of key humanitarian programme cycle documents referencing anticipatory action, including global guidance, field-level planning documents, or agency-specific guidance	4	13	Substantially exceeded expectation
1.3.1: % of countries with Humanitarian Response Plans (HRPs), Flash Appeal (FA) and other coordinated plans (except Refugee Response Plans [RRPs]) where the Integrated Food Security Phase Classification (IPC/ Cadre Harmonisé) (Acute Food Security or Acute malnutrition) or similar analysis based on recognised Food Security or Nutrition methodologies is available for year of publication	85%	85%	Met expectation
1.3.2: % of countries with HRPs, FAs and other coordinated plans (except RRPs) where available IPC/CH (Acute Food Security or Acute Malnutrition) or similar analysis based on recognised Food Security or Nutrition methodologies is referenced in humanitarian plans	100%	96%	Moderately did not meet expectation

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 assesses the five UN agencies’ collective approach to anticipatory action (AA), including how they are building their capacity to better anticipate crises and build resilience.

Agencies have performed strongly against this output in 2024, meeting or exceeding expectations in five of the six performance indicators. In 2024, 6.8 million people were covered or assisted by agencies’ collective AA frameworks and efforts. These activities included:

- Developing or reviewing 16 collective AA frameworks for climate-related hazards, including for tropical storms in Haiti and Madagascar; droughts in Guatemala and Honduras; and for floods in Chad and Niger.
- Embedding AA into 13 Humanitarian National Response Plans (HNRPs): for example, this includes clear financial requirements and activity planning in contexts such as Nigeria, Mozambique and Chad, and integrates AA into response and risk planning in high-risk contexts such as Afghanistan, DRC and Myanmar.
- Taking coordinated anticipatory action (several agencies working together to implement preventative measures) to manage floods in Bangladesh, Nepal, Chad and Niger.

Agencies have also taken steps to improve coordination in-country, with humanitarian actors and affected communities and populations. Beyond the specific frameworks agreed, AA coordination needs are increasingly identified and managed through regional and national AA coordination bodies/groups.
With regards to agencies’ accountability to affected populations (AAP), agencies have conducted joint early warning messages to notify people in advance of imminent risks and available assistance (often in collaboration with the country’s AAP working group), and includes community feedback from previous assistance in each AA framework.

Only one indicator narrowly missed its target: 1.3.2, where 27 of 28 countries with a coordinated Humanitarian Response Plan (HRP) or HNRPs referenced Food Security or Nutrition analysis/methodologies. This data was not mentioned in the Burundi Response Plan, and agencies should work with all Country Offices to remind them of the common points/data which should be referenced in each HRP/HNRP.

It is also noted that activities and criteria for triggering AA vary per agency; in OCHA for example, more than 80% of prearranged funding is in HRP contexts, but overall there are ten criteria by which agencies assess whether they should support a coordinated effort. Agencies should, where possible, simplify and standardise these activities and criteria to improve coordination efforts.

Agencies have also noted the challenges and barriers to scaling up AA in volatile, conflict-affected humanitarian settings such as South Sudan, Ukraine and Venezuela, citing limited operational space for early action, and challenging security conditions. FCDO should explore with agencies if and how donors can help mitigate these challenges and ensure a consistent application of AA, irrespective of the context.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output since the last Annual Review, and we do not anticipate making further changes. However, as agencies have noted the impact of funding reductions on 2025 results, milestones may be revised in future discussions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Since last year’s recommendations were logframe-focussed, there are no output-specific recommendations from the 2024 Annual Review to address.

Although agencies performed well against this joint output, key lessons identified included ensuring AA is considered in all HRP/HNRPs; and managing the challenges and barriers to scaling up AA in high-risk, conflict affected countries. FCDO also encourages agencies to continue improving coordination and where possible, standardising its criteria for triggering AA; in line with the Grand Bargain, AA efforts should be fully coordinated (e.g. through joint assessment, planning and implementation).

Output Title	Prioritise humanitarian assistance to people in greatest need and provide them with what they need the most to bounce back from crisis
Output number:		2	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Achievement	Progress against Milestone
2.1.1: % of Cash Working Groups who have transitioned to the new Inter Agency Standing Committee (IASC) cash coordination model in line with the agreed transition plan	100%	100%	Met expectations
2.2.1: Interagency model(s) developed and implemented, allowing countries to monitor and report results, disaggregated (by sex, age and disabilities) where relevant/feasible at the outcome level, against country strategic objectives, in a way that enables decision-making and response adaptation	1) draft statement on data disaggregation for HPC steering group / 2) consultations on the inception report / 3) consider the appropriateness of using JAWS / 4) reflect on major lessons learnt and takeaways regarding the utility and efficacy of outcome monitoring	1 – achieved / 2 – achieved / 3 - not achieved / (work cancelled) / 4 - achieved	Met expectations
2.3.1: % of HRP contexts which have adopted interagency IASC Accountability to Affected People (AAP) action plans, or equivalent	40%	69%	Substantially exceeded expectations
2.3.2: % of HRP contexts that meet the minimum actions for AAP as outlined in the IASC Collective AAP Framework	50%	73%	Moderately exceeded expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

For the second consecutive year, we assess that agencies have met expectations against this milestone, leading to an output score of A.

The overall programme milestone for Indicator 2.1 has been met. Agencies intend to focus on implementing more effective cash coordination for the remainder of this programme, and over the coming years.

For Indicator 2.2, the one milestone not achieved related to considering the appropriateness of the JAWS project. As this project was cancelled due to US funding cuts, achievement of this indicator was beyond agencies’ control.

Indicators 2.3.1 and 2.3.2 relate to accountability to affected populations (AAP), and overall, agencies have exceeded expectations for both targets. Agencies’ joint Annual Report indicates there has been genuine engagement with programme participant communities, and there have been examples of successful collective feedback mechanisms (e.g. on the Syrian border, and in Venezuela), where there were rigorous data collection methods and the inclusion of marginalised communities in decision making.

However, a general persistent barrier to effective AAP is the lack of coordination between agencies, and the lack of coordinated agency feedback mechanisms. There needs to be greater engagement with affected populations and communities in the design of assessments and interventions, and the validation of decisions. AAP mechanisms should also be streamlined and have a plan to meaningfully include and respond to affected populations’ feedback.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output since the last Annual Review. However, as agencies have noted the impact of funding reductions on 2025 results, milestones may be revised in future discussions. Also, with the JAWS project cancelled, and 100% of Cash Working Groups now transitioned to the IASC model, 2025 milestones against these indicators will need to be revised/updated.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

With several process-related indicators achieved (e.g. indicator 2.1), we recommend that the next programme includes indicators focussed on the proportion of cash in responses, and on AAP, monitoring the proportion meeting minimum collective AAP requirements (as this could go down). Additionally, with agencies comfortably exceeding their targets on producing AAP action plans (indicator 2.3.1), it would be useful to track the effectiveness of these action plans. Similarly, the next programme’s logframe should measure the effectiveness of coordinated cash transfers.

Output Title	Protect the people most at risk, including from conflict-related sexual violence and address barriers to humanitarian assistance
Output number:		3	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Achievement	Progress against Milestone
3.1.1: / a. % of Humanitarian Country Teams (HCTs) who have received and been sensitized on the benchmarking tool to facilitate its use / b. % of HCTs that undertook collective protection advocacy	a) 25% b) 60%	a) 28% / b) 72%	Moderately exceeded expectation
3.2.1: % of Protection from Sexual Exploitation and Abuse (PSEA) Networks that have rolled out the UN Victims’ Assistance Protocol, including standard operating procedures (SOPs) for referral and provision of services for survivors of SEA, to allow for improved and systematic assistance to SEA survivors	40%	34%	Moderately did not meet expectation
3.2.2: % of Civil Society Organisations (CSOs) implementing/cooperating partners assessed based on UN Implementing Partner PSEA Capacity Assessment	60% of CSO's partner assessed	65%	Moderately exceeded expectation
3.3.1: % of HRP contexts where access working groups are functional (as defined in the Minimum Package of Services on Humanitarian Access)	80%	83%	Met expectation
3.3.2: % of HRP contexts where the HCT developed a joint and coordinated approach to facilitate access and mitigate constraints that hamper it with a view to achieve concrete deliverables and outcomes on humanitarian access	75%	83%	Moderately exceeded expectation
3.4.1: Extent to which agencies have delivered against commitments made at the Joint Call to Action / IASC Gender-Based Violence (GBV) funding high-level roundtable in November 2023	UNICEF - 1 OCHA - 1 WFP - 1 UNHCR - 2 IOM - 2 Total – 7	UNICEF - 1 OCHA - 2 WFP - 3 UNHCR - 2 IOM - 2 Total - 10	Moderately exceeded expectation

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 measures agencies’ collective efforts to protect people most at risk and address barriers to humanitarian assistance. These activities include Protection from Sexual Exploitation and Abuse (PSEA); protecting people at risk of Gender-Based Violence (GBV); and joint measures to improve and facilitate humanitarian access.

Agencies have achieved or exceeded five of the six indicator targets. However, indicator 3.2.1, which assesses the percentage of PSEA networks rolling out the UN Victims’ Assistance Protocol, has missed its target for the second consecutive year. In a period where PSEA activities and resources are threatened due to funding reductions, agencies’ continued underperformance against this indicator is concerning, and there is a risk that years of progress and achievements related to PSEA could roll back. Given this significant under-performance, we have overall scored this indicator an A, meeting expectations, despite other indicators largely being above expectations. FCDO requests that agencies produce a joint action plan to outline how they will address the underperformance on indicator 3.2.1, and improve PSEA networks’ use of the Victims’ Assistance Protocol.

Recommendation 2: RUSH Agencies to produce an action plan, covering how they will address continued underperformance against indicator 3.2.1, and both maintain and improve PSEA activities in a challenging funding climate.
Additionally, Output 3.1.1. (measuring the same indicator as Outcome 3) represents a decrease on last year, despite meeting the logframe indicator target. It is essential that in the current challenging funding climate, protection and access targets do not slide back, even if logframe indicator targets were achieved.

Despite this, there have been positive achievements under this overall output. UNICEF has provided tailored technical assistance and capacity-building support to PSEA networks and Humanitarian Country Teams (HCTs), and over 2,000 professionals globally have received training or orientation on the Victims’ Assistance Protocol. Implementation quality has been a growing focus, with several countries prioritising deeper integration and refinement of SOPs to strengthen their survivor-centred victim assistance mechanisms.

Capacity building extends to protection, with indicators 3.1.1 and 3.1.2 exceeded; these measure the percentage of HCTs made aware of the protection benchmarking tool, and the percentage of HCTs undertaking protection advocacy. The overachievement in both indicators highlights a continued commitment to improving knowledge and consistency in HCTs approach to protection across the UN system.

Indicator 3.2.2 also highlights strong interagency coordination, and increased engagement with and capacity building of Civil Society Organisations (CSOs) on PSEA. 65% of implementing and cooperating CSO partners were assessed using the UN Implementing Partner PSEA Capacity Assessment.

Indicator 3.1.1 underlines OCHA-led efforts to establish Humanitarian Access Working Groups (HAWGs) in operations with response plans – the target of making 80% of these working groups functional was exceeded, and with HAWGs typically co-chaired by OCHA and an NGO partner, there is a clear effort to involve a variety of local and national actors in addressing barriers to humanitarian access.

Agencies have also performed strongly on indicator 3.4.1, either meeting or exceeding the number of IASC GBV Round Table commitments they planned to deliver in 2024. Achievements include IOM increasing its dedicated GBV staffing by 250% from the 2022 baseline of 4; OCHA reporting that Country-Based Pooled Funds (CBPF) funding to Women-Led Organisations (WLOs) reached $99.8 million USD, supporting 101 WLOs; and UNHCR providing 15% of its funding to women-led organisations, as well as including dedicated sections on GBV in its annual reporting.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There has only been one logframe change since the last Annual Review. The target of indicator 3.1.1. was increased due to overperformance in the previous Annual Review. This target has been narrowly exceeded again this year. Given the continued underperformance of indicator 3.2.1, FCDO will discuss with agencies how they intend to address this in the future.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Agencies have cited a lack of funding and resourcing as factors for continued underachievement against PSEA-related targets. In its action plan (see recommendation 2), agencies should explain how they plan to avoid rollbacks in PSEA achievements in a challenging funding climate. On protection, agencies have noted that the benchmarking tool will be rolled out to all HCTs in 2025, which will improve coordination and consistency in countries’ approach to protection issues. Agencies should also clarify plans to ensure the rest promotes robust and inclusive access coordination, and the centrality of protection.

Output Title	Prevent and anticipate future shocks and build resilience in long-running crises by tackling the underlying drivers of humanitarian crises
Output number:		4	Output Score:	A
Impact weighting (%):		23.3	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Achievement	Progress against Milestone
Indicator 4.1: Anticipatory Action
OCHA: # of new or improved collective Anticipatory Action facilitated	12	16	Moderately exceeded expectation
IOM: # of IOM country offices including Preparedness and Disaster Risk Reduction in their crisis response planning	34	39	Moderately exceeded expectation
UNICEF: % of country offices that meet organisational benchmarks on updated preparedness plan	88%	98%	Moderately exceeded expectation
UNHCR: % of declared emergencies which were identified as high risk of emergency by Division of Emergency, Security and Supply (DESS) prior to emergency declarations	100%	77%	Moderately below expectation
WFP: # of people with more resilient livelihoods in the face of risks and shocks through WFP assistance	21.5m	20.4m	Moderately below expectation

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 measures agencies’ individual approaches to anticipating and preventing drivers of crisis. The final score is an aggregate of the individual agency sub-indicators, and with the majority of agencies meeting or exceeding targets, we assess an output score of A.

There have been several positive examples of agencies’ work in this area. IOM upgraded its Emergency Preparedness Dashboard, now providing improved risk profiling and contingency planning insights across 124 countries and 9 risk types; this upgrade has specifically strengthened IOM’s ability to identify high risk countries lacking preparedness plans, which guided the development or update of 72 contingency plans. IOM have also provided seed funding to 17 country offices, strengthening country-level capacity to anticipate, mitigate and respond to potential shocks more effectively.

128 of UNICEF’s 130 country offices met organisational preparedness benchmarks, and UNICEF strengthened risk analysis and preparedness capacity in 50 countries. 25 country and regional offices received nearly $7.5 million USD in dedicated preparedness funding, enabling them to implement targeted activities to mitigate the impacts of natural disasters and public health emergencies. OCHA also coordinated AA in Bangladesh, Nepal, Chad and Niger for floods, and facilitated the development or update of 12 coordinated AA frameworks.

Although UNHCR and WFP did not achieve their targets, there is evidence of positive action and development in both agencies. WFP has made notable progress around resilience at HQ level, strengthening AA frameworks, expanding its use of AI in early warning systems, approving resilience-related policies, and working with country offices to expand their disaster risk financing coverage. However, this progress is not translating to the country level, covering 1.1 million people less than the 2024 target. WFP should address how it intends to translate its HQ progress on resilience into the field; this will form part of a wider action plan to address several missed non-PbR indicators (including PSEA).

Recommendation 3: WFP to submit an action plan to FCDO, addressing how it plans to address gaps between achievements at HQ and the field, and how it plans to improve PSEA and GBV-related results.
UNHCR’s indicator was changed to only cover conflict-related emergencies, and managed to identify 24 of the 26 which occurred in 2024 – emergencies in Libya and Syria were missed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Two indicators have been tweaked since the last Annual Review. IOM’s target was increased following overachievement in 2023, and UNHCR’s indicator was tweaked to only cover conflict-related emergencies. However, as agencies have noted the impact of funding reductions on 2025 results, milestones may be revised in future discussions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Although performance has been strong overall, there is a need to understand how agencies’ HQ work on in this area translates to progress in the field. Also, agencies’ reporting did not provide much detail about coordination on preparedness and AA – output 1 assesses this but we identified that coordination remains an issue, and we would appreciate further information on how the UN system as a whole is working together on preparedness, and coordinating to avoid duplication. We plan to use a 2026 Round Table discussion to cover this.

Recommendation 4: Agencies to present on AA and preparedness coordination in a 2026 UN Round Table discussion.

Output Title	Prioritise humanitarian assistance to people in greatest need and provide them with what they need the most to bounce back from crisis
Output number:		5	Output Score:	A
Impact weighting (%):		23.3	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Achievement	Progress against Milestone
Indicator 5.1: Localisation
OCHA: % of eligible national partners accessing direct humanitarian funding through CBPF	30%	35%	Exceeded
IOM: / % of funding transferred to local and national actors in humanitarian programme / % of humanitarian funding for LNAs, as a proportion of total humanitarian IP Transfers and Grants	7% / 58%	1) 7.38% / 2) 67.78%	Moderately exceeded expectation
UNICEF: % of humanitarian funding provided to local and national actors	37%	48%	Moderately exceeded expectation
UNHCR: / % Proportion of local and national responders among UNHCR funded partners. / Share of local and national respondents in overall partnership funding disbursed to UNHCR funded partners. / # of funded partners led by forcibly displaced and stateless people or their host communities / % of Project Partnership Agreements led by national or local responders	Increase in at least two of these four indicators from 2023 to 2024.	All indicators increased from 2023 to 2024 / 1: Increase - 87% (85%, 2023) / 2: Increase - 58% (57%, 2023) / 3: Increase - 219 organisations (93, 2023) / 4: Increase - 72% (68%, 2023)	Moderately exceeded expectation
WFP: % of WFP funding to cooperating partners, awarded as directly as possible to local and national organisations	25%	18.9%	Moderately below expectation
Indicator 5.2: Learning and Evaluation
OCHA: % of OCHA-targeted recommendations made in independent evaluation reports implemented by due date	70%	75%	Moderately exceeded expectations
IOM: # of evaluations conducted including joint system-wide or independent evaluation in which IOM have engaged	8	8	Met expectation
UNICEF: / a) % of L3 crisis responses activated by UNICEF and evaluated within 24 months of declaration. / b) % of IAHEs launched during the calendar year to which UNICEF contributed a) budget support and b) participated in the management group. / c) % of ongoing or completed thematic evaluations within a calendar year, as defined in the UNICEF global evaluation plan.	a) 65% / b) 100% / c) 100%	a) 100% / b) 100% / c) 100%	Moderately exceeded expectations
UNHCR: / a) % of expenditure on evaluation as proportion of total UNHCR expenditure / b) Proportion of substantive policies/strategic results areas evaluated at least once in 10 years	a) 0.21% / b) 30%	a) 0.14% / b) 23%	Significantly below expectation
UNHCR: To share relevant policy & guidance on targeting & prioritisation of needs & resources within & across crises (as means to best support most severe needs/most vulnerable in a context of constrained resources). This could include: Operational guidance, methodologies, monitoring approaches, learning and evaluation/best practice from the field etc.	Joint UNHCR-WFP Analytical Framework used for assessment and targeting of basic needs assistance used in at least 8 countries / New Programme Handbook issued for UNHCR staff including key elements of targeting and repository of tools for use by operations / Ongoing learning opportunities for UNHCR staff on fundamentals of targeting and specific tools	Framework used in 11 countries.	Moderately exceeded expectations
WFP: % of implemented evaluation recommendations	80%	61%	Moderately below expectation
WFP: # of joint and system-wide evaluations in which WFP engaged in reporting year	8	9	Moderately exceeded expectation

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 5 tracks agencies’ individual efforts related to localisation, and learning and evaluation. Overall, the majority of agencies have met or exceeded targets for both, leading to an output score of A.

Output 5.1 focusses on localisation, and agency achievements include:

- IOM rolling out its Localisation Framework.
- UNICEF developing common, cross-sector approaches to localisation.
- WFP approving its Localisation Policy in June 2025 and partnering with more than 1,000 NGO cooperating partners in operations.
- OCHA Country-Based Pooled Funds providing 35% of its funding ($329 million USD) to national partners, and developing capacities of LNAs.
- UNHCR disbursing 58% ($693 million USD) to local and national partners, and 87% of UNHCR-funded partners were local and national responders.

While overall achievement against the indicators of output 5.1 met or exceeded agreed indicator targets, particularly for UNHCR and UNICEF, WFP did not meet its distribution target, allocating 18.6% of its contributions to local and national organisations (against a target of 25%). Although WFP cited operational and funding pressures as factors for this shortfall (a decline from the 2023 figure of 31.1%), WFP anticipates renewed alignment, resourcing and improved measurement of its engagement with national and local actors following the approval and subsequent implementation of its localisation policy (June 2025). OCHA’s achievement, while exceeding its target, falls below the ERC’s ambition, stated in 2025 in the context of the Humanitarian Reset, of transferring 70% of country-based pooled funds[9] to LNAs. These statistics illustrate a wider concern, that although the majority of agreed indicator targets have been met or exceeded, UN agencies are not shifting enough of a proportion of overall funding to local and national actors. For example, even though IOM allocated 67.78% of its humanitarian funding provided through implementing partner transfers and grants to local and national actors, only 7.38% of overall funding was transferred to LNAs in its humanitarian programme. Similarly, only 48% of UNICEF’s humanitarian funding was provided to LNAs. Although these figures met or exceeded targets measured by the current logframe, we recommend that the logframe for RUSH’s successor programme encourages agencies to shift further towards supporting local and national actors, in line with senior UN officials’ stated ambitions in the context of the humanitarian reset.
[9] This is different from WFP’s target, which covers all contributions, whereas OCHA’s target covers country-based pooled funds only.

Output 5.2 covers agencies’ learning and evaluation activities, and overall results indicate that MEL continues to not be prioritised enough. UNHCR in particular has significantly missed its target spend for learning and evaluation, with the milestone itself way below the recommended average. This low investment is reflected in its second missed sub-indicator, where only 23% of its substantive policies/strategic results have been evaluated at least once in 10 years.

Milestones related to implementing recommendations from evaluations are particularly weak, with little evidence that agencies are using recommendations to learn and design future interventions. Although OCHA met its learning and evaluation target, there is little evidence that OCHA is fully evaluating and learning from previous programming. WFP also missed its target, only implementing 61% of evaluation recommendations (against an 80% target). With funding likely to be tight, agencies have a greater need than ever to make evidence-based interventions, and need to showcase a continued commitment to MEL.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Three sub-indicators have been tweaked since the last Annual Review. WFP’s 5.2 target was reduced from 100% to 80% to align with corporate reporting (but the 2024 achievement was still 61%); UNICEF’s second 5.2 indicator had the wording changed, and UNHCR’s 5.1 target was updated to achieving two of the four metrics (all four were achieved). As agencies have noted the impact of funding reductions on 2025 results, milestones may be revised in future discussions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Performance against this output has been mixed, particularly with regards to learning and evaluation. We recommend that agencies consider how they will continue to prioritise localisation, and learning and evaluation, in a challenging funding environment. We also note that the current RUSH logframe contains several process-related indicators, which are important to track activity. However, any new programme logframe should measure the next step – the impact of localisation beyond measuring funding, and instead of capturing how many evaluations were completed, there should be indicators which capture how learning has shaped future activity (the impact of these recommendations). As part of the humanitarian reset, we are looking for all partners to increase their localisation ambitions, not just in terms of volume of funding to local partners, but also the quality of funding (how this funding is used, and its impact).

Recommendation 5: The logframe of RUSH’s successor programme should include indicators which go beyond processes, and capture the longer-term impact of agency activities, on programme participants and communities.

Output Title	Protect the people most at risk, including from GBV and address barriers to humanitarian assistance
Output number:		6	Output Score:	A
Impact weighting (%):		23.3	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Achievement	Progress against Milestone
Indicator 6.1: PSEA
OCHA: # of high-risk contexts having inter-agency PSEA coordinators	10	13	Moderately exceeded expectation
IOM: % of HRP countries – where IOM has an operational presence and participates in the HRP/FA/RRP – with full-time PSEA focal points and that have prioritized PSEA in their country plan	45%	52%	Moderately exceeded expectation
UNICEF: % of UNICEF country offices with reporting system rolled out office-wide and partners trained on PSEA reporting requirements and procedures	95%	100%	Moderately exceeded expectation
UNHCR: % of people who receive support from the Victim Care Officer(s) and chose to pursue a resolution process where circumstances allow.	57%	72%	Moderately exceeded expectation
WFP: # of children and adults who have access to a safe and accessible channel to report sexual exploitation and abuse by humanitarian, development, protection and/or other personnel who provide assistance to affected populations	49,044,810	31,410,871	Moderately below expectation
Indicator 6.2: GBV
OCHA: Proportion of Humanitarian Country Teams (HCTs) with engagement of women-led organisations.	75%	85%	Moderately exceeded expectation
IOM: # of dedicated GBV Specialists supporting IOM operations (disaggregated by location – country/region/HQ)	8	14	Substantially exceeded expectation
UNICEF: % of country offices that have implemented a minimum set of gender-based violence risk mitigation actions in their humanitarian operations	30%	43%	Moderately exceeded expectation
UNHCR: # of persons reached by UNHCR GBV programmes	2024 result sets milestone	1.67m	N/A
WFP: % of specific CO (Country Office) that engage with food security clusters/sectors to disseminate resources on GBV risk mitigation through training, awareness raising sessions, establishment of action plans to respond and mitigate GBV	30%	30%	Met expectation

Indicator 6.3: Inclusion (disaggregated data by sex, age and disabilities)
OCHA: Percentage of OCHA's analytical products that include data disaggregated by relevant geographic and demographic factors	88%	100%	Moderately exceeded expectation
IOM: % of active Displacement Tracking Matrix (DTM) operations where applicable disability inclusion indicators are integrated into data collection activities	50%	51%	Met expectation
UNICEF: % of countries providing disability-inclusive humanitarian programmes and services.	70%	70%	Met expectation
UNHCR: Percentage of UNHCR country operations that report against the core indicator relating to participation of refugees and asylum seekers report that the extent to which UNHCR supported the participation of refugees and asylum-seekers was “extensive”.	68%	55%	Moderately below expectation
WFP: % of country offices reporting at least 80% of beneficiary related indicators, disaggregated by sex	95%	100%	Moderately exceeded expectation
WFP: # of women, men, boys and girls with disabilities accessing food/cash-based transfers/commodity vouchers/capacity strengthening services	10,396,611	9,500,000	Moderately below expectation

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 6 measures agencies’ individual efforts related to PSEA, GBV and inclusion. Although overall, the majority of agencies have met or exceeded targets, leading to an output score of A, it is important to review the three groups of activities separately.

As with Output 3, there are concerns with agencies’ performance on PSEA. Although four of the five agencies met or exceeded their targets, there are concerns about the agencies’ distribution of PSEA officers. For example, although IOM exceeded their target number of PSEA focal points, there are 78 PSEA officers deployed across 63 countries, and IOM could consider spreading officers to cover a wider range of countries.

Other results indicate that PSEA is not being prioritised enough, or is even being deprioritised at country level. Only 38 of 73 IOM’s 2024 appeals had a PSEA coordinator involved, while although UNHCR exceeded its PSEA target (with 72% of people receiving support from the Victim Care Officer(s) and choosing to pursue a resolution process), this figure is a decrease on last year’s achievement of 74%. WFP’s field-level results also fail to reflect their efforts to strengthen PSEA at the HQ level (including through creating a PSEA Director position); their result is particularly concerning, falling below last year’s baseline, with only a quarter of people reached having access to safe reporting mechanisms.

UNICEF’s PSEA results were promising, with a strong 100% achievement, and evidence of scaling up reporting systems and strengthening capacity in all countries with a humanitarian response. There is clear evidence of UNICEF integrating PSEA into training and partnership agreements. However, while the number of PSEA allegations increased for the second successive year, reporting numbers remain small, and there are concerns that if PSEA resources are cut, this reporting could fall even further.

There are wider concerns that PSEA will be deprioritised in light of recently announced funding cuts, and it is essential that agencies outline how they will continue to prioritise PSEA in the future, to prevent rollbacks of previous progress and achievement.

The results against GBV indicators are mixed. IOM performed strongly, with 14 GBV specialists now operational (5 at HQ, and 9 in country offices). IOM have already exceeded the 2025 target of 10, but there are concerns that multilateral funding cuts will affect future achievements, and the maintenance of this dedicated support. WFP have just met their 30% target, but again, field-level achievements have not reflected efforts to strengthen GBV at HQ level; for example, in 2024, WFP mainstreamed GBV within its Gender, Protection and Inclusion service, through including GBV in wider training sessions and guidance material. Although UNICEF exceeded its target and almost doubled its 2023 achievement, integrating GBV resources into normal activities, their target of 30% was quite low, and agencies should consider how to continue mainstreaming GBV activities across all contexts. OCHA have technically exceeded their Humanitarian Country Team (HCT) engagement target with women-led organisations (WLOs); however, with the indicator now including one-off consultations, it is unclear whether the WLOs consulted are full members of HCTs, and if the ‘engagement’ is regular and meaningful, as opposed to one-off consultations which is insufficient engagement.

Achievement in the inclusion-focussed indicators is also mixed. Most agencies have achieved or exceeded targets, with good evidence of inclusion being mainstreamed and considered in activities. For example, IOM is using the Washington Group of Questions on disability (a recognised standard set of questions in the humanitarian and development communities), and broadening questions out to gather data on barriers to access, and UNICEF’s engagement initiatives for persons with disabilities has led to: over 23,000 persons with disabilities reached with multipurpose cash assistance in Palestine; more than 89,000 persons with disabilities accessing sanitation services in Yemen; and nearly 9,300 women and children with disabilities receiving primary healthcare in Bangladesh. Globally, 23,394 women and children with disabilities received GBV support from UNICEF-funded projects, up from 3,153 in 2023.

However, some targets feel unambitious - for example, although IOM have disability inclusion indicators integrated into data collection activities in 51% of its Displacement Tracking Matrix operations, there is a question why integration has not been possible in the other 49% of operations. Similarly, although UNICEF is providing disability-inclusive humanitarian programmes and services in 70% of its operating countries, it would be useful to understand the barriers preventing inclusion in the remaining 30%. Additionally, UNHCR and WFP have missed inclusion-related targets.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

One sub-indicator has been tweaked since the last Annual Review. WFP’s 6.2 target was reduced to 30%, which was achieved. As agencies have noted the impact of funding reductions on 2025 results, milestones may be revised in future discussions. However, funding cuts cannot result in these priority areas being deprioritised or stripped of resources.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Although there have been several positive examples of achievement, there are concerns that vital interventions related to PSEA, GBV and inclusion, and their mainstreaming across wider activities, will be deprioritised and heavily cut, as a result of wider agency budget cuts. It is essential that progress in these priority areas is not lost or rolled back, and FCDO will work with agencies to determine how these areas will continue to be prioritised in any new UN programme. It is also essential to examine agencies’ stated high level of ambition for these areas, which is not reflected in milestones or achievement (e.g. for GBV and inclusion). As part of the new programme and logframe, FCDO will discuss whether agencies should re-evaluate ambition, ensuring that these areas are not deprioritised, but that equally, ambitions stated by senior UN officials are not unrealistic.

## D: VALUE FOR MONEY
FACT: In 2024 alone, RUSH agencies saved over $296.9 million USD through efficiency activities (see ‘efficiency’ section below).
Key cost drivers and performance

The RUSH Business Case outlined how FCDO would assess and monitor Value for Money (VfM) through its rolling programme of Central Assurance Assessments, the Annual Review process, and its well-managed institutional relationships with the five RUSH agencies.
The programme’s key cost drivers remain: agency mandates; context/operational environment; systems and resourcing costs including deployment and staffing; and procurement and logistics.
The RUSH logframe indicators continue to address these cost drivers, focussing on improving the efficiency and effectiveness of the humanitarian system through: reducing management costs; encouraging early action; encouraging joint or bulk procurement; enhancing the use of cash in delivering humanitarian responses; strengthening the quality of data and the roles of local agents; strengthening anticipatory action frameworks; enhancing climate resilience; strengthening joint-needs assessments; and developing higher quality data to be used more transparently.
VfM performance compared to the original VfM proposition in the business case
The original VfM proposition, as written in the RUSH Business Case, rests on agencies’ operational effectiveness, as well as the ability of RUSH to promote greater collaboration across the agencies. To measure VfM performance against this proposition, FCDO uses the ‘5 Es’ framework:

Figure 2: The ‘5 Es’ Framework:
The ‘5 Es’ Framework

Economy - Are we (or our partners) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our partners) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs of an intervention having the intended effect? (‘Spending wisely’)
Equity - How fairly are the benefits distributed, in particular amongst marginalised groups? (“spending fairly”)
Cost-effectiveness - What is the intervention’s ultimate impact on our foreign policy objectives, relative to the inputs that we or our partners invest in it?[Grab your reader’s attention with a great quote from the document or use this space to emphasize a key point. To place this text box anywhere on the page, just drag it.]

Below is a short assessment of agencies’ VfM performance in 2024, with case studies:

Economy

In a challenging funding environment, agencies have taken steps to reduce operating and programming costs, while conducting joint purchases, increasing purchases from local suppliers, and strengthening procurement procedures to ensure high-quality products are bought for the best possible price. For example:

UNICEF’s Global Shared Services Centre saved over $30 million USD in 2024 by consolidating some of its automated processes. UNICEF also reduces operating costs by having 54% of its offices in shared premises, pooling services such as HR, IT, logistics and administration.

UNHCR follows common UN procurement principles (prioritising VfM; fairness, integrity and transparency; effective international competition; and UNHCR’s priorities), and will introduce a new Procurement and Administrative Instruction Policy in 2025. It also: has launched a new Supply Strategy to simplify its supply chain; has pursued joint tenders with other organisations; regularly reviews past and expected future demand through forecasting; and sources products locally (e.g. establishing three contracts in East and Horn of Africa for the provision of environmentally friendly tarpaulins, blankets and buckets).

IOM has signed 45 long-term agreements with suppliers in 2024; these lengthy agreements have reduced procurement processing costs by 50% and cut procurement time for large-value items from 60-180 days to 14 days. IOM has also participated in shared UN services (e.g. IT licenses) and procurement frameworks and has saved $99.2m USD through digitising emergency dispatch processes.

WFP has sourced 59% of its food locally or regionally (1.97 million metric tonnes), reducing delivery costs and timelines.

Efficiency

Agencies have shown anecdotal evidence of spending their funds efficiently. These initiatives have not only saved money, but improved operations and outputs through stronger and more precise data and estimations, and freeing up staff’s time to work on mission-critical issues instead of admin work.

UNICEF saved over 200,000 staff hours in 2024 by streamlining finance, travel and recruitment processes, and supported nearly 50,000 civil society organisations with a unified registration, risk and capacity assessment mechanism. UNICEF also reduced average ‘packed-to-ship’ supply times to 17 days, down from 36 in 2021, through securing priority access and pre-positioning supplies. UNICEF’s Global Shared Services Centre generated over USD 30 million in savings in 2024 alone.

UNHCR has saved $59 million USD in 2024, including through digitising processes (such as travel requests), which has streamlined multiple services, reduced costs, and improved response times.

WFP has saved $169.9 million USD in 2024, through 59 initiatives which have not only saved money, but improved the purchasing and positioning of supplies. For example, its Supply Chain Optimisation Upstream Tool (SCOUT) analyses where to best buy food, where to send and store it, and how to use limited resources to deliver it on time. SCOUT has saved over $2 million USD in 2024 alone, and is projected to save over $50 million USD in the coming years.

IOM has also generated efficiency gains of $38 million USD in 2024, including through digitisation, online training and AI usage, which has freed up staff to work on mission-critical priorities instead of drafting correspondence and summarising reports.

Effectiveness

In 2024, agencies showed more limited evidence of effectiveness compared to the other E’s, but there is anecdotal evidence of investments having the intended effects. Sections B and C of this Annual Review focus on delivery against the Theory of Change and logframe, but from a VfM perspective:

UNICEF was able to distribute supplies and services to children quicker through joint procurement of supplies with other agencies and buying locally. For example, UNICEF procured$5.6 billion worth of supplies and services for children in 160 countries, procuring 79% of these supplies jointly with other UN agencies. Also, 66% of the 5.2 million cartons of ready-to-use food which UNICEF delivered to 66 countries were sourced from local suppliers, and cash and voucher assistance continues to provide a rapid, flexible and effective way of meeting families’ urgent needs, yet provide some form of self-sufficiency.

UNHCR led 28 of 32 protection clusters and cluster-like mechanisms globally, supporting the humanitarian response in contexts such as DRC and Sudan. This enabled rapid, coordinated responses; for example, the UNHCR-led Global Protection Cluster managed 530 support requests, and led 17 in-person missions, while improved tracking tools supported timely and informed decision-making in emergencies such as Afghanistan and Ukraine. Of 35 country operations reporting survivor satisfaction data on UNHCR’s GBV programming, 79% maintained or improved rates above 75%.

WFP used streamlined processes and improved targeting to respond to 31 emergencies in 2024, and support 124.4 million people through food deliveries, cash transfers, vouchers, and individual capacity strengthening initiatives. The median time for the first transfer to reach people in 47 crises was 24 hours.

In 2024, IOM’s crisis response reached over 26.4 million people, and has strengthened efforts to mainstream Accountability to Affected Populations principles throughout its work; for example, IOM country offices engaged over 538,000 affected persons in decision-making for the design, planning and implementation of its humanitarian programming. IOM has also continued using cash and voucher assistance, reaching more than 3 million people in 124 countries and territories, enabling over 1.2 million people to meet their basic needs and access essential goods and services.

Equity

The five agencies continue demonstrating commitment to distributing their activities and supplies fairly, and reaching marginalised populations:

In 2024, UNICEF spent 14% of its programming on activities focussed on gender equality, an increase of 3 percentage points from 2023. The 2025 Executive Board also acknowledged UNICEF’s significant progress in its Gender Policy and Gender Action Plans, delivering strong results in activities such as child marriage prevention, and building girls’ leadership and skills. UNICEF met or exceeded 88% of the UN’s Disability Inclusion Strategy requirements, and reached 5.2 million children with disabilities in 2024.

UNHCR provided 1.4 million children with child protection services in 2024, and at least 75% of its operations incorporated disability inclusion; this includes over 93,000 adults and 18,000 children with disabilities being reached through interventions such as cash assistance, shelter and psychosocial support. 54% of participants in UNHCR’s livelihoods programmes were women, and its GBV prevention and response services reached over 1.6 million people in 86 countries.

Of the 124.4 million people reached by WFP’s activities in 2024, 66.8 million were female, 71 million were children, and 9.5 million were persons with disabilities. WFP has reached marginalised groups through improved targeting, tracking and data monitoring (including disaggregation).

IOM has introduced several policies and strategies focussed on inclusion, including its first Disability Inclusion Strategy (2025-28), and Race Equity and Equality Strategy, which are both aligned with IOM’s Strategic Plan. IOM also ensured that persons with disabilities had greater participation in decision-making, through creating inclusive platforms (such as disability committees in IDP camps) and launching more than 400 targeted engagement with persons with disabilities.

Cost-effectiveness

Based on the overall logframe results, it can be assessed that the RUSH programme continues to be cost-effective. The programme’s Business Case states that the five agencies, along with the Red Cross Movement and CERF in Humanitarian Partnerships Group’s wider portfolio, are an “incomparable channel for delivery of humanitarian assistance at scale globally.”
This remains the case, and the UK’s provision of flexible, core, predictable funding is essential in funding agencies’ central assurance and essential oversight functions (e.g. safeguarding and risk management, resource mobilisation), which are integral to the UN humanitarian system’s delivery. Continued funding of this programme remains a key metric to gauge the UK’s strong global reputation and leadership in the humanitarian system, and is integral in the delivery of the UK’s multilateral and humanitarian objectives.
Therefore, agencies’ continued good performance, and its role in encouraging coordination between the five humanitarian agencies, indicate the programme’s ongoing cost-effectiveness.
Assessment of whether the programme continues to represent value for money

Although many of the metrics are not applicable to OCHA, due to its coordination role, all agencies have taken steps to not only reduce their spending in a challenging funding environment, but improve the speed and preparedness of operations through: sharing, streamlining and digitising processes; using data to better reach marginalised groups and buy high-quality resources at competitive prices; and pursuing joint agreements and procurement.

However, there are no VfM-specific indicators in the current RUSH logframe, and much of agencies’ reporting on the topic is anecdotal. It is recommended that for the next phase of the UK’s core UN humanitarian funding, metrics are introduced which enables VfM assessments to focus less on individual case studies, and more on the bigger picture (i.e. to what extent does the UK’s investment and engagement with agencies help deliver VfM)?

Recommendation 6: RUSH’s successor programme should put in place stronger mechanisms for clear assessment of VFM - including but not limited to indicators that monitor programme effectiveness within the logframe.
However, based on the above analysis, the anecdotal examples provided, and agencies’ overall delivery against the logframe’s output indicators, it is assessed that the RUSH programme continues to represent good Value for Money.

E: RISK

Overview of risk management

The overall risk rating for this programme remained at ‘major’ during the reporting period, reflecting a stable level of risk in both the programme’s activities and operating locations and within an appetite for the programme.

This rating, and the programme’s internal risk register, are reviewed at Quarterly Risk Reviews organised by the Deputy Risk and Assurance Lead. These meetings, which are attended by the PRO, programme team, Humanitarian Adviser and Institutional Leads, are used to examine all programme risks and assess whether the individual ratings and/or mitigations should be updated, and to support identification of new risks. The Deputy Risk and Assurance Lead then updates the Risk Register.

Over the course of the last 12 months, FCDO has continued its influencing and assurance activities, including through engagement in governing boards, donor fora and via undertaking its own targeted assessments. These activities ensure FCDO continues to possess a good understanding of agency capacity and capability and can influence further consolidation and strengthening of risk management across partner agencies.

The programme’s risk appetites across all seven categories were within appetite for the reporting period. The risk appetite has been regularly reviewed through the course of the reporting period and is in line with the risk appetite statement of FCDO’s Humanitarian Policy and Partnerships Department. This ensures the risk appetite is in line with that currently applicable to a humanitarian programme, recognising the challenging operating environments in which humanitarian assistance is provided. The spectrum of programme risks have remained broadly constant over the past 12 months and remains where the majority of risks sit.

It is worth noting that the one severe risk we hold relates to: the continued high level of humanitarian need in challenging environments across the globe. Although the global humanitarian context relies on external factors, we continue to mitigate this risk through multiple actions, which include: encouraging agencies to plan ahead to deliver joint needs assessments and maintain their own risk registers; engage with donors, agencies and policy leads to identify and highlight risky contexts; and liaise closely with other donors to leverage support from others. This risk is within appetite for the reporting period.

Aside from this, key risks relate to funding cuts across the humanitarian landscape, fraud and aid diversion in humanitarian contexts and challenges in reporting and investigating the latter. These risks are being closely tracked by FCDO and mitigation strategies are in place. There are also several agency specific risks which are being closely monitored by the FCDO team.

Assurance

FCDO’s programme and risk and assurance teams, as well as Institutional Leads, have continued their influencing and assurance activities, including through engagement in governing boards, donor fora and via undertaking its own targeted assessments. These activities ensure FCDO continues to possess a good understanding of agency capacity and capability and can influence further consolidation and strengthening of risk management across partner agencies. During the reporting period this includes refreshing the due diligence we hold on UNHCR.

With regards to specific assurances provided in the RUSH Business Case:

Climate and Environment: Due to the limitations around attributing core-funding to specific crisis/shocks/interventions, this programme does not require compliance with FCDO’s internal guidance. However, as large multilateral organisations, UN agencies’ global presence is considerable and therefore there are likely environmental impacts from its operations. This includes the emissions of complex logistical infrastructure required for large humanitarian operations (for example, air and sea freight, personnel movement). FCDO’s Central Assurance Assessments review agencies’ environmental risk management systems and processes, including their efforts to ‘green’ their operations and supply chain. No new climate-specific risks have been identified since the last Annual Review, but FCDO will continue to engage with agencies on this, including through the joint PbR indicator (1.1.1, for which agencies exceeded their target this year[10]), and a ‘deep dive’ discussion at a future agency Round Table discussion.
[10] PbR Indicator 1.1.1 - # of frameworks for climate-related hazards developed or reviewed (including in complex emergencies). 2024 target = 12. 2024 achievement = 16.

Gender Equality: The RUSH Business Case notes how the programme complies with the International Development (Gender Equality Act) 2014. We continue to expect all partners to consider mitigation of risks of gender-based violence within their operations and to implement global standards and guidance, including the IASC Guidelines for Integrating GBV Interventions in Humanitarian Action. All UK-funded humanitarian programmes consider Sexual and Reproductive Health and Rights. FCDO monitors agencies’ approach to gender equality, and tackling GBV through several logframe indicators. These include PbR indicator 3.4[11], where all agencies met or exceeded the target number of commitments they were asked to deliver against, and non-PbR indicators 6.2 and 6.3 (detail of agencies’ performance can be found in Section C of this Annual Review).
[11] PbR Indicator 3.4 - Extent to which agencies have delivered against commitments made at the Joint Call to Action / IASC GBV funding high-level roundtable in November 2023. 2024 target = 7. 2024 achievement = 10.

Public Sector Equality Duty: Due to the nature of this flexible core funding, it is not possible to attribute funds to specific interventions or crisis and shocks, or people with protected characteristics. However, FCDO does monitor agencies’ efforts to reach marginalised groups through the due diligence/Central Assurance Assessment process; the Annual Reviews; and through non-PbR indicators 6.2 and 6.3 of the RUSH logframe. FCDO continues to place a strong emphasis on promoting gender equality, disability inclusion and other potential factors of marginalisation and engage with partners to consider how their operations could impact protected groups and support the implementation of the IASC Guidelines on Inclusion of Persons with Disabilities and the UN Disability Inclusion Strategy.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Partnership and Engagement

At HQ level, FCDO has sustained its long-term, strong relationships with all five agencies, at senior and working level. Institutional Leads meet regularly with agency focal points, and have participated in agencies’ governing board meetings. Senior officials from FCDO (principally at Deputy Director/Director level) have attended several boards, and have held regular meetings with senior executives from each agency. This close, regular level of engagement has maintained the UK’s position as a respected donor and voice in the UN humanitarian system, which bolsters our continued efforts to encourage its reform.

In relation to RUSH specifically, the FCDO programme team organises a quarterly ‘Round Table’ discussion with all agencies, where agencies’ performance is discussed, and key thematic issues such as localisation and PSEA are explored in ‘deep dive’ discussions. Agencies remain engaged in these meetings, coordinating on presentations and inviting technical experts to explain their ongoing activities. Specific challenges or issues with delivery are followed up, bilaterally, with FCDO Institutional Leads. In addition to these meetings, FCDO holds quarterly internal Portfolio Compliance Board meetings to discuss the programme’s risks and review any fraud and SEA cases within individual agencies.

Reporting

The FCDO programme team manages its relationship with agencies through individual, signed Memoranda of Understanding (MoUs). The MoUs require agencies to submit a joint report in May each year, outlining results against PbR indicators (Outputs 1-3), in addition to individual reports by the end of June, covering individual results for each agency against non-PbR indicators (Outputs 4-6).

This year, all reports were received on time and provided results against all indicators, but the length and quality of the five agencies’ reports were variable. The joint PbR report was written in line with FCDO’s template, and provided useful case studies of successful interventions, but further detail was required to explain results against specific indicators, specifically the indicator where results were not met. For the non-PbR reports, all five agencies followed the reporting template provided in advance by FCDO, but the length of reports varied, and different formats and focusses were adopted by each agency. There was a strong level of anecdotal detail, including specific case studies and strong examples of considering VfM, but although length does not directly determine quality, multiple reports lacked critical detail on why specific targets were not met. In some of these cases, explanations focussed on the work and achievements which had been completed against these indicators, instead of providing adequate explanation of the challenges and reasons why targets were missed.

We recommend that for the PCR and future reports, FCDO provides a non-PbR guidance note in advance (matching the PbR guidance note), setting a recommended range for report lengths, but providing a clear steer to agencies that if targets are missed, explanation should focus less on anecdotal achievements, and more on challenges which caused targets to be missed.

Recommendation 7: FCDO to produce a non-PbR guidance note, setting a recommended range for report lengths and a common set of standards.
FCDO is also provided with access to the annual reports and audited accounts of each agency, and these are scrutinised by the programme team to ensure there is no financial mismanagement or risks to our funds.
Funding

Funding to the agencies is distributed in line with the timetable and conditions agreed in each agency MoU. Payments are released in three tranches; 50% non-PbR in April following FCDO’s review of agencies annual audit accounts; 20% non-PbR in July following receipt of agency specific reports; and the final 30% PbR payment in October on submission and review of a combined report where at least 80% of PbR milestones were met. Agencies have provided payment requests on time, which has allowed all payments since the last Annual Review to be made on time.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring

FCDO monitors agencies’ performance through multiple processes including: agency bespoke reporting feeding into our Annual Review; quarterly ‘Round Table’ discussions with agencies (further detail in Section F); regular engagement between Institutional Leads and agency focal points (further detail in Section F); engagement in agency governance meetings, briefings and country visits for donors; and regular engagement with FCDO teams in country on agency performance. The RUSH programme does not have a Monitoring, Evaluation and Learning (MEL) component, and an external, programme-funded evaluation is not planned.

The RUSH Annual Review process is timed to begin when agencies submit their annual reports, covering results against logframe milestones. These reports are reviewed by the programme team, Institutional Leads, the UN Humanitarian Adviser, and technical experts from across FCDO. The programme team then drafts the Annual Review, with the above technical experts providing input where relevant. As noted in Section A of this review, Annual Review recommendations are followed up with partners and addressed by an agreed deadline.

FCDO uses ‘deep dives’ at quarterly Round Table discussions to monitor agencies’ progress in thematic areas noted in the Business Case. In 2025, Round Table ‘deep dives’ covered agencies strategic plans and monitoring; localisation; the use of unearmarked funding; and PSEA.

In addition to these activities, the programme management team and Institutional Leads have monitored agencies’ performance through one field visits; assessments of agencies’ own evaluations; reviews of any independent evaluations produced; and participation at agencies’ governing boards, strategic dialogues, and other bilateral meetings with agencies.

Evidence

As noted in Section E, there is a breadth of anecdotal evidence provided in partners’ annual reports (on VfM, but also through case studies relevant to logframe indicators), but higher-quality evidence is required to illustrate the impact of the UK’s intervention, and core funding as a whole, on the speed and scale of reform within the UN humanitarian system.

Learning

The Annual Review serves as the principal learning point for the programme team. Key lessons and recommendations for the year ahead are noted in Section A.

When field visits and agency governing boards take place, Institutional Leads, the UN Humanitarian Adviser and/or the programme team share key lessons, observations and recommendations across FCDO, through organisation-wide presentations and back-to-office reports.

Agency Financial Reports and audited annual statements
Agency	Date of last narrative financial report	Link to the last narrative financial report	Date of last audited annual statement	Link to the last audited annual report
IOM	29/05/2025	IOM Financial Report and Audited Statement	29/05/2025	IOM Financial Report and Audited Statement
OCHA	31/03/2025	OCHA Financial Report and Audited Statement	23/07/2025	OCHA Financial Report and Audited Statement
UNHCR	31/03/2025	UNHCR Financial Report and Audited Statement	23/07/2025	UNHCR Financial Report and Audited Statement
UNICEF	15/05/2025	UNICEF Financial Report and Audited Statement	23/07/2025	UNICEF Financial Report and Audited Statement
WFP	06/06/2025	WFP Performance Report 2024	10/06/2025	WFP Audited Financial Statement 2024