## Annual Review Template

Title: Nigeria Portfolio Monitoring, Evaluation and Learning (PMEL)
Programme Value £ (full life): £3m		Review date: June 2025
Programme Code : 301515	AMP start date: 07/03/23	AMP end date: 30/06/26

Summary of Programme Performance
Year	2023	2024	2025	2026
Overall Output Score	A	A	A+
Risk Rating	Minor	Minor	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003072.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/S3015159.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
The Portfolio Monitoring Evaluation and Learning (PMEL) programme was designed to respond to His Majesty’s Government (HMG) Nigeria’s objective of making the best use of evidence to inform the policy and programming portfolio.

PMEL supports the FCDO vision of taking “a long-term view of our international policy objectives while being agile and responsive within that”.[1] The FCDO’s Vision Statement says, “We will be best in class in using evidence, data and digital to inform our policy and our action.”[2] The 2021 Integrated Review commits the FCDO to put “greater emphasis on using insight and analysis from around the world to target our diplomatic interventions overseas more effectively.”[3]
[1] ‘FCDO Vision Statement’, August 2020.
[2] Ibid
[3] HMG (2021), Global Britain in a Competitive Age: The Integrated Review of Security, Defence, Development and Foreign Policy, page 46

The mandate of the PMEL programme is to support HMG Nigeria to understand what works in initiating and establishing sustainable change through its portfolio of advocacy, influence, development, and diplomacy.

In line with this mandate, the added value of the PMEL programme is to support HMG Nigeria to improve its learning about what works and why at portfolio level.

Furthermore, PMEL’s intended contribution is to support HMG Nigeria to use these insights and learning processes to inform evidence-led portfolio level adaptive strategies, backed by allocation of resources, to maximise progress towards country goals.

PMEL is achieving the above objectives through the remaining two components i.e. Evidence and Learning. The Data component was dropped because it became misleading, with a false assumption of data generation as a discrete activity, see further details in para 110.

This review covers programme activities between July 2024 and June 2025, the first full year of implementation.
Context over the last 12 months
In January 2025, the UK Foreign Minister announced the FCDO reforms and connection of its work to two domestic priorities of the British people that cannot be solved without work abroad – boosting economic growth and tackling irregular migration.[4]
[4] https://www.gov.uk/government/speeches/the-locarno-speech-by-the-foreign-secretary-9-january-2025

Building on this, six new FCDO priorities have been agreed – Growth, Security, Europe, Migration, Climate & Nature and Development. These priorities currently influence the trajectory of the organisation and interventions/activities have begun to align accordingly.

In January 2025, the President of the United States of America signed an executive order that froze all foreign aid for a 90-day review. This spend freeze has evolved into termination of most contracts (implementation and personnel) with the few remaining contracts expected to be managed by the US State Department.

The impact of the US Foreign Aid cuts has been felt across the development sector globally, including across the multilaterals (UN, WHO, GAVI, Global Fund, etc.), and by governments of donor recipient countries where key sectors relied on this funding.

In February 2025, the UK Prime Minister announced that the UK will reduce aid spending from 0.5% of Gross National Income (GNI) to 0.3% of GNI to fund higher defence spending.[5] Refer to para 14 – 17 below for more details.
[5] https://hansard.parliament.uk/commons/2025-02-25/debates/8BF58F19-B32B-4716-A613-8D5738541A30/DefenceAndSecurity#contribution-DB32B970-42F2-4B1B-A92C-54CA0B28BA41

While the implications of these significant contextual changes are still evolving, some strategic shifts are already emerging which is impacting the choice of interventions/activities undertaken by PMEL
About changes to UK ODA
At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision reduce the UK’s Official Development Assistance (ODA) and reinvest it into defence. The ODA budget will gradually reduce to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.

The UK remains fully committed to playing a globally significant role in humanitarian assistance and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.

ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.

We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.
Implementing Partner Performance
Oxford Policy Management Limited (OPML) has performed well during this first full year of implementation. The PMEL team has consolidated its position and built relations with a broader range of primary beneficiaries, while remaining agile in responding to a growing range of requests under its evidence component. It has also looked to extend its ambition in feeding evidence into learning sessions and events beyond the remit of the country office under its learning component.

Feedback from primary beneficiaries (Programme and Block SROs) has been largely positive on the work products, understanding of the issue and delivery approach. The quality, delivery and timeliness has overall been strong, scoring 5 out of the maximum score of 6 and tracked as part of the contract KPIs – see para 97 below.

FCDO Management of the Programme
There were no changes to the Senior Responsible Officer (SRO), Programme Responsible Owner (PRO), Technical Adviser (Statistics Adviser) and Programme Manager roles for PMEL during the period under review.

The SRO and Statistics Adviser provided support to the PMEL team especially in relating internal organisational nuances which influenced decisions and on which pieces of work to lean into. This contributed to the successes achieved by the PMEL programme during the period under review.

FCDO continued to meet with the PMEL team bi-weekly during the year under review. This facilitates regular check-ins to discuss activities, financials, stakeholder management and any emerging risks.
Summary supporting narrative for the overall score in this review
The overall score of PMEL is A+ which is exceeding expectations in terms of delivery and achievements across the implementation phase during this period under review (July 2024 – June 2025).

During this period, PMEL has consolidated and extended buy-in across teams in the office, including senior leadership. A revised log frame captures the merging of data and evidence components into a unified evidence component that better reflects PMEL’s evolved way of integrating data into both descriptive and evaluative analysis.
Output 1 (Knowledge products): Exceeded expectations (A+) with milestone targets exceeded for the demand-led studies. While the target for the outcome case studies was not met due to internal organisational changes despite PMEL’s efforts to secure interest from colleagues; the knowledge products generated have informed key decisions during this reporting period since the change of Government, see details in para 38 - 47.

Output 2 (Learning): Exceeded expectations (A+) with milestone targets met and a demonstrated extension of ambition to engage in national multi-stakeholder networks and international learning fora.
Major lessons and recommendations for the year ahead
Key Lessons
1. Agility, breadth of offering and a high level of responsiveness remained key to PMEL’s success: PMEL continues to show agility to lean into issues that are important to HMG Nigeria. Leveraging insights from the SRO and Statistics Adviser coupled with the regular check-ins, PMEL focused its efforts to main areas of interest from the office. With all blocks now engaged, PMEL is well placed to respond to HMG Nigeria strategic pivots.
2. Visibility, ease of contracting and quality of service combined to boost PMEL: During the year, colleagues across the mission have increasingly come to see PMEL as a ‘useful’ provider of quality evidence and analysis. PMEL’s profile and reputation have been further boosted by greater exposure at the Delivery Board and Country Strategy Board sessions as its contributions are increasingly name checked.
3. Combining international and national expertise remained key: PMEL’s pool of international and national consultants have worked well together during the year and have been brought onstream quickly and effectively. The success of this combination approach further strengthens the relevance of local contextual understanding to the delivery of an effective PMEL contract.

Linking evidence to learning in a busy country office requires deliberate planning: While recognising that much learning is informal, the PMEL team notes that there was a low ‘conversion rate’ from the evidence product to a block or team lesson-learning meeting or session. Without more deliberation there is a risk that reports remain limited in circulation and/or use.
Key Recommendations:
1. Ensure PMEL remains aligned with the emerging Business and Country Plan: As mentioned above, FCDO’s priorities and approaches globally are evolving, and HMG Nigeria is keen to stay aligned with these changes. The continuous leverage of relevant insights from the PMEL SRO and Statistics Adviser are essential to ensure PMEL’s resources are deployed in the most efficient and effective manner to respond flexibly to the likely strategic shifts alluded to above.
2. Internal Stakeholder Management: There will be a significant turnover at the top of the BHC as well as within block leads and advisers across HMG Nigeria over the next reporting period, so PMEL will need to engage successors early on to get them onboard to maintain the current levels of senior engagement across the office.
3. Build dissemination and outcome feedback into ToR for evidence products (outcome case and demand-led studies) to strengthen the evidence-to-policy and learning pathway: Leveraging on successes during the year under review, PMEL should be more deliberate in building dissemination moments – such as presentation sessions or mini workshops – and intermediate outcome feedback into the ToR for subsequent workstreams as much as is possible. This will strengthen the process of sharing of and reflecting on PMEL-generated evidence within and across teams and blocks.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Due to the agreed changes to the approach during programme inception, the ToC statement for the PMEL programme was revised to:

“if PMEL and HMG Nigeria partner track, analyse and learn from evidence drawn from interventions, with PMEL sharing this evidence in easy-to-engage formats,
and if HMG Nigeria colleagues engage in a meaningful and timely cycle of strategic learning, drawing on this evidence,

then HMG Nigeria will design and implement more strategic, aligned, and effective cross-portfolio interventions that will result in improved portfolio impact in Nigeria.”

This ToC has remained unchanged during the year except for a reduction in the number of components from three (data, evidence, and learning) to two (evidence and learning). It was agreed that the data component which was previously the monitoring component was now redundant since the activities meant to be delivered within that component were de-emphasised as mentioned above.

The focus of the programme has shifted towards light-touch, high frequency learning, and evidence outputs. In this way, PMEL supports HMG-N in self-assessment of its contribution to, and progress towards, its BCP goals. Cross-portfolio learning in turn creates more integrated, effective and targeted HMG investment in Nigeria.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

1. Almost 18 months into implementation (after 6 months of inception), the programme has started contributing towards expected outcomes and impact. During its first full year of implementation the programme has gathered pace and gained visibility and traction amongst HMG Nigeria colleagues across blocks and teams, such that interest and demand for PMEL support is increasing.
2. PMEL’s regular participation in HMG Nigeria delivery board meetings during this year has further enhanced its visibility and recognition while enabling the PMEL team to identify new opportunities to provide evidence-based input.
3. The logframe milestones at intermediate outcome and outcome level are determined by simple average of rubric-based self-assessment scores produced by HMG Nigeria colleagues who are the primary users of the work products. Notable workstreams that have contributed to outcome-level strategy discussions (more detail provided in Section C below) include:
4. In the wake of the cost-of-living crisis affecting Nigerians in 2023/24 stemming from the policy reform packages implemented by the Government, PMEL responded rapidly and effectively to a request for a Poverty and Social Impact Analysis (PSIA) of the inflationary effects of the Government of Nigeria’s macroeconomic reforms and of its social protection response in April 2024. This PSIA workstream continued to provide ‘real time’ inputs to HMG Nigeria strategic deliberations on how best to advocate regarding the blockages in government cash transfer programme delivery. PMEL conducted an opinion poll on a selected pool of beneficiaries all geo-political zones in the country to gather evidence regarding the impacts of the previous cash transfers.
5. The PMEL GEDSI context review with its mapping of ‘tractable’ policy opportunities was well timed to feed into the Governance and Stability block’s internal strategic reflections on how best to support and mainstream GEDSI across the portfolio.
6. PMEL’s review of the UK engagement across Energy transition, decarbonisation and climate finance sectors in Nigeria over the past 10-15 years which fed into the design of a successor programme for the UK Nigeria Infrastructure Advisory Facility (UKNIAF) programme. This received a nil score for the intermediate outcome and score of 3 for the outcome. Score of 3 for the outcome implies that evidence use is transparent and embedded in processes, systems and working culture.
7. The review of HMG Nigeria’s approach to localisation in its humanitarian response provided evidence that fed strategic reflections on how best to strengthen capacity building, partnerships and decision-making power amongst local partners in the next iteration of humanitarian programming. This received a 3 score for the intermediate outcome and score of 3 for the outcome. A score of 3 for the intermediate outcome implies significant engagement during the learning/dissemination event and significant follow-up discussion.
8. PMEL’s review of contributions of Nigerians in diaspora (UK) which estimated the size of the Nigerian diaspora in the UK, contribution of Nigerian diaspora to the UK economy, contribution of Nigerian diaspora in the UK to Nigeria and non-economical contributions of the diaspora to both the UK and Nigeria. The report findings have been used by the High Commissioner in ministerial briefings, key internal documents and strategies. It has also supported the people-to-people block with decisions on which workstreams they should not focus on, what they need to do to engage better and draw on this relatively untapped resource. The Deputy High Commissioner’s feedback was that “…. I think it was a great initiative, and the team have pulled together an impressive amount of information in a short time. I found it useful and informative. And agree it’s how to take the next step”.
9. This review received a score of 3 for the intermediate outcome and score of 4 for the outcome. Score of 4 for the outcome implies that evidence use is transparent, embedded and instrumental, directly informing portfolio strategies, programmes and initiatives.
10. The PMEL stocktake of HMG Nigeria’s utilisation of technical assistance (TA) has been timely in feeding ongoing senior leadership team discussions on how best to allocate a diminishing aid budget in pursuit of its country goals. The High Commissioner referenced this report during the Country Strategy Board regarding how it is helping us reflect better on how best to maximize the identified modalities of TA use. Extracts from the report were also shared with the Parliamentary Under Secretary of State in the Foreign, Commonwealth and Development Office as part of the evidence to justify the recommended approach for one of our programmes.
11. The PMEL review of the foreign aid cuts - implications and opportunities was particularly timely for HMG Nigeria. While the US Governments cuts was at the core of the review, it also captured information on expected cuts from other governments that have made similar announcements and responses from select country governments. These insights have informed internal reflections about HMG Nigeria portfolio design.
12. PMEL’s synthesis of ‘Thinking and working Politically’ (TwP) learning from the Partnership to Engage, Reform and Learn (PERL) programme as well as the TwP PERL Value for Money (VfM) How-To-Note which was shared during the influencing working group session that had block SROs and sector advisers in attendance. This provided another opportunity to remind colleagues about the relevance of the TWP principles which are fundamental to the success of the partnership approach of working in overseas countries.
13. PMEL developed seven outcome case studies in February 2025 requested and used by the Development Director to feed into the strategic global review commission from FCDO HQ. Four of these case studies were new, although did not include the determination of HMG Nigeria contribution using contribution analysis. The other three were repurposed existing PMEL outcome case studies. This process was led by the Deputy development Director who appreciated the timeliness of response and the quality of the content.

*See annex for rubric scoring interpretations
OUTCOME	Intermediate Outcome Indicator 1		Jan-24 (baseline)	Jun-24	June-25
Decision makers use PMEL evidence-led learning to support coordinated cross-portfolio strategies	Number and quality of adaptive strategies	Planned strategies / (Not cumulative)	0	1 adaptive strategy (quality score 3+)	2 instances of change in a strategy, programme or initiative (quality score 3+)
		Achieved		No strategy (quality score 1 out of 4)	5 instances of change in strategy and initiatives (see para 38, 40, 41, 42 and 44 above) / (Average quality score 3+)
INTERMEDIATE OUTCOME	Intermediate Outcome Indicator 1		Jan-24 (baseline)	Jun-24	June-25
Internal and external decision makers engage purposefully in policy reflection during, and after, facilitated block, team and portfolio-level learning events	Quality of engagement by decision makers during and after learning events	Planned events (Not cumulative)	0	1 event / (quality score 3+ out of 4)	2 events / (quality score 3+)
		Achieved		2 events / (quality score 2 out of 4)	4 events (see para 38, 40, 41, and 46 above) / (quality score 3)

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
During the year under review, PMEL has strengthened its ability to be highly responsive to emerging demands.

1. There is increased demand amongst block and team leads for substantiated evidence to justify their programming approach through the demand-led studies which has resulted in milestone targets against output 1.2 being exceeded.
2. In addition, information in previous section corroborates the existing demand and potential future demand is substantiated by the likely increase of increased expectations from the centre to demonstrate the effectiveness of our portfolio.
3. Learning events and sessions held during this year met milestone target expectations. PMEL has also shown ambition in stretching these targets to include national and global network learning sessions.
4. The global network learning sessions provide an opportunity for PMEL to contribute to existing global body of evidence in these areas which further strengthens the case for using ODA funds for this programme. The Lead consultant that worked on the synthesis of ‘Thinking and working Politically’ (TwP) learning from the PERL programme as well as one of the leads on the programme (DAI Supplier) participated in one of the Organisation for Economic Cooperation and Development (OECD) Development Assistance Committee (DAC) plenary sessions on governance reform in Paris in November 2024.

The theme of the session was “Working politically and working patiently: Lessons from UK Governance work in Nigeria.” Here is the feedback from the OECD colleague – “Your expertise in the field was crucial for ensuring a productive and fruitful conversation. Sharing the experience of this specific programme in Nigeria was highly appreciated among members. In fact, some delegates mentioned that was one of the best sessions of parts that they enjoyed the most. Your participation contributed enormously to the success of the session, and we are extremely grateful for that.”

This consultant also shared these findings with the FCDO Governance Cadre in December 2024.

The Lead consultant that worked on the synthesis of the TwP Value for Money (VfM) implications learning from the PERL programme is currently finalising a think piece and blog for the TwP Community of Practice. In addition, she presented at the Palladium Conversation Series in June 2025.

The PMEL team also presented the methodology and results of Small Area Estimate (SAE) of Out of School Children (using Kano as a pilot) virtually to FCDO statistics cadre in May 2025 and at the Statistics Donor Partner Group (DPG) meeting at the World Bank Office in Abuja in June 2025. A key outcome of this meeting is that DPG now wants to set up a technical working group on SAE led by the National Bureau of Statistics. This was on the basis that there is increasing demand from government stakeholders for this method and will be good for partners to be aware of what others are doing

For these reasons, this review recommends the programme continues.

## C. DETAILED OUTPUT SCORING

Output Title	Timely, relevant and accessible outcome-level knowledge products produced to support HMG Nigeria learning
Output number:		1	Output Score:	A+
Impact weighting (%):		70%	Weighting revised since last AR?	Yes

*See annex for rubric scoring interpretations
Indicator(s)	Milestone(s) for this review	Progress
1.1. Number and quality (content, robustness and importance) of outcome case studies	5 outcome case studies / (quality score 3+ out of 4)*	3 outcome case studies delivered successfully and highly rated / Average quality score 3.7
1.2. Number and quality of demand-led studies	5 demand-led studies / (quality score 3+ out of 4)*	11 demand-led studies delivered and highly rated / Average quality score 3.6

Briefly describe the output’s activities and provide supporting narrative for the score.

We have scored output 1 an A+ because PMEL has exceeded one of its milestone targets and almost met the other while maintaining high quality. In addition to this, the agility of PMEL in responding to various knowledge product generation requests as well as relevance of these products to the organisational context contributed to this score (see section B above). PMEL Component 1 maps directly onto the logframe Outputs 1.1 and 1.2.

1. Indicator 1.1 (outcome case studies) covers the analysis of claimed ‘significant outcomes’, self-identified by HMG Nigeria colleagues and which signal progress towards its eight Business Country Plan goals. And Indicator 1.2 (demand led studies) covers the evidence need requests received from HMG colleagues.
2. PMEL is continuing to produce series of Outcome Case Studies that map pathways to the outcome using contribution analysis to determine HMG Nigeria contribution vis-à-vis other influences, to assess the outcome ‘claim’. This evidence is synthesised and fed into HMG Nigeria learning resources or instances as detailed under Component 2 (see Output 2 below).
3. During the year under review (ending June 2025), while the milestone target of five outcome contribution case studies was not met, the knowledge products generated have informed key decisions, see details in para 38 - 47. PMEL produced the following case studies:
(a) PERL programme Thinking and working politically outcome study (November 2024). PMEL was tasked to produce an outcome case study on the contribution of the soon-to-close PERL programme during its lifetime to a range of outcomes through its ‘Thinking and Working Politically’ approach. The case study was well received by HMG Nigeria colleagues. This study received an average quality score of 3.6. It has also prompted PMEL’s contribution to learning beyond the country office at series of high-profile events (see Output 2 below) and a follow-up demand-led study on PERL’s approach to VfM (see below).
(b) Health Sector Wide Approach (SWAp) outcome case study + one-page brief (February 2025). This case study examined HMG Nigeria’s contribution, through partner collaboration and coordination, technical input, and funding, to support the Nigerian Federal Ministry of Health’s development of a sector wide approach (SWAp). The SWAp reforms are seen as a key vehicle for progress towards universal health care and improved health outcomes. The SWAp outcome case study was well received by HMG Nigeria colleagues, who provided feedback that ‘the attribution analysis summary in Annex A is really, really excellent, and couldn’t have come at a better time. It has broader relevance for the specific strategy questions core SLT are currently grappling with’. This study received a quality score of 3.7.
(c) Deradicalised women outcome case study + one-page brief (March 2025). This case study examined the HMG Nigeria’s contribution to the economic empowerment and reintegration of women who have escaped insurgent groups through an ISF-funded project in Borno state The case study was well received by HMG Nigeria colleagues, who provided feedback that ‘The content is great;  the report provides wider lesson learnt about what works that would be useful across the mission’.
PMEL evidence component output 1.2 (demand-led studies) centres on responding in a timely way to emerging demands for evidence and analysis across the portfolio. During the year under review, PMEL has exceeded its milestone target due to requests from HMG colleagues to do more, producing 11 demand-led studies as follows:
1. PMEL’s review of the UK engagement across Energy transition, decarbonisation and climate finance sectors in Nigeria over the past 10-15 years (August 2024) which fed into the design of a successor programme for the UK Nigeria Infrastructure Advisory Facility (UKNIAF) programme. PMEL was commissioned by the Sustainable Economic Transformation (SET) block to write this review which was well received including being highlighted during a delivery board session. It was followed by a presentation and learning session with SET block colleagues in October 2025 which was also well received (see output 2 below).
2. Poverty and Social Impact Analysis (PSIA) outputs (September 2024 – March 2025). During this year, the PMEL team continued to provide the social protection lead with monthly barometer outputs and analysis on the ongoing cash transfer distribution blockages at the Federal and Partner State levels. Although this workstream began during the last Annual Review period, during the current year, the PMEL team produced a poll on cash transfer distributional impact (October 2025) and 8 monthly bulletins [two in September, one in October and two in November, one in January, one in February, and one in March). This PSIA support involved close collaboration and high flexibility. Outputs were well received by HMG Nigeria colleagues. This workstream and its outputs received an average quality score of 3.25.
3. Education Note (Kano State Enrolment Trends Data Analysis from Small Area Estimation (SAE) models (January - June 2025). Under this workstream, the Education Lead Adviser commissioned PMEL to undertake an analysis of enrolment and attendance data (national and Kano) and to trial the use of small area out-of-school estimation method for Kano. SAE results were shared with stakeholders from PLANE, AGILE and UNICEF. PMEL provided some improved population estimates for the PLANE Cost Benefit Analysis draft report. The PMEL team presented the methodology and results of SAE of Out of School Children virtually to FCDO statistics cadre on May 13, 2025, and later presented it at the second quarterly Statistics Donor Partner Group (DPG) roundtable meeting at the World Bank Office in Abuja on June 5, 2025, thereby contributing to learning in the wider development community (see output 2 below). In response to the growing demand from government and key stakeholders for granular-level data (at LGA level for instance), the DPG has recommended setting up a Technical Working Group specifically on SAE headed by the National Bureau of Statistics to which FCDO (through PMEL) is expected to contribute. This workstream received a quality score of 2.75.
4. Scoping note for Office of National Statistics (ONS) intervention as a supplier of the Women’s Integrated Sexual Health – Dividend (WISH-D) programme (March 2025). PMEL undertook data scoping on SRHR to understand what demographic and SRHR data is currently collected, published, and used including the data gaps that exist. PMEL also identified users of this data and how it is used to inform policy and resource allocation; what the barriers, levers, and incentives of SHRH data collection, publishing, and sharing with stakeholders were. Recommendations were provided on specific areas where FCDO support could be critical. A second part of the data scoping for ONS intervention has involved collecting information to keep FCDO up to date on the finalisation of the Nigeria Demographic and Health Survey, NDHS 2024, which lost funding from USAID and is currently waiting to be published and disseminated. PMEL is also keeping track and regularly reporting to FCDO any useful information around the next census. This workstream received a quality score of 4.
5. TWP PERL VfM How-To-Note (March 2025) and think piece/blog (June 2025). The PERL TWP outcome case study produced prompted HMG colleagues to commission a follow-up demand-led study on TWP VfM. This was delivered in the form of a ‘How To’ Note on Conceptualising and assessing VFM in governance and diplomacy initiatives. The study was reviewed, finalised and well received by HMG Nigeria colleagues. This study received a quality score of 3.75. HMG colleagues further commissioned another product under this workstream: A Think Piece and accompanying blog on ‘Making the Value for Money (VFM) Case for Thinking and Working Politically (TWP): Evidence from PERL.’ These two additional outputs are in draft and expected to be completed by end of June 2025. PMEL also participated in two panel-based learning events on this theme organised by the Thinking and Working Politically community and by Palladium (see more detail under Output 2 learning below). This was an important element of projecting PMEL’s contribution to learning beyond the Nigeria office.
6. GEDSI review (April 2025): This demand-led study was designed to feed into a wider internal GEDSI review. It was delivered in two components: A set of GEDSI programme assessments on post-2018 HMG Nigeria programmes using a collaboratively designed rubric; and a broader GEDSI context analysis paper that included a set of ‘tractable opportunities’ for HMG Nigeria engagement on GEDSI. These products were well received by HMG Nigeria colleagues. This two-part study received an average quality score of 4.
7. Localisation review (April 2025). This demand-led study was commissioned by the FCDO Humanitarian team to review the efficacy of HMG Nigeria’s approach to localisation in its humanitarian response and draw lessons for future interventions. The study was well received by HMG Nigeria colleagues, who provided feedback that the analysis was ‘very useful to organise our thoughts and start to think through the way forward on localisation’.
8. USAID fallout implications and opportunities report (May 2025). This demand-led study was commissioned by HMG Nigeria Senior Leadership Team (SLT) considering the USAID hard stop to review its implications and opportunities for the portfolio. It was well received by HMG Nigeria colleagues.
9. HMG Nigeria’s Utilisation of Technical Assistance Review (May 2025). This study was commissioned by SLT to get a better understanding of HMG Nigeria’s utilisation of technical assistance to date, and review the benefits, challenges and what works well with TA approaches. It was well received by HMG Nigeria colleagues.
10. Nigerian UK Diaspora contributions Review (May 2025). This study was commissioned by the SET block to review the economic contribution of the Nigerian diaspora in the UK through work, business, higher education and remittances. This study was well received by HMG, who provided feedback that it was an ‘incredibly helpful report: informative and useful for various workstreams across the mission.
11. Social Protection programme review (June 2025): Under this demand-led workstream, PMEL produced two outputs to support the HMG Nigeria in its review of its social protection programme. The first PMEL output was to provide relevant evidence to support a Human Rights social protection grant proposal and the second was an Options Note to guide future HMG Nigeria social protection investment.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

As explained above, this evidence output was amended during the year to accommodate both the original data and evidence outputs. These changes include reworded output statements, revised rubrics and revised milestones – approved by SRO in January 2025. These changes have been captured in the change log tab of the logframe template.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

See para 114 below on progress on recommendations from previous AR which have all been completed. Lessons learned and recommendations for this output are captured in section A.

Output Title	Learning: Coordinated, evidence-led learning activity conducted to support portfolio-level learning and adaptation
Output number:		2	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	No

*See annex for rubric scoring interpretations
Indicator(s)	Milestone(s) for this review	Progress
Number, quality and utility of block, team and portfolio-level learning resources or instances	2 block/team events / 2 portfolio events / (Avg. quality score 3+)	Two block/team learning sessions held: / October 4, 2024 (UKNIAF successor evidence base presentation to SET block) and / March 31, 2025 (Localisation of humanitarian response presentation to humanitarian team). / Quality score 3.3 / Two portfolio learning events (Influencing working groups) delivered in November 2024 and February 2025. / In addition: / One national network learning event was delivered on the back of PMEL’s education sector demand-led workstream: / June 5, 2025: A PMEL team led by Dr. Liz Omoluabi presented at a Development Partner network learning event, sharing their Small Area Estimation method and its application at the Statistics DPG roundtable meeting at the World Bank Office in Abuja. / Three global platform learning events delivered on the back of the PERL TWP outcome case study: / November 22, 2024 at a plenary session of OECD/DAC Govnet. / December 4, 2024 at a session of the FCDO Governance cadre. / June 17, 2025 at a Palladium Conversation Series.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. We have scored output 2 an A+ because PMEL has exceeded its milestone targets by engaging with national and international lesson learning events while also maintaining high quality. PMEL Component 2 maps directly onto the logframe Outputs 2
2. Component 2 centres on synthesising and communicating relevant evidence from PMEL’s work across components 1 in accessible and impactful ways within block and portfolio learning spaces, with reflection, analysis and learning facilitated by PMEL.
3. The learning component is key to prompting portfolio-level strategic engagement (PMEL intermediate outcome) and strategic adaptation (PMEL outcome).
4. During the year under review, PMEL delivered two block/team-level learning sessions:
- On October 4, 2024, PMEL presented the findings (to SET block colleagues) of their review of UK engagement across Energy transition, decarbonisation and climate finance sectors in Nigeria over the past 10-15 years which fed into the design of a successor programme for the UK Nigeria Infrastructure Advisory Facility (UKNIAF) programme. The presented findings prompted in-depth discussion on the three sectors (energy transition, decarbonisation, green skills and industrial strategy, and climate finance).
- On March 31, 2025, PMEL presented the findings (to Humanitarian team colleagues) of their review of the efficacy of HMG Nigeria’s approach to localisation in its humanitarian response and lessons for future interventions. This session was well received and received an average quality score of 3.3.
During this year, PMEL also facilitated two cross-portfolio learning events through the formation of an Influencing Working Group, set up to drive cross-portfolio learning at the advisory level, with PMEL acting as Secretariat. The Group learns from political economy analysis (PEA) and other relevant data generated at the intervention level to improve evidence-based decision making:
- The first Influencing Working group meeting was held on November 21, 2024, with 21 participants from across the portfolio (not including PMEL team and external speakers). During this inaugural meeting, colleagues shared completed, ongoing and planned PEA work and discussed implications for strategy, programming and influencing (PMEL produced the minutes and action summary).
- The second Influencing Working group meeting was held on February 25, 2025, and was more narrowly targeted at advisors, with 10 participants from across the portfolio. Colleagues again shared completed, ongoing and planned PEA work and discussed implications and action points (PMEL produced the minutes and action summary).
1. Beyond the country office, PMEL colleagues presented at a national network learning event, delivered on the back of PMEL’s education sector demand-led workstream. On June 5, 2025, a PMEL team led by Dr. Liz Omoluabi presented at a Development Partner network learning event, sharing their Small Area Estimation (SAE) method and its application at a Statistics Donor Partner Group (DPG) roundtable meeting at the World Bank Office in Abuja.
2. Finally, PMEL was able to draw on its PERL TWP outcome case study to contribute to three global learning events during the year, promoting its evidence-based learning beyond the confines of the Nigeria office:
- On November 22, 2024, a PMEL consultant presented the findings of the PERL TwP outcome study to a plenary session of OECD/DAC Govnet titled ‘Working politically and working patiently: lessons from UK governance work in Nigeria.’ The PMEL consultant and former Team Lead for FCDO funded PERL programme were discussant in this session alongside the Director of the Thinking and Working Politically Community of Practice (TwP CoP).
- On December 4, 2024, a PMEL consultant presented the findings of the above study to a session of the FCDO Governance cadre. The session was well attended, provided visibility and shared learning for this flagship Nigeria governance programme internationally across the cadre.
- On June 17, 2025, the former Team Lead for FCDO funded PERL programme, PMEL consultants that led on the TwP and VfM-How-to-Note and PMEL team lead joined a panel discussion at a Palladium Conversation Series event on ‘Working politically, patiently and sustainably: Lessons from UK Governance work in Nigeria.’ moderated by the Director of the TwP CoP.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

The only change to this output was the output number – changed from output 3 to output 2.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See section para 114 below on progress on recommendations from previous AR which have all been completed. Lessons learned and recommendations for this output are captured in section A.
## D: VALUE FOR MONEY

Key cost drivers and performance
As a programme focussed on “coordinated learning” in support of portfolio adaptation and change, the key cost driver relates to personnel costs. In this regard the assessment reflects excellent Value for Money (VfM) delivered by the programme in managing this key cost driver, including driving down management costs.

Management costs as a percentage of total proforma value was 24% (reduced from 27% after the last contract amendment) but the team has achieved 19% (management costs as a percentage of total spend during the period under review).
	Revised Proforma	Actual Spend / Aug. 2023 – Mar. 2025*	%
Total	2,556,112	1,282,953	50%
Management	613,464	248,228	40%
%	24%	19%

*March 2025 was the last invoice submission for the quarter.

PMEL has continued to achieve significant savings on consultant fee rates and expenses. The table below reflects the % savings achieved through managing average fee rates down across both national and international staff members against the original proforma rates. This has been achieved without compromising the quality and delivery of expected outputs.
Weighted[6] mean daily fee rates for consultants
[6] Weighted by total number of days paid in the period.
	Average / proforma rates	July 2024 to March 2025* Average	Variance with proforma %
National	403	321	-20%
International	739	540	-27%

*March 2025 was the last invoice submission for the quarter.

VfM performance compared to the original VfM proposition in the business case

According to the Business case, it is expected that PMEL will increase the impact of BHC Nigeria ODA programmes sufficiently to deliver at least a 10% return on PMEL (based on quantifiable benefits alone) as well as “leverage value from the £100m already invested through BHC Nigeria’s portfolio by supporting better decision-making”.

The OPML team confirmed that due to the programme’s budgetary envelope, it will not be cost-effective to quantitatively assess the 10% return on PMEL, but they will qualitatively assess the leveraged value through better decision-making which is captured in a separate comprehensive annual VfM report.

Across the 5E’s of VfM, PMEL’s VfM framework uses rubrics that provide a programme specific definition of each criterion, sub-criteria and standards used as the basis for making evaluative judgements of the programme’s VfM; as well as the evidence used to assess VfM. This provides a clear and transparent basis on which the judgements are made. A separate assessment was completed to align with this Annual Review, and is summarised below:

Economy: PMEL has been judged to offer Excellent VfM against this criterion. PMEL continues to deliver good value for money in relation to the economy, consistently meeting budgetary benchmarks and showing potential for cost savings. The programme demonstrates effective cost control, with average management costs and unit costs for various roles consistently meeting benchmarks, often significantly falling below proforma rates. This is achieved through robust procurement processes, consistent negotiation of consultant fee rates, and leveraging existing retainership agreements.

Efficiency: PMEL has been judged to offer Good VfM against this criterion. PMEL has demonstrated agility and responsiveness to evolving HMG-N needs and learning requirements, evidenced by its offerings and logframe changes. The programme produces relevant and high-quality outputs that receive positive feedback, and it actively engages stakeholders, including FCDO, development partners, and government representatives, through regular updates and co-design approaches. Mechanisms like the Influencing Working Group were established to drive cross-portfolio learning and improve evidence-based decision-making.

Equity: PMEL has been judged to offer Good VfM against this criterion. PMEL prioritises Gender Equality and Social Inclusion (GEDSI) as a cross-cutting focal area, actively incorporating a GESI lens into its analysis and choice of knowledge products. Examples include the analysis of female enrolment in schools, the GESI stocktake, and the ISF de-radicalised women study. GESI considerations are also integrated into decision-making processes, contributing to discussions on HMG’s approach to GESI and informing learning events.
The core PMEL team is 50:50 male/female split. The core PMEL team and consultants are a mix of British and Nigerian experts in an almost 50:50 ratio who operate seamlessly and have delivered quality work products appreciated by primary users.

Effectiveness: PMEL has been judged to offer Good VfM against this criterion. PMEL shows adequate progress in facilitating decision-makers' engagement in policy reflection and use of evidence. Outputs such as demand-led studies and social protection monthly bulletins informed programmatic and strategic decisions as captured in previous sections. The Influencing Working Group aims to improve learning and evidence-based decision-making. However, there is an acknowledged need to proactively strengthen how evidence feeds into Country Strategy Board and Business Country Plan processes.

Assessment of whether the programme continues to represent value for money
18 months into implementation, PMEL is delivering significant VfM for HMG Nigeria. It has earned numerous positive feedback from FCDO colleagues for whom it provided demand-led knowledge products and evidence. In addition, through the assessment referenced in previous sections, the evidence provided by PMEL has been considered by the Senior Leadership in decision making which supports the overall value proposition of the programme –leveraging greater value from BHC Nigeria’s portfolio by supporting better decision-making. All the above provides sufficient evidence for the programme to continue.

E: RISK

Overview of risk management

1. Overall risk rating: This AR recommends maintaining the programme risk rating at Minor. No significant changes in the context that requires altering the risk rating.
2. To ensure effective risk management, PMEL’s risk register is regularly updated by the programme manager, reviewed by PMEL leadership team, and FCDO, and reported in the quarterly reports.
3. As of May 2025, there were eight active risks in the register that span across policy & programme delivery and public service delivery & operations categories. Four of these risks have a moderate residual risk rating and four have a minor residual risk rating.
4. The regular bi-weekly interactions between the PMEL team and SRO, Statistics Adviser and Programme Manager helps with prompt risk identification and mitigation. In addition, regular catchups between the SRO and Statistics Adviser also facilitated the co-creation and review of the mitigation approaches.
5. The four risks with ‘moderate’ residual rating are related to: PMEL’s inability to generate sufficient work to utilise available budgetary resource; potential impact of HMG Nigeria blocks and teams’ non-engagement with PMEL; unwillingness of blocks and teams to share relevant programme and block level data; and the risk of data privacy policy breach (upgraded from minor).

1. OPM is mitigating these moderate risks by improving its visibility across the office (was able to secure regular attendance at the delivery board this year), minimising administrative burden on HMG Nigeria staff, effectively communicating the value offering of PMEL as well as strengthening engagement with HMG Nigeria staff to demonstrate value and adopting a co-delivery and co-learning approach with HMG Nigeria colleagues. Regarding the privacy policy breach, PMEL team members have relevant security clearances and all contracts include confidential information clauses. The programme also has an agreed confidentiality policy with OPML.
2. The four risks with ‘minor’ residual rating relate to: unfavourable political economic conditions in Nigeria; external stakeholders unwilling to share information or provide access to the project team; the risk of poor data quality or insufficient data available or generated at the programme level to answer strategic questions for PMEL (downgraded from moderate to minor); and the risk of delay from stakeholders in providing information to the PMEL team.
3. Mitigation strategies in place for these minor risks centre on updating PEA analysis for the project implementation, open and honest communication towards stakeholders on needs and uses of information and leveraging OPML team’s experience and approaches for operating in environments with limited data quality.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
1. In the year under review, OPML initiated and completed a contract amendment to (i) make changes in key programme leadership (ii) make changes in inception deliverables (iii) provide an additional pool of experts to undertake the necessary skill set for various studies, and (iv) make changes in contract key performance indicators.
2. These amendments were driven by clearer understanding of the demand and needs of HMG Nigeria colleagues, with the recognition that the programme is designed to be dynamic and responsive. No additional funding was required under the contract amendment.
3. There is need for another contract amendment to capture additional pool of experts for potential studies. This amendment also does not require any additional funds.
4. In the Supplier Relationship Management (SSRM) Performance Scorecard, OPM scored 93% for the period covering Oct. 2024 till March 2025.
5. According to the agreed contract KPIs, PMEL has consistently performed beyond the agreed threshold of 450 on the KPI scores for delivery and quality, financial management, strategic partnership and stakeholder relationship, safeguards and cross-cutting priorities by FCDO’s judgement. In the latest quarter, January – March 2025, PMEL was scored 510 - the highest since its inception (see PMEL KPI score trend graph below) which reflects the supplier’s improving performance on this contract over time.
PMEL Contract KPI Scores

A total of £1.27m (£386k in Y1, £886k in Y2) has been spent on the programme since inception until March 31, 2025; which is about 42.4% of total programme life cycle budget of £3m.

OPM submits financial statements and forecasts alongside narrative reports quarterly. The PMEL team is fully aware of FCDO financial requirements including the annual project audit.

1. OPML has improved in financial forecasting variance which was previously above the 5% agreed threshold. Based on the suggestion of the SRO, PMEL implemented a monthly financial review to track and improve spend. An increase in demand-led studies based on the appetite of HMG Nigeria colleagues contributed to improving resource utilisation. This year, OPM has reported a steady reduction in variance over the past three quarters 7% in July to September 2024, 3% in October to December 2024, and -0.2% in January to March 2025.
2. FCDO plans to commission the first independent financial and programme audit of the Nigeria PMEL programme to cover August 2023 - March 2025. The audit aims to provide assurance on the use of programme funds for intended purposes and help stakeholders understand risks that could jeopardise the delivery of the programme, with expected recommendations for programme and financial management. The spending pause directive from HQ has impacted the contracting timelines for the audit process. The expected audit opinion from this exercise, once commissioned and completed, will be noted in the next annual review report.

To provide further assurance to senior management, we have obtained a copy of OPML’s global audited financial statement for 2024, and we have no concerns about OPML’s financial stability.

OPML has not procured, and does not plan to procure, any assets or equipment for the PMEL project. If this happens, OPM will monitor all equipment in its possession or control through assets registers.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
PMEL's SRO, Statistics Adviser and Programme Manager maintain regular communication with PMEL through bi-weekly update meetings.

During these meetings, the PMEL team presents an update on progress against each component, flags issues arising and outlines next steps. SRO feedback and discussion around this update then informs PMEL decision making for the next two weeks.

In addition, the PMEL SRO and Statistics Adviser are in frequent ad hoc communication with the PMEL team leader and component leads around specific issues as they arise.

The PMEL team provides a quarterly report which provides a formal summary of progress across each component, on the finances and risk elements as well.

As part of the Annual Review process, HMG-N colleagues who were primary beneficiaries of PMEL’s products were invited to provide beneficiary feedback using the rubric-based scoring tool developed to map onto the programme logframe. The feedback has been captured in previous sections above.

The scoring of the logframe indicators follows the steps below:
- Share surveys with few questions with primary beneficiaries of PMEL work products at output, intermediate outcome, and outcome levels.
- The survey questions are scored on a rubric scale of 1 (lowest) – 4 (highest). The meaning of each score is included in the annex below.
- The simple average of the scores is calculated and returned as the indicator quality score and assessed against the milestone to determine output, intermediate outcome and outcome progress.

A summary of the logframe changes capture three significant shifts in the way that the programme operates and its progress is measured. This review has confirmed that those changes are fit for purpose.
1. The distinction between outputs 1 (data) and 2 (evidence) - the original specification of two separate outputs labelled ‘data’ and ‘evidence’ - started to lose its utility during the year under review. This happened as the PMEL team began to respond to an increasing number of demand-led requests for analytical studies, designed to capture learning to feed strategy and programme reflections. These studies integrated data generation with analysis so that the component label ‘data’ became misleading, with a false assumption of data generation as a discrete activity. At the same time, the outcome case-study pipeline of work continued, this also combined data generation and analysis. The decision was therefore taken with the PMEL SRO to combine these two outputs into a single ‘evidence’ output, with two discrete output indicators capturing ‘outcome case studies.’ (output 1.1) and ‘demand-led studies’ (output 1.2).
2. As a result of the above merging of outputs 1 and 2, output 3 (learning) was relabelled as output 2. At the same time, feedback from the Statistics Adviser confirmed that the programme assumption that country office learning could be accurately captured by measuring learning ‘events’ was false. Much learning happened in more informal and internal ways and this was being missed under the current metric. With approval of the PMEL SRO, the narrow focus on learning ‘events’ in the learning output indicator statement, indicator and accompanying rubric were therefore changed to capture ‘portfolio-level learning resources or instances’ more broadly.
3. At the intermediate outcome/outcome level, the team reflected that it was no longer accurate to limit measurement of evidence uptake by HMG Nigeria to a change in the incidence of ‘adaptive strategies.’ This narrow metric did not capture evidence uptake adequately. In fact, evidence uptake was seen more broadly in the transparent, embedded and instrumental use of evidence across the office. Through discussion with the PMEL SRO, the PMEL team formulated a new set of rubrics to capture more meaningfully the ‘quality of uptake’
Evidence
There have been limited changes in evidence sources or requirements during the implementation period to date. These continue to combine desk review with key informant interviews and some limited fieldwork involving focus group discussions and semi-structured interviews. The only significant addition to primary data collection suite of methods was to secure approval for a telephone poll survey to measure the poverty and social impact of the cost-of-living crisis on cash transfer beneficiaries.
Learning
1. During this first full year of implementation the programme has supported learning at block, team and portfolio level, as well as extending its ambition to influence national network learning and global learning platforms. These are detailed under output 2 above.
2. This Annual Review process itself provides an opportunity for the PMEL team to reflect on its utility and performance based on HMG Nigeria colleagues’ assessment as well as leveraging this for adapting its approach as it moves into the next 12 months of implementation.

Date of last narrative financial report	May 19, 2025	Date of last audited annual statement	March 31, 2024

Progress on 2024 Annual Review Recommendations
	2024 Recommendations	Progress
1	OPML to provide required details for the completion of its contract amendment:	OPML provided the required information and that contract amendment was concluded.
2	FCDO to ensure PMEL engages all delivery teams and blocks	FCDO has supported the PMEL team to achieve this during the period under review.
3	OPML to improve on its financial forecasting	FCDO has supported PMEL on this and the forecast variances have reduced significantly as at last quarter.
4	OPML to consider building buffers in its timelines	From discussions with the SRO and Statistics Adviser, the PMEL team have built sufficient buffers in their timelines
5	OPML Logframe Review	The logframe review was completed and approved in January 2025.
6	OPML to include an additional risk around the uptake of the learning and outcomes from their work.	From subsequent discussions, the team decided not to include this risk. Rather, regular discussions were held with the PMEL team during the bi-weekly discussions to ensure internal organisational nuances were considered by the PMEL team before suggesting new workstreams and events.

Annex – Rubric Scoring Definitions and Interpretations

Outcome Indicator Rubric Scoring
	Rubric score 1 (Lowest)	Rubric score 2	Rubric score 3	Rubric score 4 (Highest)
Rubric statement	Evidence discussed but poorly understood	Evidence use is transparent, reflecting an increased understanding of evidence by decision-makers	Evidence use is transparent and embedded in processes, systems and working culture	Evidence use is transparent, embedded and instrumental, directly informing portfolio strategies, programmes and initiatives
Rubric definition	HMG-N colleagues engaged minimally in translating evidence in to learning.	HMG-N colleagues clearly understand the evidence and are able to interpret its significance to their work.	PMEL evidence uptake by HMG-N colleagues is widespread across the office and becomes embedded in decision making processes.	There is a clear pathway from PMEL evidence uptake contributing to the content of portfolio strategies, programmes and initiatives
Intermediate Outcome Indicator Rubric Scoring
	Rubric score 1 (Lowest)	Rubric score 2	Rubric score 3	Rubric score 4 (Highest)
Rubric statement	Limited or no engagement during and after the event.	Significant engagement during the event but no follow-up cross-portfolio discussion.	Significant engagement during the event and significant follow-up cross-portfolio discussion.	High level of engagement during the event and highly significant follow-up cross-portfolio discussion
Rubric definition	Very poor attendance by HMG-N colleagues, highly passive during the event and with no engagement in taking learning outcomes into their own work.	Adequate attendance by HMG-N colleagues, passive listening during the event but no engagement in taking learning outcomes into their own work.	Good attendance by HMG-N colleagues, active listening during the event and some engagement in taking learning outcomes into their own work.	Very good attendance by HMG-N colleagues, active listening during the event and strong engagement in taking learning outcomes into their own work.
Output 1 Indicator Rubric Scoring
	Rubric score 1 (Lowest)	Rubric score 2	Rubric score 3	Rubric score 4 (Highest)
Rubric statement	Poor quality of content, low research rigour, and minimal importance	Reasonable quality of content, sufficient research rigour and important	Good quality content, robust research and highly important	High quality content, highly robust research and highly important
Rubric definition (Content)	Data collected did not satisfy research needs. The research failed to build on and extend on existing knowledge.	Data and information collected left some gaps in answering the research questions. The research marginally added to what was already known in the field.	Data and information collected were largely sufficient. The research presented fresh ideas on an existing issue.	Data and information collected covered all research needs. The research elicited and explored a new, emerging issue.
Rubric definition (Rigour)	Analysis and conclusions were weak and largely unsupported by the data. The evidence base was not trustworthy, based wholly on single sources of evidence.	Some analysis and conclusions were not consistent with the data or lacked a clear read through from evidence to analysis and conclusions. The trustworthiness of the evidence base was weak, based largely on single sources of evidence.	Analysis and conclusions were largely consistent with data with a logical read through from evidence to analysis and conclusions. The trustworthiness of the evidence base was good, based largely on triangulated sources of evidence.	Analysis and conclusions were robust and wholly consistent with data and based on a logical read through from evidence to analysis to conclusions. The trustworthiness of the evidence base was excellent, based wholly on triangulated sources of evidence.
Rubric definition (Relevance)	The research was not relevant to HNG-N priorities/goals or its operation as a portfolio.	The research was marginally relevant to HMG-N priorities/goals or its operation as a portfolio, and issues that may demand solutions in the foreseeable future.	The research was relevant to HMG-N priorities/goals or its operation as a portfolio, and issues that may demand solutions in the foreseeable future.	The research was highly relevant to key HMG-N priorities/goals or its operation as a portfolio, and issues that may demand solutions in the foreseeable future.
Output 2 Indicator Rubric Scoring
	Rubric score 1 (Lowest)	Rubric score 2	Rubric score 3	Rubric score 4 (Highest)
Rubric statement	Low quality event with low value learning outcomes	Reasonable quality event but low value learning outcomes	Good quality event and useful learning outcomes	High quality event and highly useful learning outcomes
Rubric definition (Event Quality)	The event was poorly designed and completely lacked an effort to engage and interest participants.	The event was adequately designed to engage participants, but in didactic mode with largely passive reflection and learning.	The event was well designed, engaging participants actively in reflection and learning.	The event was extremely well designed, using a mixture of media and techniques to engage participants actively in reflection and learning.
Rubric definition (Learning Outcomes)	The event did not generate purposefully discernible learning outcomes.	Adequate facilitation generated a set of learning outcomes but without a clear emerging consensus and little or no momentum built for utilising this learning.	Good facilitation generated a clear set of learning outcomes and some agreement around how this learning could be utilised.	Excellent facilitation brought a strong shared learning and built strong momentum for how this learning could be utilised.