## UKSIP Annual Review 2024

Title: The UK Sustainable Infrastructure Programme Latin America (UKSIP)
Programme Value £ (full life): up to £177.5m		Review date: 1 January – 31 December 2024
Programme Code: 301516	AMP start date: November 2017	AMP end date: December 2029

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024
Overall Output Score	B	B	B	B	A+	A+	A
Risk Rating	Moderate	Major	Major	Major	Minor	Moderate	Moderate

DevTracker Link to Business Case:	Business Case / Business Case Addendum
DevTracker Link to results framework:	Results Framework

A. SUMMARY AND OVERVIEW

Description of programme

The UK Sustainable Infrastructure Programme (UKSIP) is a bilateral programme funded by the Foreign, Commonwealth, and Development Office (FCDO) and delivered by the Inter-American Development Bank Group (IDBG). The programme was managed by the UK’s Department for Business, Energy and Industrial Strategy (BEIS) and transferred to FCDO in April 2022. The Programme has approved funding for up to £144m CDEL for blended finance investments and £33.5m RDEL for technical assistance (including £2.5m set aside for monitoring and evaluation of the programme) by the year 2029.
[note] Blended Finance is a strategic tool to mobilise private capital through the targeted use of concessional funding in high-impact projects in which actual or perceived risks are too high for commercial finance alone (see Blended Finance | IDB Invest)
[note] Figures reflect a recent Business Case Addendum which swapped £6m of uncommitted CDEL to RDEL, overall budget envelope is unchanged

UKSIP supports countries in Latin America and the Caribbean (LAC) to reduce emissions, adapt to climate change, ensure infrastructure and communities are resilient to its effects, and invest in cost effective nature-based solutions through technical assistance (TA) and blended finance investments.
[note] Under Phase 2 the following countries are in within scope of UKSIP: Colombia, Peru, Brazil, Mexico, Haiti, Belize, Dominican Republic, Jamaica, Suriname, Guyana, The Bahamas, Barbados, Trinidad and Tobago, Honduras, El Salvador, Guatemala, Costa Rica, Panama

UKSIP is delivered through two arms of the IDB Group: The Inter-American Development Bank (IDB), which leads UKSIP’s TA to the public sector and IDB Invest, which leads UKSIP’s blended finance investments and the TA to the private sector.

UKSIP is important to the UK’s relationship with IDBG and its shareholder objectives. UKSIP is the first IDBG trust fund to support deeper collaboration between IDB and IDB invest bringing together IDB and IDB Invest operations within a single fund and ToC, demonstrating the value of combined operations to achieve impact. UKSIP funding, for both TA and blended finance, has helped IDB and IDB Invest to develop their expertise in novel and challenging markets where private capital mobilisation can have significant developmental impact, IDBG has a new institutional strategy with greater emphasis on climate mitigation, adaptation, and resilience, and IDB Invest has substantively evolved its strategy, including by committing to adopt an ‘originate to distribute’ business model.

2024 marks the first year of implementation of Phase 2 of UKSIP which brings the following changes agreed in a Business Case Addendum;
1. Extension of the programme lifetime to December 2029;
2. Expansion of the programme’s thematic scope to include adaptation and resilience, and nature-positive activities alongside low-carbon sustainable infrastructure;
3. Expansion of geographic scope - adding Haiti, Belize, Dominican Republic, Jamaica, Suriname, Guyana, The Bahamas, Barbados, Trinidad and Tobago, Honduras, El Salvador, Guatemala, Costa Rica, Nicaragua, and Panama alongside Mexico, Colombia, Peru, and Brazil.
4. A commitment from IDBG to reinvest programme reflows within this scope.

UKSIP is supporting the delivery of shareholding objectives in Phase 2 by piloting approaches that can be scaled across the Bank - e.g. increasing focus on A&R, nature, and climate-vulnerable geographies, and supporting the shift an originate-to-distribute business model.

Governance updates were implemented in 2024 to underpin this (see programme management section).

Summary supporting narrative for the overall score in this review
UKSIP scored an A. Across all three Output categories (public sector TA, private sector TA, and blended finance), UKSIP scored a minimum of an A, and scored A+ for Output 1, public sector TA.

Programme scores are determined by delivery against output indicators and mutually agreed milestones. An "A" rating signifies strong performance in line with expectations and reflects successful delivery against challenging targets. "A+" scores - such as those achieved in 2022 and 2023 - indicate exceptional outperformance, and they are therefore definitionally rare and not sustainable over time. If consistently achieved, they would suggest that milestones were set too low and require recalibration. As a result, the best possible reasonable scoring outcome for a programme over its lifetime is a mix of “A”s and “A+”s.

UKSIP met and in some cases exceeded its public sector (Output 1) and private sector (Output 2) TA targets. UKSIP outperformed on Output 1.2 - number of tools, methodologies and approaches developed that enable sustainable low carbon, adaptation and resilience or nature based investments. UKSIP also outperformed targets on Output 1.3 - number of engagements that increase visibility of UKSIP and increase national ambition, for example through supporting the Energy Transition Agenda of the Ministry of Mines and Energy in Peru through an extensive comms campaign (including a video featuring HMA Lima) on clean cooking in the City of Cuzco, lessons from which are feeding development of future government programmes in this sector.

One blended finance investment closed in 2024. The BRK Ambiental Maranhão UKSIP investment consists of a senior loan of $5m and a performance-based incentive grant of $4m. The transaction built on UKSIP’s previous support for large scale public-private partnerships in the Brazilian water sector and used UKSIP concessional finance to incentivise energy efficiency and social development measures. The shifts in programme scope, both thematically and geographically, have added complexity to deal origination and closure. A share of programming is expected to be directed toward smaller and less mature markets, where transaction sizes are smaller and market inertia and barriers slow down the deployment of resources.

2024 Recommendations from the 2023 Annual Review	Progress/achieved?
Updated programme governance: In light of the programme’s expanded scope following the agreement of UKSIP’s extension, FCDO and IDB should update the programme’s Theory of Change, LogFrame, and Management Arrangement. We will also re-project the LogFrame milestones with IDB to ensure they are (a) stretching, and (b) achievable within resources available under Phase 2, as significant outperformance of some milestones in 2023 suggests that current milestones underestimate IDB delivery capacity.	Theory of Change and Logframe updated with new milestones.
Private capital mobilisation measurement: Effective measurement is a cornerstone of programme delivery. From 2024 onwards, IDB and FCDO should use the OECD DAC’s methodology on private capital mobilisation.	Implemented in the latest reporting for ICF KPI 12, Volume of private finance mobilised for climate change purposes because of ICF’.
Prioritise delivery under UKSIP’s new scope: In Phase 2 UKSIP will have an expanded scope. IDB and FCDO should prioritise delivery of programming (technical assistance and blended finance) towards new themes and areas. Geographically that includes Caribbean and Central American countries, and thematically that includes adaptation and resilience, and nature-positive activities, with a requirement that all new TA programming include a gender equality, disability, and social inclusion (GEDSI) component.	This has been prioritised so far, with two new technical assistance projects and two of the three most recent blended finance investments all delivering in the Caribbean with the majority focusing on either adaptation and resilience or nature-based solutions.
Improve communications processes and delivery: Communication of impact is central to UKSIP’s Theory of Change. ‘Demonstration effects’, replication, and scale are only possible through dissemination of information. IDB and FCDO should adopt a strategic approach to all programme communications to maximise the potential for replication and scale. At minimum, this should include agreed objectives, audiences, and desired impacts for every piece of communications associated with the programme.	A new communication strategy and visibility plan has been launched, and new format of TA meetings to focus more on strategic coordination and opportunities including comms. A brief review of the new TA meeting format provided suggestions to improve efficiency and effectiveness.
Replication and the demonstration effect: The fundamental objective of UKSIP’s blended finance programming is to encourage replication of business models through demonstration. FCDO and IDB should, using the transformational change narrative as a foundation, review the extent to which programme interventions are encouraging replication through demonstration, and produce recommendations for the 2024 Annual Review which identify mechanisms through which this can be enhanced.	This has been achieved by implementing lessons from previous operations. In water and sanitation, insights from the Aguas do Rio projects informed the structuring of BRK Maranhão, with shared features helping to streamline the process. In addition, during the structuring of pipeline operations within funds, similarities enabled faster execution.
Description of impact: UKSIP has a broad portfolio of TA and blended finance projects and it is critical that the UK and IDB are able to communicate their impacts succinctly and with clarity. IDB should update the tables of TA and blended finance reporting included in their donor reports from 2024 onwards to follow a ‘IDB did X with Y partner to achieve Z outcome’ or similar format.	Details regarding TA work and the specific partners involved in attaining the desired objectives are documented in the annual report, notably within the Logframe chart. For public sector TA work, this information is now consolidated into a dashboard that is updated bi-monthly
Earlier delivery of IDB’s annual report: UKSIP’s annual review cycle is out of sync with other development programming delivered by FCDO, and means that annual reviews are completed well-into the following review period. IDB should aim to provide an early draft of its annual report to allow the Annual Review to be completed earlier in the year, in line with other FCDO programmes.	The IDB has delivered the Annual Report on time, in accordance with Article 9.3 of the Second Amended and Restated Arrangement Regarding the Establishment of the UK Sustainable Infrastructure Program, which requires submission of the Annual Report no later than April 30th each year

Major lessons and recommendations for the year ahead

Reflows
Discuss and confirm the appropriate ratio of TA and blended finance funding to be supplied from fund reflows at the UKSIP annual meeting. The programme has significant resources available for the blended finance window, and significant constraints on funding for the technical assistance window. Phase 2 has also moved UKSIP into more challenging markets and segments where blended finance transactions will often be smaller. The FCDO and IDB should explore the scope to, for a defined period (e.g. a year), amend the current 80-20 funding split agreed for reflows, whereby the blended finance window receives 80% of available funds from reflows each year and the technical assistance windows receive 20%. This will maximise UKSIPs ability to fund impactful projects year on year and allow efficient employment of available resources.

Post engagement
- Broaden UK Embassy engagement with and understanding of UKSIP, supporting opportunities for UKSIP investment and catalysing delivery of UKSIP projects:
  - Blended Finance is a central component of UKSIP’s value proposition. In Colombia and Brazil, it has enabled pioneering, high-impact projects that align with host country priorities and contribute to technical and market development. To improve Embassy engagement with this offer, the UKSIP Programme Team and IDB Invest should collaborate to identify ways to enhance awareness and understanding among Embassy staff. This could include facilitating opportunities for posts to share potential investment leads and build relationships with IDB Invest country investment officers.
  - The UKSIP Programme Team and designated post contacts should work together to encourage broader engagement across Embassy teams whose work intersects with UKSIP’s objectives. This cross-team collaboration will enable UKSIP to better leverage UK expertise and relationships, thereby enhancing the effectiveness and impact of project delivery.

Describing programme impact
- Develop a new high-level impact statement that captures the expanded Phase 2 scope. Enabling better clarity in communicating UKSIPs purpose supporting understanding and easing engagement with UKSIP by expert and non-expert stakeholders.
- Develop sector-based impact narratives that identify and describe the systematic change delivered by programme interventions (public sector TA, private sector TA, and blended finance) in different sectors. Drawing out lesson learning and synergy in the portfolio across contexts, and drawing on IDBG advisor sector networks to build a narrative of the cross-cutting programme impact and potential to deliver systemic change that we can communicate with clarity to non-expert stakeholders building visibility and understanding of the programme, creating opportunities for broader shared learning, collaboration and informed decision making

Strategic direction
- Review and update the UKSIP transformational change narrative. As noted in the previous annual review, encouraging replication through the demonstration effect of UKSIP interventions remains a fundamental aim of the programme. However, this cannot easily be quantified, and specific attribution is difficult to measure. Qualitative measures, such as UKSIP’s transformational change narrative and assessment against ICF Key Performance Indicator 15 are often the best substitutes. We recommend that IDB review the transformational change narrative and update it, where appropriate, with new examples from the programme (e.g. FX EDGE, ReInvest+).
- Prioritise delivery of adaptation and resilience and nature-based investments. Engage with HMG inhouse expertise including climate teams at post, and with IDBG during project development and delivery, ensure that discussing progress on this is a regular agenda point of formal meetings outlined in the management arrangement (on TA, BF and as part of the strategic annual meeting) We should also ensure close monitoring of these projects, including use of disaggregation to highlight the projects that deliver on these themes and ensure lessons learned are captured and disseminated effectively to enable demonstration of or encourage replication of impact.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

UKSIP aims to increase private sector investment in sustainable infrastructure, adaptation and resilience, and nature positive projects by addressing market barriers that inhibit access to global capital markets. It has 3 components:

1. Technical Assistance to the Public Sector to create improved enabling policy/institutional/regulatory environments for private investment in sustainable infrastructure.
2. Technical Assistance to the Private Sector to improve the project pipeline for sustainable infrastructure projects by directly supporting the private sector. At the pre-investment stage, this includes support to develop pre-feasibility reports and different forms of assessment, and at the investment stage this includes support to structure transactions and identify investors. This TA contributes to a pipeline of investable projects for UKSIP and IDB Invest more widely.
3. Concessional blended finance to de-risk investments and attract private capital into novel and innovative projects.

The Theory of Change (ToC) is shown below. This was updated in 2024 to capture the programme’s expanded scope,

- Output 2.3 and Outcome 3.5 were updated with references to adaptation and resilience, and nature, and Outcomes 3.1 , 3.3, 3.4 and 3.5 to cover the wider geographic reach.
- References to improving buy-in for NDC ambition on sustainable infrastructure under Outcome 3.2 and Impact 4.2 have been removed –while this remains important, the programme cannot attribute a direct contribution.
- A change was made to include “private sector sees benefits and invests in the low-carbon sector (demonstration effect)” to Outcome 3.5 – this is to highlight the benefit of demonstration effects of UKSIP interventions.

Progress toward outcomes
2024 is a transition year for UKSIP towards an expanded Phase 2. Delivery under the new scope did not substantively begin until 2025 as such, this Annual Review principally focuses on the original scope of the programme i.e. supporting four partner countries to achieve greenhouse gas emissions reduction commitments and mobilising private investment into low carbon sustainable infrastructure in Brazil, Colombia, Mexico and Peru.

Outcome Indicator 1 monitors the change in the enabling environment for low carbon sustainable infrastructure, adaptation and resilience and nature investments through UKSIP public sector technical assistance. UKSIP met its milestone for Outcome Indicator 1 in 2024 by providing technical assistance that led to the adoption of 2 policies and regulations. Of note is UKSIP’s work with the Brazilian Government on EcoInvest (see below case study.) Another TA project has supported technical studies for the Government of Colombia supporting development of a low carbon public transport system.

IDB Invest surpassed 2024’s milestone for Outcome Indicator 2 – which measures the number of projects reaching financial close that receive support from both UKSIP technical assistance and blended finance - by reaching financial close on one blended finance project, BRK Ambiental Maranhão.

The Phase 2 redesign has also introduced three new Outcome Indicators;
Outcome Indicator 3 measures the number of blended finance investments and technical assistance projects which contribute to GESI outcomes, reflecting the enhanced focused on social development co-benefits from programming in Phase 2. IDBG exceeded the Outcome Indicator 3 LogFrame target.

Outcome Indicator 4 measures the impact of UKSIP TA on the IDB Invest pipeline of projects that may not be financed through UKSIP Blended Finance – to build a broader picture of the impact of UKSIP funding within IDB Invest beyond the programme. There is no target as this has been newly introduced – IDBG plan to provide first reporting on this Indicator in 2025.
Outcome Indicator 5 measures the geographic diversification of UKSIP, reflecting the ambition in the ToC to deliver impact in the widest possible range of UKSIP countries. As Phase 2 was still developing in 2024 the programme had not yet moved beyond the original 4 countries however, this is already happening in 2025 and will be recorded in the next review.
Indicator	Progress
Outcome 1 - Number of low carbon related policies reflected in planning and procurement processes and/or infrastructure investments. / Milestone: 2	Achieved: 2 / EcoInvest 1st blended finance auction of USD 1 billion concessional finance – Brazil / Consultation of tender documents for the purchase of 296 electric buses for Bogota – Colombia
Outcome 2 - Number of low carbon infrastructure projects which reach financial close that have benefited from UKSIP TA / Milestone: 0	Achieved: 1 / BR-G1025 & BR-L1646 BRK Ambiental Maranhão
Outcome 3 - Number of investments and TC activities which contribute to GESI outcomes / Milestone: 1	Achieved: 6 / Public TA - 3 / Studies to support Ministry of Transport in developing technical and institutional capacity to integrate environmental, social and governance (ESG) for sustainable infrastructure projects and develop risk management analyses and mitigation strategies. – Brazil / A diagnosis and assessment of access to and use of electricity and essential services by the low-income population – Brazil / Study to understand women safety perception in Mexico City’s Public Transport – Mexico / Private TA – 2 / A study to assess the current Colombian regulation for renewable plants dispatch to the system and illustrate its impact on private energy producers’ revenues. And bankability. / An analysis of the impacts of allowing vertical integrations within the Peruvian energy market / Blended Finance – 3 / Promoting gender, diversity and inclusion in the supply chain of water and sanitation projects - Brazil
Outcome 4 - Number of UKSIP TA interventions which have led to IDB Invest financial mandates, including a breakdown of which investments are mitigation-focused, A&R-focused, or Nature Positive-focused / Milestone: N/A	N/A
Outcome 5 - Geographic Diversification: Number of UKSIP target countries with a minimum of either one TC component delivering impacts in-country or a blended finance investment in-country / Milestone: 4	Achieved: 4 / Brazil / Colombia / Mexico / Peru

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

There is strong evidence that UKSIP should continue to operate. Across all outputs and outcomes, IDB met, and in many cases exceeded, performance milestones for 2024. The programme continues to perform well against the full set of value-for-money assessment criteria.
The newly approved Business Case Addendum provides the programme with flexibility to align with changing context and FCDO development priorities. As noted in the ToC section above, 2025 has already seen multiple projects approved and begin implementation within the expanded scope. This is evidence that the programme has been able to adapt its delivery model to begin to meet the ambition of the expanded scope.

The Mid-Term Evaluation in 2023 found through discussion with stakeholders that “there is strong belief in the potential of UKSIP projects to achieve significant impacts.” Although there has been some slowdown in delivery this year in preparation for Phase 2, speaking to stakeholders again for this review has shown broad positive sentiment about the impact of this programme both developmentally as well as strategically through promoting UK visibility benefitting relationships with key regional partners. In addition to this the latest ICF KPI 15 reporting found that UKSIP had progressed to a stage of beginning to show “partial evidence” of transformational change.

Based on the history of strong delivery, the positive sentiment within the network and the launch of new projects in the expanded scope. We continue to see the potential for UKSIP to increase pace of delivery and begin to achieve its potential to deliver significant impact.

UKSIP is still the only private sector focused programme the UK is delivering in Latin America and the Caribbean, complementing the UK’s offer in Africa and Asia. As the Business Case Addendum notes, the significant development and climate financing needs in the region remain, and the expansion to Phase 2 brings further priority climate vulnerable countries including small island developing states into that scope. UK visibility through UKSIP can improve the strength of key UK country partnerships in the region and can provide opportunities where there are limited other sources of funding for financing innovative impactful projects.

## C. DETAILED OUTPUT SCORING

Output Title	Improved policy or regulatory environments and capacity to deliver Sustainable, resilient and natural infrastructure (Public Sector Technical Assistance)
Output number:		1	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)		Milestone(s) for this review	Progress
Output 1.1 / Sustainable low carbon infrastructure, adaptation and resilience, or nature policies or regulations adopted that have received support from SIP technical assistance activity. (actual).		2	Achieved: 2 / 2024-2027 Strategic Plan (Transport) – Brazil / Public bike system in the downtown area of the city of Oaxaca – Mexico
Output 1.2 / Number of relevant public sector institutions that have adopted methodologies, tools, and approaches to promote sustainable low carbon infrastructure, adaptation and resilience, or investment in nature as a result of UKSIP TA (actual).		8	Achieved: 20 / Brazil / • BR-T1529 / Ministry of Mines and Energy (MME) - A diagnosis and assessment of access to and use of electricity and essential services by low-income population and detailed analysis of the situation of the low carbon hydrogen market . / Energy Research Company (EPE) - H2+Brazil Platform prototype, technical assessment of recommended technology and infrastructure, user experience analysis for H2+Brazil Platform, and software requirement specifications. / Chamber of Electric Energy Commercialisation (CCEE) - Evaluation of trends and probabilities for the future evolution of the Brazilian electricity market and roadmap for CCEE. / • BR-T1478 / Brazilian Ministry of Ports and Airports - Procurement documents and guidelines for contracting a Mobility as a Service (MaaS) platform, a study regarding Sustainable infrastructure components, and a study was developed and provided a pilot for new business models and procurement in sub-utilised railway sections. / • BR-T1607 / Brazilian Ministry of Finance - Design of blended finance and the liquidity facilities, developed blended finance auction, and development of a programme manual for EcoInvest. / Colombia / • CO-T1663 / Colombian Superintendency of Public Utilities - Design an institutional strengthening programme. / Municipality of Orito - A pre-feasibility study to identify, diagnose and formulate a generation system based on non-conventional renewables that will support the creation of an Energy Community. / • CO-T1671 / TransMilenio - A consultancy for the technical, technological, economic, legal and financial structuring of the alternatives for the electrification of the fleet and the general operation of the El Vínculo. / City of Montería - Technical assistance for the implementation of zero emissions technology fleet in the public transport system. / Bogotá’s Secretariat of Environment – A consultancy to develop documents to hire the administrator of an autonomous trust to support the financing of small freight transport operators in transitioning from conventional trucks to electric freight vehicles. / Departamento Nacional de Planeación (DNP) – Support to close the skills gaps in the railroad sector in Colombia. / Mexico / • ME-T1451 / Metropolitan Area of Pachuca – A study to improve the quality of the service of public transport in the Metropolitan Area of Pachuca. / State of Nayarit - A sustainable mobility study for the state of Nayarit. / City of Oaxaca - Design of the public bike system in the city’s downtown area and a study for managing and implementing pedestrian streets and parking around the main city plaza. / • ME-T1494 / Federal Commission of Electricity (CFE) - Organised workshops for the Green Hydrogen Working Group. / National Institute of Clean Electricity and Energy (INEEL) – Workshops of the Green Hydrogen Working Group. / • ME-T1500 / Water utility of Ciudad Juárez (Chihuahua) – List of EE identified projects partially implemented and still being discussed. / Water utility of La Paz (Baja California Sur) – List of EE identified projects partially implemented and still being discussed. / Peru / •PE-T1523 / Peruvian Ministry of Energy and Mines (MINEM) – Energy auditors pilot training. / • PE-1524 / City of Juliaca – Consultancy to analyse the potential of wastewater reuse in a major city
Output 1.3 / Number of engagement events with UKSIP / partner governments / (Ministerial and/or senior official participation) that effectively / increase UKSIP visibility / and support increased / national ambition. (actual)	Brazil	2	Achieved: 3 / Two trainings for Ministry of Transport and Ministry of Ports and Airports. / Presentation of Transport Strategic Plan 2024-2027. / G20 – “Women in the Energy Transition” event.
	Colombia	2	Achieved: 1 / Launch of Technological Ascension Fund.
	Mexico	2	Achieved: 2 / British Embassy/CONAGUA workshop. / Three workshops of the Green Hydrogen Working Group.
	Peru	2	Achieved: 4 / Water public-private-partnership (PPP) event. / Launch of Energy auditors’ programme with MINEM. / Closing of the Energy auditors’ programme with MINEM. / Energy Policy consultation workshop.
[note] Output 1.3 was added to the log frame following the successful completion of the PIP. Given the timings, it was agreed that the milestones for this output would commence from 2023 onwards.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 assesses UKSIP’s ability to improve the enabling environment for private investment by providing technical assistance to address regulatory or policy barriers. UKSIP scored A+ for Output 1 in 2024 as it significantly exceeded expectations for Output 1.2, moderately exceeded expectations for Output 1.3, and met expectations for Output 1.1.

Output Indicator 1.1 measures the number of sustainable low carbon infrastructure, adaptation and resilience and nature-based solutions policies or regulations adopted as a result of UKSIP technical assistance. UKSIP met expectations for Output1.1 in 2024.
[note] Specifically, the indicator measures policies that target macro-level or upstream origination of projects as per the IDB Sustainability Framework.

UKSIP supported the city of Oaxaca in Mexico with the design of the public bike system. This is part of broad support through UKSIP TA to the Mexican transport sector to encourage a sustainable redevelopment. This activity, designed with inclusivity in mind, delivers local sustainable transport solutions in a southern city, places where public transport and active mobility have been challenging historically.

Output Indicator 1.2 measures the number of relevant public sector institutions which adopt methodologies, tools, and approaches to promote sustainable low carbon infrastructure as a result of UKSIP technical assistance. In 2024 UKSIP significantly outperformed expectations - programme support led to 20 individual institutions adopting at least one methodology, tool, or approach that promotes low carbon infrastructure, adaptation and resilience or nature-based solutions, including EcoInvest in Brazil (see case study below).

Technical Assistance case study: EcoInvest Brazil
EcoInvest is a first-of-its-kind instrument that has been developed as a partnership between the Brazilian Finance Ministry and the Interamerican Development Bank. It is designed to mobilise private capital and reduce foreign exchange risks faced by foreign direct investors in Brazil, and therefore increase investment in Brazil’s ecological transition.
FX risk is a major hurdle to mobilising finance to EMDEs. Hard currency investments leave in EMDE borrowers vulnerable to financial instability and debt distress, while also limiting the willingness of financiers to invest in critical longer term development projects. More than 80% of MDB and DFI lending to Low-Income Countries and Lower Middle-Income Countries is in hard currency, primarily USD, with as little as 20% of the dollar amount invested remaining within these economies’ borders over time, indicating that a domestically denominated investments are more conducive to sustainable economic development and growth.
EcoInvest has four credit lines:
- A blended finance auction facility to reduce the cost of capital for Brazilian project developers and facilitate their access to international markets by holding auctions of concessional capital;
- A liquidity facility to cover short-term cash-flow gaps caused by currency volatility
- An FX hedge derivatives products facility to cover local lenders’ counterparty risks with project developers and stimulate the development of a Brazilian derivatives market,
- A project development and preparation facility supports the build-out of a pipeline of investable projects.
Since launch, EcoInvest has held two blended finance auctions. The first covered a range of climate sectors and is on track to mobilise $7.5bn in private investment. The second auction focused on the restoration of degraded lands, with results yet to be announced.
Output Indicator 1.3 measures the number of high-level events (i.e. Ministerial and/or Director or Director General official participation) delivered in collaboration with partner governments and Embassy teams supporting increased buy-in for national ambition. UKSIP supported a total of 10 high-level events.

The successful launch of the Energy Auditors pilot training programme providing direct support to the Ministry of Mines and Energy improving their technical capacity. This supports Peru’s energy transition agenda building capacity in the energy efficiency sector where Peru is behind its regional peers.
[note] According to regulator indicators for sustainable energy RISE 2023 - Peru | RISE

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been minor changes to this indicator reflecting the programme’s extension in time and scope (specifically including adaptation and resilience and nature-based solutions)

In 2024 FCDO and IDB advanced work on tranche three technical assistance projects in the transport sector approving two uplifts (in Mexico and Peru) and one new project in Peru. The two countries were prioritised on the basis of having smaller portfolios of TA projects than Brazil and Colombia. These projects will continue delivery through 2025, although all UKSIP Phase 1 technical assistance should have closed by early 2026.

In February 2024 UKSIP, in partnership with IDBG and the Brazilian Finance Ministry launched EcoInvest. As the RDEL budget was already depleted it was exceptionally agreed with IDB to fund this from investment income accrued over the life of the programme. This project was prioritised due to its innovative design and potential for impact and replication. It has continued to attract significant senior level attention, and in 2025 has been approved for a further uplift (out of scope of this review).
The full UKSIP RDEL budget from the original business case has been committed, all further projects under the expanded scope of Phase 2 are expected to be financed from programme reflows, with approximately just under £1m available per year for public sector and private sector TA (a 2025 BC Addendum will likely mean some extra RDEL is available, outside of scope of this review). As such, future-years targets for Output 1 indicators are lower, reflecting the smaller amounts of funding available for TA through the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In last years’ review, improvements to communications were identified as a priority, specifically focusing on ensuring results land with local government and private sector stakeholders. It was noted that IDB should work with FCDO Posts and the UKSIP programme team to agree objectives, audience/s, and intended impact for each communications activity. This led to the development updated communications strategy and a detailed workplan improving understanding of the roles of IDB, FCDO UK, and embassies in developing comms and ensuring impact through engagement with and developing key comms opportunities.

Recommendation for 2025:

IDB and FCDO should continue to prioritise communications to ensure that UKSIP takes full advantage of the opportunity provided by a Latin American COP and the myriad of build-up international Climate and Development events. In particular it should leverage results of flagship projects such as EcoInvest to provide broader visibility for the programmes other successes. It should also focus on consolidating important lesson learning and dissemination of findings with the majority of long running Phase 1 technical assistance projects ending (for example a consultancy being developed to look across all the Colombia TAs to provide support for Colombia’s latest NDC). This will also enhance programme value for money and sustainability by maximising the impact of existing interventions. IDB and FCDO should use communication opportunities to articulate the narrative impact of UKSIP, encourage replication and consolidate lessons learned for the future.

Output Title	Commercially credible private sector-led low carbon infrastructure, adaptation and resilience and nature investment projects are developed (Private Sector Technical Assistance)
Output number:	2	Output Score:	A
Impact weighting:	25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output 2.1 - Number of pre-investment UKSIP TA interventions that improve the emissions profile, or bankability of low carbon infrastructure, adaptation and resilience, and nature positive investment projects, including an ex-post breakdown of which investments are / 1. Mitigation-focused / 2. A&R-focused / 3. Nature Positive-focused	12(2 in-year)	Achieved: 2 (2 in-year) / RG15048 - Supporting the IDB Energy Division to assess the impacts of vertically integrating activities across the electricity value chain – Peru. / RG15146 - Support to Colombian Renewable Energy Dispatch – Colombia.
Output 2.2 - Number of engagement events with private sector partners and public comms activities (blog posts, publications, reports) that effectively increase UKSIP visibility and/or are intended to support replication of approaches piloted through UKSIP private sector TA.	0 (0 in-year)	Achieved: 1 (1 in-year) / RG4422, Support to IDB Invest Sustainability Week – Regional.
Output 2.3 - Number of investment technical / advisory engagements that improve the / emissions profile, or bankability of low carbon / infrastructure, adaptation and resilience, and / nature positive investment projects	2 (2 in-year)	Achieved 4 (4 in-year) / RG14924 - Calida biogas Project – Peru. / RG14844 - Amazonas Hybrid Microgrids – Peru. / RG15050 - Materani Solar PV Project - Peru / RG15271 - Brusque Mechanise waste recovery – Brazil.

Output 2 assesses UKSIP activities to improve the pipeline of commercial low carbon private sector infrastructure, adaptation and resilience or nature investment projects through its private-sector technical assistance. Delivered by IDB Invest, this focuses on increasing the bankability of specific projects, differing from UKSIP’s upstream public sector technical assistance component.

Output indicator 2.1 measures the number of pre-investment UKSIP TA interventions that improve the emissions profile, or bankability of low carbon infrastructure, adaptation and resilience, and nature positive investment projects. In 2024 UKSIP met its milestone of 2.

Two new private sector TAs launched in 2024 focused on pre-investment projects. They do this through both directly helping specific sustainable projects reach eligibility for private investment and by fostering the adoption of innovative financial, legal and operational structures that can catalyse the development of bankable sustainable investment at the market level unlocking private sector financing. These new TA projects are delivering across the original four UKSIP Phase 1 countries, ongoing work includes:

- Accelerating investment into Colombia’s energy transition by supporting energy market development through recommendations to market stakeholders on the legal framework for the integration of renewable energy into the grid.
- Providing advisory services, including a regulatory proposal, to IDB’s Energy Division - allowing them to assess the impacts of vertical integration activities across the electricity value chain in Peru this can inform the design and delivery of bankable context tailored projects in this sector.

Output indicator 2.2 measures the number of events with private sector partners and public comms activities (blog posts, publications, reports) that effectively increase UKSIP visibility and/or are intended to support replication of approaches piloted through UKSIP private sector TA. In 2024 UKSIP exceeded the milestone of 0 through 1 related event.
2024 is the first year of reporting on Output Indicator 2.2. The indicator was introduced to (a) ensure alignment between reporting on public and private sector TA, and (b) incentivising shared lessons learned and replicable models from private sector TA to enhance the programme’s contribution to market transformation through dissemination and sharing of lessons and findings, as well as encouraging engagement with the sustainability sector. Retrospectively, there are eight engagements that would have met this criterion. This year the project supported IDB Invest’s Sustainability Week, an annual sustainability event in Latin America focused on engagement with the private sector.
Output indicator 2.3 measures the number of investment technical advisory engagements that improve the emissions profile or bankability of low carbon infrastructure, adaptation and resilience and nature investment projects. In 2024 UKSIP met its milestone of 4, an improvement on underperformance against indicator targets in prior years.

This year has included examples of developing innovative legal, financial or operational structures for projects which have transformative potential. Such as in Peru, where many parts of the Norte Chico region lack natural gas coverage for cooking, leaving inhabitants reliant on dirtier and less sustainable cooking fuels. The Calida project addresses this by piloting a biogas project to test the viability of scaling up. Here UKSIP provided technical financial support to improve project bankability. Also in Peru, UKSIP is delivering an adaptation and resilience assessment for the Matarani solar project, an early example of delivery under the programme’s new scope.
In Brazil the Brusque project focussed on designing a mechanised waste recovery facility in Brazil. This has been a flagship project on the incorporation of mitigation considerations within the waste management sector, catalysing similar projects in the country.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

In 2024, a new Output Indicator was added, Output 2.2 which looks at monitoring comms and engagements that lead to longer term impact through the replicability and visibility of UKSIP delivery on the private sector side.
In addition to this Output 1.1 was updated to reflect the programme’s extension in time and scope (specifically including A&R and NbS).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

2023’s annual review made two recommendations relevant to private sector TA. The first was to focus delivery on the new themes and geographies brought into scope in Phase 2 of the programme. As noted elsewhere, UKSIP is still in the early stages of delivery on Phase 2, but there has been clear progress against this recommendation with the launch of two new Caribbean private sector TA projects in 2024 – one focused on A&R, and the other on nature. The second recommendation called for IDBG and FCDO to allocate a share of UKSIP reflows to fund private sector TA in the remaining years of the programme. This has been actioned.

Recommendation for 2025: A theme across UKSIP delivery, but particularly on private sector TA ensuring impact is communicated clearly in the form of “we did X with Y to deliver Z impact.” More broadly it is important to focus on the impact of private sector TA both as compliment to our public sector TA and (most importantly) as enabler of blended finance investments – there should be clear narratives drawn that illustrate this link in an obvious way where the TA has influenced successful blended finance (or where not how we expect it do so in the future). In addition to these points, as per last year, it will be important to continue to focus on delivery in the expanded thematic scope.

Output Title	Blended Finance - Public and private investment mobilised into private sector-led projects in UKSIP target countries, which deliver low-carbon infrastructure, adaptation and resilience, or nature investment.
Output number:		3	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output 3.1 / Number of Blended Finance investments reaching financial close (cumulative)	7	Achieved: 8 (1 in-year) / BR-G1014 - Mendubim Solar PV Power Project – Brazil. / CO-L1279 - Guagua Fontibon Electric Bus Project – Colombia. / CO-L1280 - La Union, Solar Power. - Colombia. / CO-L1281 – La Mata, Solar Power.- Colombia. / CO-L1284 - Guagua Usme Electric Bus Project – Colombia. / BR-G1019 - Aguas do Rio – Bloco 1, Water & Sanitation – Brazil. / BR-G1020 - Aguas do Rio – Bloco 4, Water & Sanitation – Brazil. / (2024) BR-L1646 - BRK Ambiental (Senior Loan) & BR- G1025 – BRK Ambiental (Grant) - Brazil.
Output 3.2 / Volume of private finance leveraged through UKSIP Blended Finance investments (cumulative)	£174.84m	Achieved: £164.87m (£3.98m in 2024) / BR-G1014 - Mendubim Solar PV Power Project: GBP 20.05 million – Brazil. / CO-L1279 - Guagua Fontibon Electric Bus Project: GBP 15.92 million – Colombia. / CO-L1280 - La Union: GBP 17.7 million – Colombia. / CO-L1281 - La Mata: GBP 13.04 million.- C Colomba. / CO-L1284 - Guagua Usme Electric Bus Project: GBP 20.45 million – Colombia. / BR-G1019 - Aguas do Rio – Bloco 1: GBP 41.83 million – Brazil. / BR-G1020 - Aguas do Rio – Bloco 4: GBP 31.90 million – Brazil. / BR-L1646 - BRK Ambiental Maranhão (Senior Loan): £ 2.21 million – Brazil. / BR-G1025 - BRK Ambiental Maranhão (Grant): £ 1.77 million – Brazil.
Output 3.3 / Level of installed capacity of clean energy (MW) in UKSIP target countries generated as result of UKSIP supported interventions (cumulative)	299 MW	Achieved: 316 MW / BR-G1014 - Mendubim Solar PV Power Project: 226 MW – Brazil. / CO-L1280 - La Union: 50 MW – Colombia. / CO-L1281 - La Mata: 40 MW – Colombia.
Output 3.4 / Number of public knowledge products issued by IDB Invest covering lessons learned from UKSIP blended finance investments	N/A	N/A
Output 3.5 / Percentage of SIP blended finance investment in blended finance operations which support adaptation and resilience focused activities and nature positive activities	0	0
[note] Figures reflect the GBP/USD exchange rate at the closure date of each project. These are now reflective of the OECD methodology for measuring mobilisation

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 assesses mobilisation of private capital into low-carbon infrastructure, adaptation and resilience, or nature-positive projects. Overall, UKSIP met its milestone expectations for Output 3 in 2024 - exceeding on Output 3.3 with 316 MW of installed clean energy achieved and slightly underperforming Output Indicator 3.2 with £164.87m of private finance mobilised cumulatively on blended finance investments, with a single investment made in 2024 (using two different instruments – senior debt, and a performance-based incentive grant).

The milestones are set by IDB invest using their own methodology which relies on data from recently closed projects as well as their current pipeline of future investments. With Output 3.2 and 3.3 designed to align with the HMG ICF key performance indicators.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As was recommended in 2023’s Annual Review, UKSIP has shifted to using the OECD’s private capital mobilisation methodology for Output 3.2. In practice, this has and will reduce the headline figures for private finance mobilised through programme interventions. Modelling for Output 3.2 has now been updated with the OECD methodology now the basis of each in-year LogFrame milestone for Output 3.2 until the programme close in 2029.

The new Output 3.4 is designed to incentivise and track replication through knowledge sharing, in this case by measuring the publication of lessons learned reviews for each new UKSIP blended finance investment. This implements a recommendation from the 2022 Annual Review. In line with the updated Management Arrangement, these are set to be published two years after financial close and the first is therefore expected in 2026. The new Output 3.5 measures the share of blended finance spend targeted toward the new themes brought into scope of the programme in Phase 2 – nature, and A&R.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Implementation of 2024’s main blended finance recommendation – to increase the share of the programme’s blended finance spend outside Colombia and Brazil (with a focus on the programme’s ‘new’ themes and geographies) is ongoing. Through the Management Arrangement IDB and FCDO agreed to new minimums on the share of blended finance spend on A&R and nature, and in Central America and the Caribbean. Through the update of the LogFrame IDB and FCDO set new targets for spend in these areas. The practical impact of this will take time to work its way through into blended finance transactions, which can take years from origination to final close.

Recommendations for 2025: IDB and FCDO should continue to prioritise blended finance investments which focus on the programme’s ‘new’ themes and geographies – A&R and nature, Central America and the Caribbean.

## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

Economy - Are we or our partners buying inputs of the appropriate quality at the right price?
To administer the programme IDB charge fees of 5% for technical assistance and 2.5% for blended finance activities. These relate to the amounts allocated to the TA and blended finance budgets from each FCDO contribution to UKSIP. TA fees include costs of operation, origination, design, due diligence, and administration. Blended finance fees cover the costs of project origination, portfolio management, due diligence, risk, and commercial appraisal.
Fees for UKSIP administration are comparable to those charged in other similar MDB trust funds – fees from programmes delivered with World Bank entities have charged administrative fees in the range of 3-5% - and remain the same as agreed under the original business case.

Efficiency - How well are we or our partner converting inputs into outputs?
The business case outlines efficiency objectives as (1) addressing barriers and market failures to promote investment in sustainable, adaptation and resilience and nature related infrastructure, (2) efficiency in delivering outputs, and (3) minimising market distortion and ensuring additionality.

Addressing the barriers and market failures
As outlined in the KPIs, UKSIP has continued strong delivery in 2024 aimed at addressing market failures. Among others, UKSIP has (1) provided concessional financing to support 1 low-carbon asset to reach financial close, which may not have happened without UKSIP investment, (2) improved the bankability of four low-carbon sustainable infrastructure projects, and as well as supporting two market-wide sustainability innovations that could enable sustainable projects through private sector technical assistance, and (3) supported 20 public sector institutions to adopt methodologies, tools, and approaches to promote sustainable low carbon infrastructure, adaptation and resilience or Nature Based solutions.

Efficiency in delivering outputs
As of year-end 2024, 43% ($57,584,893) of all UKSIP approved funds (blended finance and technical assistance) had been disbursed for project outputs. In comparison, total administrative expenses for the programme totalled $5,884,897. As such, the ratio of administrative expenses to disbursements made is 0.1:1, in line with prior years.

To deliver blended finance, IDB Invest (IDB Invest) deploy UKSIP funds alongside IDB Invest monies into larger deals. This incentivises IDB Invest to strike a balance between using concessional funds to leverage private sector investment into deals which would not happen otherwise, and capital preservation, as it ensures that IDB has the same motivation to preserve UKSIP funds as its own. As the deals IDB Invest is using UKSIP funds to invest in are often novel – deploying technologies in new geographies or at greater scale than has been done previously – there are limited examples of comparable deals against which to compare the value for money of UKSIP investments.

UKSIP benefits from economies of scale through IDB’s existing structures, systems, and in-country presence. UKSIP’s IDB technical advisers draw on specialist resources from across the organisation according to need. A core feature of the programme is the delivery partnership between the public sector and private investment arms of IDB, that are increasingly working in a more coherent and integrated manner.

On average, UKSIP TA projects are approved within approximately half the time provided to project teams for all IDB technical assistance projects. The average time in months for approval of UKSIP technical assistance projects is 2.8, while the IDB Group average is 4.06.

Minimising market distortion and ensuring additionality
IDB follows MDB guidelines for the use of concessional financing, to ensure that this is only deployed when required and in line with expected criteria. Key considerations in the approval of projects through UKSIP is that projects (a) catalyse private investment and lead to additional climate and development investment, and (b) that the project could not proceed without IDB involvement. These conditions are scrutinised as part of IDB Invest’s investment committee review process.

To maximise additionality, UKSIP combines TA with investment to address market barriers in ways the private sector is unable to engage – through regulatory reform or direct assistance to financial institutions. In 2024, the combination of TA and blended finance was applied to the BRK Ambiental Maranhão project. Over the course of the programme, all eight blended finance transactions have benefited - either directly or indirectly - from UKSIP technical assistance, demonstrating the effectiveness and impact of the TA–blended finance model.

To achieve transformational change in target sectors, IDB uses innovative policy, market and financial instruments to demonstrate new policies, tools or investment models, which may not have been trialed at scale before in certain geographies. This increases the value for money and additionality of using ICF to demonstrate replicable policies and business models. This encourages future replication of such deals by countries for policies, and the private sector for financing models.

As examples, in 2023 UKSIP supported two Blended Finance transactions to reach financial close part of the same overall project – Aguas do Rio - with the aim of (a) supporting the universalisation of basic sanitation services in Brazil, and (b) demonstrating and enhancing the mitigation of the environmental impact of the water sector in Brazil by incentivising best-practice. Both investments were made as performance-based incentives (PBIs). In 2024, UKSIP supported a further Blended finance transaction in the Brazilian water PPP pipeline (Public Private Partnership) again supporting the universalization of basic sanitation and in particular showcasing the financing of low environmental impact water and sanitation infrastructure in small urban areas in Brazil. This transaction again employed PBIs.
These transactions are helping to demonstrate the viability of PBIs to support mitigation activities in large infrastructure projects at scale, with the potential for replication in other geographies and sectors with significant abatement needs.

As PBIs are grants, they are unlikely to displace private investment, which would be a risk if capital used for the PBI was used as part of a loan, which a private lender could provide. The PBI instead, as a limited amount of capital, influences the sponsor to achieve certain performance (in this case environmental, and gender inclusion) targets, and therefore influences how the sponsor uses a larger pool of capital from investors in the project.

Effectiveness - Are outputs achieving outcomes?
Technical assistance can trigger transformational change that leads to strengthened enabling environments, increased availability of bankable low carbon, adaptation and resilience or nature investment projects. Blended finance can take advantage of this environment, while itself improving commercial sustainability of projects and delivering broader development outcomes.

In 2024 UKSIP’s technical assistance has helped enable market conditions, regulatory frameworks, and policies of not only UKSIP partner countries but into the whole LAC region to develop in line with low-carbon futures. For example support to the Ministry of Mines and Energy in Peru to develop a transition agenda has supported development of a pilot introducing induction stoves in the City of Cuzco. Lessons learned from this are now feeding development of a similar project in Mexico.

UKSIP continues to be the only major UK bilateral climate mitigation investment programme in the region, and feedback from embassies suggests that the programme has significantly supported the UK’s international climate and diplomacy efforts. UKSIP supports the UK’s shareholding in IDB, aiding the UK’s ambition for organisational and broader MDB reform to optimise climate finance/private capital mobilisation.

The extent to which the outcomes, as per the Theory of Change, are being achieved has been analysed as follows:

Outcome	Progress	RAG Rating
Institutions and frameworks strengthened: Improved enabling institutional / policy / regulatory environment for sustainable infrastructure across the widest range of UKSIP target geographies	The technical assistance projects have developed recommendations and improvements to institutions and frameworks. Outcome 1 of the LogFrame to date the programme has enabled adoption of 19 low carbon, adaptation, resilience or nature-related policies reflected in planning and procurement process and/or infrastructure investments. The extent to which these are leading to environmental impact will be seen in the medium to long term. Furthermore, whilst our projects produce recommendations and support organisations to implement, the extent to which these are followed through and adopted in the longer term remains to be seen.
Increased availability of bankable projects: Improved capacity of project developers, across the widest possible range of UKSIP target geographies.	Closing blended finance deals through UKSIP shows the availability of bankable projects which have been developed through IDB support. Delivery of private sector TA also aims to improve the availability of bankable projects for example in development of projects under the Public Private Partnership scheme. The extent to which public sector upstream TA has led to bankable projects though is less clear, however, UKSIP has demonstrated positive examples. In Colombia, this year UKSIP has provided broad structuring support as part of a tender under consultation for the purchase of over 296 electric buses and an estimated investment of USD244 million.
Development outcomes: Infrastructure unlocks local growth or development.	There are strong development outcomes expected through the blended finance projects as the projects become operational. To strengthen our monitoring of this, In Phase 2 (2024 onwards), IDB have agreed to provide reporting against a series of social development indicators, including # of projects with a poor and vulnerable communities’ component (# projects); number of full-time (equivalent) jobs created or supported, disaggregated by gender; number of Micro, Small & Medium Enterprises (MSMEs) supported; and e. communities/ hectares/other relevant unit with improved resilience or adaptation component.
Commercial sustainability of low carbon markets improves: Local financial institutions increase lending and investment.	UKSIP has demonstrated clear evidence of developing the commercial sustainability of low carbon markets, In Colombia, UKSIP TA supported the fourth green bond auction in the local market. In Brazil, UKSIP worked with Maua, a local fund manager, to incorporate mitigation and adaptation as part of its overall business model to support the development of portfolios focused on sustainability. This work was also shared through Maua’s value chain to encourage replication. Also, in Brazil UKSIP has supported the development of EcoInvest, a foreign exchange hedging and blended finance platform that is designed to stimulate the development of the domestic FX hedge and FX derivatives market in Brazil by demonstrating the commercial viability of longer tenors and innovative products (e.g. stop-gap liquidity solutions) to local financial institutions. The first blended finance auction of which is on track to mobilise $7.5bn private investment from a mix of domestic and international sources.
[note] The Red Amber Green (RAG) rating refers to the extent to which the outcome is currently being achieved. Red = outcome not being achieved and not progressing. Amber = outcome partially achieved or progress is being made to achieve outcome. Green = outcome being achieved.
[note] IDB(G) supports PPPs across Latin America and Caribbean region. These partnerships unlock funding from the private sector through providing income, while sharing risks across aspects of an investment and are a tool in helping close the gap between publicly available finance and the investment need for infrastructure. IDB(G) works to develop legal and regulatory frameworks for PPPs as well as well as on building lists of projects that can be financed through PPPs – IDB is responsible for supporting project bankability.

Equity - (including gender equality and, disability, and overall cost-effectiveness.)
All UKSIP TA projects follow IDB’s Environmental and Social Safeguards Policies - standard 9, gender-related policies, and procedures, and all IDB Invest technical assistance projects and blended finance operations follow IDB Invest’s Sustainability Policy.

Gender equality contributes to poverty reduction, results in higher levels of human capital for future generations and improves the development effectiveness of public investments. Promoting gender equality is pivotal to accelerating economic and social development in Latin America and the Caribbean.

IDB’s Operational Policy on Gender Equality in Development commits the Bank to improve its capacity to apply a gender perspective systematically across operations and analytical work, as well as to direct investment in promoting gender equality and women’s empowerment. In addition to which IDBs Gender and Diversity Action plan for 2022-25 sets specific targets for IDBG to monitor their delivery deliver on the policy basis.
In 2024 the programme introduced several actions to improve reporting and delivery of GESI co-benefits. This is part of FCDO and IDB’s push to more closely integrate GEDSI into UKSIP programming in acknowledgement of the intersections and dependencies between achieving development, GEDSl, and climate outcomes. FCDO and IDB remain committed to this approach through UKSIP and will continue to explore options to enhance UKSIP’s impact on GEDSI over the remainder of its lifetime.
Programming requirements: FCDO agreed with the IDBG that all new technical assistance (~15% of UKSIPs spend) programming would include a GESI component, and all new blended finance programming (~85% of UKSIPs spend) is required at minimum assess opportunities for promotion of positive GESI outcomes.

Reporting requirements:
- FCDO set a new minimum reporting standard for IDB – that “in its Annual Report the IDB will explain how programming is aligned with IDB GESI policies and will explain how GESI co-benefits are being assessed and reported.”
- FCDO has introduced a GESI indicator to the programme LogFrame to facilitate better tracking of UKSIP’s GESI related activities. It has also agreed a set of non-LogFrame development indicators with IDB to track GESI related data across the programme (see Management Arrangement)
  [note] Number of investments and TC activities which contribute to GESI outcomes
- For standard AR reporting, the UKSIP programme team covers gender (and wider GESI issues) in the Equity sub-section of the VFM chapter. The team also highlights specific projects with explicit gender co-benefits.

Some of UKSIP’s impacts on gender and vulnerable communities are:
- Understanding women’s safety perception in Mexico City’s Public Transport (Mexico). To help women and girls feel safer when using public transport in Mexico City, the city’s Ministry of Mobility and Women’s Secretariat used UKSIP support to partner with experts and a consultancy firm to create a baseline study on how gender affects mobility in the city’s transport system. They also ran workshops to raise awareness about sexual violence and trained staff on how to respond to incidents. Using these insights, the team developed practical recommendations tailored to each type of transport (e.g. buses, metro lines). These efforts are now shaping public policies that aim to make travel safer, more comfortable, and more accessible for women and girls across the city
- Promoting gender, diversity and inclusion in the supply chain of water and sanitation projects (Brazil). UKSIP provided a Performance-Based Incentive grant for the BRK Ambiental (BR- G1025) project, for which one component of the PBI is aimed at increasing the participation and procurement volume of women and Black-led SMEs in the water and sanitation supply chains in Maranhão and Tocantins. The project supports the universalisation of basic sanitation services in Brazil and is expected to demonstrate the financing of systemic climate mitigation opportunities through the expansion of sewage services in small urban areas.

Overall cost effectiveness
Taken together, UKSIP’s performance against the VFM metrics of economy, efficiency, effectiveness, and equity demonstrate its cost effectiveness (e.g. UKSIP’s ultimate impact on its stated objectives relative to inputs). Since the conclusion of the Performance Improvement Plan, UKSIP’s delivery has substantively improved, with an increase in both the speed and scale of programming to achieve intended objectives. The programme has also increased its cost-effectiveness and value for non-climate developmental outcomes over time, particularly with regards to gender equality and social inclusion.

As a programme designed to create transformational change, where benefits are expected to be accrued following programme closure and full impacts unlikely to be realised for years after that, it is not possible to put a pound-for-benefit rating on UKSIP interventions at this stage. However, even with that proviso, on the basis of ongoing delivery UKSIP has demonstrated its cost effectiveness as a vehicle to achieve the UK’s climate objectives in its target countries.

Assessment of whether the programme continues to represent value for money
UKSIP performs well against the full set of value-for-money assessment criteria, and early closure of the programme could affect (a) the delivery of an extensive technical assistance portfolio, (b) recognition of the UK as a donor behind those projects (c) the UK retaining a strategic position to work with IDB on the deployment of programme reflows and new ODA into climate vulnerable countries.

E: RISK

Overview of risk management

In line with FCDO’s risk appetite, UKSIP’s strategy, context, and delivery risk appetite is receptive, and its financial and fiduciary risk appetite is cautious. Currently all programme risks fall within PSCMD’s risk appetite. In 2024 UKSIP delivered within its risk appetite.

UKSIP’s risk profile remains moderate. In 2024 and beyond the main risks are associated with adapting delivery to its new scope and ensuring timely development of impactful projects in new countries and themes. Noted in the programme risk register that fewer and smaller opportunities for blended finance in the expanded themes or due to beneficiary capacity could be disincentives to engaging in the expanded scope. These have been addressed in the Phase 2 redesign through setting targets in the Logframe and engagement with relevant expert advisors and this risk has reduced as UKSIP entered 2025 with launch of multiple projects in the expanded scope.
A specific risk on ensuring sufficient safeguards are in place for social (including SEAH – Sexual Exploitation, Abuse and Harassment) and environmental risks and including mitigations to introduce regular monitoring of this in formal programme update meetings. Worth noting that this was added not in response to specific programme risk, but rather the seriousness with which FCDO takes in ensuring secure safeguarding control is implemented within its programme portfolio.
The risk register has been updated to reflect these. Initial mitigations to these have been designed into the programme’s governance, via the Management Arrangement update in Spring 2024, and via new agreed ways of working between IDB and FCDO.
Going forward into 2025 and beyond, the changing development context does mean longer term budgetary uncertainty, however the current financial position of the programme is satisfactory to continue delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

IDB reported UKSIP financial information to FCDO for 2024 in line with expectations and ICF portfolio requirements. IDB administers and accounts for the programme resources in accordance with its financial regulations and provides unaudited financial statements of programme activity to FCDO.

IDB have fulfilled their duties and delivered against the terms and conditions outlined in the restated management arrangement signed in May 2024. IDB have reported to FCDO in line with the agreed timelines, for both project approval processes and broader reporting requirements, as well as information requests including to support exercises to manage technical assistance budget uncertainty.

IDB reports Value for Money indicators in the year-end Annual Report, which provides additional reported metrics and financial information relating to the UKSIP portfolio. This reporting has aided FCDO financial management of the programme in 2024.

UKSIP Encashment History
FCDO uses Promissory Notes (PNs) to fund UKSIP. Since programme launch in 2017, three PNs have been laid - £52m in 2017, £59.5m in 2022 and £17m in 2024. The first two promissory notes have been fully encashed, and as of 31 December 2024 a further £3,919,318 of the third PN had also been encashed (November 2024), with a remaining balance of £13,080,782

The fiscal envelope set by the business case allows for up to an additional £49m of ODA to be committed to the programme by 2029. This has been forecasted by the UKSIP team, with actual commitments subject to change depending on HMG-, FCDO- and departmental-level budget processes, including Spending Reviews. The programme team will continue to monitor the programme’s value for money and progress against its objectives to assess the overall value of allocating further ODA to UKSIP (outside scope, a further £9m PN has now been laid in 2025).

UKSIP Financial Management
The transition from BEIS to FCDO, and the implementation of the Performance Improvement Plan, have improved the overall financial management of the programme and brought it more closely in line with best practice. Most importantly, FCDO encashes funds at the point of need (e.g. ahead of the board approval date for a blended finance transaction, or at the point of implementation for a technical assistance project) rather than in large blocks well-ahead of a transaction or technical assistance intervention.

The transition to Phase 2 required an update to UKSIP’s financial management, principally to manage the implications of an increased reliance on financial reflows (generated by returns on UKSIP investments). Starting in 2023, and concluding in early 2024, FCDO and IDB worked closely to develop a new Management Arrangement and plans for use of reflows plus any further contributions from FCDO. This negotiation included a re-confirmation of programmatic fees, agreement on rules to govern the use of ODA and non-ODA moneys within UKSIP, a re-confirmation of the process for the commitment and encashment of PNs, and agreement of a strategy to diversify programme spend across its different climate finance themes and wider set of geographies.

Roughly £4.8m of reflows are expected to be generated per year between 2024 and 2029, although this could vary depending on the performance of UKSIP investments. These are expected to be spent according to an 80-10-10 ratio, split between blended finance investments (80%), private sector technical assistance (10%), and public sector technical assistance (10%).

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

In October 2022 FCDO and IDB agreed a revised Evaluation Plan. The plan set out that UKSIP should be evaluated by an external reviewer, contracted by IDB, along 5 dimensions: opportunity for transformational change, national planning, private finance mobilization, bankable projects, and UK visibility & country partnerships.

In line with the evaluation plan, a mid-term evaluation (MTE) was carried out in 2023, concluding in February 2024. The MTE was tasked with reviewing programme delivery and analysing market conditions for sustainable and climate resilient infrastructure – and has helped inform use of investment reflows for UKSIP’s Phase 2.

Following this the ToC and Logframe were redesigned in 2024 to (a) to appropriately capture and incentivise action under UKSIP’s expanded geographic scope; (b) to establish targets that are sufficiently stretching and achievable through the resources available in Phase 2. Key changes include:
- Adding references to the broadened scope on adaptation and resilience and nature positive activities where appropriate
- Adding an indicator that measures engagement and comms through private sector TA to monitor opportunities for replication, and increased visibility of UKSIP work
- Adding two indicators on blended finance that track knowledge products produced – increasing the learning value of UKSIP (in line with updated management arrangement for future BF investments) and look at percentage of investments which support adaptation and resilience and nature based solutions targeting 39% over the lifetime of the programme.
- Indicator measuring mobilised private capital has been updated to follow OCED methodology in line with the UK ICF reporting (implemented)
- Three new outcome indicators covering GESI outcomes, a new indicator on IDB invest financial mandates to measure the wider influence of UKSIP TA on the IDB pipeline of investments and finally a new indicator to measure the ambition for growing geographic diversification under the new scope.
- All indicators have had agreed new target milestones up to the programme’s extended end date of December 2029.

These changes reflect the findings of the MTE, and the changed objectives and scope of the programme within the business case addendum and restated management arrangement.

Evidence
This AR has been conducted based on the Annual Report produced by IDB, it has also drawn upon broader evidence including ongoing discussions between IDB and FCDO, Annual Meeting (September 2024), work with and feedback from UK embassies over the last year, and finally interviews with stakeholders conducted during the drafting of this review. The AR is also informed by FCDO’s field visit in September 2024 to Peru, where the programme team and embassy saw UKSIP projects and met UKSIP beneficiaries.

Learning
This year, with the transition to Phase 2, has seen the programme begin to put into practice the learnings from the Mid-Term Evaluation, finalised in February 2024, the findings of which were a significant factor in development of the business case addendum, refreshed Logframe and ToC, and the restated management arrangement.

The MTE was carried out by an external reviewer tasked with assessing UKSIP against five dimensions: opportunity for transformational change, national planning, private finance mobilisation, bankable projects, and UK visibility & country partnerships. The MTE also contained a forward-looking assessment of UKSIP’s potential implementation in broader geographical and/or sectoral contexts – this last section has been key in the development of the broader geographic scope (to Central America and the Caribbean) and the broader thematic scope (adaptation and resilience and nature based solutions).

All of the MTEs Recommendations have now been implemented within the programme and formalised in the updated management arrangement; summarised below

MTE Recommendation	Response
Introduce a common set of guidelines to govern engagement and programme interactions between the central programme team, Posts, and IDB.	Included in the updated UKSIP Management Arrangement for Phase 2 of the programme.
IDB to involve GESI staff in the design of technical assistance projects.	From May 2024, all new technical assistance projects in UKSIP will be required to have a GESI component.
UK embassies should be more fully integrated into the monitoring, evaluation, and learning process.	FCDO will explore options for greater embassy involvement in MEL and include this in updated guidelines for embassy involvement in the programme, which will be developed in 2024.
IDB should keep real-time records of changes to technical assistance projects, and share these with embassies for approval.	Implemented, requests are shared with reasonable turn around to allow comment from FCDO teams.
Include a new GESI-focused indicator in UKSIP’s LogFrame.	Implemented
Prioritise programming in the Caribbean under the new scope of UKSIP as set out in the Business Case Addendum.	First Caribbean TA projects on both public and private side have now launched. Outside the scope of this review we have also seen the closure of blended finance covering the Caribbean.

As discussed elsewhere in this review, the Management Arrangement now reflects the broadened geographic and thematic scope of the UKSIP programme, designed to deliver the ambition of the business case addendum drawing from the findings of the MTE.

The key changes this has included are:
- Specific minimum targets on implementation of adaptation and resilience and nature based solutions in Phase 2, as well as to prevent overweighting in any one geography to encourage geographic diversification.
- Increasing focus on GESI through requirement that all technical assistance programming should have a GESI component, and that all blended finance programming should seek to include GESI components where possible. As well as including a GESI outcome Logframe indicator to systematically record the impacts
- Adding non-logframe indicators that better measure broader poverty, vulnerability and GESI co-benefits, more systematically collecting the broader developmental co-benefits of the programme.
- IDB and FCDO also agreed to draft a new set of embassy engagement guidelines as part of the management arrangement to ensure maximally effective interactions between embassies, the UKSIP programme team, and IDB.

As this review is being written the programme is still in the midst of transitioning to Phase 2. This will continue as we monitor mature Phase 1 TA projects to a close toward the end of 2025 and into early 2026.
Slightly beyond the scope of this review, but useful for context, we have now seen the first allocations of UKSIP funding into the expanded scope, utilising reflows from programme with investments in line with the methodology set out in the business case addendum and management arrangement. This has seen a split roughly similar to that of the original UKSIP programme budget (80:20 – TA to Blended Finance).
From this initial reflows allocation we have funded two new TA projects split equally between private and public. Both TA projects are focused in the Caribbean with the public sector work seeking to build resilience in power infrastructure, while on the private side the project is focused on developing the enabling environment for investment in nature-based solutions and resilient infrastructure, both sitting firmly within the expanded scope of Phase 2.

On the blended finance side as well we have recently seen two investments reach financial close, one using the capital portion reflows received from the programme. These have both been Caribbean regionally focused investments in sustainable infrastructure, with one of the funds also having a resilience component.

This shows the programme is putting into practice the learning and recommendations drawn from MTE and previous Annual Reviews to implement its broadened scope through investments in new markets and new sectors.
Even with this progress however, we are still in the early stages of Phase 2 and the recommendations from the previous review remain relevant now, we should continue working on:
- Developing and sharing expertise in the themes and countries being brought into scope under Phase 2. This extends beyond the programme – a core ambition for Phase 2 is that UKSIP contributes to IDB’s wider development of expertise in these areas.
- Assessing the extent to which new markets and themes require a different mix of public-sector technical assistance, private-sector technical assistance, and blended finance to facilitate demonstration, market development and replication;
- Continuing to build the evidence base for UKSIP’s contribution to transformational change through demonstration, replication, and scale.

Development impact
MEL conducted so far shows that UKSIP contributes to a range of Sustainable Development Goals (SDGs), examples below.

13: Climate Action: through all projects by reducing emissions pathways.
7: Affordable and Clean Energy. Increasing use of clean energy is designed into all projects. This has broader development benefits beyond climate, by reducing price volatility shocks experienced through fossil fuel reliance and extending energy access. Examples of activities include: trialling solar power for public buildings including primary schools across Mexico, reducing operating costs and emissions; and supporting inclusion of non-conventional renewables at scale in Colombia’s energy grid, and part-financing alongside local currency private financing the largest solar developments to date in the country.
9: Industry, Innovation, and Infrastructure: an impact area designed into all projects with multiple examples, including: the use of performance-based incentives (PBIs) to reward greenhouse gas emissions abatement efforts in the water sector in Brazil. This is demonstrating at scale that PBIs are a viable, replicable model for incentivisation of emissions reductions in hard-to-abate sectors. This investment is one of first and largest public-private partnerships under Brazil’s new sanitation framework, so acts as a demonstrator for the contracting and project approach for the sector.
11: Sustainable Cities and Communities: through developing business cases for electrifying mass transport in major cities with high traffic volumes and poor air quality; electrify diesel ferries used to access islands off Brazil. UKSIP’s innovative loan to finance electrification of Bogota’s bus fleet was particularly transformative, a deal structure which cities in the region and beyond are seeking to replicate.
6: Clean Water and Sanitation. Partner countries are in places water stressed with large populations lacking access to clean water. UKSIP has supported a range of projects to finance and improve the energy efficiency of water and sanitation infrastructure across all 4 countries. In Brazil, UKSIP investment into the Aguas Do Rio projects is supporting the provision of sanitation services to 10 million people, including vulnerable communities, and again in 2024 with the financial close of the BRK Ambiental Maranhão investment in another underserved area of Brazil. In Mexico, where water scarcity has become more pressing in the past year, UKSIP technical assistance funding is supporting water operators to become more energy efficient.
5: Gender Equality. See section above.
8: Decent Work and Economic Growth. Development of infrastructure provides local economic benefits through employment during construction and operation. Reduced emissions from sustainable infrastructure reduces health impacts on workers and populations from fossil fuel generation.
10: Reduced Inequalities: by including contract requirements in some UKSIP investments in to increase employment and training opportunities communities for women and communities of African descent where they have historically been disadvantaged.

Date of last narrative financial report	June 2025	Date of last audited annual statement	31 December 2024