## Annual Review

Title: JUST ENERGY TRANSITION PARTNERSHIP SUPPORT, SOUTH AFRICA
Programme Value £ (full life): £19.98m (of which, up to £9m CDEL)		Review date: 15 March 2026
Programme Code: 301523	AMP start date: 15 March 2023	AMP end date: 15 March 2029

Summary of Programme Performance
Year	2023/24	2024/25	2025/26	2026/27	2027/28	2028/29	2028/29
Overall Output Score	N/A	B	A
Overall programme risk rating	N/A	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006341.odt (Main business case and $1bn guarantee business case) / and / DevTracker Programme GB-GOV-1-400013 Documents (fcdo.gov.uk) / ($300m Room to Run guarantee)
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

This review covers the UK contributions to South Africa’s JETP, including the bilateral grant programme and other technical assistance contributions; the mobilisation of the AfDB guarantee; Development Finance Institution spend; engagement with and leadership of the International Partners Group; and diplomacy and influencing. The review period is from 16 March 2025 to 15 March 2026 and includes an update and emerging results from spending in the years 2023-2026.

Description of programme

The South Africa JETP was announced at COP26 in November 2021. The Partnership is between SA and the International Partners Group (IPG), now comprising of the UK, Germany, France, the EU, Denmark and the Netherlands. It aims to support SA to deliver its Just Energy Transition as set out in the South Africa JET Investment Plan 2023-27.

Last year’s Annual Review (2024-2025) provides further detail on the background of the JETPs and the UK’s contribution which consists of: $1.3bn in guarantees via two facilities with the African Development Bank to increase its sovereign lending for JET aligned infrastructure projects; $500m in BII and PIDG investments, and; over $34m of grant comprising a range of projects delivered by FCDO and DESNZ.

The UK’s JETP support programme is a bilateral grant programme managed by BHC Pretoria. It forms part of the wider UK government package of support to South Africa’s Just Energy Transition. The UK theory of change and logframe, is intended to measure the combined impact of UK support to South Africa’s JETP, not just the bilateral grant provided through the UK’s JETP business case/business case addendum. This includes all aspects of the UK pledge, not least the UK’s diplomatic engagement and influence. However, as the bilateral programme progresses to implementation the team’s focus on bilateral programme spend and JETP guarantee deployment has necessarily increased. The logframe weightings have been amended accordingly.
Table summarising JETP support programme spend
Area ​	Implementer ​	23-24 ​	24-25 ​	25-26 ​	Total spend by end March 2026	Key results ​
Influencing ​					​	​
Energy Modelling ​	Loughborough Uni, Uni of Cape Town ​	£230,023 ​	£338,789.07 ​	-​	£568,812.07	Improved SA modelling capacity, coordination and data transparency ​
Energy road map and reform of energy markets ​	Energy Council ​	£288,285 ​	£350,000 ​	[Supported by UKPACT - £499,980] ​	£638,285​	Transformational change through policy change. Energy policy roadmaps for SA Gov. ​
Health research ​	SA Medical Research Council ​	£4,821 ​	£27,250 ​	-​	£32,071​	Peer reviewed articles with new data – influencing decisions in SA on coal plant extensions and emissions. ​
Project Preparation ​					​	​
General scoping for projects across Mpumalanga ​	PWC ​	£97,566 ​	£1,230 ​	- ​	£98,796​	130+ projects scoped and connections made e.g. with GIZ, BII, PIDG ​
Range of projects ​ / (first is energy distribution and water) ​	ASI consortium ​	-​	£791,701.78	£1,633,275​	£2, 424,977.78	Jobs, GHG, people with improved services. Improved revenue for SA budget ​
Blended Finance CDEL ​					​	​
Agribusiness in Mpumalanga ​	Technoserve ​	-​	£500,000 ​	£2,040,000​	£2,540,000​	Jobs in Mpumalanga ​ / Private finance mobilised ​
Non agribusiness investment ​	TBD: CFP out ​	-​	-​	-​	​	Jobs in JET areas including Mpumalanga ​
Other programme
Legal advice for AfDB guarantee negotiations	Hogan Lovells ​	£9,840​	£9,000 ​	£5,000 ​	£23,840​	​Legal advice to finalise the guarantee
Programme funded Energy Adviser ​	Local FCDO staff member ​	-​	-​	£33,600​	£33,600​	Keep abreast of energy developments, produce capitals update and liaise with key SA institutions, Energy Council etc ​ / Develop policy issues ​
Totals​	​	£630535​	£2,017,970.85	£3,711,879​	£6,360,384.85	​

Summary supporting narrative for the overall score in this review

The programme overall scored an A, with one output substantially exceeding expectation, one moderately exceeding expectation and one meeting expectation. The weighting of output 1 has increased to 70% reflecting the programme team’s increased focus on programme implementation.

The bilateral programme in isolation is not sufficient to deliver the NDC goal of the partnership, and the objective of the programme remains to maximise ambition and implementation to narrow the gap. While SA is not on track to meet the high ambition 2030 NDC target envisioned in the partnership, there have been notable successes throughout the year in moving potentially transformative projects forward in complex areas through the bilateral programme, while maintaining successful leadership of the IPG.

Major lessons and recommendations for the year ahead

Recommendation	Who and when?
Develop a (sub-)theory of change on ‘Just’ job creation in South Africa, ideally with collaboration/input from others working in similar areas.	PRO – target September 2026.
Engagement with South African Government stakeholders needs to be thorough and their buy-in and ownership clearly secured at key milestones (ideally early ones) for the project prep work for AfDB lending. Continue to focus on developing and strengthening relationships with the relevant line Ministries responsible for delivery of relevant JET policies and reform; in particular DEE, National Treasury and COGTA. These will advance UK and joint IPG priorities.	JETP Team, ASI, over course of 2026.
Now that projects are moving to implementation, develop a clear communications plan which delivers positive messages to a range of local audiences and highlights the tangible outputs being delivered through the programme.	JETP Team and Comms rep – target end of May for refined comms plan agreed by JETP Huddle.
Review of the identified indicators and consider where it may be possible to better capture the potentially transformative impact on social and economic justice of the projects which would capture impact beyond the proposed hard metrics identified.	SRO/PRO and VFM expert – target end of April 2026
Continue streamlining IPG co-ordination. This could include seeking a volunteer to revive the IPG Comms working group and CSO engagement, both of which need to be reprioritised. The team should encourage other partners, including within SA gov, to drive donor co-ordination.	PRO - ongoing.
Focus on developing clearer measures of success of the partnership – in coordination with the broader IPG determining whether SA JETP needs a new political anchor going forward and what does success look like for the partnership if it is not the achievement of the aim set out in the 2021 political declaration? Given the fact the JETP was envisioned as running to 2027, work with ECED, the IPG and the JET PMU to clarify and agree what the JETP support will look like post-2027 and communicate this to stakeholders.	JETP Team with ECED – agree timelines with Envoys at meeting on 12th March.
Liaise with the central SSRM team to provide an update since the ASI scorecard submission and seek continued support on the contract management as required.	PRO – by end of April

Progress on Last Year’s Recommendations
The Programme team kept a tracker of progress against last year’s Annual Review recommendations. A summary can be found at Annex A.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The JETP theory of change, is high-level. It assumes that a combination of influencing, investment finance and technical assistance, will lead to policy reforms and catalyse private and public sector finance to accelerate the energy transition, reduce emissions and create jobs in the coal areas. While this may still hold, it is now clear that South Africa will not meet the high-end ambition of the 2030 NDC range, and hence the overarching aim of the JETP outlined in the political declaration will not be fully met. South Africa has submitted its 2035 NDC which is less ambitious than hoped and does not appear to be aligned with the majority of cost-effective decarbonisation pathways to 1.5 degrees.

This has been raised with both UK and SA Ministers. There is broad agreement that good outcomes are being achieved and that a higher level of impact (in terms of steps taken which will ultimately enable emissions reductions) will be achieved than without the JETP support of the UK and partners. However, this issue is monitored regularly, and the coming year will provide the opportunity to further assess progress and agree next steps including potentially a revised political commitment.

The September 2025 review of the logframe made some amendments to the impact and outcome indicators including amendments of milestone targets (some increased and some decreased), but the outcomes targeted remain the same.

This year, ASI have updated the sub-theory of change on project preparation TA which refines the indicators but does not substantially change the outcomes and targeted impact.

A priority for the UK’s JETP work, is supporting a “just transition”. i.e. that those whose livelihoods are most impacted by the transition out of fossil fuels, find alternative livelihoods. The challenge faced by the JETP in South Africa, is that the location of new livelihood choices and job creation is not easily aligned with the locations where job losses will occur. It is a priority for the South African Government, that new jobs are created in the region of Mpumalanga. However, many of the new agricultural jobs from commercial farming and new value-chains, are unlikely to be in the same areas as the households affected by closure of the coal mining/ power station areas.

This Annual Review, therefore, recommends that a more detailed Theory of Change is needed to consider the challenge of creating new job opportunities in the specific locations affected by transition out of coal. The international JETP programme(s) have already been considering the paucity of data on job creation from the green transition, and it is recommended that the Pretoria team work with the World Bank’s ESMAP team, engaging with the relevant South African government partners, to ensure knowledge-sharing around employment creation is being utilised in the UK programme. The ToC should also consider gender issues – women and girls but also more broadly. For example, youths (young men) when unemployed, are correlated with higher crime rates which have large social costs.

Recommendation 1: The BHC team should develop a (sub-)theory of change on ‘Just’ job creation in South Africa, ideally with collaboration/input from others working in similar areas, including the ESMAP programme. Ensure the BHC is linked into the “job creation” work around the international JETP programme.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Progress on Impact

The overarching impact of the JETP Business Case is linked to:
SA meeting the most ambitious greenhouse gas (GHG) reduction target possible within its Nationally Determined Contribution range to the extent of available resources. This was part of the 2021 JETP Political Declaration;
improved economic development via alternative economic activity in the coal areas – with the chosen measure of a narrowing unemployment gap between Mpumalanga and other SA provinces.

Progress on national level Emission reduction (objective i): Following recommendation 2 of the 2025 annual review, during the year the JETP team reviewed the interim indicators for outcome indicator 1 with the DESNZ Economic Advisor for Country Analysis & Ambition in the International Climate Analysis Team.

The UNFCCC’s transparency framework requires SA to submit an updated biennial transparency report this year (2026) which would include 2024 emissions data when produced. This will enable us to better understand whether SA met the 2024 milestone and where they are likely to land within the 2030 NDC range. However, as outlined in the 2025 Annual Review, key South African institutions have indicated that they expect South Africa will meet the high end (low ambition) of the 2030 NDC range, landing at around 410MCO2te.

South Africa submitted its 2035 NDC range of 320-380 Mt CO2-eq in October 2025. While its net-zero ambition by 2050 still stands, this range is less ambitious than we would have liked as it is less ambitious than the recommendation made by the SA Presidential Climate Committee.

The current assessment is that if SA meets the lower end ambition of both the 2030 and 2035 NDC, the impact statement could still hold, however this assumes that emissions fall linearly (e.g. by an equal amount every year) to meet these targets - and that there are no rebounds/unexpected emissions changes (e.g. increases) in the years in between, which seems unlikely.

Progress on Unemployment differential (objective ii):
The ToC envisages that livelihood creation in Mpumalanga, a coal-heavy region of South Africa, will be possible through SME support and supporting economic diversification. At the start of the intervention (baseline data from Jan-March 2022), the unemployment gap between Mpumalanga and the national unemployment rate in South Africa was 6.1%.

According to the Stats SA quarterly labour survey for Q3 2025, Mpumalanga has the 4th highest official unemployment rate out of provinces in South Africa (34.0%), and the third highest combined rate of unemployment and potential labour force (47.5%). The unemployment gap between Mpumalanga and the National combined unemployment rate in SA is now 5.1%.

Although there was a noticeable improvement in 2025, Mpumalanga continues to record some of the highest unemployment rates in South Africa, with economic activity particularly high for youth and women. During 2025, 37,000 jobs were created in the province.

The UK’s contribution on labour market interventions includes:

- Support provided by Growth Gateway to increase investment readiness of SMMEs in Mpumalanga
- Technical assistance and capital development grant funding to pre-commercial farms in Mpumalanga. It is expected that the 2 blended finance investments to date will create 198 jobs
- Improved services and more reliable electricity access through the Municipal Utility Reform Project should also support SMEs which are an important source of job creation in most economies.
Progress on Outcomes

Policy reform and transformational change

South Africa has continued to take steps towards reform of the electricity market and decarbonisation in 2025/2026, with various levels of IPG involvement including through technical assistance and influencing, although challenges persist. Key policy progress includes:

- Progress on the rules, codes, standards and secondary legislation needed for the South African Wholesale Electricity Market is being made, and market capacity is being built. On 27 November 2025 the National Energy Regulator of South Africa (NERSA) approved the granting of a Market Operator licence to the National Transmission Company South Africa (NTCSA) alongside new Grid Capacity Allocation Rules to facilitate fair and non-discriminatory access to the network.
- NERSA approved the appointment of a 14-member Electricity Market Advisory Forum which will advise the regulator on the finalisation of the regulatory instruments and ensure readiness amongst stakeholders as the market evolves.  The NTCSA is delivering the oversubscribed SAWEM school. Further work is needed to unbundle the Eskom divisions; finetune the market code; finalise the wholesale market tariff rules and trading rules; and agree vesting contracts with each coal plant.
- NERSA has issued ten electricity trading licences. A challenge brought by Eskom to the High Court on five of these licences has been temporarily stayed, with Eskom joining the NERSA working groups on the trading rules development process.
- The Transmission Development Plan outlines the need to construct more than 14,000km of transmission lines over the next decade. Minister Ramokgopa launched a Request for Qualification and draft regulations for private sector Independent Transmission Projects (ITPs) for 1,164km of transmission lines in July 2025. This is being supported by the establishment of a Credit Guarantee Vehicle (CGV), with World Bank backing, to mobilise private capital by de-risking projects in place of a sovereign guarantee. The CGV is expected to be ready to de-risk the first phase of ITP procurement by mid-2026, with planned annual ITP windows thereafter, and the potential for expansion to support the delivery of other infrastructure projects in the future.
- Cabinet approved the 2025 Integrated Resources Plan (IRP) in October 2025. The document outlines the planned allocation of South Africa’s primary energy resources. Key allocations in the plan leading up to 2030 include 10,313MW of solar PV; 7,341MW of wind energy and 6,000MW of gas to power, as well as 5,200 MW of new nuclear capacity by 2039.
- After being delayed by US objections, South Africa’s updated Accelerating Coal Transition Investment Plan (ACT IP) was approved by the Climate Investment Funds (CIF) Trust Fund Committee in June 2025. Efforts are underway to finalise the programme of activities and pave the way for expedited ACT implementation. Implementation of South Africa’s Updated ACT IP will be overseen by the ACT IP Governing Committee.
- Eskom’s stability and performance have continued to show a positive trajectory. In September 2025, the utility announced its first return to profitability since FY2017. However, municipal debt continues to threaten Eskom’s financial sustainability. Both Eskom and the South African Government are trialling and prioritising various measures to improve municipal distribution infrastructure and collections across the country.
- Following the signing of the Climate Change Act last year, South Africa consulted on phase two of its carbon tax arrangements in Nov-Dec 2024. Minister George approved publication of the draft National Greenhouse Gas Carbon Budget and Mitigation Plan Regulations for public comment in July 2025.
- South Africa submitted its revised NDC for 2035 in October 2025, with a GHG emissions target range of 320-380 MtCO₂e by 2035. This was higher than the range recommended by the Presidential Climate Commission (PCC).
- Between 9 December 2025 and 12 February 2026, Eskom’s unbundling strategy advanced through several major developments. On 9 December 2025, Minister Ramokgopa approved Eskom’s revised unbundling strategy. Minister Ramokgopa signalled that transmission assets would remain inside Eskom, prompting investor concern because this contradicted earlier commitments that NTCSA would become fully independent within five years. By 12 February 2026, President Cyril Ramaphosa used his State of the Nation Address to overrule the December proposal, announcing that South Africa would proceed with a fully independent, state‑owned transmission entity holding and operating transmission assets, and he established a task team to resolve remaining restructuring issues within three months.
UK support contributed the following during the AR review period:

- The UK has supported emissions modelling capacity in South Africa, enabled the introduction of high-resolution temporal modelling via Renewables.Ninja and institutionalisation of updated cost-performance frameworks by DEE. This materially shifted near-and medium-term renewable energy capacity outcomes in the Integrated Resources Plan. Although final capacity outcomes remain scenario-dependent, the IRP 2025 clearly reflects a structurally higher renewable ambition than the 2023 draft - based on the trust built and introduction of Renwables.Ninja into the planning process.
- The submission of SA’s 2035 NDC range. The UK and IPG lobbied through various channels both to encourage SA to make a timely submission and to encourage high ambition. The submission was less ambitious than we had hoped for, though continues to show a strong focus on a Just Transition. The UK registered this view in correspondence between the High Commissioner and the then Minister for Forestry, Fisheries and the Environment.
- The next phase of the Energy Council’s work on the South African Wholesale Electricity Market included development of a market implementation roadmap, supporting regulatory and governance alignment, examining financial implications of market liberalisation, and improving stakeholder readiness ahead of market launch.
- Transmission infrastructure is a huge constraint on the energy transition in all JETP countries. A focused grid assessment was also carried out for South Africa by the Energy Council (funded through the UK bilateral programme). The roadmap was submitted and taken on board by NTCSA and NECOM. The project contributed to early design considerations for the Electricity Market Advisory Forum, supporting NERSA’s early thinking on market governance and oversight. On grid capacity allocation, a technical approach for an analytical programme flowing from the grid assessment has been agreed by NTCSA; Eskom Distribution has agreed to collaborate on downstream access and collector-level opportunities and DEE has committed to supporting cost-recovery and policy components.
The transformational change indicator in the logframe was updated in September 2025 to ensure the scoring matches the ICF KPI guidance. The team judge that there is partial evidence that transformational change is likely (score 4), however there remains blockers and inconsistent messaging from SA Gov, and capacity to take forward projects remains a challenge.

Public and private finance mobilised

The targets for mobilising public and private finance were not met. On public finance mobilisation, this is because there have been delays in mobilising public lending due to a lack of investable projects in the pipeline. Following the exceeding of the original target in 2024, there is still a sizeable amount of unspent existing pledge, and progress on emissions in SA is mixed, hence new pledges are plateauing. Despite this, one success has been following UK influence, Norway confirmed their status as a ‘Friend of the JETP’ and will continue to mobilise funds for SA’s transition (though they did not provide a defined pledge amount). On private finance mobilised, the target set assumed mobilisation from additional BII deals, however data on finance mobilised and jobs from BII investments closed this FY will be reported in the next reporting cycle.

Mobilising finance for economic diversification:
A key area of progress has been the closing of some deals by SMMEs supported by the centrally managed Growth Gateway programme, with $20.6m of private finance and $1.1m of public finance leveraged. The TA input required was intensive, however multiplier effects are beginning to be realised (more than 50% of the deals closed in the last 5 months of 24+month intervention). The deal accelerator has demonstrated the strong potential for investment-led growth, but also exposed the persistent structural barriers that prevent high-potential SMMEs from scaling or securing consistent funding including limited investment readiness, misalignment with investors, execution bottlenecks, fragmented ecosystem support and challenging operating environments. These learnings have been collated and shared with other partners within the ecosystem through the Just Technical Working Group and have been developed into a position paper to be more broadly disseminated.

BCG are developing a Mpumalanga SMME Growth Hub as a structural solution to address some of the above challenges. The Growth Hub is intended to connect local enterprises to market opportunities, capital, and technical assistance, thereby strengthening coordination across partners, removing duplicative efforts, and enabling shared learning. This is being positioned to receive CIF ACT support.

In tandem, from April 2026 the UK is seeking to deliver a new catalytic finance facility for green economy SMEs programme in Mpumalanga. This aims to overcome some of these barriers by deploying and recycling concessional capital, crowding in commercial finance to small- and medium-sized enterprises in Mpumalanga to enable job creating growth.

The JETP CDEL investments made this year for lending to agri-businesses have already mobilised $12m in public finance and $2.4m in private finance. As above, it is envisaged that this model will be scaled crowding in more players to provide new financial products and services in Mpumalanga, without the need for grant funding.

Jobs and service improvement

The number of planned jobs committed to be increased or maintained increased to 7,491 this year, against a target of 4,000 in the logframe. This figure includes both short term (for example construction or seasonal jobs) and long-term jobs. 356 jobs are expected to be maintained or increased by the first JETP CDEL agri-business investments, while elsewhere the finance leveraged through the Growth Gateway programme has resulted in approximately 2,365 jobs committed to be increased or maintained. It is hoped that the implementation of the Municipal Utility Reform Project (MURP), the first project under the UK-supported guarantee will create a number of jobs across phases in future years.

Outcome indicator 3.2 was added during the logframe review in September 2025 to measure the number of households benefiting from improved service delivery in future years once the MURP and future relevant projects under the AfDB guarantee are implemented.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The JETP is a multi-faceted and multi-dimensional endeavour. Although there has been much progress, SA is not on course to meet the high ambition of the 2030 NDC which was the ambition of the initial political declaration. However, while there remains significant uncertainty over the pace and extent of South Africa’s just energy transition, the scale of potential change means that the impact of the programme only needs to be modest to drive large overall benefits.
This current scenario represents the ambitious nature of targets where the ‘counterfactual’ (i.e. no JETP) is difficult to judge, but where we can assert that without the JETPs, the finance flows and focus on investment plans and coal transition would have been lower and emissions higher, hence our inputs are merited even if South Africa does not meet the high ambition target. This remains our judgement, and we continue to support efforts that can move closer to the high ambition target. This should be the focus of discussions on the future of the partnership so that any follow up is based on realistic goals.
The JET PMU are intending to conduct a review of progress on the partnership so far in 2026 including engaging with the IPG on its longer-term future and lessons for country partnerships. The BHC team and the IPG will need to engage with this and come to decisions this year on the future of the partnership beyond the current agreed programme. This should include discussions on the learnings from the model, and clarification and agreement on what the JETP support will look like post-2027 with including appropriate targets and measures for success.

In terms of the specific bilateral programme, while it is early in project implementation to be able to report results, we are confident that the projects will contribute to the long-term indicators targeted, and that the team are managing the contracts to achieve good value for money. South Africa continues to be a priority country for Energy Transition and JETP remains a key pillar of the Country Business Plan,

## C. DETAILED OUTPUT

Output Title	UK funds targeted to deliver spend in an effective and just manner
Output number:		1	Output Score:	A – output met expectation
Impact weighting (%):		70	Weighting revised since last AR?	Yes, up from 30%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Value of projects ($) reaching financial close via AFDB, BII and PIDG and grant projects using UK funding under JETP that are transformative or catalytic and do not displace private sector. Cumulative	$321m (target $270m)	Significantly above target / First tranche of JETP CDEL deployed / JETP elements of the City of Joburg loan enabled by the AfDB Room to Run guarantee / 2 BII transactions reached financial close (Red Sands and Revego) / BII investments into funds subsequently benefiting JETP eligible businesses added
1.2 Value of BII, PIDG and AFDB and grant investment projects ($)(as a subset of 1.1) funded by UK JETP which are not solely ESG positive but sufficiently “Just” in nature. “Just” investments are those in Mpumalanga. Cumulative	$18.97m (target $11m)	Significantly above target / Total amount of BII investment in Agristar (macadamia nut farm in Mpumalanga) was updated in consultation with BII / JETP CDEL disbursed to farm businesses in Mpumalanga, with aim of contributing to economic diversification in the province
1.3 Value of projects ($) in pipeline which are being substantively worked up as investment projects using UK grant funding under the JETP support programme. Cumulative	$400m (target $410m)	Moderately did not meet target / One project in pipeline (Municipal Utility Reform Project) substantively progressed in readiness for AfDB board approval
1.4 Value of projects in pipeline which are being substantively worked up as investment projects using UK grant funding under the JETP support programme and which are sufficiently "Just" in nature. Cumulative	$400m (target $400m)	Met target / Municipal Utility Reform Programme aims to implement water and electricity infrastructure improvements in 4 municipalities in Mpumalanga, contributing to improved service delivery in the region most impacted by the transition.
1.5 Value of Development Capital Grant funding deployed for blending which aims to achieve Just outcomes. Cumulative.	£1.84m (target £1.5m)	Significantly above target / 1.84m disbursed across two farm investments so far with a further disbursement planned in March 2026.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output met expectation with the value of projects reaching financial close, including those which are sufficiently ‘just’ exceeding target, though the value of projects in the guarantee pipeline was slightly lower, explained below.

BII/PIDG

Two additional deals reached financial close from BII:
- $43m investment in Revego Africa Energy Fund which invests in operational renewable power assets
- Financial close reached on the Red Sands battery storage project via Globeleq (70% owned by BII, 30% by Norfund; UK share is circa $18.2m of the total investment).
Additionally, investments made by BII into JETP eligible funds (totalling $2.4m) were reported to the JET PMU this year. These included fund investments in NOA Group, SolarAfrica Energy and Wetility.

BII signed a $150m debt facility with FirstRand Bank to support Transition Finance projects across the African continent, marking BII’s first Transition Finance transaction. It is expected that a large proportion of this will benefit projects in South Africa and the total apportioned to projects in South Africa will therefore be counted in future years once individual deals are concluded.

With the launch of the Independent Transmission Projects and future REIPPP rounds, it is plausible that we will hit the $500m of BII/PIDG investment pledged for the JETP by 2027, although some of the deals are likely to be operationalised after that date.

Though no further deals were signed by PIDG this year, in the review conversation they welcomed the BHC team’s efforts to connect them with opportunities and asked that we continue with this.

AfDB Room to Run guarantee

One project was badged under the JETP Room to Run Guarantee this year. The AfDB approved a loan to the city of Johannesburg Metropolitan Municipality to finance critical infrastructure projects in electricity, water, sanitation and solid waste management. The climate elements of the loan were enabled by the Room to Run guarantee facility, with the electricity portion ($86m) counting towards the JET.

The room to run guarantee facility expires in July 2026 hence it is unlikely the balance of the $300m pledge will be utilised.

AfDB JETP guarantee pipeline

Progress has been made in developing pipeline projects for use of the AfDB JETP guarantee. The first project, the Municipal Utility Reform Project (MURP), was announced by National Treasury as part of the medium-term policy budget statement in November 2025, following progress facilitated by the transaction advisory team to conceptualise and develop the project including developing the Business Case for National Treasury and COGTA. Support included establishment ofthe funding flow mechanism. This will allow tranches of the loan to flow from AfDB to National Treasury upon the verification of pre-determined disbursement linked indicators, and from the national fiscus directly to the Programme Management Office (DBSA) that will manage the performance-based contract with private sector contractors.

The planned pipeline amount for this project could have been higher as the transaction advisors advised National Treasury that a loan amount of $557m would be preferrable in order to deliver the full scope of the proposed interventions, to include infrastructure expansion, however National Treasury decided on a cap of $400m on this programme.

The associated loan request of $400m is on track to be submitted to the AfDB board in 2026. This follows a delay from the originally planned December 2025 submission due to protracted engagement with key stakeholders and the month long-end of year break. There remains a significant risk to resolve on the overlap between the MURP and the cabinet approved Eskom Distribution Agency Arrangements which are also targeting the 4 MURP municipalities.

Target setting for the 2026 annual review assumed that the two projects in the pipeline would be substantively worked up for investment. However, the Special Purpose Vehicle (SPV) structure proposed by the East London Industrial Development Zone (ELIDZ) for the provision of a £28m 15MW rooftop solar photovoltaic (PV) and battery energy storage system encountered regulatory challenges during its submission to the National Treasury’s Budget Facility for Infrastructure (BFI). By the end of the review period, the IDZ has not yet adequately addressed National Treasury’s concerns, preventing the project from progressing. As a result, this phase of technical assistance has concluded pending the required regulatory clarification and approval from National Treasury.

Initial work was also undertaken to prepare a project to support the implementation of regenerative braking across the freight rail network of rail state-owned enterprise, Transnet. Unfortunately, Transnet decided to withdraw from the project after the initial phase, resulting in a fruitless payment for the technical advisory work already completed, including an inception report and the start of a Technical Scope Report and Cost-benefit analysis.

During the review period, ASI finalised a renewed project pipeline development process which has proposed a list of potential new opportunities and will guide direction for future projects use of the guarantee. Key activities included the establishment of project selection criteria, comprehensive engagement with South African Ministries, Departments and Agencies, and the systematic identification and screening of project opportunities. This process delivered a refined portfolio of technically robust and strategically aligned proposals consistent with the JETP Support Programme’s mandate. Six projects have been shortlisted and will be submitted to the relevant partner institutions for further review and final selection.

JETP CDEL

Technical agreements were signed with two South African agri-lenders for DevCap grants to catalyse the stabilisation and expansion of high job-creating growth potential, pre-commercial farmers in Mpumalanga. By absorbing part of the financing risk, the UK grant makes loans serviceable for the farmer (e.g., sub-prime interest, longer repayment timeframes, interest/repayment moratorium etc.) and viable for the lender (tailored first loss). An initial £987km of FCDO funds have been invested in 2 agri-lenders for on-lending to two farm businesses in Mpumalanga (Zwagershoek and Afrikan Farms) with an additional disbursement expected, and one more farm proposal in advanced stages.

The JETP team have concluded a call for proposals for a new catalytic finance facility for green economy SMEs programme in Mpumalanga for delivery in 2026-2027 (budget dependent). This will enable the blending model to be deployed for some of the high job-creating growth potential businesses supported by the Growth Gateway in Mpumalanga outside of the agri-sector.

The proposed catalytic finance facility for green economy SMEs will bolster desired outcomes in Mpumalanga and continue the direction of travel in line with steers from Ministers on using innovative models to crowd in private finance. This programme should therefore be prioritised as far as possible for CDEL budget in 2026/2027. The programme should take into account the learnings identified from the agri-business blended finance initiative piloted this year.

Note: the value of grant projects delivered across the JETP portfolio outside of the bilateral programme (e.g. centrally managed programmes) are not included in the total value for this indicator to prevent double counting at output level. At outcome level, finance and jobs data are reported from the CMPs the team work with on JET in country but are separated out to ensure they are not double-reported to the ICF. A log of all JETP-aligned grant projects registered with the JET PMU can be found here: Investment-Register-Dashboard - Just Energy Transition.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following recommendation 7 in the 2025 annual review, the weighting of this output was increased to reflect that the JETP bilateral programme is now more advanced and requires more of the team's focus, while still maintaining the influencing objectives in output 2. Weighting is more towards output indicator 1.3 and 1.4 as these are within the control of the programme team.

The 2026 target for output 1.1 was reduced from $700m to $270m. The previous target was based on planned loans to Eskom, however as a result of the National Treasury moratorium on Eskom and subsequent reluctance to borrow, these didn't go ahead, hence the number and value of projects closing have been lower than planned with the JETP programme pivoting to project preparation.

The 2026 target for output 1.2 was reduced given that much of the JETP grant money has been spent, however we expect an uptick in our ‘just’ contribution in 2027 with the implementation of the Municipal Utility Reform Project.

Outputs 1.3 and 1.4 were added to measure the success of the project preparation which has become the core bilateral programming element. The JETP team have worked with the ASI consortium to develop additional output indicators within ASI’s own results framework to track the interim steps to securing funding for and delivering the planned infrastructure projects.

Output 1.5 was added to measure progress in disbursing CDEL for capital development grants.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on recommendations

The 2025 annual review recommendations 8 and 9 set out the need for the guarantee framework agreement to be completed before the SRO left post. While this was not completed, the remaining issues were picked up by the new SRO in collaboration with IFID and the final agreement reviewed by a range of lawyers acting for both parties, ultimately resulting in the framework agreement being signed in December 2025. In tandem, the end date of the agreement was extended to enable delivery of the first project scoped for use of the guarantee, as well as to give scope for future projects.

Lessons learned

In order to progress the CDEL blended finance work, we have had to accept the tax liability associated with blending our funds with private partners in South Africa, albeit routed through a long-standing not-for profit partner. The value for money case was assessed by an Economist and our assessment of the options available concluded that this was still the best option to support job creation in Mpumalanga in the current financial year. It did not represent a material change to the JETP business case because a) the cost increase was marginal when compared to the potential benefits outlined in the CBA, due to the recycling of funds over a 10+ year period and, b) this approach to de-risking catalyses market-wide change - demonstrating a pathway to providing previously limited expansion capital to pre-commercial businesses. However, it did mean that FCDO had to provide additional funds to cover the tax liability.

The key lesson was therefore to ensure tax liabilities are examined and understood in advance of future CDEL deployments. Meanwhile, the BHC is exploring the potential for an agreement with the Government of South Africa that would remove the need for BHC supply chain partners on the development side to pay tax on grants. This could potentially result in the return of tax paid on this and any other future grants.

The BHC team should ensure the learning on the tax liabilities issue is communicated to the centre to avoid this issue being replicated in other programmes. The BHC team should continue exploring the possibility of an agreement with the Government of South Africa that would remove the need for BHC supply chain partners to pay tax on grants. If this is achieved, the BHC team must ensure the tax paid on this and any future grants is returned and used to deliver JETP objectives.

Lessons learned on ASI project preparation

The JETP Support Programme is a complex programme, providing specialist technical support with notable resource constraints in terms of people and capacity, in a complicated and dynamic political environment. ASI identified challenges from which the programme has learned lessons including: tension between programme objectives and the GoRSA regulatory environment; lack of support for some proposed projects from beneficiaries; timely deployment of technically competent TA; navigating a complex and challenging set of stakeholders; and affordability of projects funded by debt.

Key lessons from the reporting period highlighted the importance of mapping approval processes for all key decision‑making institutions at the outset of project preparation. Without an agreed process map, the project team could not align approval timelines across institutions, resulting in significant delays. As a result, several planned committee submissions and approval deadlines were inadvertently missed.

A second key lesson from project preparation was the need for a formalised project screening tool. The tool should clearly reflect the JETP’s priority targets, ensuring that programme resources are directed only toward projects that advance core objectives. It should also require documented engagement and commitment from potential development partners, confirming that the proposed concept responds to an organisational need and aligns with the partner’s strategic direction. Only project concepts that meet these screening requirements should progress to task‑order development.

In the review interview with AfDB, their key lesson related to this was the need for SA Government to be in the driving seat on the Municipal Utility Reform Project, particularly COGTA as the owner/project sponsor. It was noted that the way the project was structured was unusual with FCDO procuring the advisory team; in their view ideally there would have been a tripartite agreement.

Recommendation 2: Learnings on stakeholder engagement from this year should be reviewed and implemented. Though it will take time, engagement with South African Government stakeholders needs to be thorough and their buy-in and ownership clearly secured at key milestones (ideally early ones). Once a project is conceptualised, a consolidated, cross‑institutional approval process map should be developed, formally endorsed by the senior political and technical levels of all participating entities, and embedded into the project preparation schedule.

More broadly, the BHC team should also continue to focus on developing and strengthening their relationships with the relevant line Ministries responsible for delivery of relevant JET policies and reform; in particular DEE, National Treasury and COGTA. These will advance UK and joint IPG priorities.

Recommendation 3: Now that projects are moving to implementation, the BHC team should develop a clear communications plan which delivers positive messages to a range of local audiences and highlights the tangible outputs being delivered through the programme. This would supplement the JET-P engagement plan.

Output Title	UK influence with all stakeholders (IPG, SA government, interested parties) ensures effective JETP implementation
Output number:		2	Output Score:	A+ – output moderately exceeded expectation
Impact weighting (%):		25	Weighting revised since last AR?	Yes, down from 65%

Indicator(s)	Milestone(s) for this review	Progress
2.1 Minimum %age of those participants surveyed who assess impact of coordination groups and joint resources as positive and helpful to the way they work (according to survey). See definitions for more detail	98% (target 75%)	Significantly exceeded target / In an anonymous online survey completed by IPG members there was a 98% average score in agreement (either ‘agree’ or ‘strongly agree’) that the co-ordination and joint resources were helpful to the way they work. Note 5 responses were received against a target of 6.
2.2 Number of substantive collaborations supported by UK with private sector or philanthropies or NGOs or new development partners which support the outcomes and impact above and further the aims of JETP. See definitions. Cumulative [indicator retired]
2.3 Number of substantive collaborations supported by UK with SA Government which support the outcomes/impact above and further the aims of JETP. Cumulative [indicator retired]
2.4 Number of policy issues being substantively progressed in collaboration with the IPG and/or SA Gov to further the aims of the JETP. Cumulative	(target 3)	Met target / Work with DEE on mini-grids participation viability study and regulations / Energy Council continued work with NTCSA and NECOM on SAWEM implementation including grid capacity / UKPACT work with NERSA on tariffs

Briefly describe the output’s activities and provide supporting narrative for the score.

IPG co-ordination
This output moderately exceeded expectation, with the IPG survey significantly exceeding target, and the number of policy issues meeting target.

As per recommendation 6 of the 2025 annual review, the BHC team have looked to streamline IPG co-ordination where possible, for example by reducing the frequency of Envoy level co-ordination meetings to 6-weekly and removing a separate capitals co-ordination meeting. The Friends of JETP update is now run yearly. The survey results showed strong agreement from IPG members that the co-ordination was helpful, suggesting that the streamlining so far has not resulted in a negative impact, though it should be noted that there were less respondees this year (5 respondees against a target of 6, and compared to 8 in the previous year).

Respondents suggested that the sharing of information and market intelligence at climate counsellor level, as well as the agreement on priorities, unified IPG lines and annual report were most helpful. IPG members suggested SA institutions themselves should take on more of the donor co-ordination and technical working groups. Two respondees highlighted a greater focus on communications is needed.

In a reflective conversation between the visiting ECED lead and the JET PMU, the PMU recognised the importance of UK leadership, especially in getting the JETP up and running. They felt we now need to be clear what is in scope for IPG coordination vs what works best bilaterally.

In terms of donor co-ordination, there has been mixed momentum. The Just Technical working group, led by AfD, has been run regularly. The Transmission and Distribution donor co-ordination groups run by GEAPPP have been helpful but often proved difficult to get the right people (with knowledge of the technical project detail) in the room. As the PMU work to institutionalise the JET portfolios into government, it will be important to consider how donor co-ordination fits in and where the relevant department can help drive it.

Unfortunately, no further Civil Society Organisation (CSO) engagement was run by the UK this year and efforts to seek another IPG member to lead were not successful. It is important that the IPG continue engagement with CSOs and this should therefore be revisited.

Policy change
The logframe now measures the progression of substantive policy issues rather than the number of new policies worked on or collaborations.

The Energy Council have continued to engage with NECOM and NTCSA to work through complex policy and regulatory issues for the launch of the South African Wholesale Electricity Market. This year, critical work has also started to engage with DEE on a viability study for private participation in the installation of mini-grids. This is a policy priority for the DEE.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output weighting reduced to 25% given increased focus on bilateral programme activity as outlined under output 1. Output indicators 2.2 and 2.3 were retired in the logframe as the JETP has moved from substantive new collaborations to growing the existing collaborations and implementing policies and programmes. The team’s focus is therefore no longer on the number of new policies or relationships worked on, but on progressing the substantive issues required with partners the team already have relationships with. Hence output indicator 2.4 was added to begin measuring issues being substantively progressed.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

The 2025 annual review recommendation 6 outlined the need to ensure the BHC team’s efforts on IPG co-ordination are proportionate, including delegating to other IPG members where possible. The team have aimed to streamline IPG co-ordination by reducing the frequency of regular drumbeat meetings and removing the need for a separate regular engagement with Capital working level counterparts outside of the regular Envoy meetings. The team continue to provide the Capitals update to ensure IPG Capitals are kept informed of key developments in the energy space in SA.

This was also the first year of the Department of Energy and Electricity functioning as its own department. The BHC team identified the need to strengthen bilateral engagement with the department and used the opportunity of South Africa’s G20 engagement to build a more robust connection. The country-based programme-funded Energy Advisor is playing a vital role in building this connection and using his expertise to progress mutual objectives. We are now in regular contact and have developed a joint action plan with the department. As outlined in recommendation 2, the team should continue focussing on strengthening relationships with the relevant line Ministries including DEE but also NT and COGTA, to continue advancing UK and joint IPG priorities.

Recommendation 4: The BHC team should continue streamlining IPG co-ordination. This could include seeking a volunteer to revive the IPG Comms working group and CSO engagement, both of which need to be reprioritised. The team should encourage other partners, including within SA gov, to drive donor co-ordination.

The grant agreement for the Energy Council project, contributing to output 2.2, ended in March 2025. However, around the time the deliverables were supposed to be finalised, the Energy Council had issues with their service provider and so proactively changed their plans to improve the quality of delivery. Following this, there were delays in the NTCSA (the new transmission company under Eskom) formally releasing the roadmap which had a knock-on effect on the final deliverables.

The key lesson here is projects aiming to influence policy change in this context must have flexibility around timing proactively built in, anticipating the fact that navigating the changing landscape and the political challenges in the various organisations of government will inevitably lead to delays and require shifts in approach to achieve the aims and ensure value for money.

Output Title	UK business investment opportunities in SA’s JET created
Output number:		3	Output Score:	A++ substantially exceeded
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of UK businesses identified for which JETP is a material opportunity and who are likely to do something and who are then connected with a specific opportunity. Cumulative	26 companies identified (cumulative), 27 opportunities connected (one to a company already identified in previous year) / Target 11 businesses identified, 4 connections made.	Substantially above target / UK registered bank connected with various opportunities including IPPO and a relevant SMME exploring opportunities on landfill and municipal waste. / British multi-national bank connected with SA bank to discuss transition finance opportunities. / UK biochar company connected with DFFE to overcome regulatory hurdle. / NTCSA energy market trading opportunity shared with 2 UK companies. / UK electrolyser company connected with SA electrolyser company / Tender for Sanedi EV transaction advisor shared with 3 UK companies / EV tender for City of Joburg buses shared with 1 UK company / UK off-grid renewables company connected with Vodacom / Detail on the Independent Transmission Projects shared with 4 UK companies / Additional opportunity on EV charging systems in SA shared with a UK energy company previously identified.
3.2 Number of deals which are substantively progressed (e.g. country visits, negotiations started). Cumulative [retired indicator]

Briefly describe the output’s activities and provide supporting narrative for the score.

This output significantly exceeded expectation with a cumulative 26 companies identified and 27 opportunities connected.

The Department for Business and Trade identified an additional 12 UK businesses and connected with specific opportunities in the JETP space in SA this year. In addition, the JETP team connected 3 further businesses with opportunities as outlined above.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output indicator 3.2 was retired as data from the Department of Business and Trade regarding deals in progress may be commercially sensitive. The JETP team continue to identify opportunities for UK businesses in the JETP space and connect them with relevant contacts.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Recommendation 10 in the 2025 AR considered deprioritising this indicator. In discussion with the JETP Huddle including the High Commissioner, it was decided that it should continue to be included in the JETP logframe given the UK’s continued focus on growth for both South Africa and the UK. The JETP team continue to engage with the Department for Business and Trade to ensure businesses and opportunities are captured throughout the year and have even submitted a joint proposal for JET-aligned non-ODA funding.   No additional export wins or FDI were reported under outcome 4 in the reporting year, however several are in train which should be reported next year.

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case
The major cost drivers for the programme are technical assistance costs for ASI for the JETP guarantee project preparation, as well as management costs, overheads and travel expenses. For the blended finance for agriculture, the main cost driver is the CDEL grant, with technical assistance from Technoserve funded from the centrally managed team.
Project preparation spend/ASI contract

The ASI contract is a £9.6 million drawdown contract shared jointly with the Urban Resilience Team. £3.8m is provisionally allocated for JETP, £2.4m of which is expected to be spent by end of March 2026. The contract runs until August 2027, with scope to extend to July 2029. The timeline for preparing projects is ambitious and project implementation will continue beyond the life of the ASI contract. The projects taken to investment stage for AfDB lending will be monitored through AfDB’s processes, however it is important to FCDO to be able to track the impact of project preparation and the lending leveraged. A requirement to report back to FCDO on the results is being incorporated into the results frameworks of the various projects.

Over the course of the year, we have worked with ASI to develop both the VfM framework and indicators for the programme. The updated ASI logframe is attached at annex A. The VfM indicators are:

Criteria	Proposed metrics	Data source	Baseline
Economy	For URP & JETP combined: Average fee rate per day across the team delivering TA / For URP & JETP combined: Cost of local personnel as % of overall personnel costs / For URP & JETP combined: Expenses as percentage of the project budget	Internal management and financial data	1. £538 / 2.65% / 3. Expenses make up 2.17% of the total budget at the baseline
Efficiency	For JETP: Unit cost per project, which has been i) been developed to proposal stage and ii) for which funding has been mobilised / For URP & JETP: % of TA costs focussed on moving forward viable projects.	Internal management and financial data / MERL data	To be developed based on data from FCDO on comparable programmes / 50%
Effectiveness	For JETP: TA cost per investment leveraged from international and/or BIP investors. / For JETP: Proportion of infrastructure investments with clear climate rationale and mitigation and/or adaptation outcomes.	Internal management and financial data / MREL data	1. To be developed based on data from FCDO on comparable programmes / 3. 100%
Equity	For JETP: Proportion of projects for funding aligning with JETP ‘Just’ requirement / For JETP: Proportion of projects which will ultimately contribute to improved service delivery	Internal management and financial data / MERL data	TBC / 50%
Cost-effectiveness	Cost per job created / Price per tonne of GHG emission abated/reduced / Cost per Household with access to improve service delivery / Whole-of-programme cost	Additional modelling	1 – 4 To be developed based on data from FCDO on comparable programmes

ASI have noted the difficulty in establishing a baseline for the efficiency, effectiveness and cost effectiveness metrics against similar programmes due to the nature of the programme – TA for project preparation targeting specific sectors with multiple aims simultaneously and in specific locations. The BHC team have enlisted the support of a VfM specialist from within the FCDO to identify appropriate benchmarks and baselines from similar FCDO programmes for the VfM of the pipeline development work. Initial inputs are outlined below, however given the breadth of inputs, this work will continue beyond this AR.

Initial feedback from the VfM specialist is that the scope of the contract is very broad, and has adopted design features from the UK ICF, (UK International Climate Fund), reflecting the source of the UK’s funding and net-zero lens on energy transitions. However, the VfM specialist has noted that assessing VfM against the high level ICF indicators is likely to understate the results and impact of the package and in particular the focus of the Municipal Utility Reform Project which is aiming to address broader social and economic inequalities in Mpumalanga as part of the ‘Just’ commitment. This hugely important work firmly adds value in supporting change at the municipal level through a new model using private sector contracting which will support the municipalities capacity to deliver the serve through and increase revenue. This may not, in itself, reduce emissions or directly result in long term Mpumalanga jobs – but it will help remove political and social barriers to SA energy transition – and it will directly contribute to reducing poverty. It is important that results are explained in this context, potentially with a MEL indicator that measures removing of political and social barriers to transition.

The VfM specialist also noted the important distinction with regards to GHG emissions, whereby the long-term outcome of the JETP is macro-level emissions reduction, but to deliver this macro-level outcome a Just Transition is required, which will involve projects that may increase emissions at the micro/household level due to increased access to energy and water services.

The reporting on the investment portfolio therefore needs to make clear which intended result the project is contributing to and how. It will be important to develop a clear narrative, with case studies, on how the TA is helping to deliver the broader just and social transition to show the value for money of the programme from an equity point of view, beyond the hard metrics on indicators such as jobs, GHG reductions and households with access to improved services.

Recommendation 5: The BHC team should consider a review of the identified indicators and consider where it may be possible to better capture the potentially transformative impact on social and economic justice of the projects which would capture impact beyond the proposed hard metrics identified.

Municipal Utility Reform Project
It is very early days for results reporting on the MURP, with the mechanism for allocating funds to the projects only agreed in late 2025 and loan approval still underway. The pre-feasibility reports conducted by ASI on each of the four municipalities voluntarily participating in the Municipal Utility Reform Project identified similar positive economic Benefit Cost Ratios (BCRs) to those outlined in the strategic case for project preparation in the business case addendum (1.59 – 2.57 for water, 2.28 for electricity). This confirms that there continues to be a case for project preparation spend in these municipalities. However, lack of consistent data from the municipalities continues to prove a challenge and as such the BCRs continue to be indicative. The MURP design has been adapted to incorporate a data baselining exercise by the private sector contractor once appointed in the enabling phase, which will inform an updated cost benefit analysis.

Ultimately, the quality of activity identified for each municipality and opportunity for impact still look very positive, though the timeframe for delivering and reporting results is likely to run well beyond the ASI contract which ends in 2029 and it will only be possible to assess the effectiveness of the project preparation then. This was recognised in the business case, and our work with ASI on developing the Results Monitoring Framework for the Municipal Utility Reform Project has a focus on ensuring the outcome and impact level results on jobs created, GHG emissions avoided, and service delivery improvements to households are monitored by the PMO and fed back to FCDO through the guarantee relationship with AfDB. This will ensure we are able to track these and assess the cost effectiveness of the intervention. A similar approach will need to be taken for future projects.

Technoserve spend and agriculture jobs
The business case addendum and the previous annual review assessed the economic case for SME investments in Mpumalanga. The expected cost per job outlined in the previous annual review for the agribusiness CDEL was approximately £10k. Following this calculation, we expect to create or maintain 198 jobs for the first tranche of £1.158m CDEL, resulting in an average expected cost of £5,848 of grant per planned job. This is a positive indication as it is lower than estimated and broadly in line with the comparators identified last year. However it should be recognised that these are planned jobs. Also, to validate the assessment of VfM further work is needed to assess the quality of the jobs (how many are seasonal vs permanent etc). The programme team acknowledge that the creation of a new, seasonal job in agriculture, does not replace the loss of a coal mining income to the dependent family and should not be perceived as such.

Despite this, it is important to capture the potentially transformative impact of the investment. For example, the value of supporting the stabilisation of and expansion of sustainable businesses beyond the jobs numbers. Ensuring the business and jobs are sustainable will have greater impact than the creation of jobs which turn out to be shorter term if the business itself is not sustainable. Again, the team should further consider ways to measure and report on the broader transformative social and economic impact beyond jobs numbers.

The £1.158m of CDEL has also leveraged £1,818,700 of private finance (ratio 1:1.6) and mobilised an additional £9,143,962 of public investment into similar initiatives being carried out by agri-lender partners (ratio 1:7.7). Importantly, this project is seen as a pilot and hopes to act as a proof of concept and crowd more finance into the region and sector. If this is achieved it will exponentially increase the value for money through the leveraging of further public and private finance.

BCG spend, jobs and green growth

The deal accelerator work has leveraged finance this year, with one large deal substantially increasing the overall ratio of TA input costs to finance leveraged. There are planned jobs reported, though it will be difficult to collate accurate data on indirect jobs given BCG are not the investor. As noted above the work by BCG has highlighted the persistent structural barriers that prevent high-potential SMMEs from scaling or securing consistent funding. SME finance is a high-risk activity, and the replacement of mining incomes in Mpumalanga will not be secured solely by the provision of SME finance. The planned catalytic finance facility may offer VFM via proof of concept (similar to the agri-financing pilot), while the operationalisation of the SMME Growth Hub can create synergistic benefits that improve VFM for BCG and other ecosystem actors. Transferring BCG’s relationships and SME and funder databases into the hub (with full time staff rather than consultancy) aims to create a long term sustainable solution which should lower the input cost required for deal acceleration and subsequent jobs over time. However the creation of viable jobs, and replacing mining incomes will continue to require a portfolio of approaches both across the IPG and beyond.

The Growth Gateway programme assumes that capital mobilised in green growth investments will lead to job creation, however as discussed above we do not yet have a good ToC on job creation. The World Bank ESMAP team are looking into this. Any findings should be taken into account both in SA and more broadly under the Growth Gateway programme to ensure continued value for money on investment readiness TA.

Assessment of whether the programme continues to represent value for money

The 2025 annual review explored whether the programme still provides VfM if the high ambition 2030 NDC won’t be met. It was noted that the key determinant here is whether the interventions in the programme stand on their own merit. Our judgement remains that they do so – the work on alternative employment in Mpumalanga targets one of the poorest provinces, and the model is being employed by the Economic Growth team in tandem and in line with the FCDO direction on investment and mobilisation of private capital. The ASI work on project preparation for infrastructure projects will bring broad benefits in terms of infrastructure and service improvement, and is utilising a shared contract with the Urban Resilience team to prepare projects, with the added benefit of a funding stream already being identified through AfDB lending and the guarantee.
The opportunity to diversify South Africa’s energy mix out of coal is significant, and as such the potential reward from interventions in South Africa and the other JETP countries remain significant. The obstacles to energy diversification in South Africa are many and complex. Electrification, and reliable, affordable, access to electricity will make diversification of the energy mix, and shutting the coal plants, possible. An essential criteria for this to happen, is protecting thousands of poor households in provinces like Mpumalanga from the poverty that would follow closure of the plants without provision of alternative incomes.
This review has reported progress on setting up mechanisms to support economic diversification and inequalities at municipal level. Now that the foundations are in place, and key governance decisions made, we can expect to see progress on actual results accelerate. These should include: project preparation, investment approvals, disbursement of funds, and results reporting. Further work is ongoing to continue improving the MEL framework and ensuring quality of results reporting. Early signs are encouraging for project preparation, and disbursement of the JETP CDEL.
Regarding the value of the broader JETP partnership, an update was communicated to the new Minister for Development in July 2025 through an information note and follow up meeting. This noted that the UK approach has taken a pragmatic and flexible approach to maximise ambition on emissions reduction, rather than withdraw funding. This reflects the ambitious nature of targets where the ‘counterfactual’ (i.e. no JETP) is difficult to judge, but where we can we assert that without the JETPs, the finance flows and focus on investment plans and coal transition would have been lower and emissions higher, hence our inputs are merited even if South Africa does not meet the high ambition target. This remains our judgement, and we continue to support efforts that can move closer to the high ambition target. However, as noted above going into 2026, the UK and IPG will need to consider the longer-term approach to SA’s JETP including how to measure success in any follow up, given the financing commitments were generally made up to 2027.

E: RISK

Overview of risk management

The programme has an overall risk rating of Major, which continues to reflect the complex environment in which the JETP operates, as well as the severe strategic risk that international headwinds and domestic politics/context mean South Africa is slowing the energy transition and hence not meeting high ambition emission reduction targets. The likelihood of missing targets has been communicated to UK Ministers and there has been broad agreement that work should continue where it represents value for money irrespective of the likelihood of South Africa hitting the high ambition 2030 target. Going into 2026, the UK and IPG will need to consider the longer-term approach to SA’s JETP given the financing commitments were generally made up to 2027.

Recommendation 6: Given the admission that South Africa is not on course to meet the high ambition of the 2030 NDC, the BHC team should focus on developing clearer measures of success of the partnership – in coordination with the broader IPG determining whether SA JETP needs a new political anchor going forward and an alternative vision of success to the one set out in the 2021 political declaration. Given the fact the JETP was envisioned as running to 2027, the BHC team should work with ECED, the IPG and the JET PMU to clarify and agree what the JETP support will look like post-2027 and communicate this to stakeholders.

A full review of the programme risk register was conducted in August 2025 with support from the Africa Risk and Programme Compliance Lead and broader Team. Two risks were noted as consistently above appetite, one related to Fraud and Fiduciary, and one to People, both with cautious appetites and major net risk ratings. This prompted a discussion with the JETP Huddle around strengthening mitigations, deciding whether the risk is being tolerated and/or considering a reassessment of appetite. As a result, the People risk appetite was updated to receptive, increasing our tolerance to the risk and noting that the team is willing to operate with some fluidity in staffing and leadership, culture and behaviours supported by improvement plans, as long as we have strong systems, strong communication and information management systems, some overlapping functions and strong capability.

The fraud and fiduciary risk appetite remains cautious, however we clarified that the risk appetite differs between the bilateral programme and the broader JETP portfolio. Our appetite for the bilateral grant programme remains cautious, however our appetite across the broader JETP portfolio has increased to receptive as we are moving into implementation phase for use of the AfDB guarantee, and the number of partners has increased. Some partners have systematic problems and poor track records. We remain willing to engage in sectors and contexts where we are most exposed to fraud risk, where returns justify it.

Mitigations are in place to reduce this risk. For the Municipal Utility Reform Project, we have adopted a results-based contract financing option administered by an experienced independent PMO (DBSA) who will procure in adherence to the AfDB’s Borrower’s Procurement System, with no funds flowing directly to municipalities. Funds will be disbursed based on the achievement of DLIs and an Independent Verification Agency is built in to provide a 2nd/3rd line of defence. It will provide ongoing review of performance, this should deter and detect fraud within reasonable timeframes although won't be immediate. A separate fraud risk register has been adopted to monitor this risk throughout programme delivery.

Areas requiring particular assurance

1. Gender equality

Recommendation 4 in the 2025 annual review outlined the need to ensure that measures of gender equality are assessed in the make-up and behaviour of all implementing partners of the programme.

1.a. ASI

The ASI contract includes social value KPIs which allow for the tracking, reporting and where needed adjustments to ensure the inclusion of women and other marginalised community members in the delivery of the ASI support as well as to encourage greater inclusion in the municipalities ASI work with. As of December 2025, 47% of subcontractors engaged are businesses where the shareholders are majority black OR women, against a target of 50%.

Within the Municipal Utility Reform Project, the 2025 annual review recommended we incorporate into performance-based contracts in the municipalities GEDSI measures around the engagement of, for example, professional women and equal pay. These have been actioned through an increased GEDSI focus to embed social and gender considerations into contract design, monitoring and implementation.

This includes a targeting strategy which the MURP contractor will be required to follow for effective and equitable infrastructure upgrades and meter installations, ensuring vulnerable households, such as female-headed households, are prioritised. The collection of customer data will provide municipalities with the data needed to update social registries, an important step in ensuring vulnerable households access the basic services they are entitled to. Women, serving as central facilitators in community education and feedback processes, will play a crucial role in strengthening trust in service delivery while also creating jobs for local women. The rehabilitation of streetlighting will be rolled out in a way which prioritises positive impacts on women’s mobility and safety in public spaces. Contractors will be required to set and meet targets for women’s participation in employment and training opportunities and will be required to adopt codes of conduct, training for workers, and other measures to mitigate GBV risks.

One of the Disbursement Linked Indicators for the loan is tied to the implementation of the Environmental and Social Systems Assessment (ESSA) action plan and the Customer and Connection data being made available, meaning payments to the borrower are only made once these conditions are met. The programme action plan places programme control with the central PMO who will be required to report to an independent verification agency on the social and gender recommendations.

1.b. Technoserve

As part of the TA provided under the central CASA programme, Technoserve provides gender TA which includes co-developing gender action plans with the farms supported, carrying out gender assessments and creating a gender strategy for each farm.

For the blended finance investments, the CASA logframe and the accountable grant include a target of 50% jobs for women. Both of the agri-lenders are required (as per the technical agreements with FCDO) to report on gender inclusivity metrics including percentage of female founders/board members/senior management etc.

2. Safeguarding

2.a. ASI

The ASI consortium consists of multiple downstream partners. The ASI PMU has developed a set of Duty of Care Standard Operating Procedures (SOPs) which includes safeguarding SOPs, and training on these SOPs was delivered to consortium partners.

In February 2026 ASI’s Head of Operation and Risk for Africa visited Cape Town and Pretoria to conduct a full review and update of the programme’s duty of care policies and procedures, operational procedures and safeguarding. This culminated in a set of recommended actions including ongoing scenario-based safeguarding refresher training; an audit of supplier safeguarding policies to ensure alignment with ASI and FCDO expectations; reminders of reporting mechanisms; implementing of travel reports to facilitate an easy mechanism for concerns to be raised. Following which, ASI developed a thorough plan for implementing the recommendations, which includes specific timelines and courses of action. Implementation is currently in progress.

2.b. Technoserve

As the number of downstream partners increases, it was noted that FCDO may have limited oversight of safeguarding practices across the delivery chain. The JETP team do not engage directly with vulnerable groups, however it was noted that the blended finance CDEL presents a greater safeguarding risk given the funding flowing directly to farms employing workers from rural communities.

Technoserve conducted a thorough due diligence on each agri-lender which identified gaps in ESG, AML, whistleblowing and safeguarding. These were not considered red flags, given the size and stage of development of the institutions, which prior to FCDO had not yet received investment from international donors. To mitigate the risk, required progress in all of these areas is written into the agreements with lenders as a condition of the CDEL, with further disbursements contingent on progress being made. The lenders are now working on the required formalisation of their policies and systems - they are showing good progress (e.g., AFF draft policies, Hortfin ESG/AML workshop completed). As the Technoserve contract ends, it will be important to ensure continued monitoring of this progress is built into the transition plan.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

ASI

In May 2025, the SRO submitted a score of 50% to the SSRM scorecard for the period of 1 October 2024-31 March 2025. Since then, the contract has continued to prove challenging to manage, though ASI have taken several steps to address each of the issues and there has therefore been some improvement.

Recommendation 7: The BHC team should ensure the central SSRM team are updated on progress through the next scorecard submission and seek their support if needed.

Supplier performance is assessed against 3 KPIs. Payment of 10% of the core fees is tied to KPI performance and this payment is withheld upon invoicing every quarter. At the end of the year, the programme SRO will determine whether the withheld amount is fully paid to ASI, partially paid or withheld in full, based on ASI’s aggregated KPI performance over the year. FCDO have indicated that it will not be fully paid based on performance so far.

An update on each of the KPIs is below:

Timely provision of budget forecasts with high levels of accuracy in quarterly forecasting, efficient spending and maintenance of financial records.
Forecasting has generally been submitted on time but with low levels of accuracy (average -9.95% over the period of Aug 24 – Dec 25), predominantly driven by delays in TO submission, approval and mobilisation with some smaller variance caused due to core team fluctuations, expense variations and human and process errors. ASI have recognised that financial variance overall has exceeded target tolerance and improvements to financial management – while incomplete – are being made.

Timely delivery of high-quality quarterly reports, programme deliverables and agreed workplans (including TOs).
In the initial months of implementation, the JETP Support Programme team failed to produce deliverables of the required standard, and timeliness of delivery was poor. Key team changes have been implemented by ASI and have led to better allocation of roles and responsibilities across the consortium. The recent introduction of a JETP Co-ordinator should further help address reporting and programme delivery issues. In the latter half of 2025 deliverable quality and timeliness has improved, however the annual report submitted in December 2025 was poor quality and lacking programme specific analysis, requiring resubmission. Continued focus on improving the quality of deliverables and providing high quality products the first time around is needed.

Contribution and timely response to FCDO processes including risk reports, MREL and technical enquiries.
The JETP Support Programme team is responsive to ad hoc FCDO requests. There have however been delays in the submission of minutes from various meetings. Performance on MREL was mixed. Engagement initially only focussed on measurement of the ASI contract, and MREL had to be broadened to ensure that results for the projects for which funding is mobilised (such as MURP) can be tracked and reported, including beyond the life of the ASI contract. This was addressed through the development of a MURP specific results framework in mid-2025 and MREL engagement has seen some improvement in the latter half of 2025. The risk register process is improving though there were delays sharing it with FCDO and a key programme risk was missed.

There have been inefficiencies and inaccuracies across operational, financial and programme management. ASI have now established and maintained a suite of Standard Operating Procedures which details the systems and processes ASI use which all partners must follow which is beginning to help improve the programme management.

The BHC team have been stretched during this period and steers to ASI were not always consistent as a result. To ensure FCDO is an effective partner to deliver the programme, the BHC team will aim to ensure internal alignment across both sides of the contract and respond promptly to asks for clarification.

Technoserve

Technoserve has proved to be a strong delivery partner, responding quickly to set up the pilot CDEL blended finance in short timeframes, adjusting to the clarification on tax status and providing clear reports and regular updates. Feedback from both the agri-lenders and the TA beneficiaries during site visits was overwhelmingly positive. They provide timely forecasts and quarterly reporting.

Energy Council

The delays to completion of the Energy Council project meant that some of the final payment has remained with the Energy Council and not all deliverables were achieved before the Accountable Grant Agreement ended. While the Centre for Delivery stipulate a programme closure period of 18 months, there was not a clear PrOF rule regarding what is deemed ‘reasonable’ beyond the end date of a project. Advice was sought from Financial Accounting to ensure the delay was managed appropriately. Ultimately the SRO agreed to the continued work to ensure the completion of the deliverables by the end of this financial year. Energy Council continue to provide regular updates and the BHC team continues to have confidence in their ability to deliver. The Programme Manager has worked closely with the Energy Council to calculate the interest gained from funds remaining with the Energy Council to ensure it is used appropriately.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Monitoring is conducted by the BHC team throughout the year, including through 3 field visits this year which also informed the annual review.

The annual review process consisted of:
Desk based exercise to review programme documentation including reporting from implementing partners
Focussed VFM review by an expert/economist
3 x field visits to support review of the new CDEL agri-business element and the Growth Gateway SME support, including interviews with beneficiaries, lenders and implementing partners
1:1 interviews with: ASI consortium partners; National Treasury as govt counterpart for ASI work; East London as a beneficiary of TA from ASI; AfDB; BII; PIDG
Discussion with internal teams on JET-aligned programmes – UKPACT and Economic Development Team
Feedback from JET PMU to capitals counterpart
Survey of IPG partners via Microsoft forms

Results relating to the wider JETP initiative

The BHC team have continued to track the many different programmes and investments contributing to SA’s JETP and sharing this with the PMU. We have also begun implementing the PMU’s monitoring template which aims to gather data on 5 core indicators from all these programmes (GHG emissions, jobs, service improvement, community involvement, livelihoods). While this has been challenging (and not always possible for closed programmes), the UK has made progress in providing pilot data and worked with the PMU on how best to present the data.

Input has been provided into the PMU’s quarterly monitoring reports found here: JET-Q3-December-25-Final.pdf

Results specific to the bilateral JETP support programme

The BHC team has continued to follow up with Loughborough, the Energy Council and SA Medical Research Council to track how the deliverables have been used, with updates shared in the policy change outcome/outputs above.

Where implementing partners report directly to the centrally managed Centres of Excellence, we have ensured they explicitly identify and speak to our key JETP metrics, for example on finance mobilised and gender jobs targets. For the JETP CDEL, the continuation of the Technoserve TA under the CoE is not yet confirmed, so the team will need to clearly plan how the data will be collected going forward.

The MREL framework for the ASI contract expanded over the course of the year to include the projects (such as MURP) for which funding is being mobilised. It will be particularly important to ensure the results of the projects including MURP can be tracked and reported to FCDO by the AfDB through the guarantee relationship, hence the full results framework has been mapped and reporting to relevant parties included.

As outlined in the VfM section, the VfM specialist has made recommendations on the MEL indicators including how we can better capture the transformative change of the interventions. Work will continue to finalise the recommendations from the VfM review in line with recommendation 4.

Evaluation

As mentioned above, the JET PMU is planning to conduct an evaluation of progress so far on the JETP which should feed into conversations with the IPG on the future of the JETP as per recommendation 6. The coming months will also see a review prior to the decision on continuing the ASI consortium contract in March 2026.

Learning
The BHC team have aimed to capture lessons and share them with the IPG and wider donor community. For example presenting to the Just Technical Working Group on the lessons from the Growth Gateway programme and presenting emerging findings on viable projects from the project preparation work. The ASI programme includes ‘pause and reflect’ sessions with FCDO to review progress, share lessons and adapt direction. Key lessons identified for the programme have been outlined throughout the report. A key lesson identified for wider FCDO development work is the need for an update to the guidance on development capital grants, which should include the issue identified on tax implications.

Date of last narrative financial report	ASI: December 2025 / Technoserve: December 2025	Date of last audited annual statement	ASI: 29 September 2024 / Technoserve: December 31 2024

Annex A: Update on recommendations from 2025 Annual Review

Of the 11 recommendations from the 2025 Annual Review, 6 have been completed and 5 are ongoing. Substantive action has been taken on all 5 of these, however they are ongoing because they are recommendations we should continue to take into account, rather than because they have not yet been addressed. An update on each recommendation is provided below.

No.	Recommendation	Action to be taken	Update since last AR
1	Use senior officials’ and ministerial visits to SA to push and progress approvals through national and local SA institutions. This applies to issues related to the FCDO/AfDB guarantee $400m loan work for distribution municipalities in particular, but also for pushing progress on markets, emissions, transmission and other work.	Revive engagement strategy and consider key moments to utilise seniors and visits.	Ongoing - Continued to use HC to unblock issues on the $400m loan. Project was announced by NT in the mid-term budget statement in November 2025. G20 visit of DESNEZ Minister used to push key messaging on reform. Various engagement on SA’s NDC submission including letter to Minister George.
2	Review (with input from the UK’s Department for Energy Security and Net Zero (DESNZ) where possible) the interim impact milestones for GHG emission reductions in the log frame given SA’s deferrals of coal plant decommissioning.	As per recommendation.	Completed - Review conducted with DESNEZ economic advisor on country analysis and ambition. His view was impact statement could still hold. Agreed interim milestones should stay the same for now, and then we should re-assess once SA submits its next Biennial Transparency Report in 2026. If this is delayed, DESNEZ will look to provide support for alternative modelling.
3	Ensure that the UK keeps the issue of ‘Just’ at the forefront of all its programming and influencing work and consider how to mainstream it beyond the existing Just thinking.	Keep ‘Just’ in the IPG shared priorities and maintain Just elements of the programme through both ASI and the SME work. Share learnings from UK’s Just work with wider development partners.	Ongoing - work to make use of the available CDEL to support blended finance structures in the JET. Also encouraging BCG to explore options using the CIFs funding to proceed with their SME hub concept. / Presented our evidence synthesis review of our SME development work to the ‘Just’ donor technical working group to ensure lessons learned were disseminated and taken into account by other donors. / Just criteria is included in the selection criteria for guarantee pipeline projects supported by ASI, and in ASI reporting on progress and performance (logframe and VfM)
4	Ensure that measures of gender equality are assessed in the make-up and behaviour of all the implementing partners of the programme. We should include in the AfDB loan work and conditions of the performance-based contracts in the municipalities genuine measures around the engagement of for example professional women and equal pay. Implement the drafted requirements on CDEL implementers in this area.	Include gender measures in ASI PBC requirements and in agreements with CDEL implementers. / Raise gender with all implementing partners as part of regular programme management check-ins; discuss current status and any steps to be taken.	Ongoing - ASI building in reporting on indicators to track risks and benefits for women and marginalised people as part of the PMO requirements for the municipality projects such as MURP. / Included in Technoserve agreement requirement for proportional and meaningful assessment of how the specific needs of girls, women, boys and men are considered, and reflect to what extent women and girls have been included in design, implementation and monitoring. Also included a target for 50% of jobs created or maintained to be for women.
	Amend the methodology descriptor for Transformational Change via civil societies to reflect the reality that the civil society are unlikely to positively promote the JETP as their focus is often exclusively on Just and jobs; the ambition should focus more on getting CSOs talking about emissions and encouraging them to make concrete reasonable and actionable suggestions to support progress on the JETP.	Draft updated wording for level of change descriptors.	Completed - Amended methodology descriptor in logframe. / Liaising with the central results support team for ICF KPI 15 to determine whether we can streamline our methodology to better align with the ICF criteria.
6	The BHC Pretoria team should continue to ensure that work to coordinate the IPG is proportionate and consider with HQ if there is more that could be managed from HQ/the centre.	Discuss with ECED on ways of working, regular review of what we can ask ECED to manage.	Ongoing - Regular discussion with JETP huddle on co-ordination including ECED leading on non-paper on future of JETP.
7	In the next revision to the logframe, the weighting of the IPG co-ordination work should reduce (suggested level is about 10%). New indicators should be added to measure progress on programme spend including the project preparation work with ASI and the CDEL blended finance investment for SMEs.	Discuss recommendation with JETP huddle to ensure consensus on reduced IPG co-ordination. / Draft appropriate indicators to measure programme progress for next logframe review.	Completed - New output indicators 1.3 and 1.4 added to measure progress on ASI and output indicator 1.5 to measure progress on CDEL blended finance investment for SMEs. / Amended weighting of IPG survey indicator (output 1.1).
8	AfDB loan guarantee framework agreement (implementing the existing heads of terms and signed concept note) needs to be finalised before SRO leaves (her legal background is essential). There also needs to be a model for securing expertise long term with such guarantees.	SRO to prioritise finalisation of guarantee framework. Discuss plans for long-term resourcing with IFID.	Completed - Guarantee framework agreement signed December 2025.
9	IFID should put more pressure on AfDB to finalise the guarantee documentation and for AfDB to deploy more local resource to find pipeline and progress projects.	Share recommendation with IFID and track progress.	Completed - guarantee framework agreement signed December 2025.
10	Given that output 3 has been exceeded and the time it absorbs from the BHC Pretoria team, to deprioritise this. The UK Department for Business and Trade team should continue to engage to increase the number of deals which are substantively progressed.	Discuss recommendation with JETP huddle. Adapt logframe targets accordingly.	Completed - Steer from HC was to keep this element given continued focus on UK Growth. / JETP team will continue to identify businesses where possible and push DBT to share where they have made connections. Submitted a non-ODA bid which could help facilitate connecting UK companies with potential JETP opportunities.
11	Before the next Annual Review, do a value for money analysis on (a) the BII and PIDG investments on some of the hard metrics suggested within the value for money section and also on (b) the ASI Consortium work.	Discuss what existing VfM analysis is done by BII and PIDG and how this can be incorporated. / Develop VfM framework for ASI Consortium work.	Ongoing – Reviewed and worked with ASI to refine the MEL framework. Also secured 10% resource from a VfM expert in energy cadre to conduct a VfM framework review and support on developing appropriate benchmarks and baselines in January 2026. Early recommendations have fed into this AR, and this work will be continued as per recommendation 4 in this AR.