## SA JETP
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | South Africa Just Energy Transition
IMPACT | Impact Indicator 1 |  | Baseline 2020 | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029) | Emissions are estimated from an assumed 500 Mt baseline in 2020
SA on trajectory to achieve 1.5 GT of GHG emissions reduction by 2042, through a just energy transition from coal to renewable energy | Annual emissions and (GHG (CO2te) emission reductions) in relevant JETP sectors reported as achieved by SA Govt or in absence of a report SA coal closure and transport policy on track | Planned | 500 Mt CO2 | 418 Mt (82 Mt CO2 emissions reduced from baseline) | 398 MT (102 Mt CO2 emissions reduced from baseline) | 388 MT (112 Mt CO2 emissions reduced from baseline) | 379 | 369 | 360
Achieved
Source
FCDO emissions modelling based on SA's highest NDC ambition, then updated coal plant decommissioning schedules. Achieved data will be sourced from South Africa's submission to the UNFCCC once available.
| Impact Indicator 2 |  | Baseline Jan-March 2022 | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Rates of employment (including informal sector) in Mpumalanga - narrowing the gap versus national average. Gender disaggregated. | Planned | Mpumalanga: 51.6% unemployment. National average: 45.5% unemployment | NA | NA | 5.8% gap | 5.7% gap | 5.6% gap | 5.5% gap
|  | Achieved |  | Mpumalanga: 47.9% National average: 41.7% (6.2% gap) | Mpumalanga: 47.8% National average: 41.9% (5.9% gap) | Mpumalanga: 47.5% National average: 42.4% (5.1% gap)
Source
Stats SA - Quarterly Labour Force Survey
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029) | Assumptions
Policy reform and transformational change takes place in key JET IP sectors of Energy, Electric Vehicles, Hydrogen, Just | Number of JETP supportive policies, regulations and standards adopted or amended due to IPG influencing/initiatives or support, including UK participation. Cumulative number. | Planned | NA | 2 | 4 | 8 | 9 | 10 | 11 | 1. GSA remains collaborative and supportive of the JETP and builds capacity 2. Stable SA government throughout 3. NGOs, business and other stakeholders engage to achieve JETP 4. Open educated media transmits JETP messages fairly.
|  | Achieved |  | 3- EV white paper, private sector transmission policy, curtailment policy | 7 - EV Tax incentive; Loan with ongranting to municipalities; Electricity Regulation Amendment Act coming into force; NECOM 2.0 plan/workstreams | 11 - UCT contribution to IRP modelling; NDC submission; ITP draft regs published; market implementation roadmap
Source
Collation of policies /key legislation passed in JETP sectors
| Outcome Indicator 1.2 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Transformational change in SA Govt, SA NGOs and private sector and MDBs - working together to achieve and embed energy transition across all parts of society, but especially ministries. | Planned | See separate tab | A. PS - 1. B. Central Gov - 1 C. Local gov - 1 D. CSOs - 1 | A. PS - 2 B. Central Gov - 2 C. Local gov - 2 D. CSOs - 2 | 4. Partial evidence that suggests transformational change is likely | 4. Partial evidence that suggests transformational change is likely | 4. Partial evidence that suggests transformational change is likely | 5. Substantial evidence that suggests transformational change is likely or already occurring
|  | Achieved |  | A. PS - 2 B. Central Gov - 0 C. Local gov - 1 D. CSOs - 1 | A. PS - 3 B. Central Gov - 2 C. Local Gov - 2 D. CSOs - 2 | 4. Partial evidence that suggests transformational change is likely
Source
Various - see transformational change tab
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
| 5 (3 HCS + 2 CBS) | 9.12
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029) | Assumptions
Substantial amount of public and private finance mobilised by UK actions to support the JET IP and contributes towards the overall $98bn funding requirement | Public climate finance mobilised (GBP) ICF indicator (this includes DFIs) using some UK influence. Cumulative. | Planned | 0 | 50m | 150m | 2.7bn | 2.7bn | 2.7bn | 2.7bn | 1. JETP stays on course and attracts more funding of all types. 2. Private investor appetites remain high and economy and policy environment conducive.
|  | Achieved |  | USD 2.6 billion (NL, DK joining IPG + Canada, Spain and Switzerland JET aligned contributions) | 2.6bn plus USD 13.81m this year | 2.64bn
|  | Of which MDB DFI finance or other ICF programme leveraged |  |  | 13.81 USD | 25m USD
Source
| MDB, DFI and other ICF programming separated out |  | Reports from DFIs, MDBs, programme implementers and public sector collaborators
| Outcome Indicator 2.2 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Private climate finance mobilised (GBP) using some UK influence. ICF indicator (this includes philanthropies). Cumulative | Planned | 0 | 0m | 100m | 900m | 1.1bn | 1.5bn | 1.5bn
|  | Achieved |  | 0 | 687.45m | $712.28m
|  | Of which MDBs or DFIs or other ICF programmes leveraged finance |  |  | From BII and PIDG investments | $709.87m
| MDB, DFI and other ICF programming separated out |  | Source
Reports from DFIs and MDBs, programme implementers and private sector collaborators
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
| 4 (2 HCS + 2 CBS) | 9.12
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029) | Assumptions
Energy transition (in broader sense of JET IP) occurs in a just manner, ensuring benefits are felt by all of society | Number of jobs or incomes committed to be increased or maintained by UK funded JETP investments and UK technical assistance. Target of at least 50% women. "Just" investments. | Planned | 0 | 0 | TBC | 4000 | 15000 | TBC | TBC | 1. Same conditions as in Outcome 2 around investment environment and JETP but particularly need supportive Mpumalanga municipalities 2. Assuming that promised investments will materialise and not be cancelled and translate into jobs.
|  | Achieved |  | 0 | 3444 | 7491
|  | Of which Just |  |  | 356 | 1237
|  | Of total - Non MDB, DFI, other ICF |  |  | 0 | 198
| MDB, DFI and other ICF programming separated out |  | Source
Reports from MDBs, DFIs, ICF programmes and programme implementers
| Outcome Indicator 3.2 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| # of households estimated to have or projected to benefit from improved infrastructure, services and/or environment as a result of projects, with GEDSI disaggregation | Planned |  |  |  | N/A | 128 200 | TBC | TBC
|  | Achieved |  |  |  | N/A
Source
Report from JETP Support Programme Implementers
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
5 (3 HCS + 2 CBS)
OUTCOME 4 | Outcome Indicator 4.1 |  | Baseline (21/22) | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029) | Assumptions
Substantial amount of private finance mobilised by UK actions, including from UK business, to support the JET IP and contributes towards the overall $98bn funding requirement | Value of exports (£) in JETP sectors from UK business | Planned | 25.6m | 0 | 40 | 11m | TBC | TBC | TBC | 1. Private investor appetites remain high, policies are conducive to investment and no significant macro economic downturns in UK or SA. 2. DBT continues to resource JETP area.
|  | Achieved |  | 0 | 2.995m | 2.995m
Source
DBT reporting
| Outcome Indicator 4.2 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Value (in £) of committed investments in JETP sectors by UK business (cumulative) | Planned | 0 | 100m | 5bn | 10m | TBC | TBC | TBC
|  | Achieved |  | 0 as project not yet at financial close | £2bn and $370m | £2.26bn and $370m
Source
DBT reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
4 (2 HCS + 2 CBS)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029) | Assumptions
UK funds targeted to deliver spend in an effective and just manner | Value of projects ($) reaching financial close via AFDB, BII and PIDG and grant projects using UK funding under JETP that are transformative or catalytic and do not displace private sector. Cumulative | Planned | 0 | 200m | 500m | 270m | 720m | 1bn | 1.5bn | 1. Same issues as Outcome 2 above around investment environment and SA or dev partners swiftly develop, high quality and well-targeted project proposals to absorb the lending space created by the guarantee. 2. AFDB deploys broader team to guarantee so that it focusses on "Just" sectors, including Mpumalanga 3. Conducive investment environment and policies, especially in Mpumalanga. 4. Bilateral programme team continue to have grant funding available for project preparation. 5. Able to secure CDEL in future year ODA budgets.
|  | Achieved |  | zero as projects progressed but not reached financial close | 163m | 321m
Source
AFDB, BII and PIDG reporting; reporting from programme implementers for JETP CDEL
| Output Indicator 1.2 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Value of BII, PIDG and AFDB and grant investment projects ($)(as a subset of 1.1) funded by UK JETP which are notsolely ESG positive but sufficiently "Just" in nature. "Just" investments are those in Mpumalanga. Cumulative | Planned | 0 | 0m | 40m | 11m | 411m | 411m | 600m
|  | Achieved | 0 | Zero as not yet at financial close | 10.5m | 18.97m
Source
AFDB, BII and PIDG reporting; reporting from programme implementers for JETP CDEL
| Output Indicator 1.3 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Value of projects ($) in pipeline which are being substantively worked up as investment projects using UK grant funding under the JETP support programme. Cumulative | Planned | 0 |  |  | 410m | 600m | 600m | 600m
|  | Achieved |  |  |  | 400m
Source
Weighting - 70 |  | Report from JETP Support Programme Implementers
1.1 15, 1.2 15, 1.3 25, 1.4 25 1.5 20 | Output Indicator 1.4 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Value of projects in pipeline which are being substantively worked up as investment projects using UK grant funding under the JETP support programme and which are sufficiently "Just" in nature. Cumulative | Planned | 0 |  |  | 400m | 600m | 600m | 600m
|  | Achieved |  |  |  | 400m
Source
Report from JETP Support Programme Implementers
| Output Indicator 1.5 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Value of Development Capital Grant funding deployed for blending which aim to achieve Just outcomes. Cumulative. | Planned | 0 |  |  | £1.5m | £3.5m | TBC | TBC
|  | Achieved |  |  |  | £1.84m
Source
Report from JETP Support Programme Implementers
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
4 (2 HCS + 2 CBS)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
UK influence with all stakeholders (IPG, SA government, interested parties) ensures effective JETP implementation | Minimum %age of those participants surveyed who assess impact of coordination groups and joint resources as positive and helpful to the way they work (according to survey). See definitions for more detail | Planned | 0 | 75% | 75% | 75% | 75% | 75% | 75% | 1. Continued SA government and dev partner engagement with JETP. UK continues to chair (may need to drop first indicator when pass on chairing). 2. Continued engagement from NGOs and broader stakeholders and SA Government remains committed to JETP. 3. ODA funding remains available to support collaborations. 4. Funding remains in place for staff at post leading IPG co-ordination.
|  | Achieved |  | 54% average score. See full question breakdown for further information. | 96% average score. See full questionnaire breakdown for further information. | 98% average score. See full questionnaire breakdown for further information
Source
Survey of key participants (with participation from at least 6 of the development partners)
| Output Indicator 2.2 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Number of substantive collaborations supported by UK with private sector or philathropies or NGOs or new development partners which support the outcomes and impact above and further the aims of JETP. See definitions. Cumulative | Planned | 0 | 3 | 7
|  | Achieved |  | 6 - Spain, Canada, NL, DK, Switzerland, GEAP | 10 - Norway, Japan, CSOs, Energy Council
Source
Emails/meetings
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
25 | Number of substantive collaborations supported by UK with SA Government which support the outcomes/impact above and further the aims of JETP. Cumulative | Planned |  | 0 | 3
|  | Achieved |  | 5 (Energy Council with DMRE, UCT with DFFE on emissions, , work on energy distribution with Necom, UK Pact one stop shop secondment to DITC, creation of 5 TWGs) | 12 (Energy Council with NECOM; NT and COGTA on process for ongranting AfDB loan to munis; EV trade mission with DTIC; EV Technical Working Group with IDC; SA Medical Research Council and DFFE).
Source
Various - meeting read outs, programme reports
| Output Indicator 2.4 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Number of policy issues being substantively progressed in collaboration with the IPG and/or SA Gov to further the aims of the JETP. Cumulative | Planned |  |  |  | 3 | 4 | 5 | 5
|  | Achieved |  |  |  | 3 - Work with DEE on mini-grids participation viability study and regulations; Energy Council continued work with NTCSA and NECOM on SAWEM implementation including grid capacity; UKPACT work with NERSA on tariffs
Source
Various - meeting read outs, programme reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | FCDO (FTEs)
4 (2 HCS + 2 CBS)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029) | Assumptions
UK business investment opportunities in SA’s JET created | Number of UK businesses identified for which JETP is a material opportunity and who are likely to do something and who are then connected with a specific opportunity. Cumulative | Planned | 0 | 2 businesses identified and 0 connections made | 8 businesses identified. 2 connections made | 11 businesses identified. 4 connections made | 13 businesses identified. 5 connections made. | 15 businesses identified. 6 connections made. | 17 businesses identified. 7 connections made. | Conducive investment environment remains (as per Outcome 2) and DBT remains committed to resource JETP response
|  | Achieved |  | 3- UK fuel cell company with Energy Council and B4SA, 4-5 UK banks involved in the transmission roundtable in London in Jan 2024. | 11 - 3 UK companies linked with concession opportunity; tidal and floating solar company; e-waste company; trading company comments on wheeling framework; smart meter company biochar company; 2 consultancies connected with Energy Council; RFP shared with 1 company. | 26 companies identified, 27 opportunities connected. See Annual Review document for detail
Source
Email chains
| Output Indicator 3.2 |  | Baseline | 2024 | 2025 | 2026 | 2027 | 2028 | Target (2029)
| Number of deals which are substantively progressed (e.g. country visits, negotiations started). Cumulative | Planned | 0 | N/A | 3
Impact weighting 5% |  | Achieved |  | 1 - energy trading company supported with connection to Min of Elec, SA Parliament etc | 2 - UK company substantively progressed, including SA visit
Source
Email chains
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
4 (2 HCS + 2 CBS)

## Indicator definitions
Impact Indicator 1 | Definition
GHG (CO2te) emission reductions in relevant JETP sectors reported as achieved by SA Govt or in absence of a report SA coal closure and transport policy on track | JETP sectors refers to those set out in the JET Investment and Implementation Plan - electricity, new energy vehicles and green hydrogen as well as the focus invesmtent areas - Road to Rail and Energy Efficiency.
Impact Indicator 2 | Definition
Employment levels in Mpumalanga versus other provinces | Take Labour force survey for the whole previous calendar year and compare 1) average of all provinces excl Mpumalanga and provinces with higher average unemployment and 2) %age difference with Mpumalanga. See how %age changes over the years. This ensures any SA wide macro events are excluded (as all provinces affected by those). Main challenge is that job effect in next 4 years likely to be minimal due to employment effect delays.
Outcome Indicator 1.1 | Definition
Number of policies, regulations and standards adopted or amended due to IPG influencing/initiatives or support, including UK participation. | The policy, regulation or standard adopted must also be in force and not just announced as a deliverable. Look at lobbying effort and substantive impact when "counting" so don’t count both primary and secondary legislation as separate items unless work on them and impact very different. Example - passing of Electricity Regulation Amendment Act.
Outcome 1.2 | Definition
Transformational Change | See separate tab as this is a complex definition
Outcome Indicator 2.1 | Definition
Public climate finance mobilised into JETP areas using some UK influence (GBP) ICF KPI - see methodologies | Note that the £ from this will only be partly counted for UK ICF reporting as we can not double count $ that BII, PIDG or AFDB are themselves reporting. Example would be bringing in a new dev partner e.g. Japan, Netherlands, Denmark either into JETP generally or specific investment. DFIs count as public.
Outcome Indicator 2.2 | Definition
Private climate finance mobilised into JETP areas using some UK influence (GBP) ICF indicator | Note that the £ from this will only be partly counted for UK ICF reporting as we can not double count $ that BII, PIDG or AFDB are themselves reporting. Example - BII or PIDG investment with co-financing or private project scoped out by UK with bank investment.
Outcome Indicator 3.1 | Definition
Number of jobs or incomes committed to be increased or maintained by UK funded JETP investments and UK technical assistance. Target of at least 50% women. "Just" investments. | Investments or projects that directly link to creation of jobs or incomes can only be counted for this indicator. Expenditure that relate to skills development doesn't count as it may not lead to job creation. Example - BII investment in Hydrogen project - use their job methodology for likely jobs (and women), UK scopes out project in Mpumalanga e.g. via UKPACT support which later receives investment.
Outcome Indicator 3.2 | Definition
# of households estimated to have or projected to benefit from improved infrastructure, services and/or environment as a result of projects, with GEDSI disaggregation | Minimum number of households projected to benefit from the JETP Support Programme implemented by ASI. Benefits will be identified through the Cost Benefit Analyses of each project and include improvements such as simple basic improved water and sanitation facilities; access to regular water supply; disruption reduction in energy supply.
Outcome Indicator 4.1 | Definition
Value of exports (£) in JETP sectors from UK business | Count the export the same time as DBT count it.
Outcome Indicator 4.2 | Definition
Value (in £) of committed investments by UK business (cumulative) | A committed investment is one where signature has occurred on a legally binding agreement as opposed to an MoU. If financial close is needed then investment must reach financial close.
Output Indicator 1.1 | Definition
Value of projects with AFDB, BII and PIDG that are transformative or catalytic and do not displace private sector | Transformative or catalytic refers to those projects that needed funding from AFDB, BII or PIDG to be successful, are not duplicated elsewhere, do not displace Private sector money with public and contribute solely to specific aspects of the JETP within Investment and Implementation Plan.
Output Indicator 1.2 | Definition
Value of projects which are not just ESG but sufficiently "just" in nature with AFDB and PIDG and BII | Projects in Mpumalanga qualify as "Just" So for example funding embedded commercial and industrial solar in Gauteng is not a "Just" project but any job creating investment in Mpumalanga would count.
Output indicator 1.3 | Definition
Value of projects ($) in pipeline which are being substantively worked up as investment projects using UK grant funding under the JETP support programme. Cumulative | Projects refers to packages of interventions, not individual micro projects as defined by FCDO and ASI in the context of the JETP Support Programme. Substantively means project beyond pre-feasibility stage/feasibility stage
Output indicator 1.4 | Definition
Value of projects in pipeline which are being substantively worked up as investment projects using UK grant funding under the JETP support programme and which are sufficiently "Just" in nature. Cumulative | Projects refers to packages of interventions, not individual micro projects as defined by FCDO and ASI in the context of the JETP Support Programme. Substantively means project beyond pre-feasibility stage/feasibility stage
Output indicator 1.5 | Definition
Output Indicator 2.1 | Definition
Minimum number of participants assess impact of UK's IPG co-ordination and joint resources | Annual survey for participants of the technical working groups (ie members of the IPG, other donors such as Denmark, Canada, Government of South Africa, AfDB, WB) and wider JETP community to assess effectiveness of the UK's IPG co-ordination, donor co-ordination and joint resources. Questions aim to identify whether the co-ordination is helpful to the way they work; whether it impacts their actions or funding decisions; whether information and data accessibility has improved; whether it creates or strengthens stakeholder relationships and measuring the influence on Gov of South Africa's approach. Scale of Not applicaple; 1 - Strongly disagree; 2 - disagree; 3 - agree; 4 - strongly agree. Need at least 6 different dev partners to respond.
Output Indicator 2.2 | Definition
Number of substantive collaborations with private sector or philathropies or NGOs or new development partners which support the aims of the JETP | Substantive collaborations refers to more than 3 interactions with a particular party - pushing a behavioural and policy change or investments i.e. furthering the outcomes in the log frame. Long term information sharing and commitment to the JETP should be evidenced. This could be working on a blended finance initiative for example - beyond initial talking of the idea and the philanthropy committing substantial time to the design elements.
Output Indicator 2.3 | Definition
Number of substantive collaborations supported by UK with SA Government which support the outcomes/impact above and further the aims of JETP. Cumulative | Substantive collaborations with refers to more than 3 material interactions (and beyond planning meetings and creating an MoU) with an entity that is not just with the joint IPG and SA secretariat. Engagement with all relevant Government ministries and downstream bodies such as DMRE,DSI, NERSA DBSA, DIT, Infra SA, DBSA, IDC, SA Treasury and ensuring they're working towards JETP aims. Example is hydrogen partnership once it morphs into actual sharing of technology and more interaction between 2 universities
Output Indicator 2.4 | Definition
Number of policy issues being substantively progressed in collaboration with the IPG and/or SA Gov to further the aims of the JETP. Cumulative | Policy issues refers to any issue or policy change which will further the outcomes of the log frame and enable delivery of JETP goals. Evidence of substantive progression may be a public announcement by the Government of South Africa; a written commitment from the Government of South Africa; draft regulations published; court applications made.
Output Indicator 3.1 | Definition
Number of UK businesses identified for which JETP is a material opportunity and who are likely to do something and who are then connected with a specific opportunity OR No. of barriers to market identified and overcome. Cumulative | The larger number should include more than listing the businesses but also identifying and scoping out some of the opportunity with an aim to making introductions or connections. The smaller number is about actually making those connections e.g. finding tender opportunities, JV partners etc.
Output Indicator 3.2
Number of deals which are substantively progressed (e.g. country visits, negotiations started) | Substantively progressed refers to negotiations, engaging lawyers or advisers or committing money in form of visits, feasibility studies, banks for finance etc

## Impact indicator one calcs
| part1 | part2 | part1a | part2a
2020 | 500 |  | 500
2021 |  |  | 479.6
2022 |  |  | 459.2
2023 |  |  | 438.8
2024 |  |  | 418.4
2025 | 398 | 398 | 398 | 398
2026 |  |  |  | 388.4
2027 |  |  |  | 378.8
2028 |  |  |  | 369.2
2029 |  |  |  | 359.6
2030 |  | 350 |  | 350
slope | -20.4 | -9.6
intercept | 41708 | 19838
20.4

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | Output 3.1 | Original indicator provided two options: Number of UK businesses identified for which JETP is a material opportunity and who are likely to do something and who are then connected with a specific opportunity OR No. of barriers to market identified and overcome. Not cumulative - new in that year. It was agreed to focus on the first option: No. of businesses identified for which JETP is a material opportunity. The 2024 target was also reduced from 8 businesses identified and 2 connections made to 2 businesses identified and 0 connections made | Katie Dewing | 4519000%
2 | Output Indicator 2.2 | 2024 Target revised from 5 to 3 | Katie Dewing | 4519000%
3 | Output Indicator 2.3 | 2024 Target revised from 2 to 0 | Katie Dewing | 4519000%
4 | Outcome Indicator 3.1 | 2024 target set at 0 [previously unset] | Katie Dewing | 4519000%
5 | Impact Indicator 2 | 2024 and 2025 target set at 0 [previously unset] to account for slow rate of change | Katie Dewing | 4519000%
6 | Outcome 1 | Transformational change indicator and targets set - see transformational change tab | Katie Dewing | 4520800%
7 | Outcome 4 | targets pending updates from DIT colleagues | Katie Dewing | 4520800%
8 | Impact Indicator 1 | Targets added (previously not inputted) based on data from senior climate change and energy advisor in UK who has been assessing GHG emission trajectories | Katie Dewing | 4520800%
9 | Impact indicator 2 | Data for national unemployment % added to the baseline, and the Mpumalanga figure updated in line with latest data from Stats SA, which was adjusted post Covid | Katie Dewing | 4536200%
10 | Output indicator 2.1 | Indicator has been updated from: "Minimum %age of those participants surveyed who assess impact of coordination groups and joint resources as positive and changing the way they work (according to survey)" to "Minimum %age of those participants surveyed who assess impact of coordination groups and joint resources as positive and helpful to the way they work (according to survey)". Definition also amended in line with survey changes. Note: This definition was used in the survey of the 2024/2025 annual review but the change was not added to the change frame due to human error (Amy Freer 08/09/2025). 2026 target reduced to 75% to reflect fact that team's focus will be more on programme now that IPG structures are established. Target added for 2027-2029. | Katie Dewing | 20/08/2024
11 | Impact Indicator 1 | Targets added for 2028 and 2029 - target has been lowered as South Africa won't meet the high end of its NDC 2030 ambition. Amended source to 'updated decommissioning schedules' as the schedules in the investment plan have been extended. Amended to add in other JETP sectors in definition. | Amy Freer | 4587800%
12 | Impact Indicator 2 | Targets added for 2026 - 2029. Added source as Quarterly Labour Survey. | Amy Freer | 4587800%
13 | Outcome 1 | Amended source as there are now more than 4 JETP 'sectors' as per implementation plan. Updated assumptions. FCDO FTE updated.
14 | Outcome Indicator 1.1 | Target increased for 2026 and added for 2027 - 2029. Definition updated. | Amy Freer | 4587800%
15 | Outcome Indicator 1.2 | Targets amended for 2026-2027 and added for 2028-2029. Amended definitions and removed evidence column - evidence is saved each year as part of the AR. | Amy Freer | 4587800%
16 | Outcome Indicator 1.3 Definitions and targets | Outcome definitions have been updated to align with the ICF criteria for KPI 15 reporting - indicators are now divided under the ICF criteria rather than stakeholder groups. Subject to refinement following consultation with ICF and MEL advisors. | Amy Freer | 4587800%
17 | Outcome 2 | Removed 2 assumptions as they have not materialised, hence the pivot of the JETP programme to project preparation. FCDO FTE updated. | Amy Freer | 4587800%
18 | Outcome indicator 2.1 | Targets for 2025, 2026 and 2027 increased to make more stretching. Original targets were exceeded in 2024. Changes were: 2026: 300m (original target) 2.7bn (new target set in August 2025); 2027: 300m (original target) 2.7bn. Targets added for 2028 and 2029 - 2.7bn. Changes approved by PM and SRO. Target plateaus given there is still a lot of unspent pledges, and progress on emissions in SA is mixed. | Amy Freer | 4587800%
19 | Outcome indicator 2.2 | Targets for 2026-2027 increased and 2028-2029 added. | Amy Freer | 4587800%
20 | Outcome 3 | FCDO FTE updated | Amy Freer | 4587800%
21 | Outcome indicator 3.1 | Job creation targets added for 2026/2027 based on information from implementing partners. | Amy Freer | 4587800%
22 | Outcome indicator 3.1 definition | Added 'or maintained' as UK funding being used to safeguard jobs as well as create additional jobs. | Amy Freer | 4587800%
23 | Outcome indicator 3.2 | Added indicator to measure outcomes from improved service delivery through the JETP programme. Target for 2027 added. Definition added | Amy Freer | 4587800%
24 | Outcome 4 | FCDO FTE updated.
25 | Outcome indicator 4.1 | Added source. Added target for 2026. | Amy Freer | 4587800%
26 | Outcome indicator 4.2 | Indicator has been updated to make it cumulative. Targets added for 2026. Added source. | Amy Freer | 4587800%
27 | Output 1 | Weighting amended to 65% (and split per indicators) to reflect that the JETP bilateral programme is now more advanced and more of team's focus is on delivery of the programme, while still maintaining the influencing objectives in output 2. Weighting is more towards output indicator 1.3 and 1.4 as these are within control of the programme team. Added to assumptions. FCDO FTE updated. | Amy Freer | 4587800%
28 | Output indicator 1.1 | Target for 2026 reduced to $700m. Previous target was based on planned loans to Eskom, however NT moratorium on Eskom and subsequent reluctance to borrow meant these didn't go ahead. Added source. | Amy Freer | 4587800%
29 | Output indicator 1.2 | Target reduced for 2026 and added for 2027-2029. 2026 Just figures unlikely to be as high as initial target given much JETP grant money is spent. Expect an increase in 2027 on ASI project. Added source. Removed 'or vehicle manufacturing or deprived areas/at risk communities.' as these are not counted by the JET PMU as Just investments. Amended indicator definition. | Amy Freer | 4587800%
30 | Output indicator 1.3 | Added indicator to measure the volume of projects being substantively worked up as investment projects using UK grant funding under the JETP support programme. Added source. | Amy Freer | 4587800%
31 | Output indicator 1.4 | Added indicator to measure the subset of projects under output indicator 1.3 which are Just. Added source. | Amy Freer | 4587800%
32 | Output indicator 1.5 | Added indicator to measure the value of Development Capital Grant funding provided for blending to achieve Just outcomes. | Amy Freer | 4587800%
33 | Output 2 | Weighting amended to 30% (see explanation in output 1). Assumption added. FCDO FTE updated. | Amy Freer | 4587800%
34 | Output indicators 2.2, 2.3, 2.4 | Output indicators 2.2 and 2.3 will no longer be measured as the JETP hs moved from substantive new collaborations to growing the existing collaborations and implementing policies and programmes. No longer about the number of new policies we work on or new relationships, but focus on progressing the substantive issues with those we have collaborations with. Hence output indicator 2.4 added to measure issues being substantively progressed. | Amy Freer | 4587800%
35 | Output 3 | FCDO FTE updated. | Amy Freer | 4587800%
36 | Output indicator 3.1 | Changed to cumulative. Targets increased for 2026-2027 and added for 2028-2029. | Amy Freer | 4587800%
37 | Output indicator 3.2 | Output indicator 3.2 will no longer be reported due to confidentiality of DBT data. | Amy Freer | 4587800%
| Impact Indicator 1 | Added to source - Achieved data will be sourced from South Africa's submission to the UNFCCC once available. | Amy Freer
| Output Indicator 1.1 and 1.2 | Added to source - reporting from programme implementers for JETP CDEL | Amy Freer
| Outcome Indicator 2.1, 2.2 and 3.1 | Added to source to include programme implementer reporting | Amy Freer
| Outcome Indicator 2.1 and 2.2 | Amended subset of achieved data to include other ICF programmes. This is to ensure no double counting for ICF reporting

## Transformational Change
ICF Score | Descriptor
1 | Substantial evidence that suggests transformational change is unlikely or will not occur
2 | Partial evidence that suggests transformational change is unlikely
3 | Not enough evidence yet to assess, or the balance of evidence is inconclusive
4 | Partial evidence that suggests transformational change is likely
5 | Substantial evidence that suggests transformational change is likely or already occurring
Label | ICF Criteria | Weighting | Indicators
A | Political will and local ownership | 35% | Government speaks positively about JET and indicates that not wedded to coal. Provinces/municipalities engage with the IPG. Projects underway in partnership with provinces/municipalities. Provinces/municipalities are advanced in using funds provided by the IPG for effective projects. Private sector speak positively about JETP. SA NGOs and community groups positively promote JET and the role of the JETP/IPG.
B | Capacity and capability | 35% | Capacity across government increased such that JETP projects can be successfully designed and implemented. Government using significant proportion of IPG loan funds for the JET in line original investment plan Government presents good capacity to build up further projects and access more financing. Provinces/municipalities have capacity to develop pipeline for future funding. CSOs have increased capacity to engage with government and society on JET. Private sector work in collaboration with the IPG and government to deliver significant change. Joint projects with SA NGOs achieve positive change.
C | Leverage / create incentives for others to act | 20% | SA Govt takes progressive steps towards delivery of South Africa’s Wholesale Energy Market.
D | Sustainability | 10% | SA Govt continues to prioritise just energy transition policies and projects.
Note: Definitions have been updated in line with the ICF15 reporting guidance to collate evidence across relevant ICF criteria and following recommendations from the 2025 Annual Review. We had noticed difficulties with the scales we previously set out, for example there was evidence of level 2 without being evidence of level 1. Re-categorising our indicators under the ICF criteria brings our measurement in line with the overall ICF scoring methodology. The programme team will review the proposed changes with the relevant ICF and MEL advisors and may look to refine further as a result of these consultations.

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.