## Annual Review

Title: ACTION (Accelerating Climate Transition and Innovation) Rwanda
Programme Value £ (full life): £15m		Review date: Sept 2025
Programme Code: 301524	AMP start date: 01/04/2024	AMP end date: 01/04/2029

Summary of Programme Performance

Year	2024/25
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301524 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301524 Documents

A. SUMMARY AND OVERVIEW

Description of programme

ACTION Rwanda programme delivers on a key international development priority for the UK to tackle climate change and protect nature, as outlined in the refreshed 2022 Strategy. It responds directly to a vital pillar of FCDO’s 2022-25 Strategic Vision to build strategic partnerships with trusted partners to tackle climate change and delivers against a core part of the cross-party White Paper on UK’s International Development priorities. Following the 2024 UK elections, it is clear that global action on climate change, shared prosperity and growth, and investment in mutual partnership will be crucial for the newly elected UK government – ACTION responds to all those priorities. In Rwanda, taking action on climate change complements our existing priorities to provide social protection to the most vulnerable and alleviate humanitarian risks; strengthen governance of key Government of Rwanda institutions; and improve inclusion. Programme design has closely followed the recently refreshed BHC Kigali Gender Equality and Social Inclusion assessment which has identified groups with particular vulnerabilities.

ACTION builds on the UK’s previous climate programming in Rwanda and draws on the UK’s comparative advantages: a trusted relationship with government, ability to programme directly through financial aid, and adaptation/resilience expertise delivered through technical assistance. We will therefore focus on building on previous successes and further bolstering the capacity of GoR to meet own climate ambitions through this programme.

ACTION Rwanda is part of a coherent UK approach to improving access to climate finance in Rwanda. For instance, this programme’s support to Intego Facility will work with the UK’s support for Ireme Invest (funded by a CMP – Access to Climate Finance) to help establish a common platform for financing Rwanda’s climate priorities. This model enables coordinated funding of long-term investments aligned behind national climate plans - moving away from an inefficient project-by-project approach.

ACTION Rwanda focuses on targeted interventions that build the resilience of the most vulnerable to climate shocks, deliver UK’s climate agenda and COP commitments at scale, and leverage additional finance.
It will use a multi-component approach to galvanise public action on climate change. This will include:
1. Component 1 - Direct Financial Aid for Adaptation. This component provides direct financial aid for adaptation, aligned to key priorities in the NDC in the climate resilience space. This includes targeting adaptation to the most vulnerable and providing support to the RGF through the Intego (NDC) Facility. The Facility works through proposal rounds to provide public sector financing for key districts and public sector bodies to deliver on the adaptation priorities outlined within Rwanda’s NDCs.
2. Component 2. Technical Assistance (TA). This aims to strengthen Rwanda’s climate coordination, national planning and delivery towards NDCs. This builds on our technical assistance to the GoR in recent years, which has included building the core functions of Rwanda Green Fund (RGF) through bilateral governance programming and CMPs.
Component 3. Monitoring, Evidence, Research and Learning (MERL). This aims to build evidence on what works and use Rwanda to showcase progress with transferable lessons.

During the first year of programme implementation there have been two distinct developments with regard to FCDO supported programmes in Rwanda and globally which have impacted on this programme, and will continue to impact in remaining years. Firstly, as a result of Rwanda’s action in DRC the UK has put in place a series of measures including the pausing of financial aid (unless specifically exempted). This has meant that apart from an initial tranche of financial aid in February 2025, further payments have been paused. Secondly, as a result of the UK’s move to 0.3% of GDP for ODA FCDO in Rwanda - as in all countries where the UK provides ODA - will be allocated fewer resources, moving towards £5m annually in 2028/9. This will mean that whilst climate is likely to remain a priority for FCDO supported work in Rwanda, funds will be reduced compared to the original business case and will be focused more on technical assistance (component 2) than financial aid (component1). Recommendations for managing the implications of both these changes are included in this annual review.

Summary supporting narrative for the overall score in this review

This Annual Review (2024/25) scores A. The two programme outputs score A (output 1), A (output 2). Under output 1 this reflects the good collaboration between Rwanda Green Fund and FCDO in signing an MoU and making solid progress towards implementation of the Intego project pipeline. It further recognises the constraints placed on the delivery of the financial aid component resulting from the UK’s measures in response to Rwanda’s action in eastern DRC. Output 2’s score reflects the impressive agility that the programme team have shown in re-directing ACTION’s focus towards a new technical assistance partnership which has been quickly mobilised and aligned to evolving GoR and UK priorities.

The programme outputs in the logframe are structured around the design, due diligence and procurement phases of the two key delivery components: output 1 relates to the Rwanda Green Fund Intego project delivered through UK financial aid; and output 2 relates to the new Technical Assistance partnership with Government of Rwanda, delivered by World Resources Institute (WRI). The third business case component ‘Monitoring, Evidence, Research and Learning (MERL)’ is not currently active and therefore not reflected in logframe outputs or reported against in this review.

Details of the output progress is in Section C.

Major lessons and recommendations for the year ahead

Lessons and recommendations are shown throughout the following sections. Some key overarching recommendations for the programme include:

FCDO, Government of Rwanda and WRI to review progress and performance of the grant against government and project objectives, and agree a way forward including whether to extend the accountable grant and costed workplan into future years [December 2025]
Develop a comprehensive logframe reflecting the shift in the programme’s outcomes, outputs and indicators away from the financial aid modality (component 3) and towards direct technical assistance targeting unlocking private finance (component 1). Incorporate rigorous milestones relating to private investment mobilised. This will involve a revision of the theory of change, including to recognise the role of mobilising private sector funding to reach targets for strengthened resilience, as well as a refresh of the VFM and equity cases for the programme. With increased reliance on technical support, a clear influencing and engagement plan will be required. [February 2026]
- Host a UK Climate and Nature Learning Forum event in Kigali showcasing the continued priority placed on climate by FCDO, and the breadth of the UK’s climate and nature work in Rwanda – delivered bilaterally via ACTION as well as through central programming such as WISER (Weather and Climate Information Services) and Transforming Energy Access. [January 2026]
- Explore the possibility of supporting additional TA requests from RGF and other agencies such as REMA under component 2, including relating to Management Information Systems (MIS) [December 2025]
- Under component 1, develop a future strategy for direct support to government in the context of reduced finance, including learning lessons from the initial Intego project which was financed. [December 2025]
- Continue to involve political and governance colleagues across the BHCK in discussions, particularly around decentralised climate action in Rwanda, and its impact on resilience for the most vulnerable. [ongoing]

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The overarching impact of the programme is: Rwandans are more resilient to climate change.

There are three programme outcomes:

- Strengthened institutional capacity and more effective adaptation programming within Government
- Improved evidence and learning leading to more effective, adaptation and resilience focused, FCDO programming in Rwanda
- Strengthened resilience of poor and vulnerable households to withstand current and future weather and climate related shocks and stresses

The assumptions underpinning this Theory of Change include:
Political will to meet Rwanda’s climate commitments remains strong, particularly in light of additional challenges around poverty reduction, youth employment and economic growth which could be seen as competitive to climate goals.
Rwanda’s governance and institutions responsible for carrying out their environmental obligations remain strong
- Sound fiscal management and budgetary distribution means that an appropriate level of domestic funding is maintained on climate and environment commitments
- Policy decisions and funding levels of other Development Partners are maintained to supplement Rwanda’s journey towards achievement of its NDCs
- Rwanda’s NDCs are revised in line with future UNFCCC milestones (for example the 2025 revision) and goals/indicators are aligned to Rwanda’s growth and capacity
- Rwanda maintains a steady green growth towards becoming a Net Zero economy by 2050
- Rwanda continues to strengthen its Monitoring, Results and Verification (MRV) systems

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As none of the programme components have progressed to implementation, this Annual Review will not assess progress against the Theory of Change (ToC) outcome or impact statements. These elements will be revisited during the upcoming logframe refresh in the next reporting period.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As above, it is too early in the programme lifecycle to evaluate progress against expected outcomes and impact. The next Annual Review – informed by the revised logframe – will evaluate progress against anticipated milestones.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

At time of writing this Annual Review, the programme is in its first year and not yet into implementation. However, during the reporting period BHC Kigali have made impressive and rapid pivots to keep the programme relevant and future facing.

Initially this was a direct response to the UK’s response to events in eastern DRC, which resulted in the pausing of financial aid (component 1). However, drawing on the ethos ‘In the midst of every crisis lies great opportunity’, BHC Kigali’s decision to quickly pivot to signing a new agreement with WRI focused on unlocking private investment aligns with both GoR objectives and FCDO’s shift away from core service delivery and towards a model based on technical assistance and partnerships. It is also a pragmatic shift reflecting the reduction in the UK’s ODA to 0.3%. The programme is therefore in a good position to continue into the next reporting period.

## C: DETAILED OUTPUT SCORING

Output Title	Rwanda Green Fund Intego project MOU signed, due diligence and procurement complete
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 5-year MoU signed between FCDO and Government of Rwanda for Intego facility	Scope of MoU activities agreed / 5-year MoU between FCDO, MINECOFIN and Rwanda Green Fund signed	Agreed - October 2024 / Signed - December 2024
1.2 3-year Intego project allocated to UK, due diligence done and work plan finalised	Due diligence process conducted by Rwanda Green Fund on first cohort of Intego projects / Intego project allocated to UK / Project work plan finalised by IP	Due diligence conducted and summary report presented to DPs - February 2025 / UK funds disbursed - March 2025 / Achieved - August 2025

Briefly describe the output’s activities and provide supporting narrative for the score.

This output covers the signing of a 5-year Memorandum of Understanding between FCDO, MINECOFIN, and the Rwanda Green Fund, and the due diligence on a delivery partner to implement a UK-supported Intego project. There are two indicators under this output. Both have met their targets. This output scores an A.

Over the reporting period, good progress has been made in signing an MoU with Government of Rwanda to underpin the UK’s financial aid support. Effective collaboration has been observed between RGF and BHC Kigali (as well as other development partners) in progressing through the due diligence and procurement phases of the first Intego pipeline of projects. This is despite the complex challenges presented by the ongoing conflict and eastern DRC and UK measures.

1.1 5-year MoU signed between FCDO and Government of Rwanda for Intego facility
Following a series of meetings, in December 2024 a Memorandum of Understanding was signed between the UK Government’s Foreign Commonwealth and Development Office and the Government of Rwanda (jointly the Ministry of Finance and Economic Planning and Rwanda Green Fund) for non-budget support financial and technical cooperation. As set out in the business case, the agreement covers financial aid to the Intego (public sector) facility for both technical assistance (component 1) and direct delivery of projects.
[note] Rwanda’s Green Fund’s Intego (Public sector) facility finances projects submitted by non-commercial, public institutions at both central and local levels for the implementation of projects that align to the country’s Nationally Determined Contributions (NDCs).

The UK’s funds are deliberately not earmarked for any specific sector, but determined by government need – across a range sectors critical for adapting to the worst impacts of climate change sectors, including sustainable infrastructure, agriculture and transport and other.

1.2. 3-year Intego project allocated to UK, due diligence done and work plan finalised
Rwanda Green Fund have worked effectively and collaboratively with BHC Kigali and other development partners throughout the reporting period. This has included regular written updates and board meetings to ensure a common understanding of progress and ample opportunity to raise concerns.

Following the first Intego call for proposals in 2023, the first cohort of 12 Intego projects were approved by the RGF Board of Directors in June 2024. From this first cohort, the UK were allocated one project, well aligned to the Foreign Secretary’s focus on nature and biodiversity: Empowering Nyamasheke's Vulnerable Communities, which aims to enhance the adaptive capacity of climate vulnerable communities through sustainable land management practices like agroforestry, afforestation and terracing.

A successful Intego project kick-off meeting was held by RGF 8th on January 2025, attended by representatives of RGF and all development partners (KfW, LuxDev and FCDO) were present. KfW-funded consultancy firm Facility Management Consultant (FMC) also attended. FMC are providing technical assistance to the Intego facility, across all aspects ranging from procurement, legal, financial, and environmental.

In March 2025, FMC presented their due diligence findings on all 10 Intego projects to RGF and development partners. Major findings included: project documentation with substantial gaps; district implementing partners requiring additional capacity to successfully implement projects, albeit with some recruitment plans in place to address gaps; the landscape restoration projects (6 out of the total of 10) were found to a follow a business-as-usual approach primarily involved mono-species plantations i.e. mainly eucalyptus for the forest components and bamboo along riverbanks. An effective mitigation plan was agreed.

FMC is currently working to capacitate implementing partners of all Intego projects - including strengthening project technical studies, project design and monitoring & evaluation tools - to ensure procurement can commence from September 2025.

UK financial aid measures relating to eastern DRC conflict
In February 2025, the British High Commission Development Director wrote to Rwanda’s Minister of Finance and Economic Planning setting out six measures the UK was taking in response to the situation in Eastern DRC. This included a measure to pause direct financial aid to the Government of Rwanda (excluding support to the poorest and most vulnerable), which incorporates the UK’s financial aid to the Intego facility. The letter further set out the conditions that would need to be met in order for financial aid to be resumed.

Pausing any future disbursements to the Intego facility resulted in the UK’s planned funding for a second Intego project, Nyabahanga Sub-Catchment Rehabilitation (disbursement scheduled for April 2025), being paused. This project was subsequently reallocated to KfW. The financial aid pause did not however affect the use of funds already disbursed for the UK-funded Empowering Nyamasheke’s Valuable Communities project. BHC Kigali continued to play a constructive and active role as a development partner in the facility’s governance for the remainder of the reporting period, attending board meetings and feeding into key documents such as the Intego due diligence report.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Not applicable as this is the first annual review for the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As above, not applicable.

Recommendations:

Develop a future strategy for direct support to government in the context of reduced finance.

Output Title	World Resources Institute (WRI) Accountable Grant climate finance grant signed, mobilised and inception phase underway
Output number:		2	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Sector consultation	Consultation period	Discussions held with GoR and wider sector - June 2025
2.2 Costed workplan agreed and accountable grant signed	Due diligence / Kick-off meeting / Work-plan finalised / Agreement signed	Conducted on WRI - July 2025 / Undertaken between FCDO, WRI & GoR - July 2025 / Inception phase work plan approved - August 2025 / FCDO-WRI accountable grant signing ceremony - August 2025

Briefly describe the output’s activities and provide supporting narrative for the score.
This output covers the procurement and mobilisation of an accountable grant to the World Resources Institute (WRI) to unlock climate finance. It includes sector consultations, due diligence, and agreement of a costed workplan, culminating in the signing of the grant and initiation of the inception phase in collaboration with the Government of Rwanda. There are two indicators under this output. Both have met their targets. This output scores an A.

This reflects the very good progress and agility demonstrated over the reporting period in adapting the programme to respond to the ongoing situation in eastern DRC and UK measures; but also in seizing the opportunity to quickly re-align to broader shifts in the direction of GoR priorities and UK ODA away from direct delivery and towards unlocking private investment.

2.1. Sector consultation
Following the decision to pause financial aid, from April to June 2025 BHC Kigali undertook a series of consultation discussions with key government agencies (including MINECOFIN, Ministry of Environment and Rwanda Green Fund), development partners (including GIZ and AfD), and civil society, to determine an appropriate alternative delivery model and focus for the UK to deliver Government of Rwanda climate and nature objectives. The Government provided clear direction on the need to accelerate the process of unlocking private climate finance through innovative new approaches, driven by diminishing grant funding and the need to move towards a long term financial self-sufficiency. This is clearly articulated in the Climate and Nature Finance Strategy published in October 2024.

During this consultation period, in March 2025, BHC Kigali were approached by World Resources Institute (WRI) following the sudden closure of the formerly USAID-funded RAMP (Resilience and Adaptation Mainstreaming Program) programme, which operated in Rwanda, Kenya, Ethiopia and Uganda. RAMP’s model is a particularly effective one because of its focus on building long term, national-level capacity in climate adaptation planning. It adopts an innovative ‘triangular’ model, facilitating collaboration and learning exchange between UK universities like SOAS, East African universities like University of Rwanda, and finance ministries.

Following a series of further discussions with MINECOFIN, RGF, Ministry of Environment and WRI, it was agreed to explore taking forward the most innovative aspects of the RAMP model – notably its focus on long term institution strengthening – alongside the government’s stated aim of unlocking investment in the short term.

2.2 Costed workplan agreed and accountable grant signed
WRI submitted a concept note to BHC Kigali consolidating these short and long term capacity needs, focused on 3 initial workstreams: 1. Project structuring and pipeline development – translating GoR’s sector investment plans into bankable projects; 2. Rwanda Green Fund Investment Arm operationalisation - embedding technical assistance within RGF to capacitate the new structure and lead consultations with DFIs and private investors; 3. Investor interface – preparing investor-facing communication and pitch materials, and hosting events such as a Rwanda Climate Investment Roundtable targeting investors.

WRI were further deemed a suitable delivery partner owing to their extensive and relevant experience in the climate finance sector, and established capacity and networks within Government of Rwanda, enabling them to quickly mobilise. A local due diligence assessment was conducted by BHC Kigali on WRI in July 2025.

The concept note was approved by the BHC Development Director, and a signing ceremony for the new FCDO-WRI accountable grant held at BHC Kigali on 20th August. The accountable grant agreement - which runs until March 2026 with a view to extending into future years subject to performance and budget - will support key agencies such as MINECOFIN and RGF through embedded TA and a structured programme of support from WRI’s in-house advisors. It will retain the flexibility to respond to evolving government needs over the long term. The overarching aim will be to unlock private investment to finance the government’s climate and nature goals, including its ambitious NDCs, and pioneer innovative approaches that other countries can learn from – as already seen through Rwanda’s leadership role in the Taskforce on Access to Climate Finance.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is a new programme output, as such there were no changes to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Not applicable as this is the first annual review for the programme.

Recommendations:

- Work with WRI to set out specific milestones and indicators to inform a revised logframe and theory of change.
- Develop plans for an extension with Government of Rwanda and WRI, based on performance this year.

## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost driver under ACTION during the reporting period has been financial aid disbursement to the Rwanda Green Fund Intego facility of £2.7m. During the next reporting period cost drivers are expected to change as the UK pivots away from financial aid as a modality for largescale projects, and as the WRI grant becomes a more prominent component within the programme.

VfM performance compared to the original VfM proposition in the business case.

The VfM proposition of the business case assumes that, as above, the main cost driver behind ACTION programme funds will be financial aid (which holds for this reporting period).

Economy
The Rwanda Green Fund (RGF) currently oversees a large and diverse climate finance portfolio and has the capacity and experience to deliver effectively. It has a track record of value for money delivery and has consistently demonstrated cost-effective implementation. Additional funding reinforces earlier UK contributions (originally made to FONERWA, RGF’s predecessor), protecting those investments. Additional funds disbursed during this reporting period therefore allow RGF to strategically expand its impact and maximise the benefits of the climate finance it receives.

Efficiency
Intego provides direct funding to public sector, national and local institutions (and PPPs where appropriate), building their long-term knowledge and capacity to deliver against key NDC priorities. This would not be possible by delivering these projects through a third-party contractor. The Intego model – centrally managing a pipeline of projects funded by different development partners who are well linked up – further enables efficiencies by facilitating synergies and lesson learning across projects.

Equity
Investment in the Intego facility directly supports the poorest and most climate vulnerable. The UK-funded Intego project, which aims to build community climate resilience of rural agricultural community through sustainable land management practices such as soil and water conservation, afforestation and reforestation. This will particularly benefit women who are particularly affected by climate change in Rwanda because the majority of smallholder farmers are female, the majority of women rely on farming as their primary source of income, and women are primarily responsible for water availability and food security at the household level).

We have further ensured that the MoU with the GoR for support to Intego has specific GESI indicators, and require RGF to improve its approach to diversity, inclusion and safeguarding.

Effectiveness
Given that implementation has not yet started, it is too early to comment on the effectiveness of the programme in terms of delivery and development impact and outcomes. However, based on the performance so far during the due diligence and procurement phases there is good evidence that both financial aid and technical assistance components will continue to be effective towards achieving its intended results into implementation.

Assessment of whether the programme continues to represent value for money.
Over the reporting period, strong VfM has been demonstrated. Investment in the Intego facility enables scale-up, replication, and sustainability of results; and enhances national and institutional ownership and multiplier effects.

E: RISK [½ to 1 page]

Overall risk rating: Major

Overview of risk management

The Business Case outlines the programme’s anticipated context, reputational, fiduciary, delivery, operational, people and safeguarding risks, also captured in the programme risk register on AMP. This is updated on a quarterly basis following review of the ACTION risk register. ACTION’s risk in the Business Case was assessed overall as “Moderate” and judged to be within the risk appetite for the broader FCDO Rwanda programme portfolio risk appetite statement.

This moderate risk level is consistent with the recent fiduciary risk assessment of Rwanda Green fund (Jan 2023) which provided an overall rating of moderate due to the fact that GoR’s systems continue to strengthen. This includes: recent improvements in the public financial management (PFM) system; an enhanced and cohesive integrated financial management information system (IFMIS), with real-time linkages with other government databases, and capacity and experience in managing climate finance from multiple sources. The level of risk was judged acceptable given the clear and robust risk mitigation strategies included in the programme risk register set up on AMP (FCDO Aid Management Platform).

For this AR it is assessed that the risk rating should change from “Moderate” to “Major” due to the programme continuing to be affected by the conflict in eastern DRC (see section C).

Update on Partnership Principles

The UK’s financial aid remains subject to consideration of the Partnership Principles that underpin the provision of UK aid. As set out in the MoU signed between FCDO and the Government of Rwanda in December 2024, this includes ‘respecting human rights and other international obligations’. As detailed in section C, the UK’s financial measures introduced in March 2025 relating to Rwanda’s actions in eastern DRC remain in place at the time of writing.

The programme’s pivot away from funding financial aid for large scale projects and towards a new technical assistance grant with WRI mitigates this by reducing the programme’s dependence on the Partnership Principles and decisions relating to financial aid.

Annual Statement of Progress

Current level of fiduciary risk and direction of travel since last ASP	A Fiduciary Risk Assessment (FRA) was conducted in February 2023. There are plans for a light touch FRA/ASP in December 2025 (subject to BHCK ODA management approval). / The FRA and ASP are the main way in which BHCK monitors the Rwandan government’s commitment to improving public financial management and financial accountability and fighting corruption. The FRA made the following conclusion: / “The overall fiduciary risk to the UK Foreign, Commonwealth and Development Office (FCDO) financial aid through the Rwanda Green Fund is ‘moderate’ with positive trajectory’ when compared to the previous National FRA of 2022. The corruption risks associated with the wider Government of Rwanda (GoR) systems are also ‘moderate’ and that there is an overall ‘positive trajectory’ when compared to the previous National FRA”. / The reason for overall “Moderate” risk rating given to FCDO’s financial aid to Rwanda Green Fund is due the fact that GoR systems continue to undergo strengthening, with recent improvements in public financial management (PFM) system; an enhanced and cohesive integrated financial management information system (IFMIS), with real-time linkages with other government databases, and capacity and experience in managing climate finance from multiple sources.
Specific assessment of corruption risk and direction of travel since last ASP	The overall risk of corruption is “Moderate” and there is an overall ‘positive trajectory’ when compared to the previous National FRA of 2022. Commitment to improve PFM remains very high in Rwanda and strong progress is being made continually.
Is a full FRA update required?	The most recent FRA was concluded in February 2023 which indicated moderate, with ‘positive trajectory’ from 2022. We judge that the fiduciary risk is improving and doesn’t warrant a full FRA update at this time but as above there are plans to do a light touch FRA/ASP by December 2025.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Delivery performance

The programme is delivered through two main components:

- Component 1 (Rwanda Green Fund): Financial aid to Government of Rwanda for climate adaptation programming through Rwanda Green Fund public window (Intego Facilty)
- Component 2 (World Resources Institute (WRI): Technical Assistance to Government of Rwanda through World Resources Institute (WRI)

Component 1 (Rwanda Green Fund (RGF): over the reporting period the activities under this component have focused on procurement of the TA service provider FMC and completion of inception phase. A competitive procurement process led by RGF was successful, resulting into selection of German firm FMC, as the service provider of the TA. The firm has successfully completed inception phase despite some delays. The inception deliverables have been approved by RGF and Development Partners Forum.

Component 2 (WRI): activities over the reporting year have focused on procurement and mobilisation. WRI have been procured through an accountable grant arrangement with FCDO. WRI have provided concept note and costed workplan to FCDO, with the scope of activities to be delivered agreed upon. Following the concept note and workplan approval and accountable grant signing, WRI have now published the ToRs for embedded technical assistance within RGF.

Commercial Performance
Component 1 (RGF): FCDO’s support to the RGF Intego facility is managed through a MoU with GoR, that sets out all the guiding principles and procedures of the RGF funding. Intego has in place its own in-country governance and accountability structures. Governance arrangements have been designed to ensure efficient decision making and review mechanisms, while maximising the flexibility of the facility to respond to evolving circumstances within the agreed upon strategic scope, allowing for clear accountability to the donor and government.
The Board of Directors is the principal decision-making body and meets at least once a quarter to approve pipeline projects. The RGF’s secretariat is responsible for day-to-day management of the Fund, including mobilisation and management of resources used in financing activities for protecting and preserving environment and natural resources. The Rwanda Green Fund and DPs forum meet at least monthly to review deliverables and to approve or suggest changes. Despite the potential for difficulties over the UK’s financial aid pause, FCDO’s relationship with RGF remains collaborative, professional and productive. The RGF team remains in regular contact with FCDO and continues to actively share updates on inception phase deliverables, seeking DP approval or sign off where necessary.
Component 2 (WRI): FCDO’s funding to WRI is underpinned by an accountable grant arrangement. This sets out expectations across: disbursements and progress reporting; due diligence; audit and assurance; communication and branding; reporting suspicions of fraud, bribery and corruption; and managing programme assets. To date, the WRI team has delivered a successful mobilisation phase, with key deliverables submitted and approved by FCDO.
Financial Performance

Component 1 (RGF) - RGF have developed a detailed operational manual (assisted by the TA service provider) to guide financial management, approved by DPs. RGF has also submitted a letter to FCDO detailing accounting treatment that will be used for FCDO funding to ACTION programme. The programme team have used this letter to write an information note that has been approved by BHC Kigali Development Director. To date, only one disbursement has been made of £2.7m which has been allocated for Landscape Restoration for empowering Nyamasheke's vulnerable communities. No further disbursement has been made as the programme has been affected by financial aid pause.

World Resources Institute (WRI) Component – An accountable grant has been signed setting out the financial management and reporting for this project. The project has just completed mobilisation and has not started implementation, but as the project moves to implementation, WRI will submit financial reports to FCDO on a quarterly basis. Financial reports will be reviewed by the Programme Manager and approved by the SRO before disbursements are made. The programme manager will manage HERA forecasting and disbursement in line with agreed workplan. No payment has been made during this year of review.

G: MONITORING, EVIDENCE AND LEARNING [1 page]

Monitoring
Monitoring activities during the review period included regular engagement with implementing partners across both programme components, supported by quarterly reporting and structured review meetings. These sessions helped identify progress, challenges, and lessons learned, informing adjustments to implementation. The logframe remained the primary results framework, complemented by RGF’s Monitoring, Evaluation, Reporting and Learning (MERL) procedures. All Intego-funded projects are required to submit quarterly progress reports detailing outputs, expenditure, and forecasts. Implementing partners are expected to develop monitoring plans aligned with RGF’s MERL framework. While a dedicated external MERL service provider has not yet been procured, RGF continues to lead monitoring efforts. The Annual Review process included inputs from across FCDO and the Government of Rwanda.

Evaluation
All projects under the Intego facility will undergo End of Project Evaluations (EPEs), commissioned and managed independently by RGF. These evaluations will apply OECD-DAC criteria—relevance, effectiveness, efficiency, impact, and sustainability. Implementing partners will support fieldwork and provide feedback on draft reports but will not lead the evaluation process.

Evidence
RGF’s MERL system supports ongoing evidence generation. Evidence gathered will inform programme adaptation and strengthen climate programming delivery. The programme’s business case includes a dedicated MERL component to build transferable lessons, though procurement of the service provider is pending.

Learning
Learning has been captured through quarterly reporting and partner engagement. Implementing partners document lessons learned, both positive and negative, which inform adaptive programming. Key lessons include the importance of early stakeholder engagement and flexible implementation planning. These insights will guide future programming and inform broader FCDO climate finance approaches. Learning priorities for the coming year include strengthening inclusive data collection, improving evidence use in decision-making, and embedding adaptive management practices across both technical assistance and financial aid components.

Date of last narrative financial report	Not yet due as the programme was in mobilisation and inception phase	Date of last audited annual statement	Not yet due as the programme was in inception phase