BUSINESS CASE ADDENDUM

PROGRAMME TITLE
Directorate/ Post	Freetown	Contact name	Keith Hammond
Original programme budget	£4,950,000 (increased to £19,950,000 in costed extension)	Country or region targeted	Sierra Leone
Cost extension value / (if applicable)	£528,000	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	HoM (cost extension approved by Minister)
New increased or reduced programme budget (if applicable)	£20.468 million	Original programme start and end dates	22/7/2022 - 31/3/2025 / (current end date 30/6/2025)
Latest AR programme score	A+	New programme end date (if applicable)	31/3/2026
		Programme ID	301526

Detailed information
Programme summary	The programme was approved in July 2022 with a budget of £4.95 million intended to cover a single round of solar system installations in medical facilities, followed by two years working with the Government of Sierra Leone on a country-wide plan for solar Operations and Maintenance (O&M) and directly funding O&M for the systems we had installed during this period. Soon after approval a decision was taken to cut outer year spending (and thus work on O&M) as part of HQ-driven ODA reductions. The programme focussed on solar systems for hospitals – installing at Kabala, Kambia and Bonthe, a backup system serving both the Ola During Children’s Hospital and the Princess Christian maternity hospital in Freetown and a capacity increase for an existing solar system at Masanga Hospital. / System design was based on assessments of power usage assuming reliable power supply. Lessons learnt have included a faster than anticipated increase in energy demand as partners increased investment in equipment more quickly than expected once the power supply became reliable. / Since commencing the programme, we better understand the available options for maintaining hospital systems, the limited existing capability, and investment barriers for credible firms such as the lack of payment security instruments to guarantee GoSL payment commitments. Working on O&M should have been more central to the original programme design.
Changes	All of the installations funded under the original business case were successfully completed in 2023, and all have functioned reliably since completion with O&M support from the project. / In March 2024 Development Minister Andrew Mitchell approved a cost extension of £15 million, increasing the budget ceiling to £19.95 million. This uplift funded 12 additional hospital systems and 25 smaller Community Health Centre (CHC) systems. Of these additional systems 11 hospital systems and the 25 CHC systems have been completed, and all have operated reliably since completion. / This cost extension extended O&M support for the increased number of programme-funded systems and also brought back work on the development of a public sector wide O&M plan. / This work resulted in the design of a hub and spoke model covering UK funded hospitals and several hundred World Bank and USAID funded small systems at remote schools and clinics. Subject to approval, the World Bank intends to fund the setting up of an O&M regime for solar systems at GoSL facilities across the country (including those we have installed), but it will not begin before the second quarter of 2026. / The current amendment proposal seeks to deal with i) an implementation challenge and ii) a gap before an effective O&M regime becomes operational. / At one site (Koidu Government Hospital) the Ministry of Health unintentionally allocated the only vacant land on the site both to our solar project and a major expansion of the hospital by an American NGO. The Government of Sierra Leone (GoSL) have now created space for the solar plant adjacent to the hospital. Part of the programme extension would fund ground mounts for this site and installation costs. Two US NGOs have offered to cofinance the installation. / The work FCDO led on O&M resulted in agreement that the optimal structure will involve hubs at large sites (mainly hospitals) that each cover around 50 surrounding small systems. Public and private sector models are viable, but in each case, investment is needed to create capacity as it is not currently available at the hospital locations. A World Bank supported regime is not expected to start operating until June 2026. The cost extension will provide O&M cover for the 17 hospitals we funded through to March 2026. This will protect the value of installation warrantees. These are not valid if O&M cannot be evidenced and making the contractor responsible for O&M through the warranty period will mean they are unambiguously responsible for rectifying any faults that arise. / We have requested an uplift in funding to cover the cost of the extension as part of the portfolio adjustments process that Ministers are currently considering. If we do not receive additional funding, we would seek to fund the cost extension from within our existing portfolio allocation. We would propose making the following reductions to other programmes: / A £205,000 reduction in CDEL from our Invest Salone Programme, reducing funds for capital grants to Sierra Leonean businesses and consultancy support associated with grants. This programme ends in March 2026 and will still have a £2.9 million budget. There will be some loss of private cofinancing and technical assistance to businesses, but these will not significantly impair programme outcomes. / A £323,000 reduction in RDEL from our Saving Lives Programme. The allocation for this programme exceeds current planned expenditure as we scale down in response to anticipated ODA reductions and we would reallocate as is already built into our portfolio adjustments request that is with Ministers.
Implementation	Our existing MOU with Sustainable Energy for All (SEforALL) will be extended with a new end date (31/3/2026) and a new expenditure ceiling of £20.468 million. SEforALL is an International Organisation that is part of the UN System and hosted by the United Nations Office for Project Services (UNOPS). / The co-funding for the completion of the installation at the Koidu Government Hospital will come from two US NGOs (The Susan Thompson Trust contributing $250,000 and Partners in Health contributing $125,000). Both have said they will transfer their Koidu contributions directly to SEforALL. / Once SEforALL has received payments from each contributor, they will sign a contract amendment with the constructor for completion of Koidu and extension of O&M coverage.
Budget	Pre/post amendment finance profile: / The existing approved budget is £19.95 million / By the end of May 2025, £19.866 Million had been disbursed. / The value of the cost extension is £528,000. / The additional funding will be spent by March 2026. / The extension will not take the programme beyond the current SR period.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☐ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☒ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition. / The cost of the installation at Koidu Hospital will be higher than planned but will ensure quality installation of equipment that has already been procured. The revised design is inherently higher cost, but the final configuration of new buildings and the solar system is probably optimal. / Additional O&M support will support service delivery during the programme period and is expected to bridge to a new World Bank funded O&M regime. By March 2026 Government hospitals will have received a year of extra O&M services that were not in the Business Case delivery ambition. We are seeing additional O&M as positive impact but Koidu as negative impact, leading to a neutral assessment overall.
Risk	There is a risk that despite written commitments one of the partners offering a contribution to Koidu costs fails to pay. If this occurred, we would not proceed with installation and we would present options under the asset disposal process (likely transferring to GoSL or sale at a loss). As SEforALL will not charge overhead of staff costs in relation to Koidu there would be no additional use of UK funds. Both contributing parties have a strong history of support to Sierra Leone’s health sector, and we assess this risk as being low. / There is a risk that the World Bank support for O&M does not proceed. It is part of the Sierra Leone component of the regional Distributed Access through Renewable Energy programme, with the Sierra Leone plan due for approval later in 2025. They have said approval is “highly likely” but cannot commit ahead of approval. We would still have ensured operation until March 2026.
Results/Monitoring and Evaluation	The two output level results we expect to see as a result of the extension are: / A working solar system at Koidu Government Hospital, in line with existing results framework. / Robust O&M at the 17 FCDO supported hospital sites through to March 2026. / At outcome level we would expect to see health benefits extend over a longer period because the reduced risk of systems failing due to a lack of effective O&M. / The original theory of change remains valid as both system installation and O&M are within it. / The O&M extension will ensure monitoring of energy performance at hospitals until March 2026, and a recently started system to track health outcomes across all government health facilities will provide evidence of the impact of the Koidu system, as well as the other 41 FCDO funded systems. We will directly monitor the installation work at Koidu and plan one field trip to a sample set of hospitals to monitor the effectiveness of the O&M support and system performance.

REVISED JANUARY 2025