## Annual Review Template

Title: Powering Sierra Leone’s Hospital Programme
Programme Value £ (full life): £20,478,000		Review date: 04/11/2025
Programme Code: [AMP ID#] 301526	AMP start date: 26/07/2022	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A	A+	B
Risk Rating	Minor	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003681.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005391.xlsx

Abbreviations
FCDO	– Foreign Commonwealth & Development office
GoSL	– Government of Sierra Leone
SEforALL	– Sustainable Energy for All
CA	– Crown Agents
WTYSL	– What Took You So Long
O&M	– Operation and Maintenance
EmOne	– EmOne Energy Solutions
MoH	– Ministry of Health

A. SUMMARY AND OVERVIEW

Description of programme
The goal of the programme is to improve the delivery of critical health services in hospitals and health centres by installing solar energy systems that deliver clean electricity on a reliable and sustainable basis. This has been delivered through three phases of implementation:

The original Business Case of the programme, approved in July 2022, provided £4.95 million to fund Phase 1. This phase installed primary energy systems at three regional hospitals in (Kabala, Kambia, and Bonthe), a backup energy system for the Ola During Children’s Hospital and Princess Christian Maternity Hospital in Freetown, and a capacity increase for an existing solar system at Masanga Hospital. The capacity of clean energy installed in Phase 1 was around 0.6 Mw. This phase of work was completed by the end of the 2023-24 financial year as planned with an approved initial budget of £4.95million

With Phase 1 making good progress, a decision was made to substantially scale up the programme through a Business Case Addendum which provided a £15 million budget increase. This was approved in May 2023. The scope of the Addendum was:

1. To fund operations and maintenance (O&M) support for the systems installed in Phase 1, through to the programme end date in March 2025. This was done by amending installation contracts to include O&M cover for this period.
2. To install a primary energy system for Kailahun District Hospital and 25 Community Health Centres. This work was contracted soon after the Business Case Addendum was approved using designs that had been developed in preparation for Phase 1. This work is referred to as Phase 2.
3. To develop detailed designs and specifications for 11 additional hospitals (in the district capitals in Port Loko, Pujehun, Kenema, Koidu, Magburaka, Makeni and Moyamba and four sites in Freetown). This work was done by Crown Agents through an extension to their project management contract.
4. To install solar energy systems in the 11 additional hospitals that Crown Agents provided specifications for. This installation work is referred to as Phase 3, and new international tenders were run to select both the EPC (engineering, procurement and construction) and the project manager for the Phase 3 sites.
5. To support the Ministry of Health (MoH) to develop a robust sector wide O&M strategy for all solar energy systems operating in public sector health facilities. This support has been provided directly by SEforALL.
A second Addendum to the Business Case was approved in June 2025 to increase cost by £528,000 and extend the end date of programme to 31 March 2026. The scope of this Addendum was to allow the programme to complete construction at one outstanding Phase 3 hospital site (Koidu Government Hospital) and extend O&M cover for FCDO funded installations through to the end of this financial year.

Summary supporting narrative for the overall score in this review
The Development Director at the British High Commission Freetown has agreed that this will be a “light touch” Annual Review, as unanticipated staffing issues resulted in limited resources being available. It focuses solely on lessons and risks that are relevant to completion of the programme by the end of March 2026, namely installation of the system at Koidu Government Hospital and continued O&M provision to the 17 FCDO funded hospitals. It scores all outputs based on results reported by the service provider, SEforALL, but with limited verification. Greater verification and deeper analysis of overall results from Phase 3 of the programme are deferred to the Project Completion Review (PCR) due to be completed by June 2026.

The programme scored A+ (moderately overperforming expectations) in the 2024 Annual Review, largely because the commissioning of Phase 2 systems was ahead of schedule. At the time of that review progress towards commissioning of the 11 Phase 3 hospital systems was also assessed as being on track.

In the months following the 2024 Annual Review, problems emerged at two of the Phase 3 sites:
Delay at Port Loko Government Hospital: Commissioning the system was delayed by 6 weeks due to a shipping error. A container of components for the installation was shipped back to China in error, instead of to Freetown during transshipment through Lome. There was no increase in cost.

Delay at the Koidu Government Hospital: Site installation was delayed by 12 months with an increased cost of £480,000, primarily due to insufficient coordination and engagement between hospital management and FCDO/SEforALL. The delay was caused by the proposed site for the solar installation being double allocated by hospital management; it being also allocated to an American Non-Governmental Organisation, Partners in Health (PiH). This was discovered on the first site visit by SEforALL, who found PiH construction work already underway on the site. It was further delayed by it initially appearing that solar panels could be mounted on the rooves of the buildings PiH was constructing on the site. However, SEforALL were informed in January 2025 that design and warranty issues with the new building meant this solution could not proceed, and so a new site – and new mounting equipment – would be needed. With only 10 weeks to the programme end date and around £1m already spent on components for the system (such as solar panels batteries and inverters, and designs) installation at Koidu would not be completed. Following discussions between FCDO, the MoH and PiH, it was agreed through a Business Case Addendum that the UK would provide an additional £205,000 to complete a redesigned system, with PiH and another NGO between them contributing a further £275,000. The system is being ground-mounted on an adjacent site to the hospital and is due to be commissioned by March 2026. As this is the end of the programme, and there is not currently an agreed O&M plan in place post-programme end, the delay means that Koidu will have no period of contracted O&M to help the hospital technical team understand effective operation of the system.

A recent FCDO field visit to Koidu hospital revealed that a combination of complex factors resulted in the delays and budget over run; these are fully detailed under Output One. However, the underlying causes identified were a lack of coordination with hospital management and insufficient sharing of documentation around final designs. Better engagement with Koidu hospital management team could have allowed the team to; identify the conflict in land allocation earlier, understand how hospital management prioritised land allocation which could have allowed them to recognise that PiH’s broader plans for hospital expansion would take precedent over the solar instillation, and have a greater understanding of the impacts of this change on the type of installation mounting required.

The other ten Phase 3 hospitals were completed by early May 2025 within budget. Feedback to the review team, through regular engagement with SEforAll and in-person monitoring visits, has been that the systems are largely performing reliably and improving health outcomes. To date, there has only been one serious technical fault that has required EmOne to seek support from the manufacturer, at Phase 3 hospital in Magburaka. A faulty part resulted in the system being shut down for around 2 weeks before the problem was diagnosed and the part replaced.

The hospitals provided good feedback on the O&M support from EmOne. The review team observed that EmOne is playing a significant role in supporting the hospitals with technical challenges and with managing their energy supply during the rainy season. Although this is positive, it raises concerns about sustainability once the programme ends in March 2026. Engagement with the MoH on a permanent O&M solution after the end of our programme has so far not yielded results.

The output on O&M support was therefore scored as a B, especially as installation delays at Koidu mean that the hospital will have no period of contracted O&M to help the hospital technical team understand effective operation of the system. Primarily due to the significant time and budget overrun at Koidu, both the component and the installation component is further marked as a B. The output on communications was scored as an A. This output scores lead to an overall programme score for the 2025 Annual Review of B.

Major lessons and recommendations for the year ahead
The Development Director at British High Commission Freetown agreed that the focus of this light touch review was to identify lessons and risks that relate to activities that will be undertaken between the review date, and the revised programme end date of 30 March 2026. The activities are i) completion of a solar system for Koidu Government Hospital and ii) the provision of O&M support to already completed solar systems supporting 17 hospitals. These risks and lessons were identified through engagement with SEforAll, EmOne and in-person monitoring visits by the review team.

Lessons and recommendations relating to completion at Koidu Government Hospital:

1. Learning from the need to better coordinate between hospital management, the FCDO programme team should put in place and lead an enhanced coordination mechanism with SEforAll, EmOne, Koidu Government Hospital and – where appropriate – the Ministry of Health. SEforAll should be responsible for tracking progress, which should be monitored closely and emerging risks escalated immediately to ensure installation is completed by end March 2026; a very tight timeframe with limited space for delays.
2. Learning from the need to closely oversee delivery and enhance engagement with Koidu government hospital management, monthly field visits will take place with SEforALL and FCDO. This will support engagement, maintain momentum and increase transparency over pace of delivery.
3. While most system components are already in Sierra Leone, a small number will need to be imported and any delay in customs clearance could result in delayed completion. FCDO, the Ministry of Health and SEforALL should engage with customs prior to goods arriving to minimise the risk.
4. Another timing risk relates to the need to shut down power to all or part of the hospital for periods as part of the installation process. Times for any shutdowns and any mitigation necessary to power the most critical loads should be agreed well in advance with hospital management and should be documented.
5. A plan (developed and overseen by SEforALL) should also be agreed well in advance for tapping into the hospital’s EDSA supply. In addition, planned upgrade work to the hospital will occur after the solar installation is complete. There needs to be early engagement with partners to ensure that any impacts on the solar system from the upgrade are fully understood.
6. The site for the solar panels is outside the existing hospital perimeter and has poor boundary security. A plan (developed and overseen by SEforAll) is needed to secure materials during construction, and by the government to ensure the security of the installation once completed.
Recommendations relating to Operations and Maintenance (O&M):

1. EmOne have developed a good approach to O&M with a clear tiering of roles that include on site technicians, a dedicated in country maintenance team and support from outside Sierra Leone for the most technically challenging issues. This has worked well and should act as a formally agreed and disseminated model for the tiers of support needed in any system wide regime that takes effect after March 2026.
2. Hospital technicians can be supported to provide preventative maintenance, repair of relatively minor faults and effective optimisation of system loads – particularly in the rainy season. The technical team at Kambia Government Hospital (a Phase 1 hospital which was commissioned in 2023) were able to play these roles with substantially less back up from EmOne than the Phase 3 hospitals. SEforAll should put in place a plan with EmOne to ensure that as much support and training as possible should be given to the Phase 3 technical teams to prepare them for the ending of contracted O&M support in March 2026.
3. Koidu Government Hospital will face a particular challenge as it will be commissioned just prior to the programme closing and will have no period of contracted O&M to help the hospital technical team understand effective operation of the system. EmOne should ensure technicians are closely involved in the installation. SEforAll should arrange for the technicians to spend time at a Phase 1 hospital for training.
4. FCDO, with SEforAll, should engage with the MoH on identifying and ideally putting in place a sustainable plan for O&M after the programme ends. At a very minimum, the MoH needs to own all system warranties and the process for liaising with manufacturers as needed.
5. If major faults occur during a time when no O&M support is being provided there is a risk that technicians seriously damage systems in making efforts to repair them. This may also result to health and safety risks to human beings. If there is an O&M gap, the MoH should consider a protocol under which systems are mothballed until O&M is available to avoid costly damage occurring. The FCDO should engage the MoH on this.
6. The FCDO should engage with the World Bank on a previously stated plan to support an O&M regime for public solar systems. If that support is agreed, it is likely there will be a gap in O&M support for the solar systems we installed between the end of this programme and a new O&M regime coming online. Recommendations 4 and 5 would apply in this circumstance.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change for the programme is shown below:

This Theory of Change remains valid and early evidence from supported hospitals suggests that improved power supply has led to significant improvements in health outcomes, including reductions in numbers of preventable deaths and maternal mortality.
Input
Reliable electricity made available to hospitals and connected staff quarters, with a maintenance plan that ensures that electricity provision is sustained over time.
Process
Outcome

Output
 Impact
Increased hours of operation, and reduced emergency response times. Faster and more accurate diagnosis. Better staff and patient hygiene, and improved staff attendance and retention.
Increased access to modern healthcare and a reduction in preventable deaths, including during childbirth and of new-born babies.

Empowering women and girls (Campaign Goal 1) by ending preventable deaths and Ensuring Healthy Lives (SDG 3).
Sterilization and refrigeration and piped water always available. More advanced diagnosis options. Energy for staff quarters.

Efficiency
Economy
Effectiveness
Cost-effectiveness
Equity considerations

Although it is reflected, a weakness in the Theory of Change is that it does not highlight clearly enough the extent to which O&M is a necessary condition for a sustained flow of programme benefits.

A more thorough evaluation of the Theory of Change will be carried out for the PCR.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The Programme’s outcome and impact indicators as per programme’s logframe are as follows:

The programme’s outcome is ‘increased energy access to modern healthcare’, with the following indicators:
1. Installed capacity of solar with storage at supported facilities.
2. Average hours per day of power outage per facility
3. Reduction in up-time of fuel-based generator
The programme’s impact is ‘improvements in health outcomes and in environmental impact’, with the following indicators:

1. Clean electricity supplying the facilities (changed from original logframe which focuses on carbon emissions avoided)
2. Number of births supported by improved power supply in Government hospitals, measured by average number of monthly births.
The programme is on track to deliver expected outcomes in terms of the improvement in power supply we hoped to see at health facilities and the health benefits we expected this improvement in power supply to deliver. The delay at Koidu Government Hospital has resulted in this happening at higher than intended cost, though at more than 40 other sites (hospitals and community health centres) these outcomes have been delivered within projected cost and without significant delays.

The main risk to achievement of the programme impact is the lack of a confirmed O&M regime after the programme ends. Serious work on O&M started after approval of a cost extension number 1 and the ambition set was to agree an O&M approach with the government and other partners. Seeing the way that contracted O&M support has been structured highlights the fact that some tasks can be undertaken by existing hospital staff, but more specialist support is essential to ensuring systems operate reliably over a long period. FCDO should do whatever possible to encourage the MoH and/or development partners to support the implementation of an O&M system.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This programme will end in March 2026.

## C. DETAILED OUTPUT SCORING
Output Title	Project Management, Design, Monitoring
Output number:		1	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: / All procurements contracted (EPC, PM firm, Comms firm)	No target	Met: All procurement for phases 2 and 3 completed by June 2024
1.2: Project Steering Committee established and meeting regularly (cumulative)	9 steering committee meeting took place by March 2025	Exceeded: in lieu of a formal steering committee, weekly progress meetings were held with SEforALL and all contractors who are part of the programme. Reports of 19 of such meetings were shared with the FCDO. / These are complemented by the monthly meetings with and reporting to FCDO, and the ad-hoc meetings with the Ministry and other stakeholders which are more focused on direct problem-solving. These included; / November 4&5, 2024: STEM Traineeship Graduation Ceremony and Reception. / November 6, 2024: Phase 2 commissioning & phase 3 unveiling ceremony / November 7, 2024: Roundtable with development partners and Government sharing lessons learned and project updates / April 4, 2025: Presentation on business models to SL mini-grid accelerators group / June 12, 2025: Phase 3 commissioning ceremony / July 3, 2025: Presentation on business models to MoE, MoH, EU, SEforALL, GIZ, UNOPS
1.3: Number of health facilities monitored by FCDO during the installation phase (cumulative)	18 hospitals and 25 CHCs by March 2025	Partially Not Met: 10 completed hospital visits and the Koidu site were monitored over the reporting period.
1.4: Lessons learning process	Completion of lessons learnt reports from FCDO, SEforALL and Tetra Tech	Met: Tetra Tech and CEMMATS (the project’s Project Management firm) completed and submitted the phases 1&2 endline report in March 2025 designed for full comparability with the original baseline analysis, despite a change in project management contractor and subsequent update of the project MEL framework between reporting periods. They submitted the phase 3 baseline report in April 2025 and the phase 3 endline report in June 2025. / After the completion of phase 1 and before starting phases 2 and 3, SEforALL hired Catalyst Energy Advisors to perform an impact assessment of phase 1 and a developmental evaluation of phases 2 and 3 to capture impact performance data from the already operating hospitals and feed the lessons learned into the design of the 12 hospitals and 25 clinics from phases 2 and 3. The results were presented to the SEforALL high management in July 2025 and will be publicly available through our website.

Briefly describe the output’s activities and provide supporting narrative for the score.
Procurement of Phase 3 went well. In lieu of steering committee, weekly progress meetings were held with SEforALL and all contractors who are part of the programme and reports of 19 of those meetings were shared with the FCDO. The FCDO also conducted monitoring visits to ten (including phase 1 and phase 3) hospitals during the reporting period (though short of the 18 planned), but this did not prevent the double allocation of the Koidu site. Deeper engagement and documentation with hospital management might have prevented the issue at Koidu, and more intensive monitoring by both SEforAll and FCDO might have identified exactly what had caused the delay in construction, as the original site was allocated to Partners in Health for the construction of a canteen. Recent FCDO field visit to Koidu hospital revealed that a combination of complex factors resulted into this happening. These factors included:

  1. Crown Agents (who led the design phase) agreed the plans with the Ministry of Health centrally without the involvement of the hospital itself. Nothing was put in writing to the hospital to confirm what had been agreed;
  2. The hospital did not inform Crown Agents that it had already allocated the site to Partners in Health, which it claims to have done 2 years beforehand;
  3. Hospitals in general are regularly offered multiple projects by development partners and keep all options on the table until they come to fruition, which is what happened in this instance;
  4. There is a large construction project underway to significantly expand the capacity at Koidu hospital, which Partners in Health are leading. Therefore, it is not surprising that their canteen construction was prioritised for the original site over FCDO solar project;
  5. Procurement of roof mount structures happening before realising a) the roofs of the old building would not be suitable and b) the roofs of the new buildings would not be ready for use until late 2026.
  6. New land across the road from the hospital then had to be acquired for ground-mounts. This then meant that additional materials for ground mount structures had to be procured for the site.

These issues led to the output being scored as a B.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The changes made during this period were on procurement - the contracting of an amended design for Koidu Government Hospital and an extension of O&M support until end March 2026.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous AR – in order to ensure visibility and oversight, SEforALL should endeavour to institute fortnightly meetings by end of October as the scope or work increased and new project management and communications firms come on board. The FCDO (PRO) should monitor this for compliance on a monthly basis going forward: - recommendation actioned. Fortnightly meetings were organised by SEforALL following programme scope increase in October 2024.

Recommendation from previous AR – FCDO to assess the provision of limited power to the staff quartets at CHC sites without compromising the reliability of power supply for medical uses – SEforAll carried out an assessment on behalf of the FCDO. It assessed that this should only be done if existing systems can provide power to staff quarters without requiring capacity increases, there would be limited cost involved, and load limiters could be deployed to ensure there was no risk of usage by staff resulting in facilities losing supply. This resulting in the provision of power to staff quarters at some sites but not at others. More data will be provided in the PCR.

New Recommendation 1 – FCDO should institute fortnightly coordination meetings with implementing partners, EPC contractors, and key stakeholders to ensure timely completion of the Koidu installation and to monitor provision of O&M support and training to all hospitals through to end March 2026. FCDO should conduct monthly field visits to Koidu and as many other hospitals as possible during the remainder of the programme to check O&M activity.

Output Title	Implementation
Output number:		2	Output Score:	B
Impact weighting (%):		50	Weighting revised since last AR.	Yes

Indicator(s)	Milestone(s) for this review	Progress
2.1: Hospital electrification construction: number of energy systems installed and commissioned	Complete 18 hospitals and / 25 CHCs by June 2025	Partially Met: 17 hospitals and 25 CHCs completed by June 2025. 1 hospital to be completed by March 2026
2.2: Third party verification of installations completed	Complete 18 hospitals and / 25 CHCs by June 2025	Partially Met: / 17 hospitals and 25 clinics verified by third party by June 2025 / 1 hospital (Koidu) to be completed by March 2026
2.3: Number of female engineers trained through the project (TBC)	22 by March 2025	Exceeded: 23 female engineers trained through the project, with final ceremony taking place in November 2024.
2.4: Number of trained staff on solar energy in healthcare facilities	29 by March 2025	Met: 29 trained staff on solar energy at health facilities so far solarised (1 staff per site). 17 trained by March 2025 plus 12 trained in previous year.

Briefly describe the output’s activities and provide supporting narrative for the score.
Most Phase 3 installations were completed in line with the planned time and budget. At Port Loko, commissioning was delayed by a shipping error. At Koidu more serious issues resulted in both a time and a cost increase, as has been described in this review. This review therefore scores it as B because 2 systems are late and one over budget.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output changed in this period to reflect the delay to the installation and the subsequent new design of the Koidu system. The weighting of this output also changes, reduced from 70% to 50% to account for the new output on O&M.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
Lessons learned, progress and recommendations for the year ahead on this output have all been captured in pages 3 and 4 above.

Output Title	Communications
Output number:		3	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1: Communications and dissemination strategy developed	No target for this review	Met: 2 completed - 1 strategy each for Phases 2 and 3 in 2024
3.2: Video footage of hospital completed (pre-, post-, and final)	10 by March 2025	Exceeded: 22 videos documenting pre-, during and post completion phases of Phase 2 / 12 videos documenting pre-, during- and post- completion phases of Phase 3
3.3: Impact stories and interviews: Number of staff and/or patient feedback on system improvements (TBC)	No target for this review	Met: 12 beneficiaries (healthcare workers and patients) plus Minister of Health interviewed for Phase 3. / 9 beneficiaries interviewed for Phase 3 hospitals

Briefly describe the output’s activities and provide supporting narrative for the score.
The quality and quantity of communications products have been good during this reporting period, exceeding expectations on quantity. Given that this is a light-touch review and focussed primarily on the remainder of the programme, the review team has not been able to more thoroughly assess the impact of the communications products but will do so as part of the PCR. This output has been scored as A.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There was no change to this output during the past year and there’s no planned change after this review. The programme ends on 31 March 2026.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
The 2024 annual review did not provide any recommendation on this output. It should be noted that communications will be increasingly important as the programme comes to an end.

Recommendation 1 – SEforALL should ensure communications materials capture relevant video footages and impact stories at every level of implementation for the remainder of the programme for presentation to the FCDO.

Output Title	Operation & Maintenance (O&M) contracts for hospital systems
Output number:		4	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	No (New output)

Indicator(s)	Milestone(s) for this review	Progress
4.1: Number of hospital systems with programme funded O&M contracts in place with an operational O&M delivery plan	No target for this review (new output indicator added)	O&M funded contract in place covering all hospitals. O&M delivery plan not as robust as it should be at the hospital-level.

Briefly describe the output’s activities and provide supporting narrative for the score.
This is a new output included to reflect the importance of work on O&M to the sustainability of programme results. There is no milestone for the current review. The review team assessed the output as a B. All of the systems installed under this programme do have funded O&M in place, however the approaches witnessed by the review team appear more ad-hoc than “an operational O&M delivery plan” at the hospital-level. There is heavy reliance on EmOne to support and trouble shoot, with EmOne providing remote monitoring and proactively flagging issues before they emerge. The Phase 1 hospital visited by the review team appeared less reliant on EmOne than the Phase 3 hospitals.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is a new output, created since the 2024 Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous AR – A logframe indicator on O&M activity should be added to Output 1, and the weight of that Output increased – Output indicator on O&M activity added as a separate output indicator as part of logframe review. The output weighting for output 2 reduced to account for output indicator 4.

Recommendation from previous AR – If the government and development partners agree to develop a sector wide approach to O&M that involves building capacity within the public sector, FCDO should then consider extension of the programme to support transition to government led O&M regime – A sector wide O&M approach has not yet been agreed. FCDO approved the extension of the programme through a Business Case Addendum to extend O&M cover for FCDO funded installations through to end March 2026. A further extension of the programme will not be approved.

This review has two new recommendations related to O&M for the remainder of the programme:

New Recommendation 1 – FCDO to continue to engage with the MoH and the World Bank (and other development partners as required) on the development of a sector wide approach on O&M to ensure the sustainability of programme funded systems.

New Recommendation 2 – FCDO, through SEforAll, to take measures to maximise the O&M support and training given to the hospitals, as set out in the recommendations listed on pages 3 and 4 of this review.

## D: VALUE FOR MONEY

This is a light-touch Annual Review that is focussed primarily on lessons and risks relevant to the completion of the programme, namely the completion of the installation of the system at Koidu Government Hospital and continued O&M provision. Both of these are aimed at ensuring maximum value for money of the programme. A more in-depth assessment of the Value for Money of the programme as a whole will be carried out for the PCR.

E: RISK

Overview of risk management
This Annual Review has made clear the risks to the timely and successful completion of the programme. A new enhanced coordination mechanism (including fortnightly meetings) for the remainder of the programme will closely monitor the existing risks and any new risks arising. SEforAll is also expected to be engaging on the risks with downstream partners on an ongoing basis and reporting back to FCDO at fortnightly meetings (or as any new risk emerges).

The lessons and risks set out on pages 3 and 4 of this Annual Review are all aimed at mitigating the risks associated with a delay to the completion of Koidu and to the sustainability of the systems once the O&M under this programme ends.

BHC Freetown has placed this programme on its Post Risk Register and has escalated it to Africa Directorate in FCDO headquarters. BHC Freetown has committed to providing regular updates to Africa Directorate for the remainder of the programme.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Overall, the performance of delivery partners and the FCDO on the Powering Hospitals Project has been constructive and aligned with programme objectives. The FCDO team has been closely engaged in the delivery of the programme and in responding to the situation at Koidu Government Hospital in particular.

The partners (SEforAll – FCDO tier 1 implementing partner, EmOne - the EPC contractor, Tetra Tech and CEMMATS - the Project Management Firm) have all demonstrated strong technical expertise in system design, procurement, and installation. However, the delays described in this review and hospital-level acceptance have created challenges in execution especially at the Koidu government hospital.
Thus, given the persistent issues encountered at Koidu, it is reasonable to question whether programme management and oversight were sufficiently robust. A more proactive and structured approach to project governance - particularly in risk identification and mitigation - might have helped prevent or reduce the severity of these delays. Greater oversight, such as an earlier visit to the site initially, could have ensured earlier detection of bottlenecks and more agile responses to emerging challenges. This could have captured the issues, detailed in Output One, including understanding the Koidu hospital management’s prioritisation, duplication of site allocation and procurement of incorrect solar mounts.
In terms of partner response, SEforALL has demonstrated a generally reactive posture to the delays, taking steps to mitigate further risks once issues were identified. While their interventions have helped stabilise certain aspects of the programme (such as designs and early procurement), there remains room for improvement in anticipating risks and coordinating more timely support to avoid compounding delays.

Drawing on the lessons learned outlined above, FCDO are now implementing significantly enhanced oversight and further strengthening the programme management for the remainder of the programme between FCDO and partners to help mitigate the ongoing delivery risks.

G: MONITORING, EVIDENCE AND LEARNING

This is a light-touch Annual Review that is focussed primarily on lessons and risks relevant to the completion of the programme, namely the completion of the installation of the system at Koidu Government Hospital and continued O&M provision.

The review recommends monthly monitoring visits for the remainder of the programme. A more in-depth assessment of the results, evidence and learning from the programme as a whole will be carried out for the Project Completion Report. The review recommends that the programme teams instructs SEforAll to have a robust plan for data and evidence collection to inform the overall results of the programme for the PCR.

Date of last narrative financial report	26/09/2025	Date of last audited annual statement	22/10/2025