BUSINESS CASE ADDENDUM

PROGRAMME TITLE	Priorities for Universal Health Coverage: Cost-Effective Health Services for Everyone (PURCHASE)
Directorate/ Post	Human Development Department, / Global Health Directorate	Contact name
Original programme budget	£4.25m	Country or region targeted	Africa, Global
Cost extension value (if applicable)	N/A – No cost extension	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Director, Global Health Directorate
New increased or reduced programme budget (if applicable)	£4.25m – no change	Original programme start and end dates	06/12/2023 to 31/03/2026
Latest AR programme score	B	New programme end date (if applicable)	30/09/2026
		Programme ID	301528

Detailed information
Programme summary	PURCHASE was approved in December 2023. The Business Case recognised that constrained fiscal space in many low and low-middle income countries (LMICs), exacerbated by the Covid-19 pandemic, was making it challenging for governments to invest in their health systems, and prioritise limited funding to the most cost-effective interventions. / The two programme components are: / Support for advocacy and policy to progress the goals of universal health coverage. / Strengthen leadership and capacity at the regional and national level for evidence-based decision making on Health Financing (Evidence Informed Priority Setting) / In its first year, PURCHASE has advanced component 1. The programme has provided impactful, well received, technical assistance to the South African government to unlock National Health Insurance reforms; supported policy makers through the World Bank’s country-led Joint Learning Network on UHC; and funded the Centre for Global Development (CGD)’s New Compact for Heath Financing, an innovative framework for a country lead approach to aid, being piloted in Laos and Ethiopia. / Component 2 (a technical partnership with Africa CDC’s Health Economics and Financing Unit) has not been advanced. This was due to delays caused by: a) the organisation’s directive to receive direct financing, rather than the intermediary envisaged in the Business Case, and the subsequent Due Diligence Assessment (DDA) required across UK ODA funds; and b) partner staff changes and change of priorities in the HEF Unit. / The need for PURCHASE is now more relevant, following the 2025 shifts in ODA funding, aligned with the Foreign Secretary’s vision for stronger, domestically financed health systems. Many countries, particularly in Africa are struggling to mobilise domestic financing and spend the available money effectively and efficiently. While activities and lead partners and the budget profile will change, the outcome and impact remain the same.
Changes	There are two drivers of change for this amendment: changes to the external funding context, and to the main partner, which now require PURCHASE to pivot its work, and represent a material change to the BC: / Following the 2025 shifts in the global funding landscape, there is an urgent need to provide support to countries facing rapid transition from aid (‘health financing cliffs’) LMICs are seeking technical assistance on how to replace external funding and shift models of care from donor-supported services to domestic budgets. / Delays to the DDA with Africa CDC (being conducted across UK programmes) and the lack of fiduciary assurances in the draft assessment to allow direct funding, combined with partner staff changes and change of priorities in the HEF Unit means that the technical collaboration with Africa CDC as set out in the BC is no longer viable during the remaining programme timeframe. / To respond, we are proposing the following changes to the programme budget, partners and outputs. The programme outcomes and impacts remain unchanged. / Introduce a new component (Technical Support to Countries for Health Financing). We will invest up to £2.5m in short-term, immediate technical assistance under a collaborative partnership between the World Bank and WHO. This will deliver health financing guidance, review financial protection strategies and provide in-country support to assess and respond to the current health financing crisis. The collaboration will draw on the Bank’s strengths in on-budget support with WHO’s systems approach to health financing. / Significantly reduce the budget for component 1 (Technical Support for Priority-Setting, Africa CDC). We will not proceed with the planned contribution to Africa CDC’s HEF (originally ~£3.75m). Instead, we will retain up to £0.5m that could potentially be provided in short-term pilot funding, and we are exploring options to mobilise this funding, combined with drawing down technical assistance, working closely with APEX. This recognises the important role of this regional institution in building health economics capability on the continent. If the pilot goes ahead and is successful, it will be incorporated into a subsequent Health Systems and Financing programme/CoE. / A six-month time extension to retain the flexibility in response to urgent and evolving needs, ensuring we can sustain momentum and extend high-impact activity efficiently. There are currently no plans for spend next financial year. / We will not proceed with external evaluation, given the short duration of the programme. / The programme has also flexed the UHC Advocacy Fund, within existing ProF rules, to include a Wilton Park event on rights (recognising that rights-based access is central to UHC goals, including access for all and prioritised essential services). We will maintain close criteria for funding any new or extending existing grants. / Overall, we assess the changes to the BC to neither increase nor decrease programme VfM.
Implementation	Technical Support to Countries for Health Financing: A joint workplan for £2.5m with two arrangements: / £1.5m funding will be channelled through the existing World Bank Health Systems Transformation and Resilience Fund (HSTRF). An updated DDA is nearing completion, with no red flags. There is a live Administration Arrangement with HSTRF which will need amending to include this new activity. / £1m through a Contribution Arrangement with WHO, allocating funding to the HQ Health Financing directorate in Geneva and the AFRO region. WHO’s Central Assurance Assessment is in place and the WHO Hub are content with this proposal. / Agreements with World Bank and WHO will be agreed up to March 26. We will mobilise agreements in an accelerated timeframe after the addendum has been signed off.
Budget	This extension involves no additional costs to the programme. The new health financing activities will be funded by reallocating existing funds within the £4.25m approved Business Case. / Approved financial profile (agreed Dec 24) / Amended financial profile / £2.375m of funding will be transferred from the Technical Support for Priority Setting component and £125k from Evaluation to the new Technical Support to Countries for Health Financing component (£2.5m total). / Affordability: Budget has been secured for this activity in 25/26. No funding is profiled in FY26/27.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☐ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☒ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition. / The need is far greater than was the case two years ago. However, this focussed work is short-term and so may not result in greater outcome and impact level change. As a result, there will be a negligible change.
Risk	The reputational risk to reducing Africa CDC’s HEF support is low. This grant was not signed, and we have confirmed with Africa CDC that the original proposal is not viable and are working through options for a short-term grant. Wider support, including institutional development, is being provided by APEX, and UKHSA secondments. / One new risk has been identified because of this change:

Results/Monitoring and Evaluation	The theory of change has been amended at output and activity level to include health financing and domestic resource mobilisation, with outcomes adapted. / Intermediate outcome 2 will be replaced with ‘improved alignment of external and domestic health financing flows, systems, and priorities at the country level, enabling more efficient and feasible pathways to sustain universal health coverage’. This reflects the move towards responding to the urgent health financing work, which will be delivered at global and country-level. / Procuring external evaluation at this stage of the programme has been assessed not to be Value for Money due to the short time frame (6 months) of implementation. Regular programme monitoring is expected to provide sufficient assurance.
[note] CGD latest analysis shows 26 countries most vulnerable, collectively receive $3.4 billion in US bilateral global health assistance—can be considered “highly exposed” and “highly fiscally constrained” and are exceptionally unlikely to be able to fill the gap. 26 Countries Are Most Vulnerable to US Global Health Aid Cuts. Can Other Funders Bridge the Gap? | Center For Global Development