## Log Frame
Please refer to the Guidance Notes tab for advice on completing the various fields in the log frame.
Please refer to the Results Framework Prof Guide for broader information on the log frame approach
PROJECT TITLE | Priorities for Universal Health Coverage (UHC): Cost-Effective Health Services for Everyone (PURCHASE)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Mar 24) | Milestone 2 (Mar 25) | Target (Sept 2026)
Sustainable progress on Sustainable Development Goal target 3.8 on achieving universal health coverage, particularly in the Africa region. | African Union average UHC index score. | Planned | 44 | 45 | 47 | 47
Achieved
Source
Data is tracked through the World Health Organization Global Health Observatory database for SDG 3.8.1 (UHC Service Coverage Index); African Union average UHC index score.
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (Dec 25) | Milestone 2 (Mar 26) | Target (Sept 2026) | Assumptions
Progress on reforms and effective financing for UHC in countries, with efficient prioritisation of health budgets ,transitioning from aid to utilising more domestic resources, and essential health benefit packages that reflect available resources, and ability to implement. | Global, regional or national commitments, policies and/or legislation for the improved alignment of external and domestic health financing and national priorities to sustain/strengthen universal health coverage | Planned | 0 | 15 | 30 | 45 | 1) UHC advocacy activities and WB Compacts are a contributing or catalytic factor in sustained or strengthened express commitment to UHC. 2) Selected country government (Ethiopia, Syria, Ghana, Uganda, Indonesia) are able to influence the process, integrate the WB Compacts into national plans 3) Selected countries will engage with and begin to implement WHO technical guidance
Achieved
Source
HSTRF Annual report on Compact uptake/progress; World Bank Governance Calls; Evidence of formalised commitment following engagement supported by UHC Advocacy Fund, World Bank Compacts and WHO technical assistance ( in selected countries) including government statements, new or updated UHC roadmaps and policies, or specific initiatives and policies introduced or strengthened with the explicit aim of supporting UHC implementation.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 (NEW) | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | 2026-04-01 | Assumptions
A technical partnership with Africa CDC for an inception grant is fully mobilised and is able to begin delivery. | A completed and agreed DDA with an action plan, co-developed with Africa CDC | Planned |  | Completed DDA (including management response) | Action plan agreed between FCDO and Africa CDC | 1 | 1) Africa CDC will agree to the action plan and are able to carry out the necessary recommendations to enable direct funding. 2) FCDO HST's Programme Addendum is approved to pursue a partnership with Africa CDC and enable a full year activity. 3) FCDO HST receives an adequate ODA allowance to enable funding of this inception. 4) FCDO HST's has the capacity and resource to mobilise this partnership at pace. 5) Africa CDC's new workplan and activities will align with the newly expanded scope of PURCHASE.
Achieved
Source
Internal: FCDO's Due Diligence library, Signed Agreement
| Output Indicator 1.2 |  | Baseline | 2026-04-01 | 2026-05-01 | 2026-05-01
| Africa CDC have signed an MoU agreement with an agreed workplan and revised log frame | Planned | 0 | Agreed Revised PURCHASE log frame | MoU signed | 1
Achieved
Source
DevTracker for MoU agreement and revised log frame.
IMPACT WEIGHTING (%) | Output Indicator |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (Nov 25) | Milestone 2 (Feb 26) | Target (March 26) | Assumptions
Well-coordinated technical collaborations, learning and institutional development for health financing including transition from aid and maximising available resources | Number of countries receiving joint technical assistance to support broader health financing process from the World Bank and WHO | Planned |  | 1 country | 3 countries | 7 countries | 1) WB and WHO activities align well and these activities support country's needs on health financing 2) The countries where there is joint WHO and WB activity are actively transitioning from aid.
Achieved
Source
PURCHASE Quarterly reporting, World Bank HSTRF Annual review, governance calls, interviews with FCDO Health Advisors and country staff
| Output Indicator 2.2 |  | Baseline | Milestone 1 (Jun 26) | Milestone 2 (Aug 26) | Target Sept 26
| Number of countries receiving health financing technical assistance to strengthen functional evidence-informed priority setting processes, units and/or teams supported by Africa CDC Health Economics & Financing Programme or through technical support that they coordinate. | Planned | 0 | 1 country | 2 countries | 3 countries
Achieved
Source
Africa CDC HEP annual report; evidence of capacity building (training reports; workshop outputs; process mapping)
IMPACT WEIGHTING (%) | Output Indicator |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1(Mar 24) | Milestone 2 (Mar 25) | 2026-03-01 | Assumptions
Better context-appropriate evidence and tools for country decision-making on health financing including transition from aid | Number of evidence products (including policy briefs) and tools developed or tailored to support countries and institutions to manage resources for health including coordinating external financing, increasing DRM, EIPS processes | Planned | 0 | 1 | 2 | 5 | 1) Key decision makers are able to and want to engage with the events, and products developed by our partners.
Achieved
Source
| Output Indicator |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (Mar24) | Milestone 2 (Mar25) | 2026-03-01 | Assumptions
Increased political engagement on UHC and strengthened UHC advocacy networks and approaches | Number of advocacy engagements and activities ( e.g. events, dialogues, policy briefs) delivered through global, regional and country-level platforms (in-person or virtual) | Planned | 0 | 5 | 7 | 12 (cumulative) | 1) Advocacy events are able to reach influential stakeholders and decision-makers who can shape political and policy commitments on UHC. 2) Advocacy activities bring in new partners, ideas or policy framings that can sustain or enhance commitment to UHC. 3) Advocacy is necessary to sustain and strengthen commitment to UHC on political and policy agendas.
Achieved
Source
UHC Advocacy Grant quarterly reporting; Annual Review returns from partners
| Output Indicator 4.2 |  | Baseline | Milestone 1 (Mar24) | Milestone 2 (Mar25) | 2026-03-01
| Number of global, regional and national-level political and policy stakeholders reached with advocacy activities - including downloads, citations referenced in or used in decision -making processes or discussions | Planned | 0 | 50 | 70 | 120 (cumulative)
Achieved
Source
UHC Advocacy Grant quarterly reporting; Annual Review returns from partners
IMPACT WEIGHTING (%) | Output Indicator |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Change frame
Use this change log to record all changes to the log frame over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disaggregated by sex) | Joe Bloggs | 2022-01-01
1 | Impact | Updated milestone to reflect extension of PURCHASE to September 2026 | FCDO | 2025-02-25
2 | Outcome | Amended from 'Progress on reforms and effective financing for UHC in countries, with effective prioritisation of health budgets and essential health benefit packages that reflect available resources and ability to implement.' to 'Progress on reforms and effective financing for UHC in countries, with efficient prioritisation of health budgets ,transitioning from aid to utilising more domestic resources, and essential health benefit packages that reflect available resources, and ability to implement.' | FCDO | 2025-02-25
3 | Outcome Indicator 1 | Amended from 'Global, regional or national commitments, policies and/or legislation for evidence-informed priority setting and/or universal health coverage introduced or strengthened' to 'Global, regional or national commitments, policies and/or legislation for the improved alignment of external and domestic health financing and national priorities to sustain/strengthen universal health coverage'; Updated assumptions, milestones and respective dates' to 'December 2025 to March 2026' to reflect new activity | FCDO | 2025-02-25
4 | Outcome Indicator 2 | Removed | FCDO | 2025-02-25
5 | Output 1 | Addition of new output 'A technical partnership with Africa CDC for an inception grant is fully mobilised and is able to begin delivery. ' with updated assumptions | FCDO | 2025-02-25
6 | Output Indicator 1.1 | Addition of new output indicator 1.1 - ' A completed and agreed DDA with an action plan, co-developed with Africa CDC' | FCDO | 2025-02-25
7 | Output Indicator 1.2 | Addition of new output indicator 1.2 - 'Africa CDC have signed an MoU agreement with an agreed workplan and revised log frame' | FCDO | 2025-02-25
8 | Output | Removed 'Strengthened regional frameworks, networks and leadership for evidence-informed priority setting in the African Union and its Member States' and the associated indicators; was formerly Output 2 | FCDO | 2025-02-25
9 | Output 2 | Amended from 'Well-coordinated technical collaboration, learning, and institutional development support for evidence-informed priority setting in Africa' to 'Well-coordinated technical collaborations, learning and institutional development for health financing including transition from aid and maximising available resources; updated assumptions | FCDO | 2025-02-25
10 | Output Indicator 2.1 | Amended from ' Number of countries receiving assistance to develop or tailor tools, establish and/or strengthen functional evidence-informed priority setting processes, units and/or teams supported' to 'Number of countries receiving joint technical assistance to support broader health financing process from the World Bank and WHO' | FCDO | 2025-02-25
11 | Output Indicator 2.2 | Amended from 'Number of EIPS related strategic and technical activities collaboratively implemented with international and country level partners' to ' Number of countries receiving health financing technical assistance to strengthen functional evidence-informed priority setting processes, units and/or teams supported by Africa CDC Health Economics & Financing Programme or through technical support that they coordinate.' | FCDO | 2025-02-25
12 | Output 3 | Amended from ' Better context-appropriate evidence and tools for regional and country based decision-making' to 'Better context-appropriate evidence and tools for country decision-making on health financing including transition from aid' | FCDO | 2025-02-25
13 | Output Indicator 3.1 | Amended from 'Evidence products developed or tailored for use by African States for regional and country-based decision making.' to ' Number of evidence products (including policy briefs) and tools developed or tailored to support countries and institutions to manage resources for health including coordinating external financing, increasing DRM, EIPS processes' | FCDO | 2025-02-25
14 | Output Indicator 4.1 | Amended from ' Number of advocacy engagements (events, dialogues, policy briefs) delivered through global, continental, regional and country-level platforms.' to ' Number of advocacy engagements and activities ( e.g. events, dialogues, policy briefs) delivered through global, regional and country-level platforms (in-person or virtual)' | FCDO | 2025-02-25
15 | Output Indicator 4.2 | Amended from ' Number of global, continental, regional and national-level political and policy stakeholders reached with advocacy activities.' to 'Number of global, regional and national-level political and policy stakeholders reached with advocacy activities - including downloads, citations referenced in or used in decision -making processes or discussions' | FCDO | 2025-02-25
16
17
18
19
20
21
22
23
24
25
26

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.