## Annual Review Template

Title: Health Systems Connect
Programme Value £ (full life): £2.93m		Review date: 18 May 2026
Programme Code: 301530	AMP start date: 6 April 2023	AMP end date: 31 March 2026 (BC no cost extension granted to 31 March 2027)

Summary of Programme Performance
Year	23/24	24/25	25/26
Overall Output Score	B	B	B
Overall programme risk rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	D0003600.odt (live.com)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301530

A. SUMMARY AND OVERVIEW
Description of programme

The Health Systems Connect (HSC) programme facilitates collaboration between UK health policy experts and practitioners from UK national health organisations and corresponding institutions, in partner countries. The programme works in Low- and Middle-income Countries (LMIC) to tackle health system bottlenecks defined by country partners, through facilitated multi-directional learning exchanges and effective partnerships. It complements bilateral health ODA and influencing efforts to support national progress towards Universal Health Coverage (UHC).

The programme is implemented by the NHS Consortium for Global Health (NHS Consortium), which is co-hosted by NHS England (NHSE) and the UK Health Security Agency (UKHSA). The NHS Consortium membership consists of a group of NHS Arm’s Length Bodies (ALBs)[1] which provide access to UK-based technical experts via drawdown through a Consortium Technical Advisory Service (CTAS). The UK expertise available includes health workforce planning, education and training; health finance topics including health technology assessment and prioritisation; health service regulation and health security, including public health training. The NHS Consortium Secretariat provides a coordination function and a single point of access to match technical expertise from the UK ALBs with requests from partner countries.
[1] UK Health Security Agency (UKHSA); Office for Health Improvement and Disparities; Public Health Wales; Care Quality Commission (CQC), International Institute for Health and Care Excellence (NICE); Office for National Statistics (ONS); NHS Resolutions; NHS Health Research Authority; Health Services Safety Investigations Body.

Summary supporting narrative for the overall score in this review
The programme scored a B (outputs moderately did not meet expectation). Overall, while delivery performance improved in year 3, output and outcome achievement and evidence of change remain uneven across countries, with stronger results in a small number of partnerships. FCDO programme team have concerns related to monitoring and value for money.

Technical exchanges (output 1) were well received. For example, in Ghana 54 technical exchanges were delivered involving Ghana’s National Health Insurance Authority (NHIA) and focused on strategic purchasing and data analytics. Output 2 partially did not meet expectation. The target for delivery of learning events was achieved; however low survey response rates limited the reliability across some indicators. NHS Consortium reviewed the cross-country webinar series and in year 3 deeper partnership countries were paired for learning exchanges by thematic workstreams. Different national contexts and stages of health system reform, and varying stakeholder requests meant that cross-country learning activity was limited. Output 3 (management) was marginally achieved and is described in Sections C and F.

By the end of year 3, the programme had established partnerships with Ghana focusing on health financing, Malawi on health workforce, the Philippines on primary and ambulatory health care structures, Tanzania on universal health insurance and Zimbabwe on human resources for health. However, programme performance varied across countries, with outcome level results concentrated in Ghana and Malawi (examples of Most Significant Change (MSC) stories below).

All planned HSC programme activities have now been completed, and the programme endline external evaluation was finalised at the end of March 2026 (see annex A for a summary). The evaluation provided useful lessons, which will inform the scoping and design of a future health partnerships offer for FY27/28.

Major lessons and recommendations for the year ahead

Context – operational bottlenecks at the middle-management level (officials carrying out specific reforms) created barriers to delivery even when political will and senior buy-in (e.g Ministerial level) was present. Interventions should be grounded in early political economy analysis and tailored to local cultural, political and operational realities. Given contexts, priorities and personnel can change over time, the programme should be flexible and context‑responsive.

Programme management - delays at multiple stages shortened the time available for implementation and constrained performance. These delays reflected several factors, including the absence of an in‑country delivery partner to enable timely decision‑making and delivery, and the lack of a separate service provider to provide independent challenge and accountability. As a result, accountability for performance and reporting was weakened. Value for money was an issue, with a relatively high proportion of spend on core management costs compared to drawdown of technical expertise through CTAS. Monitoring activity tended to focus on documenting activities and engagements, rather than consistently evidencing outputs, outcomes or progress along reform pathways. In addition, in future programming, greater emphasis should be placed on the selection, preparation and management of technical experts, to strengthen contextualisation, and ensure there are clearer mechanisms to monitor and assess performance.

Learning Intended to be a major focus of the programme, cross country learning was a challenge throughout. In year 3, different national contexts and stages of health system reform, and varying stakeholder requests meant that cross-country learning activity was limited. Mutual learning between participant ministries of health and health institutions, including participant UK institutions was not captured through the logframe. Evidence of mutual learning benefitting the UK has been at the individual level, and more formalised knowledge sharing mechanisms could have improved institutional learning.

Sustainability and impact - rather than expanding geographic coverage, or increasing the number of work-themes, greater impact is likely to result from allowing sufficient time for reform processes to mature, where engagement is aligned with ongoing health system reforms and includes operational roles responsible for implementation, integrating mechanisms continuous improvement and learning. The key ‘ingredients for success’, seen in the evaluation and MSC stories, were continuity of personnel (across all stakeholders), strong country management and in-country FCDO-counterpart relationships, and when the work themes aligned with the priorities of the country partners.

Recommendations in the year 2 Annual Review focused on future options for health partnerships and international engagement by ALBs. This work has been ongoing throughout year 3 and is being taken forward through a small, no-cost extension of the programme.

The main activities under the HSC business case have now been completed. Progress has been mixed. The programme has only just started to generate tangible changes across health systems strengthening priorities, but there have been broader benefits of collaboration, capability development, and learning. This year, the evaluation provided a set of clear recommendations to inform the design of future health partnership activity. These include building on existing UK partnerships where outcomes and delivery success have been demonstrated (notably Ghana and Malawi), maintaining relationships and continuity, and redressing the balance of funding towards technical expertise, in relation to core costs.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The HSC programme aims to contribute to improved coverage of essential services to progress towards UHC in ODA eligible LMICs. There was a single amendment to the Theory of Change (ToC) in year 3, with the removal of output 3 (increased effectiveness of the UK partnership approach) following a recommendation in year 2 to only monitor the effectiveness of the partnership at the outcome level.

The HSC programme aims to contribute to the ToC impact across two high-level outcomes:

- Outcome 1: Successful implementation of national Health Systems Strengthening (HSS) reforms in partner countries, with expertise provided by the NHS Consortium.
- Outcome 2: UK-host country strategic health partnership and relationship strengthened.

Programme activities are two-fold: technical exchanges between UK health experts and institutions and their counterparts in partner countries, and networks for shared learning between and beyond the counterparts involved.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to deliver on Outcome 1 across some deeper partnership countries, most notably Malawi and Ghana. Evidence of adoption against Outcome Indicator 1.1[2] is strongest in these two countries and they accounted for the majority of the 11 adopted policies/tools recorded at programme close. In Malawi, regulatory and workforce reforms progressed from technical engagement in year 2 to formal adoption, including continuous professional development (CPD) policy reform and strengthening of medical regulation processes of the leading national institution. In Ghana, financing and costing tools developed were formally adopted and are being used by the National Health Insurance Authority (NHIA) to inform tariff setting and strategic purchasing reforms.
[2] Number of health policies, strategies, and associated implementation guidelines produced by collaborative efforts between the UK and host countries.

In the Philippines, Zimbabwe and Tanzania, outputs were delivered and fed into ongoing reform processes, but there is no evidence that reforms were formally adopted at the point of this assessment. In Tanzania and the Philippines, progress was slower as a result of factors, including disease outbreaks and political disruption in Tanzania, and natural disasters and significant staff turnover in the Philippines.

Outcome 2: This outcome is more challenging to measure. The partnership survey provided some insights, though its reliability was constrained by a low response rate (cumulative total n=14). MSC stories point to strong relationship‑building, with partnerships seen as a trusted and a low‑risk entry point for engagement, reinforced by the credibility of the NHS brand and a collegiate approach. The programme was valued for supporting global health diplomacy and senior‑level engagement by some and seen as reinforcing trust and positioning the UK as a “credible partner in health”. Discussions with posts where partnerships were better established suggest this is most effective when complementing a bilateral offer (see Country Case Studies below). However, some country examples identify there were missed opportunities to support co-creation and in some instances a lack of contextualisation to national systems and clear explanation of NHS specific terminology.

Country Case Study Zimbabwe: Too early to see tangible changes on health systems strengthening priorities, but broader benefits of collaboration.

‘The partnership model demonstrates that it is possible to achieve development outcomes with limited ODA. UK soft power (respect for British education and institutions, diaspora links), gives us a unique selling point’ HMA, Pete Vowles.

As is the case with any technical collaboration, in-person visits helped relationships with senior government officials. Workforce strategies focusing on non-financial measures such as flexible working, alongside workforce planning to address supply and demand, task shifting, and systems and processes, were effective. Progress on taking forward work on digitising the Human Resource Information System was more challenging – understanding where UK expertise would be most beneficial and tackling bigger constraints (such as Zimbabwe being in the midst of HR IT system transition). Despite this – the type of engagement was well received, as a more equal approach to sharing expertise between the UK and Zimbabwe – demonstrating reciprocity and long-term partnership behind country-led priorities and alignment to national strategies.

Box 1

Box 2

Country Case Study: Supporting Ghana with Strategic Purchasing

Working with National Health Insurance Authority (NHIA) staff through technical knowledge exchange, as they developed Costing Manual (estimates of the costs of health services, tariff setting and pricing in the health systems) and a policy paper on primary care payment models. Methodologies for costing and pricing are now documented and “used daily,” and the NHIA is better able to “disseminate how it aligns tariffs with the true cost of service delivery” and communicate how tariffs are derived. The partnership was described as “smooth, constructive, fruitful, supportive, responsive, and based on mutual respect and mutual learning,” with NHIA ownership central throughout. Importantly, this is one part of a much wider, longer-term partnership between the two countries on Health Financing.

The activities set out in the original business case for the HSC programme (covering the period 2023–2026) have now been completed. An external evaluation has been carried out (see appendix A for summary). A no‑cost extension to the HSC business case has been approved, allowing for a limited interim offer to be delivered during FY26/27. This will enable continuity of engagement in countries which demonstrated evidence of effective partnership, while scoping and planning for a future UK Health Partnership offer is undertaken.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

Based on the evidence from programme performance and the evaluation, there is justification to continue in a reduced number of established deeper partnership countries, where good results were demonstrated and as part of a wider development offer, albeit with a review of the operating model which did not provide good VfM (see Section D). This will require streamlining of NHS Consortium secretariat resourcing and improved governance and reporting. A proposed interim offer will protect the programme’s investments to date and align with the FCDO priority for modern partnerships, providing expertise to support systems so countries are increasingly able to thrive without aid. In parallel, scoping, design and planning will be conducted to deliver a new UK partnership offer in FY27/28.

The xHMG Global Health objectives, the Global Health Ministerial Group and several departments (DBT, HMT, DHSC and FCDO) have agreed the following xHMG health priorities: economic growth, global health security, health systems building, and global health architecture reform. These priorities provide a strong rationale for maintaining and deepening UK engagement in health partnerships and exemplify the four shifts in our approach to development[3].
[3] from “donor” to investor, from service delivery to system support, from grants to expertise, and from international intervention to local provision.

FCDO programme teams propose:

To maintain relationships and continuity, to take forward an interim health partnerships offer in FY26/27, with a focus on fewer, proven partnerships which show opportunities to complement a broader bilateral programme of work and ensure a more streamlined NHS Consortium Secretariat coordination function to maximise value for money. And to carefully consider the most effective and efficient programme management and reporting processes for this interim offer.

Conduct design, scope and planning for a future UK Health Partnership offer commencing FY27/28, in collaboration with the Department of Health and Social Care (DHSC) and other xHMG and country stakeholders.

## C. DETAILED OUTPUT SCORING

Output Title	Development of HSS policy reforms and strategies through UK*-Host country technical exchange
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for Y3	Progress
1.1 Number of health policies, strategies, and associated implementation guidelines produced by collaborative efforts between the UK and host countries	8	13 (moderately exceeded) / Malawi = 5 / Ghana = 8
1.2 Number of technical exchanges between the UK and partner countries.	68	121 (exceeded) / Ghana = 54 / Nepal = 0 / Philippines = 15 / Malawi = 20 / Tanzania = 15 / Zimbabwe = 17
1.3 Proportion of partner organisations reporting that they have applied knowledge and skills through partnership activities and changed work practices	75%	61% (n=23 responses)

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall assessment
Overall, Output 1 (1.1 and 1.2) exceeded year 3 delivery milestones; with strong performance in Malawi and Ghana which offset delivery constraints in other countries.

Indicator 1.1 - performance exceeded the year 3 milestone, with 13 policies, strategies or associated guidelines produced against a target of 8. Delivery was concentrated in Ghana (8) and Malawi (5), reflecting sustained engagement, partner readiness and alignment with active country reform agendas. However, across the full programme period (2023-2026), cumulative delivery fell short of the original target (25 policies, strategies or guidelines, against a target of 32), this reflects slower progress in early years in some countries, and Zimbabwe and Tanzania, selected later in year 2. The results also highlight the extended timelines required for complex system reforms.

Indicator 1.2 - exceeded expectations (to note disaggregated data by type for this indicator was not provided and therefore a broad definition of a ’technical exchange’ should be adopted). In year 3, 121 technical exchanges were completed against a milestone of 68, demonstrating strong demand for UK technical expertise. Ghana accounted for the highest volume (54 exchanges) which reflects the high level of buy-in and interest in delivery from Ghanaian counterparts which resulted in several in-person week-long country visits. Exchanges across countries covered a broad set of HSS themes, including regulation, workforce development, financing, digital systems and policy design. While numbers of exchanges were high, not all exchanges progressed to policy reforms or adoption, reinforcing the importance of sequencing and continuity. Country examples are set out below.

Indicator 1.3 - performance against this indicator was below target. In year 3, 61% of respondents reported applying knowledge and skills gained through partnership activities, against a target of 75%. The output indicator refers to ‘proportion of partner organisations reporting that they have applied knowledge and skills’, whilst the output noted n=23 this refers to individuals with the total number of 9 partner organisations, with 3 of those ALBs (National Institute for Health and Care Excellence (NICE), UKHSA and NHSE) and 6 institutions across 4 programme countries (Ghana, Malawi, Zimbabwe and the Philippines). The low response rate should be considered when interpreting this result and it is noted that the survey does not capture data regarding how the knowledge has been applied. The cumulative three‑year result also remained at 61%. Qualitative evidence from the mutual learning MSC story suggests in some cases that learning uptake occurred, for example in Ghana partnership activities noted that it informed UK benefit package design and co-payment structures, however, translation into changed practice was not evidenced.

Examples of country exchanges

Ghana - 54 technical exchanges focused on strategic purchasing and data analytics with the National Health Insurance Authority (NHIA). The technical exchanges led to the development of tools to aid national health insurance implementation (including costing analysis and templates) and the completion and adoption of the Costing Manual and progress on the review of Tariff Operational Manual. The activities delivered have supported the national free PHC initiative, launched by the President of Ghana, and align with FCDO’s bilateral efforts to support this agenda by the Accra High Commission team.

Malawi – 20 technical exchanges supported activity building on reform design work in year 2 between the UK General Medical Council and the Medical Council of Malawi (MCM) and led to the formal adoption of revised disciplinary procedures, the clarification of fitness‑to‑practice decision thresholds and the roll out of online registration system, strengthening fee collection and the MCM’s financial sustainability. Other workstream outputs included a harmonised national Continuing Professional Development (CPD) Policy, developed and adopted by the Ministry of Health’s Quality Management Directorate (QMD).

Zimbabwe – the health workforce theme supported Government priorities under the Health Workforce Compact (2024-2026). 17 technical exchanges focused on health workforce planning, retention strategies and blended learning approaches. The programme did not deliver outputs against indicator 1.1 reflecting a shorter delivery timeline (due to country selection in year 2 and an extended 6 month scoping period). One work sub-theme was deprioritised after Zimbabwe transitioned its relevant IT system and the timing of national approval processes, affected the adoption of some policies within the programme’s timeline.

Philippines - 15 technical exchanges supported topics of digital health governance and interoperability, and a review of a government ambulatory care pilot. These outputs contributed to ongoing reform discussions and institutional learning but did not result in formal policy or tool adoption. The work faced challenges related to staff turnover and restructuring in the Philippines Department of Health. The evaluation raised questions over how well the NHS was contextualised during technical exchanges - despite the explicit interest from Philippines counterparts to learn from the UK model - some reported that the relevance was not clear.

Tanzania - 15 technical exchanges were completed on health financing sub-themes including national health financing structures, information systems and innovation, evidence-base decision making and clinical guidelines. Delivery was constrained by political disruption, disease outbreaks and changes in government priorities and work on health system resilience was discontinued in late 2025. Technical exchanges, due to political disruption, were substituted by pre-recorded sessions made available through the NHS Futures online platform.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during year 3 of the programme. A review of the programme log frame will be required prior to any new activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key lessons from year 2 highlight that each country context is different, barriers to work can arise that require the NHS Consortium to be agile, and that moving from scoping to workplan sign-off took considerable time and effort. In addition, it was recognised that the programme demands a high level of effort from the FCDO focal points in country, impacting VfM. These lessons continued to be experienced in year 3. Higher targets under this output were achieved in Ghana and Malawi (year 1 countries).

Following a year 2 recommendation a review of country workplans was conducted, which aimed to reduce or close workstreams or country engagement considered unlikely to achieve intended outcomes. The review resulted in a reduced number of workstreams and work in Nepal was closed in April 2025, which supported the NHS Consortium to focus greater efforts on the remaining countries.

Recommendations for the year ahead are listed in section A.

Output Title	Enhanced cross-country knowledge sharing and learning on HSS best practices and innovations.
Output number:		2	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for Y3	Progress
2.1 Number of learning network events conducted	8	8 (met expectation)
2.2 Proportion of learning events participants who rate the quality of the event as informative/useful (both in-country and regionally)	90%	100% (n=4) / (not scored due to low response rate)
2.3 Degree of health institutions’ implementation of relevant lessons and best practices in their HSS efforts following their participation in knowledge platforms (either in-country or regional)	Average score of 3.2	Average score of 3.53 (n=15 participants)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output partially did not meet expectation, scoring a B. While the target for delivery of learning events (output 2.1) was achieved, performance against outputs 2.2 and 2.3 was constrained by low response rates reducing the reliability of results.

Indicator 2.1 - Following last year’s recommendation to review and improve on the approach to cross country learning, this year countries were paired based on technical themes. This allowed countries to learn from each other, with some efficiency gains related to CTAS and NHS Consortium resourcing. This wasn’t always compatible, for example Ghana and Tanzania both worked on digital health transformation, but Tanzania stakeholders requested that sessions were focused on foundational knowledge, while Ghana requested more advanced learning. Examples of sessions delivered in year 3 included:

- Two Technology Enhanced Learning and blended learning sessions with Malawi and Zimbabwe attendees, which included e-learning approaches and best practice.
- Workforce Planning and Management sessions led by NHSE and World Health Organization (WHO) were delivered for Zimbabwe attendees, with participation from Malawi and the Philippines.
- A Digital Transformation session, which convened representatives from Ghana’s NHIA, Tanzania’s MoH and NHSE to share practical lessons on digital health reform.
- A cross-country learning and reflections session bringing together colleagues from the Philippines, Malawi and UK.
Indicator 2.2 - A third of respondents reported limited application of learning and a third a broader application of their learning. But the very low response rate for this indicator (4 respondents across 8 events, with a cumulative total of 10 respondents across 15 events, from a total of 342 participants) means it is hard to interpret. A separate survey of the cross-country learning series conducted by NHS Consortium found that 72% of respondents reported “no implementation, discussion only, or limited application” from the learning series webinars they attended (but again, this was a low response rate, from a survey of 11 respondents drawn from the UK, Philippines, Nepal, Malawi, and Zimbabwe).

Indicator 2.3 - data for this indicator was collected using a scaled question designed to assess the extent to which participating institutions applied the knowledge and best practices shared through the learning sessions. Participants rated knowledge uptake and application using a five-point scale (1 = No Implementation to 5 = Full Integration and Active Collaboration), indicating how far insights from the learning sessions had contributed to ongoing health system strengthening reforms. The average score across respondents was 3.53 out of 5, suggesting a moderate level of uptake. However, the reliability of this finding is limited by a low response rate and delays to data collection, which began in June 2025. In addition, NHS Consortium noted the challenges in isolating the contribution from learning events, versus the in-country technical exchanges, which were delivered in parallel.

Describe any changes to this output during the past year, and any planned changes as a result of this review. There were no changes made to this output in year 3.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As noted above, in response to the year 2 recommendation that the NHS Consortium undertook a review at the end of the five-part webinar series to inform the programme’s cross‑country learning objectives, the programme adjusted its delivery of the learning approach in year 3.

The recommendation for the coming year is to review the programme logframe with the option to remove this output during delivery of the interim partnerships offer FY26/27. The evidence in the evaluation noted that the learning component of the programme proved difficult to implement with many aspects of the early ambition set out in NHS Consortium Learning Strategy (Jan 2024) significantly scaled-back.

Output Title	Effective management of the Health System Connect
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for Y3	Progress
3.2 Country selection and workplans agreed	Evidence of implementation of agreed country workplans	Partnership delivery across 5 countries* completed
3.3 Effectiveness of the coordination roles and responsibilities undertaken by the leadership and management body in the partnership	4	4.56 (n=9) / (partnership assessment survey data from partners in Ghana, Zimbabwe and Malawi)
3.4 Percentage of Strategic Advisory Board (SAB) meeting actions/ recommendations actioned within 2 months	Average of 90% of recommendations actioned within 2 months	83% of SAB recommendations actioned within two months.
3.5 Percentage of rapid response requests "fulfilled" within 30 days	90% of rapid response request approved within 30 days	100% (1/1) / Botswana RR request timeline achieved. Note the RR did not proceed.
3.6 Programme MREL tools and approaches agreed, and endline evaluation completed	1 programme review with Evaluation Partner / 3 Quarterly progress review with FCDO completed. / Endline evaluation completed and recommendations agreed.	1 Programme Review meetings held with CADMUS / 3 quarterly progress review meeting and 1 final reporting meeting with FCDO held / Final report received end of March.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme broadly met expectation under this output, scoring an A.

Two new deeper partnerships (Tanzania on universal health insurance and in Zimbabwe on and human resources for health) in year 2 had workplans approved by FCDO in April year 3.

There is positive survey results related to the coordination roles and responsibilities, although responses are exclusively from the stronger partnership countries (Ghana, Malawi and Zimbabwe) which could imply self-selection bias, and a small sample size means this should be interpreted with caution.

There was one referral for rapid response from Botswana that was progressed to concept note stage in year 3 which met the timeline; however, the request was withdrawn and did not proceed due to availability of country stakeholders.

In year 3 the second learning cycle was completed with the external evaluation partner in July 25, which served as an opportunity to review programme performance, agree on the overall evaluation framework and methodology, and on the scope for the evaluation deep dive countries.

Describe any changes to this output during the past year, and any planned changes as a result of this review. Minor changes to the definition for output 3.5.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

The recommendation for NHS Consortium to reduce the time spent on scoping, and review and close out any workstreams and activities that were unlikely to achieve intended outcomes, with a view to maximise the impact of country activities in year 3, was implemented. Several areas of work and the Nepal programme were closed in April 2025. Limited output-level result were achieved in Nepal prior to activities closing, this was a result of delays due to a long scoping period, capacity constraints for in-country support, and the country context, where the delivery is focused on the sub-national level, and requires a higher proportion of in-country versus virtual engagement.

The recommendation to actively promote the rapid-response delivery component was implemented through several updates [short presentations and by emails] to the FCDO network during year 3. Despite some initial interest (from Uzbekistan and Botswana), this did not materialise due to the availability of stakeholders.

The recommendation to strengthen M&E through case studies and accelerated data collection was partly addressed. MSC stories were completed, some in time to contribute qualitative evidence to the endline external evaluation. Quantitative data collection was more uneven, with low response rates noted across all survey results.

Recommendations for the year ahead are set out in section A.

## D: VALUE FOR MONEY

Key cost drivers and performance

Economy was demonstrated across the CTAS day rate, which is lower than the average market rate (approx. av £657/day - approved in year 3 forecasting review). In year 3, experts with higher (than market average) rates have been deployed for some interventions. From a sample of 131 technical experts deployed in year 3 (set out below) most experts are deployed in the mid to senior level. Commercial benchmarking, against FCDO roles and external global health contractors commissioned by FCDO, evidence that the NHS day rates offer VfM at the lower to average mid band but not at the higher level, therefore the VfM of the CTAS drawdown in year 3 appears good. The evaluation highlighted that the selection of CTAS should consider softer skills as well as experience working with or in the partner country, which may provide opportunities for more junior and mid-level staff involvement.

Grade level	Day rate range	Percentage
Mid to Senior Level	£316-£549	65%
Director Level	£550-£760	25%
Senior Executive	£761-£967	10%

The ratio of core NHS Consortium Secretariat costs (programme management and in-house technical health advisers 68%) to CTAS (23%) did not demonstrate good VfM.

The NHS Consortium in-house technical health advisers were expected to provide a mix of core support and technical advice to countries, but primarily provided core support: coordinating, relationship management and knowledge brokering between the UK technical experts and country partners and institutions. This meant the ambition was not met for this resource to provide any technical drawdown assistance. Future programming should streamline centralised management functions to improve the ratio of core costs to CTAS and avoid senior technical experts providing logistical support.

Efficiency gains were observed where the programme complemented other FCDO or HMG investments and through remote modalities (for example the Malawi General Medical Council–Medical Council of Malawi partnership was fully online). The centralised “one‑stop shop” model supported coordination and simplified access to UK expertise. However, efficiency was constrained by lengthy country selection, scoping and workplan approval processes, which reduced the delivery window for implementation. The demand‑led CTAS model also relied on goodwill and availability within UK institutions, highlighting the need for more formalised institutional engagement with ALBs in future offers. A demand-led model requires standing capacity within what are primarily domestic departments.

Effectiveness varied across countries. In Ghana, interventions were well aligned with government priorities and context, with co‑produced tariff and costing tools influencing NHIA financing reforms. Elsewhere, effectiveness was weaker, with evaluators identifying insufficient contextualisation of NHS experience in some countries (notably the Philippines and Nepal), alongside challenges in translating short technical exchanges into sustained reform outcomes. In the Philippines some CTAS delivered presentations designed for NHS audiences, and some participants found that the relevance to their government systems and NHS specific terminology not well explained. In future, CTAS should receive an overview of the partner government’s culture and national health system prior to deployment.

Equity and gender considerations were applied in the design and during workplan development. However, this is reflected more through alignment with health systems strengthening and support of UHC principles, but systematic application was limited. While the programme included a VfM indicator related to equity‑focused reforms, disaggregated data was not provided by NHS Consortium and the logframe did not include a specific equity indicator, limiting the ability to robustly assess equity impacts.

Sustainability can only be assessed partially given the programme timeframe. Prospects were strongest where reforms were embedded within institutions and aligned with ongoing national processes (notably Ghana and Malawi). In other countries, outputs had not translated into adopted policies, tools and strategies (outcome 1.1) by programme close. Evidence of sustained partnership relationships (Outcome 2) and institutional learning beyond individuals was limited. The partnership survey did not achieve a representative response rate and evaluators considered that the survey ‘served more as a barometer to make sure HSC interventions were being well received’. The sustainability ambition of the shared cross country learning networks has not been realised, however learning products from these sessions are available through the NHS Futures Platform and can be accessed beyond the end of the programme.

As set out in section A, an option is being considered to take forward interim health partnerships offer, which will support sustainability of interventions across some countries. This interim offer will run parallel to the scoping and design of a potential UK health partnerships offer from FY27/28.

E: RISK

Overview of risk management

There has been no change to the overall risk rating in year 3 which remains “Moderate”. FCDO updates its risk register quarterly, informed by progress updates from the implementing partner, any changes to operational context, quarterly reports and the programme’s strategic and advisory board. Risk categories for the programme remained within the Directorate risk appetite. The lead partner of the NHS Consortium (NHSE) is a Government ALB and subject to grant functional standards (a set of guidelines for the management of grants administered by Government departments and ALBs). The programme has no downstream delivery partners and does not directly work with vulnerable or marginalised groups. Therefore financial, fiduciary, and safeguarding risks are considered low. No safeguarding or financial risks have been reported during year 3. The climate and environment risk for the programme remained low and reflects the assessment as set out in the programme’s business case.

A strategy and context risk relating to changes in UK Government and priorities has been monitored in year 3. Whilst the ongoing merger between DHSC and NHSE has not impacted delivery this requires continued monitoring as it will be a factor in decision-making regarding a future UK health partnership model.

A further strategy and context risk, related to changes in political context in partner government or changes in government priorities, such as change in political leadership, was specifically noted following political unrest in Tanzania. This resulted in communications challenges with key stakeholders and led to delays in delivery of planned technical exchanges, with some exchanges recorded as webinars and uploaded to NHS Future Platform. NHS Consortium are not able to track if stakeholders have engaged with this content online.

Operational and programme delivery risks related to resourcing and capacity across FCDO focal points in partner countries to facilitate country level influencing, and peer-to-peer technical partnerships with stakeholders, has been monitored throughout the programme lifecycle. In year 3 this was considered as a contributing factor (amongst others) in the closure of the Nepal programme in April 2025.

A further capacity risk was monitored in year 3 in relation to availability of technical experts and capacity of ALBs. In year 2 the Care Quality Commission (CQC) paused their membership contribution due to capacity constraints, this pause continued throughout year 3. NHS Consortium mitigated this through drawdown of alternative ALBs. However, a key point, referenced above under efficiency, sets out that draw-down of technical experts, in a demand-led model, requires standing capacity for international work to mitigate this risk and that the programme ultimately relied on the goodwill of managers to release staff.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Governance
This investment is governed through a Memorandum of Understanding (MoU) with NHS-England, which co-hosts the NHS Consortium Secretariat. The governance and decision-making structures remain as laid out in the management case of the business case, with NHS Consortium accountable to the FCDO through quarterly requirements (a change from business case approval from six-monthly, which aligns with payment schedules).

A Strategic Advisory Board[4] met twice in year 3 with a focus to provide strategic advice and a challenge function to the programme.
[4] Strategic Advisory Board Membership included: xHMG FCDO, DHSC, UKHSA, NHSE Senior Leadership and external advisory members - WHO health technical and Senior Parliamentarian with Global Health expertise.

Finance
The main cost drivers for the programme are staffing and technical assistance costs. Programme payments are made in arrears, following FCDO’s receipt of quarterly payment reports and narrative updates. Forecasting in year 3 has met the requirements of 95% forecast accuracy as set out in the MoU. Total underspend for the programme in year 3 in relation to NHS Consortium costs (core NHSC resource, CTAS, travel and delegation hosting) is circa 0.1% from the year 3 budget allocation, an improvement, following significant underspends in year 1 and 2. At the end of year 3, NHS Consortium (NHSE) spent 61% of its original budget.

The overall spend at the end of year 3 is outlined in the table below.

Year	NHS Consortium (NHSE) spend
1	£302,988
2	£745,125
3	£743,534
Total	£1,791,647

Programme Management
The NHS Consortium Secretariat (programme management and in-house technical health advisers) was resourced by a core team of eight staff (5.5 FTE).

In year 2 the quality of NHS Consortium reporting was identified as an area for improvement. Reports had to be resubmitted due to inaccuracies and inconsistencies. This improved in year 3, with timely and structured adherence to quarterly governance and reporting processes, however there were some elements of bias in self-monitoring and reporting (highlighted in the independent evaluation), with delays in data collection, and disaggregated data was not provided for all programme indicators (further details in Section G).

The latest NHSE annual financial reports were published on October 2025 (NHS England: annual report and accounts 2024 to 2025 - GOV.UK). FCDO is confident that NHS Consortium has taken the necessary precautions to avoid and protect against all forms of financial mismanagement and fraud, with anti-Fraud and Corruption policy.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation, Evidence and Learning

External evaluators (CADMUS) supported the programme design and delivery of Monitoring, Reporting, Evaluation and Learning (MREL) through structured learning cycles and an endline evaluation[5]. Learning cycles took place September 2024, March and July 2025. These cycles sought to strengthen the programme’s theory of change, logframe, and use of monitoring tools.
[5] The evaluation undertook in‑person fieldwork in Ghana and the Philippines, alongside remote interviews with stakeholders in Zimbabwe, Nepal and Pakistan.

While a range of monitoring tools were introduced, implementation was uneven. Monitoring activity tended to focus on the delivery of activities and engagements, rather than consistently evidencing outputs, outcomes, or progress along reform pathways. Several monitoring tools were not implemented to schedule, and delays in data collection led to low response rates, particularly for surveys intended to evidence learning uptake and effectiveness of the partnership.

In some cases, tools recommended by evaluators (including partnership surveys and reform journey mapping) were not applied consistently as designed, limiting the robustness and comparability of findings. Monitoring coverage was strongest in more mature and better-performing partnerships (notably Ghana and Malawi), with more limited data from other countries, reducing confidence in cross-country assessment.

The quality of evidence is mixed and across some indicators is constrained by small sample sizes and reliance on self-reported data. Qualitative evidence (including MSC stories and evaluator interviews) provide further insights into results achieved in some contexts, however evidence of outcome-level change is concentrated in a small number of countries.

To support the annual review, FCDO consulted senior representatives from programme partners and stakeholders across HMG (DHSC, NHSE, UKHSA) to gather insights and reflections on year 3 progress and recommendations for the interim partnership offer in FY26/27. In addition, FCDO consulted focal points in-country to support review of delivery progress and reporting documents (such as the MSC stories), as required.

The evidence generated from the evaluation has already fed into the planning for the interim health partnership offer and will be a key source of evidence used in the planning and scoping of a future UK heath partnership offer in FY27/28.

Date of last narrative financial report	March 2026	Date of last audited annual statement	NHSE last audited statement Oct 2025

ANNEX A:

Health Systems Connect (HSC): Endline Evaluation – summary

HSC programme (2023-2026) provided demand‑led technical assistance to partner governments via UK health experts across three modalities: deeper partnerships, rapid response, and cross‑country peer learning, with the aim of supporting health systems strengthening (HSS) and progress towards Universal Health Coverage (UHC).

Purpose and method

The independent endline evaluation assessed programme effectiveness, efficiency, alignment with partner and UK priorities, sustainability, equity, and value for money. Given the short implementation period and complex policy reform pathways, the evaluation used theory‑based methods, including realist evaluation, process tracing, and outcome harvesting. Fieldwork was conducted in Ghana and the Philippines, with remote data collection in Zimbabwe, Nepal, and Pakistan.

Key Findings
1. Programme achievements and impact
- HSC met or was on track to meet some outcome targets, but results were unevenly distributed, with the strongest adoption of outputs in Ghana and Malawi.
- 11 policy tools or reforms were adopted, notably in professional regulation and health financing; however, broader system‑level impacts (e.g. UHC index changes) could not yet be evidenced due to timing.
- Success was strongly associated with government buy‑in, continuity of key personnel, contextual understanding, and partner system capacity.

2. Alignment and partnership quality
- Interventions were well aligned with partner government priorities and widely praised for a peer‑to‑peer partnership model.
- The programme aligned well with the UK’s shift towards partnership‑based ODA.
- Cross‑country learning was valued but showed limited evidence of application beyond discussion, in most cases.

3. Efficiency and delivery model
- The centralised ‘one‑stop shop’ model for deploying NHS expertise was efficient in principle, but lengthy country selection and approval processes reduced the effective delivery window.
- Rapid response interventions were highly effective and catalytic but under‑used.
- The model worked best where delivery was tailored to political and operational realities and supported by in‑person engagement.

4. Sustainability
- It was too early to assess sustainability directly, but prospects were strongest where reforms were embedded in institutions, backed by leadership, and supported by ongoing relationships (notably Ghana).
- Sustainability of more complex reforms remains conditional and likely to require continued support and follow‑up beyond short engagements.

5. Equity and inclusion
While equity and gender were acknowledged conceptually (linked to UHC), systematic application and monitoring were limited.

6. Value for money
- HSC represented good economy compared to large bilateral HSS programmes, leveraging UK public‑sector expertise at relatively low cost.
- However, programme management costs outweighed technical deployment costs, and effectiveness was constrained by the light‑touch, non‑embedded delivery model.

Headline recommendations
1. Move towards a joint cross‑government management model for future partnerships.
2. Select realistic, deliverable reforms and map required external financing and support upfront.
3. Strengthen contextual preparation and soft‑skills requirements for deployed experts.
4. Formalise institutional engagement with UK ALBs, not just individuals.
5. Prioritise continuity of personnel and minimise gaps between programmes.
6. Simplify country selection, build on existing partnerships, and pilot new countries via rapid response.
7. Streamline central management costs to improve the ratio of spend on technical assistance.