## Template
Note 1) Due to the adaptive nature of the programme, these indicators are indicative and may change, particularly for Components 2-4 where the activity will mostly take place in Year 2 and beyond.
Note 2) Some indicators are likely to deteriorate regardless of this programmes work (e.g. healthcare sector emissions). We are consulting partners to establish effective metrics and measurements for success.
Note 3) in the Logframe agreed in November 2023, monitoring indicators for Component 4 on air quality have been developed following the progress on scoping work and will be further developed as this work reaches completion in Years 1. [PREVIOUSLY: Note 3) Monitoring Indicators for Component 4 on air quality will be developed once scoping work has been conducted (Year 1)]
PROJECT TITLE | Climate and Health Programme #301532
IMPACT | Impact Indicator 1 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
Reduction in the number of preventable deaths from the health impacts of climate change | Under 5 mortality rate (per 1000 births) | Planned | 38.9 (2021 figure)
Achieved
Source
WHO Reporting on U5 Mortality: https://apps.who.int/gho/data/node.main.CHILDMORTUNDER5?lang=en
| Impact Indicator 2 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Global maternal mortality ratio | Planned | 223 (per 100,000 live births), 2020 figure
Achieved
Source:
WHO Data on Maternal Mortality: https://data.who.int/indicators/i/AC597B1
SDG indicator 3.1.1
| Impact Indicator 3 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Number of deaths attributed to disasters | Planned | The average disaster mortality stood at 47,337 in absolute terms in 2015-2021
Achieved
Source:
SDG indicator 13.1.1
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments | Assumptions
Improved international cooperation and dialogue at the intersection of climate and health | Number of countries who are members of ATACH and signed up to one (or both) of the COP26 Health Commitments. | Planned | 70 | 75 | 85 | 100 | Milestones are cumulative
Achieved
Source
WHO ATACH membership
| Outcome Indicator 1.2 |  | Baseline: September 2023 | Milestone #1 September 2024 | Milestone #2 September 2025 | Target September 2026 | Comments
| High-level ATACH meetings are successful and meet their objectives. | Planned | 1 (WHA76) | COP28 and Global Meeting | WHA and COP29 Meetings | Annual Meeting/COP30 | Qualitative reporting based on participant feedback will be used to complement milestone reporting
Achieved
Source
ATACH reporting
OUTCOME 2 | Outcome Indicator 2.1 (Previously Outcome Indicator 2.3) |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
Climate resilient and low carbon sustainable health systems | 2 | Planned | 0 | 2 | 2 | 4 | Outcome level indicators that are disease and shock related will be difficult to identify and set realistic milestones for as there is limited data available with forecasts. This Outcome will therefore be supplemented with narrative reporting.
|  | Achieved |  |  |  |  | The milestones relate to the bilateral projects, to be captured via project reporting and to wider impact via the WB and ATACH, to be covered in the Global Survey Milestones are cumulative
Source
Project reporting
ATACH Reporting
| Outcome Indicator 2.2 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Number of countries with increased capacity on healthcare sector greenhouse gas emissions through baseline measures of carbon footprint of healthcare system and action plans (process indicator for early stages of the programme) | Planned | 0 | 0 | 1 | 1 | Milestones are cumulative
Achieved
Source
Project reporting from Posts and World Bank Reporting
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
Increased international investment in building climate resilient and low carbon health systems | Number of low-and-lower-middle-income countries that report receiving international funds for health and climate change work | Planned | 28% (2021 figure) | 30% | 33% | 37%
Achieved
Source
WHO Health and Climate Change Survey Report
| Outcome Indicator 3.2 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Public finance committed for adaptation in the healthcare sector | Planned | 2,172m USD (2021 figure) | > Baseline | > Baseline | > Baseline
Achieved
Source
OECD DAC - https://public.tableau.com/views/Climate-RelatedDevelopmentFinanceProvider2021/CRDFDP?:language=en-US&publish=yes&:display_count=n&:origin=viz_share_link&:showVizHome=no#1
OUTCOME 4 | Outcome Indicator 4.1 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
More countries address the health impacts of air pollution through national planning efforts. | Number of countries that develop/update air quality management plans, with health impacts included. | Planned | TBC
Achieved
Source
CCAC reporting
INPUTS (£) | FCDO (£) |  | Govt (£) 4.3 million | Other (£) 4.5 | Total (£) 6.5 | Total (£) 6 | Comments
These figures are Annual (not cumulative)
INPUTS (HR) | FCDO (FTEs)
Note 4) we are discussing suitable metrics for tracking international public finance for low carbon health systems with partners.
OUTPUT 1 | Output Indicator 1.1 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments | Assumptions
ATACH Secretariat operational and able to demonstrate impact, expand reach, monitor and report progress IMPACT WEIGHTING: 20% | ATACH core roles recruited and in place | Planned | 0 | All core roles recruited | Restructure roles to meet evolving demands | TBD
Achieved
Source
ATACH reporting
| Output Indicator 1.2 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Robust ATACH workplans in place and being delivered | Planned | None | Satisfactory progress across all workplans evidenced in reporting; and new strategy and plans for evolving structure agreed | New workplan and structure to be in place and delivering on objectives | Delivery of the actions in the workplan | These milestones will be complemented by narrative reporting.
Achieved
Source
ATACH reporting
| Output Indicator 1.3 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Core products finalised and available to ATACH members, including online live hub populated with key products to facilitate in country work on climate and health | Planned | ATACH website live, but with no information sharing hub | Guidance developed on 'No Regret' interventions. Online hub live with existing V&A assessments / HNAPs accessible. First wins library available to access.Overall indicator framework and draft indicators agreed at national (health system) level. | Online live hub populated with key products. Annual C&H global progress report and recommrndations. Key indicators developed and agreed at sub-national level. | Key indicators developed and agreed at all three levels including health-care facility level. | Community of practice will be reflected in the milestones, and key products from the workplan when they are agreed for 2025 and 2026
Achieved
Source
ATACH reporting
| Output Indicator 1.4 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Number of knowledge sharing and best practice sharing events | Planned | 0 | 1 - global meeting (March 2024) | > 3 | > 3 | Milestones are cumulative
Achieved
Source
ATACH reporting
INPUTS (£) | FCDO (£) |  | Govt (£) 1.5 million | Other (£) 2 milion | Total (£) 1.5 million |  | Comments
|  |  |  | £1.5 million is confirmed. £0.5 million is 'At Risk' | Confirmed |  | These figures are Annual (not cumulative). Financial support from the Netherlands government (amount unknown) In Kind support from Spain for the Global Meeting (venue etc.)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments | Assumptions
Countries assess vulnerability and build the resilience of their health system to climate impacts and shocks, and to reduce health sector emmisisons, with support from the UK IMPACT WEIGHTING: 30% | Number of countries supported to conduct a climate change and health vulnerability and adaptation assessment | Planned | 0 | 2 | 4 | 5 | Milestones are cumulative
Achieved
Source
Project reporting: Bilateral Component and Funding Multilateral Partner (HSRTF)
| Output Indicator 2.2 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Number of countries supported to reflect and consider health impacts in their National Adaptation Plans and/or climate adapation and resilience in health reform plans | Planned | 0 | 1 | 2 | 2 | Milestones are cumulative. Milestones updated in light of the ODA cut to 0.3% of GDP announcement.
Achieved
Source
Project reporting: Bilateral Component and Funding Multilateral Partner (HSRTF)
| Output Indicator 2.3 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Percentage of ATACH Member countries that have submitted vulnerability and adaptation assessments, and plans to adapt and build climate resilience of their health systems (including HNAPs, health components of NAPs and health reform initiatives) | Planned | 0% | 30% | 40% | 50% | A contract will be raised with the developers the ATACH Community of Practice website, in the second quarter of 2024 for the next phase of development and will include a repository for national documents, including HNAPs, V&As, and emissions reductions plans.
Achieved
Source
ATACH Reporting
| Output Indicator 2.4 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Percentage of ATACH Member countries that have submitted documentation and plans for decreasing carbon emissions and climate sustainability of their health systems | Planned | 0% | 30% | 40% | 50% | A contract will be raised with the developers the ATACH Community of Practice website, in the second quarter of 2024 for the next phase of development and will include a repository for national documents, including HNAPs, V&As, and emissions reductions plans.
Achieved
Source
ATACH Reporting
INPUTS (£) | FCDO (£) |  | Govt (£) 2.8 million | Other (£) 2 milion | Total (£) 4.5 million | Total (£) 4.2 million | Comments | Assumptions
These figures are Annual (not cumulative).
INPUTS (HR) | FCDO (FTEs)
Note 5) Country-specific metrics will be developed for each element of technical assistance provide
OUTPUT 3 | Output Indicator 3.1 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
Countries have demonstrable increased access to finance for implementation of climate and health action, on mitigation and adaptation measures IMPACT WEIGHTING: 30% | Number of countries with UK support that have access to climate finance (including UK ICF) for adaptation and mitigation measures within the health sector | Planned | 0 | 2 | 4 | 5 | Milestones are cumulative
Achieved
Source
Project reporting, further measures TBC
| Output Indicator 3.2 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Number of countries with UK support that have access to finance via mulltilateral agencies and banks for climate and health adaptation and mitigation measures | Planned | 0 | 2 | 4 | 5 | Milestones are cumulative
Achieved
Source
Project reporting, further measures TBC
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | Comments | Assumptions
This Output will be a result of input recorded in Outputs 1 and 2
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline: May 2024 | Milestone #1 August 2024 | Milestone #2 August 2025 | Target September 2026 | Comments
Countries access support to integrate air pollution in their health planning IMPACT WEIGHTING: 20% | Number of countries that access capacity building workshops on air pollution and its impacts on health via the AQMx platform and its associated Techincal Advisory group. | Planned | No platform/guidance | No platform/guidance | 50 | 80
Achieved
Source
CCAC reporting
| Output Indicator 4.2 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Number of LMICs using the platform in their national planning processes for air quality management | Planned | 0 | 0 | 40 | 60
Achieved
Source
CCAC reporting
| Output Indicator 4.3 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Number of countries supported by the CCAC to integrate air pollution into its health planning | Planned | 0 | 0 | 8 | 10 | This includes countries supported under vehicles projects, but also those directly engaged in the ACAP Ghana meeting and subsequent national planning activities supported by CCAC/SEI under ACAP funding. Namely, this includes the champion countries Morocco (counted already in HDVE funding), Ghana, Madagascar, Kenya, Cote d'Ivoire, and South Africa. CCAC Sec is additionally providing direct support to South Africa to develop a briefing note on air quality and health for the G20 following their request for support to UNEP.
Achieved
Source
CCAC reporting and Relevant FCDO Post Reporting
| Output Indicator 4.4 |  | Baseline: September 2023 | Milestone #1 September 24 | Milestone #2 August 25 | Target September 2026 | Comments
| Number of countries supported by the CCAC to reduce short-lived climate pollutant emissions | Planned | 0 | 0 | 3 | 3
Achieved
Source
CCAC reporting and Relevant FCDO Post Reporting
INPUTS (£) | FCDO (£) |  | Govt (£) 0.4 million | Other (£) 0 | Total (£) 0 | Total (£) 0 | Comments
These figures are cumulative
INPUTS (HR) | FCDO (FTEs)

## Change frame
Serial No. | Logframe Section (Updated) | Updated (Include the new text here) | Logframe Section (Previously) | Agreed Previously | Rationale for Update | Date Actioned | Suggested By | Notes
1 | N/A | N/A | N/A | N/A | N/A | 2024-05-14 |  | New column added to capture nuance that cannot be captured elsewhere under the Indicators and milestones.
2 | Baseline Milestones; Milestones #1; Milestones #2 and Target September 2026 | Baseline set at September 2023 and Milestones #1 set to September 2024; Milestones #2 set to August 2025 and Target set to September 2026 following annually from that. | Baseline Milestones, Milestones #1 and #2 and Target July 2026 | Baseline was July 2024; milestones #1 July 204; Milestones #2 June 2025 and Target were July 2026 | Baseline updated to September 2023 as the Business Case was approved in September 2023. The subsequent annual milestones were therefore also updated to be in line with this. | 2024-05-14
3 | Impact Indicator 1 Baseline September 2023 | 38.9 (2021 Data) | Impact Indicator 1 Baseline July 2023 | 38 (2021 data) | Inaccurate data | 2024-05-14
4 | Impact Indicator 1 Milestone#1 |  | Impact Indicator 1 Milestone#1 | 35 | Inaccurate projection. Data not available. | 2024-05-14 |  | Data is not available for estimated reduction in under-5 mortality globally. It will also not be possible to measure a reduction in this number as a result of this programme.
5 | Impact Indicator 1 Milestone#2 |  | Impact Indicator 1 Milestone#2 | 30 | Inaccurate projection. Data not available. | 2024-05-14 |  | Data is not available for estimated reduction in under-5 mortality globally. It will also not be possible to measure a reduction in this number as a result of this programme.
6 | Impact Indicator 1 Target September 2026 |  | Impact Indicator 1 Target July 2026 | 25 | Inaccurate projection. Data not available. | 2024-05-14 |  | Data is not available for estimated reduction in under-5 mortality globally. It will also not be possible to measure a reduction in this number as a result of this programme.
7 | Impact Indicator 2 Milestone#1 |  | Impact Indicator 2 Milestone#1 | 220 | Inaccurate projection. Data not available. | 2024-05-14 |  | Data is not available for estimated reduction in maternal mortality globally. It will also not be possible to measure a reduction in this number as a result of this programme.
8 | Impact Indicator 2 Milestone#2 |  | Impact Indicator 2 Milestone#2 | 200 | Inaccurate projection. Data not available. | 2024-05-14 |  | Data is not available for estimated reduction in maternal mortality globally. It will also not be possible to measure a reduction in this number as a result of this programme.
9 | Impact Indicator 2 Target September 2026 |  | Impact Indicator 2 Target July 2026 | 175 | Inaccurate projection. Data not available. | 2024-05-14 |  | Data is not available for estimated reduction in maternal mortality globally. It will also not be possible to measure a reduction in this number as a result of this programme.
10 | Impact Indicator 1 Source | WHO Reporting on U5 Mortality: https://apps.who.int/gho/data/node.main.CHILDMORTUNDER5?lang=en | Impact Indicator 1 Source | WHO reporting on U5 mortality stats | Incomplete entry | 2024-05-14
11 | Impact Indicator 2 Source | WHO Data on Maternal Mortality: https://data.who.int/indicators/i/AC597B1; SDG indicator 3.1.1 | Impact Indicator 2 Source | SDG indicator 3.1.1 | Incomplete entry | 2024-05-14
12 | Outcome Indicator 1.2 (Milestone#1) | COP28 and Annual meeting | Outcome Indicator 1.2 (Milestone#1) | 2 (COP28/Annual meeting) | Presentation/proofing error | 2024-05-14
13 | Outcome Indicator 1.2 (Milestone#2) | WHA and COP29 Meetings | Outcome Indicator 1.2 (Milestone#2) | TBC | Milestones defined because the ATACH Secretariat has now been set up and is fully functioning. Therefore, milestones are clearer. | 2024-05-14
14 | Outcome Indicator 1.2 (Milestone Target September 2026) | Annual Meeting/COP30 | Outcome Indicator 1.2 (Milestone Target July 2026) | TBC | Milestones defined because the ATACH Secretariat has now been set up and is fully functioning. Therefore, milestones are clearer. | 2024-05-14
15 | N/A | N/A | Outcome Indicator 2.1 | Vulnerability of low and medium income countries to mosquito-borne disease (dengue) | Outcome level indicators such as disease and shock related will be difficult to identify and set realistic milestones for as there is limited data available with forecasts. This Outcome will be supplemented with narrative reporting. | 2024-05-14 |  | Outcome Indicator Deleted
16 | N/A | N/A | Outcome Indicator 2.2 | Countries' level of detection, preparedness, and response to health emergencies | Outcome level indicators such as disease and shock related will be difficult to identify and set realistic milestones for as there is limited data available with forecasts. This Outcome will be supplemented with narrative reporting. | 2024-05-14 |  | Outcome Indicator Deleted
17 | Outcome Indicator 2.1 | Number of countries with increased capacity in health sector adaptation and resilience through vulnerability & adaptation assessments and new HNAPs and other technical assistance (process indicator for early stages of the programme) | Outcome Indicator 2.3 | Increased capacity in health sector adaptation and resilience through vulnerability & adaptation assessments and new HNAPs (process indicator for early stages of the programme) | Added detail to capture activity via components other than just the technical assistance via bilateral and MDTF support. | 2024-05-14 |  | The reference number also updated from 2.3 to 2.1.
18 | Outcome Indicator 2.2 (Milestone #1) | 0 | Outcome Indicator 3.2 (Milestone #1) |  | No milestones agreed as the they were not clear due to the adaptive nature of the programme. Also, Output Indicator folded under Outcome 2 (it sat previously under Outcome 3). | 2024-05-14
19 | Outcome Indicator 2.2 (Milestone #2) | 1 | Outcome Indicator 3.2 (Milestone #2) |  | No milestones agreed as the they were not clear due to the adaptive nature of the programme. Also, Output Indicator folded under Outcome 2 (it sat previously under Outcome 3). | 2024-05-14
20 | Outcome Indicator 2.2 (Milestone #3) | 1 | Outcome Indicator 3.2 (Milestone #1) |  | No milestones agreed as the they were not clear due to the adaptive nature of the programme. Also, Output Indicator folded under Outcome 2 (it sat previously under Outcome 3). | 2024-05-14
21 | Output Indicator 1.1 (Milestone #2) | Restructure roles to meet evolving demands | Output Indicator 1.1 (Milestone #2) |  | Not specified due to the adaptive nature of the Secretariat's role | 2024-05-14
22 | Output Indicator 1.1 (Milestone #2) | TBD | Output Indicator 1.1 (Target July 2026) |  | Not specified due to the adaptive nature of the Secretariat's role | 2024-05-14
23 | Output Indicator 1.3 | Robust ATACH workplans in place and being delivered | Output Indicator 1.2 | ATACH team reporting progress on workplan outputs through their regular reporting. | Updated as the ATACH Secretariat is up and running and milestones can now be refined for the immediate future. | 2024-05-14
24 | Output Indicator 1.2, Milestone #2 | New workplan and structure to be in place and delivering on objectives | Output Indicator 1.2, Milestone #2 |  | No milestones specified as the ATACH Secretariat had not been set up. | 2024-05-14
25 | Output Indicator 1.2 Target September 2026 | TBD | Output Indicator 1.2 Target July 2026 |  | To be specified as the ATACH Secretariat's work evolves | 2024-05-14
26 | Output Indicator 1.4 | Number of knowledge sharing and best practice sharing events | N/A | N/A | Output Indicator 1.4 added to capture activity through ATACH | 2024-05-14
27 | Output Indicator 2.1 Source | ATACH Reporting; Project reporting: Bilateral Component and Funding Multilateral Partner (HSRTF) | Output Indicator 2.1 Source | WHO Global Survey | Source updated to the one with the most relevant information, i.e. reporting from projects funded via the programme. | 2024-05-14
28 | Output Indicator 2.2 | Number of countries supported through the programme to have health impacts reflected in their National Adaptation Plans | Output Indicator 2.2 | Percentage of countries that have health impacts reflected in their National Adaptation Plans | Metric updated to more effectively quantify the change being affected by the programme | 2024-05-14
29 | Output Indicator 2.2, Milestone #1 | 1 | Output Indicator 2.2, Milestone #1 | TBC | Milestone was not specified as it could not be predicted what this will be given the adaptive nature of the project. It has now been specifief in light of updated metric. | 2024-05-14
30 | Output Indicator 2.2, Milestone #2 | 1 | Output Indicator 2.2, Milestone #2 | TBC | Milestone was not specified as it could not be predicted what this will be given the adaptive nature of the project. It has now been specifief in light of updated metric. | 2024-05-14
31 | Output Indicator 2.2 Target September 2026 | 1 | Output Indicator 2.2 Target July 2026 |  | Milestone was not specified as it could not be predicted what this will be given the adaptive nature of the project. It has now been specifief in light of updated metric. | 2024-05-14
32 | Output Indicator 2.2 Source | Project reporting: Bilateral Component and Funding Multilateral Partner (HSRTF) | Output Indicator 2.2 Source | TBC | Not specified as due to the adaptive nature of the programme these were not yet definitively known | 2024-05-14
33 | N/A | N/A | Output Indicator 2.3 | Climate literacy of healthcare sector professionals | Output Indicator removed because the bilateral programme support is not directly linked to Health Care workforce training. An Output Indicator has been added to Output No. 1 to reflect training of healthcare personnel through ATACH (Output Indicator 1.4). | 2024-05-14 |  | Output Indicator removed
34 | Output Indicator 4.1 | Number of countries with UK support that have access to climate finance (including UK ICF) for adaptation and mitigation measures within the health sector | Output Indicator 4.1 | How many countries with UK support have access to climate finance or ICF eligible finance for mitigation measures within the health sector | Combining the Output Indicators 4.1 and 4.2 to cover adaptation and mitigation as the projects (ATACH and bilateral) cover the two in tandem. | 2024-05-15
35 | N/A | N/A | Output Indicator 4.2 | How many countries with UK support have access to climate finance or ICF eligible finance for adaptation measures within the health sector | Combining the Output Indicators 4.1 and 4.2 to cover adaptation and mitigation as the projects (ATACH and bilateral) cover the two in tandem. | 2024-05-15
36 | Output Indicator 4.2 | Number of countries with UK support that have access to finance via mulltilateral agencies and banks for climate and health adaptation and mitigation measures | N/A |  | Output combined with Output Indicator 4.1 as the projects (ATACH and bilateral) cover adaptation and mitigation in tandem. New Output defined as Output Indicator 4.2. | 2024-05-15
37 | Outcome Indicator 3.1 | Progressive increase in the number of low-and-lower-middle-income countries that report receiving international funds for health and climate change work | Outcome Indicator 4.1 | low-and-lower-middle-income countries reporting receiving international funds for health and climate change work | Indicator updated to more effectively quantify the change being affected by the programme | 2024-05-21 |  | Reference number also changed from 4.1 to 3.1
38 | N/A | N/A | Outcome Indicator 4.3 | Public finance committed for developing low carbon and sustainable health systems | Deleted as this is already covered in the Outcome Indicator 3.1 (previously 4.1) and Output Indicators 3.1 and 3.2 (previously 4.1 and 4.2 respectively). | 2024-05-21 |  | Outcome Indicator Deleted
39 | Outcome 4 | More countries address the health impacts of air pollution through national planning efforts. | N/A | N/A | New Outcome added | 2024-05-21 |  | New Outcome Added
40 | Outcome Indicator 4.1 | Number of countries that develop/update air quality management plans, with health impacts included. | N/A | N/A | New Outcome added | 2024-05-21 |  | New Indicator under new Outcome
41 | Output Indicator 2.1 | Number of countries supported to conduct a climate change and health vulnerability and adaptation assessment | Output Indicator 2.1 | How many countries with UK support have conducted a climate change and health vulnerability and adaptation assessment | Proofing update. | 2024-05-21 |  | Unchanges - proofing update only
42 | Output 3 | Countries supported by UK to reduce health sector emissions and build resilience | Output 3 | Countries measure health sector's GHG emissions and develop action plans |  | 2024-05-21
43 | Output Indicator 1.3 Milestone 1 | Guidance developed on 'No Regret' interventions. Online hub live with existing V&A assessments / HNAPs accessible. First wins library available to access. | Output Indicator 1.3 Milestone 1 | Guidance developed on 'No Regret' interventions. Online hub live with existing V&A assessments / HNAPs accessible | Further metrics added to capture the activity as it has evolved. | 2024-05-24
44 | N/A | N/A | N/A | N/A | N/A | 2024-05-31 |  | Notes had been added in the original logframe to give context to the adaptive elements of the programme. One of these notes, Note 3) has been updated to account for the changes.
45 | N/A | N/A | N/A | N/A | N/A | 2024-05-31 |  | Note 3) Monitoring Indicators for Component 4 on air quality will be developed once scoping work has been conducted (Year 1). UPDATED TO: Note 3) As stated in Note 3) in the Logframe agreed in November 2023, monitoring indicators for Component 4 on air quality have been developed following the progress on scoping work and will be further developed as this work reaches completion in Years 1.
46 | Outcome Indicator 2 | Climate resilient and low carbon sustainable health systems | Outcome Indicator 2 | Health system more resilient to climate-sensitive disease and climate-related shocks | Outcome 2 and Outcome 3 updated and combined as the projects are now set up and it is clearer how the activities will shape up and the outcomes that they would lead to. Re. Outcome 2, outcome level indicators such as disease and shock related will be difficult to identify and the programme is not contributing to these directly but indirectly via other Outcomes. | 2024-05-31 |  | Outcomes 2 and 3 merged
47 | Outcome Indicator 2 | Climate resilient and low carbon sustainable health systems | Outcome Indicator 3 | Health systems more sustainable, with reduced carbon emissions | Outcome 2 and Outcome 3 updated and combined as the projects are now set up and it is clearer how the activities will shape up and the outcomes that they would lead to. Re. Outcome 3, there limited focus specifically on carbon emissions specifically in the programme. The programme is not directly leading to this, but only indirectly via other outcomes. | 2024-05-31 |  | Outcomes 2 and 3 merged
48 | N/A | N/A | Outcome Indicator 3.1 | Number of people in country served by healthcare facilities with no, or unreliable, electricity supply No of hours additionally supplied by renewable energy sources (Source project reporting) | Deleted due to very limited focus specifically on this in the programme. The programme is not directly leading to this, but only indirectly via other outcomes. | 2024-05-31 |  | Removed.
49 | Outcome Indicator 3 | Increased international investment in building climate resilient and low carbon health systems | Outcome Indicator 4 | Increased international investment in building climate resilient and low carbon health systems | N/A | 2024-05-31 |  | Unchanged - only the reference number updated from 4 to 3.
50 | Outcome Indicator 3.2 | Public finance committed for adaptation in the healthcare sector | Outcome Indicator 4.2 | Public finance committed for adaptation in the healthcare sector | N/A | 2024-05-31 |  | Unchanged - only the reference number updated from 4.2 to 3.2.
51 | Impact Indicator 3 Milestone #1 |  | Impact Indicator 3 Milestone #1 | 47000 | Milestone removed as the metrics are based on Sustainable Development Goal (SGD) 13.1.1 and SDGs do not have forecasts. | 2024-06-03
52 | Impact Indicator 3 Milestone #2 |  | Impact Indicator 3 Milestone #2 | 45000 | Milestone removed as the metrics are based on Sustainable Development Goal (SGD) 13.1.1 and SDGs do not have forecasts. | 2024-06-03
53 | Impact Indicator Target September 2026 |  | Impact Indicator Target July 2026 | 40000 | Milestone removed as the metrics are based on Sustainable Development Goal (SGD) 13.1.1 and SDGs do not have forecasts. | 2024-06-03
54 | Outcome Indicator 2.2 | Number of countries with increased capacity on healthcare sector greenhouse gas emissions through baseline measures of carbon footprint of healthcare system and action plans (process indicator for early stages of the programme) | Outcome Indicator 3.2 | ncreased capacity on healthcare sector greenhouse gas emissions through baseline measures of carbon footprint of healthcare system and action plans (process indicator for early stages of the programme) | Specified the metric in terms of number of countries as this was not specified previously | 2024-06-03
55 | Outcome Indicator 2.2 Source | Project reporting from Posts and World Bank | Outcome Indicator 3.2 Source | Lancet Countdown, indicator 3.6 | More useful, relevant and complete data to be found in Project reporting where the programme is supporting the outcome via the bilateral component and via WB reporting where the Outcome is being achieved via that component. | 2024-06-03
56 | Output Indicator 1.2 Milestone #1 | Satisfactory progress across all workplans evidenced in reporting; and new strategy and plans for evolving structure agreed | Output Indicator 1.2 Milestone #2 | Satisfactory progress across all workplans evidenced in reporting | Milestone updated to add detail in light of the component now being set up. | 2024-06-03
57 | Output Inficator 1.3 Milestone #2 | Developed Climate and Health Indicator Framework. Online live hub populated with key products. Annual C&H global progress report and recommrndations. | Output Inficator 1.3 Milestone #2 | Developed Climate and Health Indicator Framework. Online live hub populated with key products. | Milestone updated to add detail in light of the component now being set up. | 2024-06-03
58 | Output Indicator 2.2 | Number of countries supported through the programme to have health impacts reflected in their National Adaptation Plans | Output Indicator 2.2 | Number of countries supported through the programme to have health impacts reflected in their National Adaptation Plans | Metric updated to more effectively quantify the change being affected by the programme | 2024-06-03
59 | Outcome Indicator 3.2 Milestone #1 | > Baseline | Outcome Indicator 4.2 Milestone #1 |  | Milestone specified | 2024-06-03
60 | Outcome Indicator 3.2 Milestone #2 | > Baseline | Outcome Indicator 4.2 Milestone #2 |  | Milestone specified | 2024-06-03
61 | Outcome Indicator 3.2 Milestone Target September 2026 | > Baseline | Outcome Indicator 4.2 Target July 2026 |  | Milestone specified | 2024-06-03
62 | N/A | N/A | Output Indicator 3.3 | Number of countries publish action plans for healthcare decarbonisation and/or GHG baseline footprint assesments, with UK support | Indicator removed. Replaced by Output Indicator 2.3 and 3.1 | 2024-06-03
63 | Output Indicator 3.2 | Indicators that assess progress of countries in delivering their climate resilience and low carbon sustainability goals identified, developed and promoted | Output Indicator 3.2 | Countries produce baseline assessment of the health sector's GHG emissions | There limited focus specifically on carbon emissions specifically in the programme. The programme is not directly leading to this, but only indirectly via other outcomes. | 2024-06-03
64 | Outcome Indicator 3.1 | Number of low-and-lower-middle-income countries that report receiving international funds for health and climate change work |  | Progressive increase in the number of low-and-lower-middle-income countries that report receiving international funds for health and climate change work | Progressive increase in the number of low-and-lower-middle-income countries that report receiving international funds for health and climate change work | 2024-06-04
65 | Ouput 2 | Countries assess vulnerability and build the resilience of their health system to climate impacts and shocks, with support from the UK | Output 2 | Countries assess the resilience of their health system to climate-related shocks, with support from the UK | Output specified, further detail provided. | 2024-06-04
66 | Output Indicator 2.3 | Percentage of ATACH Member countries that have submitted vulnerability and adapation assessments, and plans to adapt and build climate resilience of their health systems (including HNAPs, health components of NAPs and health reform initiatives) | N/A | N/A | New indicator added to capture output on HNAPs and CHVAs via ATACH | 2024-06-04 |  | New Output Indicator
67 | Output Indicator 3.1 | Percentage of ATACH Member countries that have submitted documentation and plans for decreasing carbon emissions and climate sustainability of their health systems | N/A | N/A | New Indicator | 2024-06-05
68 | Outcome Indicator 3.1 Milestone #1 | 30% | Outcome Indicator 4.1 Milestone #1 | 0.3 | WHO does not provide forecasts. Therefore these are estimates of global trends | 2024-06-05
69 | Outcome Indicator 3.1 Milestone #2 | 33% | Outcome Indicator 4.1 Milestone #2 | 0.35 | WHO does not provide forecasts. Therefore these are estimates of global trends | 2024-06-05
70 | Outcome Indicator 3.1 Target September 2026 | 37% | Outcome Indicator 4.1 Target July 2026 | 0.45 | WHO does not provide forecasts. Therefore these are estimates of global trends | 2024-06-05
71 | N/A |  | Output Indicator 3.3 | Number of countries publish action plans for healthcare decarbonisation and/or GHG baseline footprint assesments, with UK support | There limited focus specifically on carbon emissions specifically in the programme. The programme is not directly leading to this, but only indirectly via other outcomes. | 2024-06-05 |  | Removed.
72 | Output Indicator 1.3 Milestone 2 | Online live hub populated with key products. Annual C&H global progress report and recommrndations.Key indicators developed and agreed at sub-national level. | Output Indicator 1.3 Milestone 2 | Developed Climate and Health Indicator Framework. Online live hub populated with key products. | Removed reference to indicator framework. This will be developed at national level earlier and is captured in Output indicator 3.2 | 2024-06-05
73 | Output Indicator 1.3 Milestone 1 | Guidance developed on 'No Regret' interventions. Online hub live with existing V&A assessments / HNAPs accessible. First wins library available to access.Overall indicator framework and draft indicators agreed at national (health system) level. | Output Indicator 1.3 Milestone 1 | Guidance developed on 'No Regret' interventions. Online hub live with existing V&A assessments / HNAPs accessible. First wins library available to access. |  | 2024-06-05
74 | None - Indicator removed. |  | Output Indicator 3.1 | Percentage of countries that have assessed the environmental sustainability of at least one health care facility | Decided to remove, captured better in other indicators. Difficult to measure direct UK influence on this. | 2024-06-05 |  | Removed
75 | None - Indicator removed. |  | Output Indicator 3.2 | Indicators that assess progress of countries in delivering their climate resilience and low carbon sustainability goals identified, developed and promoted | delete as wrapped in to Indicator 1.3 on core products | 2024-06-05 |  | Removed
76 | Output 2 | Countries assess vulnerability and build the resilience of their health system to climate impacts and shocks, and to reduce health sector emmisisons, with support from the UK | Output 2 | Countries assess vulnerability and build the resilience of their health system to climate impacts and shocks, with support from the UK | Output 3 folded into Output 2. Previoulsy Output 2 covered only the vulnerability and adaptation assessments. Now it also covers carbon emissions that were previously only under Output 3. | 2024-04-17
77 | Output Indicator 2.2 Target September 2026 | 2 | Unmodified | 3 | Target reduced due to ODA cuts and reduced focus on bilateral work | 2024-04-17
78 | N/A | N/A | Output 3 | Countries supported by UK to reduce health sector emissions and build resilience (sustainably) | Folded into Output 2 | 2024-04-17 |  | Removed
79 | Output 3 | The same as previous Output 4 | Output 4 | The same as previously agreed | Output numbering updated as previous Output 3 is deleted | 2024-04-17 |  | Change in numbering. No change in substance
80 | Output 4 |  | Output 5 | Online platform for Air Quality Management guidance (AQMx) developed and functional, being used to inform national planning efforts. | Output numbering updated as previous Output 3 is deleted | 2024-04-17 |  | Change in numbering. No change in substance
81 | Output Indicator 4.1 | Number of countries that access capacity building workshops on air pollution and its impacts on health via the AQMx platform and its associated Techincal Advisory group. | Output Indicator 5.1 | Platform goes live and is populated with key guidance on tackling the health impacts of air pollution. | Output indicator updated in response to Annual Review recommendation. The programme did not contribute to the previous indicator. The new indicator records programme results. | 2024-04-17
82 | Output Indicator 4.2 | The same as previous Output Indicator 5.2 | Output Indicator 5.2 | The same as previously agreed | Output numbering updated as previous Output 3 is deleted | 2024-04-17 |  | Change in numbering. No change in substance
83 | Output Indicator 4.4 | Countries supported to reduce short-lived climate pollutant emmissions | N/A | N/A | N/A - new output indicator added to capture new programme activity | 2024-04-17
84 | Output Indicator 4.3 | Number of countries has the CCAC supported to integrate air pollution into its health planning | N/A | N/A | N/A - new output indicator added to capture new programme activity | 2025-05-14
85 | Output Indicator 1.2 Target September 2026 | Delivery of the actions in the workplan | Output Indicator 1.2 Target September 2026 | TBD | Specifying the target | 2025-05-14
86 | Outcome Indicator 2.1 Source | ATACH Reporting | Outcome Indicator 2.1 Source | WHO Global Survery on climate and health, | Making the source relevant to allow accurate capturing of programme output and avoid taking credit for activity beyond the programme purview | 2025-05-14

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.