Annual Review

Title: Climate Resilient and Sustainable Health Systems Programme
Programme Value £ (full life): £18m		Review date: 15-02-2026
Programme Code: 301532	AMP start date: 15/11/2023	AMP end date: 31/03/2028

Summary of Programme Performance
Year	2025	2026
Overall Output Score	A	A+
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006007.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/S30153211.xlsx

Glossary of Abbreviations
ACAP – Africa Clean Air Programme
AQMx – Air Quality Monitoring Matrix
AU – Africa Union
AR – Annual Review
CCAC – Climate and Clean Air Coalition
CHVA – Climate and Health Vulnerability and Adaptation Assessment
COP – Conference of the Parties (Annual International Climate Meetings)
CREWS – Climate Risk and Early Warning Systems
CRIBS – Climate Resilient Infrastructure for Basic Services
DDA – Due Diligence Assessment
DLIs- Disbursement Linked Indicators
FY – Financial Year
HNAP – Health National Adaptation Plan
HSTRF – Health Systems Transformation and Resilience Fund
IBRD – International Bank for Reconstruction and Development
IDA – International Development Association
ICF – International Climate Finance
MDB – Multilateral Development Bank
NGO – Non-Governmental Organisation
ODA – Official Development Assistance
PCR – Programme Completion Report
PHC – Primary Health Care
SHHR – Sexual and Reproductive Health and Rights
VfM – Value for Money
WHA – World Health Assembly
WHO – World Health Organisation
WISER – Weather and Climate Information Services (a Met Office programme)
ToR – Terms of Reference
UKHSA – UK Health Security Agency
UNEP – United Nations Environment Programme
UNICEF – United Nations Children’s Fund

## A. SUMMARY AND OVERVIEW
Description of programme
The Climate Resilient and Sustainable Health Systems programme works to strengthen climate resilient health systems and better equipped to cope with the health impacts of climate change, whilst adopting low-carbon and sustainable pathways as they develop and grow – this supports global and national efforts to fulfil commitments made at COP26 (Conference of the Parties). It seeks to achieve this by: (1) enhancing international leadership and coordination through the Alliance for Transformative Action on Climate and Health (ATACH); (2) providing catalytic investments and technical assistance to help countries assess vulnerabilities, develop adaptation and mitigation plans, and build investment cases; and (3) mobilising resources and leveraging large-scale international climate finance and (4) advocating for and supporting efforts on air pollution and its impacts on health. The programme complements diplomatic, partnership and policy engagement, and evidence and research work to reach this vision.
To date, the programme has played an instrumental role delivering the UK co-leadership of ATACH with the World Health Organisation (WHO), initiating the Health Systems Transformation and Resilience Fund (HSTRF) with the World Bank and supporting the Climate and Clean Air Coalition (CCAC) integrating health into their approach.
New work this year responds to growing demand for climate services for health, with proof-of-concept projects embedding health in two existing FCDO climate programmes (Weather and Climate Information Services (WISER) and Climate Risk and Early Warning Systems (CREWS)), complementing partners’ efforts to improve the quality, availability and use of climate data and early warning for health.
Associated with Official Development Assistance (ODA) reductions there is a consolidation process with programmes. Hence, components under this programme are planned to become elements of a broader health systems programme and envisaged Centres of Expertise. This transition can help situate climate considerations within a broader health agenda.
Summary supporting narrative for the overall score in this review
The programme scores an A+ overall for this year. Although some output indicators were partially met, all outcomes are on track, and several areas of performance exceeded expectations. Where output indicators were not met, much of this is underpinned by factors beyond the control of the programme, for example countries not prioritising low-carbon pathways), and the impact the programme has had on the climate and health agenda globally is immense, particularly when compared to its size. Given this overall impact, the programme is judged to have scored an A+ on balance, reflecting 50% of outputs scoring A and 50% scoring A+.
The programme has successfully continued to elevate the climate and health agenda, convening multilateral partners and countries to drive implementation of COP26 and other commitments. ATACH has convened partners to share best practice, expand the evidence base and coordinate, seeing 59% of its 102-country membership completing vulnerability and adaptation diagnostics and plans. This has engaged the World Bank to shape and leverage its wider health lending portfolio to consider climate. In turn, World Bank initiatives and operations also provide lessons and tools feeding into ATACH. Our direct support to countries has mobilised action on the ground and generated learning. In Nigeria, our WHO‑aligned support for the Climate and Health Vulnerability and Adaptation Assessment (CHVA) and Health National Adaptation Plan (HNAP) catalysed integration of climate into bilateral FCDO health programming, leveraged $145m in World Bank health operations, and mobilised HSTRF funding to roll out the HNAP across all states. The programme’s component on air quality has helped forge synergies between climate change, air pollution and health policies and investments. More progress is needed to maximise impact, for which strong cross-government working and a new core investment in the CCAC provide opportunities in the coming year.
No.	Title	Weighting	Score
1	ATACH Secretariat operational and able to demonstrate impact, expand reach, monitor and report progress	20%	A+
2	Countries assess vulnerability and build the resilience of their health system to climate impacts and shocks, and to reduce health sector emissions, with support from the UK	30%	A
3	Countries have demonstrable increased access to finance for implementation of climate and health action, on mitigation and adaptation measures	30%	A+
4	Countries access support to integrate air pollution in their health planning	20%	A

Major lessons and recommendations for the year ahead
1. Maximise opportunities from the FCDO restructure. Greater coherence with a systems agenda, both health and broader governance approaches, are opportunities for the climate and health agenda. This agenda has risen swiftly as a global priority, but remains new and is maturing, with a fast-evolving evidence base. It requires strong capacity and capability to effectively engage others, remain agile and responsive and support transition to mainstreaming. This overarching lesson points to opportunities from the FCDO restructure, which offers the opportunity for increased integration of climate and health into new ways of working, international engagement, policy, business cases and business planning across FCDO. Notably, ‘nexus’ areas have the potential to provide greater value and coherence, delivering multiple goals simultaneously.
2. Manage the closure of the programme carefully to ensure that the progress made on climate and health is secured. The programme’s achievement lays a strong foundation for mainstreaming, Centres of Expertise and a more-systems based approach. It will be key to ensure this indeed happens. Given its agile and catalytic nature, sensibly managing programme closure is critical. The Programme Completion Report (PCR) should look to comprehensively capture lessons and evaluate impact, making recommendations to maintain partnerships and for impactful mainstreaming as FCDO’s approach evolves. The programme offers lessons on agility and responsiveness that should be considered in future approaches.
3. Continue to invest, via multiple channels, in the capability on climate and health. Global climate and health expertise, whilst growing, remains limited. The programme has underpinned efforts to expand the base. However, more is needed and fundamental for progress, integration and building multi-disciplinary and sector partnerships. Programme funded posts and continued support to partnership platforms could be considered.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The programme seeks to reduce preventable deaths from climate change induced health impacts by making health systems climate-resilient, low-carbon, and sustainable. It does this by strengthening global leadership and coordination; supporting countries in assessing vulnerabilities and integrating climate adaptation and mitigation into health planning, policies and programmes; integrating air pollution reduction and its health impacts into national strategies; and mobilising domestic and international finance for climate and health. These interconnected actions enable countries to strengthen health systems to withstand climate related shocks and changing patterns of disease, reduce emissions and improve air quality, together enhancing global health security and saving lives.
No substantial changes have been made to the outcomes or impact since the Business Case, except defining the air quality outcome. Outputs have changed in line with new activities approved by the Programme Board. Following the last AR, two ATACH outputs and corresponding indicators were consolidated into a new Output 1, and Output 4 was further developed to capture the full range of support on air pollution. This year programme implementation has matured, leading to an uptick in delivery of outputs and progress on outcomes. New activities were scoped and will support efforts to strengthen integration of health in climate data and services, early warning systems and emergency preparedness. The logframe will be updated immediately following this AR to capture outputs and outcome changes required to review at the PCR.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to meet all its outcomes.
Outcome	Assessment
Improved international cooperation and dialogue at the intersection of climate and health.	ATACH is supporting coordination on climate and health, compiling and sharing experiences, and convening members at World Health Assembly (WHA), the Global Conference on Climate and Health and COP30 to drive delivery. The new task teams have increased collaboration amongst groups of partners and countries to deliver specific guidance and tools.
Climate resilient and low carbon sustainable health systems	The WHO climate-health survey and ATACH reporting shows notable progress on numbers of countries strengthening health system climate-resilience. 41 ATACH countries met the criteria in WHO’s General Programme of Work 14, of implementing their COP26 commitments to building a climate resilient health system by the end of 2025 – exceeding the target of 28 countries. Our bilateral support coupled with technical assistance via HSTRF and best practice sharing in ATACH has built capacity and supported action towards this outcome. These efforts also strongly supported enhanced global coordination and momentum through engagement in the development of the Belem health action plan launched at COP30. Catalytic funding for the Nigeria Climate Resilient Infrastructure for Basic Services (CRIBS) programme has been adopted as best practice and is being rolled out in several countries globally, mainly through World Bank channels.
Increased international investment in building climate resilient and low carbon health systems	No recent global assessment is available to comprehensively assess the level of increased investment the programme has contributed to. However, progress on outcome 2 has been fundamental to building the investment case, plans and projects to mobilise resources. HSTRF support is strongly linked to World Bank pipelines and has shaped larger health operations. Collaborations through ATACH and CCAC have contributed to action by multilateral climate funds, global health institutions and (Multilateral Development Bank) MDBs to support more climate resilient and sustainable health systems. Our support to WISER and CREWS has leveraged philanthropy and MDB resources.
More countries address the health impacts of air pollution through national planning efforts	There is evidence more countries are committed to addressing the health impacts of air pollution. In March 2025, 22 countries committed to reducing the health impacts of air pollution by 50% by 2040 at the Global Air Quality Conference. Through our programme support and partnership with CCAC, countries can access air quality management tools online to support their efforts. African countries receive targeted support via the Africa Clean Air Programme (ACAP), and the newly launched CCAC country programme will provide bespoke support to countries.

Planned Action:
Considering the ODA reductions and FCDO 2030 restructure context, the programme is planned to close in 2026/27. Some components will continue, integrated into new programmes, and gains will be built into future policy and diplomatic engagement. The proposed actions to achieve this are:
1. Assess programme levers and gains to make robust recommendations to maximise their long-term impact and embed outcomes and outputs in future policy and programmes.
2. Engage in strategic and transition planning on the design and set up of future health programmes and the new Centres of Expertise to allow successful programme components to continue.
3. Ensure sustainability of programme activities and continued impact by influencing multilateral partners, bilateral programmes and the FCDO Climate and Health networks.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Given its performance and the value for money it represents, there is a strong case to continue with the programme. However, with the longer-term objective to integrate the agenda and the wider organisational context, the decision has been taken to close the programme in FY2026/27. Successful and effective components and approaches will continue through other FCDO programmes in a more mainstreamed way or built into policy and diplomatic engagements.
## C. DETAILED OUTPUT SCORING
Output Title	ATACH Secretariat operational and able to demonstrate impact, expand reach, monitor and report progress
Output number:		1	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestones for this review	Progress
ATACH core roles recruited and in place	Restructure roles to meet evolving demands	Achieved.
Robust ATACH workplans in place and being delivered	New workplan and structure to be in place and delivering on objectives	Achieved.
Core products finalised and available to ATACH members, including online live hub populated with key products to facilitate in country work on climate and health	Online live hub populated with key products. Annual C&H global progress report and recommendations. Key indicators developed and agreed at sub-national level.	Achieved.
Number of knowledge sharing and best practice sharing events	> 3	Achieved. 8 Technical Meetings run on a range of subjects.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output is on track to meet end-of-programme targets and exceeded expectations in this period.
Completion of the governance restructure has led to more active partner and country members’ engagement through constituency groups, all represented in the Steering Group. It has supported more representative and inclusive approaches, oriented to meeting country priority needs and increasing the impact of ATACH globally. The task teams have delivered three products (on high value products; decarbonising health supply chain and measuring greenhouse gases), directly responding to countries’ calls for evidence-based guidance on where to invest to strengthen climate and health resilience. The ‘Smart Buys’ product provides 8 high value adaptation actions for health sector adaptation. ATACH has also undertaken workshops and learning on a range of areas of the climate-health agenda. These include 8 technical meetings including on ‘climate resilient and environmentally sustainable health supply chains’, which had 286 registrants and ‘making mental health systems climate resilient and sustainable’. There were on average 205 registrants per technical meeting.
The ATACH workplan was agreed by the Steering Group in early 2025 for two years. Planned events and products have been delivered and well received. A review of the plan and new activities is to be agreed at a Steering Group meeting in February 2026 (based on evaluation insights and country priorities). Feedback from countries at the Global Conference in July and the ATACH Day at COP30, and our engagement following the Wilton Park conference on finance for climate and health is helping shape this.
The Community of Practice has been updated with a key document repository, 19 case studies and a resource library. Between March – September 2025, the Community of Practice had 17,000 unique visitors from over 140 countries, up from 15,000 in the previous six-month reporting period (reporting on numbers until February 2026 expected in April 2026) showing the hub is being accessed by a wide range of countries. Feedback from countries has consistently highlighted the usefulness of the online Community of Practice to address climate change and health challenges, and the need to maintain and further strengthen the sharing of case studies, successes and lessons learned through the online Community of Practice.
Several knowledge sharing and best practice events were held this year. The second in-person global ATACH meeting was held alongside Global Conference on Climate and Health in Brasilia, between 28-31 July 2025. Two regional meetings were held: PAHO/ATACH Caribbean Meeting (Barbados, June 2025), Western Pacific Action Forum (Singapore, September 2025). These played a critical role in engaging partners and informing the COP30 Belém Health Action Plan.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes made to this output in the past year and none planned as a result of this review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
Progress since last year (addressing lessons and recommendations):
1. We have engaged closely in Steering Group meetings and more widely to monitor the restructure of ATACH Secretariat.
2. We have also engaged with the Secretariat to agree and implement a communications strategy.
3. We have maintained a strong UK representation at the ATACH Steering Group to encourage consistent messaging on maximising the health case within climate change and other sectors.
Lessons learned and recommendations for the year ahead:
ATACH has been impactful in generating global momentum and inspiring action for climate resilient and sustainable health systems. This has been maintained during the WHO’s extensive restructure process during this period. Both WHA and COP action plans set expectations to enhance ATACH’s role in monitoring progress and supporting country action. Its resources are not commensurate with aspiration and given central WHO constraints, funding for ATACH will rely heavily on external resources. FCDO should encourage the Secretariat to develop a funding strategy that diversifies its funder base and considers a range of models over time, and support implementation, whilst considering its own future contributions, including secondments.
Holding the ATACH Annual Meeting alongside the Brazil Global Conference amplified country and partner engagement. Opportunities to host any future events strategically alongside similar umbrella events should continue to be sought and consideration given to alternating virtual and in-person meetings.
The Belem Health Action Plan incentivises country-level implementation of adaptation action in the health sector. ATACH’s involvement supported alignment with country needs and evidence based on practice. ATACH is mandated as having a monitoring and secretariat role in the Plan, which is positive for coherence of further action. However, this needs work to ensure it supports and compliments other processes at country and global level and it is appropriately resourced. FCDO to engage with WHO team and key partners.
WHO have contracted consultants to undertake an external independent evaluation of ATACH. This is due for completion in early 2026. FCDO should use the findings from this to inform funding and operational decisions, and engagement with ATACH partners.
Output Title	Countries assess vulnerability and build the resilience of their health system to climate impacts and shocks, and to reduce health sector emissions, with support from the UK
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone	Progress
2.1: Number of countries supported to conduct a CHVA	4 (cumulative)	Achieved: 6 (cumulative) with 3 during this AR period. / World Bank HSTRF: Timor Leste, Comoros, Liberia (activity was supported in previous AR but completed during this period). / Direct bilateral support: No new CHVAs have been supported this year. Previous support to Pakistan, Somalia and Nigeria.
2.2: Number of countries supported to reflect and consider health impacts in their National Adaptation Plans and/or climate adaptation and resilience in health reform plans	2 (cumulative)	Achieved: 4 total - 2 HNAPs (cumulative) and 2 supported in national planning. / World Bank HSTRF, climate being integrated in health national planning in: Iraq and Philippines / Direct bilateral support: Nigeria – support to translate the HNAP (supported in previous period) to states level in up to 21 states (World Bank HSTRF supporting further 15).
2.3: Percentage of ATACH Member countries that have submitted vulnerability and adaptation assessments, and plans to adapt and build climate resilience of their health systems (including HNAPs, health components of NAPs and health reform initiatives)	40% (cumulative)	Achieved: / 59%* of countries have completed a CHVA and 53%* have completed HNAPs. / 40% of countries have submitted both CHVAs and HNAPs.
2.4: Percentage of ATACH Member countries that have submitted documentation and plans for decreasing carbon emissions and climate sustainability of their health systems	40% (cumulative)	Not quite met: 21.5%* have submitted either a GHG emissions assessment or plans to reduce GHD emissions and enhance health system sustainability since 2020. / 25%* of countries have completed an assessment, while 14%* reported that an assessment is currently ongoing. / 18%* of countries have submitted plans since 2020. 17%* have started these plans.
*Data is based on 102 ATACH WHO Member States, as of 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.
Progress against this output has been significant, and this output is on track to meet end-of-programme targets and largely exceeded expectations for this review period with most indicators exceeding targets. Output Indicator 2.4 has marginally missed targets. However, this was expected as more low-income countries (majority of new country members) prioritise resilience over low carbon pathways. Nonetheless, the number of countries reaching the target has increased (despite a fall in percentage).
Our contribution to the World Bank HSTRF has supported:
1. Small Island Developing States with TA across islands (for example, supporting evaluation of climate vulnerability of health infrastructure, mapping hospital capacity and performance, and designing a regional model to enhance access and resilience).
2. Deep-dive country analytics on 4-5 country exemplars in collaboration with the Gates Foundation and Harvard University. This will include developing a model to assess service delivery disruptions during climate events and the analytical approach has been piloted in Colombia and Liberia;
3. 15 states in Nigeria to develop health adaptation plans, complementing bilateral country programme support in up to another 21 states;
4. West Africa (Cameroon, Chad, the Republic of Congo, and Central African Republic), with technical assistance that is leveraging World Bank operations to include health systems responses to climate shocks; measures to reduce the impacts of climate shocks on laboratories and other public health infrastructure; and addressing the climate change related impacts on epidemic prone diseases;
5. Capacity building in Iraq; and Brazil‘s Ministry of Health in COP30 planning to identify high-value health sector adaptation actions.
6. Building on last year, progress in 5 deep-dive countries includes: Liberia - a CHVA has recently been completed. Democratic Republic of the Congo (DRC) - a simulation exercise for a cholera outbreak response and WASH guidance will be used to inform World Bank operations. Zambia - technical assistance has identified gaps to support climate informed health systems. Philippines - a climate resilient infrastructure and emissions tool is being piloted in 140 facilities and planned for national adoption. Bangladesh - activities delayed due to a change in government but are now restarting.
Bilateral support in Nigeria this year has helped: translation of the federal HNAP to state level plans and developed state level climate-health data to support delivery. which were used in local budget allocations and leveraged the HOPE primary health care (PHC) funding from World Bank; leveraged the Lafiya programme to support integration of health into Nigeria’s Nationally Determined Contribution 3.0, ensuring health as a driver and measure of success for climate action; strong integration of climate change into the FCDO Nigeria supported Lafiya programme and in policy and partnership engagement with others; and applying the CRIBS methodology into national government primary health care rehabilitation and reconstruction programmes.
The £30k catalyst (provided in the previous reporting cycle) that helped the CRIBS Expert and Oversight Group access additional expertise to develop the methodology and approach is now being supported through an FCDO bilateral programme of up to £39m to develop CRIBS in primary health care and education facilities. It has been integrated into the World Bank health programme, HOPE PHC, to incentivise states to develop up to 2000 CRIBS climate resilient PHCs. Whilst learning continues to develop the approach, it is being implemented as a model of good practice globally, especially through UNICEF and World Bank channels and in ATACH. It has demonstrated how a small investment can leverage much larger investment and impact. During the monitoring visit partners highlighted how the TA had been crucial for traction, informing key decisions on retrofitting PHC sites for better climate resilience and strengthening the interventions and building local capacity. Further reporting is expected imminently. In Bangladesh, new work was initiated in November 2025 to support completion of the HNAP and provision of climate-informed sexual and reproductive health and rights (SRHR) services. Results will be reported in the next review period. Beyond the immediate outputs, this project is expected to provide insights for increased policy engagement and health diplomacy during transition and in new transformed programmes and policy approaches at HQ and in country offices.
ATACH has provided a platform for best practice exchange, galvanising countries to progress CHVAs and HNAPs. ATACH has also supported over 15 Global South countries during this reporting period, through seed grants to advance specific priorities that included actions to undertake CHVAs and prepare HNAPs. For example, Botswana completed a CHVA in January 2025, and ATACH helped translate the findings into a five-year (2025-2030) costed HNAP, outlining innovative interventions to improve the climate-resilience of its health system. Although the percentage of countries that have submitted documentation and plans for decreasing carbon emissions and climate sustainability of their health systems narrowly misses the target, it is important that it is contextualised against the GPW14 target related to low carbon sustainable health systems. WHO set a target that 17 countries would be committed to implementing low carbon systems by the end of 2025. ATACH member countries account for the 17 out of 19 countries who have hit this indicator, highlighting that progress is predominantly being achieved by countries that are members of ATACH.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output was updated following the previous AR, combining indicators on climate resilience and low carbon health systems to monitoring progress on COP26 health commitments. To reflect action beyond CHVAs and HNAPs, a sign of the maturing agenda, this output will be updated to capture broader support for climate resilience, e.g. emergency preparedness and early warning systems.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress since last year (addressing lessons and recommendations):
1. Given direct contracting had a heavy programme management burden for fairly low value contracts, the last review recommended the team explore broader mechanisms for delivering bilateral TA. This year the programme is supporting activity in Nigeria and Bangladesh via budget transfer to Posts, linked to their health programmes. This has reduced the contract management burden on the team and Posts, brought decision making closer to delivery and supported efforts to embed climate-health within the country office priorities, programmes, budgets and partnership engagement.
2. The last AR found the HSTRF governance structures and partnership working could be strengthened. The programme team has engaged the World Bank to encourage increased partnership with a range of actors, which has seen some fruition, e.g. in Mozambique with Global Fund. The due diligence assessment (DDA) supported efforts to strengthen the governance structure. A Results Framework, updated workplans, and first annual fund-wide narrative progress report were submitted and agreed by the Partnership Council (PC) in November. Formal ways of working for the Partnership Council and informal engagement structures are now in place.
Lessons learned and recommendations for the year ahead:
1. The budget transfer to Nigeria saw slower, less structured formal reporting. Teams using this modality should agree reporting expectations in the dual-lock agreement and arrange regular touch points. This has been considered in our support to Bangladesh and WISER. Consideration should be given to benefits (strongest where they link to larger initiatives) and learning in future technical assistance models offered through new Centres of Expertise.
2. To spot opportunities and better assess World Bank HSTRF impact and partnerships in country (and following last AR’s recommendation), the programme team should conduct at least one joint visit with the World Bank team in the next period. Furthermore, where HSTRF climate support is active there should be more proactive engagement with Posts to optimise approaches.
3. The products, learning and partnerships built from the bilateral support could help shape the new Health and Climate Centres of Expertise. Both health and climate advisors involved in this work could be champions, offer in-house expertise/experience and share their learnings.
4. ATACH and World Bank Joint Learning Network offer a wealth of good practice and learnings that should be embedded within the new Centres of Expertise offer.
Output Title	Countries have demonstrable increased access to finance for implementation of climate and health action, on mitigation and adaptation measures
Output number:		3	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone	Progress
Number of countries with UK support that have access to climate finance (including UK International Climate Finance (ICF)) for adaptation and mitigation measures within the health sector	4	Achieved: >4 / 1 – Bilateral: Nigeria. / 3 – CREWS: Barbados, Cambodia and Senegal. FCDO £285k, leveraged matched climate finance from CREWS. / 2 – WISER: South Africa, Nigeria. / 2 – ATACH: Timor-Leste and Guinea.
Number of countries with UK support that have access to finance via mulltilateral agencies and banks for climate and health adaptation and mitigation measures	4	Achieved >4. / HSTRF: Fiji, Kiribati, Tonga & Tuvalu ($159.54m); Togo ($70m); Philippines ($495.60m); Zambia ($50m); Bangladesh ($404m); DRC ($250m), West and Central Africa region ($530m) and Nigeria ($525m – reported last year) / ATACH: Botswana. / Bilateral: Nigeria.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output is on track to achieve end-of-programme targets and exceeds expectations for this review period.
Through the World Bank HSTRF, as reported by December 2025, our contribution has helped shape over $1.8bn International Development Association (IDA) and International Bank for Reconstruction and Development (IBRD) health finance to build climate resilience. For example, in Fiji, Kiribati, Tonga, and Tuvalu, climate action is being integrated into the design of the Bank approved regional Pacific Healthy Islands Transformation Project. Beyond the countries listed in the table, in Cameroon, Chad, the Republic of Congo, and CAR, the technical assistance has enabled support to build climate change emergency response into the operations of Health Security Programme III (HeSPIII). In Togo, it has supported the development of climate interventions for resilient health service delivery and infrastructure to be delivered in the Essential Quality Health Services for Universal Health Coverage Project – 93% of the operation’s financing was preliminarily identified as climate financing.
In Nigeria and Bangladesh, ICF from this programme is supporting health adaptation plans at national and sub-national level. In Nigeria, this mobilised additional country programme (Lafiya) funding and World Bank HSTRF resources for translating HNAP to States.
Support from this programme to WISER and CREWS, large FCDO climate programmes, has galvanised engagement and support from climate and environment teams in FCDO to further consider the health sector in climate programming. The funding via CREWS has mobilised matched resources from the CREWS Multi-Donor Trust Fund managed by the World Bank to undertake work in three countries on extreme heat and health. The use of the CREWS mechanism for this provides an explicit opportunity to leverage additional financing for extreme heat adaptation from MDBs. Furthermore, Rockefeller Foundation finance was leveraged for deeper, longer-term programming in WISER, and strengthened global learning in CREWS. The partnership with the UK Met office, further strengthened through WISER Health, has enabled broader understanding of the Met Office expertise offer overseas along with its domestic work with the UK Health Security Agency (UKHSA). This will offer new engagement opportunities to extend the impact of this initial work. It positions well to benefit from strong UK institutional and technical expertise to enable value adding partnerships in targeted countries. It will also play an important role in helping direct and mobilise larger investments going to Green Climate Fund, MDB and other boards for early warning systems. For example, in Nigeria the work scoping out national and sub-national approaches to integrated climate environment and health early warning systems, will help to direct the World Bank $300m health security operation that has early warning systems as a key deliverable.
Beyond the finance leveraged, the Smart Buys publication (detail in Output 1), ATACH finance sessions and engagement with finance partners broadly and via a recent dedicated Wilton Park event have all supported progress in access to finance for climate and health by Global South partners.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes made to this output in the past year and none planned as a result of this review.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
Progress in addressing lessons and recommendations from last year is addressed in outputs 1 and 2. Lessons learned and recommendations for the year ahead:
1. There is some overlap between climate finance and multilateral financing in the current indicators, and a gap in capturing other resources, especially philanthropic, that the programme is mobilising. The indicators should be reviewed to more clearly report on the progress made, identify where the programme investments have mobilised others, and where possible capture the magnitude of other investment catalysed or shaped.
2. The initial investment in WISER Health has proved catalytic to bring in other partners in FCDO and Rockefeller, opening possibilities for further interest, such as Wellcome Trust. It has provided an entry point for further potential collaboration with the UK Met office and with UKHSA which should be explored and exploited. This represents value for money (VfM) beyond originally envisaged and should be maximised in future policy and diplomatic engagement and partnerships.
3. Progress made via this output should feed into future activities in the transformed health department and Centre of Expertise, shaping multilateral priorities and technical assistance. The programme team should consider how best to feed in recommendations and lessons into future department structures and capacity, business cases and offers. For example, lending operations leveraged through HSTRF will continue to deliver beyond programme closure, ensuring FCDO capacity to engage is maintained so these continue to align with UK objectives and visibility.
Output Title	Countries access support to integrate air pollution in their health planning
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	Yes, up from 10%

Indicator(s)	Milestone	Progress
4.1: Number of countries that access capacity building workshops on air pollution and its impacts on health via the (Air Quality Monitoring Matrix) AQMx platform and its associated Technical Advisory group.	50	Achieved. 360 participants from 63 countries have attended workshops in the period covered by this AR. 51 of those countries were LMICs
4.2: Number of LMICs using the platform in their national planning processes for air quality management	40	Achieved. 83 countries are active users of AQMx. 68 of these countries are LMICS.
4.3: Number of countries supported by the CCAC to integrate air pollution into its health planning	8	Not met: 6 countries in total are being supported on air pollution and health. Ghana, Morocco, South Africa, and Kenya all have active support through CCAC. In addition, CCAC are strengthening the health impact of projects being funded by our programme in DRC and Liberia.
4.4: Number of countries supported by the CCAC to reduce short-lived climate pollutant emissions	3	Achieved. Preparations are underway to support 3 countries (Morocco, Liberia and South Africa). These will be delivered up to a year following this AR. This will increase further in the coming year, with the launch of the CCAC’s new country programme.

Briefly describe the output’s activities and provide supporting narrative for the score.
The output is on track to achieving the end of programme targets with most indicator targets exceeding expectations. Output Indicator 4.3 narrowly misses the target. We expect this fourth metric to be met in the coming months with the launch of the CCAC Country Programme, which will provide support (include on health impacts of air pollution) to 7 additional countries. CCAC are also adding more advanced guidance to the AQMx platform aimed at upper-middle income countries. This will further expand the usage of AQM and boost uptake of the guidance.
The programme supported implementation of the UK Co-Sponsored UNEA-6 Resolution to create a global knowledge sharing platform for air quality managers (AQMx), with workshops, outreach activities and the set-up of a Technical Advisory group. The number of users accessing the site is promising but did not quite meet expectations – data on how countries are using the AQMx resources in their national planning processes is not yet available but is being considered. Beyond this, our support for AQMx strengthened the CCAC-FCDO relationship which contributed to the formalisation of the Funding Committee, as well as the cross-HMG decision to take on the co-Chair role at ministerial level. As members of the Funding Committee, the FCDO Air Quality policy lead contributes actively to CCAC’s funding recommendations, thereby influencing broader CCAC Trust Fund resource allocation.
As co-chair of the Board and with our seat we engage proactively in decisions relating to overarching CCAC strategy. We supported the ACAP set up, filling a crucial funding gap for support on air pollution in African countries. Thus far, CCAC has secured the commitment of 5 African countries to be “ACAP Regional Champions, and convened countries via the Africa Union (AU) around air pollution action. The ACAP is still in early implementation stage, so we are engaging with other potential donors to build financial and political support. As co-Chair of the CCAC, we will encourage the Secretariat to work with the AU to establish the ACAP as a formal AU programme, to provide it with an institutional home and embed it more firmly within AU structures.
A move to core unearmarked funding in our latest contribution is supporting CCAC to mainstream health within their metrics. Among other things, this ensures that health is integrated within the new US$150m Country Programme through ensuring health expertise is included in the Country support teams. This will support Global South countries to reduce short-lived climate pollutants, embed health benefits and capture health co-benefits.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Output indicators were amended to reflect support this programme provided to AQMx use and the ACAP (latter agreed in March 2025). The previous output indicator covered set-up of AQMx, which was not achieved as our contribution was delayed whilst the DDA was completed. Further amendments are proposed to account for our recent core contribution and the support to the new Country Programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year it was too early to report at length against this output but good progress on the activities and recommendations has been made this year.
1. The AQMx is fully functional with many accessing the site. There is limited information on how its resources are being used. FCDO should engage CCAC to urge measurement of its impact beyond access statistics, and to take steps to broaden its reach amongst developing country partners.
2. The relationship established with CCAC has provided substantially bigger gains compared to the value of our funding. Our seat at the Funding Committee and the Board enables us to engage on broader strategy and decisions, which we have used to integrate health across broader CCAC operations. As co-Chair, and through the seats we occupy on the Board/Funding Committee, FCDO should be more proactive in setting the agenda, to ensure UK objectives are prioritised and ensure impact and sustainability of the support provided. This will become increasingly important as we shift to policy influencing following ODA cuts and closure of this programme.
3. ACAP is now functional, providing support on air pollution action in Africa. Close monitoring is recommended to ensure continued prioritisation of local ownership and engagement within African countries and AU. Additionally, the programme team should actively engage Posts where ACAP is supporting work. This will raise awareness and potential for engagement through policy and programmes. It should also strengthen our monitoring and evaluation loops, dependent upon country office capacity, to support central engagement with CCAC.
4. CCAC reporting is regular, but insufficiently detailed. FCDO should engage more closely with them to clarify expectations around output indicators and metrics.
5. CCAC has proved an effective and efficient platform for HMG super-pollutants and AQ-health goals. Continued support and engagement should be considered through future determinants of health programmes.
## D: VALUE FOR MONEY
Key cost drivers and performance
Key cost drivers for each Supplier/Partner along with an analysis against the 5 E’s Framework have been evaluated as part of this AR, and key findings are summarised below. The key cost drivers across the programme remain the same as for previous AR periods and vary by partner but generally include staff remuneration and administrative expenses. For ATACH, the main drivers are administration costs, event costs, and governance restructuring and the two World Bank components (HSTRF and CREWS) and CCAC are primarily impacted by administration and staff costs. Bilateral support via budget transfers does not have direct cost drivers, as procurement is managed locally, and WISER has no direct programme costs but relies on Met Office staff and administrative expenses. The programme-funded post incurs minimal costs, limited to remuneration and travel.
VfM performance compared to the original VfM proposition in the business case
Economy across the programme is generally moderate. ATACH and HSTRF face relatively high staff and administration costs, though these are offset by strong delivery and leveraging of additional finance. CCAC also incurs high staff costs but benefits from lower Secretariat fees compared to other multilaterals. Bilateral budget transfers demonstrate good economy by using existing delivery mechanisms and local partnerships, though procurement oversight is limited. The programme-funded post offers high economy due to low remuneration and travel costs. WISER and CREWS represent good economy by embedding health components into existing climate service initiatives and leveraging established mechanisms, despite high institutional cost drivers.
Efficiency across the programme is generally high, with most components achieving or exceeding output targets within forecasted costs. ATACH delivered all indicators and strengthened global cooperation, while HSTRF supported climate-resilient health systems and mainstreamed climate considerations across operations. Bilateral budget transfers proved highly efficient by leveraging existing delivery mechanisms and local partnerships to advance health adaptation plans. Programme-funded posts contributed significantly to delivery across outputs, particularly through stakeholder engagement. CCAC achieved strong progress on its online platform and air quality initiatives with modest funding, and was judged to have a high efficiency. For WISER and CREWS, efficiency is expected to be high due to integration into established programmes and partnerships, though it remains too early for a full assessment.
Effectiveness across the programme is generally high, with most components contributing significantly to intended outcomes and global influence. WHO’s ATACH has become a recognised platform for international cooperation on climate and health, shaping major initiatives such as the Belém Health Action Plan. The World Bank’s HSTRF extends impact by integrating climate-health priorities into Bank operations, engaging governments and attracting partners around unified plans. Bilateral budget transfers strengthen local capacity and sustainability by embedding climate considerations into existing health programmes, while the programme-funded post has amplified success through strategic stakeholder engagement. UNEP’s CCAC is beginning to show progress in supporting countries to meet air pollution targets, though its impact remains moderate for this review period. For WISER and CREWS, effectiveness of the broader initiatives is strong, with early signs of leveraging philanthropic and multilateral finance and building partnerships to support outcome 3.
Equity across the programme shows mixed performance. Bilateral budget transfer equity impact is high, empowering local decision-making and strengthening engagement with local stakeholders, ensuring strong equity dimensions in health programmes. ATACH demonstrates moderate equity, reaching a wide range of countries and addressing issues affecting women and children, while the programme-funded post also shows moderate equity through support for Brazil’s COP30 Presidency social justice principles. In contrast, HSTRF has low equity, with limited evidence of benefits reaching vulnerable groups, and CCAC similarly scores low, with most users of AQMx not from LMICs and unclear distribution of benefits. It is too early to assess equity of WISER and CREWS.
Cost-effectiveness across the programme is generally moderate, with strong progress toward outputs and outcomes relative to the scale of investment, though comprehensive measurement remains challenging in some areas. ATACH and HSTRF deliver significant results compared to team capacity and modest funding, but both require improved governance and equity integration to enhance long-term sustainability. Bilateral budget transfers show promising cost-effectiveness by leveraging existing programmes and local networks, though it is still early to fully assess impact. The programme-funded post demonstrates high cost-effectiveness, achieving substantial influence and outcomes at low cost, despite difficulties in quantifying “influencing impact”. It is too early to assess cost effectiveness of CCAC, WISER and CREWS.
Assessment of whether the programme continues to represent value for money
In keeping with the programme’s appetite for innovation and experimentation, it represents good VfM, is mobilising finance and partners, and provides lessons for future FCDO programmes and policies.
## E: RISK
Overview of risk management
Programme risks were identified in the Business Case, and the programme risk register is used actively to manage risk throughout the year, and is reviewed and updated at least quarterly. The overall programme risk appetite is receptive given this is a new area of work and the programme is designed to be agile and innovative. The overall risk rating remains moderate. Residual risks are all within the directorate’s risk appetite for each category apart from the risk of any staffing cuts. 2026 FCDO restructuring risks reducing capacity too early to effectively manage-out the programme and maximise its gains in the new approaches.
Our risk appetite for risks relating to sexual exploitation, abuse and harassment, human rights abuses, and financial and fiduciary is cautious, with programming decisions taken with those in mind. Programme partners know the need to raise any issue directly with FCDO and via the reporting-concerns line.
The main current risk is ‘strategic and context’ relating to geopolitical dynamics and changing commitment to climate change and global health (e.g. US withdrawal from the WHO and Paris Agreement) and reductions in ODA that over time might impact delivery at country level and in global fora. Partnership working and using UK leadership in climate and global health continues to support delivery of goals. We are monitoring the situation and will consider action within the context of wider FCDO response and decisions and will work with like-minded partners to ensure progress.
With staff changes in the team over the last year, there is currently an increased ‘people’ risk as the team has managed recruitment processes and vacancies and inducted new colleagues into roles. A permanent health advisor has been recruited, but the programme officer's role remains vacant since March and will likely not be filled in the restructured FCDO. Programme delivery and management is being prioritised, alongside ensuring programme impacts and gains are used in future.
During this review period, a DDA on the World Bank HSTRF was conducted. The key risks identified were with delays on the Partnership Council and finalisation of the results framework, budget and workplan. All the areas have now been addressed by the World Bank team. Producing the DDA led to a closer dialogue with the Trust Fund team on governance structures and delivery, supporting set up of formal arrangements alongside more informal regular engagement.
## F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Partner	Summary of Performance
WHO	Good performance. The Secretariat has been providing regular reporting and been responsive to our requests for further detail.
EACDS (Expert Advisory Call Down Service)	Fair performance. Most work completed in the last review period, only work in Nigeria by Halcyon via DAI draw down continued to end March 2025. All key performance indicators delivered. However, there were some delays increasing costs. The Supplier forecasting was not accurate and invoicing delayed.
World Bank	Good performance. The fund was in inception and set-up phase to July 2025. Initial formal reporting slower than hoped but informal reporting received. This has improved following the recent DDA and governance arrangements tightened up.
CCAC, UNEP	Good performance. Formal and informal reporting is received on time. However, narrative reporting can sometimes lack the detail required.

FCDO capacity to deliver and manage the programme is summarised below.
Team	Roles	Summary of Performance
The programme team	SRO, PRO, 2 technical leads, and HEO ATACH lead	The PRO has contributed 60% of their time to overall programme management, and delivery of specific components. SRO dedicates about 30% of their time to programme oversight and leadership, and delivery of specific components. A significant proportion of SRO time is also dedicated to linking programme gains to policy, international and stakeholder engagement. In addition, a Heath Adviser, an Air Quality Lead and a Fast Stream HEO form part of the team and lead of relevant components.
Commercial	Global Health Directorate Commercial Lead; Commercial Grants Hub	Due to ODA cuts announcements, new arrangements were signed much later than hoped and complex procurement options avoided. Therefore, commercial engagement has been minimal but useful. Commercial lead has been kept informed of planned activity and any implications for potential contracts. Commercial grants hub have provided support with signed amendments to existing grants arrangements.
Bilateral Budget Transfer		These are linked to existing FCDO programmes and their experienced management teams, with dual-lock agreements setting our expectations and partnership approaches between teams. The team in Nigeria has provided regular informal updates and held joint AR field visits. The work has been independently commended by the World Bank, who have complemented our funding to cover states not supported by our contribution. Some delays in formal reporting are being resolved.
Finance	Finance Analyst and Finance Business Partner	The finance team has provided strong support and enabled compliance with forecasting, budget transfers and helped ensure relevant reporting is requested from partners.
Centre for Delivery		Monthly updates provided have kept the programme team abreast of new policies to ensure compliance and most effective use of ODA.

## G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
The monitoring activities during this period included: 1) Regular engagement with partners and formal and informal reporting that we receive; and 2) International engagement and field visits (see table).
Activity	How these informed programming decisions
WHO Global Conference, Cartagena, March	Engagement with partners provided feedback on the need/role for AQMx and CCAC’s capacity building work and provided an evidence base for making core contributions.
ATACH Annual Meeting and Global Conference, Brasilia, July	Reaffirmed the strong convening role of ATACH. Basis for recommending continued support in new health systems programme.
COP30 ATACH Day, Belém, November	Demonstrated global progress and best practice. Highlighted the power of the sharing platform to motivate action and ATACH’s growing reach to non-health actors. Basis for recommending continued support.
Field Visit to Nigeria, May	Assessed impact of support to Nigeria. Included visits to a PHC facility supported by CRIBS. Learning included impact of government and local buy-in. Engagement with UNICEF and local communities flagged need for an exit plan and sustainability. Learning applied to engagement with Posts and multilateral partners, and informed budget transfer decision.
World Bank Joint Learning Network Meeting, Bahrain, October	Assessed the country practice exchanges, guidance and World Bank activity. HSTRF governance was discussed, supporting DDA actions. Notable takeaway: World Bank is doing excellent work – we have flagged the need to be kept more informed, resulting in more regular communication. Findings are also feeding into wider thinking on working with the Bank amidst reduced ODA.
Engagement with CCAC Secretariat, London (June) and Paris (October)	Regular, senior (including ministerial) engagement with the CCAC since the UK became co-chair. This has provided deeper insight into CCAC operations and increased opportunities to advance UK priorities, including health. Shaped funding decisions and recommendations for continuation.

This AR has received inputs from technical and policy leads within the Climate, Environment and Health team and has been reviewed by the Senior Health Adviser in the Health Systems Strengthening team.
Evidence
Through the programme lifetime, evidence of what works to build climate resilient and low carbon sustainable health systems has grown and partners engaging on these goals also expanded. The experimental, opportunistic and agile nature of the programme has been instrumental in helping to expand that evidence base and learning by doing. Partners are adapting their approaches with the learning and good practice the programme supports. The programme has evolved to incorporate evidence and continues to stay at the forefront, consistently focusing on catalysing and opening space for climate-health action as milestones are progressed. The evaluation underway of ATACH will provide valuable insights for the platform itself, and for partners operating on agenda moving ahead. Evidence of the health impacts of climate change on a range of vulnerable and marginalised groups has also grown but less is known about specific approaches to address these in inclusive and coherent ways. As the programme is closing, future FCDO policy, programme and engagement work in global health should continue to seek to propel momentum on climate and health, expand the evidence of what works, and galvanise others to invest in the evidence and expertise base required.
Learning
Limited structured and formal learning processes have been adopted across the programme. Instead, the team has engaged actively with multilateral partners and Posts to assess the impact of our support and to adapt approach to maximise this. This has included:
1. Feedback from ATACH events and member surveys has been used to work with WHO regularly to consider approach, priorities and functions of the alliance to better meet the needs of countries. This led to the restructure and identification of strategy and workplan priorities.
2. Learning and best practice amongst the membership of ATACH is being systematically collected and is used to support peer-to-peer learning, and engagement and structure of international events such as the Global Conference held in July 2025 and ATACH General Meeting. These lessons strongly informed the Belem Health Action Plan.
3. Regular calls and in-person meetings with CCAC have supported review and learning. The three Board meetings in 2025 were also good opportunities to engage with the Secretariat, share lessons and assess impact of our support. We fed back our views regularly.
4. Regular engagement with Post in Nigeria and a field visit helped to capture learnings from work being conducted on the ground. This helped us share lessons learned with FCDO Networks, other country offices and to other countries through multilateral partners.
5. Supporting the set-up of a new fund at the World Bank came with teething issues that offered lessons on establishing governance structures and smoothing running of ways of working. The formality of a DDA served as a useful tool for structured discussions and to agree actions, and better understanding of trust fund governance. The Fund has a strong learning and global knowledge sharing component.
Key lessons for this programme have been recorded in sections A and C. Key lessons for wider FCDO development work:
  1. Programmes are a powerful tool to catalyse action and prove concepts for an emerging global policy priority. Complementing funding with policy influencing and stakeholder engagement is critical for impact and to shape the global offer. For example, our modest contribution to CCAC has had far-ranging impacts which has strengthened cross-HMG work with CCAC; progressed implementation of the UNEA-6 resolution; and, supported the set-up of ACAP, the first of its kind and addressing a key gap in air pollution support globally. Our engagement has secured health firmly in CCAC’s operational framework.
  2. Lessons, products and relationships built by this programme should inform future FCDO climate and health policy and programme work. Our credibility and relationships with and through ATACH, World Bank HSTRF and CCAC provide an excellent base for continued global engagement and broader health goals and will shape future global health programmes. Lessons from bilateral support and best practice from our partners should inform offers in the new Centres of Expertise.
  3. The programme and broader work on climate and health highlights that nexus areas are complicated. Effective integration across sectors and systems requires experimental, innovative and risk-taking approaches that brings together internal and external partners to collaborate and expands the evidence, expertise and tools available to succeed. They stand to deliver greater VfM and quality, sustainable results, optimising resources in a constrained environment. FCDO should take care not to lose its appetite to take risks and innovate as it restructures.
The learning aims for the next, final year is to capture lessons at PCR and share these with future FCDO programmes and policy teams to continue to integrate climate-health into broader global health, and climate and environment agendas.
Date of last narrative financial report	WHO-ATACH October 2025 / World Bank Informal Climate- Health Narrative Report 9 October 2025 / World Bank HSTRF First Annual Report November 2025 / CCAC Informal Narrative Report December 2025	Date of last audited annual statement	WHO-ATACH – June 2025 / World Bank HSTRF –September 2025 / CCAC – Interim Certified Financial Statement – 19th December 2025