## Annual Review Template

Title: Promoting Equalities Regional Programme (PEP-R)
Programme Value £ (full life): £6,880,000		Review date: 08/06/2025
Programme Code : 301533	AMP start date: 02/03/2023	AMP end date: 31/01/2027

Summary of Programme Performance
Year	2023/24	2024/25	2025/26
Overall Output Score	A	A
Risk Rating	Minor	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301533 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301533 Documents

A. SUMMARY AND OVERVIEW
Description of programme

This Annual Review reports on the activities of the Promoting Equalities Regional Programme (PEP-R) between 1 April 2024 and 31 March 2025.

PEP-R contributes to building a safer, more equitable and prosperous world, building the capability of the FCDO to focus on women and girls and other left behind groups across the scope of diplomacy and development policy, activities, and programming. The programme strengthens regional and international networks and partnerships, enhances effective use of research, evidence, and data, increasing targeted policy action, empowers civil society organisations, and supports national level shifts in discourse towards gender and equalities (G&E) issues.

The programme delivers this through technical and policy advisory support provided by insourced and external expertise; funding small catalytic initiatives through an Equalities Enabling Fund (EEF) and making learning and evidence on equalities widely available and accessible via an Equalities Resource Hub (ERH). This reporting period was the first full fiscal year of programme delivery.

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

Summary supporting narrative for the overall score in this review

PEP-R has scored A, outputs met expectation.  Output 1 and Output 2 scored A, both meeting expectation and Output 3 scored A+ moderately exceeding expectation. The programme has delivered against outputs across multiple components, either meeting or exceeding expectations.

Major lessons and recommendations for the year ahead

Lessons

L.01 Operating model: using an external provider for elements of programme management, including monitoring, evaluation and reporting of internally focussed processes presented efficacy and efficiency challenges, with duplication of work.
- L.02 EEF: Access to small amounts of flexible funding to advance equalities is highly valued by senior leaders in the global network; however, robust selection and close ongoing engagement between central teams and Posts is critical to ensure projects are not isolated events and that they sustainably contribute to wider programme objectives. Communicating impact across FCDO HQ and the network is crucial to ensure lessons are shared and the value of the work is more widely understood.
- L.03 EEF: Managing a programme with multiple small projects requires an elevated level of central programme management capacity. More efficient approaches will be explored in the next financial year; however, efficiency will remain constrained by limitations in FCDO systems.
- L.04 Internal and seconded advisors: Advisors can be drawn into work beyond the programme remit or focus on administration rather than provision of expertise in the absence of clear and consistent objectives.
- L.05 ERH: Activities required more funding than expected, with the resource mapping process taking considerable time and requiring sustained investment. This presented challenges to delivering an overall cost-effective solution.
Recommendations

R.01	Agree clear roles, responsibilities, milestones, and financial reporting processes with implementing partners at the start of next delivery phase. This will support smoother handovers in future changes to programme team staffing.	Owner: PRO / Time: June 2025
R.02	Ensure the central programme team is adequately staffed and equipped with the technical capacity to provide consistent oversight, facilitate learning exchange, and support adaptive management of EEF projects.	Owner: SRO / Time: Ongoing from April 2025
R.03	Finalise a capability strategy against which all programme advisors can set objectives. Include relevant stakeholders in development of objectives (i.e. geographic and thematic senior leaders).	Owner: SRO / Time: June 2025
R.04	Assess future of the ERH, considering how an overall cost-effective solution can be achieved within available funding levels.	Owner: PRO / Time: June -August 2025
R.05	Review and update programme logframe to ensure indicators are measurable and that planned methods for collection are realistic and proportionate to context. Consider more qualitative measures such as recording behavioural change at the outcome level through change stories.	Owner: PRO / Time: June-July 2025
R.06	Increase communications that share lessons and best practice to increase senior engagement, drive participation across the network and build understanding for our mainstreaming and capability approach.	Owner: SRO / Time: March 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Theory of Change (TOC)

The TOC outlines how the component inputs, advisory support, EEF and ERH will:
- Increase access to G&E resources
- Mainstream equalities into FCDO policy, programmes, and diplomacy
- Increase collaboration and understanding of country needs
- Share policy, evidence, and research as a global public good
This will result in:
- Increased confidence, enabling teams to embed equalities considerations into their work
- Strengthened relationships with relevant external stakeholders
- Increased external awareness of FCDO research and evidence on G&E
As a result, the FCDO effectively promotes G&E work through policy and programming, with the aim of creating a safer, more equitable and prosperous world where all women, girls, and excluded populations can fulfil their potential, claim their rights and be free from all forms of discrimination.

Changes to the theory of change

Major TOC changes since business case include:
Rationalisation of the TOC to include 3 inputs and 3 outputs that aligned to the programme components. The planned outcomes were re-worded to be clearer and more concise.
There have been no changes in-year to the TOC; however, the reporting framework was finalised and targets set. A business case addendum was completed to account for an increase in funding to enhance delivery, in alignment with the existing TOC.
- Advisory capacity: The number of regional gender and equalities advisors (RGEAs) was increased from four to six roles, and two new advisory roles added to focus on increasing consideration of the Public Sector Equality Duty (PSED) across the breadth of FCDO work.
- EEF: To streamline similar programme management activities, additional funding was allocated to PEP-R to fund LGBT+ interventions, instead of operating a separate LGBT+ rights fund.
The TOC logic, supporting evidence and assumptions remain and hold up against experience implementing the programme to date, with feedback gathered at regular intervals from advisors, training events and the ERH.

Mainstreaming equalities into FCDO policy, programmes, and diplomacy has always been a core focus of the programme, and this will continue in 2025/26. The TOC will be reviewed and reflect our intention to increase the FCDO’s capability on mainstreaming G&E across all our work.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

PEP-R is making progress towards planned outcomes and overall impact. It has delivered against outcome indicator 1, meeting expectation, has moderately not met expectation against outcome indicator 2 and moderately exceeded expectation against outcome indicator 3.

Outcome 1: Advisory and technical assistance are increasing knowledge and confidence, when accessed. Although data is limited, respondents to a feedback survey administered to EEF project leads shows over 90% of teams reported improved knowledge on G&E; however, ability to include LGBT+ considerations scored lower than other equalities areas. 66% also reported they felt better equipped to plan and budget for projects that mainstream G&E. Although meeting the target, this suggests that further work is needed to translate improved knowledge into ability to action. This was also evidenced in the quality of proposals submitted to the EEF, which had greater consideration of accessibility, inclusion, and safeguarding than previous years. The key advisory support offered by the programme is outlined below:

RGEAs: Ongoing technical support was provided to the network by the advisors. They ran multiple learning and development sessions which strengthened regional collaboration and shared learning, building capability to counter rollback, including through strategic communications and coalition-building. Feedback indicated an increase in the understanding of mainstreaming and mechanisms were put in place to encourage participants to disseminate learning beyond their immediate teams to drive an FCDO wide effort. 79% of Posts (75) covered by RGEAs had a nominated G&E lead. No leads are established in certain locations due to lower levels of staffing, reflecting a challenge with this indicator not capturing the diversity of contexts the programme is operating in, rather than an issue with programme delivery.

- Equalities Impact Unit (EIU): Introduced this year, the EIU advisors have significantly raised FCDO’s equalities standards. They have embedded equalities into planning, spending, and programme cycles through updated tools and mandatory Equality Impact Assessments (EIAs), including for Business Cases over £40m and Country Business Plans. Their targeted support and capability-building initiatives, particularly applying the Public Sector Equality Duty (PSED), have improved the quality of how the PSED is applied and monitored through the Management Assurance Process.
- Capability Secondee: The secondee has delivered numerous initiatives, from producing new eLearning modules to leading on Equalities Week which reached over 3600 FCDO staff. 69% of attendees at capability sessions provided positive feedback; however, also identified that training was often not tailored to the audience, leaving some attendees unsure of their role or next steps. To enable teams to embed equalities considerations effectively into their work, training should include practical guidance relevant to specific roles.

Outcome 2: Five teams reported strategic follow up activities, driven by the EEF Most projects ended in March, therefore data available on follow-up is limited at the time of writing. Ten teams reported engagement with external G&E events, indicating an increase in engagement with external stakeholders, crucial when building relationships and credibility. Evidence to date suggests there may be a risk that, without adequate engagement and follow-up, projects are limited, isolated interventions that are not delivering sustainable results or enabling future activity. These results indicate that there has been insufficient progress against the intended outcome; however, there is evidence that activities and outputs delivered by PEP-R have been key to building relationships on G&E across the overseas network. All responses to the EEF project lead survey reported “strengthened partnerships” and reports from multiple Heads of Mission highlighted the importance of the EEF to delivering their priorities. Measuring progress towards this outcome proved challenging. The focus on quantitative metrics in the logframe indicators missed key details and data sources and proved unfit for fully measuring the impact of programme activity. A review of the logframe is recommended to ensure indicators and methods for collecting and measuring results are appropriate, to enable better assessment of the causal links between activities, outputs, and outcomes. Despite the logframe indicators not capturing the contribution of the RGEAs, these advisors played a critical role in strengthening relationships with external stakeholders. For example:
- RGEA MENA led a cross-FCDO effort to engage Saudi Arabia ahead of their chairing of CSW in Mar 2025. This strategic engagement plan included a bilateral visit to Riyadh and sustained engagement in Geneva and New York. The result was a strong Political Declaration delivered at CSW.
- Caribbean Women Peace and Security (WPS): RGEA LATAC secured funding through the Integrated Security Fund to enable BE Georgetown to launch a WPS initiative, establishing a new partnership with UN Women.
- Chile Gender Equality MoU: RGEA LATAC visit to Chile included engagement with the Ministry of Foreign Affairs and Ministry of Women, resulting in a gender equality MoU being signed with the Chilean government.
Outcome 3: Since launching, the ERH has reached a total of 20,195 users, with 77% users accessing resources. 5,331 resource pages were visited, with 4,117 requests to access resources. Newsletter sign-ups also indicate growing engagement, with 710 subscribed users. Findings from a user survey showed 77% of respondents reported improved access to G&E resources compared to 12 months ago with 61% confirming that engaging with ERH resources improved their awareness of G&E considerations and their relevance to their work. 48% agreed that having access to tools from the ERH helped them feel more empowered and effective in their roles. This suggests that despite successfully increasing awareness, the majority of users did not find the ERH an effective tool to enable them to embed equalities considerations into their work. Costs associated with the ERH, such as identification of resources, were high, despite partner efforts to find efficiencies. Audience engagement has been driven by development of original content and a strategic communications plan. The implementing partner has identified direct engagement with users through webinars, live discussions, or original content as critical for future growth of ERH audiences.

In the coming year the TOC will be revisited to ensure resources are allocated to components with the strongest link between inputs and impact and, therefore, value for money confidence. The programme may benefit from an effort to consolidate its focus and results to ensure the individual activities add to a sum greater than the constituent parts. PEP-R will continue to consolidate the results achieved to date, with a renewed focus on the strategic alignment. The programme will remain flexible to respond to changes in the global operating context that may undermine progress to date.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This programme was created to capitalise on opportunities since the merger of the FCO and DFID. It has a unique mandate, drawing together advisory expertise, with strategic funding, to advance equalities priorities across the network, delivering impact and driving wider FCDO objectives. No other programme fulfils this mandate. The programme continues to represent good value for money. However, recognising changes to the operating context, a reassessment of components is required to ensure the programme has strategic alignment and delivers for the organisation. The challenges and opportunities identified in the business case continue to exist, and this programme is well situated to respond. PEP-R remains integral to the Directorate Business Plan. Improving organisational capability and mobilising action will drive equalities priorities across the global network and will ensure teams understand how considering equalities makes their work more effective, efficient and higher impact.

## C. DETAILED OUTPUT SCORING

Output Title	Posts have increased access to G&E technical advice, support, and capability-building initiatives.
Output number:		1	Output Score:	A
Impact weighting (%):		34%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Type of technical advisory support provided to staff as part of PEP-R advisory/ technical support.	5	Outputs met expectation
1.2 # of staff L&D opportunities held across PEP-R components for G&E.	50	Outputs moderately exceeded expectation / A total of 59 opportunities delivered in this reporting period.
1.3 % of positive feedback received from advisory and TA support provided	75%	Outputs moderately did not met expectation / 73% of feedback on advisory and technical support was positive.
1.4 # of PSED capability initiatives offered to the network	10	Outputs moderately exceeded expectation / 14 capability initiatives offered in this reporting period

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 scored A, meeting expectations. Indicators 1.1, 1.2 and 1.4 met or moderately exceeded expectations; however, indicator 1.3 moderately did not meet expectations. Taken as an average, the output met expectations. Technical assistance has been delivered to EEF project teams by the Social Development Direct, including via workshops and one-to-one bespoke support on core themes: disability inclusion, safeguarding, inclusive programme management and MEL. The modality of this provision was reviewed in year and shifted to focus on one-to-one demand-led provision, in response to engagement levels and feedback. Policy advisory support was provided in all regions covered by RGEAs. The programme delivered 59 learning events in the period, through the RGEAs (18), Capability Secondee (26) and delivery partner, covering key issues such as ending violence, LGBT+, disability, gender equality and how to mainstream equalities issues across their work. Recruitment processes outside of this programme’s control resulted in some gaps in provision, notably in Sub-Saharan Africa and South and Central Asia. Differences between regions and resource constraints in the network have presented challenges with achieving a cohesive and consistent delivery offer of advisory support. An e-learning programme was created and series of virtual workshops/seminars/panel discussions run across the network. An additional 14 events focussed on PSED, moderately exceeding expectations. This result reflects a low response rate to feedback surveys and should be treated with caution given limitations in the sample. The PSED initiatives have delivered against the programmes planned outcomes with clear linkages between output and outcome level changes. Across these initiatives, 73% of feedback received was positive, slightly below target. The team have also increased access to guidance through the central Equalities Gateway and development of a training module.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones for this output were finalised in year and an additional indicator added (1.4) to give a specific focus on driving and measuring the impact of PSED-focussed initiatives. Changes to this output will be required in the coming year, reflecting key changes to this programme.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR:
Recommendation	Status	Update
Synergies should be explored with other aspects of the programme. The secondee and RGEAs can play an effective role in supporting Posts applying for the EEF and identifying resources to include on the ERH.	Complete	Synergies between advisors and other components, have started to be realised, including between the RGEAs and EIU to drive the increase in compliance. In this reporting period advisors played an active role in the process for allocating project funds and have supported identification of resources for upload to the ERH.
On-boarding of the RGEAs should include clear communications to networks of stakeholders to build buy-in to the roles but also to clarify what advisors will deliver and ensure their roles remain linked to delivery of the programme objectives.	Complete	A role overview pack was developed and has been regularly cascaded to key stakeholders, giving a clear remit to the advisory roles. A secretariat function has been established to further clarify delivery objectives ensuring alignment with programme objectives.

Lessons learned this year
L1.1 Demand driven work from the network can result in reactive support and initiatives rather than proactive activities that drive the bigger strategic picture. This was notable in the central capability offer, which focussed on providing support to individual initiatives, above the development of the capability strategy to assess where support would be most impactful.
L1.2 Efforts and results are naturally different based on type of Post, such as between large Posts and very small embassies (VESPs) and posts or ODA and non-ODA. Different feedback forms used across components made it cumbersome to report on this output. A standardised feedback form used across components, capturing audience details, would be more efficient and ensure detail is captured on who is engaging with the programme and identify where and how advisory support achieves the greatest impact.
L1.3 Recruitment and onboarding has taken considerable time causing gaps in some roles and regions. Addressing this is beyond the scope of this programme, however, time and potential gaps caused should be planned for and mitigated where possible.

Recommendations for the year ahead
R1.1 Expand outreach across the FCDO network to engage teams not traditionally involved in G&E work. Develop and deliver tailored content and engagement strategies that reflect specific roles, regional contexts, and thematic priorities.
R1.2 Ensure all advisory roles have clear objectives that link back to the programme logframe and FCDO priorities. Working across Gender, Equalities and Rights department, the programme should refine the offer to the network, outlining an approach to mainstreaming that can be adapted to meet the context.
R1.3 Design and implement a standardised feedback tool for use across all programme components. Ensure the tool captures relevant audience data, is easy to use, and supports proportionate, targeted data collection to inform programme learning and adaptive management.

Output Title	Posts are enabled to carry out new, catalytic, and enabling G&E work through access to the EEF, opening up opportunities to work with local organisations and stakeholders.
Output number:		2	Output Score:	A
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 # of projects funded through the Equalities Enabling Fund	35	Outputs met expectation / 40 projects were proposed and 34 mobilised and delivered
2.2 # and type of learning products from EEF projects disseminated within and outside of FCDO.	20	Outputs met expectation / 20 learning products including reports, blogs and toolkits developed so far

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 scored A, with outputs meeting expectation. 2.1 and 2.2. both met expectation and are on track to achieve end of programme targets. 40 projects were proposed and 34 delivered by the end of the year. Projects concluded end of March 2025, and, at the time of writing, some are yet to report back results. The majority have produced learning which has been shared internally, and externally where appropriate. Learning products included reports, blogs, white papers, and toolkits.

In the first full year of project delivery, the programme successfully implemented 34 projects across 30 countries. Projects have been impactful and catalytic, contributing positively to equality objectives. In several cases projects have successfully adapted to challenging and changing operating contexts to enable meaningful and safe delivery. Challenges with programme management capacity in the overseas network and changing domestic contexts led to some delays in mobilisation and six project cancellations. Examples of successful projects include:
- Supporting the launch of the first women-led, faith-inspired network for climate action at a high-level Wilton Park conference.
- Establishing a network of LGBT+ educational outreach spaces in Kosovo creating a safe inclusive environment for LGBT+ youth.
- Improving access to education, employment, and training for visually impaired young people in Somalia.
- Producing a policy paper on tackling the gender pay gap in Mexico.
Case study 1: Tackling the Gender Pay Gap in Mexico
The UK has experience and expertise in tackling the gender pay gap, with large employers required by law to publicly report their gender pay gap. BE Mexico City developed a project around sharing UK experience and expertise via the Office for Equality and Opportunity, commissioning local research, and producing a policy report on how to close the gender pay gap in Mexico. The report was launched successfully in March 2025, with recommendations presented to representatives of the Mexican Congress. The report launch event also gained media coverage, sparking a national conversation. Learning from the project will inform future events, partnerships and initiatives related to gender equality and inclusive economic development.

Case study 2: Going Further, Faster: Towards Radical Collaboration among Multi-faith Women-led Climate Action Networks

In collaboration with the Irish Embassy, Islamic Relief and the International Union of Superiors General, BE Holy See’s project launched a new network of women of faith, the first of its kind committed to climate justice. Launched at a Wilton Park-organised event near Rome, over 50 participants estimated to represent 73 million women worldwide (including former President of Ireland Mary Robinson) committed to working together, learning from each other, and scaling up the climate action they are taking. They committed “the power of billions of women to ignite global momentum to profound, lasting change … in a way that leaves no one behind” and to “replicate this way of being in our own institutions, communities, and countries.” The launched concluded with an audience with Pope Francis. The project team are continuing work on the modalities, funding, and structure for the network.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones for this output were finalised in year and there were no other changes. Changes to this output will be required in the coming year, reflecting key changes to this programme.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR:
Recommendation	Status	Update
The EEF criteria and strategic focus should be simplified, and more support given to Posts ahead of the next funding window to enable more high-quality proposals that meet the programmes outcomes.	Complete	This year the EEF criteria was streamlined. Teach in sessions with policy teams advised how to tailor bids to a policy area. Advisors supported Posts to develop proposals. Social Development Direct provided technical advisory support with disability inclusion, safeguarding, inclusive programme management and MEL.
Create a more targeted approach for bids to help achieve a fully balanced portfolio across themes and geographies.	Complete	A weighted scoring system was implemented to assess strategic alignment. This included geographies, thematic policy areas and wider priorities.

Lessons learned this year:
L2.1 30+ projects exceeded the capacity for effective central oversight and programme management.
L2.2 Some projects were hindered by the capacity and capability at Post, with gaps in project management, due diligence, and reporting capabilities which are beyond the scope of this programme to address.
L2.3 The ability of the EEF projects to be flexible and responsive to evolving contexts in which they operate is crucial to success.
L2.4 Aligning the EEF with similar internal funds created efficiencies and enabled better strategic planning.
L2.5 Involving key stakeholders from policy teams improved strategic alignment and resulted in a more balanced selection of projects across themes and geographies.

Recommendations for the year ahead:
R2.1 Improve efficiency by funding fewer, larger projects; replace detailed reporting with mid-point check-ins to remove burdensome reporting; and simplify financial management by allocating budgets directly to Post.
R2.2 Implement a more structured governance process for teams responding to changing operating contexts which require project adaptation.
R2.3 Embed sustainability planning throughout the project lifecycle to ensure long-term impact and enable follow-on work.

Output Title	FCDO G&E resources are shared as a global public good through the Equalities Resource Hub.
Output number:		3	Output Score:	A+
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.Equalities Resource hub designed and launched	ERH designed and launched	Outputs met expectation
2. % of total and repeat users accessing G&E resources on the Equalities Resource Hub.	5000 users / 10% are repeat users	Outputs substantially exceeded expectation / 20,195 users
3. # of website resources accessed	500	Outputs substantially exceeded expectation / 4,117 clicks to resources
4. # of marketing and communication materials disseminated to priority users in the Hub (Y2 of implementation [Y3 of programme] onwards).	30	Outputs moderately exceeded expectation / 45 materials disseminated to priority users
5. # of resources uploaded to the Equalities Resource Hub	200	Outputs met expectation / 200 resources uploaded to ERH

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 scored A+, moderately exceeding expectation. 3.1, 3.4 and 3.5 met or moderately exceeded expectations and 3.2 and 3.3 substantially exceeded expectation. Taken as an average, the output moderately exceeded expectation.

The ERH intended to create an externally accessible ‘centre of expertise’ as a global public good to showcase and share what the UK had to offer from across its funded programmes and policy expertise. It was designed and launched during this period, with a virtual event attended by 250 people. The event received positive feedback on the inclusivity of its format, including live sign language interpreters. The ERH had 20,195 users since launch, with 4,117 accessing resources. Most activity happened in the last three months of the period. Although there is clear audience growth, reflected in user numbers and achieved through an effective strategic communications plan, it is unclear who users are and what level of engagement has been achieved with target vs secondary audiences. It is therefore not yet clear that it is fulfilling the original intention and mandate. More work is required to understand who is using the ERH and why they are accessing resources to better understand its impact. Implementing partners suggest monitoring needs to encompass qualitative as well as quantitative measures, to better capture this. 61% of respondents to the ERH user satisfaction survey agreed or strongly agreed that engaging with ERH resources improved their awareness of G&E considerations and their relevance to their work, however only 48% agreed or strongly agreed that having access to these tools helped them feel more empowered and effective in their roles. The target of 200 resource uploads in the period was met; however, the mapping and preparation of resources required more inputs than anticipated.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones for this period were agreed in-year and an additional indicator to measure the number of resource uploads was added to focus efforts on ERH being a live platform, mitigating the risk of it appearing static. Changes to this output will be required in the coming year, reflecting key changes to this programme.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.

Progress on recommendations from the previous AR:
Recommendation	Status	Update
A clear communications plan will need to be developed for the ERH launch to ensure the content is widely shared and utilised.	Complete	Implementing partners brought in a dedicated ERH manager responding to this recommendation; and delivered a strategic communications plan to engage audiences.
Further engagement with teams across FCDO should become a routine part of the ERH management process to ensure new resources are mapped and prepared for uploading at the future date.	Complete	Regular engagement with key internal stakeholders was established in year to ensure new resources were identified for publication.
We should also explore what external partners (civil society, donors, and governments) we could partner with in future to contribute to ERH ongoing development.	Paused	As the ERH launched later in-year than anticipated, due to events outside of the programme’s control, external partnerships were not explored in this period. This will be considered as part of the review of the ERH’s future.

Lessons learned this year:
L3.1 The process for mapping resources is time-intensive and requires sustained attention to maintain a coherent, quality, curated library.
L3.2 Feedback and analytics on how the ERH is being used by different audiences is limited. It is difficult to measure who is accessing resources, how they are being used, and to draw causal links with the programme outcomes.
L3.3 A strategic communications plan is critical to connect audiences with resources. As this was not integrated from the outset, momentum did not build until the end of the period when a dedicated communications function was in place.
L3.4 The current indicators do not measure whether the intervention is reaching the target audience or meeting their needs.

Recommendations for the year ahead:
R3.1 Review the programme components to assess impact and value for money, aligning future delivery with available funding, FCDO priorities and the UK Centres of Expertise model. Identify opportunities to streamline costs and improve efficiency.
R3.2 Explore ways of sharing learning from this component further, building on the value of resource mapping and related activities to inform future programming and external engagement.
## D: VALUE FOR MONEY

Key cost drivers and performance
- Staffing and salaries: This is a significant cost driver for the programme (for both insourced and outsourced roles), travel and in-country costs.
- EEF: Funding is provided to small external organisations to deliver interventions to advance G&E priorities in-country.
- ERH: The design, launch and maintenance of the ERH, including ongoing communication and curation of resources.
- Cross cutting support: Partner fees are a significant cost driver, providing technical assistance and programme management support.
VfM performance compared to the original VfM proposition in the business case

Economy: The principal cost drivers are staff salaries and travel costs. Staff salaries and in-country costs remain in line with set FCDO parameters. Insourced roles for the EIU and RGEAs offer significant savings on sourcing the equality roles externally as day rates for external experts with the level of expertise are projected to be more than double the in-house costs. Travel costs are incurred in line with FCDO guidelines, and travel opportunities are maximised by combining key events, monitoring missions and training. Working with the external partner, fees and staff costs were agreed at inception and remain in line with the expected consultancy fees and overhead costs are reasonable; however, it would be more economical to complete these activities inhouse. Significant resource is required to map resources, and prohibitive costs are required for identification, preparation, and publishing of resources.
Efficiency: The programme has adapted to challenges, directing resources to where they will have the most impact. There have been challenges with the quality of some external programme management support, inefficiencies in reporting and MEL processes, and with duplication of programme management activities between FCDO and the external partner. It would be more efficient to complete some activities inhouse. Different modalities of technical assistance had varying impacts, for example drop-in sessions had less impact than anticipated, whereas one-to-one demand led support proved a more efficient use of programme resources. Insourced project-funded posts improved efficiency as FCDO staff have better access to and understanding of internal systems, resources, and decision-making processes, enabling faster collaboration, learning, and compliance. Additionally, control over recruitment and management ensures teams are optimally skilled and focused on high-priority tasks.
Effectiveness: There is a clear increase in equalities considerations in portfolios, policies, and regional strategies. EEF proposals for 2025/26 showed greater meaningful integration of key considerations such as disability inclusion. Access to the EEF has enabled teams to drive conversations in country, support women to protect their rights and develop new tools and expertise. Most reported projects were implemented effectively; however, in some contexts there were challenges with downstream partner delivery. Insourcing advisory support offers an effective way to provide technical assistance. It enables FCDO staff to build deep expertise, apply learning across FCDO, and contribute to more coherent, evidence-based strategic decisions. Their roles also improve access to sensitive information and foster trusted relationships, which are crucial for impactful advisory work - something that outsourced roles have historically struggled to achieve due to security and access limitations.
Equity: The entire programme has a focus on driving gender equality, disability inclusion, LGBT+ rights and other equality considerations across the FCDO. The EEF supports localised and community-based interventions, with communities and key stakeholders engaged during the design.
Cost-effectiveness: The programme is successfully building capability and using evidence and technical assistance to drive our foreign policy objectives, leveraging limited resources to deliver across the network and multiple thematic priorities.

Assessment of whether the programme continues to represent value for money
The analysis undertaken during the development of the business case has not significantly changed. Based on the above, there is sufficient evidence the programme demonstrates VfM and should continue. It is achieving results, and the strategic outputs are driving change across the FCDO. There are areas for improvement, and a review of the external programme management, ERH and mechanisms for external technical support is recommended.
Despite uncertainties around future ODA funding, by developing capabilities that drive organisational priorities, this programme delivers for the FCDO. It is uniquely positioned across the network to deliver change, both in the UK and in the overseas network.

E: Risk

Overview of risk management
The programme overall risk rating is moderate based on the risks identified in the programme risk register and the mitigation measures in place. The risk appetite for the programme reflects FCDO’s organisational risk appetite and delivery sits comfortably within this. The programme risk has been upgraded from minor to moderate to reflect the inherent risks associated with working with smaller organisations and the global context in which Posts and equalities or rights-focussed organisations are operating in. The original implementing partner DDA was reviewed, and the assessment remains a proportionate assurance to the risks of the programme.

There have been some areas of pressure during this period, particularly in establishing an effective hybrid delivery approach between external implementing partners and insourced delivery. We have worked closely with external partners during this period to establish an effective approach. Quarterly meetings have included risk reviews and escalation of potential issues.

The main delivery mechanism is through insourced advisory roles. Risks remain around how these roles operate coherently and cohesively with each other and the other programme components. A new secretariat function has been established to coordinate advisors and drive consistency in delivery of programme objectives.

The risks associated with working with smaller organisations remain and have been proactively managed throughout the year. Increased communication between the Programme Management Team and local project teams has mitigated these risks, alongside bespoke technical assistance on safe delivery. Further additional controls, to support safe delivery of EEF projects, have been identified to implement in future years.

Climate and environmental risks associated with the programme are assessed to be low. The programme has proactively sought opportunities to support positive climate action, for example, by funding catalytic initiatives that advance rights and positive change for climate/nature. Several risks are driven by changes to global development funding. The programme will need to continue to respond to contextual changes; retaining the flexibility to pause, stop or amend activities during the next period. The programme risk register will be reviewed and amended to reflect any programme restructuring.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

PEP-R is supported by an external partner consortium led by Plan International, with Social Development Direct leading technical assistance and implementation of the ERH and SightSavers managing the secondee. Programme management of EEF initiatives is devolved to internal teams, with oversight by the FCDO programme team which also oversees the insourced advisory roles. The structure and processes of the programme board were updated in the year to establish an internal governance board alongside a partner delivery board. Partner board meetings have facilitated updates on key delivery and dialogue on risk management.

Some programme management activities were duplicated between FCDO, and external partners and some reporting and MEL processes were inefficient and cumbersome when deployed. Steps were taken to reduce inefficiencies created through the programme operating model, reducing duplication, and improving the quality and timeliness of fiscal reporting. It is recommended that future agreements incorporate well-defined milestones, clear roles and responsibilities and reporting requirements at the start of the delivery period.

Six confirmed EEF projects were cancelled in-year with 34 successfully delivered. The FCDO programme team proactively provided support to ensure compliance and effective delivery. However, programme management capability and capacity remained an issue for some teams. A more focused and strategic approach with a reduced number of live projects is recommended. To avoid underspend, a reserve-list of projects should be kept, and clear milestones for project mobilisation established, to ensure projects disburse a sizeable portion of funding ahead of the calendar year-end.

The programme successfully recruited and integrated eight insourced roles, with four of these positions based overseas. All insourced roles have delivered timely reporting. Overall programme underspend was 15%, driven by:
- Late EEF project cancellation and underspend and overdue payments declared by teams at the year end.
- Underspend of 11% by the external partner driven by lack of demand for technical assistance and a reduction in MEL activities, requested by FCDO.
Fiscal management overall has significantly improved due to changes to the EEF, a new budget agreed with the external partner and greater clarity on managing in-sourced roles.

EEF: Projects have effectively budgeted and forecast in their expenditure currency in accordance with internal guidance. The requirement for quarterly forecasts has been instrumental. Although reliance is placed on teams for accurate, timely reporting, proactive follow-ups ensured that most variances were identified early, allowing for reallocation of funding. Fiscal management of the EEF required considerable resource from the central programme team. Though there are opportunities to improve efficiency, this will continue to require a higher level of project management resource than anticipated in the original business case. It is recommended that budgets are transferred to teams to manage locally in future years.

Implementing partner: The quality of fiscal management required improvement at the start of the period. The programme team worked with the external partner to produce an activity-based budget linking costs to activities and deliverables. Continued use of an activity-based budget is recommended to enable better monitoring. Establishing clear milestones in future agreements will facilitate greater accountability and transparency.

Insourced roles: There were significant challenges in forecasting costs due to unforeseen internal recharges. The programme team collaborated with FCDO teams to clarify additional expenses and ensure all costs were captured in forecasts. The programme is well placed to capture these costs accurately in future years.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
This annual review has been conducted by the FCDO programme team as a desk-based exercise drawing on monitoring reports, learning products, alongside interviews and surveys of 16 EEF project leads. A field visit to an EEF project was also completed in February 2025. Monitoring activity during the period included quarterly activity reports and finance reports from the external partners, end of year project completion reports for EEF projects, quarterly reports from advisors and regular feedback gathered from training initiatives. The programme board has monitored progress on a quarterly basis. Regular and ongoing support and monitoring of EEF projects has also been conducted by the programme team. MEL support was provided by the delivery partner; however, due to challenges monitoring internal activity, this was reduced to focus on activity directly delivered by external partners. As that the programme takes a new and unique approach, the programme team take a dynamic approach to MEL and test the different components.

Evidence
There have been no changes in the evidence base for the programme. This review is based on limited evidence in some areas. Twelve out of 34 teams responded to the feedback survey, and therefore, due to the small sample size, the evidence gathered may not be reflective of the wider network and should be treated with caution. As deploying a larger annual survey is not practical or proportionate, alternative sources of evidence should be identified in future years.

Learning
Learning processes have focussed on the EEF and the ERH. The majority of EEF projects produced and shared learning, including via internal and external blogs, published reports and evidence and presentation of learning to internal and external audiences. Several case studies of projects and workshops were developed and disseminated internally, to inform future programming. To share learning on the development of the ERH the FCDO Programme Team have participated in an internal research project to better understand the benefits, risks and costs associated with the operation of programme websites.

Key learning:
- The ability to respond to new government priorities and changes in operating context are critical to effective delivery.
- There is high demand for flexible funding to support small strategic initiatives delivering against equalities objectives.

Key learning aims for next period:
- Explore how impact can be delivered through a deeper focus on sharing UK expertise.
- Consolidate and disseminate widely, EEF project learning; revisit projects to capture longer term impact.

Date of last narrative financial report	10/04/2025	Date of last audited annual statement	15/04/2025