## Annual Review

Title: Promoting Equalities Regional Programme
Programme Value £ (full life): £6,880,000		Review date: 08/06/2026
Programme Code: 301533	AMP start date: 02/03/2023	AMP end date: 31/01/2027

Summary of Programme Performance
Year	2023/24	2024/25	2025/26	2026/27
Overall Output Score	A	A	A
Overall programme risk rating	Minor	Moderate	Minor

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301533 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301533 Documents

## A: SUMMARY AND OVERVIEW

Description of programme

This Annual Review reports on the activities and results of the Promoting Equalities Regional Programme (PEP-R) between 1 April 2025 and 31 March 2026.

The Promoting Equalities Regional Programme (PEP-R) contributes to building a safer, more equitable and prosperous world by strengthening the FCDO’s ability to support partner countries to deliver for women and girls and other left-behind groups using our foreign and development policy, diplomatic engagement, and programmatic interventions. PEP-R also strengthens regional and international networks and partnerships, enhances effective use of research, evidence, and data, and increases targeted policy action on equalities issues. The programme’s objectives are delivered through insourced expertise providing policy advisory support; an Equalities Enabling Fund (EEF) supporting small catalytic initiatives; and an Equalities Resource Hub (ERH) making learning and evidence on equalities widely available and accessible.

The programme has adapted in year to respond to reductions in ODA funding. This Annual Review reflects on a period where resources were refocused and, as a result, the programme was delivering against an updated delivery plan with new results targets. During this period, the programme reprioritised resources to provide internal advisory support linked to strengthening the quality and inclusivity of UK engagements. As a result, the Equalities Resource Hub closed in December 2025, and the secondment finished alongside the conclusion of the grant agreement with Plan International on 27 February 2026. The Equalities Enabling Fund also concluded at the end of March 2026. Further grants under the EEF are not currently proposed within the remainder of the programme lifecycle.

The programme is due to end in January 2027. A no cost extension to March 2028 is being considered.

Summary supporting narrative for the overall score in this review

The programme has scored A; outputs met expectations. Output one and two performed strongly, scoring A and A + respectively. Output three was new this year and moderately did not meet expectations against performance indicators, scoring B, however this review indicates this is due to resourcing issues beyond this programme’s control, rather than weak performance. Overall, the programme has delivered against outputs across multiple components.

Major lessons and recommendations for the year ahead

- Regional Advisers: a secretariat function improved coordination, coherence and collaboration between advisers but was not in place for the full period due to resourcing gaps. The programme and future models for delivering advisory inputs should consider how to establish a sustainable mechanism for coordination.
- ERH: key lessons from delivery of the ERH were captured in year and are summarised in this review.
- Secondment: key lessons from the external secondment were captured during an exit interview with the secondee to inform any future, similar secondments.
- EEF: transferring funding directly to posts to manage locally, improved programme and financial management processes. Though efficiencies were achieved, specific risks around compliance required active management to ensure funding was spent as intended and within the financial year.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The PEP-R programme aims to contribute towards building a safer, more equitable and prosperous world, where everyone can fulfil their potential, realise their rights, and be free from discrimination. The programme’s desired impact has remained consistent: equalities are meaningfully mainstreamed across the full scope of FCDO’s policy, processes, and systems to support improved quality, inclusivity and effectiveness of interventions, diplomatic engagement, and policy influence in partner countries.

The theory of change was reviewed and updated at the start of this reporting period to ensure the programme adapted to contextual changes, and decisions to close the ERH earlier than the programme’s planned end date. The planned outcomes and outcome indicators were updated to reflect these changes.

The programme’s revised theory of change (TOC) outlines how advisory expertise and catalytic funding will:
- Provide the tools, training, and guidance to enable FCDO staff to design and deliver inclusive policies, programmes, and diplomatic activities
- Develop new, and strengthen existing partnerships, internal and external
- Embed equalities considerations at key decision-making points.
Resulting in:
- Gender and equalities considerations being meaningfully mainstreamed across diplomacy, policy, and programming
- Strategic partnerships being leveraged to influence national, regional, and global approaches to gender and equalities
- Equalities considerations being mainstreamed at key decision-making points.
These interventions supported improved quality, inclusivity and effectiveness of programmatic interventions, diplomatic engagement, and policy influence in partner countries. Overall, the programme retains a coherent theory of change, with a rationalised delivery model. However, it will need further amendments ahead of the next period, to reflect the conclusion of small grants under the Equalities Enabling Fund.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme remains on track to deliver its intended outcomes. Improved capability is being demonstrated through teams mainstreaming gender and equalities across the breadth of diplomacy, policy, and programming, captured in case studies. Staff engaging with programme components reported increased competence and confidence in mainstreaming equalities considerations in their work (83% of respondents). This contributed to changes in how programmes and policy engagement were designed and delivered in partner contexts, including stronger consideration of risks, inclusion, and safeguarding. However, a low response rate limits the reliability of the data and reduces confidence in applying these findings to wider outcome level conclusions. Some evidence of partnerships being developed and leveraged to influence national, regional, and global approaches to gender and equalities were captured during this period, however, more work is needed to better record how programme activity is contributing towards specific outcomes. Accountability mechanisms were also maintained during this period through the work of a small insourced advisory unit.

Case study: Strengthening responses to violence against women and girls in Mauritius through strategic partnerships: The UK formed a strategic partnership with the Government of Mauritius to support practical improvements in responses to domestic abuse, funding specialist practitioners to provide training for frontline officers and senior leaders. This directly informed national practice, strengthening approaches to risk assessment, evidence led prosecution and multiagency working, and prompting agreed actions to strengthen implementation of existing strategic priorities on domestic abuse.
Case study: Strengthening gender integration in UK migration policy in North Africa: The programme commissioned a flagship cross-government evidence product on the gendered risks of migration in North Africa, addressing a critical gap in how gender was integrated into UK migration policy and programming. The analysis has been used to improve the quality of gender analysis in migration work, convene new policy discussions across government, and inform follow-on governance proposals on gender mainstreaming standards, demonstrating sustained policy traction beyond publication.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This programme is well placed to respond and adapt to changes in the UK’s approach to international development, particularly moving from providing grants to expertise. Case studies captured during the period demonstrate components are delivering tangible benefits and contributing towards departmental goals and priorities. In the next period, it will deliver through a new delivery architecture, contributing to a department wide portfolio strategy and working within a new Women and Equalities Community of Expertise. A no cost extension is being considered to extend the programme by 14 months to continue funding advisory roles.

## C: DETAILED OUTPUT SCORING

Output Title	FCDO staff have the gender and equalities tools, training, and guidance to confidently and consistently design and deliver inclusive policies, programmes, and diplomatic initiatives.
Output number:		1	Output Score:	A
Impact weighting (%):		34%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
# of learning opportunities arranged, delivered, facilitated	80	Outputs moderately did not meet expectation (B) / Achieved: 77
# of staff reached through learning opportunities	2400	Outputs substantially exceeded expectation (A++) / Achieved: 3045
# of gender equality, disability and social inclusion learning products, strategies or guidance documents developed	39	Outputs moderately did not meet expectation (B) / Achieved: 31

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focused on strengthening the quality and consistency of FCDO delivery by ensuring staff supporting country, regional and global portfolios have the necessary expertise to mainstream gender and equalities into programming, diplomacy, and policy engagement. Indicators measure how the programme is reaching staff and generating strategies, guidance and learning products that build capability. Learning events and products are developed by insourced roles and the external secondee, tailored to different roles, countries, and contexts. Although the number of events and learning products were moderately short of target, the staff reached still exceeded the milestone for this review, therefore, overall, this output scored A, outputs met expectation.

During this period 77 learning events were delivered across all regions, in the UK and online, compared to 73 last year. Learning opportunities focused on staff directly supporting posts, regional portfolios, and centrally managed programmes. Notably, in person regional workshops were delivered for networks across Africa, Europe, Eastern Europe, and Central Asia, and virtually for networks across the Middle East and Latin America and the Caribbean. 3045 staff were engaged through learning events over the period, more than the target of 2400.

During this period advisers produced 31 learning products, strategies and guidance documents including mainstreaming strategies, GESI analyses and thematic briefings on FCDO priorities. EEF projects primarily generated external learning and evidence products for partners. Internal learning was captured through project reporting and informal debriefs, informing future FCDO engagement, although no standalone gender equality, disability and social inclusion tools or guidance documents for staff were produced.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was updated at the start of the reporting period to consolidate and rationalise indicators following removal of externally provided technical assistance from the programme components. Targets were also revised proportionately to allow for resourcing gaps throughout the year. A review of the theory of change and results framework is planned for the programme’s next year to ensure it adapts to further planned changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR were progressed during this period, with content and engagement tailored to specific roles and contexts, being delivered through a refined offer. Standardisation of feedback processes improved data captured on performance; however, this could be strengthened further by utilising a new management system that collects more data. There are gaps in reporting of initiatives delivered and staff reached which should be captured in future years.

Output Title	Partnerships are developed to coordinate work, share learning, and amplify impact, both internally with G&E networks and champions, and externally with civil society, bilateral, and multilateral actors.
Output number:		2	Output Score:	A+
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 # of joint initiatives or policy engagements with civil society, multilateral, or bilateral actors	20	Outputs moderately exceeded expectation (A+) / Achieved: 24
2.2 # of regional or cross-post networks established or strengthened	6	Outputs moderately exceeded expectation (A+) / 12 networks were established or strengthened
2.3 # of partnerships developed through Enabling Fund projects	13	Outputs met expectation (A) / 15 partnerships with civil society organisations developed through EEF projects

Briefly describe the output’s activities and provide supporting narrative for the score.

This output measures how the programme is building partnerships and networks between the UK, civil society organisations, and partner governments. Internal and external partnerships are led by teams overseas but facilitated and supported by Regional Advisers and funding provided through the EEF. Indicators met or moderately exceeded expectations, therefore overall, this output scored A+.

During this period regional advisers established and strengthened 12 regional and sub-regional internal networks of staff. These networks provide coordination and shared learning, to support the implementation of local priorities. Regional advisers also supported 24 joint initiatives or policy engagements with civil society, multilateral or bilateral actors, including working with WROs in Thailand to improve access to justice for survivors of GBV and collaborating with UN Women on work to transform the care economy in the Western Balkans.

A further 15 partnerships were also developed with civil society organisations delivering EEF projects. During this period, a total of £560,000 was awarded in grants ranging from £11,000 to £70,000, for country-level and regional projects.

This year projects included:

In Liberia: Advancing universal human rights and equitable access to services through targeted advocacy and capacity building with communities, service providers, and policymakers.

Across the Pacific region: Supporting women-led organisations to integrate gender-based violence prevention into inclusive relief and recovery efforts across climate, disaster, and conflict settings.

In Peru: Supporting women’s political participation by building leadership capacity, strengthening networks, and understanding potential to advance safeguards against gender based political violence.

Case study: Gender Responsive Climate Action in the Gran Chaco Americano
The Gran Chaco Americano is one of South America’s most climate vulnerable regions, facing deforestation, poverty, and entrenched inequalities. Through the Equalities Enabling Fund, BE Asunción, in collaboration with BE Buenos Aires and BE La Paz, developed a project to strengthen gender-inclusive climate action and cross border cooperation across Paraguay, Argentina and Bolivia. The project was delivered with the implementing partner Grupo Sunu de Acción Intercultural and convened a Trinational Women’s Gathering and a Global Chaco Summit. These brought together indigenous women leaders, civil society and public authorities to share experiences, develop joint priorities, and articulate gender‑responsive policy positions. The project also supported the development of regional position papers and engagement linked to COP30, raising the profile of the Gran Chaco Americano in national and international climate discussions. A strong safeguarding focus ensured safe and inclusive participation throughout. A strong GBV component resulted in the launch of a regional protocol to prevent and eradicate gender-based violence, with a special focus on indigenous women who are environmental defenders. Learning from the project will inform future regional collaboration on climate, gender equality, and indigenous leadership.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was updated at the start of the reporting period to consolidate and rationalise indicators following removal of externally provided technical assistance from the programme components. Targets were also revised proportionately to resourcing gaps throughout the year. A review of the theory of change and results framework is planned for the programme’s next year to ensure it adapts to further planned changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress was made against recommendations from last year with safeguarding and sustainability embedded into EEF project selection, and efficiencies achieved by funding a smaller pool of higher value projects. Establishing and maintaining active networks takes constant, proactive effort but these are effective ways to build collective knowledge, learning and impact. Staffing gaps created challenges; however, networks can be quickly re-established with dedicated resource. EEF projects have generated new partnerships and initiatives with civil society and partner governments showing that small catalytic funds can build the capability of civil society partners and FCDO posts to advance equalities issues. It is not yet clear if this can be sustained once funding ends, therefore this review recommends revisiting previous projects to assess longer term impacts. Learning from all phases of the EEF should inform future approaches to funding smaller and shorter, post-led initiatives.

Output Title	FCDO teams embed equalities considerations at key decision-making points and monitoring and reporting mechanisms are implemented and strengthened.
Output number:		3	Output Score:	B
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Development and use of a centralised monitoring framework and dashboard (follow up completed with 100% of posts)	1	Outputs moderately did not meet expectation (B)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focused on strengthening the quality and inclusivity in programmes and policy engagement by ensuring equality considerations were systematically assessed and addressed at key decision-making points. The advisory and monitoring support provided through advisers helped posts and centrally managed programmes to identify and mitigate risks of exclusion or unintended harm, improving programme design and delivery. The development and implementation of centralised monitoring was implemented but not through a systemic tool. As a result, this indicator scored B.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output and indicator were added during the theory of change review, at the start of this reporting period, to measure the specific contributions of equalities impact advisers. A review of the theory of change and results framework is planned for the programme’s next year to ensure it adapts to further planned changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Further work is needed to refine metrics to measure the outputs and outcomes delivered by equalities impact advisers.

D: VALUE FOR MONEY

Key cost drivers and performance

The programme’s main cost drivers during this period continued to be staffing and salaries for both insourced and outsourced roles, alongside the funding for small catalytic projects.

Two significant changes occurred during this period:
- The ERH was closed, reducing expenditure this financial year and planned expenditure against the final year, while removing previously identified inefficiencies in ongoing platform maintenance and curation of resources.
- Cross‑cutting technical advisory support provided by the external partner was discontinued. Removing this external advisory layer reduced delivery costs and strengthened coherence, as it removed duplication between external technical support and the internal expertise already embedded across the programme and wider organisation.
Additionally, the programme funded fewer, higher value EEF projects, which increased efficiency by reducing internal administration.

VfM performance compared to the original VfM proposition in the Business Case

Economy
Salaries and travel costs fall within FCDO parameters and remain the primary cost drivers alongside the EEF. Insourced advisory roles remain significantly more economical than external consultancy equivalents. The early closure of the ERH delivered additional cost savings by discontinuing an activity where the remaining costs outweighed expected benefits, aligning remaining spend more clearly against the programme’s core objectives.

Efficiency
Efficiency improved this year as the programme adapted and incorporated learning and recommendations from previous reviews. The reduction in the number of funded projects lowered the administrative burden on the central team. The insourced staff and secondee provided more efficient support than external provision given their direct access to FCDO systems, networks, and decision-making structures, which also improved programme efficiencies during this period.

Effectiveness
The programme continued to support improved integration of equalities considerations across FCDO portfolios and strategies, improving value for money by strengthening decisions, reducing the risk of ineffective or exclusionary programming, and supporting earlier identification and mitigation of safeguarding and delivery risks in partner contexts. Advisory support, particularly from insourced roles, strengthened institutional capability, accelerated learning, and improved coherence across the network. A more focused project portfolio helped concentrate effort on strategic interventions with high potential for impact, though delivery challenges persisted in some contexts primarily due to internal resourcing constraints and working in challenging contexts.

Equity
No significant changes to equity considerations occurred this year. EEF‑supported interventions continued to prioritise localised delivery, ensuring targeted groups remained central to design and implementation.

Cost‑effectiveness
The programme continued to demonstrate strong cost‑effectiveness. Adjustments made this year, including the ERH closure and smaller project portfolio, ensured resources were targeted towards higher impact advisory and capability‑building work. No material changes to emissions or shadow carbon pricing assumptions were required, as the programme’s climate and environmental footprint remains low and does not materially affect VfM calculations.

Assessment of whether the programme continues to represent value for money

There is good evidence that the programme continues to represent value for money. The strategic adjustments made during the year enhanced efficiency and reduced delivery risks, while the programme continued to deliver meaningful capability gains and influence across the FCDO network, adapting to significant organisational changes, including ODA reductions. While the programme has effectively built capability, strengthened equalities integration, and informed policy and delivery across multiple geographies, it will need to adapt further as it transitions to being delivered through the Women and Equalities Community of Expertise.

E: RISK

Overview of risk management

The programme’s overall residual risk was updated to minor during this review. Over the past year delivery has continued to sit within FCDO’s risk appetite and several risks related to delivery of small projects and the ERH were closed as these components concluded on 31 March 2026; this drove a reduction in the residual risk for the programme.

Across the risk categories most risks sit at a minor residual level. During the year, several areas saw improvements, with financial‑management and delivery‑partner risks reducing to minor following tighter budget scrutiny, clearer control processes, and embedding a new funding transfer model for EEF projects.

Safeguarding remained central to programme delivery and was a key consideration in selecting which EEF projects to fund. Work with smaller organisations continued to require close monitoring, but mitigation strategies ensured risks remained within appetite. Risks associated with one project created pressure during the period, but mitigating actions prevented these exceeding risk appetites or becoming worse. Climate and environment risk has been reassessed and continues to be low, with the programme seeking opportunities to deliver climate-positive or nature-positive co-benefits in some contexts.

Governance mechanisms have continued to improve coherence and consistency across the programme. As the programme moves into its final year, risk registers have been updated to reflect changes arising from component closure.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Programme management arrangements were strengthened this year. The role of the external partner consortium was scaled back to focus on managing the secondee and the safe and effective closure of the ERH. This removed areas of duplication and reduced some previous inefficiencies in programme management.

In line with last year’s recommendations, the programme delivered a smaller and more strategic portfolio of 13 EEF projects, compared to 34 last year. This significantly reduced the administrative burden, improved oversight, and allowed the programme team to provide more targeted support to ensure better delivery, and compliance. Budgets for EEF projects were transferred to posts for local management, increasing efficiency, although requiring sufficient local capacity and reducing the flexibility to reallocate underspend centrally. The smaller portfolio and budget transfers aligned with available capacity and mitigated risks linked to overstretch last year.

The programme maintained eight insourced advisory roles, which continued to strengthen internal capability and provide effective policy support across the network. Roles were filled for most of the year, though some short gaps occurred due to staff moves and recruitment limitations that are outside of this programme’s control.

Overall programme underspend was under 5%, driven primarily by postponed travel and staffing gaps in advisory roles.

Financial management improved across the programme. Forecasting for insourced roles was more accurate, reflecting lessons learned from last year. Work with the external partner was supported by clear milestones and continued use of an activity‑based budget, enabling effective fiscal management and greater transparency.

Reporting quality, financial monitoring and collaboration between central teams, posts, and the external partner all improved. Overall, programme management was more efficient, focused, and coherent this year, supported by a smaller project portfolio, streamlined external support, and strengthened internal capability.

G: MONITORING, EVIDENCE AND LEARNING

This Annual Review was carried out by the FCDO programme team as a desk-based exercise, drawing on monitoring returns, project documentation, and interviews with a range of stakeholders. Monitoring activity during the review period included quarterly reports from both the external partner and insourced advisory roles, an exit interview with the secondee, feedback gathered from capability initiatives, and project completion reports from EEF projects. The FCDO programme team also provided regular oversight and support to teams at post delivering EEF projects.

Learning processes this year focused on the EEF and the ERH. For the ERH, the external partner produced two comprehensive learning reports that documented the end‑to‑end design, operation, and closure of the platform, offering detailed insights for any future digital resource initiatives. For the EEF, changes introduced this year, including frontloading assurance before fund dispersal, and annual reporting instead of quarterly updates, have generated learning on how to empower posts to manage funding while maintaining appropriate oversight. Internal learning identified challenges with reporting by PFPs, particularly where staff were unfamiliar with programme‑style monitoring requirements or where reporting duplicated line‑management structures. A consolidated feedback form was introduced to streamline reporting, but uptake was inconsistent. A secretariat function improved coherence of the advisory team, increasing sharing of materials and best practice to achieve better outcomes.

Case study: Learning from the Equalities Resource Hub
Key learning: The Equalities Resource Hub (ERH) demonstrated that an externally facing platform can significantly improve access to and awareness of high‑quality evidence when content is trusted, well‑curated and supported by active communications. The ERH exceeded reach expectations within a year and was positively received by users. Strong performance on accessibility standards and safety‑by‑design reinforced credibility and mitigated safeguarding risks. Although strong reach was achieved, evidence of engagement and sustained or applied use of resources was limited. Implications for future programme design: future programming should approach external knowledge platforms selectively and strategically. In a crowded evidence ecosystem, any future knowledge hub‑style investment should have a clearly defined primary audience, a distinctive value proposition, and a design focused on practical application, not volume of content. Accessibility, safeguarding, language strategy, and sustainability planning should be built in from the outset and fully costed. Communication and engagement should be treated as core delivery components, and programmes should allow sufficient delivery time to support repeat engagement and demonstrate use in practice. Where these conditions cannot be met, alternative approaches, such as embedding evidence within existing channels, networks or advisory mechanisms, may offer better value for money and clearer impact pathways.

Learning aims for next year

Consolidate and share EEF learning, including revisiting selected historic projects to capture impact of catalytic funding over longer periods.

Date of last narrative financial report	April 2026	Date of last audited annual statement	June 2025