## Annual Review Template

Title: IRAQ CATALYTIC ECONOMIC DIVERSIFICATION PROGRAMME (ICED)
Programme Value £ (full life): up to £18m		Review date: 28 AUG 2025
Programme Code: 301535	AMP start date: March 2023	AMP end date: March 2028

Summary of Programme Performance
Year	2024	April 2024-March 2025
Overall Output Score	B	B
Risk Rating	MODERATE	MODERATE

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003397.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005894.xlsx

Table of Acronyms
ICED	Iraq Catalytic Economic Diversification Programme
ASI	Adam Smith International
HMRC	His Majesty’s Revenue and Customs
WTO	World Trade Organisation
TFA	Trade Facilitation Agreement
ODA	Official Development Assistance
ITAS	Integrated Tax Administration System
GOI	Government of Iraq
KRG	Kurdistan Regional Government
BEB	British Embassy Baghdad
IFD	Iraq Fund for Development
PFRC	Public Financial Resource Centre
MoF	Ministry of Finance
PFTD	Public Finance and Tax Department, FCDO
ITAS	Integrated Tax Administration IT System

A. SUMMARY AND OVERVIEW

Description of programme

The Iraq Catalytic Economic Diversification (ICED) programme seeks to support economic development and broaden Iraq’s economy from its reliance on oil. It focuses on creating a thriving private sector and removing barriers to entrepreneurship. ICED has macro, meso, and micro components. In the previous reporting period, due to operational, financial and delivery challenges, the programme was adapted to focus on the macro component only in the first two years of the programme. The macro component provides technical assistance focussed on supporting the Government of Iraq’s economic reform initiatives. ICED is managed from British Embassy Baghdad (BEB).

In this reporting period, ICED delivered through two main components:

1) HMRC Technical Assistance (HMRC TA) (£174,249) – ICED continued delivery under an MoU signed with HMRC in 2023 to deploy tax experts to provide technical assistance in support of the Government of Iraq’s tax reform agenda. This included providing expert advice, and capacity building training directly to the Government of Iraq (GOI). In this reporting period, ICED built on the relationships developed with Iraq’s tax and customs authorities in the previous reporting period to deliver further support. The workshops in this reporting period cover leadership and change management, internal and external communications, and digitisation.

There was strong, positive engagement from senior managers across the tax and customs authorities during the workshops. When the MoU with HMRC expired in March 2025, this work was paused to reassess how best to deploy technical assistance to achieve meaningful organisational, procedural, or legislative change.

Trainings to customs officials were also delivered under a separate but complimentary HMRC managed ODA programme in this period. These will not be assessed as part of this review, but contributed to ICED aims through improving understanding of the Trade Facilitation Agreement (TFA) under the World Trade Organization (WTO) provisions and wider international customs standards, and facilitating coordination among stakeholders involved in trade facilitation.

2) ICED Public Financial Management (ICED PFM) (£372,087) - ICED PFM is a component contracted through the Public Financial Resource Centre (PFRC) PFRC Centre of Expertise. PFRC is managed by the Public Finance and Tax Department (PFTD) and delivered by Adam Smith International (ASI) and its subcontractors. BE Baghdad used bilateral ODA to ‘buy-in’ to the central PFRC Business Case.

ICED-PFM delivers targeted technical assistance to support the Government of Iraq (GOI) in advancing critical economic reform initiatives. Its primary focus is on strengthening PFM systems to establish a robust foundation for broader private sector and financial sector reforms. Key areas of intervention include enhancing revenue administration, improving fiscal management processes, and addressing systemic inefficiencies that undermine economic stability and growth.

ICED PFM built on work initially financed through the Integrated Security Fund (ISF). Activities transitioned from July 2024 with a formal inception period from December 2024 – March 2025, during which time some technical assistance was also delivered. The formal implementation period started in May 2025; outside this reporting period. During the inception phase, five workstreams were identified as potential options for support. These were:

- Supporting the Iraq Fund for Development (IFD)
- Strengthening the Kurdistan Regional Government’s Fiscal Management
- Improving state revenue administration in Iraq
- Strengthening the Central Bank’s role in Iraq’s financial system
- Strengthening the role of the Prime Minister's Office and Ministry of Finance in public financial management.

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

The programme has scored a B. This reflects mixed performance across the programme as implementing partners contended with inconsistent demand from counterparts, unaccounted for political barriers and with the quality of some activities not meeting expectations,

Where activities have been delivered, implementing partners have received positive feedback from counterparts. Both implementing partners have sought to drive up compliance with international standards and best practice which will ultimately support GoI’s ambition to increase revenue from non-oil sources.

These activities continue to be broadly aligned in with the public financial management reform priorities that show the most potential in Iraq, however the political economy challenges mean the potential impact of activities was not always realised.

ICED has now scored a B in two consecutive annual reviews. However, due to the significant change in delivery mechanisms between the two periods (ending HMRC Technical Assistance and beginning ICED PFM) we believe it does not warrant a performance improvement plan. Whilst they experienced similar challenges regarding stakeholder buy-in at times, it would be unfair to compare the two reporting periods in tandem.

Major lessons and recommendations for the year ahead

Key lessons & recommendations:

Strategic:
- To put political economy at the heart of ICED: ensure interventions are targeted towards counterparts with decision-making power, and target areas without insurmountable vested interests and resistance to change.
- To consider a ‘fail-fast’ approach to identifying and testing potential interventions: In the Iraqi economic space, there are many issues worthy of attention, but few where progress is realistically achievable under ICED. Consider a greater role for BEB diplomatic engagement in generating initial ideas and testing demand for interventions with key interlocuters, with a focus on small-scale funded interventions to either generate momentum or test potential for impact. Quickly move on from those which fail, and double down on those which show promise (breadth followed by depth).
- To maintain confidence in halting interventions which are not showing signs of success.
- To consider how UK expertise can be deployed: UK expertise is highly respected and valued in Iraq and is therefore a valuable resource that should be explored as a mechanism to deliver outputs. Deployment should be strategic, and consider resource cost on BEB to facilitate.
Programmatic:
- To ensure governance processes are followed rigorously: in a dynamic programme where decisions on interventions are made regularly, recording decisions is critical. It also enables us to keep record of and build on lessons learned.
- To be more proactive in course-correcting through logframe changes over the course of the year. Where things are not working, BEB and implementers should proactively seek to adapt logframes to a) ensure it is realistic in the operating context, and b) ensure targets are achievable for implementers. This may lead to improved output scores in future reviews.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

(Figure 1: original ICED theory of change)

The original ICED theory of change sets out the objective of the ICED programme: a ‘stable, strong and resilient economy is achieved’ in Iraq, with the impact statement outlining that the intervention would ‘create private sector jobs,’ ‘strengthen and improve Iraq’s financial and private sectors’ and ‘increase sustainability and effectiveness of Iraq’s economic structures. These statements align with the three pillars in the original programme design: macro-economic reform (including public financial management, and improving economic diversification in Iraq), meso-economic reform (including financial sector reform), and micro-economic reform (including supporting Iraqi SMEs through access to private capital).

Following the reduction in scope of the programme halfway through the 2023-2024 reporting period due to ODA reductions, the programme, and subsequently the theory of change were reduced to focus on macro-economic reform only. For this reporting period, the updated theory of change remains the same, given this pillar had the most catalytic and transformative potential, and presented the best opportunity for the programme team to utilise existing delivery mechanisms (MOU with HMRC capacity building teams), and explore and establish delivery through FCDO PFRC Centre of Expertise, allowing a focus on delivery rather than lengthy procurements.

(Figure 2: updated ICED theory of change developed in January 2024 and still current)

The refined theory of change (as presented in January 2024) still holds; however the outputs and outcomes have since expanded to cover a broader range of target stakeholders. This was possible because the PFRC Centre of Expertise holds expertise on a range of Public Financial Management issues, that the programme could benefit from. During the inception period (December 2024 – March 2025), the PFM implementing partners, ASI, developed a theory of change for their specific intervention on PFM which seeks to guide the delivery phase of the PFM intervention.
Figure 3: theory of change developed for PFM interventions under the PFRC Centres of Expertise.

The original theory of change assumptions remain partially relevant:

- FCDO is prepared to commit up to £18 million over five years. The processes tackled – reforming GoI process, improving financial sector effectiveness, building private sector capacity and skills – will take time to yield results. Without a confirmed five-year span, the likelihood of success is reduced.
- FCDO is committed to using its political resources to influence the Government. This programme is premised on development diplomacy (with small scale TA catalysing larger change) and on micro level interventions having a demonstrator effect that others will follow. Success will require sustained UK lobbying across teams in Iraq.
- FCDO continues to have access to the highest levels of policy making. The programme will enhance the FCDO’s position: hence, it is probable that this assumption will be valid.
- Political advocacy is effective. It is assumed that providing technical support will enhance FCDO’s credibility with the Government. Even with access to high levels of Government, it is not certain that the Government will collaborate.

Given reduced funding availability, the assumption of £18 million over five years has not been realised, which has necessitated a reduction in programme ambition (reducing from three pillars to one). Given the shifting dynamics of development funding in Iraq, it will be important for FCDO to work with partners to maintain ICED’s impacts. This includes ensuring ICED can be used to facilitate updated Iraq Network priorities.

The final three assumptions around development diplomacy and advocacy remain relevant. FCDO has been active and visible in the delivery of ICED. However, translating advocacy into tangible outputs remains challenging due to the high turnover of staff of both GoI partners and at the British Embassy. Additional effort is required to continue momentum and continually strengthen relationships with counterparts.

Finally, the above assumptions underestimate the impact of entrenched vested interests of influential figures and groups in Iraq in maintaining the status quo. While net-benefit and welfare improving for Iraq as a whole, any significant economic reform is likely to disadvantage a power broker who benefits from rent-seeking in the status quo and will therefore strongly resist this change. As such, even with significant access, diplomatic influence is unlikely to persuade influential figures to work against their own personal benefit or that of other sufficiently powerful figures across the political system. This is a key blocker to ICED’s success, and requires ICED to identify and operate in rare spaces of minimal resistance, or to capitalise on windows of opportunity as they emerge.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall, the programme is moderately on track to contribute to the expected outcomes and impact.

 Following the transition phase from ISF support (August to December 2024), the ICED PFM full intervention was primarily in its inception period during this reporting period, although some activities were delivered on the Iraq Fund for Development and Kurdistan Regional Government workstreams. These activities have been moderately successful: developing a suite of best-practice manuals and processes for the Iraq Fund for Development, which aim to ensure transparency and accountability are integrated into the Fund’s operations. Whilst the manuals are appreciated by the Fund’s CEO and the Governance manual has been approved by the IFD Board, the remaining manuals cannot be used until they received Board approval, which has faced lengthy delays.

Under the HMRC TA, whilst individual technical assistance and training activities have been well received by counterparts, it is not yet possible to link the cumulative impact of these activities to meaningful policy or operational change across the outcomes. We will however continue to monitor the impact over time.

For example, training was successfully delivered by HMRC with mid-senior level managers in both the tax and customs commissions on subjects including change management and digitisation. The Director Generals of the commissions were supportive of and receptive to the training; however, they do not have sufficient decision-making authority to enact meaningful reforms to implement an effective reform in their organisation in response to the training. This directive would have to have been given by the Ministry of Finance (MoF), who was not involved in the intervention as a counterpart. This example demonstrates the importance of conducting and grounding interventions in thorough political economy analyses led by exprets in the British Embassy in dialogue with relevant implementing partners.

Overall, this reporting period has been a year of delivery mechanism transition, which includes the development of reporting frameworks in-year for the PFRC component. Therefore, it is not possible to give a full view on whether the programme has made significant progress against the ICED outcomes.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This period represented a transition and inception phase from HMRC’s technical assistance, to establishing ICED PFM. Given the necessary investment in future delivery committed in this period, ICED PFM should continue into the following period. ICED PFM should be assessed critically on its delivery and impact in this subsequent period, while being mindful of what is achievable in the context in even a best-case scenario economic reform programme.

Despite the steep challenge of operating in this space, economic reform remains essential for Iraq’s mid to long-term stability. Success in this space could be transformative to Iraq’s prospects. But with state finances increasingly fragile, failure to address these challenges has a high chance of leading to significant economic instability with the next few years, undermining outcomes in Iraq across the breadth of UK interests.

## C. DETAILED OUTPUT SCORING

Output Title	Improved governance structures, tax administration and practices within General Commission of Tax (GCT).
Output number:		1.1	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	Yes – down from 30%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Technical assistance and expert advice provided to GCT to support implementation of Integrated Tax Administration IT System (ITAS)	1. Deliver a list of next steps and key changes required to deliver ITAS, following on from the roadmap delivered last reporting period. / 2. 1x workshop on managing change to support ITAS implementation.	1. Partially Achieved. A list was discussed with GCT SLT and the DG, however the work on implementing ITAS was paused by GoI. / 2. Not Achieved. Training was not delivered due to a drop in political appetite from stakeholders and a pause in ITAS implementation by GoI.
1.2 Technical assistance and expert advice provided to GCT to develop improved tax practices and recommendations in tax policy & strategy development	1. Workshop to initiate development of partnership and documentation process across PMO, MoF and GCT. / 2. Delivery of draft documentation sharing templates. / 3. Delivery of training in tax revenue monitoring and forecasting approaches.	Achieved. Delivered in September 2024. / Achieved. Draft templates shared alongside the training delivered in September 2024. / Not Achieved. Training was not delivered due to a drop in political appetite from stakeholders.

Briefly describe the output’s activities and provide supporting narrative for the score.

Following the delivery of a roadmap developed in the last reporting period on introducing an electronic tax system (ITAS) in Iraq, HMRC planned further support to the GCT to support this implementation. This included supporting GCT to further prioritise required organisational and operational changes, such as information sharing policies and processes between relevant line ministries, and delivery of training in change management and delivery of revenue monitoring and forecasting approaches, to enable accurate national budgeting.

Initial engagement from GCT, following HMRC’s previous well-received work, suggested GoI were enthusiastic about the purchase and application of an ITAS system. However, following an unexpected change in personnel at the top of GCT, and the discovery through technical discussions with HMRC that the GCT building was not able to cost-effectively host ITAS infrastructure, meant that this was not retained as a priority. This meant delivery of indicator 1.1 stalled. This highlights the need of programmes such as ICED to include design features which mitigate this political riskrisk that further consequential decisions (in this case, to procure new buildings) to support delivery do not take place in a timely manner. For example, this includes activities such as regularly testing political economy assumptions, ensuring flexibility, avoiding single points of failure in political support, and the option to ‘fail fast’ on interventions to mitigate the risk of significant sunk costs on any given issue.

Indicator 1.2 was slightly further removed from ITAS implementation and focused on implementing tax policy strategically and efficiently across the government system. Therefore, templates on document and information sharing were devised and presented to the GCT in September 2024. HMRC shared tools, processes and templates to demonstrate how the GCT could estimate the revenue generation potential of new tax policies. It transpired that no equivalent processes existed in the Iraqi tax system.

The training set out UK tax policy frameworks and highlighted roles and responsibilities of each organisation, suggesting how this could be replicated in the Iraqi context. The workshop also covered the importance of monitoring and evaluation of policy implementation and ensuring that implementation of tax reforms does not undermine any progress already achieved with the taxpayer.

Following the workshop, HMRC recommended that the GCT should:

1. Complete a stakeholder mapping exercise with the Ministry of Finance to ensure roles and responsibilities are clear between institutions.
2. Create a baseline forecast for all tax and customs revenues and formalise a forecasting process.
3. Pilot the use of the templates, tools and processes within the next fiscal year.
To our knowledge, GCT have not implemented these recommendations. Thus, whilst the training was useful in motivating GCT to identify gaps and opportunities in implementing organisational change and best practice, there was no mandate from the decision-making authorities to implement this learning systematically. This arose from political issues around whether the GCT should become a semi-autonomous revenue authority: these issues were separate to delivery of the programme and were the subject of ongoing discussion between the GoI stakeholders.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

The previous annual review recommended:

- HMRC deliver smaller more focussed tax policy documents (if this is what is required), with clear executive summary with recommendations. This allows both senior and technical officials to access the learning in a digestible form.
- Ensure translation of documents is incorporated at source, into the production time and costs.
- Build in a 6-month review of progress of Iraq’s Tax Reform Agenda, in the form of a tax dialogue with the Government of Iraq, which allows the ICED programme to understand if progress is being made.
- Use the UK’s membership of the Iraq Economic Contact Group (IECG), to ensure key messages around tax reform are being transmitted to the Government of Iraq.
In this reporting period, HMRC did produce more specific policy documents with improvement in format and clarity. Translation was provided for both documents and workshops in this period.

A Tax Reform Dialogue was not conducted. Delivery was complicated by a period of regional instability, which affected flights to Iraq, preventing HMRC from travelling at least once during the reporting period. There was also a challenge with GoI counterparts not confirming availability with enough notice, necessitating postponement of HMRC trips at least twice. Challenges with remote communications (for example, no routine use of email across the GCT), were a further impediment.

BE Baghdad did utilise the IECG to deliver messages to GoI and leveraged its position as chair for much of this reporting period to increase the frequency of ICEG meetings and improve attendance from other members. In future, HMRC could work more proactively with BE Baghdad to encourage work to continue in their absence.

The HMRC component of ICED has now concluded, however a recommendation for any similar future work is to ensure HMRC are able to adapt outputs based on the political economy. This could be achieved by holding regular (quarterly) meetings that focus on scenario planning and developing a suite of activities that speak to GoI’s priorities, that can be drawn upon as appropriate, as well as mitigate political risks. This would reduce the likelihood of outputs not being completed.

Output Title	GCT officials upskilled in leadership, change management, performance and HR policies improve the public financial administration
Output number:		2	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	Yes – down from 70%

Indicator(s)	Milestone(s) for this review	Progress
2.1 GCT officials trained in leadership and change management	1. 2x senior leadership training to GCT. / 2. Support GCT to develop leadership training plan and potential course content for middle managers to support wider change programme. / 3. 1x senior leadership training module repeated to middle management of GCT.	Achieved. Training was delivered in September 2024 and January 2025. / Not Achieved. / Partially achieved. Training materials developed, but not delivered.
2.2 GCT officials trained in performance management and HR management	1. Training on developing KPIs for performance management, monitoring and governance.	Not Achieved.
2.3 Training on how to develop a communication strategy and plan is delivered.	1. 2x training (4x separate workshops) on development of communications strategies and comms tools. / 2. GCT engaged in development of comms strategy for taxing medical professionals. / 3. GCT develop targeted comms plans for main taxpayer segments with HMRC support.	Partially Achieved. 2x workshops delivered in September 2024. Planned follow up workshop materials developed but not delivered. / Partially achieved. This was covered in Sept 2024 training. / Partially achieved

Briefly describe the output’s activities and provide supporting narrative for the score.

This output seeks to support GCT in organisational change management, which is an important factor dictating the success of implementing tax reforms.

Indicators 2.2.1 and 2.3.1 have been transferred from the previous reporting period, because of delays due to personnel changes at GCT. The two-day workshops covered the use of communication tools and strategies to improve senior leadership skills, but were not then repeated to middle-managers (as planned under indicator 2.2.3). Further, indicator 2.2.2 was not achieved due to declining appetite for these materials over the reporting period.

The first workshop (indicator 2.3.1) was delivered to GCT, with participation from across GoI, including Ministry of Finance, Ministry of Education and the PM Advisor’s Council. The workshop focused on building a high-level communications narrative around fiscal reform for internal and external use. HMRC recommended that there should be better linking between Iraq’s national Development Plan 2024-2028 and the tax reform narratives.

The second workshop under 2.3.1 was delivered just to GCT. KRG tax leadership were invited but were unable to self-fund travel to Baghdad, and this had not been accounted for within HMRC’s training budget. This workshop focused on the design of external communication approaches to individual taxpayer cohorts to improve understanding and compliance. The medical profession was chosen as a case study. HMRC reported differing views from participants on tax compliance, but most participants thought the medical profession had the lowest rates of compliance for a variety of complex institutional reasons. Despite this discussion, indicators 2.3.2 and 2.3.3 were only partially achieved. Whilst GCT did begin to engage in the comms strategy for medical profession (2.3.2), appetite diminished whilst they waited for further clarification on the policy detail from other parts of the GoI, the indicator was not completed. Indicator 2.3.3 was initially addressed in the January 2025 workshop (2.1.1) however FCDO paused the delivery of a follow up workshop in February 2025 where this comms plan was due to be developed; and thus the indicator is partially achieved.

It also became clear that public-facing processes and communications needed reform. One GCT participant noted that they could not register their own medical business to comply with tax rules because the process as it currently stood was impossible to comply with. Whilst a call centre and Facebook page exists for the public, the workshop highlighted scope for improvement on this issue.

HMRC explained to participants that major changes to policy often require change in organisational structure too, and that internal comms should not be neglected. This was also picked up in the change management workshops delivered in September 2024 and January 2025 (indicator 2.1.1). The January 2025 workshop was delivered to GCT and KRG officials, as budget was added to facilitate KRG’s attendance. This workshop included a group exercise to develop a draft change plan and consider the activities needed to digitalise the organisation. However, many of these actions require legislative change which could not be addressed directly by GCT or by HMRC under the current scope/design of the intervention. Further, those change plans were retained by each group and not aggregated into recommendations by HMRC or the participants. This was a missed opportunity to feedback formally to GoI on workshop outcomes: this was caused by the workshops planned for February by HMRC to follow up on these issues not taking place due to the logistical problems and other issues noted elsewhere in this report.

Further training on change management was planned in February 2025, and training materials were delivered. However, FCDO requested HMRC not to deliver the training because a) resourcing at the Embassy was strained and could not support the logistical lift to accommodate 4-5 HMRC officers on-platform; b) we had not seen strong enough evidence that the previous trainings were having sufficient impact, nor strong enough demand from GCT, to justify the cost of delivering the second training. Additionally, HMRC realised after conducting the first series of trainings that developing HR/performance KPIs for GCT (indicator 2.2.1) was too advanced as no internal performance structure existed. Thus, this indicator was not delivered.

The January 2025 workshop also covered digitalisation as part of the change process. Whilst WhatsApp is used to deliver internal communications messages, the workshop revealed a need for improved IT skills across GCT to realise the benefits of IT systems.

Following the workshop, HMRC recommended that the GCT should:

1. Clarify the parameters of the digitisation agenda to build a realistic plan on integration of IT into GCT systems. This includes considering investing in modern offices where IT platforms could be hosted.
2. Implement an online HR system that allows for better decision making on organisational change.
3. Improve understanding between MoF and GCT on the digitisation agenda, including GCT securing buy-in on required legislative reforms.
Participants described the sets of trainings in post-training feedback surveys as useful in helping to “crystalise decision making”, “identifying obstacles for implementation of digitisation” and “helped [us as] leaders understand how to deal with employees and change”. However, since this component with HMRC concluded at the end of the reporting period, there has been limited progress made by GoI on this agenda, and FCDO have not received proactive requests for further support.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No formal changes to the output, however important to note that the January 2025 training workshop was not formally captured as an indicator under this output. To ensure it is acknowledged as an activity, has been included in this output review.

No planned changes as this component concluded with this reporting year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The last annual review recommended the following:

- Ensure a clear roadmap of capacity building workshops is provided for a six-month period. This is to allow the ICED programme and Government of Iraq to both agree scheduling and attendance.
- ICED should seek substantive feedback on the capacity building workshops, to understand how learning is being incorporated into the tax reform agenda.
- Seek to provide training to the same officials, so that they can track their learning and development.
- Ensure that provisions are made for possible changes in the security situation, which would impact their ability to deliver training on the ground. This would require adaptation of the log-frame milestones.
- Participants in workshops should be presented with workshop packs, which have been translated into Arabic, to ensure they are able to refer to their learning in the future.
Some of these recommendations have been progressed: HMRC did translate materials and provide workshop packs to participants, although BE Baghdad had to lead on procuring the translator due to HMRC commercial rules.

Some officials received a full set of training, however due to the nature of the Iraqi civil service, many of the SLT had moved on before the next training could be completed. Whilst this is outside of HMRC’s control, it could be mitigated by taking more of a ‘training of trainers’ approach once the Senior Leadership Team of the GCT have initiated the major change programme so that knowledge stays within the institution, regardless of staff resourcing changes.

Finally, although HMRC did propose some changes to the logframe during the reporting period, these were not followed up or adopted their adoption, which was a missed opportunity given that personnel and priority changes in GoI occur frequently. In future, FCDO and HMRC could proactively discuss output potential (as part of a risk conversation) and decide whether to pursue outputs or not, which mitigates risk of under-delivery, and opens space to pursue new opportunities in place.

Output Title	ICED-PFM interim intervention – scoping and long-term design
Output number:		3.1	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	N/A – new output

Indicator(s)	Milestone(s) for this review	Progress
Scoping and workstream design for long-term intervention	Planned: Report	Achieved: report submitted.

Briefly describe the output’s activities and provide supporting narrative for the score.

3.1.1: The scoping aimed to identify additional potential interventions, alongside the existing workstreams previously funded by the ISF on the IFD and with the KRG.. It also aimed to propose a structured approach to delivering technical assistance across the parts of the Iraqi economy that had the most catalytic potential. Building on the IFD and KRG interventions, three additional areas ICED could consider supporting were recommended. This was accompanied by a record of stakeholder engagements, which evidenced demand for ASI’s suggestions. The scoping also delivered a comprehensive mapping exercise of donor-funded activity in the economic sector. This mapping was presented to, and was well received by, the Iraq Economic Contact Group and gave the UK, who was chair of the IECG at the time, credibility and leverage over coordination attempts.
[note] The IECG is a is a joint initiative aiming to support and promote economic development in Iraq, comprising the G7 plus the World Bank and the EU Mission in Iraq. The UK co-chaired, with France, from January to December 2024.

For KRG, support was provided to the nascent Debt Management Unit, by suggesting debt management software such as the UN Debt Management and Financial Analysis System (UNDMFAS).. In this stream, ASI did not give due consideration to the political economy constraints of turning deliverables into tangible impact. For example, ASI were unrealistically optimistic about the pace at which the Kurdish Government would form following November 2024 elections. This is important because the appointment of an empowered Finance Minister is a pre-requisite for mandating the establishment of a full FPU. The British Consulate General in Erbil was aware of this work, butgreater transparency and adhering to processes requiring formal approval and buy in from BEB would mitigate the risk of misplaced effort.

For IFD, support continued to be provided by the ISF team during this short-term intervention. The IFD workstream was handed to ICED-PFM from December 2024.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

FCDO recommends proposed interventions are better communicated, including explicit targets and activities that are time-bound and sequenced in a way that will maximise chance of success, although it is noted that the this interim intervention was originally designed for a period of eight weeks – due to delays in the procurement process for the substantive intervention, this interim intervention was extended in-situ.
Activity design should be more collaborative and more effectively harness the expertise within the British Embassy, including with consideration of political economy constraints, to ensure effort is focussed on activities and deliverables able to translate to tangible impact.
It is recommended that all parties be bolder in making decisions regarding pausing or stopping work that does not have sufficient political buy-in.

Output Title	ICED-PFM interim intervention – handover to long-term intervention
Output number:		3.2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A – new output

Indicator(s)	Milestone(s) for this review	Progress
3.2.1. Handover to the new implementing partner of ICED-PFM Technical Assistance	Planned: final report	Achieved: final report

Briefly describe the output’s activities and provide supporting narrative for the score.

The substantive intervention team ultimately included some of the same people, including the Project Director, which was beneficial as contextual knowledge of Iraq and previous activities was maintained.

However, whilst the report was delivered on time in November 2024 and included comprehensive contextual updates, there was scope to include more lessons learned or recommendations on ways of working with FCDO, or on how to design a flexible intervention that serves both strategic and programmatic requirements.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

FCDO recommends that any future handover report should include recommendations on ways of working and programme design; not just contextual or delivery-related updates.

Output Title	ICED-PFM substantive intervention
Output number:		4.1	Output Score:	B
Impact weighting (%):		16%	Weighting revised since last AR?	N/A – new output

Indicator(s)	Milestone(s) for this review	Progress
4.1.1. Inception phase of implementing partner of ICED-PFM	Planned: Inception pack, containing: / - Approach paper and recommendations for ICED-PFM’s focus - Strategic framework - Project management, governance and reporting systems, programme manual, updated risk register	Partially Achieved: Inception pack delivered but not implemented effectively.

Briefly describe the output’s activities and provide supporting narrative for the score.

ASI were required to deliver an inception pack. This was delivered on time and contained all required documents. FCDO provided feedback to ASI, and the reports were signed off in January.

Since sign-off, the inception pack has not been utilised to the best of its ability. For example, the kick-off phase was not sufficiently proactively driven by ASI, and whilst the Strategic Framework was designed to guide decision-making regarding new proposed interventions, it has not been referred to consistently during the delivery phase of ICED-PFM. Second, governance arrangements proposed for intervention commencement were not initially followed, meaning FCDO and ASI spent significant time in February and March of the reporting period clarifying these issues, which detracted from delivery and engagement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

FCDO recommends the inception pack template is refined in conjunction with FCDO, to ensure it is as useful and relevant as possible in future. Written deliverables should consider the optimum length and level of detail, to balance providing required information with the operationalisation of the report.

Output Title	ICED-PFM substantive intervention
Output number:		4.2.	Output Score:	C
Impact weighting (%):		17%	Weighting revised since last AR?	N/A – new output

Indicator(s)	Milestone(s) for this review	Progress
4.2.1 Technical assistance interventions planned	Planned: Concept notes by January 2025, containing: / - budget - workplan	Not Achieved: Concept notes not sent until May 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

As described in the substantive intervention’s bid, and agreed at the kick off meeting in November 2024, concept notes for the IFD and KRG workstreams detailing planned activities and budget for the inception period were expected in January 2025.

These were not received by FCDO, which was in part due to delays and uncertainty around an extension to this contract and intervention, which required more project management resource from ASI, impacting the timely submission of concept notes.

Activities were being delivered and FCDO were updated verbally through meetings and requests for information. This meant FCDO had limited influence on the nature of activities being delivered, and it was difficult to monitor quality or hold the implementing partner to account. This, over time, led to a widening gulf of expectations, and delivery of activity FCDO were not fully bought into.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

FCDO recommends a significant shift and formalisation in ways of working with ASI, to ensure deadlines are met and expectations are clear. This has been actioned since this reporting period and ASI have recognised the requirement for a revised resourcing structure, which has since been proposed after this reporting period. Communication between FCDO and ASI has also substantially improved since this reporting period.

Output Title	ICED-PFM substantive intervention
Output number:		4.3	Output Score:	B
Impact weighting (%):		17%	Weighting revised since last AR?	N/A – new output

Indicator(s)	Milestone(s) for this review	Progress
4.3.1. Technical assistance delivered	Planned: Iraq Fund for Development and Kurdistan Regional Government activities delivered as outlined in the concept notes by March 2025	Partially Achieved: Concept notes not submitted (see output 2.2.1) but activities delivered.

Briefly describe the output’s activities and provide supporting narrative for the score.

During the inception period, ASI delivered key activities under the IFD and KRG workstream. This delivery maintained key relationships developed under TAFFI, whilst the transition to ICED-PFM was completed during the inception phase. However, by not having formalised concept notes (see output 4.2), or a sense of specific activities that would be delivered and when, it was difficult for FCDO to endorse or have oversight of this work.

Technical assistance activities for IFD workstream included updating and translating the manual that had been developed under TAFFI. ASI also developed a workplan for the IFD CEO detailing potential activities. The purpose of this workplan was to share with the IFD Board of Directors to get their buy-in on IFD’s plans for the year ahead; however, during the reporting period the workplan was not signed off by the CEO or presented to the Board. ASI also recruited a Strategic Financial Advisor into the IFD, whose salary is supported by ICED. Since this reporting period, the financial advisor has been onboarded and is performing effectively, providing technical assistance to IFD staff and insight into IFD’s functionality.

ASI also delivered technical assistance to IFD upon direct request from the CEO on the operationalisation of Sectoral Holdings (‘mega firms’). The work included a document outlining the concept of mega firms, a proposal template for new mega firms to be presented to the Board (although this template has not been approved by the Board), and a comparative analysis was started on the potential of different economic ‘zones’ in Iraq (free zones, industrial zones and special economic zones).

For the KRG workstream, ASI developed a data dashboard which brought together expenditure and revenue data from 2018 – 2024 and 2021 – 2024 respectively and used this data to estimate the KRG’s Gross Domestic Product. ASI also recommended organisational improvements (such as a structure, and recommendations for change-management) for KRG’s Debut Management Unit, and the nascent Fiscal Policy Unit. Whilst KRG were open to this, they require approval from the Federal Iraq Government, which has not yet been granted, to proceed

Similar issues around a lack of proactive consultation and communication of delivery were also present in this work. Following a routine visit to KRI and a review of progress, the FCDO stopped this workstream as it was not meeting expectations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

FCDO recommends much clearer communication between ASI and FCDO to ensure FCDO are fully aware of and have actively approved activities to take place. This should be done through consistent, clear reporting, and governance processes being mutually agreed and followed.

The programme team also recommend improvements to the governance and reporting chains between BE Baghdad, ASI as the implementing partner, ASI as the PFRC Managing Supplier Centre of Expertise framework manager, and the relevant FCDO team at HQ (Public Finance and Tax Department), as ways of working and mandates between this large set of internal stakeholders was often unclear. For work in the KRI, we recommend the British Consulate in Erbil is fully aware and involved, given they own stakeholder relationships.

Some significant progress has been made towards this recommendation in the time since this reporting period.

## VALUE FOR MONEY (1 page)

Key cost drivers and performance

Promoting sustainable economic reforms will help diversify Iraq’s economy and bolster economic stability, addressing the underlying drivers of insecurity in Iraq - a core objective defined in the Country Business Plan. This work has the secondary benefit of improving the environment for UK trade and investment growth in Iraq, which provides value for money by enabling mutual growth priorities between the UK and Iraq.

ICED also focuses on enhancing Iraq’s ability to better use its own resources to encourage stability and development, from supporting tax and customs revenue administration to the efficient operationalisation of state development funds. This provides a long-term multiplier effect on the value of funds deployed under this programme.

Economy - Are we (or our agents) buying inputs/resources of the appropriate quality at the right price?

HMRC TA - Utilizing another government department (HMRC) through an MOU a) allows us to make use of well-respected UK government expertise, which can provide credibility and enable greater access and influence to stakeholders, compared to an external consultant, and b) allows FCDO to make use of permanent civil service staff time, rather than a ‘day rate’ that a commercial consultant would charge. However, because of the operating model for HMRC TA whereby FCDO cover 50% of full business costs, combined with security constraints in Iraq limiting the number of visits it is difficult to compare VFM between fixed staff time and a consultant’s day rate.

ICED PFM – ICED-PFM’s collaboration with the ASI-delivered ISF-Iraq funded programme generates cost savings. ICED-PFM leverages ASI’s platform through preferential vendor relationships and strategic pooling of resources, such as ASI’s Iraq Security Advisor, who provides services with costs shared between programmes.
Furthermore, BE Baghdad was able to benefit from PFRC managing the procurement processes such as contract set up and due diligence for both the interim and substantive interventions.

Efficiency- How well are we (or our agents) converting inputs into outputs?

HMRC TA – The requirement for high FCDO programme support (compared to delivery via a commercial supplier) hampers the input vs output balance.

ICED PFM – While ICED PFM has effectively converted effort into deliverables, it is too early to assess the tangible impact. For example, governance documents drafted but not put in force by IFD, structures for KRG fiscal policy unit drafted but unit not formed, although the structures have been used to inform the secondment of staff into a virtual fiscal unit. Going forward, a candid assessment of the potential blockers, often political, to transforming effort to real world impact should be prioritised before effort is misplaced.

Effectiveness – How well are the outputs produced by an intervention having the intended effect (are we spending wisely?)

The tangible real-world impact of the outputs delivered under ICED in this period was modest. The trainings delivered under HMRC TA were well received but it is unclear whether a momentum for change was created, and it is too early to assess the impact.

While ICED PFM continued delivery on IFD for continuity from the ISF-funded programme, the majority of workstreams were in scoping phases to position the intervention for greater impact in the subsequent period.

Equity – How fairly are the benefits distributed? To what extent will we reach marginalised groups (are we spending fairly?)

Improved revenue generation and administration will allow GOI to invest more in public services. A lack of investment in public services due to a bloated civil service and poor fiscal management of public spending disproportionality affects marginalised groups and communities that depend on public services. In a broader sense, ICED seeks to reduce the risk of economic instability in Iraq, which would disproportionately impact the poorest and most marginalised groups.

Gender, disability, and climate/environment markers are not directly incorporated into the logframe or outputs. As the programme expands, this will be reviewed.

Cost Effectiveness – What is the intervention’s ultimate impact on our foreign policy objectives, relative to the inputs that we or our agents invested?

This programme aligns closely to the Iraq Country Business Plan, supporting, directly or indirectly, goals related to Economic Growth, Security, and Irregular Migration. It works in conjunction with British Embassy Baghdad’s wider diplomatic efforts on economic reform to support GOI’s economic diversification and reform agenda, while the flexibility of the programme enables delivery under ICED to adapt to shifting resource constraints and government priorities.

Assessment of whether the programme continues to represent value for money

The second year of delivery under ICED remained one of establishment and transition. Delivery under HMRC TA was successful in engaging GOI, but was ultimately discontinued. ICED PFM first provided continuity of support to IFD, then established the framework for a longer term and wider scope intervention. The investment in an inception period, including a significant investment of BEB staff time in establishing ways of working, relationships, and access, should return greater impact in the subsequent delivery period.

The true test of VFM this period, will be delivery and impact in the next. We would expect to see a greater impact in the subsequent period, however, any assessment of VFM should also consider the context of operating in Iraq. The security environment is unpredictable and the political environment is extremely resistant to change. Against those challenges, achieving even very modest impact in the economic reform space can require significant investment. But given Iraq’s economic fragility, this is an objective of highest importance, and even modest progress should be considered success. Future progress may also be attributable, at least in part, to the inputs and delivery described in this Annual Review.

E: RISK

Overview of risk management

Overall, the risk appetite for ICED remains consistent at ‘moderate’, and the overall risk rating remains moderate. At the end of the reporting period, 62% of risks had a residual rating of ‘minor’.

Risks on the current risk register were actively managed and include consideration of programme risks and mitigations relating to all partners, and their components within the overall programme. Programme risks are regularly discussed and documented ahead of quarterly British Embassy Baghdad Programme Board. Any risks outside of risk appetite escalated as appropriate.

Political risks were actively discussed in meetings suggests an awareness of contextual challenges.

Risk management processes have been continually strengthened over this reporting period to clarify roles, responsibilities and accountabilities between the FCDO, implementing partners and PFRC framework managers. These improvements are now delivering tangible benefits to programme delivery in the current reporting period.

A risk that was persistent throughout the reporting period was unpredictable demand and engagement from GoI counterparts, which added a level of uncertainty and risk to any planned intervention. This risk has been mitigated by implementing partners designing interventions that closely follow demand, and partners continually seeking feedback from counterparts on whether interventions are meeting needs.

Fraud remains a significant concern when engaging with public institutions in Iraq, where systemic corruption continues to pose a challenge for governance and service delivery. While this risk is usually high in direct dealings, ICED-PFM is not exposed to such risk because it only provides technical assistance to institutions and does not make any investment in, or through, such institutions. However, this risk is monitored closely throughout the reporting period.

Due diligence: FCDO does not need to do due diligence for ICED, because a)Due diligence is not a requirement to do due diligence on another government department (HMRC), and b) PFRC Centre of Expertise Managing Supplier has undergone due diligence by the Public Finance and Tax Department who procured the Centre of Expertise, and the Managing Supplier are responsible for due diligence of implementing partners (ASI)

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Reporting:
HMRC were not required to provide regular reporting to FCDO, but did submit post-training reports after each visit to Iraq, detailing the activities undertaken and an assessment of their success. HMRC also maintained a risk register.Therefore, there is limited self-assessment relating to how HMRC managed programmatic obligations.

ASI delivered two reports during this period (the final report relating to the interim intervention, and the quarter 1 report that covered the inception period). ASI have been generally receptive to FCDO’s reviews and over the reporting period (and beyond) we have seen improvement in ways of working and programme management. FCDO and PFRC Managing Supplier have reflected on the need for tighter Terms of Reference being developed through the procurement process to set out clearer expectations for reporting and governance processes.

Financial management:
Over the reporting period, both partners required strong oversight by the FCDO programme manager to ensure forecasts were up to date, particularly in the last quarter of the financial year. However ultimately, both partners spent the majority of their allocations, with HMRC reporting a 6% underspend, and ASI reporting a 1% underspend. This reflects strong financial management and ability to be flexible in a challenging context, where political economy or security changes means that scoping or technical assistance missions can get cancelled at short notice.

A period in which ASI did not update their forecasts for a number of months led to expectations of an underspend, which FCDO partially nominally reallocated from ICED to other high priority parts of the portfolio. When forecasts were updated, this then led to a shortfall. ASI were receptive to FCDO’s requests to stop/pause work, and some work was pushed back into the next reporting period

Engagement between internal stakeholders:
HMRC: a weekly call between FCDO and HMRC programme managers was instigated by FCDO to ensure HMRC delivery remained on track. Additionally, given the number of HMRC officials travelling to Baghdad for trainings, significant resource was required to facilitate these visits (such as logistics, security considerations, and organising meetings on behalf of HMRC).

ASI: ASI have reflected that dual-client structure (PFRC and the Embassy) naturally requires more coordination time than the predecessor programme or the originally proposed model in ASI’s bid. ASI has responded to this challenge by implementing internal organisational adjustments. FCDO agrees with this assessment, as the same was true on our side (managing PFRC, ASI, PFTD etc), and this required a huge investment of human resource (PRO and SRO both heavily leaning in, including proposing new reporting structures and ways of working, providing feedback repeatedly in different formats, etc). There is scope for greater efficiencies to be made in the ways of working between the Embassy, PFRC Centre of Expertise and the implementing partner.

Making effective programme decisions:
FCDO made a series of decisions throughout the reporting period that improved the programme and drove value for money.

HMRC: FCDO considered the political economy context in Iraq and judged the value the trainings to mid-senior level officials in the GCT was not sufficient to justify further workshops in this format. Whilst the training itself throughout the reporting period received positive feedback, FCDO did not see sufficient evidence that it was driving policy change at the decision-making level. This decision was communicated in person to HMRC, whilst they were in Baghdad delivering training in January 2025. This adaptive and realistic approach enabled both HMRC and FCDO to agree to step back and consider in slower time how UK expertise, delivered through programming, can be better targeted.

ASI: Workstreams under ICED PFM were prioritised over the delivery period, with a number of workstreams paused or ended where the path to tangible impact appeared unlikely. This effort was led by FCDO, a more active role by the other parties to ICED-PFM would lead to more effective prioritisation, and pivoting to more impactful workstreams.

Gender Equality, Disability and Social Inclusion (GEDSI)
It can be challenging to deliver tangible GEDSI results when delivering interventions focused on macro-level policy reforms, however this reporting year there has been some progress towards it.
HMRC strove for gender representation at the workshops they delivered. This varied depending on the audience, but in one workshop HMRC achieved a nearly 50% female audience. HMRC reflected that they did not have access to data on GCT’s staffing composition and therefore it was challenging to specifically target people with disabilities for training. HMRC also suggested that in future iterations of programming, it would be beneficial to design workstreams that support GoI in designing GEDSI-prioritised personal income tax policies.

ASI has sought to ensure the HR and procurement manuals they developed for IFD include references to best practice on inclusion and fairness. However, because the manuals have not been approved by the IFD Board of Directors in this reporting period, these best practices are not currently being implemented.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
FCDO prioritised accompanying implementing partners to meetings with key stakeholders, and attended planned trainings and workshops where possible. This was sometimes difficult due to the breather break system for BE Baghdad. There is also scope for ASI to provide more notice of their visits to ensure Embassy staff availability to maximise collaboration.

Secondly, a more uniform approach to setting delivery expectations under the various workstreams would aid FCDO’s ability to monitor progress and ensure continued quality.

Evidence
Evidence collection on the HMRC side was strengthened this reporting year through ensuring feedback surveys were printed in Arabic, so participants felt encouraged to fill them out. The responses were then translated into English by an Arabic-speaker in HMRC, to keep costs down.

Learning
Several learning processes were followed over the reporting period, including quarterly and regular meetings with partners to discuss and adjust any activities. The team also used the development of proposals for FY25/26 as a learning opportunity – deciding to conclude the component with HMRC with the acknowledgement that the audience and content was not delivering impact in this political context, and adding greater flexibility in the PFRC Centre of Expertise ASI contract to add and remove workstreams as contextually and strategically appropriate.

Key lessons emerged from this reporting period, including the importance of balancing breath of activity over depth in two ways: a) through this period, we have learnt the importance of critically assessing requests from counterparts against political economy criteria. Taking a narrower and more realistic approach to delivering technical assistance at the organisational level, where priorities change frequently, will yield better political access, influence and reform results. This was highlighted by HMRC’s work in particular: attempting to service as many requests from the GCT as possible may help in strengthening HMG’s relationship with certain stakeholders, but the actual return on investment is limited because significant resource is put into developing activities that are no longer as relevant by the time of delivery. We ensured that our activities started in this reporting period were tested for their ability to withstand potential changes resulting from the upcoming election in November 2025

b) through this period we have learnt to be flexible and agile within existing workstreams. For example, much of this reporting period was spent developing best practice manuals for the IFD. However, these manuals have not been approved by the IFD Board so are not embedded within the organisation. Therefore, we have recommended to ASI to shift their focus within the IFD workstream to more achievable activities (such as training IFD employees in financial accounting methods), thus maintaining key relationships in potentially catalytic areas which can build over time.

The second key lesson is to ensure strong communication and programme management principles are embedded within implementing partners. This includes fully resourcing these roles and agreeing up front ways of working including processes for decision making. These processes are used frequently given the programme is designed to respond to GoI demands flexibly, so it is critical the processes are designed to be robust enough to ensure compliance, value for money and rigour in interventions, but flexible enough that interventions can be deployed promptly, reducing underspend risk or decision-making bottlenecks.

Date of last narrative financial report	HMRC – February 2025 / ASI – July 2025	Date of last audited annual statement	HMRC – not required / ASI – 30 September 2025