## Logframe
Please refer to the Definitions and Guidance Notes on separate worksheets
Blue denotes standard PFRC indicator
Italics denotes that this work is at the concept stage: full indicators and description will be included after concept approval
PROJECT TITLE: Iraq Catalytic Economic Diversification - Public Financial Management
IMPACT | Impact Indicator 1 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
Improved economic governance and public financial management | Evidence of improved efficiency in customs processes | Planned | No formal MoF/GCC commitment to utilising risk-based approaches, which negatively impacts clearance times |  | 0 | 0 | MoF communicates publicly its formal commitment to roll out approved risk-based strategy and action plan to border points/crossings Case study assessing improvement in clearance times at the pilot checkpoint
Achieved
Source
Verified by GCC and MEL adviser
| Impact Indicator 2 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| Improved practices are implemented across a larger number of CFPG projects, and poverty reduction targeting and impact increase | Planned | 0 improved practices in place |  |  |  | Case study assessing improved practices in poverty reduction targeting and impact
Achieved
Source
Verified by CFPG and MEL adviser
| Impact Indicator 3 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| IFD-supported investment in non-oil sectors | Planned | 0 |  |  | USD 2m | USD 25m
Achieved
Source
Verified by IFD and MEL adviser
OUTCOME 1: PFM | Outcome Indicator 1.1 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
Government expenditure is effectively and transparently managed to focus on development objectives through the adoption of robust expenditure control systems and accountability mechanisms. | Investment commenced/ completed in line with IFD Investment Policy Statement | Planned | IFD Investment Policy Statement submitted to IFD Board |  | IFD Investment Policy Statement approved by IFD Board | Mega Firms Governance structure approved by IFD | Case study showing Investment Policy Statement, private sector engagement tools and megafirms tools are being utilised by IFD staff | Security situation is stable enough for in-country work to be effective Political will of IFD is strong enough for it to implement recommended approaches and approve statements, policies and frameworks IFD brings on board the required capacity, skills, resources, policies and procedures in Investment capacity and management IFD can mobilise resources to adequately support new specialised staff in investment management IFD staff remain in place for sufficient time to develop new knowledge and skills There is sufficient data to measure IFD adoption of ICED recommendations and increased knowledge/skills of IFD staff Political will of CFPG is strong enough for it to implement recommended approaches and practices CFPG brings on board the required capacity, skills, resources, policies and procedures CFPG can mobilise resources to adequately support new specialised staff CFPG staff remain in place for sufficient time to develop new knowledge and skills There is sufficient data to measure CFPG adoption of ICED recommendations and increased knowledge/skills of CFPG staff
Achieved
Source
Verified by IFD and MEL adviser
| Outcome Indicator 1.2 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| IFD governed and operating in line with international good standards | Planned | Draft governance manual shared with IFD |  | Draft governance structure/framework submitted to IFD Board | Draft governance structure/framework approved by IFD Board | SOPs adopted and implemented
Achieved
Source
Verified by IFD and MEL adviser
| Outcome Indicator 1.3 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| CFPG governed and operating in line with international good standards | Planned | 0 | 0 | PMO endorses project and approves its launch | PMO endorses project and approves its launch | Case study showing three major recommendations to enhance project lifecycle management, in connection with the pilot project, are adopted by CFPG
Achieved
Source
Verified by CFPG and MEL adviser
| Outcome Indicator 4 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| New Kurdistan Regional Government debt reforms implemented | Planned | 0 |  | 0 | 0 | 0
Achieved
Source
| Outcome Indicator 1.4 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| New Kurdistan Regional Government fiscal reforms implemented | Planned | Virtual Fiscal Policy Unit established |  | Virtual Fiscal Policy Unit established
Achieved
Source
Verified by FPU and MEL Adviser
| Outcome Indicator 1.5 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| # strengthened processes/ systems in use/ operational # organisational performance statistics showing progress For each, a qualitative analysis (integrating GESI analysis) of actual/ expected consequences of take-up/ change. | Planned | 0 |  |  |  | (see definitions W/S) 2 strengthened processes/ systems in use/ operational 1 organisational performance statistic showing progress 1 case study on how the tools and capacity are being used
Achieved
Source
Case study
OUTCOME 2: Revenue | Outcome Indicator 2.1 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
Iraqi revenue institutions adopt selected good practices to increase and diversify the revenue base. | Customs performance Pilot implementation of risk-based approaches at checkpoint | Planned | Risk-based approaches not being used |  |  |  | Case study showing pilot checkpoint is assessing implemention of risk-based approaches | Security situation is stable enough for in-country work to be effective Political will of MoF and GCC beneficiaries is strong enough for GCC to adopt risk-based methods GCC invests in management and capacity by brining on board the required skills, resources, policies and procedures Technical staff are receptive to the intervention There is sufficient data to measure GCC adoption of risk-based methods at GCC HQ and in the pilot location
Achieved
Source
Verified by GCC and MEL adviser
| Outcome Indicator 2.2 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| Customs capacity: functional strategies, operational plans and risk management framework implemented integrating good customs practice | Planned | None implemented |  |  | 0 | 2 implemented
Achieved
Source
Verified by GCC and MEL adviser
| Outcome Indicator 2.3 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026)
| # strengthened process/ system in use/ operational For each, a qualitative analysis (integrating GESI analysis) of actual/ expected consequences of take-up/ change. | Planned | 0 |  |  |  | (see definitions W/S) 2 strengthened processes/systems in use/ operational 1 organisational performance statistic showing progress 1 case study on how the tools and capacity are being used
Achieved
Source
Case study
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
Organisational capacity: Tools, strategies, guidelines are co-developed and shared with prepared/ briefed counterpart organisations for effective performance of key functions | Iraq Fund for Development: # tools co-developed (e.g. frameworks, guidelines, analyses, diagnostics, methodologies, roadmaps, plans) % of which that integrate GESI analyses/ tools Qualitative feedback on counterpart satisfaction | Planned | Draft operational compliance manuals developed (Procurement, Finance, and HR Manual) Draft IFD Policy Statement developed Governance manual submitted to the Board | Operational compliance manuals submitted to IFD Concept paper on investment modalities drafted" | Operational compliance manuals submitted to IFD IFD Policy Statement revised and submitted to IFD Authority and Responsibilities Framework Developed and submitted to IFD Qualitative feedback on counterpart satisfaction | Updated Procurement Manual Messaging on key IFD objectives, tailored for relevant stakeholders C&E strategy Approved Finance Manual Megafirms package | Updated HR Manual Accrual-based accounting SOPs Procurement SOPs Private sector engagement package | Security situation is stable enough for in-country work to be effective Political will of IFD is strong enough for it to implement recommended approaches and approve statements, policies and frameworks IFD brings on board the required capacity, skills, resources, policies and procedures in Investment capacity and management Technical staff are receptive to the intervention IFD can mobilise resources to adequately support new specialised staff in investment management IFD staff remain in place for sufficient time to develop new knowledge and skills There is sufficient data to measure IFD adoption of ICED recommendations and increased knowledge/skills of IFD staff
Achieved
Source
Verified by IFD and MEL adviser
| Output Indicator 1.2 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
| GCC: # tools co-developed (e.g. frameworks, guidelines, analyses, diagnostics, methodologies, roadmaps, plans) % of which that integrate GESI analyses/ tools Qualitative feedback on counterpart satisfaction | Planned | Basic ASYCUDA system in place |  |  | Risk management strategy co-developed with GCC Risk management action plan co-developed with GCC | Risk management unit standard operating procedures co-developed with GCC Co-development of ‘good practice guides’ in customs border controls | Security situation is stable enough for in-country work to be effective Political will of MoF and GCC beneficiaries is strong enough for GCC to adopt risk-based methods GCC invests in management and capacity by brining on board the required skills, resources, policies and procedures Technical staff are receptive to the intervention There is sufficient data to measure GCC adoption of risk-based methods at GCC HQ and in the pilot location
Achieved
Source
Verified by GCC and MEL adviser
| Output Indicator 1.3 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
| CFPG # tools co-developed (e.g. frameworks, guidelines, analyses, diagnostics, methodologies, roadmaps, plans) % of which that integrate GESI analyses/ tools Qualitative feedback on counterpart satisfaction | Planned | 0 |  | Strategic workplan developed | Project lifecycle analysis diagnostic report Recommended reforms including improved project management processes and tools | Proposal for reform scale up across CGPF project portfolio | Security situation is stable enough for in-country work to be effective There is clarity on the level of ICED engagement required Political will of CFPG is strong enough for it to implement recommended approaches and practices CFPG brings on board the required capacity, skills, resources, policies and procedures Technical staff are receptive to the intervention CFPG can mobilise resources to adequately support new specialised staff CFPG staff remain in place for sufficient time to develop new knowledge and skills There is sufficient data to measure CFPG adoption of ICED recommendations and increased knowledge/skills of CFPG staff
Achieved
Source
Verified by CFPG and MEL adviser
| Output Indicator 1.4 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
| KRG: # tools co-developed (e.g. frameworks, guidelines, analyses, diagnostics, methodologies, roadmaps, plans) % of which that integrate GESI analyses/ tools Qualitative feedback on counterpart satisfaction | Planned | Data dashboard developed Fiscal overview for KRG FPU roles and responsibilities defined
Achieved
Source
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
Individual capacity: Staff in counterpart organisations have enhanced technical skills knowledge and professional capabilities to effectively perform key functions | IFD: - % capacity development goals in critical functional areas achieved - knowledge score (before and after) - level of counterpart satisfaction All disaggregated by participant – age, seniority, gender, disability etc. | Planned | No IFD staff trained | 75% of the following capacity development goals achieved for finance department staff (8 staff):cash based accounting, petty cash management | 75% of the following capacity development goals achieved for finance department staff (8 staff):cash based accounting, petty cash management and budget reconciliation |  | Practical training on SOPs Development of induction training for future staff on application of megafirms package documents Training on accrual-based accounting Development of online training for future staff on application of private sector engagement package documents 80% of counterpart staff are satisfied with the capacity development support given. | Security situation is stable enough for in-country work to be effective Political will of IFD is strong enough for it to implement recommended approaches and approve statements, policies and frameworks IFD brings on board the required capacity, skills, resources, policies and procedures in Investment capacity and management Technical staff are receptive to the intervention IFD can mobilise resources to adequately support new specialised staff in investment management IFD staff remain in place for sufficient time to develop new knowledge and skills There is sufficient data to measure IFD adoption of ICED recommendations and increased knowledge/skills of IFD staff
Achieved
Source
Verified by IFD and MEL Adviser, including through surveys where trainees identify as having improved knowledge
| Output Indicator 2.2 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
| GCC - % capacity development goals in critical functional areas achieved (this will include ASYCUDA) - knowledge score (before and after) - level of counterpart satisfaction All disaggregated by participant – age, seniority, gender, disability etc. | Planned | Very limited knowledge of risk management practices |  | Senior management risk management training delivered |  | Delivery of a minimum of 5 risk management trainings to GCC (20 trainees in each case), and possibly to other border/tax agencies and commercial sector Delivery of ‘on the job’ training in at least one checkpoint 60% of trainees self-identify as having improved knowledge/skills in relation to on the job training at a checkpoint 60% of trainees self-identify as having improved knowledge/skills in relation to risk management | Security situation is stable enough for in-country work to be effective Political will of MoF and GCC beneficiaries is strong enough for GCC to adopt risk-based methods Turnover of GCC staff in targeted areas is low GCC invests in management and capacity by brining on board the required skills, resources, policies and procedures There is sufficient data to measure GCC adoption of risk-based methods at GCC HQ and in the pilot location
Achieved
Source
Verified by GCC and MEL adviser, including through surveys where trainees identify as having improved knowledge
| Output Indicator 2.3 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
| CFPG - % capacity development goals in critical functional areas achieved - knowledge score (before and after) - level of counterpart satisfaction All disaggregated by participant – age, seniority, gender, disability etc. | Planned | No CFPG staff trained | 0 | 0 |  | 60% of trained/mentored staff self-identify as having improved knowledge/skills | Security situation is stable enough for in-country work to be effective There is clarity on the level of ICED engagement required CFPG brings on board the required capacity, skills, resources, policies and procedures Technical staff are receptive to the intervention CFPG can mobilise resources to adequately support new specialised staff CFPG staff remain in place for sufficient time to develop new knowledge and skills There is sufficient data to measure CFPG adoption of ICED recommendations and increased knowledge/skills of CFPG staff
Achieved
Source
Verified by CFPG and MEL adviser, including through surveys where trainees identify as having improved knowledge
| Output Indicator 2.4 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
| KRG - % capacity development goals in critical functional areas achieved - knowledge score (before and after) | Planned
Achieved
Source
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
Adaptive intervention management practices deliver high quality TA and deliverables | Evidence of reflection and learning (including PECA) informing project decisions # (cumulative) of case studies analysing how decisions informed by evidence and learning generated by the MEL processes. | Planned | 0 | 0 | 1 (post inception reflection) | 1 | 2 | Good data available to measure performance
Achieved
Source
Reflection session documentation and updated given in quarterly reports
| Output Indicator 3.2 |  | Baseline (March '24) | Q1 (to end June 25) | Q2 (to end Sept 25) | Q3 (to end Dec 25) | Target (to end March 2026) | Assumptions
| Social Value: #, % and £ (cumulative) of person days delivered by women #, % and £ (cumulative) of person days delivered by disabled people #, % and £ (cumulative) of person days delivered by Iraqi consultants | Planned | 0 | Women - Number of days: 11 - % of total days: 8.85% - Total Expenditure: £7361.63 Declared Disability - Number of days: 0 - % of total days: 0% - Total Expenditure :£0 Iraqi Nationals - Number of days: 47.875 - % of total days: 17.13% - Total Expenditure: £14,244.88 | Women - Number of days: 38.5 - % of total days: 5.61% - Total Expenditure: £44,012.37 Declared Disability - Number of days: 0 - % of total days: 0% - Total Expenditure: £0 Iraqi Nationals - Number of days: 96.5 - % of total days: 4.54% - Total Expenditure: £35,880.12 | Women - Number of days: 66.5 - % of total days: 15.68% - Total Expenditure: £58,545.00 Declared Disability - Number of days: 0 - % of total days: 0 - Total Expenditure: 0 Iraqi Nationals - Number of days: 114.5 - % of total days: 27.00% - Total Expenditure: £38,496 | Women - Number of days: 34.5 - % of total days: 11.54% - Total Expenditure: £38,484.00 Declared Disability - Number of days: 0 - % of total days: 0 - Total Expenditure: 0 Iraqi Nationals - Number of days: 83 - % of total days: 27.76% - Total Expenditure: £24,620.00 | Women and people with disabilities are available for engagement
Achieved
Source
Activity Based Budget (ABB)

## Definitions
Impact
Outcomes | From list of standard systems across PFRC intiatives
strengthened systems | 1. Procurement, Capital Investment Planning and Appraisal 2. Fiscal Risk Management & Debt Management
organisational performance statistics | IFD-supported investment in non-oil sectors (from impact indicators)
Outputs
indicator 2.1, quarter 3 | Critical functional areas: financial statement, budget preparation, financial controls, compliance, financial analysis and reporting and procurement
indicator 2.1, quarter 4 | Critical functional areas: Financial Statement Analysis & Valuation, Legal/ Regulatory Compliance, Due Diligence, Operational/ Market Due Diligence, and Deal Structuring & Negotiation.

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | Impact Indicator 1 | Baseline added: No formal MoF/GCC commitment to utilising risk-based approaches, which negatively impacts clearance times | Paul Davies | November 12, 2025
2 | Impact Indicator 1 | March 2026 milestone added: MoF communicates publicly its formal commitment to roll out approved risk-based strategy and action plan to border points/crossings Case study assessing improvement in clearance times at the pilot checkpoint | Paul Davies | November 12, 2025
3 | Impact Indicator 2/3 | Impact Indicator 2 is now Impact Indicator 3, a new Indicator is now Indicator 2: 'Improved practices are implemented across a larger number of CFPG projects, and poverty reduction targeting and impact increase, with a March 2026 milestone of: Case study assessing improved practices in poverty reduction targeting and impact | Paul Davies | November 12, 2025
4 | Outcome Indicators | Numbering changed to 1.1, 1.2, 2.1, 2.2 etc for ease of reference with the Outcome in question. | Paul Davies | November 12, 2025
5 | Outcome Indicator 1.1 | Was previously Outcome Indicator 1. End Dec 2025 milestone change from: IFD Investment Manual approved by IFD to: Mega Firms Governance structure approved by IFD | Paul Davies | November 12, 2025
6 | Outcome Indicator 1.1 | End March 2026 milestone changed from: SOPs adopted/ implemented and are guiding investments to: Case study showing Investment Policy Statement, private sector engagement tools and megafirms tools are being utilised by IFD staff | Paul Davies | November 12, 2025
7 | Outcome Indicator 1.3 | Changed from: RFPG governed and operating in line with international good standards to: CFPG governed and operating in line with international good standards. End September 2025 Milestone added: PMO endorses project and approves its launch; End March 2026 milestone added: Case study showing three major recommendations to enhance project lifecycle management, in connection with the pilot project, are adopted by CFPG | Paul Davies | November 12, 2025
8 | Outcome Indicator 1.4 | Now one indicator replacing indicators 4 and 5. Baseline changed from: Initial training on good practice in debt management held to: Virtual Fiscal Policy Unit established; End Dec 2025 milestone removed | Paul Davies | November 12, 2025
9 | Outcome Indicator 1.5 | This is the old Indicator 6 | Paul Davies | November 12, 2025
10 | Outcome Indicator 2.1 | This is the old indicator 1 for Outcome 1. Indicator changed from: Customs performance (clearance times; enforcement rates) to: Customs performance, Pilot implementation of risk-based approaches at checkpoint. Basline added:Risk-based approaches not being used End March 2026 milestone added: Case study showing pilot checkpoint is assessing implemention of risk-based approaches | Paul Davies | November 12, 2025
11 | Outcome Indicator 2.2 | This is the old indicator 2 for Outcome 2. Baseline added: None implemented. End March 2026 indicator added: 2 implemented | Paul Davies | November 12, 2025
12 | Outcome Indicator 2.3 | This is the old indicator 3 for Outcome 2. End March 2026 milestone added: 2 strengthened processes/systems in use/ operational, 1 organisational performance statistic showing progress, 1 case study on how the tools and capacity are being used | Paul Davies | November 12, 2025
13 | Output Indicactor 1.1 | End December 2025 milestone changed from: SOPs for financial and Procurement procedures developed; Corporate Governance Guidelines for Mega Firms and their Subsidiaries & SPV developed to: Updated Procurement Manual, Messaging on key IFD objectives, tailored for relevant stakeholders, C&E strategy, Approved Finance Manual, Megafirms package. End March 2026 milestone changed from: SOPs for financial and Procurement procedures finalized, Corporate Governance Guidelines for Mega Firms and their Subsidiaries & SPVs finalised, Investment Manual developed, 75% of counterparts express satisfaction (or higher) on quality of tools to: Updated HR Manual, Accrual-based accounting SOPs, Procurement SOPs, Private sector engagement package | Paul Davies | November 12, 2025
14 | Output Indicator 1.2 | End December 2025 milestone changed added: Risk management strategy co-developed with GCC, Risk management action plan co-developed with GCC. End March 2026 milestone added: Risk management unit standard operating procedures co-developed with GCC, Co-development of ‘good practice guides’ in customs border controls | Paul Davies | November 12, 2025
15 | Output Indicator 1.3 | RFPG changed to CFPG. End December 2025 milestone added: Project lifecycle analysis diagnostic report, Recommended reforms including improved project management processes and tools. End March 2026 milestone added: Proposal for reform scale up across CGPF project portfolio | Paul Davies | November 12, 2025
16 | Output Indicator 1.4 | Baseline changed from: Data dashboard developed / fiscal overview for KRG, Roles and responsibilities defined (for FPU) to: Data dashboard developed, Fiscal overview for KRG, FPU roles and responsibilities defined. End December 2025 milestone added: Close out completed including - GDP forecast developed - prototype debt management manual developed - guidance on UN DMFAS licensing developed - data dashboard finalised - fiscal note finalised | Paul Davies | November 12, 2025
17 | Output Indicator 2.1 | End of December 2025 milestone removed. End of March 2026 milestone changed from: 75% of capacity development goals in critical functional areas achieved for finance department staff (8 staff), 80% of counterpart staff are satisfied with the capacity development support given to: Practical training on SOPs, Development of induction training for future staff on application of megafirms package documents, Training on accrual-based accounting, Development of online training for future staff on application of private sector engagement package documents, 80% of counterpart staff are satisfied with the capacity development support given. | Paul Davies | November 12, 2025
18 | Output Indicator 2.2 | Basline added: Very limited knowledge of risk management practices. End September 2025 milestone added: Very limited knowledge of risk management practices. End March 2026 milestone added: Delivery of a minimum of 5 risk management trainings to GCC (20 trainees in each case), and possibly to other border/tax agencies and commercial sector, Delivery of ‘on the job’ training in at least one checkpoint, 60% of trainees self-identify as having improved knowledge/skills in relation to on the job training at a checkpoint, 60% of trainees self-identify as having improved knowledge/skills in relation to risk management | Paul Davies | November 12, 2025
19 | Output Indicator 2.3 | RFPG changed to CFPG. Baseline added: No CFPG staff trained. End March 2026 milestone added: 60% of trained/mentored staff self-identify as having improved knowledge/skills | Paul Davies | November 12, 2025
20 | Output Indicator 2.4 | Baseline and milestones removed | Paul Davies | November 12, 2025
21 | Output Indicator 2.3 | Detailed milestones added | Paul Davies | November 12, 2025
22 | Assumptions | Much more detailed and tailored assumptions added to Outcomes and Outputs | Paul Davies | November 12, 2025
23
24
25
26
27
28
29
30
31
32
33

## Social value cumulative (hidden)
| Days |  |  |  |  | £
Women | 11 | 38.5 | 66.5 | 34.5 | 150.5 | 7361.63 | 44012.37 | 58545 | 38484 | 148403
Disabled people | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Iraqi nationals | 47.85 | 96.5 | 114.5 | 83 | 341.85 | 14244.88 | 35880 | 38496 | 24620 | 113240.88
[5 empty] | 492.35 |  |  |  |  | 261643.88

## Guidance Notes
Logframe Template Guide
The logframe objectives (impact, outcomes, outputs) need to align with the Theory of Change
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.