## Annual Review Template

Title: Education in Emergencies and Protracted Crisis (EiEPC) III
Programme Value £ (full life): £90,000,000		Review date: October 2025
Programme Code: / 301539	AMP start date: 2/11/2023	AMP end date: / 1/6/2027

Summary of Programme Performance
Year	2023/24	2024/25
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005046.odt
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301539 Documents

For list of acronyms, see Annex A.
A. SUMMARY AND OVERVIEW
1. Some 234 million children worldwide are affected by crises and in need of education support, with 37% (85 million) out of school[1]. This number has surged in recent years, with increases due in part to major protracted emergencies in Gaza and Sudan, impacting education for more than 19.6 million children[2] since 2023. These numbers also reflect the increasing impact of climate change on education; in 2024 alone, 85 countries or territories saw their schools affected by climate-related hazards, with over 20 countries experiencing multiple rounds of school disruptions[3].
  [1] Global Estimates 2025 Update | Education Cannot Wait
  [2] Gaza: UNICEF & Save the Children (2023)  Education Under Attack in the Gaza Strip (PDF) Sudan: UNICEF & Save the Children (2023) 19 million children in Sudan out of school as conflict rages on
  [3] Save the Children. (2024, April 5). Half of out-of-school children live in countries most vulnerable to climate changeSave the Children International. https://www.savethechildren.net/news/half-out-school-children.
2. The Education in Emergencies and Protracted Crisis (EiEPC) III programme aims to ensure that children affected by crises can access quality, safe education, which helps them to lead healthy and productive lives. It contributes to the delivery of UK commitments on girls’ education, humanitarian support, and climate change through a combination of multilateral and bilateral partnerships.
- Component 1: Funding to Education Cannot Wait (ECW) to directly support up to 20 million children to be safe and learning and help drive reforms in the international system to improve EiEPC response (£80 million, aligned to ECW’s 2023 – 2026 Strategic Plan).
- Component 2: Boosting access to FCDO technical capability across education, humanitarian, and conflict sectors to support UK Posts and partners to respond better in the event of a crisis (£1 million).
- Component 3: Investing in thematic partnerships with organisations and UK Posts where this will deliver on UK EiEPC priorities (£9 million).
This programme work is supported by wider EIEPC policy engagement, including refugee education and climate change adaptation. It builds on the previous EiEPC II programme that ended in December 2024, which ran alongside this programme last year and funded the early stages of the technical assistance and thematic partnerships components.

Changing global aid architecture
1. Despite growing global needs, funding for education in emergencies and protracted crises (EiEPC) has declined markedly over the past few years. In 2024, humanitarian education funding fell from $3.7 billion to $3.1 billion due to stricter appeal boundaries, while development aid failed to bridge the gap[4]. As a result, the programme has missed most of its impact targets for this year. The funding gap increased even further in 2025 with the dissolution of USAID, which has removed $1 billion a year for international education including EiEPC. With other major donors likely to cut ODA, and humanitarian funding shifting towards short-term lifesaving support, EiEPC spend is expected to drop further in the coming months.
  [4] Futures-Cut-Short-FINAL.pdf
2. ECW has faced a highly challenging year. It started strongly with the appointment of Sigrid Kaag as the new Chair of its High-Level Steering Group, agreement to its updated Operational Manual and finalisation of the long-awaited hosting arrangement with UNICEF. However, the withdrawal of USAID and delays in other donor funding has reduced programme spend this year and next and will shrink the Secretariat by a third. The departure of its Director in July and ongoing Hosting Review add further uncertainty. These challenges have not affected fund delivery to date, with credit to its Secretariat for keeping deliverables on track. Nonetheless, it will need significant ExCom support over the next 12 months to successfully land its next replenishment and manage delivery risks.
3. The UK itself announced in March 2025 that it would be reducing its ODA spend from 0.5% to 0.3% of GNI by 2027. This caused some short-term budget uncertainty which delayed certain programme decisions and spend for components 2 and 3, though these are now largely back on track. Mid to long term budget decisions will be taken by FCDO Ministers and senior officials over the coming months.
4. Given that the number of children affected by crises continues to rise but the amount of funding is falling – including FCDO future funds – there is more need than ever to examine EiEPC approaches. The current multilateral architecture, while less fragmented than other sectors, still suffers from duplication and inefficiencies between organisations. There is a pressing need to clarify roles to improve cost-effectiveness and embed sustainability and self-reliance within countries.
5. FCDO has commissioned an independent portfolio evaluation to assess the most effective combination of delivery channels for EiEPC, with the aim of informing future UK investment and maximising value for money. Separately, the team has collaborated with other donors (Norway, Germany, Denmark, Canada) to undertake a rapid study of the education multilateral aid architecture. This work seeks to generate discussion on how the sector can evolve in line with the UN80 reform agenda and adapt to expected decreases in donor funding. The findings and follow-up from both these studies will be discussed in next year’s Annual Review.
Summary supporting narrative for the overall score in this review
The EiEPC III programme has scored an A for this AR. ECW is the only global fund dedicated to EiEPC and plays a unique role in advocacy, thought leadership, and grant management. While it has raised less funding than originally hoped – which has affected total reach – it is performing well against its other targets and is consistently refining and strengthening its delivery model. Its work on holistic learning outcomes, the EiE financing observatory and new MYRP consortium models are all commendable. ECW’s work has been successfully supported and supplemented by additional FCDO education capacity in the ECW Secretariat, the Sahel region and Middle East and North Africa (MENA) region. FCDO has also funded valuable initiatives on priority EiEPC themes related to climate and environmental change, refugee inclusion in national education systems and school feeding, as well as the multilateral EiEPC study.
Table 1: Summary: EiEPC Output-level performance[1]
Output	Score	Summary
Output 1: Better reach and quality of ECW programmes	A	Met expectations. Two targets have been met and one has been moderately exceeded.
Output 2: More effective system for collecting data at and generating evidence at country and global level	A+	Moderately exceeded expectations. Three targets were moderately exceeded and one target was met.
Output 3: Strong EiEPC capacities, systems and partnerships at country and global level	A	Met expectations. Two targets have been met, two targets have narrowly exceeded expectations.
Output 4: Reduced impact of climate change on education	B	Met expectations: One target was met and one was missed due to unexpected project closure

Table 2: Major lessons and recommendations for the year ahead
Overall recommendation
Overarching – ECW 2027 – 2030 Strategic Plan	Work with ECW and others to ensure lessons from implementing the current strategic plan, findings from the Genesis architecture study and evidence from research studies and evaluations (such as ERICC) are reflected into ECW’s next strategic plan.
Impact level recommendation
More crisis affected children safe and learning	In light of cuts to ODA and other overseas aid, revise the original ECW finance targets down accordingly.
Outcome level recommendations
Reformed international system which better funds, coordinates, and delivers EiEPC	Work with partners to ensure findings from the EiEPC portfolio evaluation and Genesis multilateral architecture study are disseminated widely and used to inform ongoing discussions on future of EiEPC architecture and programming. / Working with the Data for Foundational Learning lead, discuss with ECW (and others) the impact of USAID withdrawal on education monitoring and assessment for EiEPC contexts
Output level recommendations
Output 1: Better reach and quality of ECW programmes	Revise the ECW reach target for indicator 1.1, considering the financial constraints outside of ECW’s control.
Output 2: More effective system for collecting data at and generating evidence	Consider how FCDO could engage more on ECW learning briefs and dissemination events and share these with education advisors and posts. / Discuss with ECW whether to increase future milestones for output 2.4
Output 3: Strong EiEPC capacities, systems and partnerships	Engage with FCDO’s Centre of Expertise for Education and MENA teams, to ensure surge roles currently covered by the EiEPC business case are transitioned into other teams. / Engage in discussions with GPE and ECW on future school feeding research. / Use the monthly INSPIRE meetings to ‘deep dive’ into INSPIRE work within countries, to better understand the impact and variety of INSPIRE work on the ground. Look at refugee hosting countries where ECW and other actors are reducing their programming, to consider whether INSPIRE support would be appropriate. / Add a dedicated indicator to track the impact and use of the EiEPC architecture study and portfolio evaluation in future reporting.
Output 4: Reduced impact of climate change on education	Extend FCDO’s innovative work on climate resilient education systems and financing in financial year 25/26, particularly in disaster risk financing, pre-arranged finance, and anticipatory action. Introduce new indicators under this output accordingly.
Other
Risk Management	Encourage further discussion on country level risks at ExCom in light of the impact of decreasing aid budgets on partner operations.
Governance	Convene further discussions on ECW governance structures, in particular constituency models, as agreed at June ExCom.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The theory of change (ToC) underpinning the programme is set out at Annex B. There are no changes from what was set out in the EiEPC III Business Case.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
1. There is no single source of reliable data on the global impact of EiEPC interventions. We are tracking progress at global level through three complementary indicators[2]. Achievement on the three indicators this year compared to the baseline is summarised in the table below.
  [2] These indicators do not capture support for children and youth in emergencies from development funding as there is currently no agency collecting this data.
2. To note, there are some concerns for the quality of future years’ data given the withdrawal of USAID, who were major funders in this area. This should be discussed further with ECW, bringing in FCDO’s Data for Foundational Learning lead.
Table 3: Progress against impact indicators
Indicator	Baseline	Progress 23/24	Progress 24/25
% of school-aged crisis affected children in need of education support that are out-of-school (disaggregated)	35% (54% girls and 17% with functional difficulties)	Target: 32% / Achieved: 32% (53% girls and 17% with functional difficulties)	Target 31.5% Achieved: 37% (52% girls and 20% with functional difficulties)
Refugee enrolment rates a) primary school age, b) secondary school age (disaggregated)	Primary: 63% boys and 61% girls / Secondary: 36% boys and 35% girls	Target: 65% (primary) and 39% secondary) / Achieved: Primary: 65% / Secondary: 42%	Target: 67% (primary) and 41% secondary) / Achieved: Primary: 67% / Secondary: 37%
Number of children reached by education cluster partners out of those targeted, disaggregated by sex	9.3 million girls and 9.4 million boys	Target: 9.5 million girls and 9.6 million boys / Achieved: 10.6 million girls / 11.4 million boys	Target 9.5 million girls and 9.6 million boys / Achieved: / 7.4 m girls and 7.1m boys

1. Progress against impact indicators largely show a downward trend from the previous year, though changing data sets has made direct comparison slightly more challenging. It is highly likely that next years’ review will show further backsliding across all three indicators, given the major funding reductions over 2025 which will be reflected in next year’s reports.
2. On the plus side, refugee enrolment rates have continued to slightly improve on primary enrolment from 65% in 2023 to 67% in 2024. However, secondary enrolment has decreased from 42% to just 37%. This is due in part to reductions in funding, which often see more expensive secondary education cut first. However, in all but the lowest income states, the differences between enrolment rates among refugees and non-refugees remain stark, with far few refugees attending school[5].
  [5] UNHCR Education Report 2025 | UNHCR
3. The proportion of crisis-affected children out of school (OOS) in 2024 is 37%, missing the target and five percentage points higher than last year’s figures. UNESCO has updated its population estimates, using revised UN figures. Whilst this is a positive move that better reflects the available data, it means that it is impossible to directly compare figures to the previous year and assess whether the number of OOS children has increased. Nonetheless, the numbers are sobering. Over half of crisis-affected children of pre-primary age are not in school, 29% of primary school age children and 41% of secondary school age children.
4. Data on the number of children reached by education cluster partners also shows a downward trend, with partners in 2024 reaching only 76% of the children reached the previous year. This downward trend is likely to grow for next year’s data following drastic cuts to the education target figures within the 2025 Humanitarian Needs and Response Plan (HNRP). As a result of this reprioritisation process, education was disproportionately affected compared to the “Big Five” clusters (Food Security, Protection, WASH, Health, Nutrition). Across 21 countries with available data, education target numbers were reduced by 43%. In contrast, the “Big Five” clusters saw a 17% reduction in targets and a 30.5% decrease in funding needs. Some countries experienced extreme cuts, such as Chad and Sudan with up to 90% reductions. These figures reflect a shift towards prioritising lifesaving and protection activities, often at the expense of education, despite its critical role in crisis contexts. The scale of these reductions highlights the growing vulnerability of education in humanitarian planning and the urgent need for more balanced, sustainable funding approaches.
Table 4: Progress against outcome indicators
Outcome: Reformed international system which better funds, coordinates, and delivers education in response to conflict, protracted crisis, and climate change
Indicator	Target	On/Off Track
1.1 Number of ECW-supported Multi-Year Resilience Programmes (MYRPs) with evidence of increased academic and/or social-emotional learning outcomes for crisis-affected children and/or adolescents	15	On track - 15
1.2 Number of ECW MYRPs with evidence of improved coordination at the nexus	3	On track: 12
1.3 Funding mobilised for ECW Trust Fund in current Strategic period	$1.1 billion	Off track: / $934m
1.4 Number of indirect beneficiaries reached in INSPIRE supported countries (disaggregated by refugee status).	729,000	On track – 805,146

1. Outcome 1.1 Improving measurement of learning outcomes across all MYRPs has been a major focus for ECW this strategic plan. As set out in their recently published Holistic Learning Outcomes handbook, partners set their own learning outcomes based on data availability and programme design. A total of fifteen ECW-supported MYRPs have reported evidence of increased academic and/or social-emotional learning (SEL) outcomes for crisis-affected children and adolescents, meeting the target of fifteen. Of these, fourteen MYRPs demonstrated improvements in academic learning outcomes, while five showed gains in social-emotional learning. Notably, six MYRPs – in Bangladesh, Burkina Faso, Libya, Pakistan, Syria, and Uganda reported improvements in both academic and SEL outcomes. Additional evidence of partial or strong improvements in academic learning only was provided by MYRPs in the Central African Republic, Ethiopia, Mali, Niger, Nigeria, Peru, South Sudan, and the State of Palestine. One MYRP –Colombia– reported a partial or solid increase in SEL and/or well-being outcomes only. Publication of this handbook is a major step forward in improving learning outcomes measurement for EiEPC, which has lagged behind non-crises contexts.
2. Outcome 1.2 Twelve MYRPs have provided evidence of improved coordination at the humanitarian-development nexus, significantly surpassing the target of three. MYRPs in Ethiopia and South Sudan are sighted by ECW as illustrative examples, demonstrating enhanced coordination among diverse education partners to better align responses and funding in protracted crisis settings. ECW launched a nexus evaluation in 2024 to further assess coordination and delivery across development and humanitarian partners, with FCDO participating on the advisory group. The inception report highlighted numerous positive examples such as a Joint Education Needs Assessment in Burkina Faso that enabled coordinated planning between humanitarian and development partners, and the development of a costed Education Emergency Preparedness and Response Plan in South Sudan through collaboration with the Local Education Group, bringing together actors across the nexus. ECW also published a nexus diagnostic and design tools in 2024, which will be rolled out in all future MYRPs.
3. Outcome 1.3 Funding mobilised for ECW during the current strategic period (2023 – 2026) stands at $934 million, which is off track by $166m against the $1.1 billion target for the end of 2024. It is highly unlikely they will mobilise additional significant funds to reach the overall target of $1.5 billion. This shortfall reflects a challenging global environment, characterised by competing priorities and a reduction in aid to education, including shifts in US funding priorities. ECW are seeking resources in new donor markets, as well as thematic and geographic top-ups from existing donors and are developing innovative partnership models with the private sector and foundations. However, the risk of not meeting the funding target is now almost certain and will impact on final finance and reach targets for this strategic plan period.
4. Outcome 1.4: The INSPIRE programme was developed in response to the 2023 Global Refugee Forum pledge to include more refugee children in national education systems. UK support to the World Bank provides technical assistance to governments to develop and implement inclusion policies and plans, supports countries to access the IDA Window for Host communities and Refugees (WHR) for education, and provides a platform for knowledge generation and peer learning. In the period of this review, INSPIRE supported countries to reach 805,146 refugee beneficiaries, ahead of the 729,000 target. Of those, 167,260 were direct beneficiaries of the activities and leveraged funds, while the rest benefitted indirectly through changes in broader government programmes catalysed by INSPIRE activities and advocacy. In light of severe cuts to service delivery across the wider EiEPC sector, the added value of the INSPIRE programme has grown even further due its focus on sustainability and leveraging of IDA funds.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
1. The UK’s bilateral programme currently has a significant footprint in conflict and crisis settings, and the education cadre is building its capacity to deliver in these contexts. However, the EiEPC business case allows us to expand our reach beyond bilateral programming, and to explore the most effective methods for delivering in a range emergency of contexts. At this point in time, ECW remains the best option for supporting crisis response at a speed and scale that it is not possible through FCDO bilateral programming. In addition, we have mobilised much needed additional advisory capacity in contexts such as the Sahel and MENA regions, improving the effectiveness of FCDO investments in ECW and GPE; this includes essential advisory support for the ongoing crisis in Gaza. Component 3 on thematic partnerships is allowing us to accelerate progress on priority issues such as refugee integration and climate resilient education systems, all of which will become a stronger focus for FCDO in the planned shift away from direct service delivery towards system strengthening.
2. A crucial question going forward is how the UK should invest in EiEPC to maximise value for money. GPE and the World Bank have both been increasingly active in conflict and crisis settings and there are now multiple countries where ECW, GPE and the World Bank are all active. The EiEPC portfolio evaluation and Genesis multilateral architecture study will both play an important role in informing future programming and how ECW, alongside other education partners, can further strengthen its delivery to achieve the maximum possible results in the new global context.
## C. DETAILED OUTPUT SCORING

Output Title	Better reach and quality of ECW programmes
Output number:		1	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of children and adolescents reached with ECW support (FER and MYRP) disaggregated by gender and disability	10 million (54% girls and 1.8% with a disability)	Off target - 8.3m (51% girls and 1.9% with disabilities)
1.2 Number of children reached through FERs/MYRPs with a focus on climate change adaptation.	3.4m	Met expectations / 3.41m
1.3 Percentage of children reached with ECW support who are refugees.	25%	27.5% - Moderately exceeded expectations
1.4 Percentage of FER and MYRP funding transferred to national/local partners – including local women’s organizations (LWOs), organizations of persons with disabilities (OPDs), and refugee-led organizations – as directly as possible	25%	Moderately exceeded expectations: / 27.4%

1. This output scored an A as ECW have met or moderately exceeded three out of four indicator targets. They missed the target on children reached due to continued struggles to reach their financing target for this strategic plan period.
2. Output 1.1 In the first two years of the 2023–2026 Strategic Plan, ECW-supported programmes reached 8.3 million crisis-affected children and adolescents (51% girls) across 33 countries – up from 5.6 million in 2023. Of those reached, 5.9 million were supported through MYRPs (71% of total reach) and 2.4 million through FERs. This is lower than the logframe target of 10 million, in part because ECW have only mobilised 62% of its original fundraising target of $1.5bn; and in part, because the cost per child for each FER is higher than originally modelled. ECW very slightly exceed the sub-target of 1.8% of children reached having a disability. This target was set deliberately low given ongoing challenges with data collection, meaning that the real number of children with disabilities is likely much higher (see output 2.4 below).
3. Output 1.2 Climate-responsive programming expanded significantly in 2024. ECW integrated climate adaptation into  32 programmes (21 MYRPs and 11 FERs), reaching 3.41 million children in the first two years of the Strategic Plan. Eleven FERs were activated in response to climate-induced disasters such as floods and droughts, reaching over 528,000 children. These efforts reflect ECW’s growing emphasis on anticipatory action and resilience-building, including pilots in Pakistan and Somalia. Moving forward, ECW plan to set more ambitious milestones for climate-related reach for its next strategic plan to match the increasing scale of climate-driven crises.
4. Output 1.3 ECW-supported programmes reached 2.2 million refugee children – 27.5% of all children reached – moderately exceeding the Strategic Plan target of 25% and reflects ECW’s expanded support in refugee-hosting contexts such as the State of Palestine, Uganda and Egypt. Girls accounted for 50.8% of refugee children reached. FERs played a key role in this achievement, reaching 39% refugee learners through tailored interventions, including language bridging, MHPSS and accelerated learning. ECW also deepened its systems-level work to integrate refugee learners into national education frameworks, supported by an Acceleration Facility grant to UNHCR and partnerships with ministries in Chad, Ethiopia and Colombia. This is lower than their Global Refugee Forum 2023 pledge of reaching five million refugees by end 2026, because of the financial challenges noted under output 1.1.
5. Output 1.4 In 2024, ECW advanced its localisation agenda, with 29% of programme budgets planned for transfer to local and national actors, exceeding the 25% milestone. MYRPs led this progress, averaging 31.7% compared to 15.8% for FERs, supported by ECW’s new consortium model requiring a minimum 25% allocation to local partners. Beyond financial transfers, ECW strengthened meaningful engagement through capacity-building, leadership roles in coordination platforms, and partnerships with women-led and refugee-led organisations. Future priorities include tracking actual (not just planned) transfers and sustaining institutional capacity support for local actors. ECW is one of the few multilateral partners who are actively committed to increasing funding through local partners, which remains an important Grand Bargain pledge.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
1. Output 1.2 – indicator changed from: ‘percentage of children affected by a climate-induced disaster reached among total children reached with ECW support’ to ‘Number of children reached through FERs/MYRPs with a focus on climate change adaptation’ with targets added.
2. Added Output 1.3 – Percentage of children reached who are refugees. Calculated based on ECW’s Global Refugee Forum (GRF) commitments to reach five million refugee children in the 2023-2026 Strategic Plan period against their original total 19.5 million children target, which represents 25% reach.
Future changes
To revise indicator for output 1:1 as ECW will be unable to meet the original reach milestones given the global financial shifts on ODA outside of their control. Future milestones should be proportionate to actual funding raised.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
1. Previous recommendations on a GRF pledge indicator and revised climate change indicator have been met, as detailed above.
2. The recommendation to ‘Follow up with the Secretariat on how they are planning to manage First Emergency Response (FER) results given resources constraints’ was overtaken by wider budgetary constraints faced by ECW this year. FER reach targets (and their cost assumptions) will be central to the next Strategic Plan development process so will be actively discussed in the coming months with ECW.
Output Title	More effective system for collecting data at and generating evidence at country and global level
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestones for this review	Progress
2.1 % FERs/MYRPs with data on time to monitor education participation, disaggregated by sex and education level	80%	Exceeded expectations / 95% (90% FERs, 100% MYRPs)
2.2 % MYRPs with data on time to monitor learning outcomes, disaggregated by sex and education level	50%	Exceeded expectations / 58%
2.3 Number of learning briefs produced and shared through dedicated learning events (organised by ECW or partners)	5	Met expectations / 5
2.4 Number of programmes (FERs and MYRPs) where quality tools (such as the Washington Group Child Functioning Module) are used to identify and count children with disabilities.	2	Exceeded expectations / 4

1. Output 2 scored an A+ as it exceeded expectations for three indicators and met one indicator.
2. Output 2.1 95% of FERs and MYRPs provided timely, sex-disaggregated data on education participation, surpassing the 80% milestone and reaching the 2026 target of 95%. This reflects significant progress from 84% in 2023. ECW reports this is driven by strengthened reporting systems and technical support to partners from the Secretariat. Improvements in data timeliness and quality have also enabled more accurate monitoring of gender equity in participation outcomes across ECW’s portfolio.
3. Output 2.2 In total, 58% of MYRPs provided timely, sex-disaggregated data on learning outcomes, exceeding the milestone and almost 50% higher than the baseline (39%). This is major win for ECW, who have pushed hard for partners to adopt most robust learning outcome metrics and ring-fence budgets (see outcome 1.1). It also reflects a growing emphasis in the EiEPC sector on the importance of improving and measuring learning outcomes, which the ECW Secretariat have helped drive forward.
4. Output 2.3 ECW met the milestone by producing and disseminating five learning briefs in 2024, aligned with the newly added definition of ‘concise, practical tools to share lessons and inform future strategies’. These included case studies on promoting local and national actor leadership in humanitarian coordination, with multilingual resources, and on OPD engagement in the Colombia MYRP. A brief on holistic learning for SEND learners in Uganda was produced with OpenDevEd and eKitabu. A policy paper outlined key insights on EiE financing, and a background paper addressed protecting children amid conflict, climate shocks and displacement. These briefs were disseminated through targeted events and platforms, reaching key stakeholders such as donors, implementing partners and cluster coordinators.
5. Output 2.4 ECW exceeded expectations by supporting four programmes to apply quality tools such as the Washington Group Child Functioning Module to identify and count children with disabilities. This represents a step forward in addressing persistent data gaps and advancing inclusive education. ECW also reaffirmed its commitment to allocate at least 5% of programme budgets to disability inclusion and is working with partners to institutionalise the use of standardised tools across all programmes. Unfortunately, FCDO was unable to proceed with the planned Junior Professional Officer on disability inclusion due to budget cuts, which has hampered ECW capacity to move faster on these ambitions.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
1. Indicator 2.2 – The sub-indicator for 2.1 was moved into a separate indicator, with an updated baseline and milestones.
2. Indicator 2.3 – a clear definition of a learning brief was agreed with ECW and added to the logframe.
3. Indicator 2.4 – defined the wording of the disability indicator to provide clarity on what was counted as an acceptable way of assessing the prevalence of disabilities i.e. the Washington Group tools.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
1. Gender data: the FCDO team engaged with the ECW Secretariat to follow up on the availability and quality of gender-disaggregated learning outcomes data. While initial efforts have shown some positive impact, further work is required to ensure consistent and comprehensive reporting across programmes. FCDO will continue to raise this in discussions with ECW through the strategic plan process.
2. On output 2.4: due to funding constraints, FCDO was not to provide technical support to ECW on disability in the form of a JPO as recommended under the previous annual review. FCDO should review with ECW whether to increase future milestones for output 2.4 to make it more stretching, given it was easily exceeded this year.
3. As discussed above, FCDO and ECW agreed a clear definition for learning briefs and set realistic targets. Going forward, FCDO should seek to become better informed of ECW learning briefs and dissemination events, including disseminating with posts and education advisors in country.
Output Title	Strong EiEPC capacities, systems and partnerships at country and global level
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of short- and long-term TA mobilised	3	Narrowly exceeded expectations / 4
3.2 Number of countries supported with INSPIRE grants	14	Narrowly exceeded expectations / 15
3.3 Education Research in Conflict and Crisis (ERICC) partnership delivering effectively and well-coordinated	EiEPC portfolio evaluation contracted and inception report completed	Met expectations
3.4 CGD partnership delivering effectively and well-coordinated	Phase 1 completed, and Phase 2 decision made	Met expectations

1. We judge that this output scores A as it is meeting expectations.
2. Output 3.1: Four short- and long-term Technical Assistance (TA) resources have been mobilised in this reporting year.
- Education support has been provided from The Humanitarian and Stabilisation Operations Team (HSOT) to support the MENA region, with a focus on the OPTs, to end January 2026.
- A cluster coordinator position for Darfur was funded for six months at the request of UNICEF in Sudan (October 2024 to April 2025).
- We have recruited to a long-term education post in the Sahel Region which started in early 2025 from the UK and was deployed to Senegal from May.
- Our secondment to the ECW Secretariat has been extended from November 2025 to June 2026, based on the excellent contribution to ECW’s work.
1. We are considering long term solutions for the MENA regional role, which has been placed on pause due to uncertainty around future budgets. We are currently exploring whether the role could be fulfilled by posts across the region, or whether the Centre of Expertise in Education could support with EiEPC surge roles in the future.
2. Output 3.2 The INSPIRE programme has now expanded to reach a total of 15 countries with technical assistance, support for accessing IDA funds, knowledge generation and peer learning. The first cohort of four countries (Burundi, Chad, Ethiopia, and South Sudan) began implementation in June 2024. A second cohort of 11 projects was selected in late 2024 and began implementation in winter 2024. These include Benin, Colombia, Democratic Republic of Congo, Jordan, Lebanon, Mauritania, Republic of Congo, Rwanda, Armenia, Poland, and Zambia.
3. As discussed under outcome 1.4, the World Bank estimates that INSPIRE will directly support 167,260 refugee children and indirectly support a further 805,000. INSPIRE has also directly leveraged almost $100m in funding for refugee inclusion (mainly through the Window for Host and Refugee Communities under IDA) and influenced a further $441m of funding to support refugee inclusion via policy dialogue and technical assistance to partner governments. FCDO is planning to provide further funding to expand the programme, to be formally agreed shortly. The next wave is likely to include top up funding to current countries, as well as expansion into more countries.
4. Output 3.3 Working collaboratively with the Education Research in Conflict and Crisis (ERICC) programme, we have secured funding and initiated the first phase of the EiEPC portfolio evaluation. This evaluation will answer the overarching research question: ‘What is the relevance, effectiveness, efficiency, coherence, impact and sustainability of UK investments in EiEPC? How can FCDO investments be further improved for increased relevance, efficiency, effectiveness, coherence, impact and sustainability?’ We received the initial inception report in July and case studies with Lebanon, Nigeria, Syria, Sudan, Myanmar and Pakistan are now underway. We expect the final report to be available in February 2026. In addition, we have been working closely with research colleagues to ensure research generated under ERICC has relevance to policy and programme work. This has resulted in ERICC producing a guidance note for delivering EiE in emergency contexts for non-education specialists, as well ERICC collaborating on the INSPIRE guidance note.
5. Output 3.4 A partnership was agreed with the Centre for Global Development to conduct a programme review of school feeding in emergencies, drawing on data from ECW and GPE funded projects. Phase I of the study was completed in February 2025. A comprehensive report was produced, outlining preliminary findings following extensive analysis of data from ECW and GPE grantees. The report provided valuable insights but Phase 2 was required to develop findings that could influence school feeding policy and practice. However, the SRO subsequently decided in September not to continue to phase 2 due to concerns on data availability – noting that many of the proposed case study projects had already closed – and partner capacity in the light of global ODA reductions and ongoing restructures. This was a disappointing (but necessary) outcome given the critical evidence gap on how to deliver school feeding in emergency contexts in a cost effective, sustainable way.
6. In addition to these partnerships, FCDO has also commissioned a study by Genesis Analytics looking at the multilateral architecture for education in emergencies (July – October 2025). This study was co-designed by other leading education donors (Denmark, Canada, Norway, Germany) in response to the rapidly changing geopolitical and financing environment. The study is expected to inform future decisions on ECW’s strategic direction, in tandem with its hosting review, as well as wider discussions on the EiEPC architecture.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to this output over the past year.
Future changes
1. An additional indicator on the EiEPC architecture study should be added to track its future use and impact.
2. The School Feeding indicator will not be reported again from next year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Previous recommendations:
1. Engage with CGD on the school feeding in emergencies study to ensure it is of high quality and well-coordinated with the school feeding systematic review. Close involvement with CDG led to an improved phase 1 report. However, decision taken not to progress to phase 2, noting the systematic review has been cancelled.
2. Finalise the £0.4 million of funding to UNHCR via earmarking to ECW. Payment was delayed due to FCDO budget processes but will be issued in October.
3. Work with the World Bank and UNHCR to make the case for more donor funding to the INSPIRE Trust Fund window to expand country footprint. Further funding identified within FCDO to expand footprint. Discussions with other donors outside of FCDO are continuing but have not yet produced results.
4. Ensure EiEPC portfolio evaluation is high quality and contributes to future direction of UK investments. Evaluation underway, additional study has since been commissioned to inform ongoing architecture discussions.
Further recommendations:
1. Continue discussions with the Centre of Expertise for Education and MENA teams to create a transition plan for EiEPC surge roles.
2. Use the monthly INSPIRE meetings to ‘deep dive’ into INSPIRE work within countries, to better understand the impact and variety of INSPIRE work on the ground. Look at refugee hosting countries where ECW and other actors are reducing their programming, to consider whether INSPIRE support would be appropriate.
3. Given the evidence gap on school feeding in emergency contexts, FCDO should engage in discussions with GPE and ECW on future school feeding research. The ideal solution would be building in data needs into new ECW or GPE grants from the start, so that a future study would have a ready-made data set to draw from.
4. Add a dedicated indicator to track the impact and use of the EiEPC architecture study and portfolio evaluation in future reporting.
Output Title	Reduced impact of climate change on education
Output number:		4	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress
4.1 IRC partnership delivering effectively	AGA extension and inception report signed off. / Insurance policy in place and ready for trigger. / IF TRIGGER EVENT OCCURS: Timely roll-out of preparedness plans and delivery of cash transfers.	Met expectations. / In January 2025, we signed off the inception report and progressed into the implementation period of the project. An AGA extension, increasing the overall value to £3m and duration by 18 months, was signed in February 2025. / The first pilot insurance product window ran until June 2025, but no trigger event occurred.
4.2 US Grand Challenges delivering effectively	DCA with USAID signed. / Second CAPE Award issued. / First payment made to CAPE partnership. / CO-CREATE evaluation underway.	Off track. / The Delegated Cooperation Agreement between FCDO and USAID was signed in December 2024. / However, USAID issued a ‘Stop Work’ order to AKF, the implementing partner for CO-CREATE. / As we had no contact with USAID colleagues, we issued a termination notice for the DCA and as of July 2025 the DCA is no longer valid.

1. We judge this output to score B as only one of the two indicators were met. The second indicator was missed due to extraordinary factors outside of FCDO and project control.
2. Output 4.1: The UK is working with the International Rescue Committee (IRC) to develop the Climate Resilient Education Systems Trial (CREST) which is the first pilot of parametric insurance to ensure the continuity of education during a crisis. Following a successful inception phase and signing off the Inception Report, we signed an amendment to the Accountable Grant Agreement (AGA), increasing the value to £3m and extending the duration to July 2024 to 1st January 2027. The CREST project is on track, with key foundations now in place for the rest of the pilot. Household registration and community sensitisation have been completed, and the remote learning pilot showed strong engagement and positive user feedback. While no insurance payouts were triggered this season due to ‘expected range’ weather conditions, the model has demonstrated its value as a preparedness tool and IRC are working with ARC-Replica to agree the details of the next insurance product for future seasons.
3. We are currently in a competitive process to try and secure a fully funded evaluation of CREST by researchers funded under FCDO’s Strategic Impact Evaluation and Learning programme (SIEL), a learning partnership between the FCDO’s Evaluation Unit, J-PAL and IPA. If successful, this would enable an experimental impact evaluation of the CREST pilot, allowing robust data on the intervention’s effectiveness in protecting education outcomes during crisis.
4. Output 4.2 The Climate Action Partnership for Education (CAPE) – formally known as US Grand Challenges – was a partnership between the FCDO and USAID, to develop and test creative solutions that advance our understanding of what works to address climate and environmental change in and through girls’ education. The Delegated Cooperation Agreement (DCA) was signed in December 2024. The intention was to co-fund at least two projects, with USAID providing the initial monies for the first project implemented by AKF. However, due to internal policy changes, USAID issued a ‘Stop Work’ order to the implementers of the CAPE project CO-CREATE in early 2025. We subsequently issued a termination notice for the DCA, and as of July 2025 the DCA is no longer valid. As FCDO had not yet released any monies to USAID under the DCA, there were no financial implications. Our understanding is that AKF subsequently opted to continue the CO-CREATE project themselves, and to further integrate it as part of their Schools2030 model.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
1. We will remove any future milestones from the CAPE project indicator (4.2) from the logframe given it is no longer active.
2. FCDO is planning to extend its innovative work on climate resilient education systems and financing in financial year 25/26- particularly in areas of disaster risk financing, pre-arranged finance and anticipatory action. We will introduce new indicators under this output to cover additional agreements designed to further our work in this area. These are likely to include an MoU with the World Bank to further education system vulnerability assessments; and an extension to the CREST AGA to include a funding line to open a ‘Climate Window’ under the evidence and technical assistance helpdesk of the ERICC programme. This Climate Window will be designed to support posts to think about how to progress innovative disaster risk preparedness, resilience and financing approaches for education.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
1. FCDO has remained closely engaged in the mobilisation of the CREST project, providing additional technical support to help to maximise its chances of success. This included an FCDO education advisor attending an in-person workshop in Nairobi last September. To mitigate any disruption caused by the original advisor’s transition to a new role, a replacement was successfully recruited, ensuring a smooth handover and continuity of technical support to the programme.
2. FCDO has worked closely with IRC and its partners to identify the most suitable evaluation approach for CREST, including a thorough review of the options proposed by OPM in their Evaluation Design Report. In collaboration with IRC and academic partners, FCDO has developed a proposal to enter a competitive process for an evaluation funded by SIEL (the Strategic Impact Evaluation and Learning Programme). We are currently awaiting the outcome of our application.
3. There were issues at the end of the financial year on accurate financing reporting, which led to an overall underspend. FCDO will work closely with IRC to reduce risk of underspend for this financial year and to ensure a clear line of sight on spending is maintained.
4. FCDO continues to have discussions with ECW on defining its methodological approach to capturing International Climate Finance (ICF) results, though this work has been delayed due to other, more pressing, issues for the ECW Secretariat such as its programme and staff restructuring process.
D: VALUE FOR MONEY (VfM)
1. Overall, we judge the programme to be delivering good value for money (VfM). We have been able to extract maximum value from the previous programme by extending it until December 2024 to fund some of the work under components 2 and 3. We have also made further progress on building better complementarity between our different delivery channels – both bilateral and multilateral – through engagement with Posts and partners. The planned EiEPC portfolio evaluation will help the team to further tease out the value add of different programmatic investments (see MEL section).
2. Value for money metrics: The Business Case for EiEPC III included a set of indicative VfM measures. We have updated these indicators, in line with the Results Framework for ECW, with updated numbers listed in Annex E.
3. Component 1: Funding Education Cannot Wait ECW has demonstrated good performance across the majority of VfM metrics, with year-on-year improvements on refugee and disability reach (equity), number of projects with strengthened learning outcomes (effectiveness) and higher completion rates (efficiency). It continues to support high numbers of MYRPs but these will decrease over the coming months (efficiency). However, there are some questions on economy given the average cost of a FER has risen from a planned cost of $34 in the strategic plan, up to $53 last year, and $49 this year. It will be important to engage with ECW to understand the drivers behind these costs as part of the strategic plan discussions; we understand that it is reflective of overall inflation over the strategic plan period, noting that the secretariat has actively worked to drive down unit costs by focusing on a core EiE response package over the last year. Other economy metrics have remained stable, noting the considerable upheaval by the Secretariat to remain below 7% operating costs.
4. Component 2: Boosting access to FCDO capability. The FCDO team conducted a VfM analysis of the case for Programme Insourced Roles (PIRs) in 2023 which clearly demonstrated the VfM of PIRs over short-term consultancies. This year we have funded three posts – two PIRs and one short-term consultancy – as well as providing financing to fill a six-month recruitment gap for the role of the Education Cluster Coordinator position in Sudan. While the Sahel post has now been permanently filled, ODA cuts have led to delays in recruitment for the MENA regional role. This has led to costly extensions through HSOT for the post, which is now due to end in January 2026. However given the growing needs of children in the MENA region, most notably Gaza, we still feel this post delivers strong VfM and an urgent priority will be ensuring sustainability of the post beyond Jan 2026. The same is true for the ECW secondee role which is due to come to an end in the middle of next year. While we do not currently plan to extend this role further, we will need to work with ECW to ensure the knowledge and value add of this role is not lost as part of their restructuring process.
5. Component 3: Thematic partnerships The programme team have managed six partnerships over the past year (CAPE, CREST, INSPIRE, School Feeding, EiEPC Portfolio Evaluation, Genesis study). This has included scrutiny of proposals and interrogation of costs of delivery. One partnership was ended early on VfM grounds (school feeding), namely the concerns on data availability and partner capacity which would have negatively impacted quality and usefulness of the final report. A further partnership was withdrawn from (CAPE), noting no costs to FCDO were incurred. The remaining partnerships will be closely monitored for their VfM, namely:
1. October 2025: finalise the Genesis study and agree use of findings with others
2. November - December 2025: Review second annual report on INSPIRE and agree extension plans
3. Jan 2026: Review draft findings from EiEPC portfolio evaluation, as well as regular bi-weekly meetings in between
4. Quarterly monitoring of CREST activities through Quarterly Update Reports and other updates including payment requests and meetings with IRC.
E: RISK
Overview of risk management
1. FCDO’s overall risk rating for EiEPC is major. Most funds flow through ECW which works in high-risk settings with highly vulnerable children, delivering through multiple implementing partners. This inevitably means that fiduciary, safeguarding, and delivery risks are relatively high compared to other aid contexts. Risks for component 3 are also high given the protracted crises settings for INSPIRE and innovative nature of our climate partnerships. Risks for component 2 are much lower as there is no direct delivery to beneficiaries and is largely within FCDO control.
2. Risks across all three components have been heightened this year due to ongoing decreases in EiEPC (and wider aid) funding, and the subsequent organisational changes within ECW and its implementing partners. The planned reduction in UK aid budgets has added its own challenges for the FCDO team, with continued uncertainty over budgets and programme processes. This means that whilst the risk appetite for the programme is still in line with the FCDO’s risk appetite, active monitoring, managing and escalating of risks by the team has been vital.
3. Component 1: ECW A previous audit and the Due Diligence Assessment found that ECW has a comprehensive framework for managing risk. The ECW secretariat has been working on a new Risk Management Framework to address remaining gaps in risk management at both portfolio and corporate levels, and to clarify roles and responsibilities under the UNICEF Hosting Arrangement. A draft of the Framework was developed in late 2024, shared with stakeholders for feedback, and revised accordingly. However, finalisation was paused in early 2025 due to new feedback from UNICEF, ongoing discussions about ECW’s risk management and updated to UNICEF’s Enterprise Risk Management (ERM) policy, procedures, and tools. Plans to enhance portfolio-level risk reporting through a new online portal in the Grants Management System were delayed due to financial constraints. Whilst we have overall confidence in these risk management systems, we wish to see more discussions on country level risks at ExCom given the impact of decreasing aid budgets on partner operations.
4. Systems aside, ECW has faced numerous major risks this year. The withdrawal of USAID and delays in other donor funding means that ECW has reduced its planned programme expenditure for 2025 from $235.6m to $194.5m, with further reductions planned next year. This lowered the secretariat budget from $16.3m to $13 this year to ensure operational spending remains capped at 7% of total expenditure. To achieve these reductions, ECW has taken the following remedial actions:
- Programme: agreed a new portfolio prioritisation methodology to guide future FERs and MYRP renewals. ExCom agreed not to renew MYRPs in Cameroon, Haiti, Libya, Niger and Pakistan; based on the allocation criteria, MYRPs in Bangladesh, Burundi, Lebanon and Uganda will also end in the coming 12-15 months.
- Staffing: ECW implemented a range of short cost-saving measures, including recruitment freezes and increased travel efficiency. In the medium to long term, it has now agreed a staff restructuring proposal that will reduce the Secretariat from 36 to 25 staff. The ECW Director was placed on special leave from end July 2024 to the end of her contract, with recruitment underway for her replacement.
Whilst these changes are now agreed, it has been an incredibly challenging time for ECW staff and their project implementers. Heightened risks remain around responsible exit from MYRPs, the threat of further staff turnover with ECW and finding a sustainable host once ECW moves on from UNICEF.
1. The revised operational manual – spearheaded by the UK over 2024 and early 2025 – has proved highly useful in helping to manage these risks, with much clearer decision papers and language than previous practice. This was particularly important on decisions regarding ECW staffing, where a working group was set up to review several structure iterations. The newly formed Technical Advisory Group was also invaluable for gaining ExCom agreement to MYRP prioritisation and future closures, a topic that had previously failed to gain ExCom consensus. FCDO continues to engage with others on how best to use the Operational Manual to support the ECW Secretariat and ensure timely, effective and risk-based decision making.
2. Component 2: Boosting access to technical capability: Programme funded advisory posts are a critical part of our risk management strategy, playing a vital role on overseeing and improving delivery in country. All three planned posts are currently filled, either through FCDO staff (Sahel, ECW) or HSOT consultant (MENA). However, the ongoing uncertainties around future budgets and programmes led to failed recruitment for the mid-term MENA post. There is a high risk that we will not be able to fill this post by February, when the HSOT contract ends. We are in discussions with colleagues on whether this post could be recruited by MENA regional teams (preference) or included under the new Centre of Expertise.
3. Component 3: Thematic partnerships: The risk profile has been mixed across the different partnerships. INSPIRE has been largely unaffected by the wider EiEPC funding challenges, with good progress across all recipient countries. CREST has similarly performed well, although the hoped for ‘trigger event’ has not yet occurred with increasing risk that the insurance premiums will not pay out by December 2026; the team is reviewing the project design to help mitigate against this. On a less positive note, CAPE was cancelled following the dissolution of USAID; and the school feeding study was delayed then discontinued due to concerns on data availability and partner capacity.
Current level of fiduciary risk and direction of travel since last ASP	Stable
Specific assessment of corruption risk and direction of travel since last ASP	Stable
Is a full FRA update required?	No

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

1. Programme management within FCDO’s EiEPC portfolio has been effectively delivered by a small but well-coordinated team, comprising 1 FTE G7 adviser, 0.4 FTE G7, 1 FTE HEO, a 0.2 FTE EO and 0.8 FTE EO until June 2025. The climate-focused workstream is supported by a dedicated FTE G7 adviser and 0.25 FTE HEO. Strong collaboration, regular meetings, and clearly defined roles have enabled the team to work efficiently across multiple areas.
2. The Ministerial decision to move to 0.3 ODA has caused programme management challenges for the team, with final budgets for FY25/26 only confirmed in July and no decisions yet on future spend. Several programme decisions have been delayed as a result, for example on extending the end date for the ECW secondee or whether to move to phase two for the school feeding study. The planned JPO recruitment was also cancelled. With budgets now in place, the team is now moving quickly to release any outstanding payments and give certainty to partners and staff on future plans. This includes a large payment to ECW scheduled for October, as well as final payments under our GRF pledge to the World Bank and UNHCR (via ECW). It is now likely that we will not fully exhaust the full business case total of £90 million.
Table 5: EiEPC year to year budget
	23/24 spend	24/25 spend	25/26 forecast	26/27 Forecast	Total
Component 1 - ECW	2,635,535	36,065,000	29,738,174	11,400,000	80,000,000
Component 2 - Boosting access to technical capability		150,000	434,000	180,000	764,000
Component 3 - Thematic partnerships		1,387,674	3,720,000	1,686,000	6,793,672
Total	2,635,535	37,602,674	33,892,174	13,266,000	87,557,674

1. Education Cannot Wait: Payment is made under a Standard Contribution Agreement signed with UNICEF (on ECW’s behalf) in March 2024. ECW funding is overseen by a small Secretariat of 36 staff, currently based in New York and Geneva. The Secretariat is led by the ECW Director and hosted by UNICEF. ECW staff have been through a challenging staff restructuring process leading to the early departure of its Director. It is also undergoing a long-anticipated hosting review (reporting December 2025), with UNICEF announcing that it will no longer host the fund. We continue to have confidence in ECW’s ability to manage its funds, despite this considerable turmoil, with funds administered under UNICEF’s robust programme guidelines. Nonetheless, it is important that strategic decisions are made this Autumn on ECW’s future host, Director and strategic priorities, to provide certainty for staff, implementers and funders.
2. FCDO is a strongly engaged donor, with active involvement in its Executive Committee and High-Level Steering Group, as well as directly on specific issues or workstreams. A key area of leadership was our engagement on its Operational Manual, which underwent a comprehensive revision in 2024 and early 2025. This complex process was led by an Advisory Group chaired by the UK and represented a significant workload for the FCDO lead to build consensus among members, including hosting an in-person workshop in January. The final text was approved in March 2025, with a light-touch review scheduled for March 2026 to assess implementation and identify adjustments. The revised manual has already led to substantial improvements in the clarity of ExCom and HLSG decision making. The only governance issue still not fully resolved is ExCom composition, which was put on hold due to the wider funding crises but will be picked up more fully this Autumn.
3. Humanitarian Support and Operations Team. FCDO has a contract in place for short-term consultancy support in the MENA region (to January 2026) and for a co-ordinator of humanitarian education support in Darfur, Sudan (now ended). This model works well but is relatively costly and time consuming to administer over the longer term compared to PIRs, which remains our long term preference.
4. Inclusion Support Programme for Refugee Education (INSPIRE). Payment is made under the Foundation Learning Compact Administration Arrangement with the World Bank. INSPIRE is overseen by a small team in the World Bank and guided by a strategic committee co-chaired by the World Bank, FCDO, and UNHCR. The EiEPC team has regular progress check-ins with the World Bank, UNHCR, and country-based colleagues, with annual reporting, leading to a much closer relationship and greater influence. A highly successful Wilton Park event in November 2024 bought together refugee host country governments and international partners to discuss refugee inclusion in national education systems. An international workshop was then held in May 2025 in Zambia, to bring together teams from FCDO, UNHCR and the World Bank, to foster collaboration, and develop ‘roadmaps’ for the path to refugee inclusion for individual countries.
5. Centre for Global Development, Europe (CGD) School Feeding research project. An Accountable Grant Agreement was signed with CGD in July 2024. It included two phases, with a phase one report received in late January 2025. Decisions on whether to progress to phase two were then substantially delayed by the SRO whilst waiting for final budget confirmation. It was decided in September not to proceed to phase two, due to concerns on data availability and partner capacity.
6. Climate Resilient Education Systems Trial (CREST). A one-year AGA was signed in July 2024 for £1.4million, with a planned eighteen-month extension for a further £1.6 million signed in February 2025. It is administered by a small team within IRC Kenya. The programme has now successfully completed its inception phase and moved into implementation, with regular check-ins by FCDO.
7. The Climate Action Partnership for Education (CAPE). The Delegated Cooperation Agreement (DCA) was signed in October 2024. However, it was subsequently cancelled by FCDO following termination of the programme by USAID in February. No monies had been released from FCDO to USAID.
G: MONITORING, EVIDENCE AND LEARNING

Over the past reporting year, the FCDO team have monitored EiEPC investments in the following ways:
- Visit to Uganda by the PRO and SRO, and to the INSPIRE workshop in Zambia by the Education Adviser
- Routine outreach to Posts on ECW funding or where they have planned investments on INSPIRE, CAPE or CREST
- Regular monthly meetings with the INSPIRE team, including running ‘deep dive’ sessions into individual countries with UNHCR.
- Through regular monthly engagement with funded advisers through the ECW drop in sessions, as well as regular 1:1s for funded posts in the MENA region and Sahel.
- Through active involvement in ECW’s ExCom, TAG and HLSG, as well as regular check-ins with the FCDO secondee.
- Forming a steering group for the EiEPC portfolio study and holding weekly meetings with the evaluation team to ensure we are content with their methodology/findings.
1. The FCDO team also work closely with colleagues from Research and Evidence Division (RED) who lead on FCDO research on EiEPC, through the ERICC programme, to support alignment to our policy goals. RED has been closely involved in the EiEPC portfolio evaluation and informed the Genesis Analytics study. The education adviser and PRO also took part in the ERICC one day workshop in September, where they discussed how technical assistance could be improved in EiEPC contexts. The ERICC adviser also provided advice on the decision not to continue to phase 2 of school feeding, particularly on risks around data quality and availability.
2. Moving forward, the Genesis multilateral study, and the EiEPC Portfolio review will both be critical learning documents for informing future policy and programme decisions.
Date of last narrative financial report	August 2024	Date of last audited annual statement	31 December 2024

ANNEX A: ACRONYMS

Acronym
AF	Acceleration Facility
AR	Annual Review
CAPE	Climate Action Partnership for Education
CAR	Central African Republic
CGD	Centre for Global Development
CO-CREATE	Collaborative Opportunities for Climate Resilience, Empowerment and Transformation through Education
CREST	Climate Resilient Education Systems Trial
CwD	Children with Disabilities
DDA	Due Diligence Assessment
DRC	Democratic Republic of the Congo
ECW	Education Cannot Wait
EiEPC	Education in Emergencies and Protracted Crisis
ERICC	Education Research in Conflict and Crises
FCDO	Foreign, Commonwealth and Development Office
FER	First Emergency Response
FTE	Full Time Equivalent
GBV	Gender Based Violence
GLO	Gender Lead Organisation
GPE	Global Partnership for Education
HA	Hosting Agreement
HSOT	Humanitarian Support Operations Team
ICF	International Climate Finance
IDA	International Development Assistance
IDP	Internally Displaced Persons
INSPIRE	Inclusion Support Programme for Refugee Education
IRC	International Rescue Committee
LNA	Local and National Actors
MENA	Middle East and North Africa
MHPSS	Mental Health and Psychosocial Support
MYRP	Multi-Year Resilience Programme
PIR	Programme Implementation Role
PSEAH	Protection from Sexual Exploitation, Abuse and Harassment
SEL	Socio-Emotional Learning
UN	United Nations
UNESCO	UN Educational, Scientific and Cultural Organisations
UNHCR	UN High Commissioner for Refugees
UNICEF	UN International Children’s Emergency Fund
UIS	UNESCO Institute for Statistics
USAID	United States Agency for International Development

ANNEX B: THEORY OF CHANGE

ANNEX C: ACTIVE MYRP AND FER GRANTS IN 2024

	FER	MYRP	Grand Total
Afghanistan		$30 000 000	$30 000 000
Armenia	$1 000 000		$1 000 000
Bangladesh		$33 459 800	$33 459 800
Burkina Faso		$26 100 000	$26 100 000
Burundi		$12 000 000	$12 000 000
Cameroon		$25 000 000	$25 000 000
CAR	$2 500 000	$40 000 000	$42 500 000
Chad	$10 000 000	$40 946 870	$50 946 870
Colombia		$24 420 000	$24 420 000
DRC	$6 100 000	$22 200 000	$28 300 000
Ecuador		$15 410 000	$15 410 000
Egypt	$5 500 000		$5 500 000
Ethiopia	$15 340 000	$56 697 715	$72 037 715
Haiti	$2 500 000	$11 800 000	$14 300 000
Iraq		$21 500 000	$21 500 000
Kenya	$2 000 000		$2 000 000
Lebanon	$5 700 000	$12 000 000	$17 700 000
Libya	$3 500 000	$11 100 000	$14 600 000
Mali		$40 793 049	$40 793 049
Moldova	$1 500 000		$1 500 000
Myanmar		$19 000 000	$19 000 000
Niger		$11 100 000	$11 100 000
Nigeria	$2 500 000	$35 100 000	$37 600 000
Pakistan	$7 500 000	$13 200 000	$20 700 000
Peru		$13 410 000	$13 410 000
Sahel Regional		$1 545 321	$1 545 321
Somalia	$12 000 000	$6 900 000	$18 900 000
South America Regional		$1 560 060	$1 560 060
South Sudan	$500 000	$41 000 000	$41 500 000
State of Palestine	$12 000 000	$18 000 000	$30 000 000
Sudan	$12 000 000	$17 700 000	$29 700 000
Syria	$8 500 000	$20 000 000	$28 500 000
Uganda	$4 100 000	$25 500 000	$29 600 000
Ukraine		$20 400 000	$20 400 000
Yemen	$5 000 000		$5 000 000
Grand Total	$119 740 000	$667 842 814	$787 582 814

ANNEX D: VfM METRICS

VfM Measure	Indicators (qualitative and quantitative)	Baseline	2025
Economy	Hosting agreement with UNICEF which clearly sets out hosting costs / ECW operating costs (% of total spend) / Cost per beneficiary / Cost of bringing in surge capacity (consultancy fee rates)	1% fee by UNICEF / Up to 7% management costs by ECW Secretariat / $53/child for FERs and $241/child for MYRPs / Average daily rate for HSOT posts before tax - £507.90	1% fee by UNICEF / Up to 7% management costs by ECW Secretariat / $49/child for FERs (14 months) and $156/child for MYRPs (36 months) / Average daily rate for HSOT posts before tax – £507.90
Efficiency	Reduction in number of MYRPs over the strategic plan period / Amount of additional aligned funding for EiEPC mobilized in a sample of MYRP countries with a dedicated Resource Mobilization support component / % of ECW FERs/MYRPs with completion rates above 75%	28 active MYRPs / $39 million / 53% (100% FERs and 47% MYRPs	28 active MYRPs / $37.3 million / 64% (80% FERs and 60% MYRPs)
Effectiveness	Number of ECW MYRPs with improved Social and emotional Learning and/or wellbeing in targeted learning spaces / Number of MYRPs with 60% of programme showing solid evidence of improvement in learning outcomes / Number of children reached globally (disaggregated) / % of refugees reached annually (disaggregated)	5 MYRPs / 8 MYRPs / 10.6 million girls / 11.4 million boys / Primary: 66% boys and 63% girls (66% overall) / Secondary: 41% boys and 38% girls (42% overall)	7 MYRPs / 9 MYRPs / 7.1 million girls / 7.4 million boys / Primary: 62% boys and 64% girls (67% overall) - FCDO / Secondary: 31% boys and 29% girls (37% overall)
Equity	Number of children and adolescents reached annually with ECW support (FER and MYRP) disaggregated by gender, disability and refugee status / % of MYRP/FER programmes with transition rates to formal school of over 60% (disaggregated)	5.6 million (51% girls and 1.7% with a disability / 22% of total children reached were refugees (50% girls) / Over 85% of ECW programs (100% FERs, 83.3% MYRPs)	8.3m (51% girls and 1.9% with disabilities) / 27% of total children reached were refugees (51% girls) / 91% of ECW programs (100% FERs, 88% MYRPs)