## GHS R&D Programme Annual Review 2025

Title: Global Health Security R&D Programme
Programme Value £ (full life): Up to £107.9 million (original BC value was £175m of which £72m has been reallocated to support the standalone PDP programme (400499), which will be reported under separate AR; £4,890,538 was added to support the transferred JIREP project). / Cumulative spend: £66,551,259		Review date: December 2025
Programme Code: 301542	AMP start date: 10/02/2023	AMP end date: 31/12/2027

Summary of Programme Performance
Year	2023	2024	2025	2026	2027
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	GHS BC summary version updated Feb 2026.docx
DevTracker Link to results framework:	Link to updated 5 year LF

## A: SUMMARY AND OVERVIEW

Description of programme
The Global Health Security (GHS) R&D business case is for R&D investments to prepare for, prevent and respond rapidly to disease outbreaks with epidemic or pandemic potential, benefiting vulnerable populations, and building sustainable and equitable R&D partnerships with LMIC organisations. This is the third annual review for the programme, with the Business Case (2022-2027) approved in February 2023. The programme builds upon the achievements of FCDO’s previous Epidemics and GHS R&D Programme and includes FCDO’s five-year funding commitment of £80 million for CEPI (Coalition for Epidemic Preparedness Innovations).

The GHS R&D programme’s investments address UK global health priorities, to maintain the UK as a leader in global health science and technology, and to enhance global health security and build stronger health systems for early warning and response. In line with FCDO commitments to LMIC priorities, the programme draws on LMIC and UK science strengths, supporting strong and equitable country-led partnerships, and generating mutual benefits. Building LMIC and global resilience is ever more important in the context of geopolitical challenges, biosecurity risks of accidental and deliberate, as well as natural threats, the impact of climate change, LMIC vulnerability and falling ODA. The programme also champions African-led research, in line with Africa CDC’s new agenda for Health Security and Sovereignty. The programme’s inbuilt agility is enabling FCDO to respond rapidly to new outbreaks and public health emergencies, such as Zaire Ebolavirus, Marburg and Rift Valley Fever outbreaks this year, and the ongoing mpox epidemic in Africa, working with other government departments and technical agencies including DHSC and UKHSA.
The GHS R&D programme aims to:
- prioritise and reduce the time taken for the development and use of effective vaccines, drugs, diagnostics and other technologies in line with the 100 Days Mission, working closely with international and regional organisations;
- develop and invest in 5-10 LMIC and international partnerships (including Product Development Partnerships, PDPs) and funding platforms (UKRI-MRC, Wellcome Trust and the Bill and Melinda Gates Foundation) for affordable new technologies for use in LMICs, and mobilising rapid response for outbreaks;
- offer rapid response research through the pillar for emerging infectious diseases in the new Multi Hazard Research Network, (MHRN), due to launch in 2026, as part of the FCDO Science Cell’s Science in Emergencies Centre for Expertise.

For this third annual review, the four outputs cover progress on: CEPI; other partner R&D; inclusive governance, equitable partnerships and capacity building; and UK co-ordination and rapid outbreak response activities. The programme partners are:
- CEPI, an innovative global partnership between public, private, philanthropic, and civil society organisations set up in 2017 and a driver of the 100 Days Mission;
- ISARIC (International Severe Acute Respiratory and emerging Infections Consortium), a network of networks to deliver clinical research and build capability with LMIC organisations, supported by Oxford’s Pandemic Science Institute, which FCDO is co-funding with Wellcome and the Gates Foundation;
- Institut Pasteur de Dakar (IPD), a leading regional African institution for R&D, vaccine and diagnostics innovation and manufacturing, and regional public health functions, including surveillance and early warning.
Summary supporting narrative for the overall score in this review
Overall, the GHS R&D Programme has scored an A for this reporting period.

Programme achievements include:
CEPI’s progressing of four vaccine candidates to phase 2 (including Oxford’s Rift Valley Fever (RVF) candidate with KEMRI, Kenya, and potentially with IPD, Senegal); positive trial results in DRC for the licensed mpox vaccine for paediatric use; the first marketing authorisation in an LMIC, Brazil, and positive adolescent trial data in Brazil, leading to an EU recommendation to include 12–17 year-olds for Valneva’s Chikungunya vaccine;
- FCDO and IPD partnership in March 2025, with year 1 achievements including: international ISO accreditation for IPD’s Biobank (the first in Africa); quality manufacturing and starting a trial for the first-ever measles rapid diagnostic test, and strengthening trial capacity with Oxford and MRC Gambia; completing tech transfer for two vaccine platforms, as well as detecting RVF early and partnering with CEPI and UKHSA on the response;
- ISARIC’s publication of the first randomised controlled trial demonstrating effectiveness of a fully oral treatment for bubonic plague in Madagascar: these findings are set to transform treatment guidance globally, reducing costs and the need for hospital stay - enabling more community and patient-centred care with fewer adverse events;
- New partnerships agreed with the International Vaccine Institute, DNDi and MMV include research for epidemic infectious diseases (which will be reported under the PDP programme);
- Co-ordinating the cross-government forum for international epidemic and outbreak research funding, and ensuring the health and care R&D framework for pandemic PPR, led by DHSC, published in July 2025, includes reference to the UK international funders group and the need for research investments to drive global benefits, including the needs of vulnerable LMIC countries.
- During the year, the UK government developed and implemented the UK’s largest cross-government pandemic simulation, Exercise PEGASUS; FCDO’s R&D team participated in both designing the exercise and in simulating our response, working effectively with partners such as CEPI and ISARIC.
Major lessons and recommendations for the year ahead
Integrating social and behavioural sciences (SBS) into outbreak research: Operational responses to outbreaks now routinely include research to support Risk Communications and Community Engagement (RCCE), and Good Participatory Practices in trials. However, research agendas rarely recognise the need for SBS evidence to inform development of medical countermeasures and public health interventions, and care seeking/illness management in different contexts and for different social groups. Exercise PEGASUS also highlighted this as a lesson learnt for the UK’s domestic and international response.
FCDO, working with WHO and others, to continue to press for integration of social and behavioural research and interdisciplinary approaches, building on progress with partners such as CEPI and Africa-led MpoxReC (ongoing).
Treatment trial funding in emergencies: Despite the development by ISARIC of multicountry platforms for studies, with prepositioned ISARIC protocols for treatment trials in emergencies, the political willingness and lack of prepositioned funding to implement these at pace remains challenging.
FCDO to continue working with partners including GLoPID-R members and WHO, and develop options for funding to enable approval of therapeutics trials (ongoing).
Gender equality, disability and social inclusion: implementation of GEDSI principles and action is not consistent across the portfolio, although there are several examples of good practice (see VfM section).
FCDO to update, discuss and implement its GEDSI policy for global health research with all partners (end 2026)
Progress on previous recommendations
- FCDO to continue to participate in informal investor discussions to generate shared view on CEPI performance for CEPI senior management. Ongoing, including through investor engagement with strategy 3.0 development in 2025.
- CEPI to ensure that behavioural research and social science are integrated into their work, and to take a holistic One Health approach where appropriate. Ongoing process, including inclusion of social science research in Lassa Fever research programme in 2024, and links with animal vaccine platforms for Rift Valley Fever and Nipah Virus, in 2025.
- CEPI to demonstrate the impact of its work on equity and access with concrete examples in LMICs. Ongoing process. CEPI carried out a review of all agreements, and an independent Equitable Access Review of its Chikungunya Partnership Agreements.
- CEPI to continue to contribute to, and define its role, in the end-to-end ecosystem for equitable access with other stakeholders. CEPI and Gavi held discussions this reporting year on handoffs and investigational vaccine reserves and responsibilities, and CEPI published a working paper.
- The 2024 EPD annual review recommended that from 2025, progress on PDPs be reported annually through a single PDP Annual Review. This has been completed with progress from November 2024 – November 2025 in the PDP Annual Review.
Recommendations for 2026
The current trials programmes in CEPI and ISARIC require access to diagnostics for recruitment and product evaluation, but this is not within the mandate of CEPI or ISARIC to develop. This is a potential rate limiting factor in meeting the 100 Days Mission, and FCDO should consider options with its partners (by end 2026).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC) for the GHS R&D programme is based on the case that if affordable new technologies (vaccines, diagnostics and therapeutics) are developed against infectious diseases of epidemic potential alongside the generation and application of evidence on what works to improve the accessibility, equity, delivery and uptake of these products, then this will lead to increased and broad use of high-impact and efficacious products delivered efficiently to those who need them, which will then lead to improved health, demonstrated through reduced infections and mortality, reduction in the scale or number of outbreaks, and financial and social benefits. The primary outcome is that the programme will result in the development of new or improved products that are affordable and available at pace, at scale and where needed, ensuring equitable access. Additional outcomes include increased research and technical capacity at local and regional levels, new evidence-based tools, policies and practices in place, and strengthening the UK’s contribution to, and leadership in, global health.

The ToC is based on both FCDO’s track record and the evidence base for successful product development through a portfolio approach. There is also strong evidence that focusing only on products cannot have the intended impact without good availability and affordability, and improved knowledge about what works, including social science research. The strategy for FCDO’s global health research portfolio is to ‘link science with delivery’ and to support LMIC-led partnerships and networks for collaborative research and capability. FCDO continues to maintain emphasis in all our partnerships and funding on the importance of integrating social and behavioural science into R&D, from studies to understand transmission, developing and deploying medical countermeasures, community engagement, and public health and social measures.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The impact for the programme is: improved health, demonstrated through reduced infections and mortality, reduction in the scale of outbreaks, and financial and social benefits (modelled data). CEPI is commissioning modelling work on its pathogens to make the case for investment. The outcome of the programme is: increased and timely availability of new treatments, diagnostics, vaccines and other tools for global health security and responding to disease outbreaks and AMR, delivered through global technology platforms and international public-private partnerships, that are affordable, and available at pace, at scale, and where needed in LMICs, ensuring access for the most vulnerable populations

The programme is on track to deliver against its three outcome indicators:
Number of products produced by the programme, included in treatment guidelines globally and in relevant LMICs and reaching people in need; investigational candidate supplies; and progress in establishing rapid response technology platforms

CEPI has made substantial progress against this outcome by partnering with Valneva to secure approval for the world’s first Chikungunya vaccine (IXCHIQ) in Brazil, as well as USA, Canada and Europe, secured licensure for adolescent use in the EU, and agreed a supply agreement this year with Serum Institute India. Serum is further providing investigational supplies for Oxford Nipah and Rift Valley Fever candidates. CEPI’s partnership with BioNTech establishes a rapid response platform, including in Rwanda.

ISARIC published the positive results of the trial on oral ciprofloxacin for bubonic plague in Madagascar, as compared with existing intravenous regimens. This success led to ISARIC supporting the drafting of new WHO guidelines, and the implementation of these in DRC, with further trials planned in DRC comparing this oral treatment with doxycycline. FCDO has agreed a no cost extension to enable further work to ensure impact on policy and programmes. CEPI’s mpox research is enabling licensed vaccines to be authorised for additional vulnerable groups, including pregnant women.

Number of evidence products used by practice or policy-related stakeholders locally, nationally, regionally, or globally. ISARIC’s tools are used to enable multi country platform studies for dengue and Nipah.

Increased local, regional, and global capacity to respond to the challenges of diseases of epidemic potential. CEPI, with ISARIC, continues to respond effectively to outbreaks and work with governments and regulators to develop consensus on research requirements for rapid emergency licensure. CEPI has developed a global Vaccine Manufacturing network across five LMIC regions, including IPD. Our partnership with IPD is facilitating early detection and response to outbreaks of dengue and Rift Valley Fever.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
This is the third year of the new GHS R&D Programme. The response to recent outbreaks, and the PEGASUS simulation exercise, demonstrates the value of existing and trusted partnerships, funded for preparedness and rapid mobilisation. The Theory of Change is robust, based on evidence and lessons learned, with strong potential for outcomes and impact for the overarching programme. By working with experienced funders and partners, such as Wellcome, CEPI and ISARIC, who work at scale across a portfolio, in partnership with Africa-led research organisations to ensure local leadership and relevance, the programme should deliver good VfM and support the 100 Day Mission.

## C. DETAILED OUTPUT SCORING

Output Title	Accelerated development by CEPI of new vaccines and platform technologies for diseases of epidemic and pandemic potential, ensuring equitable access for LMICs through an end-to-end approach
Output number:		1	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	No

Briefly describe the output’s activities and provide supporting narrative for the score.
Indicator(s)	Milestone(s) for this review	Progress
1.1: Number of products in the pipeline, disaggregated by stage: / i. research (inc in preclinical) / ii. translation (inc in preclinical) / iii. development (inc number of clinical trials 1,2, 3) / iv. registration, licensure and post-approval / v. vaccine library and rapid response technology platforms/disease X; / (CEPI KPI-OP-1.2.1, KPI-OP-2.1.1 and KPI-OP2.1.2)	Substantive progress towards CEPI’s ambitious 2.0 strategy targets: / Preclinical: 0 / Phase 1: 4 / Phase 2: 4 / Phase 3: 3 / Registration and Licensure: 0 / Vaccine library: Creation of vaccine libraries / for six virus / families; completion of / preclinical work for two / additional virus families / Rapid response/Disease X technology platforms: Phase III initiated	Essentially met / Preclinical: 4 (Lassa, MERS, filovirus & RVF) / Phase 1: 6 (2 MERS, Nipah, RVF, Lassa, MAb for Nipah) / Phase 2: 4 (Lassa, RVF, Nipah and mpox) / Phase 3: 1 (Chikungunya) / Registration and Licensure: 1 (Chikungunya); plus post licensure studies for mpox and Zaire Ebola vaccines / Vaccine library: 20 antigen designs for Lassa and 12 for Junín were tested in preclinical models. Antigen design completed for 9 viruses in the Arenavirus family, 11 in the Paramyxovirus family, 5 Coronaviruses, 1 Phenuivirus / 14 prototype vaccines in development, with 1 in Phase I.
1.2: Number of enabling science programmes and innovative tools to accelerate vaccine development advanced / (CEPI KPI 2.2.1)	Development of assays for MERS, SARS-Cov-1, Nipah and other CEPI priority / pathogens; / Results available on Nipah strain diversity in endemic countries	Exceeded / Development and implementation of 25 assays for seven pathogens, with UKHSA and UK MHRA; implementation of additional 22 assays for further 4 pathogens (Sudan, Ebola Zaire, Marburg, Nipah) is well under way. / Nipah strain characterisation projects in Bangladesh and Malaysia, published on Genbank
1.3: Percent of CEPI-funded products/platforms with relevant access plans in place (CEPI KPI 3.3.1) and narrative evidence for progress on implementation	100% of products passing stage gate review.	Partially Met / An independent review of CEPI’s existing agreements in 2025 found that 75% met equitable access requirements (including those passing stage gate review); the remaining 25% are being addressed. / Equitable Access Review of CEPI’s Chikungunya Partnership Agreements published this year

Indicators for Output 1 have been broadly met, and this output scores an A. Across all priority pathogens, CEPI has exceeded the targets set for preclinical and Phase I activities, and moved one or two candidates to phase 2, with MERS underway by end 2025. CEPI has already exceeded its endline target of one vaccine licensed and progress has been made on enabling science and equitable access provisions, including a review of progress on the latter. CEPI has expanded its filovirus portfolio, a UK priority, with post licensure studies for the two Zaire Ebolavirus vaccines, new pan-filovirus vaccine R&D, and supported trials in two recent Marburg outbreaks.

There are challenges in taking these vaccines to phase 3, given most outbreaks of these diseases are rare and contained rapidly, and the large trials required to show efficacy are not possible. Regulatory consensus is urgent, so that vaccine development innovations will be accepted by regulators across regions for rapid or emergency licensure. CEPI worked with WHO to formalise the status of the Regulatory Advisory Group on Regulatory Preparedness and Response, with senior representatives from 13 LMIC regulatory authorities, as well as Europe and the UK. CEPI, with regulatory bodies, developers and technical agencies continues exploring alternative pathways to licensure, drawing on the FDA’s Animal Rule[1] and phase 2 studies in affected geographies. It successfully supported the approval of the of the world’s first Chikungunya vaccine, IXCHIQ vaccine by the USA FDA in the absence of traditional phase 3 trial data and is considering a similar approach to Marburg.
[1] The ‘Animal Rule’ requires using animal models alongside studies of human immune responses to establish immune correlates of protection that are also valid for humans (ie ‘immunobridging’: identifying immune functions that correlate with and are biologically responsible for vaccine induced efficacy).

Following approval of IXCHIQ, in December 2023, in Brazil, CEPI’s partnership with Valneva is supporting technology transfer to the Instituto Butantan and achieved licensure this year in Brazil, the first approval for use in an endemic country, following approval in Europe. There are positive results for a clinical study in adolescents, leading to licensure for vaccination in EU and Canada. Valneva has entered a licensing agreement with the Serum Institute of India to expand access to IXCHIQ in Asia. A second CEPI-funded Chikungunya vaccine candidate developed by IVI and Bharat Biotech International has successfully completed Phase 2b trials in partnership with Government of India’s Ind-CEPI (managed by the Department of Biotechnology, a vehicle to leverage domestic co-funding, infrastructure, and technical expertise alongside CEPI’s catalytic investments to accelerate vaccine R&D and strengthen global health security).

CEPI is supporting the world’s first Lassa fever phase 2 trial, started in 2024 with IAVI, in Nigeria, Sierra Leone and Ghana. The vaccine candidate’s phase 1 results were published this year, demonstrating safety and robust immune response, in the US and Liberia. Through CEPI’s support, the University of Oxford has launched Phase I trials for another Lassa vaccine. CEPI has also been engaging with stakeholders nationally, regionally and globally to catalyse efforts for late-stage development and rollout through the West Africa Lassa Fever Coalition.

An Oxford RVF candidate also using the ChAdOx technology is now in phase 2 (in partnership with KEMRI, Kenya). CEPI’s support to Senegal’s RVF outbreak in Senegal in late 2025 is including a Phase 2 trial, with IPD. CEPI is supporting Afrigen, a South African biotechnology company, to develop and manufacture the first-ever mRNA-based vaccine against RVF. In line with CEPI’s equitable access policy, the partnership commits Afrigen to the development of investigational stockpiles for any potential vaccine for use in outbreak situations, using affordable pricing mechanisms.

IVI/Bharat

Figure 1: Active CEPI-funded vaccine candidate portfolio by phase - 2025

CEPI’s enabling science programme is expanding the evidence base and understanding of these diseases to inform countermeasure development. Epidemiological and observational studies are proceeding for Lassa and Rift Valley Fever with African partners. CEPI has 25 assays approved for seven pathogens and published Nipah strain sequences from projects in Bangladesh and Malaysia. CEPI has caught up on contracting delays affecting vaccine library progress in 2024, and is on target with immunogen design for six viral families. As part of wider recalibration of its 2.0 targets, to link with 3.0 plans, additional viral families will be added from 2027.

CEPI has committed to including equitable access obligations in its all funding agreements with partners, (as per its Equitable Access Framework), and carried out a review to assess progress and point to improvements where needed. This year, CEPI published its Equitable Access Review of its Chikungunya Partnership Agreements, demonstrating its commitment to EA. CEPI recently published its ‘pathogen archetype framework’ which sets out a common set of access priorities for different types of pathogens and markets.

Emergency responses to outbreaks: CEPI was well prepared for rapid emergency research responses to Rift Valley Fever and Marburg outbreaks. Following success in responding to the Marburg outbreak in Rwanda in 2024, CEPI activated its support to the outbreak in Ethiopia in late 2025 for a clinical trial and facilitated communications between experts in Rwanda with counterparts in Ethiopia. CEPI continued to support the Rwandan recovered patients research, with FCDO. CEPI also continued support to six studies for licensed mpox vaccines, including early results for MVA BN’s trial testing effectiveness and safety in paediatric use.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The nested logframe for this output was finalised. It will need updating with CEPI’s revised 2.0 targets for 2026 and the new 3.0 strategy in 2027.

Lessons learned this year and recommendations for the year ahead

Progress on previous recommendations
CEPI to prioritise MTR recommendations, including efforts to progress candidates through to late-stage trials through, for example, strengthening relationships with multinational pharmaceutical corporations in 2025. CEPI continues to address the findings in designing its 3.0 strategy.
CEPI to clarify its role as part of an end-to-end approach to vaccine development and equitable access and define clear ‘hand offs’ to other stakeholders in 2025. CEPI continues discussions with other stakeholders including Gavi and published a working paper on investigational reserves in 2025.
FCDO and DHSC to contribute to consultation on CEPI 3.0 strategy in 2025. FCDO and DHSC have engaged in consultations bilaterally and with other investors on the proposed 3.0 strategy.

Recommendations for 2026
- CEPI to approve and include revised 2.0 KPI targets in its updated Results Framework, making clear in the annual report where and why targets have been adjusted, and develop 3.0 KPIs (mid 2026).
- CEPI to finalise its 3.0 strategy and replenishment plans in consultation with investors and partners; FCDO to feed in comments on key risks and mitigating actions (early 2026).

Output Title		Progress made on development of accessible new products and innovations, including clinical trials and studies, and generation of new evidence and knowledge to inform policy and programmes
Output number:			2		Output Score:		A+
Impact weighting (%):			20		Weighting revised since last AR?		No
	Indicator(s)			Milestone(s) for this review		Progress
	2.1 No of products, tools and innovations designed, developed and tested for diseases of epidemic potential (disaggregated by development stage)			At least 1 product, tool or innovation making progress in development		Exceeded (progress in 3 significant tools/technology innovations) / ISARIC: Dengue multicountry observational study (CEAP) has recruited 730 patients in 7 countries, demonstrating effective platform operation of shared ISARIC systems; / Developed the WHO Clinical Trials Maturity Framework (under review) / IPD: completed tech transfer for two vaccine platforms (mRNA and viral vector) working with partners such as Oxford
	2.2 No of trials and studies in process or completed			At least 5 studies/trials underway		Exceeded (8 studies underway) / ISARIC have completed the DEN-CORE study, and studies on dengue, Nipah, mpox progressing; / IPD launched evaluation of first measles rapid diagnostic test; / MpoxRec, Africa-led consortium progressing on Mpox multicountry studies (DRC, Nigeria, Cameroon) led by DRC
	2.3 No of publications in peer reviewed journals, with LMIC lead or co-author, female lead or co-author, and open access; no of data sets including % open access (CEPI, ISARIC, IPD, others)			At least 20 publications per year meeting at least one equity indicator criterion / Partners to explore open access for data sets		Exceeded / CEPI: 33 publications: 15 publications with a female lead author (32 with female co-author); 4 publications with an LMIC-based lead author (7 with LMIC co-author); 30 open access. / Since the launch of CEPI 2.0 in 2022, the total is 125 publications. / ISARIC: 11 publications (all open access), all with one or more female co-author and one or more LMIC co-author. / IPD: 84 publications with PubMed ID, 43 (51%) have an IPD first author, including15 women / Partners are exploring how to implement FCDO open access policy to make datasets available. ISARIC’s COVID-19 patient data set is available as open access.
	2.4 Narrative evidence to demonstrate the development of research infrastructure and knowledge tools such as clinical characterisation protocol & e-case report forms, core outcome sets, training materials, guidance notes and briefings, software, evidence mapping tools			Narrative evidence provided		Met / ISARIC’s Clinical Characterisation Protocol and electronic Case Report Form extended to 6 diseases; the Visual Evidence & Research Tool for Exploration (VERTEX) has been extended for use in Ghana, Pakistan, and the Philippines hubs. The BRIDGE 2.0 (BioResearch Integrated Data tool Generator) update allows collation of datasets in 32 sites. / IPD achieved: dual ISO certification for the IPD Senegal Biobank, the first in Africa; ISO certification for diagnostics R&D and manufacturing facilities; strengthened clinical trial management system / SSHAP and WHO produced SBS guidance for mpox, and draft protocol, collated SBS data and held a workshop with African researchers as part of JIREP extension
	2.5 Partner programmes are engaging and/or influencing national or international stakeholders eg technical networks, advisory or working groups, key decision makers.			Narrative evidence provided		Met / CEPI convened the Lassa Fever Coalition with African governments to accelerate late-stage vaccine development and rollout; advocated for equitable access provisions in the draft WHO Pandemic Agreement and worked closely with ministries of health and WHO during outbreak responses, convening African regulators as part of the African Medicines Agency launch / IPD convened a regional conference as part of Centenary events in Dec 2025; is a member of Africa CDC’s diagnostics working group; supported regional outbreak response to mpox / ISARIC researchers presented at the WHO’s filovirus Collaborative Open Research Consortium (CORC) in September 2025, following the EVD outbreak in DRC

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, this output has been exceeded, and scores A+, addressing priority diseases including filoviruses (Marburg and Ebola), Rift Valley Fever, mpox, dengue and Nipah virus.

ISARIC is making progress on working through the Hubs and member networks across LMIC geographies to address evidence gaps for its priority diseases and support uptake and use of its trial and study tools. Following a competitive call, ISARIC is establishing a new data management centre (DMC) led by the Medical Research Council, Gambia. The DMC will co-design data services for global outbreak studies, supporting management of data collected across ISARIC’s international studies and contribute to the ongoing development of tools. The centre is a pivotal step in delivering LMIC-led data management and harmonisation services.

FioCruz, the Hub in Brazil, has spearheaded the development of ISARIC’s digital platform for research acceleration and data interoperability, for clinical epidemiology research. The platform is designed to reduce barriers to research data collection and analysis, improving standardisation within and across research sites. The open software applications for automated generation of case report forms and database files (BRIDGE) and data analysis visualisations (VERTEX) have been launched with Ghana, Pakistan, and the Philippines Hubs. Using BRIDGE, the team in Ghana rapidly generated and delivered a protocol and CRF for mpox, at the request of the Ghana Health Service, illustrating these tools use in real-world outbreak response. Six ARChetype Case Report Forms (CRF) are now deployed, including COVID, dengue, mpox, and yellow fever.

Using these tools, the dengue clinical epidemiology and analysis platform (CEAP) expanded to enrolling 730 patients in 28 sites across 7 countries, allowing multilingual entry to enhance accessibility across LMICs, with automated case report form (CRF) generation, driving standardisation and comparability across multiple sites. ISARIC have also developed and published a core outcome set (COS) for therapeutic efficacy studies of hospitalised dengue as part of the dengue core outcomes exercise (DEN-CORE), with expert participants from over 30 countries. This work will feed into a dengue treatment platform trial for the evaluation of the clinical efficacy of proposed treatments, involving several ISARIC sites including in Colombia, Peru, Vietnam and Singapore. ISARIC is working with CEPI and IPD on a Rift Valley Fever clinical characterisation and seroprevalence protocol. ISARIC’s BASE Study (Bangladesh Acute Meningoencephalitis Syndrome (AMES)) seeks to bridge gaps in Nipah virus (NiV) knowledge, and has enrolled 1,580 patients from three sites to date.

ISARIC undertook and published a scoping review of the infrastructure, capabilities, and capacities required to manage and assure the quality of clinical trials, enabled by funding through ISARIC 3.0. This review was a key contribution to the development of the WHO Maturity Framework for Clinical Trials Units, a self-assessment and benchmarking tool designed to strengthen clinical trial capacity and improve research ecosystems globally. It is currently under revision following stakeholder review.

ISARIC published the positive results of the trial on oral ciprofloxacin for bubonic plague in Madagascar, as compared with existing intravenous regimens. This success led to ISARIC supporting the drafting of new WHO guidelines, and the implementation of these in DRC, with further trials planned in DRC comparing this oral treatment with doxycycline. FCDO has agreed a no cost extension to enable further work to ensure impact on policy and programmes.

IPD is using FCDO funding to build core capacities required for its end-to-end approach to public health and outbreak response, working with Oxford University’s Pandemic Science Institute, LSE, UKHSA, and CEPI.

In response to Senegal’s current outbreak of RVF, and using One Health animal surveillance data and samples, IPD supported rapid molecular characterisation through decentralised genomic sequencing. IPD is using AI and data science advances to better understand emerging viruses such as mosquito-borne Usutu, which is spreading via birds into Europe. The IPD Senegal Biobank became the first in Africa to obtain dual international certification for its quality management and biobanking practice for storing samples.

IPD’s DIATROPIX now has two ISO-certified facilities for the development and large-scale manufacturing of rapid diagnostic tests. The DIATROPIX pipeline includes outbreak (such as filovirus) and NTD diagnostics, and partnerships for RDT innovations, including a proposed Diagnostics Alliance with UK’s GADx company (formerly Mologics). IPD has made significant progress in establishing its Clinical Trials Unit (CTU), benefiting from Oxford-ISARIC collaboration. This year, following successful tech transfer of the first measles RDT to DIATROPIX, IPD recruited the first patients in the first clinical evaluation of this RDT, across 14 government clinic sites. IPD CTU is also agreeing an alliance with MRC Gambia to establish a regional hub for clinical research.

IPD’s Vaccine Research Centre (VRC), has completed technology transfer for multi-platform vaccine R&D (viral vector and mRNA), making Africa’s first measles-rubella vaccine. The unit has achieved this despite significant challenges and delays due to disrupted supply chains, supply quality and procurement bottlenecks. IPD has also completed blueprint plans with Oxford University’s Clinical Biomanufacturing Facility to develop DAVAX (Dakar Clinical Biomanufacturing Facility), and training will start next year. DAVAX will make vaccines to GMP standards for research, for regional stockpiling of outbreak vaccines for trials, and to support internal tech transfer for manufacturing at scale.

IPD is the lead African partner with UKHSA & WHO’s Collaborative Open Research Consortia (CORC) for RVF, and contributing insights for entomological, virological, immunological, clinical/product development and public health. IPD is negotiating the initiation of a phase 2b clinical trial of Oxford’s Rift Valley Fever vaccine with the MOH, CEPI, WHO and MRC Gambia.

Social sciences for outbreak response: Integrating SBS research continues to be a challenge for outbreak and epidemic research, and a major influencing objective for FCDO. SSHAP completed its 5-year programme with Wellcome and FCDO including the costed JIREP extension for its emergency response capability through to May 2025, which focused on guidance development and peer capability building. This received additional funding from Elrha to December 2025. Since 2024, SSHAP researchers have assisted the WHO in developing WHO’s guidance for research on mpox (March 2025) and a standard SBS in emergencies research protocol (to be published in 2026, and already adapted for Zaire Ebolavirus in DRC). SSHAP staff did a rapid synthesis of SBS evidence for Clade 1 mpox, to support WHO’s Emergency Committee deliberations in June. SSHAP published several briefs in English, French, and Portuguese and a question bank on climate and health research questions. Key considerations: Home based care for mpox in Central and East Africa, and Key considerations: Using social and behavioural science to inform the use of vaccines during health emergencies. SSHAP are working with the African-led MpoxReC GECIVO mpox project to support design and implementation of social science research in epidemiological, immunological and genomic components (output 4).

Describe any changes to this output during the past year, and any planned changes as a result of this review. N/A

Lessons learned this year and recommendations for the year ahead
ISARIC continues to consider how it can help to ensure that patented candidate treatments, should they achieve licensure, are available and affordable in LMICs, while taking into account that it does not have scope to negotiate access agreements. CEPI’s work on the Nipah monoclonal antibody, in which ISARIC is partnering, includes access considerations.

Progress on recommendations 2025
- ISARIC, with FCDO’s input, to consider a plan for its role in ensuring access to products by November 2025. ISARIC has developed a proposal for review by FCDO.
- FCDO and ISARIC to agree the programme logframe by May 2025. Logframe agreed in July 2025
- CEPI should scale up efforts to support female and LMIC-based researchers and work to ensure all supported publications are open access, Targets to be set in updated nested logframe, and reported on by November 2025. CEPI has somewhat increased the proportion of publications with a female and LMIC-based lead author, with 90% open access
- All partners to aim for and report on open access datasets, by November 2025. Limited progress, and needs continued effort.
Recommendations for 2026
CEPI to improve equity and representation from LMIC-based institutions and experts, and all partners to align with FCDO open access policy, including on data sets, by December 2026

Output Title		Improved arrangements for inclusive governance and equitable partnerships, and capacity strengthened with LMIC partners and networks
Output number:			3		Output Score:		A
Impact weighting (%):			10		Weighting revised since last AR?		No
	Indicator(s)			Milestone(s) for this review		Progress
	3.1 LMIC governance and leadership strengthened			Partner governance reforms demonstrating strengthened LMIC governance		Met / ISARIC Executive Board, led by an LMIC chair has met monthly, with 49% of membership now from LMICs; / CEPI recruited additional LMIC senior management and Board members
	3.2 No of equitable LMIC partnerships, leading on research agenda setting and management			Four ISARIC hubs operational and able to independently manage projects and data/quality management / CEPI providing narrative evidence for equitable LMIC partnerships / IPD partnership and logframe agreed		Met / ISARIC currently comprises 78 voting member networks spanning 140 countries, with 49% based in LMICs; Philippines and Pakistan hubs now active, along with Ghana and Brazil (4 total); / Hubs have prioritised research themes though Improving Patient Outcome Plans (IPOPs), coordinating these with regional partners / Out of 149 CEPI partners, 39 of these are with LMIC-based companies and research organisations. / IPD partnership signed in March 2025, and launched in September by FCDO Minister; logframe agreed
	3.3 No of partners and research sites adopting and using systems and tools for quality and timely research			At least 10 sites independently operational on ISARIC systems with clinical characterisation and data management activities devolved and led by LMIC-based institution		Exceeded / Documented use of ISARIC tools across 30 institutions in LMICs, mainly dengue and Nipah research sites. / MpoxRec is partnering with ISARIC and will include mpox clinical characterisation protocol and eCRF in all studies
	3.4 No of LMIC researchers attaining specialised competencies in outbreak response research for emerging infectious diseases			40 LMIC-based researchers per year receiving specialised training in clinical research during outbreaks		Exceeded / 72 LMIC-based researchers from 6 countries completed Clinical Research During Outbreaks (CREDO) training.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output has been met, and scores A.

The ISARIC Executive Board continued to strengthen LMIC governance and provide strategic oversight through representation including the Brazil, Ghana, Pakistan, and Philippines hubs. Meeting monthly, it approved new membership applications expanding the network to 78 members, 49% of which are based in LMICs. ISARIC’s reach now spans 140 countries, with 3,000 clinical research sites. The Improving Patient Outcome Plans (IPOPs) serve as the mechanism for LMIC ISARIC partners to lead on disease prioritisation. Prioritised diseases are acute respiratory infections (ARI), infectious acute encephalitis syndrome (iAES) linked to Nipah Virus, arboviral diseases, mpox, and diseases caused by filoviruses, led by each of the four Hubs.

FCDO’s partnership with Institut Pasteur de Dakar (IPD) has completed the first of four years. IPD has strengthened its Board, with a new Senegalese Chair who has deep, global experience in health and development. In addition to R&D workstreams, FCDO’s Africa Dept is funding improved public health functions and surveillance in Senegal and neighbouring countries. IPD has a strong relationship with Africa CDC, WHO AFRO and public health authorities in 12 West African countries. The partnership is also enabling strong global partnerships, especially in the UK with the Universities of Oxford and Cambridge, LSE, LSHTM, UKHSA, UKMHRA and GADx (diagnostics).

Figure 2: CEPI’s partnerships, including in the global south

CEPI has a unique role in building partnerships with the global south. CEPI has 149 partners with biotech companies globally. Of these, 39, or 26%, are with companies based in LMICs, reflecting the continuing bias in the global innovation landscape. CEPI has agreements with five partners in its Vaccine Manufacturing Facility Network (Bio Farma, Indonesia, Bio-Manguinhos/Fiocruz, Brazil, Serum Institute India, Aspen, South Africa and Institut Pasteur de Dakar (IPD), Senegal) and hosts the Regionalised Vaccine Manufacturing Collaborative. In addition to readiness for emergency manufacturing, these partners also have capacity for routine vaccines, investigational reserves, bioprocessing for reducing costs and testing mRNA and viral vector platforms. Seven of the 20 laboratories in CEPI’s Centralised Laboratory Network are based in LMICs (including Bangladesh, DRC, India, Kenya, Senegal, and Uganda). CEPI now has 81 active clinical trial sites with partners in 21 countries, with 69% in 18 LMICs.

Describe any changes to this output during the past year, and any planned changes as a result of this review. N/A

Lessons learned this year and recommendations for the year ahead

Progress on recommendations 2025
CEPI to strengthen its partnership selection process and equitable relationship management with a particular focus on partners in the Global South and capacity building across the end-to-end spectrum. CEPI is addressing this as part of 3.0 strategy development in 2025.

Recommendations for 2026
While ISARIC has an LMIC dominated Board, and prominent LMIC partners, there is a continuing need to advance the research leadership transition and enable LMIC-led research.

Output Title		Global, regional and UK epidemic research is co-ordinated and collaborative action facilitated, both during and between outbreaks, contributing to strengthened prevention, preparedness and response led by LMICs
Output number:				4	Output Score:		A+
Impact weighting (%):				20	Weighting revised since last AR?		No
	Indicator(s)		Milestone(s) for this review			Progress
	4.1 Effective international co-ordination for epidemic R&D tools and investment among major partners and stakeholders in line with 100DM, including FCDO contribution to xHMG GHS R&D investment approach		At least three narrative examples illustrating co-ordination between CEPI, ISARIC, IPD, and other partners; and effective UK co-ordination			Significantly exceeded – eight examples: / 1 CEPI convened events at CoP30, the World Health Summit, and Bio2025 to promote biosafety and biosecurity, and published its Biosecurity Strategy / 2 IPD and UKHSA agreed an MOU to work together on pathogen assays and standards, and diagnostic and vaccine development / 3 UKHSA leads WHO CORCs for two viral families, including RVF co-led with IPD / 4 CEPI, IPD and ISARIC working together on phase 2 vaccine trial for RVF in Senegal, with MRC Gambia / 5 ISARIC and partners convened the Dengue Therapeutics Consortium in Viet Nam, Jan 2025 / 6 FCDO Health Research Team convenes xHMG international funders group and meets with partners (WHO, GLoPID-R) ; published xHMG PPR R&D Framework includes international components / 7 Effective leadership and convening across government for R&D response to PEGASUS, the national pandemic simulation exercise in 2025, engaging CEPI and ISARIC as players / 8 FCDO co-chair for PDP Funders Group
	4.2 FCDO and UK government rapid response R&D mobilisation and delivery		Multi Hazard Research Network operational; effective outbreak response demonstrated			Mostly met / Multi Hazard Research Network call in mid 2025, led by Science Cell, selection due early 2026, launch planned for q1 2026; MHRN includes a pillar for emerging infectious diseases, and is part of the new Science for Emergencies Centre of Expertise / Two outbreak R&D responses effectively mobilised, co-ordinated and funded (Ebola, DRC; RVF, Senegal); mpox response portfolio progresses
	4.3 Progress made on partnerships and platforms to implement GHS programme approach for LMIC-led research on epidemic and outbreak diseases		Two new LMIC-led institutional partnerships and PDPs underway; progress on funder partnerships and joint platforms			Exceeded – four / 1 New accountable grant with Institut Pasteur de Dakar, Senegal, March 2025, and high level launch in Sept 2025 / 2 ISARIC Board led by FioCruz Chair, supported through Oxford’s Pandemic Science Institute with Wellcome and BMGF; / 3 New PDPs include three with emerging infectious disease components / 4 MRC Concordat includes scope for emergency response and two projects funded; Wellcome partnership drafted and agreed in principle but agreement on financial and legal clauses needed

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output has been exceeded, and scores A+.

Partner co-ordination for 100 Day Mission: CEPI has formal partnerships with Africa CDC, Nigeria CDC, and PAHO to strengthen vaccine manufacturing and access strategies in low- and middle-income countries. CEPI and ISARIC agreed an MOU to work together in emergency response, and on clinical trial partnerships. CEPI and IPD progressed their partnership through CEPI support to IPD biomanufacturing innovations, for Africa’s vaccine independence. CEPI is also partnering with the FCDO-funded Centre for Vaccine Manufacturing and Innovation at Pirbright on join-up with animal vaccine platforms. ISARIC and its partners convened the Dengue Therapeutics Consortium in 2025, with participants from 19 countries to review the target product profile, pipeline and trial design needs.

CEPI is responsibly integrating AI and digital innovations into its end-to-end approach, from One Health early warning, predicting viral spillover and evolution, to new vaccine design. CEPI developed and promoted the Community Statement: principles to guide the responsible development of AI for protein design, signed and supported by over 250 global experts from more than 30 countries.

CEPI has also increased efforts to include health security as a pillar of national security, given growing disease threats to national and global resilience. CEPI’s Biosecurity Strategy sets out its biosecurity aims to protect society from epidemic and pandemic threats, with an emphasis on preventing accidental and deliberate misuse of pathogens associated with CEPI-sponsored research. CEPI and the World Economic Forum collaborated on industry engagement and responsible stewardship, including a high-level meeting at the BIO2025 Conference. CEPI convened senior leaders including from the Global South at the 2025 Munich Security Conference, for a bold declaration and an Op-Ed, issued by the Global South leaders.

Environmental shifts are aggravating over 60% of known human infectious diseases, including vector borne diseases such as RVF, chikungunya, dengue and Zika, which disproportionally affect low resource settings. The intersection of environment and climate change, health and security is gathering growing political attention in global fora. In 2024 CEPI undertook an Environmental Impact and Climate Risk (EICR) Project, to inform CEPI 3.0 strategy and operations. CEPI co-hosted several events in Brazil during COP30 to help mainstream the need for vaccines against climate sensitive viral pathogens as fundamental to the climate adaptation agenda. CEPI, DNDi, MMV and Unitaid shared a joint statement in support of the Belém Health Action Plan (BHAP).

Cross HMG co-ordination: The xHMG Strategic & Response Funders Forums for pandemic preparedness and response research, chaired by DHSC and FCDO CSAs, is meeting regularly (led by DHSC), together with monthly FCDO-led UK international funder meetings. Wellcome is joining both the senior and working level meetings, and we continue to link up with GloPID-R (where UKRI-MRC represents the UK).  R&D issues are also included in regular FCDO-led Epithreat and Africa outbreak response meetings. FCDO ensured international/LMIC interests were reflected in the UK Government’s PPR R&D Framework, published in July 2025, and led the international UK response during Exercise PEGASUS.

The planned Centre for Research is now integrated as a workstream within the Science for Emergencies Centre of Expertise (SECE) and Multi Hazard Research Network, to improve efficiency, co-ordination and agility for emergency response and to reduce transaction costs, following agreement within RED and with DHSC, UKHSA and UK funders. Following selection in early 2026, the Network should be operational by mid-2026.
FCDO and its partners are demonstrating its capability to mount a rapid and well-coordinated research response to disease outbreaks, including filoviruses (Marburg Virus in Ethiopia, Zaire Ebolavirus, DRC), RVF, Senegal, and mpox.
Mpox response Mpox continues to spread in Africa, and is re-emerging in Europe. Africa CDC continues to classify the epidemic as a Public Health Emergency of Continental Security. FCDO, in liaison with other UK funders (DHSC NIHR, UKRI-MRC and Wellcome) are funding a co-ordinated portfolio of complementary research, studies and guidance, in line with the mpox research response roadmap (WHO/Africa CDC/CEPI/NAIAD). Our partners CEPI and ISARIC are also funding vaccine and treatment trials with partners in affected countries, including DRC, Central African Republic and Uganda. Bavarian Nordic, one of CEPI’s partners, recently announced early results from a trial in DRC and Uganda, showing safe and effective use of its vaccine in children, a major step.

Wellcome and FCDO are funding the Africa-led Mpox Research Consortium (MpoxReC) to lead a new three-year observational cohort study to be conducted in the DRC, Cameroon, and Nigeria (Mpox-GECIVO Africa, Mpox Genomics, Epidemiology, Clinical, Immunological, and Virological Outcomes). The project will generate vital multi-country data on mpox’s epidemiology, clinical progression, and outcomes, and will inform evidence-based strategies to control outbreaks and improve responses tailored to different populations, regions, and viral clades. It is led by the INRB, DRC, with Bayelsa Medical University Nigeria, Centre Pasteur du Cameroun, Cameroon and Center for Epidemic Response and Innovation (CERI), Stellenbosch, South Africa.

Led by Wellcome, the project has had delays in establishment, including agreeing due diligence with each institution and funding arrangements. However, data collection is set to begin in early 2026, with ethical approval, site selection and training well under way. The SBS component has been strengthened with additional funding for IDS to support the senior leadership based in South Africa. The CERI team has delivered early phylogenetic and phylogeographic analysis of the virus to show the global and regional spread. With the MRC, FCDO also invested in Imperial College’s MRC Collaborating Centre GIDA to support mpox modelling efforts in DRC, Angola and Burundi, and the UK’s Rapid Response Consortium for clade 1 immunology, virology and other basic science, with UVRI, Uganda.

Partnership with Institut Pasteur de Dakar (IPD): Following signing IPD’s accountable grant for up to £13.5 million over four years, IPD managed a well-publicised launch with the Minister of Health, Senegal and Minister for Africa, UK, in Dakar in September 2025. This generated high media interest and coverage, including in the British press (To stop disease X, we must invest in African health, Telegraph, and Inside the lab hunting for disease X – and the next pandemic, Independent.) FCDO support to IPD is enabling new UK strategic partnerships, with the University of Oxford (Pandemic Sciences Institute for the clinical research manufacturing facility, vaccine tech transfer and trials), and the UK Health Security Agency (UKHSA) for clinical samples and biobank exchanges, vaccine assays and lab diagnostics, and biosafety. IPD will also advance its longstanding collaboration with GADx (Global Access Diagnostics) on new rapid tests, for Marburg for example.

Wellcome-FCDO- BMGF partnership support to ISARIC: FCDO, together with Wellcome and the Gates Foundation, awarded ISARIC £16.5 million in 2024 over 5 years to increase clinical research capabilities to tackle infectious diseases. The ambitious new work programme is to improve global preparedness and response for emerging infectious disease threats such as mpox, filoviruses, dengue, acute respiratory infections, plague and Nipah. FCDO met ISARIC’s new Board, comprising hub leads in Pakistan, Brazil, Ghana and the Philippines, and the Global Support Centre based in Oxford’s Pandemic Science Institute, at Oxford’s conference in June.

New and refreshed strategic partnerships: FCDO has a long and successful track record of joint research with Wellcome through the JIREP programme, using two modalities: a) co-funded programmes where Wellcome also acts as the research fund manager and b) funding in parallel to the same partner and programme, with shared reporting and M&E. FCDO and Wellcome are finalising the new FCDO-Wellcome Collaborative Strategic Partnership, to be agreed by the UK’s Minister for Development and Wellcome’s new leadership in early 2026. This process has shown substantial equivalence between FCDO and Wellcome systems, norms and procedures and confirmed that Wellcome has strong and tested governance and financial management controls.

One Health programming The FCDO Health Research Team together with the FCDO Food and Agriculture Team is working closely with UKRI to contribute both technically and financially to UKRI Tackling Epidemics phase 2, which issued a call in early 2025, for project selection in December 2025, and funding in 26/27.

New accountable grant agreements for the product development partnership include three PDPs with elements addressing emerging infectious diseases (including the International Vaccine Initiative, MMV, and DNDi). Funding is allocated to these partners from this business case, and their performance is covered in the PDP annual review.

Describe any changes to this output during the past year, and any planned changes as a result of this review. Output indicator 4.3 will need revising given there are no new partnerships planned.

Lessons learned this year and recommendations for the year ahead
Continued pressures on the team to initiate and develop new partnerships on top of outbreak response and managing existing programmes. Developing new ‘modern’ partnerships take time and may also demand higher risk appetite, and we should not assume fast progress. Cross government co-ordination on outbreak research has enhanced our response. A new health adviser joined the team in mid-2025 which increases our surge capacity for outbreaks.

Progress on Recommendations 2025
FCDO to complete procurement and new partnership agreements in 2025, ensuring capability for rapid response to outbreaks. Significant progress made with IPD, ISARIC and UKRI agreements and on the MHRN. While the Wellcome partnership agreement is not finalised, we are continuing to work closely with them on infectious disease research, including mpox and cholera, and climate and health.

Recommendations for 2026
- FCDO to continue convening R&D funders across government, and increase engagement with other international funders through the GLoPID-R forum, in line with Exercise PEGASUS lessons learnt.
- FCDO will also need to review programme funding and management resources, to maintain capability for rapid research response and sufficient investment for effective strategic partnerships.

D: VALUE FOR MONEY

Key cost drivers and performance
Key cost drivers for R&D include scientific expertise, laboratory set-up and running, systems and materials procurement, the cost of pre-clinical and clinical trials preparation of dossiers for regulatory approval, other advocacy and dissemination activities, and staff costs. Operational costs may be higher in emergencies.

IPD, which joined the programme partnerships this year, is competitive, on for example its human resource costs, both for top talent and early career staff. Cost drivers that limit VfM, however, include heavy reliance on importation of critical reagents and materials to Senegal. Collaborations with UK-based groups, for instance for diagnostics and reagents, aim to streamline these activities.

VfM performance compared to the original VfM proposition in the business case
By investing in pooled funding for existing platforms and partnerships to develop tools and enable rapid response, FCDO is advancing research to save lives and livelihoods and improve health outcomes for people affected by disease outbreaks in LMICs. The programme continues to work with many stakeholders to accelerate and deliver new/repurposed products.

IPD, for example, is well-positioned for efficient and early detection of outbreaks, demonstrating VfM through support to routine surveillance programmes in the public sector whilst also ensuring readiness and cost-effectiveness for an equitable response. IPD was able to respond early and promptly to the RVF outbreak in Senegal this year pending later reimbursements from the Government of Senegal or CEPI for trials. IPD commits to supply at cost of goods with a limited margin during an epidemic for resource limited settings. The partnership therefore has the potential for impact on early detection, supporting an equitable response in the region.

CEPI’s investments in regional manufacturing drive VfM through scale and biomanufacturing improvements. This includes CEPI’s partnership with Serum Institute India to manufacture Oxford’s Nipah candidate vaccine doses for use in a world-first Phase II clinical trial and create an investigational reserve of up to 100,000 doses, helping to generate critical data and potentially halt an epidemic in its tracks.

Evidence also continues to demonstrate the likely effectiveness and cost-effectiveness and epidemic and pandemic vaccines. A new study from Imperial College’s GIDA Centre (MRC and FCDO partner) on the economic benefits of COVID-19 vaccines finds that, while they cost $79 billion to develop and deliver globally, vaccination provided health and economic benefits worth between $5 trillion and $38 trillion globally in the first year alone, based on avoided infections, hospitalisations and deaths, averting 14 million deaths. That is a very significant return on investment of between $60 and $475 per dollar invested.

Climate change and other environmental and demographic factors are threatening to put as many as 700 million people at risk of developing Lassa fever in the future, underscoring the urgent need for effective vaccines. Recent modelling for CEPI found that deploying a safe and effective Lassa vaccine across 15 countries in West Africa could save nearly 3,300 lives over 10 years and avert up to $128 million in societal costs, published in a Nature study .

Overall, the programme’s partnership and portfolio approach to R&D investment continued to drive VfM. In 2024, Research Policy Cures (now Global Health Impact) published a thorough evaluation of the neglected disease R&D landscape, including some outbreak diseases (not COVID-19) and the value of investing in this type of research. They found that investment over the last 20 years using the PDP model will have saved 40.7 million lives, or 2.83 billion disability-adjusted life years (DALYs), by 2040, which translates to an economic benefit of $49.9 trillion, or a return on investment of $405 for every $1 invested. Whilst the return on investment for this specific programme may be different, a similar return on investment is likely for this programme’s technology development components, given it uses a similar model.

CEPI is the major programme partner, with a long-standing partnership with the UK government. In 2024/25, spending and progress on key projects has increased in line with the projected budget, accompanied by better forecasting and tighter internal oversight.
CEPI continues to strengthen its Equitable Access Framework, but delivering end to end objectives is challenging, especially with respect to market shaping, procurement, deployment and use, where CEPI has a more limited mandate and resources increasingly constrained, for Gavi, for example.

On equity, the team is working with our R&D partnerships to strengthen policy for gender equality, disability and social inclusion, including organisational governance and staffing, inclusion of women of reproductive age and children in trials, and recognising biological, socio-cultural and economic vulnerabilities to infectious diseases. For example, CEPI is developing a Gender Equality Policy, and has a balanced workforce, including at senior leadership and board level. With respect to expanding access, CEPI’s vaccine trials for mpox and chikungunya are focused on pregnant women and children, and preclinical research also includes, for example, reproductive toxicity testing to enable early inclusion in clinical trials, in line with new WHO recommendations. IPD has 97% of staff from the ECOWAS region, including near 50% of women (up from a baseline of 37% in 2021, and with several key new units well above 50%), and has a mentorship programme focused on female scientists.

Assessment of whether the programme continues to represent value for money
This is the third annual review of this programme. The portfolio, including FCDO’s long-standing investment in CEPI, new ISARIC and IPD partnerships, together with our refreshed MRC and Wellcome partnerships, is building preparedness, and delivering outbreak responses, whilst maintaining good VfM.

Examples of VfM

Economy	Pooling funds: By investing through platforms with UKRI-MRC, Wellcome and BMGF, including partnerships such as CEPI and ISARIC, FCDO helps to secure maximum benefit at the lowest cost, for example, through sharing/saving on administration costs and accessing the best expertise at a fair price.
Efficiency	Cross-collaboration and co-ordination: The programmes use resources well – for example FCDO is working closely across government and with Wellcome, as well as internationally, drawing together epidemiological, immunology, policy, and innovation expertise.
Effectiveness	Relevance: Research partnerships are in areas of high priority to the FCDO, given UK government emphasis on epidemic and pandemic preparedness including in LMICs. / Leveraging strong UK and LMIC partnerships: Partnerships, such as ISARIC and IPD, and projects combine LMIC and UK expertise and leadership, building LMIC capacity while also driving benefit for LMICs and sharing UK expertise across geographies and populations. / Saving lives: By providing research funding for expanding LMIC trials through CEPI and ISARIC, FCDO helps to mitigate the loss of lives and health impacts in LMICs of outbreak diseases. / Portfolio approach across different funding mechanisms: Diversifies and reduces risk, careful technical and financial oversight by the partnerships and pooled funds or platforms, accelerating the timeline from discovery to testing, licensure and delivery of affordable, safe, effective and quality products, as demonstrated by CEPI’s success in progressing vaccine candidates. / Learning lessons and trusted partnerships: Faced with an emergency response needs, the quality of FCDO funded research is best assured by working through trusted partners such as UKRI MRC and Wellcome Trust, MMV and DNDi, organisations with access to global expertise.
Equity	Equitable access and inclusion: addressing neglected threats such as mpox, cholera and dengue; processes and mechanisms to ensure that the outputs and outcomes uphold ethical principles and drive equitable access - end to end approaches to ensure any products developed are accessible and affordable in LMICs and, where possible, manufactured closer to outbreak locations. LMIC partnerships for equality, diversity and inclusion: the programmes support researchers, including women, in LMICs through training and equitable publication policies, and build equitable research partnerships with LMIC research organisations. Promoting gender quality and social inclusion both internally and in R&D activities.

E: RISK

Overview of risk management
The overall risk level is judged to remain ‘Moderate’, within the Research and Evidence Department’s high appetite for intellectual and innovation risk. Each partner has their own risk register, and the risk register for the GHS R&D programme is in development, including new partnerships. This will be actively monitored by the FCDO programme team along with the programme partners. Overall the portfolio could face resourcing and therefore programming and delivery risks given ODA reductions by many funders, but we are working with partners to maintain our core relationships while also managing expectations. The funding and landscape for diagnostics R&D has narrowed in 2025, potentially risking delivery of the 100 Day Mission. FCDO is working with others to explore how IPD and its partners, and pivoting PDPs to identified gaps, may help mitigate this.

Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Major	Major	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

CEPI underwent due diligence prior to the signing of an MoU with FCDO, which provided a high-level of reassurance around CEPI’s governance arrangements. In the last two years, CEPI has increased spend in line with more realistic budgets, reflecting better management and forecasting, and improved its risk assessment and management. This reporting period, CEPI continues reporting on its risk register, using its Risk Management Policy, including clarity on roles, responsibilities and accountabilities at all levels of the organisation, by the Executive and Investment Committee, with ongoing quality reporting to the Audit and Risk Committee.

CEPI’s performance and investment decisions are closely managed and monitored by its Board and Scientific Advisory Committee, together with the Investors Council (which includes FCDO and DHSC). CEPI now has stronger internal structures and systems necessary to manage its growing workforce and large and complex portfolio, including more robust financial forecasts and project management, and a proportionate risk management approach with partners. In line with the mid-term review recommendations, CEPI has revised its endline targets for 2027 to be more realistic, thus reducing programmatic risk. CEPI’s draft 3.0 strategy sets out clear and realistic objectives in the expectation of reduced resources given ODA reductions, and includes managing risks associated with new AI threats.

ISARIC continues to elevate the authority of Global South membership and is delegating leadership of key workstreams to the Hubs, with increasingly prominent roles for four existing ISARIC regional hubs (Brazil, Ghana, Pakistan, the Philippines) with up to four additional hubs proposed in 2024-2029 strategy (likely to include India or Bangladesh). The Global Support Centre (GSC) is planning to transfer functions to hubs including budgetary authority, data management and quality assurance. ISARIC outcomes are contingent on hub capacity and development, so FCDO is tracking governance and management shifts over the programme.

Overall, investments in networks such as ISARIC effectively spread risk across institutions, projects, geographical regions and disease research domains. ISARIC’s risk rating is Moderate: it can deliver on programme objectives alongside responding to “average” sized outbreaks but in the event of a large or complex outbreak reallocation of some resources towards response would be required. The changing ODA environment has increased risks in the implementation of treatment trials, as funding has not been reliably prepositioned for these. This creates the risk that although platforms have been developed, the studies may not be funded. Clarity on the role of WHO’s Collaborative Open Research Consortia, coupled with funder co-ordination through GLoPID-R will help mitigate this risk.

### IPD: IPD’s growth post-pandemic continues as planned. IPD is addressing the recommendations for governance, delivery and safeguarding as agreed with FCDO in its due diligence assessment. Its Special Projects Delivery Unit, funded from 2022-2024 by Gates has closed, and the new CEO’s Executive Office is leading on the comprehensive institutional development plan. This includes enhancing communications with staff, new senior partnership, financing and operating managers, and new policies for safeguarding (PSEAH), procurement and contracting. However, digital transformation is taking longer than planned. IPD continues to work with the FCDO Manufacturing Africa initiative to strengthen business plans for its vaccines and diagnostics manufacturing business units and extending this work for both revenue and cost centres.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, on commercial and financial issues.
Following the announcement in 2025 to spend 0.3% of GNI by 2027 on ODA, the department is considering programme priorities and allocations. The UK remains fully committed to playing a globally significant role in humanitarian aid and development, including epidemic and pandemic research. It is implementing its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.

The original GHS business case was approved with a budget of £175m. When the JIREP project extensions were folded into the GHS portfolio, following the Epidemics programme’s closure in 2024, the total budget increased to £179,890,538. During this reporting period, £72m of the GHS budget has been moved to support a standalone PDP programme as recommended in the 2024 EPD Annual Review. The revised GHS budget now stands at £107,890,538.

The total programme spend to date of £66.55 million includes four payments to CEPI (£12 million in 2022/23, £16 million in 23/24 and £25 million in 24/25 with a further £17 million due in 25/26), a total of £70 million disbursed of our £80 million five-year commitment. Other payments during the reporting period include our second contribution to ISARIC of £1.15m, making a total of £1.82m, together with supplements for ISARIC’s plague trial extension and the Rwanda recovered patients study. We made a first-year payment of £2.2m to IPD and have followed up this year with a further £4.5m disbursement. Several smaller grants were also made for outbreak research with Wellcome, including a supplement to the Mpox GECIVO project for social and behavioural science research, and completion of the JIREP cost extensions for SSHAP and cholera projects. FCDO also channelled funds through UKRI MRC for the Mpox Rapid Response Consortium and Imperial College’s GIDA Centre for mpox modelling.

Our support to CEPI, in the form of an MoU, started in March 2023 over a 4-year period, for the sum of £80 million. The MoU was entered into after a comprehensive due diligence assessment of the capability and capacity of CEPI to deliver at the scale we require. Of the total expenditure to date, 95% has been spent on its main activity, vaccine R&D and manufacturing, leaving a spend of 5% on overheads (resource mobilization and administration).

Regular FCDO/CEPI meetings are undertaken to monitor progress against the agreed workplan, covering progress against the logframe, risk, finance and performance. These meetings and other interactions with CEPI are with DHSC as a UK government co-funder. The programme SRO, along with their DHSC counterpart, attends CEPI’s quarterly Investor Council meetings and has other ad hoc meetings during the year, particularly on outbreak response. Following rapid growth and increased scope, and pandemic-driven R&D underspend, efforts have focused on improved investment management and organisational efficiencies, leading to increased spend against budget and the successes reported this year. CEPI has streamlined its internal processes, organisational structure, and portfolio management, with a centralised and integrated investment management system.

In June 2024, FCDO entered into a 5-year accountable grant arrangement with University of Oxford to support the ISARIC 3.0 initiative. FCDO have allocated an overall budget of £7.35m, and to date have disbursed £1.82m, with one payment of £1.145m being made in this reporting period, with another similar amount due in the next quarter. The overall total budget includes an increase of £1.35m to their original budget to ensure the plague trial results influence treatment guidance and policy, and funding for the Marburg recovered patient study in Rwanda.

FCDO awarded a four-year accountable grant with Institut Pasteur de Dakar in March 2025, following a comprehensive due diligence assessment process. Whilst adhering with our demanding standards on programme management and financial practices, the assessment identified several areas where IPD are reinforcing policy and systems, and we are working closely with them to develop risk mitigation strategies, especially for PSEAH. This year, we have disbursed £4.56m, including a £1m contribution from Africa Division’s APEX team.

Funding partnerships: While we are finalising our agreement with Wellcome, we have also co-funded several projects to support rapid response for mpox and JIREP extensions. We have also supported two partners for mpox research, through our refreshed UKRI MRC Concordat, in DRC and through GIDA, Imperial College, on modelling. Together with the Food and Agriculture Team, we have also been fully participating in design, review and other support for UKRI’s interdisciplinary One Health call for proposals, Tackling Epidemics, planning a contribution from 26/27.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation FCDO has finalised logframes and indicators with the programme’s three primary partners and is meeting regularly to monitor progress.

CEPI’s Mid Term Review in 2024 assessed progress against the CEPI 2.0 strategy, drawing on CEPI’s Monitoring and Evaluation (M&E) Framework. This year, CEPI addressed evaluation recommendations, including establishing a clear division of labour with Gavi, and tightening KPIs for 2.0. CEPI is also addressing challenges through its 3.0 strategy, ensuring sharper focus, clarifying roles in the ecosystem, setting clear pathways to impact and a stronger focus on ensuring readiness for outbreak research with candidate vaccines.

FCDO and Wellcome are developing terms of reference for the mid-term evaluation with ISARIC. ISARIC used a collaborative, co-creative process to develop its own theory of change and core indicators to develop a logical framework with supporting outputs, outcomes, and impact indicators covering the 3.0 programme’s 20 projects and 3 platforms. This is now being used to monitor progress. IPD has engaged ITAD, which is also working with FCDO’s Africa APEX, to further review and refine its log frame, theory of change, and help IPD establish a new MLE unit as part of its Department of Partnership and Communications.

Evidence A new report from the US National Academies, Age of AI in the Life Sciences, highlights the potential of AI applications to enable advances in biological discovery and design at a faster pace and efficiency than is possible with classical experimental approaches alone. It also describes the risks of misuse for harmful purposes, and threats to biosecurity – which CEPI and other partners are reflecting in their strategic planning.
CEPI publications contribute to strengthening the vaccine R&D knowledge ecosystem and include: a global burden of Chikungunya virus infections study and a paper describing the burden of Lassa fever disease in pregnant women and children. In line with its focus on equitable access, this year CEPI also contributed towards a study on Improving vaccine equity by increasing vaccine thermostability and Advanced technologies enabling accessible and sustainable vaccine development and manufacturing for future pandemics.

IPD has generated new evidence across a range of outbreak-prone pathogens, including Rift Valley Fever, and potential new threats safely stored in IPD’s Biobank samples.

FCDO and Wellcome published a review of our support to the cholera evidence base. In 2018, Wellcome and FCDO’s JIREP programme funded nine research projects to understand the epidemiology, impact of water sanitation and hygiene (WASH) strategies, use of oral cholera vaccine (OCV) and ways to improve case management to reduce deaths from cholera in Ghana, Cameroon, Bangladesh and Kenya. Health experts from both organisations carried out a review of the portfolio, publishing a report in 2025 and blog, Turning cholera evidence into impact means breaking out of the research bubble. Recommendations highlighted purposeful policy engagement and integration of impact pathways from the start, alongside multidisciplinary and multicountry studies to ensure a joined-up approach to tackling cholera globally.

The portfolio yielded significant advancements in cholera understanding and policy influence. In DRC, the first randomised trial of a WASH m-health programme in Africa provided high quality evidence for an integrated WASH intervention to reduce cholera, included in WHO’s 2024 operational guide on preventative measures in healthcare facilities and DRC national cholera control plan. Understanding from Cameroon and DRC on vaccine effectiveness and length of protection informed WHO’s decision to adopt single-dose oral cholera vaccination in outbreak settings.

Learning
During the year, the UK government developed and implemented the UK’s largest cross-government pandemic simulation, Exercise PEGASUS. FCDO’s R&D team participated in both designing the exercise and in simulating our response, working with DHSC and other government funders, and partners such as CEPI and ISARIC. Lessons learned highlighted the need to maintain our emphasis on LMIC needs while also ensuring UK research links. We also need One Health research funder co-ordination, and rapid response capability in modelling and SBS research (which will be available through the MHRN in 2026). Our partnerships with LMIC organisations such as with Institut Pasteur de Dakar, and through the ISARIC network are building collaborative research capacity ready for adaptive platform trials for outbreak research across multiple countries and sites. Given contextual uncertainties, risk appetite and management must take account of the likelihood of failure, early trial closure and inconclusive or lack of results.

Date of last narrative financial report	31/12/2024	Date of last audited annual statement	3/4/2025