## GHS R&D Programme Annual Review 2024

Title: Global Health Security R&D Programme
Programme Value £ (full life): Up to £175 million / Cumulative spend: £57,086,367		Review date: February 2025
Programme Code: 301542	AMP start date: 10/02/2023	AMP end date: 31/12/2027

Summary of Programme Performance
Year	2023	2024
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	GHS BC Exemption summary version updated Feb 2025.docx
DevTracker Link to results framework:	GHS R&D programme - Logframe - YR2.xlsx

## A: SUMMARY AND OVERVIEW

Description of programme
The Global Health Security (GHS) R&D business case is for R&D investments to prepare for, prevent and respond rapidly to disease outbreaks with epidemic or pandemic potential, benefiting vulnerable populations, and building sustainable and equitable R&D partnerships with LMIC organisations. This is the second annual review for the programme, with the Business Case for £175 million (2022-2026) approved in February 2023. The programme builds upon the achievements of FCDO’s previous Epidemics and GHS R&D Programme and includes FCDO’s five-year funding commitment of £80 million for CEPI (Coalition for Epidemic Preparedness Innovations).

The GHS R&D programme’s investments address a priority in the refreshed UK global health strategy planned for 2025, to maintain the UK as a leader in global health science and technology, and to enhance global health security and build stronger health systems for early warning and response. In line with FCDO commitments to LMIC priorities, the programme is capitalising on LMIC and UK science strengths, supporting strong and equitable country-led partnerships for sustainable research capacity and new science and technology partnerships, generating mutual benefits. The programme’s inbuilt agility and partner readiness is already enabling FCDO to rapidly respond to new outbreaks and public health emergencies, such as Marburg and mpox outbreaks this year, working with other government departments and technical agencies including DHSC and UKHSA.
The GHS R&D programme will:
- prioritise and reduce the time taken to less than 100 days for the development and use of effective vaccines, drugs, diagnostics and other technologies in line with the G7 100 Days Mission, working closely with WHO, and other international and regional organisations;
- develop/refresh and invest in 5-10 LMIC and international partnerships (including Product Development Partnerships, PDPs) and funding platforms (for example with UKRI-MRC, Wellcome Trust and the Bill and Melinda Gates Foundation) with proven track record and VfM in developing affordable new technologies for use in LMICs, and mobilising rapid responses for outbreak research;
- establish a new Centre of Research for emerging infectious diseases: during the year, FCDO CSA agreed that this component should be included in the FCDO Science Cell’s new Science in Emergencies Centre for Expertise (SECE), given the advantages of synergies with other multi-disciplinary emergency response needs and reduced transaction costs of not having a stand-alone new centre.

For this second annual review, the updated logframe includes four outputs, covering: progress made by CEPI, as the largest component; other R&D partnerships for results and evidence; progress on inclusive governance, equitable partnerships and capacity building; and programme development, co-ordination, and rapid outbreak response activities. The programme partners are:
- CEPI, an innovative global partnership between public, private, philanthropic, and civil society organisations set up in 2017 and a key implementing partner of the 100 Days Mission;
- ISARIC (International Severe Acute Respiratory and emerging Infections Consortium), a network of networks to deliver clinical research and build capability with LMIC organisations, supported by Oxford’s Pandemic Science Institute, which FCDO is co-funding with Wellcome and Gates Foundation;
- Institut Pasteur de Dakar, a leading regional African institution for R&D, vaccine and diagnostics innovation and manufacturing, and regional public health functions, including surveillance and early warning.
Summary supporting narrative for the overall score in this review
Overall, the GHS R&D Programme has scored an A for this reporting period.

Two major achievements for CEPI include progress on Valneva’s IXCHIQ, the successful licensure of the first ever Chikungunya vaccine, in the US in 2023, Europe and Canada in 2024, which will accelerate the ongoing approval process in Brazil, together with trials launching for pregnant women and children, and a new tech transfer agreement with Serum Institute India to manufacture affordable supplies. Overcoming delays, CEPI has supported IAVI and its partners in successfully starting Phase II clinical trials for a world-first Lassa vaccine in April 2024 in West Africa. Its portfolio in pre-clinical and early clinical phases (including Rift Valley Fever) is strong, with the first ever MERS and Nipah vaccines passing stage gate reviews for phase II. In line with CEPI’s commitment to working in partnership and building capacity with LMICs, it signed agreements with three new manufacturing partners bringing the total to five LMIC partnerships Indonesia, Senegal, South Africa, Brazil and India) in its Vaccine Manufacturing Facility Network, and five of 17 laboratories in the Centralised Laboratory Network are based in LMICs (Bangladesh, India, Kenya, Senegal and Uganda).

Other programme achievements include:
- building FCDO’s institutional relationship with Institut Pasteur de Dakar, and approving a four-year partnership proposal to invest in new product R&D, innovation and manufacturing for regional health priorities, including outbreak diseases, integrating next generation digital technologies across its portfolio, using generative AI to analyse data and monitor threats, and further develop genomic capabilities, in partnership with leading UK research institutions
- new partnership agreed with ISARIC; ISARIC’s completion of the first randomised controlled trial powered to generate robust results on the treatment of bubonic plague, and its support to Rwanda for the world’s first clinical trial for Marburg virus disease treatment
- agreements in principle for FCDO’s joint platforms with UKRI-MRC and Wellcome to enable more rapid funding of research responses for emergencies and longer-term studies
- completion of FCDO’s product development competition in October 2024, with new partnerships with the International Vaccine Institute, PATH and MMV for research and new technologies for epidemic infectious diseases
- mobilising FCDO’s outbreak research responses for mpox and Marburg, working with Wellcome and UKRI Medical Research Council, and co-ordinating the cross-government forum for international epidemic and pandemic research funding, with DHSC (lead on the UK’s Pandemic Preparation and Response R&D framework for domestic PPR with international components).
Major lessons and recommendations for the year ahead
Demands on FCDO capacity Challenges to programme development include time needed to develop and procure a new multi-component programme, including for several new or refreshed partnerships with funders and LMIC organisations, and for contributing to cross-government policy processes with multiple stakeholders, while also funding and managing outbreak rapid responses. One of the key challenges in emergency response research programming is designing funding and implementation arrangements that are sufficiently rapid and agile, while also driving VfM and managing fiduciary risk, recognising that, as with all research investments, there will be inconclusive results, especially in the unpredictable environment of outbreak research.

CEPI At the mid-point of the 2.0 strategy (2022-2026), the 2024 Mid Term Review 2025.09.16 RPC model assessment - Final presentation.pptx
 found that while very substantial progress has been made by CEPI in achieving results, some objectives will not be achieved, partly due to the legacy of the COVID-19 pandemic and partly because 2.0 strategy is somewhat over-ambitious, in its large scope and assumptions that the same rapid action and levels of investment achieved during a global emergency are possible during so-called normal times. Despite best efforts to maintain political momentum, the external context has changed: there is less perceived urgency and lower absorptive capacity to engage among potential partners for the work needed to progress the KPIs. However, the MTR also found that CEPI works as a collaborative partner in a complex eco-system, across governments, WHO, global health initiatives, technical agencies, industry, academics, researchers and civil society.

Challenges in demonstrating efficacy: The recent, rapidly contained outbreaks of Marburg in Rwanda, and Sudan Ebolavirus in Uganda in 2022, have highlighted the continuing challenges and debate around how to demonstrate the efficacy of products for rare, outbreak diseases. Simply put, with only a small number of infections, it is not possible to recruit sufficient numbers to a phase III randomised control trial. In the wake of the Ebola epidemic, WHO developed and pre-approved protocols that would speed up the use of experimental therapies and vaccines while also addressing efficacy questions. This includes the pre-prepared treatment protocol used in Rwanda, and led by WHO with FCDO’s partner ISARIC, designed for an open trial which could recruit during successive outbreaks, and approved by 22 African countries. However, this may also be a slow process with infrequent outbreaks, and partners are exploring other routes to licensure.

Previous recommendations
- CEPI to manage investment and prioritisation of its portfolio effectively, including recalibrating 2.0 budgets, targets and timeline if needed, through Board and Investors Council. Underway in 2024, new budget and strategic workplan early 2025
- FCDO to continue to participate in informal investor discussions to generate shared view on CEPI performance for CEPI senior management and seek partner perspectives on CEPI’s management approach. Ongoing, including through investor engagement with strategy 3.0 development in 2025
- CEPI to ensure that behavioural research and social science are integrated into their work, and to take a holistic One Health approach where appropriate. Ongoing process, including inclusion of social science research in Lassa Fever research programme in 2024, and links with animal vaccine platforms for Rift Valley Fever and Nipah Virus, by mid 2025.
- CEPI to monitor and report on their publications, including disaggregation of authors (female and LMIC based). Achieved in 2024.
- CEPI to demonstrate the impact of its work on equity and access with concrete examples in LMICs. Ongoing process, indicator needed by November 2025.
- CEPI to review and update its KPIs and Results Framework. CEPI planning this in 2025/26.
- FCDO to shift the Annual Review date to calendar year end in order to better align with CEPI’s mid-year reporting cycle. Aiming for November 2025.
Recommendations 2025
- CEPI to consider and implement the recommendations of the MTR and publish both the MTR report and CEPI’s management response online by March 2025.
- FCDO and CEPI to finalise nested logframe and adjust timing of future annual reviews to better align with partner annual reporting, by mid 2025
- FCDO, Wellcome and MRC to continue collaborative efforts for sustaining the LMIC networks and capacity developed through the pandemic response, to maintain readiness for future outbreaks, including allocating new health adviser time and easy-to-use financing arrangements for co-ordinated emergency response for treatment and diagnostics research, in 2025
- CEPI and regulatory bodies, developers and technical agencies/partnerships to continue exploring alternative pathways to licensure, drawing on the FDA’s Animal Rule[1].
  [1] The ‘Animal Rule’ requires using animal models to establish immune correlates of protection that are also valid for humans (‘immunobridging’, identifying immune functions that correlate with and are biologically responsible for vaccine induced efficacy).
- CEPI to continue to contribute to, and define its role, in the end to end ecosystem for equitable access with other stakeholders, drawing on its Equitable Access Framework, as recommended by the MTR.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC) for the GHS R&D programme is based on the case that if affordable new technologies (vaccines, diagnostics and therapeutics) are developed against infectious diseases of epidemic potential alongside the generation and application of greater evidence on what works to improve the accessibility, equity, delivery and uptake of these products, then this will lead to increased and broad use of high-impact and efficacious products delivered efficiently to those who need them, which will then lead to improved health, demonstrated through reduced infections and mortality, reduction in the scale or number of outbreaks, and financial and social benefits. The primary outcome is that the programme will result in the development of new or improved products that are affordable and available at pace, at scale and where needed, ensuring equitable access. Additional outcomes include increased research and technical capacity at local and regional levels, new evidence-based policies and practices in place, and strengthening the UK’s contribution to, and leadership in, global health.

The ToC is based on both FCDO’s track record and the evidence base for successful product development through a portfolio approach. There is also strong evidence that focusing only on the development of tools cannot have the intended impact without good availability and affordability, and improved knowledge about what works, including social science research. The strategy for FCDO’s global health research portfolio is to ‘link science with delivery’ and to support LMIC-led partnerships and networks for collaborative research and capability, and so the option of funding only products, or only intervention research is not recommended.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The impact for the programme is: improved health, demonstrated through reduced infections and mortality, reduction in the scale of outbreaks, and financial and social benefits (modelled data). It is too early in the programme to demonstrate progress against these indicators. CEPI is commissioning modelling work on its pathogens to make the case for investment.

The outcome of the programme is: increased and timely availability of new treatments, diagnostics, vaccines and other tools for global health security and responding to disease outbreaks and AMR, delivered through global technology platforms and international public-private partnerships, that are affordable, and available at pace, at scale, and where needed in LMICs, ensuring access for the most vulnerable populations

The response to Rwanda’s Marburg outbreak in 2024 demonstrates performance at outcome level. As described in a joint editorial in the Telegraph by Rwandan Minister of Health Nsanzimana and CEPI’s CEO, within nine days of the declaration of the outbreak, the Rwanda Biomedical Centre had initiated clinical trials of experimental treatments and begun an open-label Phase 2 clinical trial of an investigational vaccine developed by the Sabin Vaccine Institute. Support to ISARIC through this programme was crucial in the set and up and launch of this world first treatment trial for Marburg virus disease. CEPI and ISARIC were well positioned to support the government through existing trusted relations and 100 Day Mission preparedness plans in place. On December 20, Rwanda announced the formal end of the Marburg virus outbreak, two full incubation periods (42 days) without the identification of any new cases.  The case fatality rate of the epidemic (<23%) was the lowest ever recorded for a Marburg outbreak.  Rwanda’s effective response is largely attributable to its extensive preparedness activities over several years, including with CEPI and other partners.

The programme is on track to deliver against its three outcome indicators:
Number of products produced by the programme, included in treatment guidelines globally and in relevant LMICs and reaching people in need; investigational candidate supplies ready for emergency rapid response research and progress in establishing rapid response technology platforms

CEPI has made substantial progress against this outcome by partnering with Valneva to secure approval for the world’s first Chikungunya vaccine (IXCHIQ) in USA, Canada and Europe, and a supply agreement with Serum Institute India. Additionally, CEPI’s partnership with BioNTech establishes a rapid response platform, including in Rwanda.

Number of evidence products used by practice or policy-related stakeholders locally, nationally, regionally, or globally. ISARIC’s positive results of the first randomised control trial for the efficacy and safety of a new treatment protocol for bubonic plague (IMASOY) in Madagascar will influence national and global guidance, with WHO convening a new technical review group on the basis of the findings.

Increased local, regional, and global capacity to respond to the challenges of diseases of epidemic potential. CEPI has made progress against the third indicator with Calls for Proposals launched to develop heat-stable vaccine technology, microarray patches for mRNA vaccines and other innovations, and developed a global Vaccine Manufacturing network across five LMIC countries to date. Our partnership with IPD is also on track to contribute to this indicator.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
This is the second year of the new GHS R&D Programme. The response to the Marburg outbreak demonstrates the value of existing partnerships, funded for preparedness and rapid mobilisation. The Theory of Change is robust, based on evidence and lessons learned, with strong potential for outcomes and impact for the overarching programme. By working with experienced partners, such as CEPI and ISARIC, who work at scale across a portfolio, the programme should deliver good VfM and support the 100 Day Mission.

## C. DETAILED OUTPUT SCORING

Output Title	Accelerated development by CEPI of new vaccines and platform technologies for diseases of epidemic and pandemic potential, ensuring equitable access for LMICs through an end-to-end approach
Output number:		1	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	Yes, reduced from 75% due to new outputs for Year 2

Briefly describe the output’s activities and provide supporting narrative for the score.
Indicator(s)	Milestone(s) for this review	Progress
1.1: Number of products in the pipeline, disaggregated by stage: / i. research (inc in preclinical) / ii. translation (inc in preclinical) / iii. development (inc number of clinical trials 1,2, 3) / iv. registration, licensure and post-approval / v. vaccine library and rapid response technology platforms/disease X; / (CEPI KPI-OP-1.2.1, KPI-OP-2.1.1 and KPI-OP2.1.2)	Substantive progress towards CEPI’s ambitious mid 2.0 targets: / Preclinical: 1 / Phase I: 9 / Phase II: 7 / Phase III: 2 / Registration and licensure: 0 / Vaccine library: Complete proof of concept for two pilot projects (successful preclinical work meeting vaccine targets). Creation of vaccine libraries for two additional virus families. / Rapid response technology platforms: Initiation of Phase I/II studies.	Met / Preclinical: 3 / Phase I: 7 / Phase II: 2 / Phase III: 0 / Registration and licensure: 1 (Chikungunya, end 2023) / Exceeded preclinical targets for priority pathogens, and made progress on clinical trials, including Lassa, Nipah and MERS Phase II. / Vaccine library: Four viral families have been prioritised. Antigen design and preclinical testing started for 3 pathogens - poxviruses (mpox), arenaviruses (Lassa fever and Junín) and orthomyxoviridae (influenza). / Rapid response technology platforms: Phase I/II clinical trial of the mRNA-based mpox vaccine programme started.
1.2: Number of enabling science programmes and innovative tools to accelerate vaccine development advanced / (CEPI KPI 2.2.1)	Five milestones, covering Nipah international antibody standard, Lassa fever epidemiology studies, and development of preclinical models for all priority pathogens.	Partially met / Completed 3 of 5; progress on preclinical models but not as extensive as targeted. / World’s largest Lassa fever study, in Nigeria, ENABLE 1.0, completed
1.3: Percent of CEPI-funded products/platforms with relevant access plans in place (CEPI KPI 3.3.1) and narrative evidence for progress on implementation	100% of products passing stage gate review.	Met 100% products / Access plans for Valneva’s Chikungunya (IXCHIQ) vaccine reviewed and report due 2025.

Overall, indicators for Output 1 have been met and it scores an A. Across all priority pathogens (MERS, Lassa, Nipah, Chikungunya, Rift Valley Fever), CEPI has exceeded the targets set for preclinical activities, and is catching up on previous delays for Lassa fever and MERS clinical trials, overall making substantial progress against its very ambitious 2.0 milestones for this year.

Following approval of the world’s first Chikungunya vaccine, IXCHIQ, in December 2023, in Brazil, CEPI’s partnership with Valneva is supporting technology transfer to the Instituto Butantan and a clinical study in adolescents, which is expected to support licensure in Brazil, the first approval for use in an endemic country . Valneva has entered a licensing agreement with the Serum Institute of India to expand access to IXCHIQ in Asia. Successful stage gate reviews have completed for Middle East Respiratory Syndrome (MERS) and Nipah vaccine candidates to enter the first ever Phase II trials, and Rift Valley Fever to enter Phase I.

Following Phase I trials, IAVI’s Lassa vaccine candidate successfully entered the first ever Phase IIa clinical trials in Nigeria, Ghana and Liberia in April 2024, with a second passing phase I stage gate review. The largest ever study of Lassa fever to generate epidemiological evidence on disease burden and incidence of infection in West Africa, ENABLE, was expanded in 2024, led by the Nigerian Centre for Disease Control. Following a workshop with SSHAP social scientists, ENABLE 1.5 will include a social sciences component to explore community perceptions of Lassa and vaccine needs.

Figure 1: CEPI-funded vaccine candidate portfolio overview (with 2.0 targets in yellow)

*Excluding the seven licensed COVID-19 vaccines, plus clinical trials for filoviruses (3 phase II, 1 phase III, 1 phase IV) and for COVID/BPCV (1 phase I, 4 phase II, 2 phase III, and 1 phase IV) and for mpox (1 phase II, and 3 phase IV)

CEPI is also taking forward a biologics workstream, given the similarities with vaccine technologies, for a Nipah Virus monoclonal antibody (mAb), and working closely with the ISARIC network’s Bangladesh hub. This year CEPI launched a call for proposals for further clinical development of the mAb candidate with Phase Ib/IIa safety trials in endemic countries expected in 2025.

CEPI has committed to including equitable access obligations in its funding agreements with partners, (Equitable Access Framework). Plans are integrated in all agreements, but more information is needed on implementation.

Emergency responses to outbreaks: CEPI was also well prepared for rapid emergency research responses to both mpox and Marburg outbreaks. CEPI and its partners in Africa are supporting three studies for the generation of additional evidence for the MVA vaccine, has a partnership with BioNTech to develop its mRNA candidate, with research and manufacturing capacity through its Rwanda partnership (see Annex 1). In response to the Marburg outbreak in September, and drawing on 100 Day Mission planning, CEPI supported the Government of Rwanda to respond fast and set up a phase 2 trial for the most developed vaccine candidate (working with WHO, IQVIA and Sabin Vaccine Institute, USA). The trial recruited over 1700 health workers and other close contacts and will generate safety and immunogenicity data.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Next reporting year we will further develop the nested logframe for this component. FCDO will also engage in consultations with CEPI as it develops its 3.0 strategy, due to start in 2026, including inputs to the results and KPI framework, which may affect the logframe.

Lessons learned this year and recommendations for the year ahead
While earlier pipeline targets are on track, later stage development is facing delays. Some of the delays can be attributed to earlier focus on COVID-19, which pushed forward timelines for other pathogens as well as the ‘first ever’ status for most of the clinical research. CEPI’s reliance on partnering with small and medium-sized biotech companies, which may lack the capacity or expertise for later stage R&D, regulatory approval and manufacturing at scale, could also be a factor, as highlighted in CEPI reviews. There is also portfolio attrition due to ‘go/ no go’ decisions by CEPI. The MTR also highlighted CEPI’s need to further define its role in the R&D ecosystem for epidemic and pandemic preparedness and for a clearer narrative and KPIs for demonstrating success and building understanding of delays in 2.0.

Previous recommendations
- CEPI to undertake portfolio analysis to understand the delays in moving from early- to late-stage clinical trials for vaccine candidates, and strengthened portfolio and budgetary spend. CEPI’s performance and financial reporting demonstrate its improved portfolio management.
- CEPI now actively tracks publications, including female lead authors and those from LMICs (indicator in logframe). CEPI has provided data.
- CEPI to provide more narrative evidence for implementation of access plans. CEPI needs to address this in its 3.0 strategy, for later stage candidates.
- CEPI to actively track early closure of projects, including documenting the strategic and scientific reasons for doing so. CEPI is considering including this indicator in the Results Framework.
Recommendations for 2025
- CEPI to prioritise MTR recommendations, including efforts to progress candidates through to late-stage trials through, for example, strengthening relationships with multinational pharmaceutical corporations (MNCs), in 2025
- CEPI to prioritise its scope of work for the remainder of the 2.0 strategy period and reformulate its Results Framework focussing on realistic goals, including access and go/no go decision indicators, in 2025
- CEPI to clarify its role as part of an end-to-end approach to vaccine development and equitable access and define clear ‘hand offs’ to other stakeholders throughout the remainder of the 2.0 strategy period and when planning for the 3.0 strategy, in 2025
- CEPI and FCDO to review results framework and finalise development of nested logframe, including a KPI to monitor ‘go/ no-go decisions’ and down-selection of candidates, and equitable access implementation, by November 2025
- FCDO and DHSC to contribute to consultation on CEPI 3.0 strategy in 2025

Output Title		Progress made on development of accessible new products and innovations, including clinical trials and studies, and generation of new evidence and knowledge to inform policy and programmes
Output number:			2		Output Score:		A
Impact weighting (%):			20		Weighting revised since last AR?		Yes – new output for Year 2 for new R&D partnerships
	Indicator(s)			Milestone(s) for this review		Progress
	2.1 No of products, tools and innovations designed, developed and tested for diseases of epidemic potential (disaggregated by development stage)			At least 1 product making progress in development		Met / ISARIC: IMASOY trial for improved plague treatment completed mid 2024, and world’s first Marburg treatment trial for an antiviral and a mAb
	2.2 No of trials and studies in process or completed			At least 5 studies/trials underway		Exceeded / ISARIC have 5 studies underway (2 dengue, Nipah, mpox) / Two JIREP extensions to enable completion of cholera studies / New Mpox multicountry studies (DRC, Nigeria, Cameroon) led by MpoxRec, Africa-led consortium
	2.3 No of publications in peer reviewed journals, with LMIC lead or co-author, female lead or co-author, and open access; no of data sets including % open access (CEPI, ISARIC, others)			At least 20 publications per year / No indicator for data sets this year		Exceeded / CEPI: 21 publications: 19% (4 publications) with a female lead author; 4.8% (1 publication) with an LMIC-based lead author; 95% (20 publications) open access. / Since the launch of CEPI 2.0 in 2022, the total is 81 publications. / ISARIC: 13 publications (all open access), all 13 had one or more female co-author and 12 of which had one or more LMIC co-author. / No datasets were reported as available by ISARIC or CEPI
	2.4 Narrative evidence to demonstrate the development of research infrastructure and knowledge tools such as clinical characterisation protocol & e-case report forms, core outcome sets, training materials, guidance notes and briefings, software, evidence mapping tools			Narrative evidence provided		Met / ISARIC developed the mpox Clinical Characterisation Protocol and electronic Case Report Form, and started this work for dengue, the Visual Evidence & Research Tool for Exploration (VERTEX) and a tool to quantify and contextualise the effects of stigma across diverse outbreak settings / SSHAP held two roundtables, produced three briefs and two question banks, and contributed to WHO’s mpox workshop and social science protocol as part of JIREP extension for mpox and Marburg responses
	2.5 Partner programmes are engaging and/or influencing national or international stakeholders eg technical networks, advisory or working groups, key decision makers.					Met / CEPI influenced stakeholders to ensure that appropriate emergency regulatory legislation is in place and on equitable access to vaccines and other biologic countermeasures. / ISARIC held an international workshop in Madagascar on plague trial results; reported three policy engagement activities: including WHO R&D Blueprint Pathogens prioritization meeting (May 2024) and collaboration on the filovirus protocol

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, this output has been met, and scores A, addressing priority diseases including filoviruses (Marburg and Ebola), mpox, dengue and Nipah virus.

ISARIC’s plague treatment trial found that oral treatments are comparable to existing intravenous regimens (results in press). This result is likely to lead to new guidance, reducing care costs with no intravenous requirement and enabling more patient-centred care. Delivering this trial is a major scientific, logistical and diplomatic achievement, delivering improved care for the most vulnerable populations whilst enhancing research capacity at local and national levels. FCDO has agreed a no cost extension to enable further work to ensure impact on policy and programmes.

ISARIC also provided key technical support for the world’s first clinical trial for Marburg and activating the WHO-led prepositioned pan-filovirus (haemorrhagic fevers) platform treatment trial. The clinical trial was initiated in less than 3 weeks after the outbreak was declared (27 September 2024) in Rwanda and recruited patients. The speed demonstrated the utility of pre-positioning agreed trial protocols in countries at risk of outbreaks, developed by WHO and ISARIC, and agreed by 22 African countries in February 2024.

ISARIC have several other clinical studies and trials in progress, although early in 3.0 delivery. An observational study is underway using the Dengue clinical characterisation protocol CCP framework, including a tailored protocol and case report forms (CRF) to deliver evidence to inform treatment decisions and new clinical trials, led by Apollo Hospitals Educational and Research Foundation and the India Registry of Intensive Care, across 28 sites in 7 countries through the clinical epidemiology and analysis platform. ISARIC have developed a core outcome set (COS) for therapeutic efficacy studies of hospitalised dengue as part of the dengue core outcomes exercise (DEN-CORE), with expert participants from over 30 countries. This work will feed into a dengue treatment platform trial for the evaluation of the clinical efficacy of proposed treatments, involving several ISARIC sites including in Colombia, Peru, Vietnam and Singapore and using data, standards, and tools from the CCP.

Work to address gaps in clinical treatment of Henipavirus disease (Nipah Virus/NiV) includes an observational study active at three sites in Bangladesh, led by the International Centre for Diarrhoeal Disease Research, Bangladesh (icddr,b). ISARIC, in partnership with the Indian Council of Medical Research (ICMR) and CEPI are co-developing the use cases for Nipah medical countermeasures, including vaccines, monoclonal antibodies, and small molecule therapeutics, including a workshop in India in April 2024, and a published review of how to improve NiV disease care.

ISARIC have led the development and deployment of an Mpox-specific Clinical Characterisation Protocol (Mpox4C) and associated electronic Case Report Form (eCRF). This was developed within the BRIDGE tool, showcasing the ISARIC tool’s adaptability for disease-specific research needs. These tools, accessible through ISARIC’s website, provide a standardised framework for capturing and analysing clinical data. ISARIC have also led significant developments in Mpox research including the first protocolised treatment programme for Clade I Mpox (conducted in Central African Republic).

As part of FCDO’s emergency mpox response (see Annex 1), Wellcome and FCDO are funding the Africa-led Mpox Research Consortium (MpoxReC) to lead a new three-year observational cohort study to be conducted in the DRC, Cameroon, and Nigeria (Mpox-GECIVO Africa, Mpox Genomics, Epidemiology, Clinical, Immunological, and Virological Outcomes. It is led by the INRB, DRC, with Bayelsa Medical University Nigeria, Centre Pasteur du Cameroun, Cameroon and Center for Epidemic Response and Innovation (CERI), South Africa. The Mpox-GECIVO Africa project will generate vital multi-country data on mpox’s epidemiology, clinical progression, and outcomes, and will inform evidence-based strategies to control outbreaks and improve responses tailored to different populations, regions, and viral clades.

With respect to Marburg readiness, FCDO and the MRC have also agreed to fund Oxford’s Pandemic Science Institute and ISARIC to work with partners in Ghana, DRC and Uganda, as well as Rwanda, on filovirus research preparedness. The project will establish the Platform Adaptive Randomised Trial for NEw and Repurposed Filovirus treatmentS (PARTNERS) trial, a multi-country, multi-outbreak clinical trial, working with WHO and governments and academic institutions in Africa, and specialists in clinical trials for outbreak-prone diseases. FCDO is also exploring funding research for Marburg patient recovery, in Rwanda, with CEPI, a vital contribution to understanding disease resurgence and vaccine effectiveness.

Social sciences for outbreak response:
FCDO and partners are focusing more on capacity building and full integration of social and behavioural science research into all aspects of the research agenda. Wellcome and FCDO agreed a costed JIREP extension for SSHAP’s emergency response through to May 2025 and for WHO, alongside funding through the humanitarian research consortium, R2HC, to embed collaboration with regional experts (linked to MpoxReC and Africa CDC research). SSHAP's published briefings on these topics were:  Key Considerations: RCCE for Mpox Vaccination in Eastern DRC; Key considerations: Mpox, mining, and vulnerabilities of women and children in eastern DRC. The vaccination briefing informed DRC’s first phase of mpox vaccination, with positive feedback from WHO.

SSHAP’s resources on the 2024 Marburg outbreak in Rwanda focus on key response considerations, including national response capabilities, local governance structures, and regional and economic implications. They have developed a viral haemorrhagic fevers question bank to support a community centred response. With inputs from FCDO to direct the scope towards potential vaccine trials for Marburg and other filoviruses SSHAP have developed a brief on the social dimensions of experimental vaccines.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is a new output to cover the new partnerships and funding arrangements.

Lessons learned this year and recommendations for the year ahead
Access pathways: ISARIC is considering how it can help to ensure that patented candidate treatments, should they achieve licensure, are available and affordable in LMICs, while taking into account that it does not have scope to negotiate access agreements. CEPI’s work on the Nipah monoclonal antibody, in which ISARIC is partnering, includes access considerations.

Recommendations 2025
- ISARIC, with FCDO’s input, to consider a plan for its role in ensuring access to products by November 2025
- FCDO and ISARIC to agree the programme logframe by May 2025.
- CEPI should scale up efforts to support female and LMIC-based researchers and work to ensure all supported publications are open access, Targets to be set in updated nested logframe, and reported on by November 2025.
- All partners to aim for and report on open access datasets, by November 2025.

Output Title		Improved arrangements for inclusive governance and equitable partnerships, and capacity strengthened with LMIC partners and networks
Output number:			3		Output Score:		A
Impact weighting (%):			10		Weighting revised since last AR?		Yes – new output for Year 2 logframe
	Indicator(s)			Milestone(s) for this review		Progress
	3.1 LMIC governance and leadership strengthened			ISARIC and CEPI governance reforms demonstrating strengthened LMIC governance		Met / Elections to new ISARIC Executive Board completed in July 2024 and met in Ghana in September 2024; including the chair and deputy chair and leaders of the four regional hubs (Brazil, Ghana, Pakistan and the Philippines). / CEPI’s Board includes LMIC independent and investor members; new Africa CDC MOU
	3.2 No of equitable LMIC partnerships, leading on research agenda setting and management			Four ISARIC hubs operational and able to independently manage projects and data/quality management / CEPI providing narrative evidence for equitable LMIC partnerships / Progress on IPD partnership, to be finalised by March 25		Met / ISARIC currently comprises 65 member networks spanning 141 countries, with over 3,000 clinical research sites. Ghana and Brazil hubs are managing projects, Philippines and Pakistan underway. / Out of 149 CEPI partners, 39 of these are with LMIC-based companies and research organisations. / IPD partnership on track
	3.3 No of partners and research sites adopting and using systems and tools for quality and timely research			At least 2 sites independently operational on ISARIC systems with clinical characterisation and data management activities devolved and led by LMIC-based institution		MpoxRec is partnering with ISARIC and will include mpox clinical characterisation protocol and eCRF in all studies
	3.4 No of LMIC researchers attaining specialised competencies in outbreak response research for emerging infectious diseases			40 LMIC-based researchers per year receiving specialised training in clinical research during outbreaks		Met (6 month target) / 15 researchers (over six months) from Ghana and Cameroon received CREDO (Clinical Research During Outbreaks) training in September 2024. Participants were mentored as they finalised research plans focusing on Marburg, Mpox, and Disease X.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output has been met, and scores A.

The shift of governance to ISARIC members from the global south was marked by establishing an Executive Board (EB), including the Hub Leads from Brazil, Ghana, Pakistan and the Philippines, and the Executive Director of the GSC, in June 2024. Nominations were opened in July 2024 for two Member Representatives to serve on the EB and the Member Assembly elected a female representative from Brazil and a male representative from Canada. The EB, which meets at least quarterly, held an in-person meeting in Ghana on 20 September 2024, during which, with the unanimous support of the EB, Fernando Bozza was appointed Chair of the EB with immediate effect.

FCDO’s partnership with Institut Pasteur de Dakar (IPD) is making progress. The partnership includes objectives to develop and test new outbreak vaccines and rapid diagnostics (such as a Rift Valley Fever mRNA vaccine, and the first rapid diagnostic tests for measles and yellow fever), through designing new products, upgrading biomanufacturing capability for research materials, undertaking quality clinical trials (phase 1 and 2) and strengthening the research ecosystem for outbreak response. IPD will also drive innovation, for example by integrating next generation digital technologies across its portfolio, using generative AI to analyse data and monitor threats, and further develop genomic capabilities.
In addition to R&D workstreams, FCDO’s Africa Dept is funding improved public health functions and surveillance in Senegal and neighbouring countries. The partnership will support strong national, regional and global partnerships, especially in the UK with the Universities of Oxford and Cambridge, LSE, LSHTM, UKHSA, UKMHRA and GADx (diagnostics).

CEPI has a unique role in building partnerships with the global south. CEPI has 149 partners with biotech companies globally. Of these, 39, or 26%, are with companies based in LMICs, reflecting the continuing bias in the global innovation landscape. CEPI signed agreements with three new LMIC research and manufacturing partners bringing the total to five in its Vaccine Manufacturing Facility Network (Bio Farma, Indonesia, Bio-Manguinhos/Fiocruz, Brazil, Serum Institute India, Aspen, South Africa and Institut Pasteur de Dakar (IPD), Senegal, and also hosts the Regionalised Vaccine Manufacturing Collaborative. CEPI works with the WHO mRNA initiative with Afrigen, South Africa and Bio Farma, Indonesia. The recent expansion to CEPI’s partnership with BioNTech aims to contribute towards building a sustainable and resilient end-to-end African vaccine ecosystem by expanding the scope of its manufacturing facility in Kigali, Rwanda. Five of 17 laboratories in CEPI’s Centralised Laboratory Network are based in LMICs (Bangladesh, India, Kenya, Senegal and Uganda). CEPI has had clinical trial studies in 55 countries, with 66% of over 113 sites in LMICs.

Figure 2: CEPI’s partnerships, including in the global south

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is a new output to cover the new partnerships and funding arrangements.

Lessons learned this year and recommendations for the year ahead
While CEPI has many leading LMIC partners, there is a continuing need to invest in the research and development capacity in LMICs to enhance global capacity, but also to bring vaccine and biologic countermeasure development and manufacturing closer to potential sites of outbreaks, highlighted in a recent Lancet comment co-authored by CEPI.

Recommendations 2025
CEPI to strengthen its partnership selection process and equitable relationship management with a particular focus on partners in the Global South and capacity building across the end-to-end spectrum, as part of 3.0 strategy development in 2025

Output Title		Global and UK epidemic research is co-ordinated and collaborative action facilitated, both during and between outbreaks, contributing to strengthened prevention, preparedness and response by LMICs
Output number:				4	Output Score:		A
Impact weighting (%):				20	Weighting revised since last AR?		Yes – Year 2 logframe weighting spread across four outputs
	Indicator(s)		Milestone(s) for this review			Progress
	4.1 Effective international co-ordination for epidemic R&D tools and investment among major partners and stakeholders in line with 100DM, including FCDO contribution to xHMG GHS R&D investment approach		At least three narrative examples illustrating co-ordination between CEPI, ISARIC, and other partners; and effective UK co-ordination			Exceeded / 1 CEPI’s Global Pandemic Preparedness Summit, Brazil July 2024 and co-develop and launch WHO viral families approach to R&D prioritisation; / 2 CEPI launches global biosecurity R&D compact / 3 CEPI and ISARIC agree MOU for clinical trials / 4 Members of the FCDO Health Research Team chair xHMG international funders group, and meetings with external partners; contributed to xHMG process to implement PPR R&D Framework and research gaps and priorities for Marburg and mpox PHEIC response / 5 FCDO co-chair for PDP Funders Group
	4.2 FCDO and UK government rapid response R&D mobilisation and delivery		Progress on centre for research; effective outbreak response demonstrated			Met / Agreed with FCDO CSA that centre should be part of the new Science for Emergencies Centre of Expertise and Multi Hazard Network; scope of work drafted; competition due 2025 (led by CSA Science Cell) / Two outbreak R&D responses effectively mobilised, co-ordinated and funded (mpox, DRC etc, and Marburg, Rwanda)
	4.3 Progress made on partnerships and platforms to implement GHS programme approach for LMIC-led research on epidemic and outbreak diseases		Progress on at least two new LMIC-led institutional partnerships and / PDP procurement; progress on funder partnerships and joint platforms			Exceeded / 1 New partnership progressed with Institut Pasteur de Dakar, Senegal, with proposal agreed October 2024 / 2 New partnership completed with ISARIC (International Severe Acute Respiratory and emerging Infection Consortium) through Oxford’s Pandemic Science Institute with Wellcome and BMGF; / PDP call launched in December 2023, completed in December 2024 / MRC concept note agreed and strategic approach drafted; Wellcome partnership drafted and agreed in principle

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, this output has been met, and scores A.

Partner co-ordination for 100 Day Mission: CEPI, the Ministry of Health (Brazil) and Fundacao Oswaldo Cruz (Fiocruz) hosted the Global Pandemic Preparedness Summit, Brazil July 2024. The summit aimed to reinvigorate momentum for pandemic preparedness and had three key themes: enhancing global disease surveillance; delivering the 100 Days Mission; enabling equitable access to vaccines, medicines and other health technologies. Outcomes included the co-publication of the WHO-led Pathogens Prioritization framework focussing on pathogen families. CEPI also launched the international Bio Funders Compact at the 2024 Global Health Security Conference in Sydney, Australia, which incorporates biosecurity into the bioscience research funding process to safeguard life science research from accidental or intentional misuse.

CEPI continued its role in the 100 Day Mission, the Pandemic Accord, the i-MCM Network, led by WHO, and XVAX (for emergency vaccine supply if needed) and signed MOUs with the Africa CDC, PAHO and Unicef. CEPI and ISARIC agreed an MOU to work together in emergency response, and on clinical trial partnerships.

Cross HMG co-ordination: The xHMG Strategic Response Funders Forum for pandemic preparedness and response research, chaired by DHSC and FCDO CSAs, is meeting regularly (led by DHSC), together with FCDO-led UK international funder meetings. Wellcome is joining both the senior and working level meetings, and we continue to link up with GloPID-R (where UKRI-MRC represents the UK).  R&D issues are also included in regular FCDO-led Epithreat and Africa outbreak response meetings.  This year, we led the UK’s mpox and Marburg R&D response (see below).

The planned Centre for Research is now integrated as a workstream within the Science for Emergencies Centre of Expertise (SECE) and Multi Hazard Network, in order to improve efficiency, co-ordination and agility for emergency response and reduce transaction costs, following agreement within RED and with DHSC, UKHSA and UK funders. Early market engagement has taken place, with procurement scheduled for early to mid-2025. Led by the FCDO CSA Science Cell.
FCDO is demonstrating its capability to mount a rapid and well-coordinated research response to disease outbreaks, including Marburg Virus Disease in Rwanda and the worsening mpox epidemic affecting many African countries.
Marburg outbreak response, Rwanda, September 2024: There are no approved vaccines or treatments for Marburg. Supported by CEPI, and drawing on joint 100 Day Mission preparedness planning, the Government of Rwanda responded fast to set up a vaccine trial in two weeks, for a phase 2 trial for the most developed vaccine candidate (Sabin Vaccine Institute, USA). The trial recruited over 1700 health workers and other close contacts. A randomised efficacy trial was started in November, but is unlikely to generate evidence, given the outbreak was contained. FCDO-funded ISARIC Oxford leads supported the first Marburg treatment trial with MoH and WHO, for Remdesivir, an antiviral, and a monoclonal antibody, using a pre-approved filovirus research protocol developed with WHO and agreed by 22 African countries at risk). UKRI-MRC/FCDO have agreed to fund ISARIC for the Rwanda trial plus readiness support to three further countries (DRC, Uganda and Ghana). FCDO is also planning to fund Rwanda’s recovered patients study with CEPI. FCDO-supported SSHAP has published an evidence brief on effective approaches to community engagement and protection, including safe but respectful burial practices and vaccine trials.

Mpox response (see Annex 1): With the rapid rise in cases of the new mpox clade 1b as well as ongoing 2b outbreaks in Africa, WHO declared mpox as a Public Health Emergency of International concern (PHEIC) in August 2024, following Africa CDC’s announcement of a Public Health Emergency of Continental Security. FCDO, in liaison with other UK funders (DHSC NIHR, UKRI-MRC and Wellcome) and through our international partners, are funding a co-ordinated portfolio of complementary research, studies and guidance, in line with the mpox research response roadmap (WHO/Africa CDC/CEPI/NAIAD). Our partners CEPI and ISARIC are also funding vaccine and treatment trials with partners in affected countries, including DRC, Central African Republic and Uganda.

The team made significant progress on developing new and refreshed partnerships and joint platforms (described in Output 3).

Partnership with Institut Pasteur de Dakar (IPD): During the year, IPD’s full partnership proposal was agreed, and due diligence assessment completed, on track for accountable grant agreement and making the first payment in 24/25. The CSA and SRF visited IPD for high level Centenary events in December 2024.

Wellcome-FCDO- BMGF partnership support to ISARIC (International Severe Acute Respiratory and emerging Infection Consortium): FCDO, together with Wellcome and the Gates Foundation, have awarded ISARIC £16.5 million over 5 years to increase clinical research capabilities to tackle infectious diseases. The ambitious new work programme will improve global preparedness and response for emerging infectious disease threats such as mpox, filoviruses, dengue, acute respiratory infections, plague and Nipah. FCDO joined the annual meeting in Ghana, and met with ISARIC’s new Board, comprising hub leads in Pakistan, Brazil, Ghana and the Philippines, and the Global Support Centre based in Oxford’s Pandemic Science Institute.

New and refreshed strategic partnerships: FCDO and Wellcome have been working in partnership for many years, including through the JIREP (with a few extensions until 25/26). During 2024 teams were developing a new Framework agreement for 2025, approved by the UK’s Minister for Development and Wellcome’s new leadership.

One Health programming The FCDO Health Research Team together with the FCDO Food and Agriculture Team is working closely with UKRI to contribute both technically and financially to the Tackling Epidemics phase 2, which will issue a call in early 2025.

The product development competition, launched in December 2023, was completed in October 2024. Successful applicants include at least four PDPs with elements addressing epidemic infectious diseases (including the International Vaccine Initiative, MMV and PATH). Work is progressing on MOUs and accountable grants, with some starting this year and some next.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output includes progress on the new partnerships and funding arrangements, and rapid response to outbreaks. 4.3 will need to be adapted as new partnerships will be agreed mainly at the beginning of the programme.

Lessons learned this year and recommendations for the year ahead
Competing pressures on the team, including two outbreak responses, and pressures on implementing and funding partners have affected progress on new agreements, and greater surge capacity is needed. Cross government co-ordination on outbreak research has strengthened and enhanced our response.

Progress on recommendations 2024
- Procurement for Centre for Research agreed and taken forward in early 2024, with funding agreement and inception activities completed by end 2024 – revised strategy agreed for integration with the Science for Emergencies Centre for Expertise, call planned for mid 2025, implementation starting by end 25/26
- Partnership agreements and grants made with IPD, ISARIC and possible new partners (depending on PDP competition outcomes) by end 2024 – good progress made on new partnerships; ISARIC grant begun; IPD and IVI agreements to be completed by end March 2025
- New partnership/framework agreements completed with UKRI-MRC and Wellcome by mid-2024; strategic approach to One Health investments agreed with RED’s Food Security and Agriculture team by mid 2024, aiming for first call by early 2025 – progress on MRC and Wellcome agreements, delayed due to leadership changes; agreements planned for end March 2025; progress on One Health strategy and agreement with UKRI on FCDO contribution to Tackling Epidemics call, mid 2025
Recommendations 2025
FCDO to complete procurement and new partnership agreements in 2025, ensuring capability for rapid response to outbreaks

D: VALUE FOR MONEY

Key cost drivers and performance
This programme funds investment in research and development to combat diseases with outbreak potential. Key drivers of cost for R&D and product development include scientific expertise (usually highly specialised), laboratory set-up and running, the cost of clinical trials (including facilities, expert time, surveillance, document preparation, report writing, etc.), preparation of dossiers for regulatory approval, other advocacy and dissemination activities, and staff costs. The key cost drivers of operational R&D include: clinical and post-clinical activities; purchase and logistics; training for participants; personnel; communications and travel.

VfM performance compared to the original VfM proposition in the business case
By investing in existing platforms and partnerships to develop tools to combat the pandemic, FCDO is advancing research and helping save lives and livelihoods and improve health outcomes for people affected by disease outbreaks in LMICs. The programme continues to prove its ability to work with many stakeholders to rapidly accelerate and deliver new/repurposed products for emerging infectious diseases in LMICs.

Evidence continues to demonstrate the likely cost-effectiveness and effectiveness of outbreak technologies. For example, climate change and other environmental and demographic factors are threatening to put as many as 700 million people at risk of developing Lassa fever in the future, underscoring the urgent need for effective vaccines. Recent modelling for CEPI found that deploying a safe and effective Lassa vaccine across 15 countries in West Africa could save nearly 3,300 lives over 10 years and avert up to $128 million in societal costs, published in a Nature study . Recent Ebola vaccination economic modelling suggests that prophylactic vaccination will save lives and could prevent nearly 90% of an outbreak’s negative economic impact. A systematic review of 25 studies found that COVID-19 vaccination was a cost-effective or cost-saving intervention for mitigating coronavirus transmission and its effect in many countries.

The programme’s partnership and portfolio approach to R&D investment continued to drive VfM. In 2024, Research Policy Cures (now Global Health Impact) published a thorough evaluation of the neglected disease R&D landscape, including some outbreak diseases (not COVID-19) and the value of investing in this type of research. They found that investment over the last 20 years using the PDP model will have saved 40.7 million lives, or 2.83 billion disability-adjusted life years (DALYs), by 2040, which translates to an economic benefit of $49.9 trillion, or a return on investment of $405 for every $1 invested. Whilst the return on investment for this specific programme may be different, the PDP portfolio and risk pooling model contribute to the outputs and outcomes, which would imply a similar return on investment for this programme’s technology development components.

CEPI is the major programme partner, with a long-standing partnership with the UK government. Throughout the reporting period they have sought to demonstrate good VfM in their activities and this builds on the evidence for economy and efficiency which was closely scrutinised in the due diligence assessment FCDO undertook prior to signing of the MoU in March 2023. The lasting impacts of the COVID-19 pandemic, and the steep decline in the need for COVID-19 funding, alongside slower progression of some projects in CEPI’s portfolio and overambitious strategic objectives contributed to a lower spend than forecast in 2022 and 2023. In 2024, spending and progress on key projects has increased in line with the projected budget, accompanied by better forecasting and tighter internal oversight on delays.

However, in terms of equitable access, the COVID-19 pandemic showed that R&D impact on lives saved is also limited by equity and delivery challenges which are often outside research programme scope. CEPI continues to strengthen its Equitable Access Framework, but delivering end to end objectives is challenging, especially with respect to financing, market shaping, procurement, deployment and use. The MTR recommended further clarification of CEPI’s role in downstream activities.

Assessment of whether the programme continues to represent value for money
This is the second annual review of this programme. The portfolio, including FCDO’s long-standing investment in CEPI, new ISARIC and IPD partnerships, together with our refreshed MRC and Wellcome partnerships, is building preparedness, and delivering outbreak responses, whilst maintaining good VfM. This will be closely monitored as the programme progresses and the expectation is that CEPI and new partners will continue to deliver positively in this area.

Examples of VfM

Economy	Pooling funds: By investing through platforms with UKRI-MRC, Wellcome and BMGF, including partnerships such as CEPI, and ISARIC, FCDO helps to secure maximum benefit at the lowest cost, for example, through sharing/saving on administration costs and accessing the best expertise at a fair price.
Efficiency	Cross-collaboration and co-ordination: The programmes use resources well – for example FCDO is working closely across government and with Wellcome, as well as internationally, drawing together epidemiological, immunology, policy, and innovation expertise.
Effectiveness	Relevance: Research partnerships are in areas of high priority to the FCDO, given UK government emphasis on epidemic and pandemic preparedness including in LMICs. / Leveraging strong UK and LMIC partnerships: Partnerships, such as ISARIC and IPD, and projects combine LMIC and UK expertise and leadership, building LMIC capacity while also driving benefit for LMICs and sharing UK expertise across geographies and populations. / Saving lives: By providing research funding for expanding LMIC trials through CEPI and ISARIC, FCDO helps to mitigate the loss of lives and health impacts in LMICs of outbreak diseases. / Portfolio approach across different funding mechanisms: Diversifies and reduces risk, careful technical and financial oversight by the partnerships and pooled funds or platforms, accelerating the timeline from discovery to testing, licensure and delivery of affordable, safe, effective and quality products, as demonstrated by CEPI’s success in progressing vaccine candidates. / Learning lessons and trusted partnerships: Faced with an emergency response needs, the quality of FCDO funded research is best assured by working through trusted partners such as UKRI MRC and Wellcome Trust, MMV and DNDi, organisations with access to global expertise.
Equity	Equitable access and inclusion: addressing neglected threats such as mpox, cholera and dengue; processes and mechanisms to ensure that the outputs and outcomes uphold ethical principles and drive equitable access - end to end approaches to ensure any products developed are accessible and affordable in LMICs and, where possible, manufactured closer to outbreak locations. / LMIC partnerships for equality, diversity and inclusion: the programmes support researchers, including women, in LMICs through training and equitable publication policies, and build equitable research partnerships with LMIC research organisations.

E: RISK

Overview of risk management
The overall risk level is judged to remain ‘Moderate’, within the Research and Evidence Department’s high appetite for intellectual and innovation risk. A detailed risk register for the GHS R&D programme will be developed over the next year, including for its major components as they take shape. This will be actively monitored by the FCDO programme team along with the programme partners.

Summary risk matrix from programme business case:
Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Major	Major	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

CEPI underwent due diligence prior to the signing of an MoU with FCDO, which provided a high-level of reassurance around CEPI’s governance arrangements. CEPI has made progress on securing investment towards its 2.0 strategy. However in 2022/23 it struggled to spend sufficiently against its 2.0 strategy budget, in part due to overoptimistic forecasting and ambitious strategic objectives. The MTR concluded that without substantial reprioritisation to increase the breadth of its activities, CEPI risks concluding its 2.0 strategy with an underspend and failure to achieve its, albeit ambitious, objectives. Consideration of realistic achievements to the end of 2026 and a plan to implement the learnings from 2.0 under the CEPI 3.0 strategy are being prioritised. CEPI has also strengthened its investment management system and oversight (see Section F).

CEPI’s performance and investment decisions are closely managed and monitored by its Board and Scientific Advisory Committee, together with the Investors Council (which includes FCDO and DHSC). The MTR found that CEPI’s governance structures work reasonably well, however relationships between committees and with management could be strengthened to improve decision-making and efficiency. CEPI must continue to develop and strengthen the internal structures and systems necessary to manage its growing workforce and large and complex portfolio, including more robust financial forecasts and project management, and a proportionate risk management approach with partners.

The substantial expansion to CEPI’s scope from a core focus on R&D to becoming a key player in an end-to-end approach to vaccine development and ensuring equitable access has caused some ambiguity on where CEPI’s role starts and finishes vis-à-vis other stakeholders in the pandemic research ecosystem. This could pose a strategic risk to the organisation if gaps remain in the end-to-end approach.

This reporting period, CEPI completed several improvements to its risk management framework following a review in 2022/23, including:
- approval of CEPI’s risk appetite;
- strengthened organisational level risk management including approval of organisational level risks and documenting of these in CEPI’s Risk Register; and
- approval of updated Risk Management Policy, including clarity on roles, responsibilities and accountabilities at all levels of the organisation, by the Executive and Investment Committee, with ongoing quality reporting to the Audit and Risk Committee
ISARIC have an ambitious agenda of governance reform embedded in the 2024-2029 programme of work to elevate the authority of Global South membership and decentralise given the increasing membership. This includes increasingly prominent roles for four existing ISARIC regional hubs (Brazil, Ghana, Pakistan, the Philippines) with up to four additional hubs proposed in 2024-2029 strategy (likely to include India or Bangladesh). The Global Support Centre (GSC) will transfer many of its functions to hubs including budgetary authority, data management and quality assurance. Whilst this is a positive development and was key to securing support for the 2024-29 strategy, there remain risks to the capacity development across all hubs which may progress at different stages and should be carefully monitored. Several other ISARIC outcomes are contingent on hub development, so this risk should be carefully managed over the programme.

Overall, investments in networks such as ISARIC effectively spread risk across institutions, projects, geographical regions and disease research domains. ISARIC maintains a risk management matrix which includes one or more large scale outbreaks in the programme period as a risk with moderate likelihood and moderate impact. It is assessed that with existing experience and capacity, ISARIC’s risk rating is Moderate: it can deliver well on programme objectives with “average” sized outbreaks but in the event of a large or complex outbreak reallocation of some resources towards response would be required.

### IPD: IPD’s rapid growth post pandemic comes with challenges. IPD has a comprehensive institutional development plan, with a Delivery Unit and new arrangements for strengthened governance, management, and organisational systems for workforce development, financing, and project management, coupled with professional development across all domains. IPD will further develop its business and commercial strategy, supported in part by FCDO’s Manufacturing Africa programme (on its diagnostics strategy) and this partnership. Our due diligence assessment (DDA) identifies four sources of major or moderate risk, with an overall assessment of Major. These internal risk areas are being addressed as part of developing the partnership’s risk mitigation strategy. Key indicators and milestones will be included in the programme logframe at output level.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The spend of £57 million includes three payments to CEPI, £12 million in 2022/23, £16 million in year 23/24 and £25 million in 24/25, a total of £53 million to date of our £80 million five-year commitment. Other payments include our first contribution to ISARIC of just over £1 million, and several smaller grants for outbreak research which demonstrate capability to rapidly mobilise funds for timely response with Wellcome and UKRI-MRC, including nearly £3 million for new Africa-led mpox research and a SSHAP extension to May 2025.

Our support to CEPI, in the form of an MoU, started in March 2023 over a 4-year period, for the sum of £80 million. The MoU was entered into after a comprehensive due diligence assessment of the capability and capacity of CEPI to deliver at the scale we require. Out of the overall expenditure for 2023, CEPI spent 95% on its main activity, vaccine R&D and manufacturing, leaving a spend of 5% on overheads (resource mobilization and administration).
Regular FCDO/CEPI meetings are undertaken to monitor progress against the agreed workplan and during these we cover issues such as progress against the logframe, risk, finance and forecasting updates. These meetings and other interactions with CEPI are done with DHSC as a UK government co-funder. The programme SRO, along with their DHSC counterpart, attends CEPI’s quarterly Investor Council meetings and has other ad hoc meetings during the year.

Following rapid growth and increased scope, and pandemic-driven R&D underspend, efforts have focused on improved investment management and organisational efficiencies, leading to increased spend against budget and the successes reported this year. CEPI has streamlined its internal processes and organisational structure, and focused on streamlining portfolio management, with a centralised and integrated investment management system. The Operational Agility Initiative, created following the Voice of the Customer exercise in 2022 is delivering improvements, in for example, the Stage Gate Review process, awardee financial reporting and grant applications in response to Calls. Awardee financial reporting has been reduced from quarterly to bi-annually to reduce burden.

There has been some discussion on amending the schedule from one to two disbursements per year, providing CEPI with replenishments across the year rather than as a one-off payment. A narrative financial report is provided annually by CEPI and this provides a good level of detail on spend for the year, allowing FCDO to closely monitor spend. Should we move to a bi-annual disbursement schedule we will require CEPI to provide financial reports to support each disbursement request.

In June 2024, FCDO entered into a 5-year accountable grant arrangement with University of Oxford to support the ISARIC 3.0 initiative. FCDO have allocated an overall budget of £6m, with an initial tranche of around £677k due to be released towards the end of financial year 2024/25. We are also agreeing to a no cost extension to ensure the plague RCT results influence policy. While we have an earlier due diligence assessment for Oxford, we have not disbursed to them on this programme, so it is difficult to gauge their programme management capabilities. However they have already proven themselves to be prompt, efficient and attentive in their interactions with us.

As mentioned earlier in the review, it is FCDO’s intention to enter into an accountable grant with Institut Pasteur de Dakar. We have undertaken a comprehensive due diligence assessment process to forensically examine the working processes of IPD to ensure that they match our requirements in an implementing partner. Whilst strongly adhering with our demanding standards on programme management, financial practices etc., the assessment has identified several areas where IPD will need to reinforce their practices, and we are working closely with them to develop risk mitigation strategies.

In addition to the major workstreams now being undertaken through the GHS programme, we have also entered into several smaller scale arrangements with the Wellcome Trust to support rapid response on emerging issues and in the final stages of the JIREP initiative. We have collaborated with Wellcome over many years and they continue to be a responsive, supportive partner. As a result, we have been able to quickly undertake a variety of studies and initiatives under this programme to address new threats and support ongoing work through work strands such as SSHAP and mpox.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
FCDO is working with partners to finalise logframes and indicators to inform monitoring, and is meeting monthly to review progress.

CEPI’s Mid Term Review in 2024 assessed progress against the CEPI 2.0 strategy and informed this annual review. The report drew on CEPI’s Monitoring and Evaluation (M&E) Framework found that CEPI 2.0 will have a substantial impact on global epidemic and pandemic PPR and helped to galvanise global commitment to accelerate the development of outbreak vaccines. Progress included CEPI advancing its enabling science agenda, reaffirming its commitment to equitable access and continuing to play to its strengths focussing on preventive vaccines for multiple pathogens. It also highlighted the high esteem in which the organisation is held within the global health architecture.

Challenges to achieving CEPI’s strategic objectives include: its substantially expanded scope compared to CEPI 1.0; unclear role relative to other actors in the preparedness and response sphere; and continued reliance on small and medium-sized biotech companies which may lack the expertise or capacity needed for later-stage R&D, regulatory approval and manufacturing at scale. These challenges are built on top of the ‘flawed foundation’ of the CEPI 2.0 strategy, which the MTR found suffered from a lack of adequate planning, partly due to the COVID-19 pandemic and partly because fundraising took place during implementation, resulting in a slow start, hindering progress and, thus, slow spending.

Evidence
A recent opinion piece from LSHTM reinforces this programme’s strategic case for early intervention, including R&D, to stop small outbreaks becoming epidemic and pandemic threats, by detecting and preventing zoonotic spillover, and early containment and availability of vaccines, therapeutics and diagnostics. CEPI publications contribute to strengthening the vaccine R&D ecosystem and include:
- The optimal mechanism to fund the development of vaccines against emerging epidemics
- Strategic considerations on developing a CHIKV vaccine and ensuring equitable access for countries in need
- The 100 Days Mission: how a new medical countermeasures network can deliver equity and innovation

In collaboration with WHO, ISARIC have been working with its members to develop consensus-driven benchmarking standards and tools for clinical research units. Progress on the clinical trial unit maturity framework (CTUMF) includes a scoping review, with key areas such as sustainability, governance, and innovation. ISARIC have also provided thought leadership and constructive challenge to the medical research community on the Mpox response: Mpox: The alarm went off. Have we gone back to sleep?. This highlighted key hurdles and gaps remaining in outbreak research, for example the amount of time it takes after a protocol is developed to get through regulatory processes before enrolment can start and the need for pre-positioned protocols in advance of outbreaks occurring.

Learning
The Marburg and mpox outbreak responses have tested mechanisms for proposal review and approval, and shown that our contracting/grant-making processes can be sufficiently flexible and ready to mobilise rapidly in case of emergencies, although remain ad hoc. Our new strategic partnerships will formalise these processes. Given contextual uncertainties, risk appetite and management must take account of the likelihood of failure, early trial closure and inconclusive or lack of results. Our collaborative research partnerships with LMIC organisations such as our partnership with Institut Pasteur de Dakar, and through the ISARIC network are building collaborative research capacity ready for adaptive platform trials for outbreak research across multiple countries and sites.

Date of last narrative financial report	28/11/2024	Date of last audited annual statement	12/03/2024

Annex 1
Summary of FCDO response to the mpox PHEIC

Mpox response: With the rapid rise in cases of the new mpox clade 1b as well as ongoing 1a and 2b outbreaks in Africa, WHO declared mpox as a Public Health Emergency of International concern (PHEIC) in August 2024, following Africa CDC’s announcement of a Public Health Emergency of Continental Security. FCDO, in liaison with other UK funders (DHSC NIHR, UKRI-MRC and Wellcome) and through our international partners, are funding a co-ordinated portfolio of complementary research, studies and guidance, in line with the mpox research response roadmap (WHO/Africa CDC/CEPI/NAIAD). These include:

Understanding transmission
- Wellcome and FCDO are funding MpoxReC, an Africa-led consortium to carry out transmission, clinical characterisation and genomic studies in DRC, Nigeria and Cameroon, complementing nine projects funded by NIHR-EDCTP3.
- UKRI-MRC and FCDO funded one of the first studies in early 2024 on the new clade Ib in a conflict-affected border province in DRC, led by South Kivu authorities, Rwandan partners and Oxford, on transmission factors and clinical progression (submitted to the Lancet).
- The 2022/23 Mpox Rapid Response Consortium (Oxford, Cambridge, Glasgow, Pirbright, UKHSA, DSTL, Uganda UVRI), funded by UKRI-MRC and FCDO, is reconvening to optimise expertise on virology, immunology, early therapeutics and diagnostics development, and sero-survey data)
Testing treatments
ISARIC support to study the effectiveness of the antiviral, Tecovirimat, in the Central Africa Republic and other research ongoing in the DRC, and deployment of the mpox CCP and eCRF to standardize disease characterization in affected country research studies, including partnering with MpoxRec and the UK.

Prevention and Vaccine effectiveness - CEPI’s emergency response to mpox: Following preparation of a regulatory dossier which reviewed the evidence base on licensed vaccines, it is supporting three clinical trials of the licensed MVA-BN vaccine in DRC (the SMART trial to test post-exposure vaccination, safety and effectiveness for children, and in November 2024, for pregnant and lactating women and infants). It is considering research on safety/immunogenicity/effectiveness in HIV positive populations and fractional dosing regimens with MVA-BN, and planning studies for the other licensed and donated vaccine, Japan’s LC16.

CEPI continues to support BioNTech’s new mpox mRNA vaccine candidate (in phase 2) as part of their strategic partnership. It is working with two UK technical agencies: international antibody standard development with MHRA, and mpox immunoassay development with UKHSA, where tech transfer is underway to partner labs in Africa (UVRI Uganda, INRB DRC) for research sample testing.

UKHSA has a partnership with CEPI to develop qualified immunological assays for vaccine and diagnostic evaluation, and planning tech transfer to UVRI, Uganda and INRB, DRC in 2025. MHRA is partnering with CEPI to develop the international antibody standard, approved by WHO.

In parallel, CEPI is working with WHO, Gavi, UNICEF, & Africa CDC on the mpox co-ordinated research roadmap, and using lessons from COVAX: advocating and supporting an end to end approach to vaccines, integrating R&D, demand planning, financing and procurement, allocation and delivery, and vaccination. CEPI has also worked with partners to collate a dashboard of ongoing and planned research studies. Bavarian Nordic and Serum Institute announced a licensing and tech transfer partnership in December 2024, to enhance access to affordable supply for affected LMICs.
Social sciences for outbreak response: In response to the mpox PHEIC and the Rwanda Marburg outbreak, Wellcome and FCDO agreed a costed JIREP extension for SSHAP’s emergency response through to May 2025. The SSHAP extension complements another JIREP extension, to WHO’s mpox social science team, as well as funding from R2HC’s emergency fund for regional activities, with partners working well together. SSHAP’s first mpox roundtable focused on risk communications, and the second roundtable discussed addressing discrimination against women engaged in transactional sex and gay, bisexual and other men who have sex with men. SSHAP's published briefings on these topics were:  Key Considerations: RCCE for Mpox Vaccination in Eastern DRC; Key considerations: Mpox, mining, and vulnerabilities of women and children in eastern DRC. The vaccination briefing informed DRC’s first phase of mpox vaccination, with positive feedback from WHO.

At the request of, and with support from FCDO, including the Senior Research Fellow, SSHAP is shifting its response to focus more on capacity building and full integration of social and behavioural science research into wider research on transmission and response, as well as vaccine trials and introduction. In November, SSHAP social scientists joined a regional WHO-Africa CDC workshop in Kinshasa, also funded by FCDO through R2HC emergency response fund, and are contributing to the WHO guidelines on social science research on mpox, joining a WHO TWG mpox meeting in Brazzaville in early 2025.  They are contributing to the FCDO-Wellcome co-funded research and will support the social science leads in each country.