## GHS R&D Yr 1 2022-23
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
Year 1 2022-23: Inception Year 2 outputs only. See next tab for Yr 2 2023-2024 onwards
PROJECT TITLE | Global Health Security R&D Programme
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
Improved health, demonstrated through reduced infections and mortality, reduction in the scale of outbreaks, and financial and social benefits (modelled data). | Reduced infections, mortality and scale of infectious disease outbreaks | Planned | 0 | N/A | N/A | N/A | N/A | Due to difficulties with attribution and changing disease patterns, we will not be setting a target but collecting data from partners on their estimated number of lives and/or DALYs saved. We will also include evidence from relevant studies conducted on products (incl. evidence on potential lives saved from clinical trials, natural experiments, etc.)
|  | Achieved |  | N/A
Source
Partner reporting and indpendent studies (incl. exploring the opportunity to commission an evaluation)
| Impact Indicator 2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Evidence of improved financial and social situation; estimated reduction in financial impact (as a result of indicator 1) | Planned | 0 | N/A | N/A | N/A | N/A | As above, unlikely to have reliable, attributable (or even contributable) data on this but will try to capture any relevant evidence generated by partners or independently to inform our assessment on programme impact.
|  | Achieved |  | N/A
Source
Partner reporting and indpendent studies (incl. exploring the opportunity to commission an evaluation)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27 | Assumptions
Increased and timely availability of new treatments, diagnostics, vaccines and other tools for global health security and responding to disease outbreaks and AMR, delivered through global technology platforms and international public-private partnerships, that are affordable, and available at pace, at scale, and where needed in LMICs, ensuring access for the most vulnerable populations | Number of products produced by the programme: i) being included in treatment guidelines globally and in relevant LMICs ii) reaching patients iii) progress in establishing rapid response technology platforms iv) investigational candidate supplies ready for emergency rapid response research | Planned | 0 | i) and ii) progress with COVID-19 vaccines iii) progress in establishing rapid response technology platforms and iv) investigational candidates ready to go eg Sudan ebolavirus narrative | See Yr 2 onwards |  |  |  | 1. Transparent use: Increased understanding and transparent use of (bodies of) evidence by policy makers. 2. Embedded use: No direct action is taken as a result of evidence, but use of evidence becomes embedded in processes, systems and working culture. 3. Instrumental use: Knowledge from robust evidence is used directly to inform policy or programme. * New products have anticipated reductions in and impact of outbreaks. * Epidemics and pandemics Ecosystem and enabling environment exists for capacity building and is implemented at the local/regional level, with appropriate and sustainable political support. * Health systems exist and are capable of deploying products
|  | Achieved |  | Continued progress with COVID-19 vaccines with 7 achieving WHO EUL; progress in Rwanda BioNTech rapid response facility; Sudan ebolavirus candidates in Uganda
Source
CEPI, PDP, and Pooled Platform Annual Progress Reports
| Outcome Indicator 2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Number of evidence products used by practice or policy-related stakeholders locally, nationally, regionally, or globally | Planned | 0 | n/a | See Yr 2 onwards
|  | Achieved |  | n/a
Source
CEPI, PDP, ACE, and Pooled Platform Annual Progress Reports
| Outcome Indicator 3 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Increased local, regional, and global capacity to respond to the challenges of diseases of epidemic potential: i. Number of new technologies demonstrating manufacturing cheaper, faster or closer to an outbreak (CEPI KPI 2.3.1) ii. Number of agreements in place that support manufacturing capacity strengthening in order to support LMICs (KPI 3.3.2) | Planned | 0 | Support one additional manufacturing innovation project that can accelerate epidemic and pandemic responses or enable the scaling of production of vaccines, particularly in LMIC settings | See yr 2 onwards
|  | Achieved |  | CEPI making progress through calls for funding, and global manufacturing network | See Yr 2 onwards
Source
CEPI, PDP, ACE, and Pooled Platform Annual Progress Reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27 | Assumptions
| Number of products in the pipeline, disaggregated by stage: i. research (inc in preclinical) ii. Translation (inc in preclinical) iii. development (inc number of clinical trials 1,2, 3) iv. Registration, licensure and post-approval v. vaccine library and rapid response technology platforms/disease X; vi. Products closed early (CEPI KPI 1.2.1) | Planned | Preclinical: 7 Phase 1: 7 Phase 2: 3 Phase 3: 1 Registration: 0 Licensure: 0 | Preclinical: 2 Phase 1: 6 Phase 2: 4 Phase 3: 2 Registration: 0 Licensure: 0 Vaccine library: 2 families | See Yr 2 onwards |  |  |  | CEPI use preclinical, Phase I, Phase II, Phase III, Registration and Licensure (CEPI KPI 1.2.1)
|  | Achieved |  | Preclinical: 5 Phase 1: 9 Phase 2: 3 Phase 3: 1 Registration: 0 Licensure: 0 Vaccine library: Progress made as planned | See Yr 2 onwards
Accelerated development by CEPI of new vaccines and platform technologies for diseases of epidemic and pandemic potential, ensuring equitable access for LMICs through an end to end approach |  | Source
CEPI Annual Progress Report - KPI 1.2.1 CEPI Results framework has milestone breakdown for their outputs (https://cepi.net/wp-content/uploads/2022/01/20211126-CEPI-2.0-Results-Framework-v1.0-jan-21.pdf)
| Output Indicator 1.2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Number of enabling science programmes and innovative tools to accelerate vaccine development advanced (CEPI KPI 2.2.1) | Planned | International standards developed for Lassa and MERS, initiated for Nipah, Rift Valley Fever. Serology assay completed for Lassa | Six interim milestones for 2022 across enabling science programmes and innovative tools | See Yr 2 onwards
|  | Achieved |  | Three milestones have been met, three are delayed | See yr 2 onwards
Source
CEPI Annual Progress Report - KPI 2.2.1
| Output Indicator 1.3 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Percent of CEPI-funded products/platforms with relevant access plans in place (CEPI KPI 3.3.1) and narrative evidence for progress on implementation | Planned | Status unclear | 100% each year for each product passing a stage gate review
|  | Achieved |  | 80% (4 of 5 products)
Source
CEPI Annual Progress Report
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
75% | No of CEPI authored/contributed peer reviewed publications. * Publications disaggregated by: - % with female lead author - % with LMIC-based lead author | Planned | 0 | Not set | See yr 2 onwards
|  | Achieved |  | Around 50 peer reviewed publication in 2022/23. CEPI does not actively monitor this indicator - data to be provided in 2023/24.
Source
PubMed search and CEPI reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27 | Assumptions
Progress made in programme development and implementation planning and delivery | Procurement progressed on: - Centre for Research - PDP/PDP-like competition (inc new technologies for epidemic infectious diseases) | Planned | 0 | Scope of work and procurement strategy agreed for Centre for Researc PDP/PDP-like competition launched | See yr 2 onwards |  |  |  | Potential partnerships include IPD, IVI (via PDP call), ISARIC (with Wellcome and BMGF), UKRI/MRC (fast track mechanism as part of clinical trials partnership), new OneHealth partnership with UKRI
|  | Achieved |  | Centre scope of work agreed and drafted, decision on procurement strategy to be taken in early 2024; PDP call launched in December 2023 | See yr 2 onwads
| Output Indicator 2.2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| FCDO contribution to xHMG GHS R&D investment approach through engagement and coordination with stakeholders (inc countries, xHMG, organisations, potential partners) | Planned |  | Narrative evidence of meetings, conference, etc | See Yr 2 onwards
|  | Achieved |  | Members of the FCDO Health Research Team have held regular meetings across the FCDO and HMG, and with external partners; contributed to xHMG process to agree PPR R&D Framework and research gaps and priorities | See yr 2 onwards
Source
FCDO, CEPI, partner reports
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Progress made on developing GHS programme approach to partnerships and joint platforms for LMIC led research on epidemic and outbreak diseases | Planned |  | Objectives and draft proposals/concept notes agreed for at least two new institutional partnerships, PDP engagement as needed, including PDP Funders Group Partnerships with MRC and Wellcome refreshed with new agreements for joint platforms underway | See yr 2 onwards
25% |  | Achieved |  | Partnerships with IPD and ISARIC agreed FCDO co-chair and leader for PDP Funders Group MRC concept note and business case drafted Wellcome dialogue progressing Joint approach clinical research funding with DHSC, NIHR, UKRI, MRC and Wellcome | See yr 2 onwards
Source
FCDO, CEPI, partner reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## GHS 2023-27
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
Yr 2- 5, 2023/24-2026/27: expanded logframe with 4 outputs (updated Feb 2025, Feb 2026)
PROJECT TITLE | Global Health Security R&D Programme
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
Improved health, demonstrated through reduced infections and mortality, reduction in the scale of outbreaks, and financial and social benefits (modelled data). | Reduced infections, mortality and scale of infectious disease outbreaks | Planned | 0 | N/A | Narrative evidence and modelling data | Narrative evidence and modelling data | Narrative evidence and modelling data | Due to difficulties with attribution and changing disease patterns, no target but using modelled number of lives and/or DALYs saved and evidence from relevant studies (incl. evidence on potential lives saved from clinical trials, natural experiments, etc.)
|  | Achieved |  | N/A | Modelling for CEPI found that deploying a safe and effective Lassa vaccine across 15 countries in West Africa could save nearly 3,300 lives over 10 years and avert up to $128 million in societal costs (Nature). Recent Ebola vaccination economic modelling suggests that prophylactic vaccination will save lives and could prevent nearly 90% of an outbreak’s negative economic impact. A systematic review of 25 studies found that COVID-19 vaccination was a cost-effective or cost-saving intervention for mitigating coronavirus transmission and its effect in many countries. | A new study from Imperial College on COVID-19 vaccines finds that, while they cost $79 billion to develop and deliver globally, vaccination provided health and economic benefits worth between $5 trillion and $38 trillion globally in the first year alone, averting 14 million deaths, a very significant return on investment of between $60 and $475 per dollar invested.
Source
Partner reporting and independent peer reviewed studies
| Impact Indicator 2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Evidence of improved financial and social situation; estimated reduction in financial impact (as a result of indicator 1) | Planned | 0 | N/A | Narrative evidence and modelling data | Narrative evidence and modelling data | Narrative evidence and modelling data | As above, unlikely to have reliable, attributable (or even contributable) data on this but will try to capture any relevant evidence generated by partners or independently to inform our assessment on programme impact.
|  | Achieved |  |  | See above | See above
Source
Partner reporting and independent peer reviewed studies
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27 | Assumptions
Increased and timely availability of new treatments, diagnostics, vaccines and other tools for global health security and responding to disease outbreaks and AMR, delivered through global technology platforms and international public-private partnerships, that are affordable, and available at pace, at scale, and where needed in LMICs, ensuring access for the most vulnerable populations | Number of products produced by the programme: i) being included in treatment guidelines globally and in relevant LMICs ii) reaching patients iii) progress in establishing rapid response technology platforms iv) investigational candidate supplies ready for emergency rapid response research | Planned | 0 | Narrative evidence | Narrative evidence | Narrative evidence | Narrative evidence | Narrative evidence | 1. Transparent use: Increased understanding and transparent use of (bodies of) evidence by policy makers. 2. Embedded use: No direct action is taken as a result of evidence, but use of evidence becomes embedded in processes, systems and working culture. 3. Instrumental use: Knowledge from robust evidence is used directly to inform policy or programme. * New products have anticipated reductions in and impact of outbreaks. * Epidemics and pandemics Ecosystem and enabling environment exists for capacity building and is implemented at the local/regional level, with appropriate and sustainable political support. * Health systems exist and are capable of deploying products
|  | Achieved |  | Continued progress with COVID-19 vaccines with 7 achieving WHO EUL; progress in Rwanda BioNTech rapid response facility; Sudan ebolavirus candidates in Uganda | i) & ii) Approval for the world’s first Chikungunya vaccine (IXCHIQ) in USA, Canada and Europe, and a supply agreement with Serum Institute India; iii) CEPI’s partnership with BioNTech for a rapid response platform in Rwanda; iv)CEPI and ISARIC support to clinical trials of experimental treatments and vaccines in Rwanda Marburg outbreak | i) & ii) ISARIC-tested regimen used in plague treatment guidance in Madagascar and DRC; Chikungunya vaccine licensed including Brazil; CEPI mpox research enables licensing for pregnant women; iii) & iv) CEPI-Serum Institute India supplying for Chikungunya, Rift Valley Fever and Nipah virus research
Source
CEPI, PDP, and Pooled Platform Annual Progress Reports
| Outcome Indicator 2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Examples of evidence products used by practice or policy-related stakeholders locally, nationally, regionally, or globally | Planned | 0 | No indicator | Narrative evidence - at least one case | Narrative evidence - at least one case | Narrative evidence - at least one case | Narrative evidence - at east one case
|  | Achieved |  | n/a | WHO treatment guidance group to use results from ISARIC plague treatment trial | ISARIC’s tools are used to enable multi country platform studies for dengue and Nipah.
Source
CEPI and other partnership Annual Progress Reports
| Outcome Indicator 3 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Increased local, regional, and global capacity to respond to the challenges of diseases of epidemic potential: i. Number of new technologies demonstrating manufacturing cheaper, faster or closer to an outbreak (CEPI KPI 2.3.1) ii. Number of agreements in place that support manufacturing capacity strengthening in order to support LMICs (KPI 3.3.2) (achieved 23/24) | Planned | 0 | Support one additional manufacturing innovation project that can accelerate epidemic and pandemic responses or enable the scaling of production of vaccines, particularly in LMIC settings | Support one additional manufacturing innovation project that can accelerate or scale epidemic and pandemic responses | Support one additional manufacturing innovation project that can accelerate or scale epidemic and pandemic responses | Support one additional manufacturing innovation project that can accelerate or scale epidemic and pandemic responses | At least three innovations which demonstrate manufacturing cheaper, faster or closer to an outbreak
|  | Achieved |  | CEPI making progress through calls for funding, and global manufacturing network | Good progress with 5 LMIC partnerships signed and innovation calls under way | 15 active manufacturing innovations projects across 11 countries, including thermostability (five projects), speed (seven projects), and scale, access and other attributes (three projects).
Source
CEPI and other partnership Annual Progress Reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27 | Assumptions
| Number of products in the pipeline, disaggregated by stage: i. preclinical (including translation) ii. clinical development (inc number of clinical trials 1,2, 3) iii. registration, licensure and post-approval iv. Libraries of vaccine candidates created and rapid response technology platforms/disease X adapted; v. Projects closed early (CEPI KPIs 1.2.1, 2.1.1, 2.1.2) | Planned | Preclinical: 7 Phase 1: 7 Phase 2: 3 Phase 3: 1 Registration: 0 Licensure: 0 | Preclinical: 2 Phase 1: 6 Phase 2: 4 Phase 3: 2 Registration & Licensure: 0 Vaccine library: 2 families | Preclinical: 1 Phase 1: 9 Phase 2: 7 Phase 3: 2 Registration and Licensure: 0 Vaccine library: Proof of concept for two pilot projects & vaccine libraries for two additional virus families. Rapid response tech: phase1/2 initiated Projects closed early: no indicator | Preclinical: 0 Phase 1: 4 Phase 2: 4 Phase 3: 3 Registration and Licensure: 0 Vaccine library: Creation of vaccine libraries for six additional virus families; completion of preclinical work for two additional virus families Rapid response technologies: Phase 3 initiated | Preclinical: 0 Phase 1: 0 Phase 2: 8 Phase 3: 1 Registration and Licensure: 2 Vaccine library: Completion of Phase 2 clinical testing for two additional virus families; completion of preclinical testing of six virus families Rapid response technologies: Phase 3 ongoing/completion | Preclinical: 0 Phase 1: 0 Phase 2: 4 Phase 3: 3 Registration and Licensure: 2 Vaccine library: Clinical proof of concept for four virus family vaccine libraries Rapid response technologies: Two licensed vaccines against viable targets for LMICs using prototype and/or platform innovations | Availability of funds, political will and commitment in affected countries, demand for vaccines by those in need and procurers, qualified partners willing to work with CEPI
Accelerated development by CEPI of new vaccines and platform technologies for diseases of epidemic and pandemic potential, ensuring equitable access for LMICs through an end to end approach |  | Achieved |  | Preclinical: 5 Phase 1: 9 Phase 2: 3 Phase 3: 1 Registration & Licensure: 0 Vaccine library: Progress made as planned | Preclinical: 3 Phase 1: 7 Phase 2: 1 Phase 3: 0 Registration and Licensure: 1 (Chikungunya vaccine) Vaccine library: Four viral families prioritised. Antigen design and preclinical testing started for 3 pathogens Rapid response technology platforms: Phase I/II clinical trial of the mRNA-based mpox vaccine programme started. | Preclinical: 4 Phase 1: 6 Phase 2: 4 Phase 3: 1 Registration and Licensure: 1 (Chikungunya); plus post licensure studies for mpox and Zaire Ebola vaccines Vaccine library: 20 antigen designs for Lassa and 12 for Junín were tested in preclinical models. Antigen design for viruses in 4 further families. Rapid response: 14 prototype vaccines in development, with 1 in Phase I.
Source
CEPI Annual Progress Report - KPI 1.2.1 CEPI Results framework has milestone breakdown for their outputs (https://cepi.net/wp-content/uploads/2022/01/20211126-CEPI-2.0-Results-Framework-v1.0-jan-21.pdf) Annual Report 2024 https://static.cepi.net/downloads/2025-07/CEPI%202024%20APR%20Report%20FINAL%20-%20V3.pdf
| Output Indicator 1.2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Number of enabling science programmes and innovative tools to accelerate vaccine development advanced (CEPI KPI 2.2.1) | Planned | International standards developed for Lassa and MERS, initiated for Nipah, Rift Valley Fever. Serology assay completed for Lassa | Six interim milestones for 2022 across enabling science programmes and innovative tools | Five milestones, covering Nipah international antibody standard, Lassa fever epidemiology studies, and development of preclinical models for all priority pathogens. | Development of assays for MERS, SARS-Cov-1, Nipah and other CEPI priority pathogens; Results available on Nipah strain diversity in endemic countries | Adapt Agility project to virus family approaches | Three or more of the enabling science tools developed through CEPI funding used by one or more of CEPI-funded vaccine developers
|  | Achieved |  | Three milestones have been met, three are delayed | Completed 3 of 5; progress on preclinical models but not as extensive as targeted. World’s largest Lassa fever study, in Nigeria, ENABLE 1.0, completed | Development and implementation of 25 assays for seven pathogens, with UKHSA and UK MHRA; Nipah strain characterisation projects in Bangladesh and Malaysia, published on Genbank
Source
CEPI Annual Progress Report - KPI 2.2.1
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Percent of CEPI-funded products/platforms with relevant access plans in place (CEPI KPI 3.3.1) and narrative evidence for progress on implementation | Planned | Status unclear | 100% each year for each product passing a stage gate review | 100% each year for each product passing a stage gate review | 100% each year for each product passing a stage gate review | 100% each year for each product passing a stage gate review | 100% each year for each product passing a stage gate review
50% |  | Achieved |  | 80% (4 of 5 products) | 100% | An independent review of CEPI’s existing agreements in 2025 found that 75% met equitable access requirements (including those passing stage gate review); the remaining 25% are being addressed.
Source
CEPI Annual Progress Report
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27 | Assumptions
Progress made on development of accessible new products and innovations, including clinical trials and studies, and generation of new evidence and knowledge to inform policy and programmes | No of products, tools and innovations designed, developed and tested for diseases of epidemic potential (disaggregated by development stage) | Planned | 0 | n/a | At least 1 product making progress in development | At least 1 product making progress in development | At least 1 product making progress in development | At least 1 product making progress in development | Availability of funds, political will and commitment in affected countries, demand for vaccines by those in need and procurers, qualified partners willing to work together
|  | Achieved |  | n/a | ISARIC: IMASOY trial for improved plague treatment completed mid 2024, and world’s first Marburg treatment trial (for 2 products) in Rwanda | ISARIC: Dengue multicountry observational study has 730 patients in 7 countries, with effective platform operation of shared ISARIC systems; Developed the WHO Clinical Trials Maturity Framework (under review) IPD: completed tech transfer for two vaccine platforms (mRNA and viral vector)
Source
Partner reports
| Output Indicator 2.2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| No of trials and studies in process or completed | Planned | 0 | n/a | At least 5 studies/trials underway | At least 5 studies/trials underway | At least 5 studies/trials underway | At least 5 studies/trials underway
IMPACT WEIGHTING (%) |  | Achieved |  |  | ISARIC have 5 studies underway (2 dengue, Nipah, mpox) Two JIREP extensions to enable completion of cholera studies and genomics New Mpox multicountry studies agreed (DRC, Nigeria, Cameroon) led by MpoxRec, Africa-led consortium | ISARIC have completed the DEN-CORE study, and studies on dengue, Nipah, mpox progressing; IPD launched evaluation of first measles rapid diagnostic test; MpoxRec, Africa-led consortium progressing on Mpox multicountry studies (DRC, Nigeria, Cameroon) led by DRC
Source
Partner reports
20% | Output Indicator 2.3 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| No of publications in peer reviewed journals, with LMIC lead or co-author, female lead or co-author, and open access; no of data sets including % open access (CEPI, ISARIC, others) | Planned | 0 | Indicator not set | At least 20 publications per year No indicator for data sets this year | At least 20 publications per year Partners to explore open access for datasets | At least 20 publications per year TBA indicator for data sets | At least 20 publications per year TBA indicator for data sets
|  | Achieved |  | Around 50 peer reviewed publications. CEPI does not actively monitor this indicator so progress is hard to measure. | CEPI: 28 publications: 9 publications with a female lead author (25 with female co-author); 3 publications with an LMIC-based lead author (9 with LMIC co-author); 25 open access. Since the launch of CEPI 2.0 in 2022, the total is 101 publications. ISARIC: 13 publications (all open access), all 13 had one or more female co-author and 12 of which had one or more LMIC co-author. No datasets were reported as available by ISARIC or CEPI | CEPI: 33 publications: 15 publications with a female lead author (32 with female co-author); 4 publications with an LMIC-based lead author (7 with LMIC co-author); 30 open access; ISARIC: 11 publications (all open access), all with one or more female co-author and one or more LMIC co-author. IPD: 84 publications with PubMed ID: 51% with IPD first author, including 15 women Partners exploring how to make datasets available. ISARIC COVID-19 patient data set is available as open access.
Source
CEPI and partner data and reports
| Output Indicator 2.4 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Narrative evidence to demonstrate the development of research infrastructure and knowledge tools such as clinical characterisation protocol & e-case report forms, core outcome sets, training materials, guidance notes and briefings, software, evidence mapping tools | Planned | 0 | n/a | Narrative evidence | Narrative evidence | Narrative evidence | Narrative evidence
|  | Achieved |  | n/a | ISARIC's mpox Clinical Characterisation Protocol and electronic Case Report Form, the Visual Evidence & Research Tool for Exploration (VERTEX) and a tool to quantify effects of stigma SSHAP held two roundtables, produced three briefs and two question banks, and contributed to WHO’s mpox workshop and social science protocol as part of JIREP extension for mpox and Marburg responses | ISARIC’s CCP and electronic Case Report Form extended to 6 diseases; VERTEX use in Ghana, Pakistan, and the Philippines hubs. The BRIDGE 2.0 (BioResearch Integrated Data tool Generator) update allows collation of datasets in 32 sites. IPD achieved: dual ISO certification for the IPD Senegal Biobank, the first in Africa; ISO certification for diagnostics R&D and manufacturing facilities; strengthened clinical trial management system SSHAP and WHO produced SBS guidance for mpox, and draft protocol, collated SBS data and held a workshop with African researchers as part of JIREP extension
Source
Partner reports
| Output Indicator 2.5 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Partner programmes are engaging and/or influencing national or international stakeholders eg technical networks, advisory or working groups, key decision makers. | Planned |  | n/a | Narrative evidence | Narrative evidence | Narrative evidence | Narrative evidence
|  | Achieved |  | n/a | CEPI influenced stakeholders to ensure that appropriate emergency regulatory legislation is in place for outbreak response; ISARIC's international workshop in Madagascar on plague trial results; reported three policy engagement activities including collaboration on the filovirus protocol | CEPI convened the Lassa Fever Coalition with African governments to accelerate late-stage vaccine development and rollout; advocated for equitable access provisions in the draft WHO Pandemic Agreement and worked closely with ministries of health and WHO during outbreak responses, convening African regulators as part of the African Medicines Agency launch IPD convened a regional conference as part of Centenary events in Dec 2025; is a member of Africa CDC’s diagnostics working group; supported regional outbreak response to mpox ISARIC researchers presented at the WHO’s filovirus Collaborative Open Research Consortium (CORC) in September 2025, following the EVD outbreak in DRC
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27 | Assumptions
Improved arrangements for inclusive governance and equitable partnerships, and capacity strengthened with LMIC partners and networks | LMIC governance and leadership strengthened | Planned | 0 | n/a | ISARIC and CEPI governance reforms demonstrating strengthened LMIC governance | ISARIC and CEPI governance reforms demonstrating strengthened LMIC governance | Partner governance reforms demonstrating strengthened LMIC governance | Partner governance reforms demonstrating strengthened LMIC governance | Potential partnerships include IPD, IVI (via PDP call), ISARIC (with Wellcome and BMGF), UKRI/MRC (fast track mechanism as part of clinical trials partnership), new OneHealth partnership with UKRI
|  | Achieved |  |  | Elections to new ISARIC Executive Board completed in July 2024 and met in Ghana in September 2024; including the chair and deputy chair and leaders of the four regional hubs (Brazil, Ghana, Pakistan and the Philippines). CEPI’s Board includes LMIC independent and investor members; new Africa CDC MOU | ISARIC Executive Board, led by an LMIC chair has met monthly, with 49% of membership now from LMICs; CEPI recruited additional LMIC senior management and Board members
Source
Partner reports and CEPI MTR
| Output Indicator 3.2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Evidence for equitable LMIC partnerships, leading on research agenda setting and management | Planned | No hubs operational CEPI has 20% partnerships in LMICs No IPD FCDO partnership | n/a | Two ISARIC hubs operational and able to independently manage projects and data/quality management CEPI providing narrative evidence for equitable LMIC partnerships Progress on IPD partnership, to be finalised by March 25 | Four ISARIC hubs operational and able to independently manage projects and data/quality management CEPI providing narrative evidence for equitable LMIC partnerships IPD partnership and logframe agreed | TBD | TBD
|  | Achieved |  | n/a | ISARIC currently comprises 67 voting member networks spanning 140 countries, with 31 (46%) based in LMICs and over 3,000 clinical research sites. Ghana and Brazil hubs are managing projects, Philippines and Pakistan underway. Out of 149 CEPI partners, 39 of these are with LMIC-based companies and research organisations. IPD partnership on track | ISARIC currently comprises 78 voting member networks spanning 140 countries, with 49% based in LMICs; Philippines and Pakistan hubs now active, along with Ghana and Brazil (4 total); Out of 149 CEPI partners, 39 of these are with LMIC-based companies and research organisations. IPD partnership signed in March 2025, and launched in September by FCDO Minister; logframe agreed
Source
Partner reports and CEPI MTR
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| No of partners and research sites adopting and using systems and tools for quality and timely research | Planned | Minimal use except for COVID 19 protocols | n/a | At least 2 sites independently operational on ISARIC systems with clinical characterisation and data management activities devolved and led by LMIC-based institution | At least 10 sites independently operational on ISARIC systems with clinical characterisation and data management activities devolved and led by LMIC-based institution
25% |  | Achieved |  | n/a | ISARIC worked with Nigeria CDC and MoH Rwanda to implement mpox eCRF MpoxRec is partnering with ISARIC and will include mpox clinical characterisation protocol and eCRF in all studies | Documented use of ISARIC tools across 30 institutions in LMICs, mainly dengue and Nipah research sites. MpoxRec is partnering with ISARIC and will include mpox clinical characterisation protocol and eCRF in all studies
Source
Partenr reports and CEPI MTR
| Output Indicator 3.4 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| No of LMIC researchers attaining specialised competencies in outbreak response research for emerging infectious diseases | Planned | 0 | n/a | 40 LMIC-based researchers per year receiving specialised training in clinical research during outbreaks | 40 LMIC-based researchers per year receiving specialised training in clinical research during outbreaks | 40 LMIC-based researchers per year receiving specialised training in clinical research during outbreaks | 40 LMIC-based researchers per year receiving specialised training in clinical research during outbreaks
|  | Achieved |  |  | 15 researchers (over six months) from Ghana and Cameroon received CREDO (Clinical Research During Outbreaks) training in September 2024. Participants were mentored as they finalised research plans focusing on Marburg, Mpox, and Disease X. | 72 LMIC-based researchers from 6 countries completed Clinical Research During Outbreaks (CREDO) training.
Source
Partner reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27 | Assumptions
Global,regional and UK epidemic research is co-ordinated and collaborative action facilitated, both during and between outbreaks, contributing to strengthened prevention, preparedness and response led by LMICs | Effective international co-ordination for epidemic R&D tools and investment among major partners and stakeholders in line with 100DM, including FCDO contribution to xHMG GHS R&D investment approach | Planned | 0 |  | At least three narrative examples illustrating co-ordination between CEPI, ISARIC, and other partners; and effective UK co-ordination | At least three narrative examples illustrating co-ordination between CEPI, ISARIC, and other partners; and effective UK co-ordination | At least three narrative examples illustrating co-ordination between CEPI, ISARIC, and other partners; and effective UK co-ordination | At least three narrative examples illustrating co-ordination between CEPI, ISARIC, and other partners; and effective UK co-ordination | Political will, regional demand and interest, continued commitment to PPR
|  | Achieved |  | Centre scope of work agreed and drafted, decision on procurement strategy to be taken in early 2024; | 1 CEPI’s Global Pandemic Preparedness Summit, Brazil July 2024 and co-develop and launch WHO viral families approach to R&D prioritisation; 2 CEPI launches global biosecurity R&D compact 3 CEPI and ISARIC agree MOU for clinical trials 4 Members of the FCDO Health Research Team chair xHMG international funders group, and meetings with external partners; contributed to xHMG process to implement PPR R&D Framework and research gaps and priorities for Marburg and mpox PHEIC response 5 FCDO co-chair for PDP Funders Group | 1 CEPI convened events at CoP30, the World Health Summit, and Bio2025 to promote biosafety and biosecurity, and published its Biosecurity Strategy 2 IPD and UKHSA agreed an MOU to work together on pathogen assays and standards, and diagnostic and vaccine development 3 UKHSA leads WHO CORCs for two viral families, including RVF co-led with IPD 4 CEPI, IPD and ISARIC working together on phase 2 vaccine trial for RVF in Senegal, with MRC Gambia 5 FCDO Health Research Team convenes xHMG international funders group and meets with partners (WHO, GLoPID-R) ; published xHMG PPR R&D Framework includes international components 6 Effective leadership and convening across government for R&D response to PEGASUS, the national pandemic simulation exercise in 2025, engaging CEPI and ISARIC as players 7 FCDO co-chair for PDP Funders Group
Source
Partner reports and MTR, announcements in the public domain
| Output Indicator 4.2 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| FCDO and UK government rapid response R&D mobilisation and delivery | Planned |  | Scope of work and procurement strategy agreed for Centre for Research; outbreak response | Progress on research response facility; effective outbreak response demonstrated | Multi Hazard Research Network operational; effective outbreak response demonstrated | Multi Hazard Research Network operational;effective outbreak response demonstrated | Multi Hazard Research Network performing well; effective outbreak response demonstrated
|  | Achieved |  | Members of the FCDO Health Research Team have held regular meetings across the FCDO and HMG, and with external partners; contributed to xHMG process to agree PPR R&D Framework and research gaps and priorities | Agreed with FCDO CSA that centre should be part of the new Science for Emergencies Centre of Expertise and Multi Hazard Research Network; scope of work drafted; competition due 2025 (led by CSA Science Cell) Two outbreak R&D responses effectively mobilised, co-ordinated and funded (mpox, DRC etc, and Marburg, Rwanda) | Multi Hazard Research Network call in mid 2025, led by Science Cell, selection due early 2026, launch planned for q1 2026; MHRN includes a pillar for emerging infectious diseases, and is part of the new Science for Emergencies Centre of Expertise Two outbreak R&D responses effectively mobilised, co-ordinated and funded (Ebola, DRC; RVF, Senegal); mpox response portfolio progresses
Source
Partner reports and announcements in the public domain
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 2022/23 | Milestone 2023/24 | Milestone 2024/25 | Milestone 2025/26 | Target 2026/27
| Progress made on partnerships and platforms to implement GHS programme approach for LMIC-led research on epidemic and outbreak diseases | Planned |  | Objectives and draft proposals/concept notes agreed for at least two new institutional partnerships, PDP engagement as needed, including PDP Funders Group Partnership agreements underway with MRC and Wellcome PDP call launch in December 2023 | Progress on at least two new LMIC-led institutional partnerships and PDP procurement; progress on funder partnerships and joint platforms | Two new LMIC-led institutional partnerships and PDPs underway; progress on funder partnerships and joint platforms | Partnerships and platforms performing to plan | Partnerships and platforms performing to plan
25% |  | Achieved |  | Partnerships with IPD and ISARIC agreed PDP call launched; FCDO co-chair and leader for PDP Funders Group MRC concept note and business case drafted Wellcome dialogue progressing Joint approach clinical research funding with DHSC, NIHR, UKRI, MRC and Wellcome | 1 New partnership progressed with Institut Pasteur de Dakar, Senegal, with proposal agreed October 2024 2 New partnership completed with ISARIC (International Severe Acute Respiratory and emerging Infection Consortium) through Oxford’s Pandemic Science Institute with Wellcome and BMGF; Plus PDP call launched in December 2023, completed in December 2024 MRC concept note agreed and strategic approach drafted; Wellcome partnership drafted and agreed in principle | 1 New accountable grant with Institut Pasteur de Dakar, Senegal, March 2025, and high level launch in Sept 2025 2 ISARIC Board led by FioCruz Chair, supported through Oxford’s Pandemic Science Institute with Wellcome and BMGF; 3 New PDPs include three with emerging infectious disease components 4 MRC Concordat includes scope for emergency response and two projects funded; Wellcome partnership drafted and agreed in principle but agreement on financial and legal clauses needed
Source
Partner reports and announcements in the public domain
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indicator 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Yr 1 logframe amended and 3 outputs added |  | Nel Druce, SRO | 2024-06-05
2
3
4
5
6
7
8
9
10

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.