## Annual Review Template

Title: UK National Commission for the United Nations Educational Scientific and Cultural Organisation (UNESCO)
Programme Value £ (2022-2026): £1,316,000		Review date: October 2025
Programme Code: 301547	AMP start date: August 2022	AMP end date: March 2026

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A+	A+	A+
Risk Rating	Minor	Minor	Minor

DevTracker Link to Business Case:	D0003189
DevTracker Link to results framework:	D0003285

A. SUMMARY AND OVERVIEW

Description of programme

The Foreign, Commonwealth & Development Office (FCDO) is the lead department for the UK relationship with the United Nations Educational, Scientific and Cultural Organisation (UNESCO). Article VII of the UNESCO Constitution requires that Member States have a ‘National Cooperating Body’ the purpose of which is to link government with the intellectual and scientific communities in that country working in UNESCO’s fields of competence.

This programme funds the UK’s ‘National Cooperating Body’ which in the UK is the National Commission for UNESCO (UKNC), and which is run as a not-for-profit organisation. The UKNC coordinates independent expert advice and representation to enable FCDO and wider HMG to maximise the potential value for money of UNESCO’s work.

As set out in the business case, the UKNC’s accountable grant from the FCDO funds the following functions of the UKNC:
1. Support the UK Government in achieving its objectives through UNESCO.
2. Support UK society and communities to maximise the benefits of UNESCO’s mission and programmes.
3. Support UNESCO to be a competent and relevant UN agency able to deliver its mission and fulfil its objectives.

The UK National Commission is funded through an accountable grant, providing for a small secretariat which supports up to nine pro bono Non-Executive Directors and the provision of pro bono advice/expertise to government from a network of scientists, experts, and leaders in the fields of UNESCO competence. Each Director specialises in one of UNESCO’s programme areas. The Board is led by the Chair, elected for a period of three years (renewable), and meets on a quarterly basis to oversee the work of the National Commission and to monitor progress against the delivery framework. FCDO attends the open session of the Board alongside representatives of all government departments with an interest in UNESCO, are invited to attend open sessions of the Board meetings.

Summary supporting narrative for the overall score in this review

This year the programme has again scored A+ and is on track to achieve the outcome of the programme, due for completion in 2026. An overall programme completion review (PCR) will be completed in 2026.

The UK National Commission continues to be performing well, providing helpful inputs and advice to HMG's UNESCO-facing work both on the policy and diplomatic sides, and important support to the UK's UNESCO designations. It is a small organisation, with a core grant of only £355,000 per annum. It has achieved an A+ in two of the three outputs, and an A in one of the outputs and so within that context we judge it has achieved an A+ overall.

However, while achieving milestones across all indicators, the UK National Commission has not yet achieved all its output indicators as set out in the framework. With continued work over the coming months, we assess that the UK National Commission can achieve these goals by programme end in March 2026.

Major lessons and recommendations for the year ahead

Going forward the FCDO continues to expect the UKNC’s work to cover the core areas of UNESCO competence (Education, Natural Sciences, Culture, Social and Human Sciences and Communication and Information) in line with the functions set out in the business case (and above). In particular, the UKNC should:

Develop a more strategic and prioritised approach – outlining more clearly how UKNC adds value to the UK, and with its limited resources, ensuring it focuses on key UK Government priorities and avoiding being spread too thinly or becoming consumed by less pressing issues.

Strengthen partnerships with relevant HMG officials and, where appropriate Devolved Administrations, relevant to UNESCO’s mandate. Closer collaboration will ensure UKNC’s activities are better integrated with national policy priorities, enhance coherence in the UK’s international position and give access to valuable expertise and resources.

Enhance UKNC’s visibility and strategically communicate with HMG the relevance and opportunities of UNESCO and any new programmes with impact to UK Government departments, and, as appropriate, to Devolved Administrations, Overseas Territories and Crown Dependencies, as well as UNESCO designated sites, civil society, academic institutions, and the broader UK public.

Continue to build the network of the UK academic and expert community with an interest in UNESCO competences and facilitate exchange both with UK government policy officials and UNESCO.

Maintain a focus on providing high-quality expert and technical expert advice to FCDO and across HMG on specialist issues in the UNESCO areas of competence.

Carefully consider how to provide support to UK designations in a sustainable and consistent way.

Recommendations will be shared with UKNC upon receipt of the annual review and formally presented during a subsequent meeting.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The UK National Commission has developed strong expertise in UNESCO’s area of competence and a broad network of experts in the UK. It serves as an example of how a national commission can leverage its influence, and is regularly called upon for advice from HMG, UK UNESCO designations, other National Commissions and the UNESCO Secretariat.

There have been no changes to the business case. The key strategic assumptions, expected results and challenges identified in the original Business Case remain applicable now. The principal strategic assumptions are:
- The programme will continue to align with UK legislation and policy frameworks, particularly around gender equality, disability inclusion, and protected characteristics.
- It will maintain robust financial management and reporting practices, ensuring low risk of misuse of funds
- UKNC remains environmentally sustainable and supportive of UNESCO’s biodiversity and climate resilience goals.
The key expected results are:
- UKNC will enhance UK policy making within the FCDO and other government departments by drawing on the expertise of UK non-governmental networks.
- The UKNC Secretariat, pro-bono directors, and expert networks, including UNESCO Chairs, will also support UK policy objectives by advising the UNESCO Secretariat, engaging with other countries’ National Commissions, and representing the UK in UNESCO fora.
The main challenges identified are:
- Demands from HMG for UKNC support may increase in response to geopolitical developments, such as international crises or shifts in global priorities, or domestic policy changes that elevate the importance of UNESCO-related work.
- UKNC may not secure the necessary additional funding to support UNESCO-designated sites across the UK, which could place significant strain on the small secretariat to meet both policy and operational commitments within the existing grant envelope.

The programme fulfils the UK’s constitutional obligation as a member of UNESCO to maintain a National Commission. This programme funds a small Secretariat which facilitates HMG access to non-governmental UK expert communities across UNESCO’s fields of competence on a pro-bono basis. The UKNC Secretariat and expert networks provide policy advice to government departments and represent the UK on technical UNESCO committees and in negotiations, enabling the UK to influence and shape multilateral policy discussions and normative instruments across education, science, culture, information and communication. There are different ways of configuring a National Commission. This programme implements the UK National Commission in a way that ensures independence from government, which provides additional benefits when engaging with external stakeholders, and also secures value for money.

The UKNC Secretariat is expected to report against its delivery framework on a quarterly basis to both the FCDO and its Board. Performance and progress of the UKNC programme must be punctual and clear in its delivery.

The delivery framework sets out key objectives that the UKNC is expected to provide evidence against, across its core aims of supporting the UK Government to achieve its policy objectives at UNESCO, supporting UK society and communities to maximise the benefits of UNESCO’s mission and programmes, and supporting UNESCO to be a competent and relevant UN agency.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The National Commission has made meaningful progress towards achieving the programme’s intended outcomes and impact. While a few output indicators outlined in the framework are still in progress, the overall risk level remains minor, as confirmed in the business case, reflecting a strong foundation for continued success.

The UKNC has shown itself to be an agile and effective organisation, and one which HMG can rely upon, for example, UKNC provided expert support in the preparation and negotiations of the Ethics of Neurotech negotiations, which enabled the UK to achieve an outcome that protected priorities. The UK Delegation noted that the UKNC plays a crucial role in supporting the Executive Boards, offering regular advice that is indispensable to the work, particularly in terms of supplying expertise. During expert meetings, they often provide specialists or tap into their supportive networks to ensure informed contributions.

However, due to the small size of the secretariat, they run the risk of taking on too much without clearly articulating the value. We will explore this challenge during the design of the next phase of UK support for UKNC.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This programme which funds the UKNC should continue for three reasons. Firstly, the UKNC is a constitutional part of the UK’s membership of UNESCO, and as noted above, this model of National Commission provides the UK with value for money and independence from government. Secondly, UKNC continues to achieve its objectives and met milestones across the three outputs in the delivery framework. Thirdly, UKNC continues to play a pivotal role in enabling HMG to effectively achieve its responsibilities under the UNESCO framework, ensuring that the UK’s commitments are met through coordinated policy implementation, strategic engagement, and expert support across relevant sectors

## C. DETAILED OUTPUT SCORING
Output Title	Support the UK Government in achieving its objectives through UNESCO
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	Yes, down

Indicator(s)	Milestone(s) for this review	Progress
UK Government Departments and experts understand UNESCO’s normative and technical work, clearly understand its strategy, role, aims, and objectives, and how they align with their work and other multilateral agencies.	UKNC works with FCDO to maintain a strategic review of UK government policy priorities in the context of the / UNESCO Medium-Term Strategy (2022-29) and Programme Budget. / UKNC coordinates two UNESCO Executive Boards, ensuring government departments know about developments and opportunities. / UKNC better communicates UNESCO’s role and programmes to UK Government.	In Progress / UKNC updated and maintains the strategic mapping exercise of the UK Government and experts at UNESCO to reflect departmental changes and policy priorities. / UKNC met with Ministers from FCDO, DfE and MHCLG to explain their role and showcase UNESCO’s work. UKNC will continue to engage with new Ministers following the reshuffle in September 2025. / UKNC provided HMG with coordination and expert advice for the 221st and 222nd UNESCO Executive Boards in April and October 2025 respectively, including recommendations for multiple UNESCO draft Resolutions. UKNC also supported in writing interventions based on the advice received from experts and maintained good information management. UKNC is preparing work on the General Conference.
Government policy leads work with UKNC and its experts to influence decisions at UNESCO.	UKNC conducts a strategic review to look at how it can work with the UK Government and Civil Society to influence and shape UNESCO's programmes. / UKNC supports the implementation of the 2019 UNESCO Global Convention on the Recognition of Qualifications Concerning Higher Education and explores how it can influence its integration and profile across the UK.	In Progress / UKNC has been advising DfE officials and Minister Smith on the work of the 2019 UNESCO Global Convention and supported the UK in its re-election to maintain the Bureau seat for the Convention. / UKNC hosted the national UK UNESCO Chairs Conference at the University of Portsmouth, in partnership with the Ocean Chair in Ocean Governance considering how to mobilise UK UNESCO Chair expertise. There was participation by 21 UK UNESCO Chairs, FCDO, Department for Education (DfE) and Arts and Humanities Research Council (AHRC). / In support of the indicator, UKNC provided expert support in the preparation and negotiations of the Ethics of Neurotech negotiations, which enabled the UK to achieve an outcome that protected priorities.
Government policy leads work with UKNC and its experts to shape domestic policies and processes in fields of UNESCO competence.	UKNC assists DCMS in reviewing and ratifying the Intangible Cultural Heritage Convention. / UKNC to give broad strategic advice and direction to DCMS on the implementation of the 1972 UNESCO World Heritage Convention.	In Progress / UKNC is supporting DCMS in the implementation of the 2003 UNESCO Convention on Intangible Cultural Heritage Convention in the UK and will host the inventory on its website. / UKNC provides ongoing support, including through the World Heritage Advisory Group, including join-up with other stakeholders as appropriate.

Briefly describe the output’s activities and provide supporting narrative for the score.

UKNC has supported the UK government with policy work across UNESCO competences – with outputs against most of the milestones in the last year. However, there is more to be done to achieve Indicator 1.1 in communicating how the UK government can use UNESCO effectively and Indicator 1.2 on conducting a strategic review with government and civil society. Would be beneficial for UKNC to adopt a more strategic approach that is aligned with government priorities, ensuring that efforts are concentrated where they will have the greatest impact, rather than being spread across too many areas. Given this, it is marked as an A.

It remains essential for UKNC to continue enhancing its visibility and communications with UK Government in order to maximise its ability to achieve Indicator 1.1. Given the small size of secretariat, UKNC needs to strategically prioritise its work to meet UK government objectives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery. The weighting will be kept under review during the next performance year, in light of the UKNC’s delivery framework and shifting HMG priorities. The indicators and milestones will be reviewed in the delivery framework for the next business case to ensure that they accurately reflect HMG priorities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In the previous annual review (2023-24), FCDO encouraged the UKNC to continue to communicate the relevance and opportunities of the new UNESCO Medium-Term Strategy, expand links with UNESCO-relevant policy teams and experts across HMG, consider how best to provide the current level of support to both new and existing UK UNESCO designations within the constraints of Secretariat resources and, based upon cross-Whitehall feedback, improve internal and external communications at UNESCO. While progress has been made upon these recommendations, they have not yet been wholly achieved.

Going forward, UKNC should continue to maintain a focus on providing high-quality expert and technical advice to FCDO and across HMG on specialist issues in the UNESCO areas of competence as well as carefully considering how to provide support to UK designations in a sustainable and consistent way.

Output Title	Support UK society and communities to maximise the benefits of UNESCO’s mission and programmes
Output number:		2	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	Yes, up

Indicator(s)	Milestone(s) for this review	Progress
UKNC provides high quality and consistent support to all accredited and aspiring UNESCO designations in the UK, Overseas Territories and Crown Dependencies	UKNC provides support to UK individuals and organisations seeking UNESCO accreditation. / UKNC provides service-level support to the UK's UNESCO designation network, per its constitutional role as a National Commission.	In Progress / The UKNC is supporting Stoke and Stockport with their 2026 Creative Cities bids and has provided feedback to Newcastle and Hull on their 2025 applications. It helped establish new terms for the UK UNESCO Global Geoparks (UGG) Committee, submitted letters of intent for Charnwood Forest and Cross-Channel Geoparks, and supported the incoming Chair. UNESCO patronage was granted to the Royal Institution, the Great Science Share, and the Greater London Authority. Five applications for the Global Citizenship Education Prize are under review, with three to be submitted to UNESCO. / UKNC continues to provide branding support for all existing and potential UNESCO designations. / Arran became a Global Geopark and the works of Charles Darwin were inscribed on the Memory of the World programme in April 2025.
Share best practice between UK designations as well as internationally.	UKNC supports cooperation between UK and international designations, including webinars, funding opportunities and support	In Progress / UKNC continues to provide ongoing support and development, including co-convening national meetings (revalidation, requests, visits etc) / UKNC co-chaired National UK Creative Cities and Man and Biosphere meetings, linking to HMG and Overseas Territories funding opportunities.

Briefly describe the output’s activities and provide supporting narrative for the score.

UKNC made progress on this output by actively supporting several UK designations and the UK was successful in two of its inscriptions. This explains the A+ rating. UKNC has already made strides on Indicator 2.2 and now has an opportunity to further advance this work by continuing to share best practice across UK networks and internationally.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

With the end of the Climate Change and UNESCO Heritage project in October 2025, and Local to Global entering Phase 2 of its programme for 2025-26, UKNC will need to carefully consider how it provides ongoing support to designations in the future in a sustainable and consistent way. The weighting will be kept under review during the next performance year, in light of the UKNC’s own delivery framework and shifting HMG priorities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

It is recommended that UKNC continues to enhance its visibility and strategically communicates the relevance and opportunities of UNESCO and its impactful new programmes. This should be done through targeted engagement with UK Government departments, Devolved Administrations, Overseas Territories, Crown Dependencies, UNESCO designated sites, civil society, academic institutions, and the wider UK public. Such an approach will ensure that key stakeholders are well-informed and positioned to benefit from these initiatives.

Output Title	Support UNESCO to be a competent and relevant UN agency able to deliver its mission and fulfil its objectives
Output number:		3	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	Yes, down

Indicator(s)	Milestone(s) for this review	Progress
UKNC plays a leading role in the development and direction of the National Commissions global network, ensuring it is relevant, efficient, focussed on priority UNESCO issues, and positively influences UNESCO programming.	With the UNESCO National Commission’s Unit and other National Commissions, utilise the tripartite UNESCO processes in the UK interest, such as consultation in the Medium-Term Strategy 2022-29; and informal and interregional meetings of National Commissions.	Ongoing / UKNC continued to influence, develop and explore best-practice guidelines and influence the agenda in the UK interest for UNESCO National Commissions, UN Regional and Interregional Meetings.
UKNC supports UK reform priorities in UNESCO fora, influencing the Secretariat directly, and indirectly through the global network of National Commissions.	Help ensure that National Commissions play their constitutional role in holding UNESCO to account and contribute to consultations, such as that on the 2022-29 Medium Terms Strategy. / UKNC continues to support the reform of the NGO Liaison Committee and its integration and relationship with the National Commission network.	In Progress / UKNC supported the development of text for Executive Board decision language to support National Commission’s constitutional role.

Briefly describe the output’s activities and provide supporting narrative for the score.
UKNC has continued to work closely with other National Commissions, particularly in shaping best-practice guidelines across UNESCO platforms and supporting the integration of new National Commissions in New Zealand, Australia, and Malta. UKNC continues to support UK reform priorities at UNESCO by helping ensure that National Commissions play their constitutional role in holding UNESCO to account, including by supporting in the development of text in Executive Board decision language.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery. The weighting will be kept under review during the next performance year, in light of the UKNC’s own delivery framework and shifting HMG priorities. With UN80 and changing UK reform priorities in the UN system, the relevance of this output will be reviewed in the next business case and delivery framework.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

To ensure its limited resources are used effectively, the UKNC should adopt strategic prioritisation to avoid overextension and focus on activities with clearly defined value. This approach would support deeper collaboration with government departments on UNESCO related advice, while also enabling the UKNC to expand and strengthen its expert network to better respond to emerging priorities and opportunities.

The UKNC should maintain and strengthen its outreach efforts with the UK academic and expert community. This will help to cultivate and sustain a robust network of pro bono expertise, ensuring that the knowledge and advice available remain both relevant and of consistently high quality.
## D: VALUE FOR MONEY

The original business case set out key indicators of value for money that the UKNC would be expected to evidence. These include:

- How well the UKNC meets the objectives and targets in its delivery framework lies above under Outputs 1 to 3 we can see that the UKNC has made significant progress on all its Outcomes while the programme runs with a modest budget of £355,000 per annum;
- How effectively UKNC responds to changing government priorities. We confirm that the UKNC is responsive to FCDO and Government requests for advice and support, reaching out to its wide network of experts and providing timely advice when asked;
- The estimated equivalent value of pro-bono policy support provided by its expert network. This is hard to calculate in quantitative terms, it is clear that the UKNC delivers access to highly qualified academics and experts across the UK and across specialist subject areas. The active participation of all the pro-bono non-executive Directors on the Board and at UNESCO events including negotiations shows that UKG receives good value for money.

Evidence is also provided by the UKNC on a quarterly and annual basis in the form of reports that outline progress made against the delivery framework, to assess the degree to which UKNC are furthering the delivery of their priorities at UNESCO.

While the UKNC Secretariat remains small, and expertise offered by the broad network is provided on a pro-bono basis, the UKNC is an active and influential National Commission at UNESCO, and the wider network of National Commissions continues to regard the UKNC well.

E: RISK

The overall risk for the programme remains minor.

Currently there is one major risk for the programme and four moderate risks. The major risk concerns unforeseen demands for support by HMG outstripping the capacity or capability of the UKNC.

The moderate risks are as follows:

1. Ongoing internal FCDO payments system (HERA) problems result in lengthy and unpredictable delays in payments to the UKNC, leading to depletion of the organisation's reserves and threatening the ongoing viability of the UKNC.
2. The UKNC is exploited by its staff, Directors or members of its expert network for personal gain, political purposes, or as a platform to publicly oppose Government policy.
3. The UK expert network becomes unable or unwilling to provide Government with quality, pro bono advice or representation across one of more fields of UNESCO competence.
4. Provision of the grant is subject to the UKNC being registered as a not-for-profit organisation with the capacity to comply with the requirement set out in the Accountable Grant Arrangement. There is a risk that members of the network use the provision of expert advice to the UKNC as a means of lobbying.

Despite the pressure on resources, the UKNC continues to deliver to a good standard, but to ensure that the major risk is continued to be mitigated, the National Commission is requested to strategically prioritise its activity and spending. Ongoing recruitment for Non-Executive Directors will ensure that there is expert policy advice across all areas of UNESCO competence.

The next delivery framework should be designed with a view to guiding prioritisation within UKNC, in line with strategic HMG equities and wider UKNC objectives.

Attendance at open sessions of UKNC Quarterly Board meetings by the FCDO programme Senior Responsible Officer and Programme Manager, the UK Permanent Delegate to UNESCO, and relevant policy leads from other government departments will support the identification of pinch points and appropriate prioritisation. Regular meetings between FCDO and the UKNC Secretary General have also been instated to foster regular dialogue around risks and prioritisation. The FCDO will also need to ensure that funding under the Accountable Grant is provided on time and in line with pre agreed payment schedules to mitigate risks.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Key costs incurred by UKNC include the Secretariat staff’s salaries, rental of the office space in London and associated running costs, and travel expenditure. Advice from the UKNC’s experts is provided on a pro-bono basis with reimbursement of expenses to individuals. All core costs are covered by the annual £355,000 accountable grant. The UKNC was able to support the establishment of a Communications role from alternative funding. This post was important for UKNC to provide effective communications about its and UNESCO’s role in the UK, and opportunities for the UK at UNESCO. Future business cases will consider the funding required for this role.

The Accountable Grant is paid, in advance, on a quarterly basis. This is authorised following presentation of spending for the previous quarter and a breakdown of costs forecast for the following quarter. The UKNC accounts are subject to an Annual Audit.

G: MONITORING, EVIDENCE AND LEARNING

Throughout the review period, both the PRO and SRO maintained oversight of UKNC’s performance by convening regular meetings, participating in quarterly open Board sessions, and assessing feedback from both internal and external stakeholders. UKNC demonstrated progress towards the objectives outlined in the delivery framework through the submission of updates, which should be on a quarterly basis, each supported with relevant evidence to indicators.

This Annual Review was conducted by FCDO officials drawing from documentation submitted by the UK National Commission, as well as from feedback from colleagues in the UK Permanent Delegation to UNESCO and from those within the UK National Commission itself.

Date of last narrative financial report		Date of last audited annual statement