## Annual Review Template

Title: Ghana Governance Programme
Programme Value £ (full life): 4,950,000		Review date: 22 May 2025
Programme Code: 301562	AMP start date: 22 May 2024	AMP end date: 21 May 2029

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301562 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301562 Documents

A. SUMMARY AND OVERVIEW

Description of programme
The Ghana Governance Programme (GGP) is a £4.95m programme for five years to support better elections, drive organised civil society demand for accountability and enhance state capacity for improved transparency and accountability in Ghana. The programme is delivered in-house through accountable grants to Civil Society Organisations (CSOs) and technical assistance to state actors. Delivery is anchored on effective collaboration with Centrally Managed Programmes (CMPs) and other Development Partners (DPs) interventions to promote complementarity and coherence.

The expected outcomes of the programme are:

1. Reforms and improved practices strengthen elections in 2024 and 2028.
2. Reforms and improved practices strengthen transparency, accountability and human rights and reduce corruption.
3. Increased protection (in principle and practice) of the political and civil rights of all persons in Ghana (e.g. PWDs, LGBT+, journalists).

These outcomes are expected to lead to an effective governance system that is transparent and accountable and protects civil and political rights (impact).

The approval of the Business Case was granted in May 2024, seven months before the Presidential and Parliamentary elections. As a result, the programme focused on delivery of election support while building the grounds for post-election accountability interventions. During this annual review period therefore, the programme was delivered by the following partners;

- UNDP managed election support to two Election Management Bodies (EMBs) – the National Peace Council (NPC) and the National Commission for Civic Education (NCCE). The focus of the interventions of these state actors were to promote peaceful and credible elections through voter education and stakeholder dialogues including the signing of National Peace Pact.
- The Centre for Democratic Development (CDD) delivered domestic election observation involving the Coalition of Domestic Election Observers (CODEO) and post-election consultations with citizens to gather inputs for the new government’s policy agenda.
- The Africa Centre for Energy Policy (ACEP) in collaboration with Transparency International, Ghana (TI Ghana) and the Ghana Anti-corruption Coalition (GACC) delivered a campaign to elicit anti-corruption commitments from candidates of the election.
- The IMANI Centre for Education and Policy evaluated the manifestos of the two major political parties and two minor ones and stimulated public debate on the reasonability and feasibility of the campaign promises.
- BHC Accra delivered the “Diplowatch” project which deployed 100 staff and coordinated observers from other Diplomatic Missions to observe the elections. Diplowatch and the wider work of the embedded election expert (funded by FCDO’s Integrated Security Fund (ISF)) mobilised technical, political, and wider like-minded diplomatic influence to improve democratic governance, supporting long-term economic growth as a result of greater accountability and political stability.
The programme also made significant progress to respond to requests for technical assistance (TA) from the Judicial Service of Ghana (JSG) and the Office of Special Prosecutor (OSP). Agreement with the International Centre for Asset Recovery (ICAR) at the Basel Institute to provide technical assistance to OSP is awaiting approval while the Rule of Law Expertise (ROLE) UK programme (FCDO Centrally Managed Programme (CMP)) has agreed to take up the judicial support following a country scoping visit.

Context
Ghana successfully held its 9th election of the fourth Republic in December 2024 and saw the transition of power from one political party to another for the fourth time. While Ghana remains the beacon of democracy in Africa, there are concerns about the outcomes of the country’s democracy. Recent Afrobarometer surveys (2017-2024) have pointed to a growing dissatisfaction with the outcomes of democracy although most Ghanaians prefer democracy to other forms of governance. Given the politically unstable context within the West African sub-region and what appears to be popular support for Burkina Faso’s military government, the risk of political instability increases for the country if it fails to meet expectations of its large youth population. As has been the practice with Ghana’s political transitions, the new government has made significant leadership changes including a reduction in the number of ministers and commenced a constitutional process to consider a petition to remove the current Chief Justice.

The December 2024 elections was fought and won on a ‘reset’ agenda. President Mahama has commenced the reset with a constitutional review to address some of the fundamental governance challenges believed to emanate from the 1992 Constitution. The President has put civil society actors (who are GGP partners) in charge of the constitutional review which provides opportunity for GGP to support relevant reforms that will promote good governance. For instance, there are strong public sentiments about using the constitutional review to amend provisions that enable political interference in key state institutions including the legislature, judiciary and constitutional bodies such as the Electoral Commission (EC) as well as law enforcement agencies. The closure of USAID governance programmes in Ghana has left a significant gap GGP cannot and will not attempt to fill. GGP will continue to work with partners to strengthen relevant legislative and institutional frameworks for improved governance.

For Annual Review of programmes undergoing significant adaptation because of reductions in ODA, please include the following standard lines (which should not be changed):

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review
Overall, the programme is meeting expectations having supported a credible election in 2024 and laid the foundation to build capacity and mobilise CSOs to drive demand for reforms and to provide TA to state actors to improve responsiveness.

Table 1: Summary of output Performances
Output	Weighting	Scores
Strengthened capacity and motivation of CSO’s and EMB’s to promote credible and peaceful elections	25 %	A
Enhanced citizens engagement with state institution and processes	30%	A
Enhanced state capacity and motivation to strengthen legislative and institutional frameworks and improve transparency, accountability and human rights as well as reduce corruption.	30%	B
Increased domestic and diaspora voices/actions for protection of rights of all persons in Ghana.	15%	B

The programme met expectations (A) with significant progress on Outputs 1 and 2 during the period under review but underperformed on outputs 3 & 4 partly due to a strategic decision to focus on the December 2024 election for the first eight months. Progress on outputs 3 and 4 were expected to gain momentum after the elections but they were affected by FCDO pause on new agreements. The future of these two outputs (3 and 4) will become clearer after June 2025 when outcome of FCDO’s ODA review will be confirmed for 2025-26. On Output 1 and 2, grants and TA to CSOs and EMBs enabled voter education and intra and inter-party dialogues to address grievances and the signing of Peace Pact to commit political parties to using appropriate means to address grievances rather than resorting to violence. Grants to CSOs enabled domestic election observation and collaboration with EMBs to ensure prompt responses to address salient issues including risk of violence and delays in commencement of voting in hard-to-reach communities. Also, grants enabled engagement between CSOs and political parties to elicit long term commitments to pursue reforms to improve transparency and accountability. These initiatives have laid the foundation for accountability and enabling monitoring of the performance of the new government by CSOs. However, a delivery partner, IMANI has voluntarily withdrawn from engagement while an agreement with STAR-Ghana scheduled to start implementation from the 2025/26 financial year is being stopped due to anticipated impact of ODA reduction.

Despite the delays in commencing Outputs 3 and 4, significant progress was made. For output 3, an Accountable grant agreement with the ICAR is ready for approval while a collaboration with the ROLE UK programme to provide support to the Judiciary is advanced. The agreement with the ICAR will embed a financial investigations expert and draw down on a prosecution expert to provide mentoring on live cases to the OSP and training to 120 investigators and prosecutors of the OSP and EOCO. A scoping report on the judiciary by the ROLE UK programme has made recommendations to support the judiciary as follows;

1. Enhance development collection and sharing of library resources and information management skills for various courts law libraries.
2. Strengthen the capacity of the Judicial Training Institute on curriculum development and delivery of training in specific areas of law and emerging areas of practice.
3. Peer-to-peer exchanges and training on judgecraft.

Major lessons and recommendations for the year ahead

Lessons
- Collaboration of diverse stakeholders, including traditional and faith-based organisations, political parties, the Electoral Commission, security agencies, and traditional leaders, is confirmed as critical for the credibility, richness and scope of the dialogues, and key for ensuring sustainability.
- Engagements aimed to promote gender equality and empower women achieve more impact when organised more frequently, rather than solely in election years and very close to election, to ensure continuous advocacy, awareness and capacity building.
- Strong interest and endorsement in the Pledge Against Corruption (PAC) Campaign from trade unions highlighted the relevance of engaging organised labour as powerful allies for anti-corruption advocacy.
- The inability to commence some interventions underscores the importance of early coordination, flexible partnerships, and adaptive strategies.

Recommendations
Consider submitting a Business Case Addendum by August 2025, to review the scope of the programme. This may include either removing Output 4 (Increased domestic and diaspora voices/actions for protection of rights of all persons in Ghana) or reducing the weighting to reflect a reduced scope. The Business Case Addendum should be informed by outcome of the Country Business Plan (CBP) and conversations with relevant Departments/ Centrally Managed Programmes (CMPs). While the promotion of human rights will remain a key priority for BHC Accra, it may be better delivered through strengthened political influencing, funding from a CMP and in collaboration with other Development Partners (DPs). This will leave GGP to focus on elections and transparency and accountability.

By August 2025, review outcome indicators, output weighting and indicators of Outputs 1 and 2 to reflect a reduction in scope of CSOs workstreams as result of closure of IMANI and STAR-Ghana’s agreements.

Include in ICAR agreement a break clause to manage the risk of reduction in funding from 2027/28 in line with FCDO’s 0.3 ODA commitment. This may require frontloading the most important activities that can gain traction within the first year of implementation to strengthen the VFM proposition of this workstream.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change (TOC), including any changes to outcome and impact indicators from the original business case.

The programme’s goal is to promote an effective, transparent, and accountable governance system that protects civil and political rights. To achieve this, the programme seeks to provide grants to CSOs and technical assistance to state actors to run credible elections, drive organised civil society demand for good governance, build state capacity to address systemic weaknesses that enhance transparency and accountability and reduce corruption as well as advance human rights priorities in Ghana.

The building blocks of the TOC are convening, coalition building, effective influencing, catalysing and ensuring greater gender equality, disability and social inclusion (‘GEDSI’). These are underpinned by regular Political Economy Analysis (PEA) in a fluid manner that enables a Thinking and Working Politically approach. For instance, following the election and the new President’s priority reform agendas, the programme has reviewed its portfolio resulting in ending some plans and reinforcement of others to ensure the programme is well aligned with the priorities of the new government.

The assumptions are that CSOs will be politically neutral, consistent and credible in pursuing advocacy for reforms while state actors will have the political ownership and can be persuaded to adopt reforms. At the lower level, it is assumed that citizens will have the capacity and willingness to engage on key issues. Thus far, CSOs have demonstrated sufficient neutrality, consistency and credibility throughout their advocacy activities while the OSP and Judiciary have shown sufficient commitment to engage. The requests for TA were demand driven with consistent follow up from both state actors. The TOC therefore remains valid although it will be further reviewed as part of the Business Case addendum.

Changes to Outcome - Given the anticipated pressure on ODA following the announcement of reduction from 0.5 to 0.3, the programme may close Outcome 3- Increased protection (in principle and practice) of the political and civil rights of all persons in Ghana (e.g. PWDs, LGBT+, journalists).This decision will be best informed by outcome of the CBP and planned engagements with relevant Departments at the centre as well as other Development Partners (DPs). Regardless of the outcome of these processes, the promotion of human rights will remain a focus for the Political and Governance Team of BHC Accra. If the decision is to close the Outcome 3, the programme will leverage on resources at the centre (e.g CMP) to mitigate the impact. With two CSOs agreements set to close (i.e. IMANI and STAR-Ghana), related indicators will also be reviewed. Essentially, against reduced ODA, the programme will focus on support to two CSOs and the OSP and build strong partnerships with CMPs (such as Rule of Law Expertise (ROLE UK) and Fiscal Transparency and Accountability Initiative (FTAI) to provide complementary support. The programme will also ensure strong alignment with other CMPs and other DPs programme to mitigate the impact of the reduced scope.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is broadly on track to achieve its outcomes but has mixed feedback on progress towards impact. Impact is measured by Ghana’s performance on the Corruption Perception Index (CPI) and level of satisfaction with democracy. Ghana dropped one point to 42/100 (from 43/100 in 2023) on 2024 CPI and is ranked 80th out of 180 countries compared to 70th in 2023. While Afrobarometer assesses level of satisfaction every two years with the next one due in 2026, a recent post-election poll by Global Info Analytics ((GIA)April 2025) showed high approval of the government. 60% of Ghanaians expressed satisfaction with the 2025 budget, a key indicator that directly influenced the public’s approval of both the President and his government, according to GIA. The current President’s 66% approval rating provides a baseline for measuring impact year on year. High public rating of a new government is however common, with the previous government gaining 62% approval at the end of the first year in January 2018; but declining to 36% by 2024.
[note] Mussa Dankwah justifies Mahama’s strong approval in latest survey - Channel1 News

The programme has made significant progress towards achieving outcome 1 and 2 but has lagged on its progress towards achieving outcome 3, as evidenced below.

Outcome 1: Reforms and improved practices strengthen elections in 2024 and 2028. / Indicators; / Level of influence of CSOs supported by GGP to impact elections in 2024 & 2028 / Level of Electoral Management Bodies capacity and preparedness to conduct the elections.

On outcome 1 indicators 1 and 2, the capacities of CSOs (e.g. CODEO, CDD), NPC and NCCE were enhanced to deliver their mandate to promote credible elections. Support from the programme enabled engagement on electoral processes, voter education and inter and intra-party dialogues to agree on the rules of the game to strengthen the electoral processes. For instance, commitment to the Peace Pact was acknowledged by the Presidential candidate of the NPP (the then Vice President) in his concession speech.

Outcome 2: Reforms and improved practices strengthen transparency, accountability and human right and reduce corruption. / Indicators; / Number of CSOs supported by GGP that have able to influence reforms and improved practices to strengthen strengthened transparency and accountability / Number of asset recovery cases investigated and successfully prosecuted.

Progress was also made towards achieving outcome 2 indicator 1 through support to CSOs (ACEP consortium, IMANI and CDD) in mobilising citizens to engage duty bearers on their anti-corruption commitment prior to the elections and on influencing post-election policy agenda. For instance, the EMBs are currently collaborating with CSOs (e.g. NPC and CDD) to plan a multi-stakeholder post-election review to agree on reform proposals to take forward ahead of election 2028. CDD has also worked with the three reform agendas commissioned by the President (i.e. Constitutional review, economic dialogue and educational forum) to formulate questions for the nationwide consultations to gather citizens views on the reforms being pursued. Subsequently, CDD has engaged members of the three committees in charge of the reform agendas to share relevant findings of the consultation. One notable finding from the consultation was citizens’ suggestion to have the Council State abolished or reformed by the constitutional review exercise. Indicator 2 was not achieved due to delay in signing the agreement with ICAR. However, good progress was made in building partnership with OSP and ICAR; and agreeing on the scope of intervention. A ministerial exemption has been secured for spend until end of June 2025 when clarity on FCDO Ghana’s 2025/26 allocation will be confirmed.

Outcome 3: Increased protection (in principle and practice) of the political and civil rights of all persons in Ghana (e.g. PWDs, LGBT+, journalists). / Indicator; / Ghana’s score/rating on the Civicus monitor

The programme lagged on its progress towards achieving outcome 3. A delivery partner was not identified during the time under review due to the strategic decision to focus on the elections in the first eight months of the programme’s life and subsequent FCDO pause on new agreements. However, the context for this Outcome has since changed following a change in government. Currently, issues of human rights in Ghana are evolving and therefore further engagement with relevant stakeholders is recommended to inform approach. The Civicus Monitor has since 2022 described the civic space in Ghana as “obstructed”, down from “narrowed” from 2018 to 2021. While it’s too early to judge the new government, there are indicators of improvement in engagement between government and CSOs. The government has initiated consultations with CSOs towards the set-up of a Governance Advisory Council that will monitor and report annually on human rights, corruption and overall governance.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

As demonstrated above, the programme has made good progress towards achieving its outcomes during its first year of implementation. Aside from influencing the 2024 elections it has laid foundations that should drive demand for transparent and accountable governance in the following years. The new government has demonstrated sufficient commitment to its campaign promise to “reset the country” and has assigned some of GGP CSO partners to either lead or be part of the change processes. The ongoing constitutional review process led by CSOs, the government’s “Operational Recover All Loots (ORAL) and the proposed Governance Advisory Council offer unique opportunities for GGP to support achieve the desired outcomes. The next phase of the programme is crucial to leverage partnerships built to influence policy changes to support Ghana build an effective governance system to promote economic growth and jobs creation in line with FCDO’s priorities.

## C. DETAILED OUTPUT SCORING

Output Title	Strengthened capacity and motivation of CSO’s and EMB’s to promote credible and peaceful elections
Output number:		1	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Level of CSO’s engagement to promote credible elections	1193 CODEO observers provide independent assessment of the electoral processes. / IMANI informs voters’ choices through analysis and sharing of information on the credibility of political parties’ manifestos. / ACEP, GACC & GII influence political parties’ anti-corruption commitments.	Met / CDD recruited, trained & deployed 1193 CODEO observers across polling stations. 100 BHC observers complemented CODEO observers. / IMANI developed and shared its manifesto analysis report to enable voters make informed decisions. / ACEP, GACC and TI Ghana (formerly GII) implemented its Pledge Against Corruption (PAC) Campaign and elicited commitments from candidates during the 2024 elections.
1.2. Number of engagement platforms created by / (i) National Peace Council (NPC) to increase dialogue to mitigate the risk of electoral violence. / (ii) National Commission for Civic Education (NCCE) to increase voter education among women and young people.	Six (6) regional and one (1) national dialogue to build consensus among political parties for a peaceful elections; / Four (4) voter education engagement involving women and young people to increase their participation in the 2024 elections.	Exceeded / The National Peace Council (NPC) facilitated one national peace pact and signed 29 constituency peace pacts across nine regions - Greater Accra, Ashanti, Volta, Oti, Savanna, North-east, Central, Eastern and Western to build consensus. / NCCE organised seven (7) Townhall meetings with women and youth activists to provide voter education and women’s participation as well as mitigate the risk of electoral violence by addressing concerns among youth political party activists.
Level on National Peace Council’s strategic communication capacity to address salient issues during 2024 elections.	a). Increased NPC’s responsiveness to crises situation before, during and after the election	Met / a). Increased strategic communication capacity of NPC with the support of two embedded GCSI Communication experts. This led to improved communication by the NPC before, during and after the elections and contributed to the significant reduction in violent incidents during the 2024 elections compared to 2020.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, the output performed well against the indicators having mobilised CSOs and EMBs to manage interventions which contributed to a credible election in 2024. Interventions by IMANI and NCCE and the NPC contributed to increased voter education and dialogues to mitigate the risk of electoral violence respectively. CODEO’s observation complemented by BHC Accra’s Diplowatch enhanced the credibility of the voting and counting processes. CODEO liaised with relevant EMBs to respond to salient issues that could have undermined the integrity of the elections if left unchecked. The initiatives by GGP partners underscore efforts to enhance Ghana’s commitment to safeguarding its democratic gains and fostering a peaceful and inclusive electoral process in the face of persistent challenges and political instabilities in the West African Sub-region. These interventions collectively improved dialogue and commitment by political actors to peace; increased awareness of the importance of women’s participation in governance and the electoral processes and strengthened youth commitment to non-violence and peaceful political engagements. While the 2024 election was not without violent incidents, the scale was significantly lower than the 2020 elections.

Below are details of progress against each indicator;

  1. Level of CSOs engagement to promote credible elections- Following the launch of manifestos of the political parties, IMANI undertook assessment of manifestos of the two major political party, one minor party and that of an independent candidate. The outcome of the assessment was shared with stakeholders including through media to enable voters make informed decision. The findings were also shared with the DPs Anti-corruption Working Group to inform their influencing strategies. The intervention contributed to issue-based discourse.

With increasing monetisation and corruption of elections through widespread and often open vote buying as well as excessive campaign financing, ACEP implemented the PAC campaign to promote the integrity of the 2024 elections. At a multi-stakeholder engagement held prior to the elections, political party candidates or their representatives made public commitments to fight corruption if voted into power.

On election day, the programme funded 1193 out of the 4000 domestic observers deployed by the CODEO led by CDD. These observers undertook independent observations, verification and reporting of electoral activities, enabling responses to risks, threats and incidents such as delay in commencement of voting in hard-to-reach communities for prompt responses. Three reports issued on the election day provided updates on activities, including the participation of party agents, the functioning of polling stations, and the collation processes and the Parallel Voter Tabulation (PVT) results on voter turnout and rejected ballots. Following the Electoral Commission’s declaration of official presidential election results on December 9, 2024, the Coalition validated the EC’s results, using the PVT estimates. The PVT findings confirmed that the EC’s official partial results were consistent with CODEO’s independent estimates, providing reassurance to the public and stakeholders about the credibility of the process.
[note] The US and Netherlands funded the remaining observers.

  1. Electoral education and peacebuilding by NPC and NCCE- The NPC organised Consultative Dialogues in 31 electoral hotspots in nine regions between November 25 and December 3, 2024. These hotspots, identified due to prior election-related violence, saw parliamentary candidates and political party leaders sign Peace Pacts in 29 Constituencies, signalling their commitment to peaceful elections. The dialogues addressed recurring issues of mistrust in the Electoral Commission and the electoral process; concerns about the role of security agencies in the election security architecture, electoral misconduct, and the rising spread of misinformation/disinformation and hate speech. A particular focus of the dialogue was on the role of the youth, who are often exploited by political actors to incite violence or who tend to exploit political tensions and act as conduits for perpetuating electoral violence. Through education and awareness, the dialogues aimed to empower citizens of these constituencies to contribute to a violence-free electoral environment. These initiatives led to improved dialogue and commitment by political actors to peaceful electoral processes. 28 out of the 29 constituencies that signed the peace pact did not experience any violence following the event.

The NCCE organized seven town hall meetings targeting 543 women from diverse professional and community groups and 491 (297 males and 194 females) political party youth activists. These engagements provided platforms for women to voice their concerns and actively participated in the electoral process, addressing structural barriers and societal norms that often limit their involvement. Women participants were drawn from associations of Market Women, Hairdressers, Dressmakers, Queen Mothers, Persons with Disability (PWDs), Teachers, Traders, Churches, and other professional groups. The interventions led to increased awareness of the importance of women’s participation in governance and electoral processes. The NCCE also organised forums for youth activists of political parties focused on promoting non-violence, peacebuilding, and constructive political engagement. Participants included apprentices, professionals, drivers, students, and persons with disabilities (PWDs) among others who were members of various political parties. These efforts sought to transform youth into agents of peaceful campaigning and democratic participation, countering their historical mobilisation for electoral violence. The youth were educated on the Vigilantism and Related Offenses Act 2019 (Act 999) and electoral processes. Additionally, 9000 voter education flyers were printed and distributed and social media used to stream live events to expand coverage.

Despite the interventions by the NCCE prior and during the elections, events after the December 2024 elections were marred by political unrest involving the youth activists of political parties. Most of these instances of unrest happened at areas not previously marked as hotspots which required urgent intervention by the NCCE. Between January and March 2025 therefore, NCCE implemented civic education and engagement activities aimed at promoting peace, national cohesion and active citizenship. The interventions reached 446 youth leaders in tertiary institutions and 501 out of school youth in high-risk areas. The sensitisation sessions increased awareness of the legal consequences of political violence, encouraged peaceful political participation, and strengthened networks among youth groups to discourage violent mobilisation. Additionally, participants enhanced their media literacy skills to counter misinformation. The Youth Leaders’ Dialogue sessions empowered student leaders across tertiary institutions with knowledge and skills in conflict prevention, misinformation management, and democratic participation. These resulted in a strengthened network of peace ambassadors committed to promoting national cohesion and contributed to end the post-election violence. The engagements also fostered stronger partnerships between the NCCE, UNDP, FCDO, Youth Leaders, National Youth Authority, and political party youth wings, enhancing multi-stakeholder cooperation in post-election peacebuilding efforts.

  1. Level of NPC’s communication capacity to address salient issues during the 2024 elections- the NPC with the support of two GCSI Communication experts implemented interventions to manage situations from escalating into violence before, during and after the elections. Videos, photographs and live streamlining of events as well as press statements and conferences were held to address salient issues to mitigate the risks of violence. The intervention built on capacity support provided to the NPC by GCSI over a year with funding from ISF State Threats demonstrating strong cross HMG cooperation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

While there are opportunities to further partner with both the NPC and NCCE, Indicators 1.2 and 1.3. will be paused until 2027/28 financial year in view of 2028 elections. The programme will, however, promote continuous collaboration with existing partners and the Election Management Bodies (including NCCE and NPC) particularly in relation to electoral reform agenda.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned
- Collaboration of diverse stakeholders, including traditional and faith-based organizations, political parties, the Electoral Commission, security agencies, and traditional leaders, is confirmed as critical for the credibility, richness and scope of the dialogues, and key for ensuring sustainability.
- Engagements aimed to promote gender equality and empower women achieves more impact when organized more frequently, rather than solely in election years and very close to election, to ensure continuous advocacy, awareness and capacity building.
- Continuous and sustained public education on peace and causes of electoral conflicts/violence within the constituencies, is confirmed as contributing to effective management of election-related tensions. This confirms the potential for continuous engagement with youth groups, enhancing media literacy programs, and strengthening partnerships to institutionalize peace education for long-term democratic stability.
- While FCDO is receptive to the opportunity to support prospective partners to improve and resolve weaknesses identified through Due Diligence Assessments (DDA), changing partners’ ways of working may require deep commitment and change from the CSO in question, the lack of this in one case led to the voluntary withdrawal of the partner.

Recommendations

- FCDO to initiate processes to close IMANI’s project by September 2025.
- By November 2025, FCDO should review the output weighting to reflect pausing of Indicators 1.2 and 1.3 and closure of IMANI’s project

Output Title	Enhanced citizens engagement with state institution and processes
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1. Number of strategic partnerships created and sustained by CSOs funded by GGP to promote citizens engagement with state institutions and processes.	Three (3) strategic partnerships established to facilitate citizens engagement with state.	4 Strategic partnerships formed_- Exceeded / CDD-Ghana in partnership with Multimedia Group and nine CSOs, organized town halls in 14 regions of Ghana to solicit citizens’ views and expectations of the new government. / ACEP has built alliances with CSOs/citizens groups including trade unions and media personnel to drive active citizenship to support the PAC campaign. / ACEP in partnership with Multimedia Group and CDD relaunched the Corruption Watch radio programme. / ACEP has built partnership with University of Media Arts and Communication (UniMAC), a public university and the Fourth Estate to train and provide continuous mentorship to student journalists on investigative journalism.
2.2. Level of quality engagements between CSOs funded by GGP and state institutions and in state processes.	CSOs funded by GGP have engaged with political parties, EMBs and other stakeholders on key electoral issues such as manifesto building, voting processes, electoral integrity and election security among others to influence credible elections.	Met / CDD engagement with the EC led to correction of the final presidential results announced and with the EC and with Election Security Taskforce led to prompt actions to address salient issues. / ACEP organised a public forum bringing together candidates of the 2024 elections or their representative to influence long term commitments to fight corruption in Ghana. Presidential candidates or their representatives who participated in the forum made public commitment to fight corruption.
2.3. % of CSOs/citizens – state actors’ engagement that have resulted in commitment to reform policies and practices.	2 CSO and state actors’ engagement have resulted in commitments to reform policies and practices.	Met / The Upper East Regional Minister committed government to review the 1 Village 1 Dam (1V1D) initiative-based findings of the assessment undertaken by ACEP consortium in collaboration with NOPRA. / EC corrected the Presidential results announced following triangulation with CDD’s PVT scores.

Briefly describe the output’s activities and provide supporting narrative for the score.
The Output performed well against the indicators through promotion of effective citizens engagement with state institutions and processes. ACEP’s Campaign mobilised citizens and citizen groups beyond the traditional civil society fraternity to include trade unions/associations. This is crucial to ensure broad-based support for the campaign although its impact/sustainability is hinged on ACEP’s ability to maintain quality engagements with the groups and sustain its credibility. Also, CDD’s national consultation reached out to diverse citizen groups across the country including creating special platforms to enable vulnerable groups to have their voices heard. CDD’s collaborative work with relevant reform committees and processes moved the agenda beyond just collating citizens inputs into influencing policy changes. Details of progress against each indicator below;

2.1. Strategic partnerships to promote citizens engagement with the state- CDD established partnership with Adom Brands and Multimedia Group (e.g. Adom FM) to undertake regional consultations with citizen groups to collate their expectations for the new government. A total of 14 town halls held involving 1331 citizens were broadcast live on radio and online. In some regions, the town halls were held in the dominant local languages in that region. Discussions at the 10 regional Townhall meetings focused on key promises by the new government in their manifesto for the 2024 general elections, and some issues that CDD seeks to address through the government-initiated reforms. These included local government, the constitutional review, anti-corruption, cost of politics, education, state-owned enterprises, electoral reforms, the economy, youth development, and illegal mining (galamsey). In addition, CDD-Ghana partnered with other civil society groups to organize special town halls targeted at women, youth, Persons with Disabilities (PWDs) and the aged to help focus on peculiar issues relating to these minority groups. Findings from the consultations have been shared with the three reform committees commissioned by the President.

ACEP built a network of labour unions, pressure groups and CSO coalitions to support the PAC campaign. Membership of the network included the Ghana Registered Nurses and Midwives Association (GRNMA), the Ghana Private Road and Transport Union (GPRTU), Trade Union Congress (TUC), Ghana Bar Association and Ghana Journalist Association. Others were Ghana National Association of Teachers (GNAT), Teachers and Education Workers Union and the Public Sector Workers Union, among others. The objective of this initiative is to build a critical mass of support to drive demand for anti-corruption reforms. Thirty-one representatives of these targeted organisations were sensitised on a simplified guide on anti-corruption commitments of political party manifestos designed by the consortium. Also, 36 (32 males and 4 females) media personnel from both public and private media outlets were trained to support the campaign to advance governance and anti-corruption reforms. They also partnered with the University of Media Arts and Communication (UniMAC) to train 49 journalism students (30 females & 19 males) on investigative journalism over two days. The training offered hands-on knowledge of investigative methods, ethical issues, fact-checking, and risk evaluation, which are essential for uncovering corruption, human rights abuses, and environmental issues in Ghana. The beneficiaries of the training have joined Investigative Clubs and will receive mentorship from an experienced investigative journalist, Manasseh Awuni Azure.

2.2. Engagements between GGP partners and state institutions. CDD held meetings with Electoral Commission, National Peace Council and Election Security Taskforce among others to discuss activities/process before, during and after the 2024 elections. CDD also worked closely with the EC, NPC and Election Security Taskforce on the election day until results were announced to ensure effective coordination of electoral activities. For instance, a member of the Election Security Taskforce was assigned to the CODEO National Information Centre liaising between CDD/CODEO monitoring activities and the security agencies for prompt response. Also, reports from CODEO observers from hard-to-reach communities to the EMBs enabled prompt response on incidents including delayed start of voting and electoral malpractices.

ACEP organised a public forum on mainstreaming anticorruption in the 2024 elections as part of the PAC campaign. Participants included Presidential candidates, Vice Presidential candidates, other representatives of political parties, government officials, law enforcement agencies (e.g. OSP) and CSOs as well as representatives of private businesses and development partners. The forum which was broadcast live on JoyNews and Channel 1 TV, with repeat broadcasts over the weekend, provided a platform for the candidates or their representatives to articulate their positions on combating corruption and outline their strategies for addressing these challenges.

2.3. Changes as a result of CSOs interventions -The ACEP consortium in collaboration with the Northern Patriots in Research and Advocacy (NORPRA) assessed the implementation of One Village, One Dam (1V1D) policy in Northern Ghana. Following engagement on findings of the assessment of the 1 Village 1 Dam initiative of the previous government, the current Upper East Regional Minister indicated government plans to reassess the 1V1D initiative. CODEO’s engagement with the EC on the election results led to correction of the results announced.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

With the planned exit of IMANI, output indicators will be reviewed to reflect the level of ambition.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Lessons learned
- The successful uptake of investigative skills among young journalists suggests a growing demand for practical, hands-on training, and mentoring will be crucial to sustain this momentum.
- Strong interest and endorsement from unions highlight the relevance of engaging organized labour as powerful allies for anti-corruption advocacy.
- The inability to implement some media partnerships and engagements with Parliament underscores the importance of early coordination, flexible partnerships, and adaptive strategies.

Recommendations

By November 2025, output indicators and milestone should be reviewed to reflect the level of ambition in line with reduction in delivery partners.

Output Title	Enhanced state capacity and motivation to strengthen legislative and institutional frameworks and improve transparency, accountability and human rights as well as reduce corruption.
Output number:		3	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of cases involving asset tracing, freezing or seizure from investigations by OSP supported by ICAR	Accountable Grant Agreement with ICAR signed	Partially Met / A proposal from ICAR for accountable grant (AG) has been reviewed and awaiting approval.
3.2. % change in cases received through the Citizen Eye and investigated by Ghana Audit Services as a result of CSO’s advocacy.	Agreement with ACEP amended to include the audit workstream.	Partially Met / Amendment to the AG with ACEP could not be completed due to FCDO pause on cost extensions.
3.3. Number of cases investigated and prosecuted by the OSP as a result of CSOs/media investigations/reports funded by GGP	ACEP shares findings of investigations with stakeholders	Not Met / The OSP workstream has not commenced.

Briefly describe the output’s activities and provide supporting narrative for the score.
Although output indicators were not fully met, the programme made good progress toward building partnership with the relevant agencies. On the TA to OSP, ICAR’s three-year proposal has been reviewed and pending Development Director’s approval, while GAS and ACEP request for AG amendment is also ready. However, an exemption to the FCDO pause on spending has only been secured for the TA to OSP while the audit intervention is contingent on the outcome of the ongoing ODA review. In the medium to long term, both interventions are likely to be impacted from 2027/28 when the 0.3 ODA target takes full effect. When that happens, the programme will submit a Business Case Addendum to review its scope.

3.1. The programme made significant progress in building its partnerships with OSP and ICAR. Building on the scoping study undertaken by ICAR with its own resources in May 2024, engagements were held with OSP and EOCO to agree on the scope of support. Further, engagement was also held with GIZ and EU on their planned support to the OSP and EOCO to promote complementarity. It was agreed to ensure alignment between support from GGP and the GIZ/EU. For instance, based on GIZ/EU plans to provide training on asset recovery, confiscation, corruption risk assessment and vulnerabilities among others, ICAR reviewed its planned training to ensure complementarity. The agreed scope of work of the AG will fund two ICAR experts to provide mentorship on live cases and train 120 prosecutors and investigators of OSP and EOCO. A financial investigations expert will be embedded while an prosecution expert will be engaged to provide specific deliverables on a draw down basis. While a ministerial exemption has been secured for spend until June 2025 and the programme is likely to have its budgetary forecast for 2025/26 financial year met, the agreement could be impacted from 2027/2028 FY when further ODA cuts is anticipated in line with the 0.3. This risk needs to be communicated to partners and built into the AG agreement.

3.2. Significant progress was also made strengthening the partnership between Ghana Audit Service and ACEP/GACC/TI Ghana. The parties agreed on intervention scope and addendum to the existing proposal. However, the amendment could not be effected due to FCDO pause on cost extensions and new agreements. This workstream will continue to be on hold until the outcome of the ongoing ODA review is known.

3.3. ACEP in collaboration with Northern Patriots in Research and Advocacy (NORPRA) assessed the implementation of One Village, One Dam (1V1D) Policy in Northern Ghana. Findings of the assessment have been shared with stakeholders including the Regional Minister of Upper East who promised to review the initiative. This activity is reported under Output 2.3 above but also represents an early step towards the type of investigations conceived under this Output 3.3 . However, overall this output was not met, as the planned work with the OSP was not started, due to a focus on elections in the early part of the period. Work with the OSP is planned to progress in the next AR period.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Final indicators and milestones will be set once the AG with ICAR is signed. There is also the risk that the audit work might not commence due to reduction in ODA.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendations
- By July 2025, review plans on whether or not to amend the scope of the ACEP agreement to incorporate the audit workstream based on outcome of FCDO ODA review.
- By May, engage ICAR and OSP on potential risk to the future of the intervention and build consensus on how to mitigate this risk. This may mean focusing on the most important issues that can gain traction within one year.
- Insert a break clause into the ICAR AG agreement to mitigate the risk of reduced ODA in line with FCDO’s plans to reduce ODA to 0.3 from 2026/27 financial year.

Output Title	Increased domestic and diaspora voices/actions for protection of rights of all persons in Ghana.
Output number:		4	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
(1) Level of preparedness of partners to implement interventions	Partner identified and agreement signed	Partially Met / Meetings were held with Ratify Ghana. Amnesty International, Human rights and the Constitutional, Legal and Parliamentary Affairs Committees in parliament and the Commission for Human Rights and Administrative Justice (CHRAJ) to identify entry points. However, engagement on this has been paused due to FCDO pause on new agreements.

Briefly describe the output’s activities and provide supporting narrative for the score.

Although the programme did not sign an agreement with any partner, it made good progress engaging with potential partners and supporting cross-office engagement on human rights.

Indicator 1.1 – level of preparedness of partners to implement- the programme made a strategic decision to delay implementation of this output until after the election in December 2024. Good progress was made between January and March 2025 in identifying and engaging potential partners for the output. Meetings were held with Ratify Ghana, Amnesty International, CHRAJ and parliament to identify entry points. However, these engagements paused following central directive to pause new agreements. Additionally, the programme team supported BHC Accra’s initiatives to advance human rights by engaging on the Affirmative Action Act, and media freedom, among others.

However, the human rights context in Ghana is now evolving following a change in government. Available data suggests that most indicators declined under the previous government but, it is too early to judge how the new government will fare. Also, FCDO Accra is currently going through Country Business Planning processes expected to be completed by July which will set country-level priorities. While awaiting the outcome of these processes, the promotion of human rights will remain a priority for FCDO Ghana and will be advanced through policy influencing and cooperation with likeminded organisations. FCDO Ghana will decide on whether or not to keep this output once the outcome of these initiatives (e.g. CBP, engagement with CMPs and central funds etc) are known.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A review of the output will be conducted once FCDO Ghana CBP is done. It will also be informed by outcome of engagements with relevant CMPs and central funds as well as other DPs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation
By August 2025, FCDO Ghana should decide whether this output will be best delivered through political influencing, a CMP or in collaboration with other DPs. The decision may mean submitting a Business Case addendum to remove this output from the Business Case.
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
The key cost drivers within the first year of implementation were direct project delivery expenses and project staff costs. Conference costs for project events and logistical expenses contributed significantly to programme spend. Implementing partners ensured that spend followed agreed workplans and reported on actual expenditure against forecast on a quarterly basis. Partners have ensured that competitive rates were secured for programme events by adhering to standard procurement practices. It is projected that the above-mentioned cost items will continue to drive spend.

VfM performance compared to the original VfM proposition in the business case
The programme’s overall VFM was very good as envisaged by Business Case with CDD delivering the best VFM compared to the other implementing partners. The Business Case sets out expectation of avoiding electoral or governance crisis in Ghana as the value proposition of the programme. Although the Business Case noted the impact of the programme will be hard to attribute with confidence, it sets out to be a relatively modest investment that can plausibly affect the outcome. Economy is to be achieved by building existing structures, ways of working, activities and partnerships, to reduce input costs and avoid reinvention of the wheel and duplication of efforts. Efficiency is to be optimised by ensuring deployment of whole of HMG’s levers to provide complementary support and agreeing indicators with partners for monitoring. Effectiveness will be achieved through a whole HMG approach by enhancing coherence and coordination across HMG and other levers, greater use of PEA and evidence-based analysis to maximise the impact of the programme. HMG is to retain some programme resources to use as a flexible, agile fund to respond to opportunities as they arise. The programme is to ensure Equity by reducing the risk of exclusion from political and democratic processes and ensuring that interventions will promote analysis of gender, equality and inclusion of beneficiaries reached in any of the supported reforms.

Programme’s performance on VFM are as follows;

Economy

The programme engaged strategically to ensure resources were invested in areas most needed. Review of CSOs proposals involved consultations with other DPs (e.g. USAID, EU, GIZ and Canada) to ensure interventions approved built on progress made by others or past FCDO programmes or will be complementary to ongoing initiatives. The programme also utilised PEA to ensure priorities remained relevant and where not, changes were introduced to improve the economy. For instance, although the programme initially approved a proposal from the Institute for Democratic Governance (IDEG) to promote consensus building around the need for constitutional review, the approval was withdrawn following the new government’s commitment to pursue these reforms. This saved the programme £200k. A local consultant has been engaged to provide Monitoring, Evaluation and Learning (MEL) support to partners maximising cost and local content. The programme is largely delivered by local CSOs at lower staffing and operational cost. Total operational costs (including staff costs) of current delivery partners are below 15 % of the total grant amount. Partners opted for cheaper venues for programme activities or paid negotiated prices. For instance, CDD’s national consultations were held at public spaces (e.g community centres, assembly halls in secondary schools) as opposed to using hotels.

Efficiency
The programme team promoted coordination between FCDO bilateral and CMPs to promote efficiency. For instance, the team has effectively engaged the ROLE UK programme to take the key cost of support to the judiciary. The programme also delivered elections support to EMBs through the UNDP Election Support programme that had already built relationships with the targeted organisations. This freed the programme team to focus on other areas of programme delivery while leveraging UNDP’s goodwill with these institutions (e.g. NCCE) to build partnerships. The programme also opted to strengthen partnership between ACEP and the Ghana Audit Service (GAS) to deliver the audit intervention. This support will complement partnership between the UK National Audit Office (NAO) and Ghana Audit Service funded by FTAI, a CMP. At partners level, efficiency gains included the use of existing structures, relationships and digital tools to optimise reach.

Equity
GGP has promoted equity by directly targeting minority groups (i.e. women, young people and PWDs) to mitigate the risk of political exclusions as follows:

All NCCE interventions targeted women and young people. The voter education targeted women and young people while post-election anti-violence dialogues targeted unemployed and marginalized youth. The initiatives prioritised inclusivity, ensuring that diverse groups, including marginalized communities, were represented in the dialogues. NCCE’s mobilisation efforts, supported by their field officers, ensured that even remote young people from outside tertiary institutions and communities were reached. NCCE also trained female parliamentarians on the Affirmative Action Act, gender sensitive budgeting and advocacy and lobbying strategies to equipped them to engage effectively and influence gender sensitive policies. Overall, more than 50% of participants were young women.

Out of the 1193 domestic observers deployed by CDD, 33% were women consistent with the national target of 30% women representation, while 4.2 % were PWDs. 401 out of the 901 polling stations observers observed hard to reach polling stations. As regards the age of the observers, 42% were young people between the ages of 15 and 35 consistent with Ghana’s definition of young people. Also 43 % (578) of participants of CDD’s Townhall meetings were women and 65 % (877) were between the ages of 15 and 35 years. CDD held special Townhalls for women, young people, PWDs and aged to provide them platforms to voice out their peculiar needs. As a result, a total of 132 PWDs participated in all the events organised by CDD.

Effectiveness
The programme has been effective at mobilising, within the short period of time, in order to influence credible elections in Ghana and to lay the foundations to influence post-election reforms for improved transparency and accountability. Interventions by the NCCE and NPC promoted issue-based electoral discourses and a generally peaceful election. Although the 2024 election was not without violence, it is widely acknowledged that the level of violence was lower compared to election 2020. The intervention of the NPC was acknowledged by the then Vice President and NPP presidential candidate in his concession speech. NCCE’s ability to exceed their targets underscores the effectiveness of their strategies.

Cost Effectiveness

Within the first year of implementation, there is evidence to indicate that interventions delivered by all programme partners utilised the right level of resources aimed at achieving overall GGP outcomes and ultimately impact. For instance, for the 2024 election observation activity, a total of 1193 observers were supported to execute their mandate. This resulted in a total cost of £157,074.57 disaggregated into approximately £132 per observer. This cost includes training for the observers’ pre-election day and expenses incurred on election day. By leveraging on key networks, programme partners engaged relevant stakeholders and institutions to efficiently employ resources to deliver expected outputs. As reported earlier, the involvement of stakeholders and positive feedback from beneficiaries validated the effectiveness of interventions and deliberate efforts were made to ensure that interventions were equitably delivered. Overall, there is good progress made to conclude that the GGP was cost effective within the first year and presents a path to fully achieving programme outcomes and impact.

Assessment of whether the programme continues to represent value for money
As demonstrated above, the programme has made significant progress towards achieving its outcome during its first year of implementation. Aside influencing the 2024 elections, it has laid the foundation to drive demand for transparent and accountable governance in the following years. The new government has demonstrated sufficient commitment to its campaign promise to “reset the country” and has assigned some of GGP CSO partners to either lead or be part of the change processes. This offers unique opportunities for GGP to support achievement of the desired outcomes. The next phase of the programme is crucial to leverage partnerships built to influence policy changes to promote an effective governance system that supports economic growth and jobs creation in line with FCDO’s Growth Agenda.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall programme risk rating is assessed as Major. This is within the FCDO Ghana risk appetite. All Partner projects have a risk register which are reviewed formally on a quarterly basis during quarterly progress review meetings and engagements with all partners. Within the Political and Governance team however, monthly reviews of all operational and programme level risks where GGP risks falls are held and risks outside the programme appetite are escalated to the BHC Accra Risk register. The GGP risk register is up to date on AMP. It was last updated in April 2025.

With regards to Strategy and Context risks, as anticipated, the 2024 election was highly contested. Against significant decline in trust in EMBs to deliver a fair election, the risk of electoral violence was anticipated to be high. Within the first year, GGP’s interventions were designed to directly contribute to efforts to mitigate the risk of violence. As noted earlier, one such intervention included inter-party dialogues and the signing of the peace pacts by political parties to commit to using appropriate channels to seek redress. Consistent with the commitment to promote peace, the Vice President and the ruling New Patriotic Party candidate conceded defeat in less than 24hrs after polls closed and before official declaration, demonstrating the impact of the signed Peace Pact. In his concession remarks, he reiterated his pledge for peace during the signing of the peace pact. That notwithstanding, the country witnessed pockets of violence following the declaration of results. Again, the programme responded swiftly through funding to NCCE to deliver targeted engagement with youth activists of political parties and students of tertiary institutions who are often used to perpetuate violence. Ghana remains relatively stable after the new government assumed office. Partners will continue to deliver interventions that contribute to efforts that mitigates this risk.

With respect to policy and programme delivery, some risks were identified. These included inadequate capacity of state institutions to directly manage FCDO funds to drive reforms, risks associated with uncertainties of ODA funding and CSOs inability to form coalitions to drive anti-corruption initiatives and advocacy. The programme team mitigated this risk through Due Dilligence Assessment (DDA). This meant that only partners that had proven capacity and capability were selected to deliver the programme. The programme is addressing gaps identified through the DDA. For instance, a MEL consultant has been engaged to build partners’ capacity in MEL. The team also ensured that there is continuous review of projects currently being supported to help prioritise spend in the event of inadequate ODA allocations.

On safeguarding, DDAs were undertaken for all partners to assess their policies, systems and processes in place to ensure these are robust to mitigate the risk of harm to vulnerable groups (e.g. women, young people and PWDs). Recommendations from the DDAs are reviewed quarterly as part of quarterly reporting. Most of the recommendations have been resolved. A few are outstanding. However, due dates for these have not yet been reached. Through quarterly progress reporting an updated DDA recommendations tracker is submitted by partners as an annex to their reports to closely monitor these recommendations to completion. The programme ensured that as part of FCDO wide partner engagement sessions which includes discussions on safeguarding, all partners were encouraged to attend. A letter on what FCDO expects from Partners in relation to safeguarding and fraud has also been issued to all Partners. Safeguarding risks have also been instituted as a standing agenda item during programme review meetings and monitor partners compliance against safeguarding rules. In the period under review, no safeguarding case was reported.

Reputational risks associated with UK perceived as interfering on sensitive issues, including on corruption, electoral malpractice, and human rights e.g., LBGT derails implementation of UK’s development and diplomatic support to Ghana’s electoral and economic environment. GGP activities have managed to avoid this risk manifesting.

Financial and fiduciary risks involved uncertainties regarding limited budget availability or ODA pause on new agreements. For the larger part of the period under review, this risk did not manifest allowing planned targets to be met. During this period, the team managed the risk maintaining a strategic and focussed work plan for all projects to provide opportunity to be flexible and adaptive in responding to possible budget cuts. However, FCDO pause on new agreements impacted on delivering between March and May, affecting the planned TA to OSP and the audit intervention. The programme team has however secured a ministerial exemption to go ahead with spend for the TA to OSP until June when the office’s ODA allocation for the 2025/26 FY will be known. This risk however increases from 2027/28 when FCDO’s 0.3 ODA commitment comes into full force. This AR has therefore made recommendations on how to deal with the potential impact of 0.3 ODA on the outer years of the agreement.

Update on Partnership Principles
GGP is aligned with Government of Ghana’s priorities to organise credible elections, improve accountability of public officials, improve public sector effectiveness and reduce corruption as well as promote and protect human rights. Consistent with the government’s commitment to domestic accountability, Ghana held its 9th election in December and had a peaceful transition of power from political party to another. The new government has initiated a number of reforms to strengthen transparency and accountability including constitutional review. A new Code of Conduct for government appointees has been launched spelling out new rules on ethical behaviour, public accountability, and misuse of office. Ghana press freedom ranking improved to 50th globally in 2025 from 52nd in 2024 with a score of 67.7% although the safety of journalists remains a challenge.
[note] 2025 World Press Freedom Index by Reporters Without Borders.

It is assessed that the GoG is broadly committed to the UK’s four Partnership Principles, although the risk is assessed as high, given the wider economic context. However, GGP does not provide any financial aid to government or its agencies. The partnership principles are currently being updated.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Programme Delivery and Partnerships

Within the first year of implementation, the FCDO GGP management team has mainly focused on mobilisation activities and finalising agreements with selected partners. GGP is currently implemented by two CSOs - CDD-Ghana and ACEP and one multilateral organisation, the UNDP. The programme however started implementation with four partners which included IMANI. IMANI voluntarily withdrew from the FCDO partnership in April 2025, citing a shift in their strategic direction. The programme also signed an agreement with STAR-Ghana Foundation to commence implementation from the 2025/26 financial year. However, this agreement is being ended given ongoing ODA review. The team-initiated processes for new partnerships in response to the supply side of accountability initiatives. These partnerships refer to an Accountable Grant with ICAR to provide TA to OSP which is ready for approval while the ROLE UK programme has agreed to support the judiciary following a scoping visit.

Generally, the mix of partnerships formed demonstrated the ability of the GGP to successfully deliver its objectives. With a key focus on the 2024 general elections, the first year of implementation:
1. supported the promotion of citizens participation in electoral processes including supporting CODEO to observe the elections.
2. delivered interventions to strengthen anti-corruption initiatives by garnering long-term commitments from candidates of the 2024 election by ACEP.
3. supported the NPC to engage Presidential candidates to commit to and sign Peace Pact and NCCE to provide voter education and train female Members of Parliament as well as engage the youth in preventing post-election violence which was implemented by the UNDP.
4. provided support to IMANI to undertake analysis of political party manifestos and engage the public to be well informed in making decisions.
5. partnered with other diplomatic missions including USA, Canada and Mexico to undertake a joint and coordinated effort to observe the elections (dubbed ‘Diplowatch 2024’). This complemented other observation missions including CODEO.
The FCDO programme management team engaged all partners on a quarterly basis following submission of their quarterly progress report to discuss progress within the quarter where updates on fraud and safeguarding risks formed part of the standing agenda. The team offered monthly briefing meetings to check on key risks emerging and provided the opportunity to discuss delivery challenges.

GGP suffered some challenges during inception which delayed the start of project activities. This was mostly due to HERA system challenges that delayed profiling of budgets into programme components. All except ACEP started effectively at the start of the third quarter of the 2024/25 financial year. Some partners delayed timelines for the submission of quarterly progress reports which impacted the timely disbursement of funds to complete project activities within the quarters. The new partnership with ICAR also suffered some delays in the process of agreeing the project proposal with the OSP. This resulted in the inability to start the project within the fourth quarter of the 2024/25 financial year. It is, however, ready to commence following a ministerial exemption to proceed with spend. Despite these shortcomings, overall, implementing partner performance has met expectations and exceeded expectations in some of the targets.

Financial Performance

GGP has an overall budget of £4,950,000 with an initial projected spend of £1,100,000 in the 2024/25 financial year. However, due to delays in finalising agreement with the ICAR on the OSP support as well as some delays in starting current projects, budget for Year 1 was revised downwards to £750,000. The total spend at the end of the 2024/25 financial year was £724,494 representing about 97% of the revised budget. Partners submitted quarterly narrative and financial reports in the standard FCDO Ghana reporting template developed by the Head of Finance, Risk and Procurement. The quality of partners reports was generally good but there is room for improvement especially around the reporting of impact. One of the partners could do better at adhering to timelines for reporting. It is anticipated that the MEL TA will enhance quality of reports. Partners forecasting accuracy was good within the first year of implementation although exchange rate fluctuations affected one of the partners whose disbursement currency is Ghana cedis. Disbursement of grants was quarterly, following receipt of satisfactory reports. The key cost drivers were direct project delivery costs and project staff costs. Overall, CDD-Ghana maximised their spending and achieved good value by choosing to hold meetings in community centres as opposed to hotels. There are currently ongoing procurement processes to commence audit of partners using a standard TOR developed by DelEX Hub for all programme audits.

GGP has a Delivery Chain Risk Map (DCRM) that sets out the financial flows within the programme and ensure that key risks are managed. Through partners quarterly progress meetings, the GGP management team at the FCDO reviews updates on partner risks including fiduciary risks and project spend in financial reports to understand the current risks impacting on project implementation as well as forming assessments on the legitimacy of expenditure. These insights support the programme team’s analysis of whether the current channels of fund flow is secured and robust. The DCRM is updated to reflect any changes. Currently there are no major risks to the chain identified. However, with the exit of IMANI and new agreements expected to be signed, the DCRM will be updated at the end of July when all factors for change have been confirmed.

Asset Monitoring and Control

None of the Partner projects in the period under review have acquired assets using FCDO funds, However, there is a clear clause in the AG and MoUs which stipulate what partners need to do when assets are acquired. The team will continue to monitor this process.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

Per design of the GGP, a MEL component was developed to strengthen the programme’s results reporting and learnings. A MEL supplier was contracted within the first year of the programme to build partners’ capacity and strengthen alignment between partners results framework and the GGP logical framework. The MEL supplier has carried out capacity needs assessments for all GGP partners and scheduled a training workshop for all partners in June 2025. The training will be followed by continuous mentoring to help partners strengthen their MEL capacity.

The following are key monitoring activities undertaken by the GGP team within the first year of implementation:

- Partners submitted quarterly progress reports. The GGP team reviewed reports and held meetings with partners to discuss feedback. These meetings provided an opportunity to discuss broadly any emerging risks to delivery.
- GGP team monitored programme activities by participating in some events. These included IMANI’s manifesto public and Ghana Anti-Corruption Coalition’s (GACC) ‘Pledge Against Corruption’ campaign launch ahead of the 2024 general elections. Other events monitored include CDD’s post-elections townhall citizens engagement sessions, UNDP’s post-election youth engagement sessions to empower them to be agents of peace and development rather than violence. The team also monitored UNDP in partnership with the NCCE training of female Members of Parliament.
- A key monitoring activity undertaken by the GGP team was the monitoring of CSOs situation rooms on election day. This was a key programme level activity that fed into Diplowatch.

The programme does not currently have an evaluation component. The programme will consider this in future if there is need for it. Also, the programme will be committed to feed into broader evaluation exercises within FCDO Ghana portfolio.

Evidence
During the period under review, the programme did not support the generation of new evidence. Rather it encouraged partners to utilise existing evidence on what works to promote credible elections.

Learning

Implementing partners documented lessons learned from their activities. One key learning commonly agreed amongst partners was the impact that a medium to long-term project could have. Ahead of the 2028 general elections, there is the need to commence design or adapt projects to respond to electoral cycle including pre-election and post-election interventions. Joint quarterly meeting involving partners to facilitate learning and sharing will be undertaken during the second year of implementation.

Date of last narrative financial report	15 April 2025	Date of last audited annual statement	Yet to be completed. Process to undertake first audit has commenced expected to be completed by June 2025

The annual review was conducted internally by the GGP management team. The process involved meetings with all partners being supported under the programme and interviews with some beneficiaries. Partner progress reports and other key programme documents were reviewed to obtain data and relevant information for the annual review.