## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1 | Impact Indicator 2 | Milestones and target corrected to align with Ghana's CPI scores | Clara Osei-Boateng | 28th Ocotober 2025
2 | Outcome 1 Indicator 1 | Wording of indicator amended to make it SMART and milestones set for 2026-2029 | Clara Osei-Boateng | 28th Ocotober 2025
3 | Outcome 1 Indicator 2 | Wording of indicator amended to make it SMART and milestones set for 2028 & 2029 | Clara Osei-Boateng | 28th Ocotober 2025
4 | Outcome 1 | Indicator 1.3 added & milestones set for 2025-2029 | Clara Osei-Boateng | 28th Ocotober 2025
5 | Outcome 2 | Milestones set for Indicators 2.1 & 2.3 and Indicator 2.2 amended & milestones set for 2025-2029 | Clara Osei-Boateng | 28th Ocotober 2025
| Outcome Indicator 3.1 | Chnaged from Civicus ranking to media freedom ranking | Clara Osei-Boateng | 14th November 2025
6 | Outcome 3 | Milestones set for 2025/6 to 2028/29 | Clara Osei-Boateng | 28th Ocotober 2025
7 | Output 1 Indicator 1 | Amended and milestones set for 2028-29 | Clara Osei-Boateng | 28th Ocotober 2025
8 | Output 2 | Output, Indicators and milestones amended | Clara Osei-Boateng | 28th Ocotober 2025
9 | Output 3 | Output, Indicators and milestones amended | Clara Osei-Boateng | 28th Ocotober 2025
10 | Output 4 Indicator 4.1. | Indictor 4.1 closed | Clara Osei-Boateng | 28th Ocotober 2025
| Output 4.2 | Mielstones set | Clara Osei-Boateng | 28th Ocotober 2025

## Template
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE :Ghana Governance Programme (GGP)
IMPACT | Impact Indicator 1 |  | Baseline (2023) | Milestone 1 (May 25) | Milestone 2 (May 26) | Milestone 3 (May 27) | Milestone 4(May 28) | Milestone (May 29) | Target (May 25- 29)
Effective governance system that is transparent and accountable and protects civil and political rights. | Extent of and satisfaction with democracy (%) | Planned | 43 |  | 45 |  | 47 |  | 49
Achieved
Source : Afrobarometer Survey
| Impact Indicator 2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone(April 29) | Target (April 29)
| Ghana score on Corruption Perception Index Score (xx/100) | Planned | 43 | 44 | 45 | 46 | 46 | 46 | 46
|  | Achieved |  | 42- Ghana dropped one point scoring 42/100 on the 2024 CPI.
Source : Corruption Perception Index
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2021) | Milestone 1 (May 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Extent to which electoral reform promoted by CSOs are imeplemented by Government of Ghana by 2028. Proposed evolving scale of CSO influence: 0 – Campaign financial bill drafted 1 – Draft Campaign and Political Party Financing Bill adopted by Attorney General or sponsored as a private members bill 2 – Campaign Financing Bill passed by Parlialement 3 –Campaign Financing Bill implemented. | Planned | CSOs influenced credible elections in 2020 through citizens engagement, election observation and anti-vigilantism initiatives (STAR-Ghana PCR, 2021) | CSOs (ACEP,CDD,IMANI)funded by GGP have influenced credible elections through stakeholder engagement and election observation. | 0-Campaign and political party financing bill drafted and presented by CDD to Attorney General | 1-Campaign and political party financing bill promoted by CDD has been adopted by Cabinet or sponsored as a Private Members Bill. | 2-Campaign and political party financing Act passed by Parliament. | 3-Campaign and Political Party Financing Act implemeted to regulate the 2028 elections. | 3-CSOs influence credible elections and enhanced transparency and accountbaility around campaign and political parties' financing. | • Peaceful electoral processes before during and after the elections. • Peace transition of power from the outcoming to the incoming government • Political parties and Electoral Commission willing to engage on electoral reforms
|  | Achieved |  | CDD trained and deployed 1193 domestic elections observers who provided realtime feedback to citizens and EMBs to ensure promot responses; ACEP convened high level anti-corruption statelholders' conference and elicited commitments from poliitcal parties and candidates on how they will tackle corruption anf IMANI conducted analysis of manifestoes of NDC, NPP, Moverment for Change and Nana Beidako, an indpendent Presidential candidate. These initiatives infleunced credible elections on before during and after December 7 elections.
Reforms and improved practices strengthen elections in 2024 and 2028. |  |  | Source | Partners Reports, Media Reports, Annual Reviews and Programme Completion Reports.
| Outcome Indicator 1.2 |  | Baseline (2020) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Level of Electoral Management Bodies capacity and preparedness to conduct the elections as demonstrated by the extent to which key benchmarks are met-covering voter education, stakeholder engagement and dispute resolution-CLOSED. | Planned | The National Peace Council and the National Commission for Civic Education have limited capacity to effectively play their roles to promote credible elections. | EMBs have enhanced capacity and organised credible elections | N/A | N/A | EMBs have enhanced capacity to implement strategies for a credible elections in 2028. | EMBs successfully organise 2028 elections with outcome acceptable to most stakeholders. | EMBs successfully organise 2024 and 2028 elections with outcome acceptable to most stakeholders.
|  | Achieved |  | NPC and NCCE were enhanced to deliver their mandate to promote credible elections. Support from the programme enabled engagement on electoral processes, voter education and inter and intra-party dialogues to agree on the rules of the game to strengthen the electoral processes. For instance, commitment to the Peace Pact was acknowledged by the Presidential candidate of the NPP (the then Vice President) in his concession speech.
Source : Surveys conducted during Annual Reviews; Parliamentary Hazards
| Indicator 1.3 |  | Baseline (2024) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Progress and influence on election of MMDCEs as evident in the following sub-indicators: 0) CDD's recommendations shared with stakeholders i) Status of reform on legislative pathway (Drafted / Cabinet Approved /Passed/Enforced etc.) ii) Number of stakeholder groups publicly endorsing reform following GGP-partner interventions iii) Evidence of GGP partner proposals reflected in legislative texts or committee reports | Planned | Current legislative framework requires that MMDCEs are appointed not elected. In 2019, the referendum to amend the constitution to allow for bi-partisan election of MMDCEs were abandoned due to lack of consensus among political parties. . | N/A | At least 5 stakeholder groups publicly endorse CDD's recommendations for election of MMDCEs. | (ii)Cabinet approves draft amendment of the constitutional provisions to allow for election of MMDCEs Proposed amendment is laid in parliament | Proposed amendment allowing for the election of MMDCEs is passed by parliament Evidence of GGP partner proposals reflected in legislative text / committee report | Implementation of the Act commences for election of MMDCEs. | Implementation of the Act commences for election of MMDCEs.
Achieved
Source : Surveys conducted during Annual Reviews; Parliamentary Hazards: Newspaper publications
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Number of reforms adopted by SIGA and SOEs to improve corporate governance and transparency as a result of CSOs advocacy | Planned | CDD has not submitted any recommendations to SIGA. | N/A | At least SIGA and 2 SOEs begin to take steps to reform SOEs sector by incorperating recommendations from the GGP partner SOE scorecard. | At least SIGA and 3 SOEs begin to take steps to reform SOEs sector by incorperating recommendations from the GGP partner SOE scorecard. | At least ISGA and 4 SOEs adopt one or more governance-related recommendations from the SOE scorecard, as documented through official communications, stakeholder reports, or management decisions influenced by GGP partner advocacy and technical engagement | At least SIGA and 5 SOEs adopt one or more governance-related recommendations from the SOE scorecard, as documented through official communications, stakeholder reports, or management decisions influenced by GGP partner advocacy and technical engagement | At least SIGA and 5 SOEs adopt one or more governance-related recommendations from the SOE scorecard, as documented through official communications, stakeholder reports, or management decisions influenced by GGP partner advocacy and technical engagement | • Legal framework remains • No/limited intimidation and self-censorship • Political space remains stable • Political will of Stakeholders (including political parties) to engage with citizen groups/CSOs, in particular marginalised and excluded groups • Citizens, including marginalised and vulnerable groups, have the potential to effect change • CSOs are able to collaborate and work together for collective action. • FCDO ensures effective coordination of the demand and supply sides interventions • Parliament has the appetite (political will) to effectively play its legislative and oversight role
Reforms and improved practices strengthen transparency, accountability and human right and reduce corruption. |  | Achieved
Source : Project proposals of implementing partners; partners reports, Annual Reviews and State Ownership Report
| Indicator 2.2 |  | Baseline (2024) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number and description of anti-corruption policy reforms at national or local levels adopted or implemented by political or institutional actors, and aligned with GGP partner-supported proposals informed by evidence-based dialogue, citizen engagement, or investigative journalism | Planned | ACEP has launched the Pledge Against Corruption Campaign | N/A | One (1) GGP partner-supported proposals on anti-corruption reforms submitted to relevant political or institutional actors. | At least 2 political or institutional actors express public commitment to anti-corruption reforms aligned with GGP partner-supported proposals. | At least 1 anti-corruption policy reforms (national or local) adopted or implemented with clear links to GGP partner-supported proposals. | At least 2 cumulative anti-corruption policy reforms (national or local) adopted or implemented with clear links to GGP partner-supported proposals. | At least 2 cumulative anti-corruption policy reforms (national or local) adopted or implemented with clear links to GGP partner-supported proposals.
Achieved
Source: Annual reports of SOEs, media reports, SIGA's State Ownership Report
| Outcome Indicator 2.3 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of documented impact stories demonstrating how OSP’s improved practices and reforms have enhanced efforts to recover assets on corruption cases | Planned | The OSP has only made one asset recovery in relation to its investigation into Labianca Group of Companies and Customs Division of Ghana Revenue Authority. Ghana Audit Service has since 2020 not used its surcharge and disallowance powers. | The scope of ICAR support to OSP defined and agreed between FCDO,OSP and ICAR. | 3 | 2 | 3 | N/A | 3
|  | Achieved |  | ICAR completed scoping on OSP and submitted a porposal for approval. The scoping established areas of capacity gaps and proposed interventions to close the gap. ICAR signed a partnership agreement with OSP setting out scope and responsisbilities of the parties involved.
Source : OSPs Report of Investigations, Annual Report, Media Reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Ghana's media freedom ranking improves | Planned | 50/180 | Ghana's ranking improved from Obstructive to Narrowed | 49/180 | 48/180 | 47/180 | 46/180 | 46/180 | • LBGT Act is not assented or implemented • Ghana remains stable • A good number of media organisations remains non-partisan. • Diaspora groups willing to engage on domestic issues.
|  | Achieved |  | Milestone was not met because no intervention was rolled out during the year under review. The Civicus Monitor has since 2022 described the civic space in Ghana as “obstructed”, down from “narrowed” from 2018 to 2021.
Increased protection (in principle and practice) of the political and civil rights of all persons in Ghana (e.g. PWDs, LGBT+, journalists). |  |  | Source: Partners Reports; Amnesty Rights Reports, Media reports , Annual Reviews and Programme Completion Report
| Outcome Indicator 3.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
Planned
Achieved
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone 5 (April 29) | Target (April 29) | Assumptions
Strengthened capacity and motivation of CSOs and EMBs to promote credible and peaceful elections.(CLOSED for 2025/26) | Number of CSO-led election-related activities supported by GGP (e.g., observer deployment, election observation reports, multi-stakeholder engagements) | Planned | CSOs influenced credible elections in 2020 through election observation, fact-checking of mis/disinformation, inclusive citizens engagement and anti-vigilante initiatives | 3 cumulative activities, including (i) deployment of 1193 CODEO Observers to provide independent assessment of the 2024 electoral processes; (ii) IMANI influences voters choices through analysis and sharing of information on the credibility of political parties manifestos and (iii) ACEP,GACC &GII influence political parties' anti-corruption commitments | N/A | N/A | N/A | N/A | At least 10 cumulative CSO-led election-related activities supported (including observer deployments, reports, and stakeholder engagements) | •CSOs political neutrality, consistency and credibility •Capacity and willingness of citizens/citizens groups to engage on key issues •EMBs will be neutral and have the capacity the in discharging their duties
|  | Achieved |  | a) CDD recruited, trained & deployed 1193 CODEO observers across polling stations. 100 BHC observers complemented CODEO observers. b) IMANI developed and shared its manifesto analysis report to enable voters make informed decisions. c) ACEP, GACC and TI Ghana (formerly GII) implemented its Pledge Against Corruption (PAC) Campaign and elicited commitments from candidates during the 2024 elections.
Source: STAR-Ghana PCR, 2021; Partners reports, Media Reports, Draft Bills etc
IMPACT WEIGHTING (%)- 0% | Output Indicator 1.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of engagement platforms created by (i)National Peace Council (NPC) to increase dialogue to mitigate the risk of electoral violence ; (ii) National Commission for Civic Education (NCCE) to increase voter education among women and youn people. | Planned | Adhoc public call for a peaceful elections. | (i)Six(6) regional and one (1) national dialogues to build consensus among political parties for a peace elections ;(ii) Four (4) voter education engagement involving women and young people to increase their participation in the 2024 elections | N/A | N/A | N/A | N/A | (i)Six(6) regional and one (1) national dialogues to build consensus among political parties for a peace elections ;(ii) Four (4) voter education engagement involving women and young people to increase their participation in the 2024 elections
|  | Achieved |  | a) The National Peace Council (NPC) facilitated one national peace pact and signed 29 constituency peace pacts across nine regions - Greater Accra, Ashanti, Volta, Oti, Savanna, North-east, Central, Eastern and Western to build consensus. b) NCCE organised seven (7) Townhall meetings with women and youth activists to provide voter education and women’s participation as well as mitigate the risk of electoral violence by addressing concerns among youth political party activists.
Source: STAR-Ghana PCR, 2021; Partners reports, Media Reports, Draft Bills etc
| Output Indicator 1.3. |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Level of National Peace Council's strategic communication capacity to address salient issues during 2024 election. | Planned | Limited strategic communication capacity to handle potential crisis. | Increased NPC's responsiveness to crisis situations before, during and after the 2024 election | N/A | N/A | N/A | N/A | Increased NPC's responsiveness to crisis situations before, during and after the 2024 AND 2028 election
|  | Achieved. |  | Increased strategic communication capacity of NPC with the support of two embedded GCSI Communication experts. This led to improved communication by the NPC before, during and after the elections and contributed to the significant reduction in violent incidents during the 2024 elections compared to 2020.
Source: STAR-Ghana PCR, 2021; Partners reports and Media Reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone 5 (April 29) | Target (April 25- 29) | Assumptions
| Number of GGP-supported CSO-led mechanisms, campaigns, tools or platforms established or facilitated for civic mobilisation and advocacy (disaggregated by GGP partners and thematic issues) (i) campaign financing (ii) constitutional reforms iii) PAC iv) MMDCEs election v)SOEs governance | Planned | Adhoc engagements between and among CSOs and state actors on issues they're aligned. | Three (3) strategic partnerships established to facilitate citizens engagement with state instutitions and processes. | At least 6 CSO-led mechanisms, campaigns, tools or platforms for civic mobilisation and advocacy on such themes as (i) campaign financing (ii) constitutional reforms iii) PAC iv) MMDCEs election and v)SOEs governance | At least 10 cumulative CSO-led mechanisms, campaigns, tools or platforms for civic mobilisation and advocacy on such themes as (i) campaign financing (ii) constitutional reforms iii) PAC iv) MMDCEs election and v)SOEs governance | At least 15 cumulative CSO-led mechanisms, campaigns, tools or platforms for civic mobilisation and advocacy on such themes as (i) campaign financing (ii) constitutional reforms iii) PAC iv) MMDCEs election and v)SOEs governance | At least 20 cumulative CSO-led mechanisms, campaigns, tools or platforms for civic mobilisation and advocacy on such themes as (i) campaign financing (ii) constitutional reforms iii) PAC iv) MMDCEs election and v)SOEs governance | At least 20 cumulative CSO-led mechanisms, campaigns, tools or platforms for civic mobilisation and advocacy on such themes as (i) campaign financing (ii) constitutional reforms iii) PAC iv) MMDCEs election and v)SOEs governance | • CSOs political neutrality, consistency and credibility • Capacity and willingness of citizens/citizens groups to engage on key issues
Strengthened CSO capacity, platforms, and mechanisms for citizens to engage state actors and demand accountability, transparency, human rights and anti-corruption reforms |  | Achieved |  | CDD-Ghana in partnership with Multimedia Group and nine CSOs, organized town halls in 14 regions of Ghana to solicit citizens’ views and expectations of the new government. ACEP has built alliances with CSOs/citizens groups including trade unions and media personnel to drive active citizenship to support the PAC campaign. ACEP in partnership with Multimedia Group and CDD relaunched the Corruption Watch radio programme. ACEP has built partnership with University of Media Arts and Communication (UniMAC), a public university and the Fourth Estate to train and provide continuous mentorship to student journalists on investigative journalism. | N/A | N/A | N/A | N/A | N/
Source
| Output Indicator 2.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Level of quality engagements between CSOs funded by GGP and state institutions and in state processes.CLOSED | Planned | CSOs funded by GGP have some level of access to state instutions and are engaged in some public policy discussions. | CSOs funded by GGP have engaged with political parties, EMBs and other stakeholders on key electoral issues such as manifesto building, voting processes, electoral intergrity and election security among others to infleunce credible elections. | N/A | N/A | N/A | N/A | CSOs funded by GGP have engaged with political parties, EMBs and other stakeholders on key electoral issues such as manifesto building, voting processes, electoral intergrity and election security among others to infleunce credible elections.
|  | Achieved |  | CDD engagement with the EC led to correction of the final presidential results announced and with the EC and with Election Security Taskforce led to prompt actions to address salient issues. ACEP organised a public forum bringing together candidates of the 2024 elections or their representative to influence long term commitments to fight corruption in Ghana. Presidential candidates or their representatives who participated in the forum made public commitment to fight corruption.
Source:CSOs proposals
IMPACT WEIGHTING (%)-45% | Output Indicator 2.3 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milesotne 5 (April 29) | Target (April 29)
| Number of civic actors and media personnel trained and supported by GGP partners, and percentage demonstrating increased capacity to engage on transparency/accountability, local governance reforms, human rights, anti-corruption issues, Auditor General's reports, constitutonal review process, etc. (disaggregated by GGP partners and thematic issues) | Planned: | 0 | 2 CSO and state actors engagement have resulted in commitments to reform policies and practices | At least 250 cumulative civic actors and media personnel trained and supported by GGP partners, and 30 percent demonstrating increased capacity to engage on transparency/accountability, local governance reforms, human rights, anti-corruption issues etc | At least 300 cumulative civic actors and media personnel trained and supported by GGP partners, and 40 percent demonstrating increased capacity to engage on transparency/accountability, local governance reforms, human rights, anti-corruption issues etc | At least 350 cumulative civic actors and media personnel trained and supported by GGP partners, and 50 percent demonstrating increased capacity to engage on transparency/accountability, local governance reforms, human rights, anti-corruption issues etc | At least 400 cumulative civic actors and media personnel trained and supported by GGP partners, and 50 percent demonstrating increased capacity to engage on transparency/accountability, local governance reforms, human rights, anti-corruption issues etc | At least 400 cumulative civic actors and media personnel trained and supported by GGP partners, and 50 percent demonstrating increased capacity to engage on transparency/accountability, local governance reforms, human rights, anti-corruption issues etc
|  | Achieved |  | The Upper East Regional Minister committed government to review the 1 Village 1 Dam (1V1D) initiative-based findings of the assessment undertaken by ACEP consortium in collaboration with NOPRA. EC corrected the Presidential results announced following triangulation with CDD’s PVT scores.
Source :Partners report, media reports, (This will be measured by the % of CSOs recommendations that have been actioned by state institutions)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone 5 (April 29) | Target (April 29) | Assumptions
| Percentage of ICAR supported cases making 4 steps or more towards conviction or asset confiscation | Planned | ICAR has no prior working relationshio with OSP | Accountable Grant Agreement with ICAR signed | 0 | 30% | 30% | N/A | 30% | • State institutions would be persuaded to adopt reforms. • Political and administrative ownership of interventions
|  | Achieved |  | A proposal from ICAR for accountable grant (AG) has been reviewed and awaiting approval.
Enhanced state actors' capacity, motivation and responsiveness to strengthen legislative and institutional frameworks and improve transparency, accountability, human rights and reduce corruption |  | Source: Partner report. Case progress is measured using ICAR's Case Progress Tool, which is used by ICAR across its portfolio for this purpose. ICAR's experts log the support provided as well as important achievements that occur. A ‘step’ is a completed task in the Case Progress Tool. A completed task is one that is marked as done, and indicates that a specific action or process has been completed or that a specific milestone has been reached. The tasks in the Case Progress Tool represent what ICAR considers to be substantive and important actions that must be undertaken at the investigation, prosecution and/or other court-related stages to successfully recover (and realise) assets whether through conviction or non-conviction based confiscation mechanisms. The tool's data analysis function counts the steps completed in a given period (usually a 12 month period) by country. The denominator for the calculation is the number of active cases (whether by country programme, or for ICAR's global portfolio) in the same period. This indicator is not cumulative.
| Output Indicator 3.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| % Increase in cases received through the Citizens Eye. | Planned | TBC | Agreement with ACEP amended to include the audit workstream. | 20% | 25% | 25% | 30% | 100%
|  | Achieved |  | Amendment to the AG with ACEP could not be completed due to FCDO pause on cost extensions.
Source: Partner report.
IMPACT WEIGHTING (%)-45% | Output Indicator 3.3 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of tools or processes adopted and applied by partner agencies to enhance the conduct of investigations and prosecutions | Planned | 0 | ACEP shares findings of investigations with stakeholders | Two | Four | Six | N/A | Six
|  | Achieved |  | The OSP workstream has not commenced.
Source : Partners Report, Media report .Based on ICAR Passport of Indicators for Operational Strategy 2025-2028, ‘legal instruments’ refers primarily to legislation that is presented to (and/or passed by) national legislative bodies. Where formal regulations are required to operationalize a law, these can also be counted here. Furthermore, the submission of written recommendations in relation to legislation (either existing or prospective) can also be counted. ‘Investigative tools or procedures’ are defined as: - Documents: such as policy documents, guidelines, manuals, SOPs, interinstitutional agreements, process maps; - Tools: such as a database, a coded Excel template, analytical software, a case management system, a sample MLA request or other sorts of templates; or - Other ways of working that structure how an institution approaches and manages efforts to confiscate assets and/or prevent, detect, investigate, and prosecute corruption or other types of financial and economic crime: such as a case prioritization procedure or a bank statement cleansing routine.
| Indicator 3.4. | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of trainees successfully completed ICAR training supported by GGP | Planned | 0 | 40 | 80 | 100 | N/A | 100
Achieved
Source : ICAR report
| Indicator 3.5 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Level of design of Comprehensive Asset Declaration Manual- edit wording | Planned | Ghana Audit Service currently has no manual guiding Asset Declaration | N/A | Draft Comprehensive Asset Declaration Manual vlaidated with stakeholders | Final Asset Declaration Manual pulicised. | N/A | N/A | Comprehensive Asset Declaration Manual guiding asset declaration standards in Ghana.
Achieved
Source : Partners Report, Media report
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29) | Assumptions
| Level of preparedness of partners to implement interventions -CLOSED | Planned | TBC | Partner identified and agreement signed | TBC | TBC | TBC | TBC | TBC | • Partners have capacity to deliver on projects/programmes (including GESI mainstreaming) • CSO and citizen-based groups, including marginalised and vulnerable groups, can be mobilized for collective action • Target service providers have the capacity (e.g. MEL) to provide quality services. • Citizens, including the marginalised and vulnerable, are willing and able to engage with CSOs • CSOs are interested in driving citizen-led agendas forward that reflect the agendas/needs and priorities of marginalised and vulnerable groups • • Risks identified by partners are within their control to manage, including risks to marginalised and vulnerable groups (to Do No Harm) • Diaspora community willing to engage
|  | Achieved |  | Meetings were held with Ratify Ghana. Amnesty International, Human rights and the Constitutional, Legal and Parliamentary Affairs Committees in parliament and the Commission for Human Rights and Administrative Justice (CHRAJ) to identify entry points. However, engagement on this has been paused due to FCDO pause on new agreements.
Strengthened diplomacy to advance democracy and rule of law |  | Source
| Output Indicator 4.2 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of joint actions initiated by the BHC-led Coordinated Mechanism for the safety of journalists | Planned | 1 | N/A | 2 | 4 | 6 | 8 | 8
Achieved
Source
IMPACT WEIGHTING (%)- 10% | Output Indicator 4. 3 |  | Baseline (2023) | Milestone 1 (April 25) | Milestone 2 (April 26) | Milestone 3 (April 27) | Milestone 4(April 28) | Milestone (April 29) | Target (April 29)
| Number of BHC-led policy dialogues (i.e. speaker series¦) held to advance democracy and rule of law | Planned | 0 | N/A | 2 | 4 | 4 | 4 | 14
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | Total (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note on E21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We have a suggestion to amend this. Given that this is already done, should we ?
Note on G25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Am I expected to choose one?