## Annual Review

Title: UK Support to the Pandemic Fund
Programme Value £ (full life): £25m		Review date: March 2026
Programme Code: 301566	AMP start date: March 2023	AMP end date: April 2027

Summary of Programme Performance
Year	2024	2025	2026
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003174.odt
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301566/summary

A. SUMMARY AND OVERVIEW

Description of programme

The Pandemic Fund (PF) is a World Bank-hosted Financial Intermediary Fund (FIF) established in September 2022 to help low- and middle-income countries (LMICs) strengthen their capacity and capability in pandemic prevention, preparedness and response (PPR). The PF’s Medium-Term Strategic Plan (2024-2029) – published in May 2024 – sets out the Fund’s ‘USP’: (i) filling critical PPR capacity gaps, (ii) fostering coordination between investors in PPR, (iii) catalysing additional investment from international partners (‘co-financing’) and domestic governments (‘co-investment’), and (iv) being flexible and responsive to changing priorities in the PPR landscape. The Strategic Plan also identifies four underlying ‘themes’ which guide projects: One Health, community engagement, gender equality, and health equity.

Since its launch, the PF has secured commitments from 28 donors (24 sovereign contributors and 3 philanthropic foundations) totalling $2.25bn; the UK pledged £25m (2022/23 to 2025/26) – the final £15m instalment was paid in January 2026. The UK sits on the Governing Board in a constituency with Canada and Norway.

As of February 2026, the PF has awarded grants totalling $1.38bn to 67 projects (53 single-country and 14 multi-country/regional projects)[1], supporting 128 countries. The Fund has prioritised investments in disease surveillance and early warning systems, laboratory systems (human and animal), and public health workforce capacity. These areas were identified as priorities in National Action Plans for Health Security (NAPHS) and Joint External Evaluations (JEE). Ahead of each funding round, the Board also agreed that the portfolio of projects selected for investment should: (i) have a geographic balance, (ii) give priority to low- and lower-middle-income countries (LICs, L-MICs), and (iii) involve a range of Implementing Entities (IEs)[2]. A new funding round for ‘high risk/high need’ countries opened for applications on 1 April 2026.
[1] First Call for Proposals (July 2023): $338m; Second Call for Proposals (November 2024): $547m – which includes Mpox projects (September 2024) worth $128.8m; Third Call for Proposals (November 2025): $499.6m
[2] As of February 2026, there are 14 approved IEs: African Development Bank; Asian Development Bank; Asian Infrastructure Investment Bank (AIIB); European Investment Bank (EIB); Inter-American Development Bank (IDB); International Fund for Agricultural Development (IFAD); International Finance Corporation (IFC); World Bank; Food and Agriculture Organisation (FAO); UNDP; UNICEF; WHO; the Coalition for Epidemic Preparedness Innovations (CEPI); Gavi; and the Global Fund to Fight AIDS, Tuberculosis and Malaria.

Progress against headline recommendations from 2025

Recommendation	Progress
The Pandemic Fund should continue to prioritise investment in low- and lower-middle-income countries (LICs, L-MICs)	Around 80% of the PF’s resources for single-country projects have been allocated to LICs and L-MICs (32% ($317m) of funding has gone to LICs, 47% ($458m) to L-MICs, 18% to U-MICs ($178m) and 3% ($26m) to HICs).
The Secretariat should monitor the amounts of co-investment and co-financing that are mobilised and spent during project delivery	The Secretariat is monitoring the amount of co-financing and co-investment disbursed during delivery (see Annual Progress Report – 2024-2025). Of the $3.7bn committed in co-financing across the first and second CFPs, ~$1.7bn (>45%) has been disbursed to projects. $2.5bn in co-investment was committed to projects financed in these rounds – $531m (21.5%) has been disbursed.
Work to encourage a broader range of organisations to become Implementing Entities (IEs), and diversify the pool of IEs delivering projects	Two new organisations (UNDP and IFAD) have received IE accreditation since the 2025 Annual Review (AR). As of mid-March 2026, IFRC and FHI 360 are on Stage 3 of the three-stage accreditation process – the final step is executing the Financial Procedures Agreement (FPA) with the Trustee. Africa CDC remain on Stage 2, but we anticipate that they will move to Stage 3 in spring 2026 (pending Board approval). UNFPA paused its application. At the direction of the Board, WHO has been removed as an IE from every project funded via the 3rd CFP, which has delivered a significant shift towards MDBs ($193m originally designated to WHO was redistributed to 7 IEs – 53% went to the World Bank, 21% to the African Development Bank). In total, 8 organisations are serving as IEs in PF projects: this is an increase from 7 last year.
Develop a more comprehensive picture of how Pandemic Fund investments support climate change and biosecurity and biosafety related activities	The role of climate change as a risk factor driving pandemic threats is set out in some of the PF’s strategic documents (e.g. Medium-Term Strategic Plan, Investment Case 2025-2027). While projects set out how activities contribute to climate change mitigation/adaptation, this has not been captured at a portfolio level. Aside from two references to climate-sensitive diseases, climate change is noticeably absent from the latest Annual Progress Report – a contrast to last year’s Report, which explicitly mentioned climate change. There is no comprehensive portfolio-level analysis or reporting on biosecurity/biosafety investments – although projects show strong biosecurity integration (e.g. as a component of laboratory strengthening).
Track aggregate outputs to provide a better understanding of the Pandemic Fund’s cumulative impact	The Fund’s Annual Progress Report (2024-2025) includes updates on a range of aggregate outputs (e.g. laboratories/surveillance points upgraded or established, health workers trained).

Summary supporting narrative for the overall score in this review

The overall score for the programme is A.

The Pandemic Fund was established as a catalytic mechanism to plug critical gaps in pandemic PPR capacity in LMICs. In line with this mandate, the Fund has continued to evolve its allocation modalities and strategic focus to ensure that its investments: (i) reach countries with the greatest capacity gaps and least fiscal space to address them, (ii) strengthen national and regional systems – rather than create parallel systems, and (iii) ensure that funds are disbursed and spent effectively by Implementing Entities (IEs) and Delivery Partners (DPs) – this is part of adhering to wider principles of good governance and operating effectively, transparently, inclusively, and accountably.
Over the past year, discussions on global health architecture (GHA) reform have gathered pace. The Secretariat have engaged with some of the reform initiatives (e.g. the Accra Reset, Wellcome Trust, EC-led discussions and WHO discussions), and will need to continue to lean in – both to ensure the Fund’s current model is aligned with norms and best practise, and to consider how the activities it finances might be folded into a reformed GHA after its sunset date of 8 September 2030 (see Operations Manual for the ‘Pandemic Fund End Approval Date’).
To better target resources, in November 2025 the Board agreed a new methodology for ‘high risk/high need’ (HRHN) countries. A dedicated funding window for these countries launched on 1 April 2026. The third Call for Proposals (CFP) – which wrapped up in November 2025 – saw a continued improvement in the geographic and income-level distribution of funding: ~80% of allocations went to LICs and L-MICs, and 47% of the funding supported countries in Sub Saharan Africa (SSA), the region with the highest demand. Eight of the 20 proposals included fragile and conflict-affected states (FCAS) – a notable increase from earlier rounds.
In terms of delivery, all bar two projects from the first and second CFPs have started implementation[3]. In the Annual Progress Reports (2023-2024 and 2024-2025), the Secretariat are open about the challenges affecting delivery, for example related to governance, security in FCAS, procurement and/or supply chain constraints, and various administrative challenges including capacity constraints in beneficiary governments. To mitigate these issues, the Secretariat has taken steps to support project delivery e.g. developing project tracking dashboards and communities of practice for IEs to improve coordination. As of March 2026, the Trustee has transferred ~$370m to IEs ($324.9m in project funds, $45.4m in IE fees).
[3] 19 projects from the first CFP and 26 (out of 28) projects from the second CFP are underway – we note that one of these projects (in Trinidad and Tobago) will begin implementation shortly
To strengthen national and regional systems, the Fund is embedding its investments within existing public health institutions and frameworks, rather than creating parallel delivery structures. Following updates to the results framework, IEs are now required to report on how projects leverage national institutions such as National Public Health Institutes (NPHIs), veterinary, agriculture, and environmental bodies. Encouragingly, 81% of projects from the first and second CFPs reported active engagement with NPHIs, highlighting their role in enhancing disease detection and response capacity. At the regional level, nearly 40% of projects reported substantial collaboration with regional or global networks.
The Fund’s governance model continues to mature. The 21-voting member Governing Board maintains parity between sovereign contributors (donor countries) and sovereign co-investors (potential recipient countries) (9 seats each) – with a further two seats for CSOs and one for non-sovereign contributors. Co-investor engagement in Board and Committee meetings has improved. In June 2025, Dr Chatib Basri (selected from contributor constituencies) secured a second, two-year term as co-chair, while Dr Sabin Nsanzimana’s (selected from co-investor constituencies) term was extended for one year, as per the Governance Framework. The UK would prefer to see the same rules apply to both co-chairs (i.e. two-year terms extendable by one additional year), but we note that this would require changes to the PF’s governance documents which the Board would need to agree.
Looking ahead, the Fund’s ability to deliver on its mandate will depend not only on effective implementation but also on its ability to adapt to a shifting global health landscape. As the architecture for pandemic PPR evolves, the Fund must prepare for a responsible and strategic transition beyond 2030.
This Annual Review will assess progress against the following areas:
1. Improving collaboration and coordination between organisations supporting PPR nationally, regionally, and globally and building capacity in countries’ abilities to detect, contain and respond to disease outbreaks – assessed, for example, via their ability to deliver on the 7-1-7 framework[4].
  [4] A framework designed to strengthen outbreak preparedness by setting time-bound targets for identifying and containing disease threats: 7 days to detect a suspected outbreak, 1 day to notify authorities, and 7 days to initiate early response actions.
2. Investment in low-income and lower-middle income countries (LICs, L-MICs)
3. Catalysing co-investment and co-financing – additional funding from domestic and international sources respectively.
4. The Fund’s governance structures, operations – including the Board, Committees, Secretariat, and Technical Advisory Panel (TAP) – and policy alignment.

Key recommendations for the year ahead
- Operationalise the ‘high risk / high need’ modality – launch the funding window on 1 April 2026. This will help ensure that a greater share of the PF’s resources reach those countries with the greatest needs and least capacity to address them.
- Strengthening co-investment and co-financing guidance. Refine definitions and expectations around co-investment and co-financing, provide targeted training for TAP members, and align criteria with other global health investors to enhance consistency and donor confidence in the Fund’s catalytic impact.
- Enhance transparency of project delivery chains – map and report on funding flows from Trustee to IEs to DPs, including transparency on fees and procurement processes.
- Independent performance evaluation – including of the Secretariat and Board co-chairs, in line with best practise in other multilateral funds.
- Start planning now for eventual transition into the wider global health architecture, including a ‘sunset’ strategy for how the Fund might integrate key functions into the GHA.
- Continue to improve governance – particularly in respect of Board and Committee meeting preparation, agenda selection, and conduct.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Pandemic Fund’s goal is to strengthen pandemic PPR capacities in LMICs through investments in national, regional, and global capacity building measures – ultimately to reduce the health, social and economic impact of future pandemics. The Fund’s medium-term (five year – 2024 to 2029) ambition is that recipient countries and regional and global networks are better prepared to prevent, detect, contain, and rapidly respond to pandemic threats.

The interventions, outputs and outcomes are:

1. Financing critical investments: providing financial resources to help countries address critical pandemic PPR capacity and capability gaps identified in national plans (e.g. National Action Plans on Health Security (NAPHS) and National Action Plans on AMR). These investments are expected to translate into measurable improvements in preparedness benchmarks – such as higher JEE and State Party Self-Assessment (SPAR) scores – and into tangible capabilities like functioning early warning and disease surveillance systems, laboratory networks, and a well-trained multisectoral workforce with emergency response capacity.
2. Technical support: deploying expertise and guidance via IEs and other partners to help countries design and implement effective PPR projects. This contributes to higher quality projects implemented on time and budget, while also building long-term institutional capacity in national systems (e.g. ministries of health, veterinary services, public health institutes).
3. Incentivising additional investment in PPR: encouraging financial commitments from recipient governments, IEs and other international sources (including bilateral donors) – thereby catalysing greater investment in pandemic PPR and complementing the activities of existing financing mechanisms / institutions. This approach also supports sustained political advocacy for PPR and encourages countries to increase their own budgetary investment in health security.
4. Enhancing coordination across sectors and stakeholders: fostering more coordinated and coherent action on PPR at the sub-national, national, regional, and global levels. PF projects bring together a range of actors – government departments, IOs, CSOs, and the private sector – and promote whole-of-government and One Health collaboration (e.g. health, finance, and animal health / agriculture ministries). By engaging multiple partners, the Fund aims to breakdown silos, integrate pandemic PPR into routine health systems, and ensure that investments are aligned with broader national and regional efforts.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

1. Improving collaboration and coordination and building capacity: the PF has continued to strengthen multi-agency collaboration. In the second CFP, 86% of projects involved two or more IEs, up from 78% in the first round, with 50% of projects including a multilateral development bank (MDB) as an IE – most commonly the World Bank. This trend was sustained in the third CFP, where 85% of projects featured multiple IEs, with several involving three partners.
Ensuring that a diverse group of IEs deliver projects has been a persistent challenge. Across the first two calls, WHO dominated, acting as an IE in 91% of projects and channelling ~48% of funding allocated to projects. This raised concerns about potential capacity bottlenecks and the need for more varied expertise. The Board repeatedly stressed the importance of expanding the IE pool and reducing concentration risks; ahead of finalising the third CFP, the Board acted to address this – removing WHO as an IE from all projects in this round and re-allocating funding to other IEs. This post-hoc process (undertaken between December 2025 and January 2026) saw $193m originally allocated to WHO redistributed to seven IEs, with the World Bank taking on the largest share ($102m – 53%), followed by the AfDB ($40m – 21%) and then UNICEF ($10m), AIIB ($10m), IDB ($9m) and FAO ($5.6m). Eight different organisations are now serving as IEs in the Fund’s portfolio, up from seven last year.
In our last AR we stated that a key challenge will be ensuring that collaboration between IEs and other partners is sustained during the delivery phase, and that project-based collaboration serves as a platform for more aligned working relationships elsewhere. We note that the Secretariat has rolled out new tools such as online project tracking dashboards and communities of practice for IEs and encourages regular information sharing among partner agencies in each country.
Following the Board’s March 2026 decision to implement a differentiated cumulative funding cap by type of IE – 30% for any single UN agency and 40% for any single MDB or GHI – a key question now facing the PF is how to ensure that the technical expertise provided by UN agencies remains accessible to both the Board (to ensure its decisions are evidence-based) and to potential recipient countries (if they want technical input at a project level – noting their sovereign right to work with the partners they judge best suited to their needs, but also recognising that recipient countries can access technical support through means other than engaging IEs). This question is particularly important in FCAS, where the number of available IEs will be limited.
We assess the Pandemic Fund as having ‘met’ this output indicator.
2. Investment in pandemic PPR in LMICs: $1.385bn has been awarded to 67 projects[5], supporting 128 countries across six World Bank geographic regions; of this, $979m has been awarded to single-country project – $316m has gone to LICs[6] (32%), $458m to L-MICs (47%), $178m to U-MICs (18%), and $26m to HICs (3%). This means that ~80% of funding awarded to single-country projects has gone to LICs and L-MICs – while this is an improvement on last year (75% of funding to date had been allocated to LICs and L-MICs), we note that this is still a smaller share than the Global Fund’s 2023-2025 allocations (where 92% went to LICs and L-MICs, 8% to U-MICs, and 0% to HICs), and Gavi – where nearly 100% of core funding is invested in LICs and L-MICs.
[5] All IDA and IBRD countries were eligible to apply for PF funding via its three open calls for proposals
[6] World Bank Group income classifications for FY26
In terms of the Fund’s geographic footprint, the largest number of projects are in SSA (25 projects) – the region with the highest demand – followed by Latin America and the Caribbean (LAC). The share of funding going to SSA has steadily increased. In the first CFP, only 32% of funding went to projects in SSA; in the second CFP (including fast-tracked mpox proposals), 50% of total allocations went to SSA. In the third CFP, across single-country, multi-country and regional projects around 47% of funding was allocated to SSA. Across the three CFPs, 44% of grants have gone to SSA, 16% to LAC, 13% to East Asia and the Pacific, 10% to Europe and Central Asia, 9% to Middle East, North Africa, Afghanistan and Pakistan, and 8% to South Asia. The UK’s preference is strongly in favour of allocations based on PPR need and vulnerability, with geographic distribution a secondary priority.
The portfolio of projects continues to have relatively limited representation from countries with context-specific needs (FCAS, SIDS), although progress was made in the third CFP: 8 of the 20 funded proposals include at least one FCAS country (five single-country projects, two multi-country and one regional entity project). We note that on 1 April 2026 the PF will launch a new modality for ‘high risk / high need’ (HRHN) countries. 33 countries have been identified as HRHN – of these, 15[7] will be eligible to apply for funding (as they do not have active single-country projects): 10 of these are FCAS, and 13 of them are in SSA.
[7] Afghanistan, Benin, CAR, Congo, Eritrea, Guinea, Haiti, Liberia, Madagascar, Mali, Mozambique, Niger, Nigeria, Sudan, Uganda
We assess the Pandemic Fund as having ‘met’ this output indicator.
3. Co-financing and co-investment: across the three funding rounds, about $10.1bn in co-financing and co-investment has been pledged alongside the Fund’s $1.385bn in grants, equating to an overall leverage ratio of 1:7.3. The ratio has inched up with each funding round: the first CFP had a ratio of 1:6.1, the second CFP 1:7.3, and the third CFP 1:7.4. While co-financing remained similar in the first and second CFPs, domestic co-investment more than tripled in the second round (to ~$2bn). The TAP has repeatedly raised concerns around validating co-financing and co-investment claims, including inconsistency in the information provided by IEs – additionally, in the third round the TAP scored some MDB proposals lower due to differing interpretations of what counted as beneficial co-financing which had a knock-on impact on the portfolio of projects selected for funding. While it is important for the TAP to be clear on its approach to assessing co-financing and co-investment, primary responsibility lies with a clear articulation of what an acceptable and consistent measure of co-investment and co-financing is with a focus on what is genuinely additional (i.e. funding that would not have been deployed for PPR without the existence of the PF), and tracking the delivery of this financing.
As project delivery gathers pace over the coming year, tracking and reporting on the volumes of co-financing and co-investment that are mobilised will be critical. The Secretariat is capturing this information and will alert the Board if there are significant shortfalls v. commitments made at the proposal development stage. Of the $3.7bn committed in co-financing across the first and second CFPs, ~$1.7bn (>45%) has been disbursed to projects; $2.5bn in co-investment was committed to projects financed in these rounds – $531m (21.5%) has been disbursed. Monitoring will enable the Fund to calculate a more accurate effective leverage ratio – and potentially inform future Board discussions about compliance mechanisms or incentives to ensure that partners follow through on their pledges.
We assess the Pandemic Fund as having ‘met’ this output indicator.
4. Governance, operations, GHA reform, and policy: since last year’s AR, the PF’s governance structures and operations have continued to evolve:
Governance: the PF formalised its committee structure in August 2025, retaining the Strategy Committee, re-naming the ‘Conflict of Interest Committee’ the Governance Committee (and expanding its mandate) and replacing the Resource Mobilisation Committee with the Finance Committee. These were much welcome developments, but the Committees and the Board itself are still not functioning as we would hope; we see this as a major risk. The Committees can appear unempowered to progress work promptly; this is in part due to scheduling and workload management of committee members, and the Secretariat’s limited capacity. The discussions of the Board are often sub-optimal, with one cause being the agenda items (and associated papers) being selected. For example, at the March 2026 Board, agenda decision items were presented on an IE funding cap, and determination of the nomenclature of key Board terms (such as IE and DP). Separate decision points were presented on both despite the clear linkages between the two items. Much better, would have been to first ask the Board to consider the strategic functions different partners in the Fund should undertake. Greater consultation with Board members as to the selection of agenda items is important, as is constructive challenge from Board chairs to the Secretariat on agenda preparation.
In 2025, the PF also launched an External Advisory Council (EAC) consisting of more than 20 representatives from industry, academia, civil society, and other stakeholders to provide strategic advice and advocacy support (e.g. Pfizer, Merrick, IFPMA, AMR Policy Accelerator). Since its launch, the EAC has defined its priorities and developed a 12 month plan of work. The Secretariat has also undertaken further outreach to secure the participation of more organisations. Capturing the value of add of the EAC and its participants as it beds in – including whether it acts as a pathway for greater participation in the PF (e.g. as a donor, or a provider of project co-financing) – will be important in the year ahead. The update on EAC activities and proposed policy papers, received at the March 2026 Board, was positive and promising.
- Secretariat: the Secretariat has grown over the past two years (from 8 FTE in early 2024 to 20 FTE in March 2026 – two more members of staff (Senior Health Economist, Operations Officer) will join the Secretariat by the end of FY26) and is now approaching a steady state. The Secretariat’s FY26 budget is largely unchanged v. FY25 at around $12.6m. The PF continues to have one of the lowest overhead ratios amongst the GHIs and other comparable FIFs: administrative and Trustee costs are 0.4% of cumulative contributions. In 2025, the Secretariat’s internal processes and planning matured: a detailed workplan was adopted, and the proposal submission portal and application templates were upgraded in line with the TAP’s feedback to make the application process more efficient.
- Co-investor representation and involvement: in previous years we noted that, despite the Board’s progressive governance structure (with equal sovereign contributor and co-investor representation), securing meaningful participation by co-investors in discussions and decision making had been challenging. The Secretariat took a range of actions to address this including meeting with co-investors to raise awareness of the PF’s governance structures, providing TA to co-investor constituencies ahead of Board and Committee meetings, and producing summaries of documentation in advance (including in French). This work has borne some fruit: more co-investors now attend Board and Committee meetings (although we note that attendance at the in-person meeting in Kigali in November 2025 was low) and participate in discussions. The Secretariat will provide support and guidance to co-investors in advance of the co-investor constituency reset process and co-investor Board co-chair selection in June 2026. The UK places great value on the inputs of co-investor constituencies. We want PF decisions to be led by the stated need of co-investor countries. In line with the UK’s wider approach to international development, we prioritise country-owned and led initiatives, and reject old-fashioned donor led interventions.
- Technical Advisory Panel (TAP): the TAP’s workload remains high. Following the second CFP (where the TAP reviewed 127 eligible proposals), the TAP and Secretariat conducted a lessons learned exercise which made various recommendations to streamline the application process and strengthen the TAP’s capacity. Almost all administrative changes were promptly implemented (e.g. extending application timeframes, simplifying the application form, and capping the number of proposals per country); the TAP was also expanded to 28 people and a ‘Roster of Experts’ was created. These enhancements were in place for the third CFP, which saw a still-substantial 92 proposals reviewed by the TAP, but with more time per proposal and more diverse expertise on hand. Alongside reviewing these proposals, the TAP also inputted into work on the ‘high risk/high need’ methodology and provided feedback on various minor and major project scope change requests. As per previous ARs, the Secretariat and Board should continue to reflect on how the TAP’s model can be refined in order to make the most of the TAP’s expertise while ensuring that TAP members are not over-burdened. As noted, it is important the Board has evidence-based advice to inform its decisions, at a strategic level, as well as a project level. Where should this come from: the TAP, UN agencies – or a combination of both? This needs clarification by the Board. As noted above, the Secretariat should continue to offer, and TAP co-chairs should facilitate access to, appropriate guidance, training, and support when assessing co-financing claims in future funding rounds.
- Global health architecture reform: the PF’s operating model is aligned with some of the principles of GHA reform, including the Lusaka Agenda’s five shifts, though with some caveats. Investments in disease-agnostic surveillance systems, laboratories, and public health workforce capacity (guided by national priorities and plans such as NAPHS) contribute to broader health systems strengthening, which supports PHC. 57% of project activities directly support gaps identified in countries NAPHS or related preparedness plans. The PF requires co-financing from recipient countries (with flexibility for LICs and FCAS) – catalysing domestic investment in pandemic preparedness, which supports Lusaka’s emphasis on sustainable financing. In terms of achieving operational coherence, the PF has taken steps to streamline application forms and IE reporting mechanisms in response to feedback – though more can and should be done here in coordination with other funders of PPR capacity building. We have identified overlaps between some PF, Global Fund C-19RM-funded and World Bank projects – although delivery via established IEs should avoid the creation of parallel structures, which aids coherence. The question of the USP of the PF vis a vis the rest of the GHA, while perhaps clear to the Secretariat and the Board, clearly needs greater articulation with the GH community. Stakeholders rightly note that the Global Fund, Gavi, WHO, World Bank (and others) contribute to PPR. Given the focus in GHA reform discussions on reducing fragmentation and eliminating overlaps, the PF (Board and Secretariat) needs to clearly articulate the functions it delivers that no other GHI does; this is the best way of ensuring these functions are safeguarded in the future architecture and after the PF’s sunset. A Special Board meeting on 2 February 2026 was a good step; although the Board statement (released on 16 March 2026) doesn’t mention GHA reform directly. As the ‘small fish’ in a big pond, the PF must shout louder to have its voice heard, especially given it has no presence in Geneva.
- Policy: 93% of projects report alignment with the One Health (OH) approach – activities include establishing new cross-government processes/structures to improve coordination between relevant ministries (e.g. a OH Steering Committee in Mongolia), developing national OH plans and strategies (e.g. Mongolia, Kyrgyz Republic), and expanding joint human/animal health surveillance (e.g. Cabo Verde, Nepal); these investments will enable earlier identification of potential outbreaks at the human/animal/environment interface and are a genuine ‘USP’ of the PF. In the first and second CFPs, more than half of projects have adopted multisectoral frameworks for OH, and 30 countries have integrated animal health into national health security plans.
The majority of projects incorporate climate change related activities – mostly in relation to adaptation. For example, various countries (e.g. India, Ethiopia, Zambia) are upgrading surveillance systems to integrate climate and environment data – this includes climate-health information systems and early warning systems for climate-sensitive diseases (e.g. cholera outbreak risk in flood-prone areas). Investments also strengthen the capacity of health systems to withstand and respond to climate-related shocks e.g. training health workers in disaster response and emergency logistics under extreme weather conditions and developing multi-hazard emergency plans that combine pandemic response with natural hazard management. We would encourage the Secretariat to analyse the PF’s portfolio to provide a broader picture of the PF’s links to climate change. In the PF’s latest Annual Progress Report, references to climate change were disappointingly limited.
In terms of biosecurity and biosafety, nearly all projects involve upgrading laboratory infrastructure to meet higher biosafety standards (including setting up BSL-2 and BSL-3 labs), improving safe handling of pathogens, and training personnel in biosafety (preventing accidental exposure to pathogens) and biosecurity (preventing loss, theft, or misuse of hazardous biological materials). In Rwanda, a new BSL-3 National Veterinary Reference Laboratory is being constructed, other animal and human labs upgraded, and sample management and transportation systems strengthened. Similarly, in Pakistan at least one BSL-2 lab in each province will be established, and key federal labs (including the National Institute of Health’s virology and bacteriology labs) will be upgraded. Pursuing accreditation (e.g. ISO 15189 for medical labs or ISO 17025 for testing labs) is also widespread across projects. As with climate change, we encourage the Secretariat to capture how the PF’s portfolio contributes to building biosecurity and biosafety capacity and capability in LMICs.

As noted above, there are some early results that can be highlighted at both portfolio and project levels:
- Through projects funded via the first and second funding rounds, 300 laboratories have been upgraded or established, more than 12,000 health facilities upgraded to strengthen disease surveillance, and at least 140,000 health workers have been trained.
- In the 22 countries that experienced outbreaks during the reporting period for the PF’s Annual Progress Report 2024-25, 35% reported applying the 7-1-7 approach; for countries that experienced outbreaks and applied the approach, 43% met the 7-1-7 targets. Furthermore, 103 7-1-7 simulation exercises were conducted in 26 projects.
- Nepal ($18.8m): surveillance coverage has been expanded (e.g. avian influenza bio-surveillance in 16 high-risk districts) and veterinary infrastructure strengthened in three regional veterinary laboratories. 196 animal health professionals have already been trained on notifiable diseases in animals. 931 poultry farmers trained on biosecurity and responsible antimicrobial usage.
- Rwanda ($24.9m): the country’s electronic event-based surveillance system (Impuruza) has been launched – enhancing real-time reporting and monitoring capabilities. An AI surveillance tool has been rolled out at border crossing location, and a new Health Intelligence Centre (to collect, process and analyse real-time health data) has gone live.
- Ethiopia ($50m): over 2,700 health professionals have been trained, 24 private facilities onboarded to DHIS2, and 1.8m travellers screened at points of entry. During the Marburg response, the project supported upgraded PCR capacity, enhanced specimen referral systems, and expanded the national surge roster to 304 professionals.
- Zambia ($18.9m): 152 professionals had been trained in surveillance and laboratory capacity, while public engagement on antimicrobial resistance reached over 133,000 people via radio and direct outreach to 200 farmers.
This delivery is impressive and the Fund should drive a constant focus on realising and maximising the PF’s impact. We have heard commentators ask, ‘but what impact has the PF had?’ – which is somewhat premature given the PF is relatively new, and all GHIs took time to realise impact. But the PF must be alert to this criticism, especially given the intense focus on architecture reform, and double down in terms of a focus on impact and articulating this to a wider audience.
The following action is planned for the year ahead:
Launch the ‘high risk/high need’ funding window on 1 April 2026: the window will be open for applications from 15 eligible countries for 12 months and will feature eased co-investment requirements and pre-announced funding envelopes for each country. This is a significant step forward in ensuring that resources are targeted at the countries in greatest need with the largest capacity gaps. We see this as perhaps the Pandemic Fund’s greatest success to-date, with the HRHN methodology (developed by a Technical Working Group that included the PF’s IEs – such as WHO, FAO, CEPI, AfDB, UNICEF and World Bank – and other partners like WOAH, under the supervision of the TAP and Strategy Committee) a valuable tool for the whole PPR community. It is important it is maintained and kept up to date.
The past year has been busy for the Pandemic Fund: from wrapping up its first resource mobilisation campaign, to running the third CFP and finalising arrangements for the ‘high risk/high need’ modality, while continuing to improve the Fund’s operations and governance structures. Alongside this, the Secretariat have navigated the changing ODA context, including cuts to ODA spending by several major donors. In the year ahead, the PF should focus efforts on monitoring and driving project delivery by IEs, capturing and communicating information on the PF’s impact, and further refining its operations. The Fund will need to navigate debates on the future of the GHA – proactively contributing to discussions on the place of PPR in a reformed GHA, and how the activities it funds will be folded into other parts of the architecture after it sunsets in September 2030.

## C. DETAILED OUTPUT SCORING

Output Title	Investment in pandemic PPR in LMIC countries: greater share of domestic investment in PPPR activities, and greater international investment in PPPR in LMICs
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: Share of domestic co-investment in Pandemic Fund projects	Evidence of the PF’s ability to draw in domestic co-investment alongside PF grants – and evidence that it is mobilising this during project delivery	Met this milestone
1.2: Share of international co-financing in Pandemic Fund projects	Evidence of the PF’s ability to draw in co-financing from a range of international sources alongside PF grants – and evidence that it is mobilising this during project delivery	Met this milestone
1.3: Number of Pandemic Fund projects in low-income and lower-middle income countries as a % of overall PF investment	More than two-thirds of PF funding in the third call for proposals directed to low-income and lower-middle income countries	Met this milestone

1.1: Share of domestic co-investment in Pandemic Fund projects

The first $338m portfolio of projects leveraged co-investment (cash and in-kind domestic contributions from beneficiary countries) of $312m (leverage ratio – 1:0.92). The second funding round (including fast-tracked mpox projects) reported co-investment of $2.1bn (leverage ratio – 1:3.85). In the third CFP, projects secured $1.56bn in co-investment (1:3.1).

~$2.5bn in co-investment was committed to projects financed in the first and second CFP – $531m (21.5%) has been disbursed to date.

1.2: Share of international co-financing in Pandemic Fund projects

$1.85bn of co-financing was leveraged in the first CFP (leverage ratio – 1:5.4). The second CFP (including mpox projects) secured $1.83bn of co-financing (leverage ratio – 1:3.67). The third CFP attracted co-financing commitments of $2.45bn – a leverage ratio of 1:4.9. Of the $3.7bn committed in co-financing across the first and second CFPs, ~$1.7bn (>45%) has been disbursed to projects.

As noted in last year’s AR, it remains unclear how much of the co-investment and co-financing is genuinely additional, rather than existing funding streams / commitments / activities that have been re-badged as cash and/or in-kind co-investment and co-financing. For example, in the second CFP one proposal in a U-MIC included a $26.4m Global Fund C-19 Response Mechanism (C19RM) Wave 2 grant as co-investment, as well as an $11.5m IBRD grant (drawn from an IBRD project approved in spring 2024) as co-financing: this funding is not additional. Similarly, various projects (particularly in the first and second CFPs) have counted existing assets (staff, lab buildings) as co-investment with relatively small amounts of funding being clearly additional (e.g. a new $1m budget line for lab reagents in one project in SSA). We note that while the amount of new investment catalysed is highly likely overstated, there is still value in partners with existing projects coordinating under the Fund’s umbrella, which might not have happened otherwise.

Evaluating and scoring co-financing and co-investment has been a persistent challenge for the TAP – and we note that it adds an additional layer of complexity to the review process (the information most frequently requested from IEs was related to co-financing and co-investment arrangements). In the third CFP, concerns about how the TAP had scored the co-financing section led the Secretariat to devise an alternative allocation scenario with non-TAP recommended proposals[8]. Alongside continuing to refine the criteria and guidance for co-financing and co-investment, further training for the TAP should be put in place. However, responsibility does not sit primarily with the TAP. While the Board agrees that leveraging finance is a key priority for the Fund, the Board has yet to have a clear strategic conversation about how to value co-financing and co-investment versus quality/ technical merit. While it is clearly not a zero-sum game, we agree with those who say that leveraging funding alone does not make for an impactful project.
[8] Proposals in this scenario were assigned an overall score of ≥80% by the TAP and included a mixture of TAP-recommended and non-recommended projects. This approach was taken due to differing interpretations of how co-financing is defined and what types of co-financing should be counted as beneficial when scoring proposals; the TAP’s evaluation of Section C was judged to have disadvantaged projects with co-financing from MDBs – leading to the post hoc process described above.

1.3: Number of Pandemic Fund projects in low-income and lower-middle income countries as a percentage of overall PF investment

$1.385bn has been awarded to 67 projects, supporting 98 countries across six World Bank geographic regions; of this, $978m has been awarded to single-country project – $317m has gone to LICs (32%), $458m to L-MICs (47%), $178m to U-MICs (18%), and $26m to HICs (3%). This means that c.80% of funding awarded to single-country projects has gone to LICs and L-MICs – while this is an improvement on last year (when 75% of cumulative allocations had gone to LICs and L-MICs), we note that this is still a smaller share than the Global Fund’s 2023-2025 allocations (92% went to LICs and L-MICs, 8% to U-MICs, and 0% to HICs), and Gavi – where nearly 100% of core funding is invested in LICs and L-MICs. Like Gavi and GF, the PF’s funding allocation to HICs should be zero.

In total, single-country projects in 11 FCAS countries have been funded (Ethiopia, Yemen, West Bank/Gaza, Burkina Faso, Chad, Lebanon, DRC, Haiti, Burundi, Somalia, and South Sudan). The PF also has a footprint in several other FCAS through multi-country or regional projects (for example, Sudan via a Horn of Africa regional project). We are confident that, through the PF’s ‘high risk/high need’ funding modality, more LICs and FCAS will receive PF support to deliver single-country projects. Board discussions as to the technical merits of single-country v. multi-country and regional projects have been frequent, but inconclusive – it is yet another example of where the Board’s discussions could be better informed through the advice of the Fund’s technical partners as well as MDBs.

Recommendations for the year ahead

- Implement the new ‘high risk/high need’ funding modality to ensure that a greater share of funding flows to low- and lower-middle-income countries and fragile contexts. We note that this window will open for applications from eligible countries in spring 2026. At next year’s review point,
  - At next year’s review point, at least 82% of cumulative allocations should be allocated to LICs and L-MICs.
- Continue to refine guidance on co-investment and co-financing and ensure that TAP members receive appropriate training and support. Ensure consistency with co-financing/co-investment criteria used by other investors in global health. This will also help bolster donor confidence in the Pandemic Fund’s catalytic claims.
- The Secretariat should consider what additional incentives can be introduced to encourage upper-middle income countries to contribute higher levels of co-investment. This might include graduated co-investment requirements or matching schemes.
- Continue to monitor and report on the amounts of co-investment and co-financing that are mobilised during project delivery – and consider how to respond if amounts undershoot commitments made in proposals. Responses might include compliance measures or adjustments to projects to address gaps in co-financing and/or co-investment.
- Monitor how changes to the composition of IEs impact project development in LICs and FCAS, including how technical organisations not eligible to act as IEs due to cumulative funding caps shape strategic project design, and monitoring throughout the project cycle. The Board should review the caps agreed at the March 2026 Board meeting if it becomes apparent that the quality (and so impact) of projects in FCAS and LIC contexts is suffering due to countries not accessing relevant technical support.
- Identify barriers that might impede the leveraging of co-investment and co-financing – this includes alignment between PF funding rounds and other budget/planning/funding cycles, and continuing to strengthen links with the MDBs, including the IMF’s Resilience and Sustainability Trust.

Output Title	Building capacity, demonstrating capability, and improving coordination: countries have functioning disease surveillance and laboratory systems, and improved public health workforce capacity – so they are better prepared to respond to health emergencies. Increased cooperation among countries, regions, and ministries on PPR.
Output number:		2	Output Score:	B
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Maintained or increased JEE and SPAR scores in relevant areas	Emerging evidence that PF investments are enabling countries to maintain or increase JEE and/or SPAR scores	Met milestone
2.2: Number and range of Implementing Entities (IEs) involved in Pandemic Fund projects	Evidence that the PF is expanding the range of IEs involved in projects, and that new organisations are accrediting as IEs	Met milestone
2.3: Projects reporting on collaboration with NPHIs and other regional/global networks and organisations	Evidence that projects are collaborating/partnering with NPHIs and linking activities with other regional frameworks, organisations and standards.	Met milestone

2.1: Maintained or increased Joint External Evaluation (JEE) and States Parties Annual Report (SPAR) scores in relevant areas

JEE and SPAR scores are used as an output indicator because they provide an internationally recognised benchmark of country-level preparedness capacities. Tracking changes in these scores in areas aligned with the Fund’s investments helps assess whether projects may be contributing to measurable improvements in national systems. While not a direct measure of project performance, they offer a proxy for system-level resilience and progress over time and help identify where support is needed.

Across the 26 countries with projects funded via the first CFP, 25 conducted SPARs – of these, 48% maintained their SPAR scores[9] in core areas aligned with the Fund’s programmatic priorities (disease surveillance, laboratory systems, and public health workforce development) and 20% increased their scores. Some countries saw declines in certain indicators (e.g. Burkina Faso and Togo in C.5.1 and C.4.5 – early warning surveillance function and effective national diagnostic network respectively). The changes in SPAR scores also point to uneven resilience in health systems, where gains in some domains (e.g. workforce surge capacity) coexist with regressions in surveillance and/or laboratory network performance. As projects are still in the relatively early phases of implementation, declines do not necessarily indicate project shortcomings – especially in activities that involve multi-year investments. We note that the PF’s SPAR analysis is consistent with the Global Fund’s (GF) latest assessment of its SPAR-based KPIs for PPR – the GF reported that countries are making progress in lab diagnostic capacity, surveillance is mixed (maturity of surveillance systems and timeliness are fragile in some countries), while rapid response capacities are one of the biggest vulnerabilities. The GF noted that, without sustained long-term financing, momentum is likely to slow: we agree with this assessment.
[9] Latest 2024 SPAR data – conducted between November 2024 and April 2025

43 single-country and multi-country projects from the first and second CFPs reported on the application of the 7-1-7 approach. Across these projects, 23 countries reported applying the 7-1-7 approach – 13 met 7-1-7 targets for at least one outbreak (e.g. Togo’s H5N1 response met an even faster 4-1-1 timeline). Additionally, 14 countries supported via the first CFP conducted 64 exercises – including simulation exercises, Early-Action Review, Intra-Action Reviews, After-Action Reviews, and/or Universal Health and Preparedness Reviews. This indicates some progress toward faster detection, notification and response.

2.2: Number and range of IEs involved in Pandemic Fund projects

The number and range of IEs delivering a project serves as a proxy for the depth of multi-sectoral collaboration and institutional complementarity – recognising that different types of organisations bring distinct strengths, such as MDBs in mobilising co-financing and UN agencies in providing technical expertise.

In the third funding round, 17 out of 20 proposals involved two or more IEs; on average, the number of IEs collaborating on a project was between two and three. Unlike the second CFP – which had four projects involving four or more IEs – no project in the third CFP had more than three IEs. 90% of projects included an MDB as an IE, with the World Bank the most common partner (featuring in 12 out of 20 proposals – 60%). MDB involvement rose sharply because of the Board’s decision to remove WHO as an IE from all projects selected in this round – this accelerated the trend of increasing MDB engagement (in the first CFP, 41% of projects included an MDB – increasing to 56% in the second CFP).

The third CFP shifted IE participation substantially. In the first two funding rounds, WHO acted as an IE in 91% of projects, chanelling about 48% of cumulative funding. Following the third CFP, WHO’s dominant role diminished in favour other multilateral agencies: FAO and UNICEF (alongside the World Bank) have expanded their presence, both in terms of project count and funding share:

- WHO is an IE in 41 out of 67 projects (61%) – $426.92m will be channelled via WHO (31% of total allocations).
- FAO is an IE in 50 projects (75%) – $312.76 m will be channelled through the organisation (23% of total funding).
- UNICEF is an IE in 34 projects (51%) – $128.09m (9% of total allocations).
We note that WHO remains a Pandemic Fund IE, co-chairs the TAP, and is eligible to be a Delivery Partner (DP) where requested by countries. Many beneficiary countries strongly support WHO’s continued involvement in PF projects funded via the third CFP: WHO will remain engaged in many countries as a DP – DPs are contracted by countries, regional entities (e.g. Africa CDC) or IEs to undertake discrete operational activities. Technical agencies, including WHO, FAO and UNICEF, bring significant value and expertise to projects – any future changes to the role/function of IEs and DPs should ensure their continued engagement in projects, including at a strategic level (alongside the ongoing technical advisory roles such entities play in executing their own mandates). A PF without the active engagement of all relevant UN agencies (at a project and strategic level) is a much weaker PF.

Since the 2025 AR, two new organisations have received IE accreditation (UNDP and IFAD). As of mid-March 2026, IFRC and FHI 360 are on Stage 3 of the three-stage accreditation process – the final step is executing the Financial Procedures Agreement (FPA) with the Trustee. Africa CDC remain on Stage 2, but – subject to Board approval – we anticipate that they will move to Stage 3 in spring 2026. UNFPA paused its application. 8 organisations are actively serving as IEs in PF projects: this is an increase from 6 last year.

We continue to encourage a more diverse range of IEs to be engaged in future CFPs, enabling countries to draw more effectively on the comparative strengths of different organisations. As highlighted in last year’s AR, collaboration should not just be measured by the number and range of IEs involved in proposals but should also extend to DPs. We therefore encourage the Secretariat to collect and report information on DPs engaged in-country, to give the Board clearer oversight of who is delivering activities on the ground and how collaboration is functioning in practice.

2.3: Collaboration with National Public Health Institutes (NPHIs) and regional/global networks and organisations

Collaboration with NPHIs and regional/global networks is included as an output indicator because it reflects the extent to which PF investments are embedded within existing health systems and institutions rather than operating in parallel. Strong engagement with national institutions and alignment with regional/global frameworks are essential for ensuring sustainability, coherence, and long-term impact – key to building resilient, country owned preparedness capacities that endure beyond the life of individual projects.

Following an update to the results framework, projects now report on how they leverage national institutions, such as National Public Health Institutes (NPHIs). 46 out of 47 projects from the first and second CFPs reported on the capacity of NPHIs (or other relevant public institutions – such as veterinary, agriculture and environmental institutions) to prevent, detect, assess and respond to public health threats. Of the 45 projects that have started implementation, 9 (20%) stated that an NPHI was not in place to oversee PPR activities, while 37 (82%) reported positively on successful establishment or enhancement of NPHIs and their role in improving disease detection and response capacity. Projects have also reported that national-level coordination has improved – with 44 projects noting enhanced partnerships in-country among ministries and other stakeholders.

Projects from the first and second CFPs reported on alignment of their work with regional or global networks and frameworks. Of these, 11 (23%) said that regional/global networks had no involvement in country-level PPR activities, 17 (36%) said there was ‘some’ involvement, and 18 (39%) noted more substantial engagement (e.g. resource pooling, knowledge exchange). For example, Bhutan’s project aligns with the Bay of Bengal Initiative for Multi-Sectoral Technical and Economic Cooperation (a regional cooperation framework); Moldova’s project is adopting EU disease surveillance and workforce standards; and Nepal’s project is coordinated with WHO’s Asia Pacific Health Security Action Framework. 29 projects reported establishing or improving cross-border coordination (e.g. through regional networks, bilateral partnerships). Many projects also enhanced their biosecurity and biosafety measures to meet international standards – for instance by upgrading laboratories to higher biosafety levels and training staff in line with WHO or World Organisation for Animal Health (WOAH) guidelines. This widespread alignment indicates that PF investments are not operating in isolation; they are reinforcing existing regional plans and global norms/standards.

There remains a need to ensure coherence between different PF-funded projects operating in the same country (or, for regional projects, the same region). 75 countries were covered by projects in the first and second CFPs – in 12 of these, there were involved in overlapping projects (for example, a single-country and multi-country project, or two multi-country projects). As delivery ramps up for projects funded in these rounds, IEs will need to identify and prevent overlaps and duplication by proactively coordinating with other each other (or, if it’s the same IE, within their organisation), sharing implementation plans and timelines, and engaging with national governments.

Recommendations for the year ahead

- Encourage a broader group of organisations to support the development of proposals, particularly regional organisations and Global South-led institutions.
- Incentivise collaboration between new and more experienced IEs, especially in multi-country and regional projects.
- Monitor and report on the range of organisations working as delivery partners, and map funding flows – from the Trustee, to IE, to Co-Investor, to DP, with transparency on fees and procurement processes.
- Ensure coherence between different Pandemic Fund projects operating in the same country. With overlapping projects in at least 12 countries, IEs (and other stakeholders) must proactively coordinate with each other (or themselves) to ensure activities are aligned.
- Consider the merits of evolution of the Pandemic Fund model, to enable funds to be allocated directly to countries, not via IEs.
Governance – Recommendations

An assessment of the Pandemic Fund’s operations and governance is set out in Section B. To help address the challenges identified, we have identified the following recommendations:
- Continue to provide support to co-investor constituencies ahead of Board and Committee meetings. Seek and act on feedback from co-investors on what actions can be taken to improve participation and engagement. The Secretariat and Board may consider exploring other options, including:
  - Provide guidance – and support, as necessary – ahead of the selection of a new co-chair from co-investor Board members in summer 2026.
- Through the Governance Committee, explore how the ‘terms of service’ for the PF’s co-chairs can be equalised – ensuring that the same term limits apply to both contributors and co-investors, enabling simultaneous co-chair rotation.
- Further develop and refine the TAP in response to feedback from the Board – noting concerns about potential conflicts of interest between WHO’s role as TAP co-chair and an IE. The Board will want to make the most of the TAP’s expertise while ensuring that TAP members are not over-burdened: this will be important ahead of the launch of the ‘high risk/high need’ funding modality.
- Develop a more comprehensive picture of how Pandemic Fund investments support climate change and biosecurity and biosafety related activities.
- Put in place an independent performance evaluation process of the Secretariat and co-chairs – identifying best practise from other multilateral funds, such as the Global Environment Facility.
## D: VALUE FOR MONEY

As the majority of Pandemic Fund projects are in the relatively early phase of delivery, a detailed analysis of the programme’s value for money will be included in the Project Completion Review (PCR), due in March 2027.

At this stage, we offer a preliminary assessment against the following pillars of value for money:

Economy: involves consideration of whether inputs are of appropriate quality and bought at a minimised price. The Secretariat remains lean, with 20 FTE (increasing to 22 FTE by end-FY26) and a budget of ~$12.6m in FY26. This low overhead – around 0.4% of cumulative contributions – should continue to be balanced against capacity needs. As noted in previous ARs, it remains important for the Board to monitor the Secretariat’s staffing and resources to ensure it can meet growing demands without undermining the Fund’s impact.

In the second CFP, the Fund introduced a cap on IE administrative fees of 7% of the grant requested, allowing up to 10% in Challenging Operating Environments (COE), FCAS and SIDS with appropriate justification. This cap, maintained in subsequent funding rounds, helps ensure that project overheads remain economical. Finally, leveraging co-investment and co-financing is a key part of the assessment of the Pandemic Fund’s economy: this has been covered in Section C.

Efficiency: considers how well inputs are converted into outputs. The PF has continued to move quickly in allocating resources: the first CFP concluded in July 2023 (10 months after the Fund’s establishment), the second CFP wrapped up in September 2024, and allocations for the third CFP were announced in November 2025. The PF also responded quickly to the 2024 mpox outbreak – allocating ~$129m to five projects supporting 10 countries. However, focusing too heavily on outbreak response could undermine the Fund’s core goal of building long-term preparedness, so such pivots must be balanced against capacity building objectives. The PF’s ‘high risk / high need’ modality will go live in spring 2026, with the window for applications remaining open for 12 months.

Efficiency also involves process optimisation – streamlining operations and systems to reduce waste, duplication or unnecessary steps. The Secretariat has continued to seek and act on feedback (from the TAP, IEs, and Board members) to improve processes – for example, the EOI stage from the first CFP was dropped ahead of the second funding round, and the application form has been streamlined and simplified (eliminating duplication and reducing cost/effort for applicants).

Effectiveness: considers how well the outputs achieve the intended outcomes and objectives. While it remains too early to fully assess impact, initial results from projects funded under the first two CFP are encouraging. For example, projects have already supported upgrades to around 300 laboratories and 12,000 health facilities and trained over 140,000 frontline health workers. In 22 countries that experienced disease outbreaks over the last reporting period, ~35% applied the 7-1-7 approach, with 43% of those meeting the target timelines for rapid detection, notification, and response – suggesting improved early containment capacity. Specific country-level gains underscore these trends. For example, Rwanda has launched a new electronic event-based surveillance system (Impuruza), with AI-powered border screening and a dedicated health intelligence centre, to speed up outbreak detection and reporting.

Nearly all projects from the first two CFPs have established baseline metrics for their interventions, so that impact can be measured once implementation progresses sufficiently. The PF has also improved its results framework, which incorporates clearer indicators aligned with the IHR monitoring mechanisms – enabling systematic tracking of outcomes across the portfolio.

Equity: this ensures that the benefits and costs of interventions are distributed fairly across different groups. The PF has taken further steps to embed equity in its funding processes and portfolio. The guidance for the second and third CFPs clarified expectations around community engagement, requiring applicants to demonstrate how civil society organisations (CSOs) and marginalised populations have been (and will continue to be) involved in proposal development and implementation. This has led to stronger evidence of CSO participation across funded projects, with over 80% of proposals in the third CFP including documented engagement with local communities. Geographic equity has also continued to improve, with a growing share of funding distributed to SSA. The TAP includes dedicated expertise in gender and social inclusion, strengthening proposal assessment from an equity perspective.

E: RISK

The main programme risks and mitigation strategies are identified below.

Risk	Description	Mitigation strategy
Policy and Programme Delivery / Rating: Moderate	Governance: an ineffective and/or non-inclusive governance structure may harm the PF's effectiveness / impact. For example, if structures are perceived to be non-inclusive it may reduce the Fund’s legitimacy in the eyes of co-investors and other developing countries; while ineffective structures may undermine the ability of the UK (and other donors) to have oversight of their investments and shape decision making.	The PF has a progressive Governing Board structure that brings together CSOs, recipient countries, donors, and IEs. However, it is important to ensure that this functions in an inclusive way so that non-donors can meaningfully participate in discussions and decision making. Effective governance requires continuous monitoring and evaluation. Identifying areas for improvement through feedback mechanisms allows for iterative adaptation of policies and procedures. FCDO will continue to advocate for this approach and work with its constituency on the Board to increase its outreach with non-donors on the Board to actively engage them in the Board’s workplan ahead of meetings/key decision points.
Policy and Programme Delivery / Rating: Major	Effectiveness and VfM of the Pandemic Fund: there is a risk that the Fund is not able to evidence the impact and VfM of its investments – particularly as it relies on timely and accurate reporting against its results framework by IEs, who may themselves face capacity constraints and/or delivery challenges (esp. in LICs and FCAS). Appropriate evidence-based advice from technical partners at both the project and strategic level; there is a risk that caps introduced on IEs may detrimentally affect this.	The Fund works through established IEs, who have a strong track record of cost effective delivery and robust M&E, and with whom the UK maintains longstanding partnerships. The PF (guided by the TAP) has developed a robust results framework and has iteratively strengthened its proposal assessment criteria following lessons identified from the first and second CFP. These measures aim to improve project selection, enhance performance monitoring, and support IEs in evidencing results, even in challenging delivery contexts. / The Board needs to identify a way to ensure IEs can provide advice at Board/ strategic level, as well as a project level; managing perceived conflicts of interest and noting that decisions are for voting members of the Board alone. We cannot expect the technical agencies to perform this function for free (especially in light of the pressure on their core budgets) and so the Board also needs to understand how to provide financial support to agencies, where such support is not provided for already.
Strategy and Context / Rating: Severe	Funding sustainability & political will: effective interventions in pandemic PPR require long-term investment that is sustainable over time. While the PF has received pledges of ~$2bn, this remains well short of the global PPR financing gaps identified to date (c. $10.5bn pa). There is a risk that PF interventions are unsustainable in the long run if they are not part of broader approaches that seek to strengthen health systems.	Continue to refine the PF’s co-investment and co-financing guidance/policies to crowd in additional investment from beneficiary countries and IEs. FCDO will work with other Board members and organisations to explore the development of options to raise PPR capacity in LMICs over the medium/long-term – including via domestic resource mobilisation, MDB financing, and improved alignment with other sources of ODA (e.g. prevention investment via the multilateral climate funds).

G: MONITORING, EVIDENCE AND LEARNING

The Pandemic Fund Secretariat remain committed to continually improving processes and systems in response to feedback. They also made efforts to incorporate lessons identified from the second CFP into the design of the third funding round.

Evaluations carried out since the PF’s establishment include: (i) independent (BCG-led) Stocktaking Review of the first call for proposals (2023), (ii) independent (BCG-led) TAP Evaluation (2023), (iii) TAP lessons learned from the second CFP (2024), (iv) Annual Progress Report for 2023-2024 and 2024-2025.