## Annual Review Template

Title: The South Sudan Humanitarian and Resilience Programme (SSHARP)
Programme Value £ (full life): £300m		Review date: April 2025
Programme Code: [AMP ID#] 301568	AMP start date: 17/5/24	AMP end date: 31/3/28

Summary of Programme Performance
Year	March 2025	September 2025	September 2026	September 2027	September 2028 (PCR)
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006100.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007079.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

SSHARP aims to: meet humanitarian needs (assistance and protection) for the most vulnerable people in South Sudan; boost resilience to conflict and climate shocks to strengthen vulnerable communities; and improve the efficiency and effectiveness of the humanitarian response. These outcomes will contribute to the impact of saving lives, alleviating suffering, protecting dignity and bolstering resilience. An additional impact is likely to be a reduction in conflict drivers due to increased social cohesion and resilience of communities to cope with shocks and stresses. Avoiding return to conflict is British Embassy Juba’s (BEJ’s) overarching aim.

To achieve this, SSHARP is organised around five outputs which work across the core objectives of the UK Humanitarian Framework: prioritise, protect and prevent. SSHARP’s output 1: emergency responses, and output 2: famine prevention, account for more than two thirds of the funding, including delivering critical food, nutrition, and water and sanitation assistance for the most vulnerable. The third output delivers protection including gender-based violence (GBV) prevention and response services. The fourth supports resilience and livelihoods as a way of preventing people falling further into humanitarian need. These outputs are delivered alongside a fifth, to create the enabling environment through common services, such as humanitarian logistics, data and evidence generation.
[note] UK Humanitarian Framework

Since SSHARP was approved in March 2024, South Sudan has continued to face a range of shocks and spikes in need. The negative impact of conflict in neighbouring Sudan continued, with over 1.1 million people seeking shelter in South Sudan since April 2023, and a range of economic impacts, such as disruption to South Sudanese oil exports, has removed significant government revenue. Extreme flooding affected multiple parts of the country from July to December 2024, and an outbreak of cholera, originally imported from Sudan, began in late September 2024. In January 2025, the pause in US foreign assistance – including USAID – had immediate effects and created persistent widespread uncertainty. Since March 2025, conflict in the north of the country has led to deaths, displacement and some embassies and agencies temporarily reducing their staff numbers.

The overall impact of US policy change in the coming months will be highly significant, but the detail of scope and size remains uncertain. The US contributes over half of all the humanitarian funding to South Sudan ($706m in 2024, or 54.1%) – a significant fall will change humanitarian action and outcomes. Already some NGOs in South Sudan are closing operations and the UN is restructuring. For example, IOM at the global level is “ending projects affecting over 6,000 staff members worldwide and implementing a structural realignment at headquarters, reducing headquarters staffing by approximately 20%”. The US policy adjustment represents a change to the established international humanitarian approach in South Sudan, but it is not inconsistent with longstanding messaging from humanitarian donors in the country that ultimately the government is responsible.
[note] Source: OCHA FTS - South Sudan 2024 | Financial Tracking Service
[note] Update on IOM Operations Amid Budget Cuts      | International Organization for Migration

The BEJ team is ensuring that SSHARP’s plans for year two are in line with the changing architecture to deliver outcomes despite the shocks: avoiding filling gaps (which is not a useful strategy given the magnitude of the gaps); determining alongside other actors what the critical priorities are and emphasising those areas; reviewing what could be reduced (partly in response to UK Overseas Development Assistance (ODA) announcements as well); driving transition opportunities, and seeking efficiencies in delivery.

Summary supporting narrative for the overall score in this review

This first Annual Review (AR) has fallen before the partner reports for the end of the financial year (the reporting year for SSHARP) are ready. Another AR will be carried out in a few months’ time to report against year one progress against milestones and therefore re-set the AR date to one that fits with the programme cycle. This AR has assessed to what degree the components are on track against the milestones, where possible, and discusses the process of mobilisation.

Overall mobilisation was complex, involving research for -and drafting of - seven Due Diligence Assessments (DDAs) resulting in 90 recommendations, as well as planning interventions and associated reporting/monitoring and risk management. The budget for the 2024/25 financial year (year one of SSHARP) also increased by 70% in-year due mainly to additional support from HQ for the impact of the Sudan crisis on South Sudan. This has added further complexity to programming. SSHARP mobilised 10 direct partners, which was a giant task taking six months to accomplish. This means the “year one” delivery is not a whole year of implementation. No deadline was set to achieve mobilisation and BEJ did not want to compromise quality of design, DDA or contracting phases; setting a deadline would have risked the inclusion of perverse incentives.

UN performance has been strong across agencies. International NGO (INGO) performance has been mixed, ranging from the Emergency Rapid Response Mechanism (ERRM) exceeding milestone targets, to THRIVE, missing all of its milestone targets. 10% of SSHARP outputs scored an A+ in this review (enablers – roads, airline and data); 60% of outputs scored an A (emergency response, famine prevention); 10% scored a B (protection/GBV); and 20% scored a C (resilience and livelihoods). The overall score is an A and the humanitarian work is higher performing than the resilience side.

Major lessons and recommendations for the year ahead

SSHARP was designed to meet complex humanitarian assistance and protection needs in one of the most difficult and dangerous humanitarian contexts in the world. SSHARP’s design also recognised the unpredictability and uncertainties of voluntary funding contributions, and the need to shift to more sustainable approaches for protracted caseloads. The design recognised the important role that UK investments could play in facilitating and enabling the rest of the system. All these things still stand, even – or rather, especially – in a context where the risk of widespread conflict within South Sudan is at its highest point since 2018, where the conflict in Sudan continues to pile on impact after detrimental impact, and as the system adjusts to new US foreign policy.

SSHARP has – and will – adapt to these challenges, and this adaptation will have the greatest chance of success if BEJ remains empowered to make flexible resourcing decisions that are informed by local conditions and regular field visits. Now, more than ever, it is crucial that our approach includes layering resilience and transition, emphasising a shift to more sustainable solutions so that humanitarian action can concentrate on timebound core lifesaving priorities and shift away from some instances of long-term service substitution.

The new and emerging US policy on foreign assistance post-dates the development of SSHARP but still serves to highlight the importance of donor coordination and joint approaches where they can assist with the Emergency Relief Coordinator’s “humanitarian reset and reimagining.“ The SSHARP design had already recognised this and the tools that the UK can best use to position the programme in this space. These include the UK’s position as Chair of the Humanitarian Donor Group (HDG) and seat on the Humanitarian Country Team Plus (HCT+). In South Sudan, the HDG has put forward coordination, resourcing, and policy steers for the year ahead, all of which have been informed by SSHARP. These include a mindset shift where humanitarian action is seen as the exception rather than the norm, only used when other options have been exhausted, and then swiftly transitions to more sustainable mechanisms where possible. International humanitarian actors should not be doing anything which could be done locally, and there is a need to shift to locally-led action where it increases value, access, and opportunity for transition. Similarly, identifying where SSHARP efforts could reduce (e.g. humanitarian health) and transition to other mechanisms such as the government/World Bank-led Health Sector Transformation Programme should be a priority for the coming year. And there will be a range of other options to consider at the project level for 2025/26, including getting the balance right between static and mobile provision, the role of cash, communicating with communities, and others.

SSHARP is now beginning to see its first results, although given the six-month mobilisation phase output, outcome delivery is still increasing and not at maximum level yet. The mobilisation phase was critical for specific project design and was unavoidable given the timeline for approval of the business case itself. This has, however, increased the risk that partners would not achieve spend targets/forecasts within a narrower time window. Fiduciary risks were mitigated (and ultimately avoided) with dedicated programme management, regular review, strong relations with partners, and budget reporting. In future, a mobilisation phase should be factored in post-business case approval but prior to the beginning of the financial year.

The business case states that up to 40% of SSHARP’s spend will be classified as International Climate Finance (ICF). The programme team estimates £28m of SSHARP’s budget in 2024/25 was spent on ICF; this is systematically tracked so we can measure progress against this objective and the ICF outcome indicator.

Key recommendations at output level, as described in section C, are:
- The South Sudan Humanitarian Fund (SSHF) should remain central to humanitarian action in South Sudan, especially as funding challenges become reality. Prioritisation (in scope and geography) and timebound response of the SSHF are as important as ever, but it needs to also look to efficiencies. BEJ should also continue to push for results that report on who has benefitted and how.
- BEJ team needs to track and articulate the different strands of work on cash transfers within SSHARP, and engage with the telecomms companies and other interested donors to explore improvements to mobile money cash transfers.
- BEJ to continue joint planning with IOM for years 2-4 on adaptations to transition work in the new funding context.
- BEJ needs to consider streamlining its GBV support in South Sudan as there are 4 funding streams under 2 programmes with similar objectives and activities which is unlikely to be efficient and represent good value for money.
- THRIVE to complete all action plan targets as set out and BEJ to tightly scrutinise progress on outputs, financial and programme management.
- A renewed focus on stakeholder management and influencing is required for IMPACT.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (TOC) for SSHARP is: IF vulnerable households in South Sudan are supported to meet basic needs, including through rapid humanitarian responses and services that reduce risks of famine, and IF households strengthen resilience through livelihood options that better withstand conflict and climate shocks, and IF this is enabled by more efficient, effective and coherent humanitarian and resilience interventions informed by evidence on what works in fragile and conflict settings AND with strengthened linkages to peacebuilding, development, and diplomatic approaches AND this is supported by advocacy and influencing to urge the government to increase accountability to, and investment in, its citizens, THEN humanitarian and protection needs for the most vulnerable people will be met, household food security and nutrition will be improved with greater resilience to shocks, overall resulting in lives saved, reduced suffering, protected dignity, and reduced conflict for the people of South Sudan.

Five assumptions were made in the business case that underpin this TOC. These still stand but two are at significant risk of being violated. First, the changes to US funding increase the risk that the humanitarian system will not continue to function adequately. Second, the assumption that the Sudan war does not cause fighting or economic chaos in South Sudan is showing signs of breaking down. The SSHARP strategy for year two will account for these risks.

The impact SSHARP aims to have, is to limit the increase of (or ideally promote a decrease in) the number of people in need of humanitarian assistance in South Sudan, while also contributing to reducing the drivers of conflict, via enhanced social cohesion and resilience of communities to shocks. This AR can present the baseline for numbers of people in need as measured by the Integrated Food Security Phase Classification (IPC) system – see below. And to create a baseline against resilience aims, an evaluation is under procurement.

From IPC:
To successfully reach the outcomes and impact of the programme, the BEJ team also needs to refine its strategic vision and hold the sector to a greater focus on outcomes. BEJ will maximise its role in the policy space (especially as chair of the HDG), as well as use its diplomatic capacity to strengthen the collective vision. This includes working with peace and development actors to strengthen complementarity and enable transition to more sustainable outcomes where possible. For SSHARP, output level service-based results under the theory of change will remain important, but leveraging broader policy change will be vital to contribute to the overall impact. The new funding era gives an opportunity to press for change. We will push the system to move to a more strategic vision-oriented way of working with greater focus on outcomes and on specific issues such as: meaningfully advancing the use of cash; pushing for transition of services to communities and/or government; and a move towards mobile, timebound responses rather than static responses that create dependence.

SSHARP supports climate outcomes primarily through the resilience and infrastructure components of the programme. This is measured by the ICF KPI 1: Number of people supported to better adapt to the effects of climate change as a result of ICF. Activities focus on improving sustainable livelihoods, such as strengthened markets for pastoral, agro-pastoral, and fishing communities, and the development – and application – of emergency coping strategies. SSHARP is testing a shift to strengthen climate resilient livelihoods in areas of high humanitarian need. Whilst this is a new approach for us, it aims to rebuild people’s coping capacity through the creation of small business opportunities such as vegetable gardening, transport services, and basic processing of agricultural products like fish and honey.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The six-month mobilisation phase and timing of this report mean that only results covering approximately one quarter are covered by this preliminary AR, and an updated AR will be issued in due course to report full results for the first financial year of the programme. While this precludes an immediate assessment of progress against outcomes, there are already indications emerging at the output level – these are highlighted in the individual partner sections below. In some cases there is an uneven level of progress within a given project For example with the ERRM we have seen an overachievement in cash distributions due to favourable market conditions in locations that required emergency response. At the same time, ERRM nutrition results are not yet at target levels due to external stock-outs, limited case-finding, and the displacement of volunteer staff. Beyond year one, SSHARP will also need to assess the impact of the two assumptions, which may not hold, especially in instances where SSHARP partner capability and capacity is reduced due to US funding reductions. BEJ has calculated that seven of the SSHARP partners were receiving over 50% of their total funding from the US. Partial drawdown of UK staff from BEJ in March 2025 due to the risk of conflict has further illustrated the difficult environment in which SSHARP operates, and which in turn may affect outcome achievement feasibility.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The cost of inaction or a further fall in funding for South Sudan is high. If people in need of critical humanitarian and resilience support do not receive it, then more will fall into higher severity of need. Reductions or limitations to humanitarian support could see a further deterioration in malnutrition trends for children; flooding risk could increase if preparedness steps cannot be taken; disease outbreaks could continue or spread further if health and water/sanitation/hygiene interventions are limited; and concentrations of people in areas of new or protracted displacement also leads to health and conflict risks if onward transportation is limited.
On the resilience side, discontinuation of efforts to develop communities’ coping strategies will increase the humanitarian caseload. All of these (non-exhaustive) outcomes from inaction carry enhanced conflict risk. SSHARP also complements planned BEJ support to the HSTP – the country-wide basic package of health services planned under HSTP does not have a surge/emergency function and humanitarian support therefore continues to be required where basic health capacity is overwhelmed. The programmes will be complementary: the care provided under HSTP will reduce the vulnerability of those potentially exposed to current or future harm, by extension reducing the humanitarian caseload. It will take the pressure off humanitarian services and provide health services with enhanced VfM. The SSHARP programme is BEJ’s largest programme with aims that underpin BEJ’s country plan (hence its overarching objectives), in particular to alleviate suffering and avoid a return to war.
## C. DETAILED OUTPUT SCORING

Output Title	Rapid emergency responses to new shocks are agile and conflict and gender sensitive.
Output number:		1	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
# Number of households receiving multi-purpose cash assistance (ERRM)	960	Exceeded. 2,883 as of 31 Dec 2024
# Number of households with improved access to water (ERRM)	4,000	On track. 1,962 as of 31 Dec 2024
# Number of people assisted through emergency response (proportion of UK funding) (SSHF)	156,000	SSHF data not available yet / ERRM total figures are offered as an alternative demonstration of progress. ERRM individual beneficiaries: 122,572 individuals. Some of the project participants received services in more than one sector. See table below.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on supporting rapid responses to new shocks or emergencies and is delivered by an NGO consortium, the Emergency Rapid Response Mechanism (ERRM), the UN Office for the Coordination of Humanitarian Affairs (UNOCHA)-managed Country Based Pooled Fund, and the South Sudan Humanitarian Fund (SSHF). Both mechanisms deliver timebound, short-term responses to unpredictable events or anticipatory action for future risk. As of December 2024, these mechanisms had delivered emergency response on the following occasions:

Mechanism	State	County	Trigger	Date of start of response	Delivery partners	Nature of activities
SSHF	Various	Aweil, Nasir, Pibor, Rubkona	Conflict related HNRP (Humanitarian Needs and Response Plan) priorities	May 2024	Various SSHF approved partners	Multisector
ERRM	Jonglei	Fangak	Flooding	21/08/2024	HFO/CINA/NRC/DRC	Health/ Shelter NFI/ Protection/ CCCM/ Education
SSHF	Various	Various	Flooding	September 2024	Various SSHF approved partners	Multisector
ERRM	Northern Bahr el Ghazal	Aweil East	Flooding/ conflict	21/09/2024	NRC/DRC	Cash, camp management, legal assistance, counselling, and shelter
ERRM	Eastern Equatoria	Lafon	Flooding	29/09/2024	NRC/CINA/MEDAIR	WASH/ Health/ Education
ERRM	Unity	Ganyiel – Panyinjar County	Flooding	18/10/2024	MEDAIR/NRC	Nutrition/ WASH
ERRM	Northern Bahr El Ghazal	Aweil South	Flooding	28/10/2024	DRC/NRC	Protection
ERRM	Upper Nile	Panyikang	Flooding	31/10/2024	SI	MPCA/ WASH
ERRM	Central Equatoria	Juba	Cholera	19/12/2024	TERM	WASH
ERRM	Unity	Mayendit	Flooding	30/10/2024	Medair	Health & Nutrition
SSHF	Various	Various	Cholera	November 2024	Various SSHF approved partners	Multisector, focus on health and WASH

ERRM beneficiaries per sector in this reporting period (HH= household):

	Individual beneficiaries (Based on 5 person households (HH) or individual number where provided)
HH multi-purpose cash	9,101
HH WASH non-food item (NFI) kits	1,117
Hygiene promotion	58,004
HH with improved water access	1,962
Improved environmental health	33,750
Acute malnutrition screening	2,669
Treatment for acute malnutrition	178
Nutrition volunteers trained	31
WASH NFI kits at health facility	30
Appropriate protection responses	2,930
Housing, land and property/collaborative dispute resolution rights	7,930
Detailed protection knowledge	81
Information on rights	25,581
	155,980

In South Sudan, the humanitarian sector has not succeeded in exiting from many areas due to the almost total absence of systems to which to handover. This has led to a degree of dependency from direct recipients and authorities, who have an expectation of aid, with the latter not delivering basic servicesthemselves. In the new era of hugely reduced international funding, the UK and humanitarian donor counterparts will push for momentum towards an even greater rapid response, mobile, timebound mode of delivery and away from long-term support in areas of dependence.

ERRM is on track to meet their logframe year one milestones and have overachieved in some areas, such as household (HH) cash. This is in line with the UK’s policy of maximising the use of cash. ERRM was able to demonstrate a reasonably quick reaction time in responding to emergencies, with 40% of their responses initiated within 14 days of receiving an alert. This falls below the target percentage of 65% but still demonstrates their ability to rapidly mobilise on some occasions. The BEJ team monitored their work in Juba IDP camps in January 2025 and was impressed with delivery.

We do not have the data from SSHF’s 2024 performance yet. That said, there are some achievements relating to localisation, enhanced agility and cholera response in 2024 to report on:
- We hope to see increased efforts towards SSHF’s vision for enhanced localisation, in line with the direction set by OCHA’s Emergency Response Coordinator in Geneva in response to the sector-wide funding challenges. Strengthening the national NGO sector to respond to emergencies is a pathway to more creative, sustainable and efficient responses. As well as a minimum of 25% of SSHF funds being channelled through national NGOs (NNGOs), SSHF allocated $500,000 in 2024 for training for NNGOs to build their capacity to access international donor funding, a decision which we have some reservations around but will look to see further evidence of results.
- To enhance agility, in this reporting period, SSHF opened a funding window that could disburse funds within 48 hours for emergencies.
- A funding allocation was made for cholera, though we had reservations with the cholera response decisions in Unity State, where arguably more priority could have been given to immediate staffing gaps with existing implementing partners. BEJ raised this with OCHA and WHO at the time.
Describe any changes to this output during the past year, and any planned changes as a result of this review. None.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

LESSON: Through ERRM, we can see the importance of coordinating through the bodies which assess needs in the country (including the Inter-Cluster Coordination Group (ICCG) that ERRM staff have now joined and the Needs Analysis Working Group (NAWG)). This brings them into the wider system, complementing their own criteria regarding where to intervene and where not to. An example of a good outcome from this level of connectedness was their response to cholera, which was timely, targeted to hotspots in Unity State and Juba, had high needs and a lacking response, and was well-coordinated with other aspects of the response, such as the vaccination campaign. BEJ monitored the ERRM cholera response in Juba and assessed the response as high quality.

LESSON: ERRM provides relief for crisis-affected populations for a maximum of three months. The sector can learn from this approach, especially how they manage their exit. Exit strategies include communicating clearly with communities from the outset, seeking government or community-led services to hand over to, but still departing even if they cannot be found and once initial emergency needs have been met. Funding cuts mean the humanitarian sector as a whole is looking at the balance of static versus mobile provision, and so these lessons are timely. ACTION: ERRM to work through HDG to share lessons for future ‘end of response’ options, including in situations where transition to other actors is difficult or not possible. BEJ has facilitated one lesson learning session on this and commits to organise more in 2025.

RECOMMENDATION: SSHF should remain central to humanitarian action in South Sudan, even as (or especially as) funding challenges become reality on the ground. Prioritisation (in scope and geography) and timebound response of the SSHF are as important as ever, but it needs to also look at efficiencies, for example avoiding too wide a number of partners and the overlap of overheads. BEJ (jointly with HDG peers) continues to advocate for strategic use of the fund, and greater transparency around how the funding choices enable this. SSHF could help to facilitate this with more timely communications on potential interventions at the correct level of detail.

RECOMMENDATION: BEJ will continue to push for results that report on who has benefitted and how – i.e. humanitarian effectiveness - not simply results reporting on processes. And the SSHF needs to avoid any situations of ‘giving a little bit to everyone,’ or the temptation to use it to assist struggling organisations as a result in itself. SSHF needs to be ready to make difficult and unpopular decisions in order to prioritise humanitarian effectiveness.
Output Title	Inclusive and accountable provision of cash, food, nutrition and WASH for households and communities in areas of greatest need
Output number:		2	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of internally displaced persons (IDPs) affected by flood/conflict receiving cash assistance sufficient to meet basic needs (measured by receipt of cash to the value of a "Survival Minimum Expenditure Basket”). (IOM)	1,000 HH (approx. 5,000 people)	This was reduced in-year to prioritise the onward transportation, to avoid an unsustainable and highly risky build-up of people in Renk, coming across the border from Sudan. It will be resumed in years 2-4. / Target number of households (HH) for Y1 is 1,000. This will now be zero. / Total overall target for 4 years is 3000 HH – this will be reduced to 2000 HH.
Number of people receiving food assistance unconditionally (disaggregated by sex) (WFP)	125,778 / (F=69,178; M= 56,600)	Met: 227,850 / (F=142,846 M= 85,004 ) / Initial plan was expanded due to UK funding uplift – this should have been reflected in the logframe by an adjustment in the milestone, not the appearance of over-achievement. This is met, not exceeded.
Number of primary caregivers of children aged 0-23 months who received Maternal, Infant and Young Child Feeding Nutrition (MIYCN) counselling services (UNICEF)	429,863	On track: 241,275 caregivers reached with UK funding between August (start of the UK-UNICEF agreement) and December 2024. At this rate the milestone will be met by end-March.
Number of displaced individuals having access to sufficient and safe water for domestic use in Malakal PoC and Bentiu IDP Sites A&B. (IOM)	40,427	No data yet and some concerns with the indicator are being ironed out.

Briefly describe the output’s activities and provide supporting narrative for the score.

The aim of output two is to prevent famine via use of a multi-sectoral response targeted to populations in areas evidenced as being most at risk. Delivery is via UN partners (WFP, UNICEF and IOM). There is also a special focus on helping displaced people who have been receiving long-term humanitarian assistance (in some cases for over a decade) to transition away from this reliance. Food insecurity has worsened dramatically in the last decade, both in absolute and percentage terms; maps below. Increased food insecurity is a consequence of conflict, climate change and economic shocks. Famine or famine-likely conditions were declared in parts of the country in 2017 and 2020, and, at present, an estimated 31,000 people are in “IPC-5” (“famine like conditions”).
[note] South Sudan: Acute Food Insecurity Situation for September - November 2024 and Projections for December 2024 - March 2025 and for April - July 2025 | IPC - Integrated Food Security Phase Classification

Deterioration in food security 2014 (LHS) to 2024 (RHS). Orange is IPC-3 (crisis), red is IPC-4 (emergency):

UK funding to WFP is intended to reduce the percentage of households with “poor to borderline” food consumption in targeted areas; reduce the application of negative coping strategies that people employ when they lack food; and contribute to prevention of malnutrition. The delivery modality is a mix of full cash distribution where there are functional markets, and full in-kind or hybrid (combination of cash and in-kind) food distribution where markets are insufficient or cash is not deemed appropriate. Based on global evidence, SSHARP encourages the move from in-kind food assistance to cash, which demonstrates cash to be a more efficient way of meeting critical needs, while also supporting the choice and dignity of households to decide how to meet their own critical needs.

Regarding cash distribution this year, WFP distributed £35m in South Sudan, of which £0.9m is attributable to UK funding. South Sudan is an expensive operating environment and due to extremely poor physical and digital infrastructure, the unit costs of getting the physical cash to where it needs to be are almost as high as the value of the cash delivered. Despite significant limitations we continue to push partners, including WFP, to: i) persevere with cash as a modality; and ii) use mobile money as far as they can. In areas where cash is not yet feasible, WFP distributes food.

WFP uses South Sudan’s dry season to procure food at scale and pre-position it to logistics hubs in strategic locations. This ensures food is in the right locations and ready for dispersal ahead of the rainy season, when roads become impassible. The chart to the left shows the metric tonnes (MT) of WFP food procured, received and distributed (using all contributions, including the UK’s) for the 2025 rainy season (which begins in around May). As of end of December 2024, SSHARP shad facilitated procurement of 8,851MT of food for 227,850 vulnerable people in SSHARP geographies. £25.3m of SSHARP’s uplift was then spent by WFP in early 2025 on an additional 12,800MT of food for 497,500 people in SSHARP geographies (some of the same people will receive more rounds of food assistance).

Our work with UNICEF focuses on integrated nutrition, water, sanitation and hygiene (WASH), multi-purpose cash assistance (MPCA), and services for children and caregivers who have experienced violence (see output three of this AR for more detail). Nutrition and cash support is targeted to pregnant women, new mothers, and their infants alongside provision of advice on appropriate child and family nutrition, while WASH support is prioritised to take place in nutrition facilities in SSHARP’s priority geographies. Since the SSHARP agreement with UNICEF began in August 2024, 194,975 primary caregivers of children under two years have received nutrition counselling services.

SSHARP is supporting UNICEF to increase efforts to use cash differently, enabling caregivers to make the best decisions for their family and achieve positive nutrition outcomes; unconditional social protection cash assistance to 1,300 caregivers over the first year of a child’s life. This will be in Ruweng Administrative Area, and builds on lessons learned from the Young Child Support Grant supported under SSHARP’s predecessor (HARISS). The 1,300 individuals taking part in the pilot will also receive the counselling services measured in the indicator above, with the aim of helping us understand more about how the combination of cash and counselling boosts nutrition outcomes. The first cash transfers were planned for April 2025.

As of the end of 2024, UNICEF reporting shows they are on track to meet the milestones for 12 of the 16 nutrition and WASH indicators that have milestones for March 2025. In some cases, they have already met the milestones. For example, SSHARP funding has allowed 4,000 people access to sustainable water systems and paid for 36,299 children with severe acute malnutrition to be admitted for treatment to a health facility.

SSHARP/BEJ pushes partners to integrate across sectors, which means delivering multiple services in a particular geographical area, rather than requiring affected people to travel between different centres to collect the essentials. This is important as South Sudan’s physical infrastructure, whether public transport or roads, is extremely limited, and the country suffers from both extreme heat and extensive flooding. UNICEF is moving in this direction with the multisector support that it offers.

In partnership with IOM, SSHARP supports internally displaced people (IDPs) in South Sudan, host communities, displaced people from Sudan, and national level enabling efforts. South Sudan has 1.84m IDPs, most of whom live in host communities; significant populations reside in more formal camp or camp-like settings. IOM’s SSHARP-funded support sits under output 2 (famine prevention) but will increasingly contribute to output 4 (resilience). Specifically, under SSHARP it includes multisector lifesaving support (Camp Coordination and Camp Management (CCCM), WASH, shelter and non-food items (SNFI), and health); flooding response; onward transportation for returnees (and refugees immediately at the border) crossing from Sudan; and transition.
[note] South Sudan | Displacement Tracking Matrix

The objective regarding transition is to achieve measurable progress towards an exit from protracted humanitarian aid delivered over the long term, which systems (and, in some instances, people) have become reliant on. This means greater community and/or government ownership of basic services and people eventually moving out of the IDP camps (or integration of camps). IDPs in South Sudan have received static humanitarian assistance for – in some cases - many years and are a target group for transition to a more sustainable way of management.

Examples of IOM’s work under SSHARP include designing cost recovery systems for water supply and engagement in resettlement discussion. BEJ staff visit the largest IDP camp, Bentiu, regularly (most recently in November 2024), to observe IOM’s work; regular field visits to other IOM locations, such as Malakal and Renk, are also undertaken. The depth of knowledge of IOM field staff is impressive, especially regarding: the technicalities of water supply systems and potential to move to cost recovery; the camp politics around changing how services are provided; and the wider politics around land ownership. For example, IOM introduced us to people who are displaced due to flooding and have moved onto the land of some of the people who live in the camp, further complicating the dynamics.

Since the US aid announcements in early 2025, IOM and BEJ have agreed that accelerating transition is the most effective policy stance that would result in long-term sustainability; the humanitarian response in the camps becomes even less feasible with reduced funding. To this end, BEJ will work with IOM to design the coming years’ work under SSHARP.

Deep Dive: detail on IOM WASH activities:
- WASH provision delivered in partnership with IOM has evolved to focus on transition to more sustainable systems. HARISS focussed on the day-to-day provision of water, including up to 15 litres of water per person per day. This delivery model inadvertently created a protracted model of service provision, which has been in place at former Protection of Civilians (PoC)/IDP locations since the conflict in 2013, with no vision on how to move away from this model. SSHARP seeks to correct this design flaw,breaking this cycle of dependency regarding water supply.
- SSHARP remains complementary to EU and US (although now paused) funding – this allows concurrent investments, which work to reduce the need for expensive fossil fuels and aluminium sulphate and instead shifts to solarisation and other techniques, such as reduced turbidity or groundwater sourcing. The long-term intention is to incentivise ownership by relevant authorities by supporting the transition to a tariff-based system, simultaneously creating a permanent revenue source for local authorities and catalysing their interest and capacity to manage it.
- Results will not be immediate, and certainly not within the single quarter of implementation covered by this report. Nevertheless, ultimately over 127,000 people will benefit from systems running at reduced cost, whilst shifting to locally-led ownership and maintenance. Critically, this is intended to break the cycle of donors committing funds year-on-year with no end in sight.
- Specifically, this means:
  - For Malakal PoC camp, WASH transition activities include ensuring that all water for over 43,000 IDPs is supplied without relying on fossil fuels (current annual cost of diesel is £74,000), and a reduction in aluminium sulphate usage (annual cost £125,000) by reducing turbidity of surface water.
  - For Bentiu IDP camp and IDP sites, over 38,000 individuals should benefit from IOM’s utilising of groundwater as the main water source. Utilising groundwater will eliminate the need for aluminium sulphate (annual cost £140,000) or sand filtration, as the aquifer’s soil acts as a natural filtration system, providing higher quality water at a lower cost. The water systems in the IDP sites were fully solarised during HARISS, which saved an investment of £110,000 per year in fuel to operate the water supply infrastructure. The next stage of transition would be for this solarisation to support the transition to a tariff-based system, creating a permanent revenue source for local authorities, while also catalysing their interest and capacity to manage it.
  - For Bentiu IDP camp, self-sufficiency, self-governance, equity, and income-generating potential will be achieved by optimising the solar energy capacity of the existing water supply system. The aim is to ensure that all water for over 46,000 IDPs is supplied without relying on fossil fuels (current annual cost £159,000).

In response to increasing numbers of people crossing the border from war-torn Sudan, a critical element of IOM’s work is onward transportation assistance (OTA). OTA enables the people (mostly South Sudanese returnees) to move voluntarily to their areas of origin or intended destination, where they have community networks, better access to markets and financial systems, and possibly can claim historical ties to land. They may alternatively choose locations with better access to services provided by the humanitarian and development sectors. Either way, it reduces the density of people near the border, which poses an increasing risk of disease outbreak, conflict and too much pressure on WASH and food systems. In the final quarter of 2024, SSHARP funding through IOM ensured dignified and safe transportation for 4,350 people via boats out of Renk and 10 flights out of Malakal on a weekly basis. Sudan-driven displacement is tracked here: Microsoft Power BI.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Given the US funding uncertainty, BEJ exercised programmatic flexibility, swiftly switching funding in Q1 of 2025 towards OTA with IOM. Funding moved away from some of the operations whose actions/impacts could be achieved in slower time, for example, some elements of camp management displacement tracking, and multi-purpose cash assistance (MPCA). The MPCA originally planned to cover new displacements in Malakal and Bentiu, but these were fewer than expected and could be covered with other donor funding that was less flexible than the UK’s. This responded to an emerging risk by delivering the following results:

1. 4,350 people moved by boat from Renk to Malakal or by air from Malakal to other locations.
2. 10,000 people moved by road from Joda point of entry (at the border) to Renk Transit Centre.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

LESSON: Having some unprogrammed funds allowed the UK to add surge capacity to a crisis. SSHARP had £1m unprogrammed and we were able to put this towards the cholera response, directing funds to where the needs were greatest with the partners that were able to deliver at that time. That said, allocating funds within the year makes us a less predictable donor, undermines the concept of buying into agencies which should be able to direct their own funding to emerging crises in an efficient way, and takes up BEJ staff time. Our conclusion is that holding a small minority of funds as unallocated during the year to support emerging crises is worth doing.

LESSON: For the transition agenda, taking time to secure the buy-in from local government and the community is essential for changes to work. Where changes were made without consultation or deep consideration of potential impacts, these were not successful. For example, the move to using local materials for latrines, whilst sustainable, was unpopular. Conversely, where there is support, the changes can work (for example, government support for land tenure can result in successful relocations, as they have in Malakal).

RECOMMENDATION: BEJ team to track and articulate the different strands of work on cash transfers (WFP, UNICEF and IOM), ensure learning is an output (potentially using BEJ’s forthcoming third-party monitoring programme), and actively guide the UN to adjust its delivery mechanisms to improve value for money. BEJ team to also engage with the telecomms companies and other interested donors to explore improvements to mobile money cash transfers, albeit in recognition that this only reaches a minority of South Sudanese in need. This is a key theme in the business case.

RECOMMENDATION: BEJ to continue joint planning with IOM for years two-four on how the transition work can be adapted for years two – four of SSHARP. BEJ and IOM met to discuss the US funding pause in February to test if assumptions underpinning the programme still stand. Options included a greater emphasis on core emergency support or to continue focus on transition. IOM is adamant that transition needs to be the priority to break the cycle of protracted service delivery. BEJ is supportive of this as it is in line with the approach set out under SSHARP, but BEJ must continue to manage risks associated with it and adapt if needed.
Output Title	Effective GBV prevention and response initiatives and psychosocial support for women and girls, men and boys
Output number:		3	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of women and youth participating in economic empowerment activities. (GOAL and IMC)	1,020	Not met (IMC on track and GOAL off track) / GOAL: 0 / IMC: Estimates that at least 550 women and girls were involved in economic empowerment activities by end March but data not formalised yet (this would exceed IMC’s milestone of 220).
Number of individuals benefiting from GBV response services. (IMC and UNICEF)	17,045	Not likely to have been met / IMC: 3,476 up to Dec 2024. Off track. Delayed start is attributed to refurbishment of Women & Girls’ Safe Spaces (WGSS), procurement of supplies, and community mobilisation. / UNICEF: up to Dec 2024: 7,130 out of a target of 7,500: on track.

Briefly describe the output’s activities and provide supporting narrative for the score.

International Medical Corps (IMC), THRIVE (GOAL-led consortium), UNICEF and ICRC contribute to this output for SSHARP. The focus is on supporting survivors of GBV through timely response work, remedial care, and environment building to prevent future risk, including by empowering women and changing social norms. GBV is endemic in South Sudan, exacerbated by humanitarian crisis, climate-related shocks, and a range of negative coping capacities. ICRC also contributes via a more broadly defined focus on protection issues.

Both THRIVE and IMC had fallen behind their expected/target milestones as of December 2024, under-achieving due to delayed programme establishment. However, IMC noted that they put acceleration plans in place to meet their targets for March 2025, and expect that when data are collated (up to end March) they will have met their milestones. UNICEF is largely on track against its objectives under this output. The mixed picture earns a score of B. It is not a C (despite THRIVE’s outputs) because IMC is likely to achieve against milestones and UNICEF is highly likely to. There are no ICRC indicators in the SSHARP logframe.

IMC began implementation in mid-October 2024, so results under this initial AR cover less than a quarter (and should therefore be considered within this context). Activities achieved up to December 2024 included: response services comprised of case management for survivors as well as Women and Girls Safe Spaces (WGSS) at seven locations, community asset mapping, referral service mapping, and the formation of activities geared towards prevention.

THRIVE has also been working on establishing its programme, which supports the prevention and resilience aims of this output. THRIVE aims to complement IMC by enrolling GBV survivors from IMC’s caseload in economic empowerment activities run by THRIVE (see output 4 for further explanation).

UNICEF and its downstream NGO partners support the delivery of services that respond to needs of vulnerable women and children, including survivors of GBV. Services are delivered in shelters, women and girl-friendly spaces, child and youth-friendly spaces, nutrition outpatient sites, and in the community in Unity, Upper Nile, and Jonglei/Greater Pibor Administrative Area States. Response activities include case management and psychosocial support delivered by trained providers in static spaces and through mobile teams. A leading theme under this project is strengthening coordination and referrals between GBV and nutrition partners. Trainings in this regard have led to improved coordination and increased two-way referrals (that is, teams at nutrition sites learn to identify and refer cases of GBV and vice versa). Under SSHARP to date, UNICEF has trained 157 nutrition and GBV partners (102 male and 52 female) in Unity (Bentiu), Jonglei (Bor), GPAA (Pibor) and Upper Nile (Malakal and Renk) on the “GBV risk mitigation in nutrition package”.

SSHARP support to ICRC contributes to outcome 1, and delivers parts of outputs 1, 2, 3, and 5. ICRC reporting will not be received until the second iteration of this AR. Given the political crisis in South Sudan, as of March 2025 and the increased risk of conflict, protection and assistance delivered by ICRC will become an increasingly important aspect of SSHARP, including in the most difficult circumstances where the adherence to International Humanitarian Law (or appropriate laws and norms in other situations of violence) needs to be central to the BEJ approach. For the purposes of AR documents, ICRC will sit under output 3 but we note its contribution to outputs across SSHARP.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

NGO partners are relatively more exposed to US funding reductions than the UN, so we will need to work with them to manage this risk. The BEJ team had intended that the GBV work with UNICEF would only fall under year one of SSHARP to bridge a gap in BEJ’s separate programme with UNICEF on GBV (GBVPSS). Given: i) the relative success of the intervention under SSHARP; ii) the risks to the sector due to aid cuts; and iii) the specific approach of bringing sub-sectors together, we are considering continuing with this workstream with UNICEF into year two.

The protection sector is already seeing delivery partners closing due to funding cuts, especially in Renk. Protection work is also vulnerable to other parts of the system contracting, such as the drugs supply chain (e.g. in the clinical management of rape). The prevention and resilience element can be harder to evidence and will therefore be under pressure as the humanitarian system contracts.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

RECOMMENDATION: BEJ needs to consider streamlining its GBV support in South Sudan as there are four funding streams under two programmes with similar objectives and activities, which is unlikely to be efficient and represent good value for money.
Through GBVPSS, BEJ is funding an evaluation of what works in terms of prevention and resilience, and this can inform the SSHARP activities, albeit not for at least a year. This is necessary given the existential threat to the work.
Output Title	Livelihood interventions which strengthen coping capacity implemented with vulnerable communities.
Output number:		4	Output Score:	C
Impact weighting (%):		20%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of value chain actors supported with training, inputs, equipment, or services by the programme (GOAL and WFP)	50	Not met / GOAL: zero / WFP: milestones are zero for year 1
Percentage of Community Action Groups that have implemented at least 70% of their Community Action Plan activities (for risk management and preparedness) GOAL	40%	Not met / Zero.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output works to find solutions to the reality in South Sudan that livelihoods are hard to sustain due to multiple shocks often faced by communities. These include conflict, climate and economic shocks. Communities often need to rely on humanitarian assistance as a result. This is a challenging agenda that is repeatedly knocked off course but continues to test new solutions to creating more shock-proof livelihoods. An example of the repeated challenges is the war in Nasir and Ulang in early 2025, which has led to the cessation of SSHARP operations in those areas. Very sadly, one of GOAL’s security guards was killed. In the new era of reduced aid, helping communities to be able to manage shocks without external support becomes even more urgent.

Multiple partners contribute to this output, including WFP, THRIVE and, to a lesser degree, IMC through its resilience work under the protection output. The output scores a C because THRIVE is yet to achieve any outputs; progress against all milestones by end of March 2025 was zero. WFP made progress under its livelihoods agenda but missed its milestones (albeit narrowly in most cases). Unhelpfully, the one indicator measured in the SSHARP master logframe for WFP on livelihoods is not set to begin achieving until year two.

THRIVE is establishing its programme of community-led, context-specific livelihoods and market strengthening interventions to increase the resilience of vulnerable pastoral and agro-pastoral communities to climate and conflict shocks. Delivery partners work in target locations that overlap with humanitarian assistance. The rationale for this co-location is: i) to provide a continuum of services so that people in the worst areas can graduate from humanitarian assistance to ??; and ii) to operate where people are at most risk of falling into humanitarian need and help to prevent caseloads increasing. The fall in humanitarian aid will lead to fewer counties being targeted by humanitarian assistance. This reduces the strength of the first part of this rationale (as the resilience intervention may end up operating in multiple areas where humanitarian aid has ceased) but not the second.

Implementation of most activities by THRIVE has not begun yet – at the time of writing, this intervention has only been mobilised for five months. Optimism bias and planning challenges meant that the logframe was not re-visited to account for delays in mobilisation, so the intervention has over-promised and not delivered. A realistic estimate of progress around November 2024 could have avoided this. Despite no output-level results yet from THRIVE, foundations have been laid, and process indicators have been met. Specifically, the team has set up offices across the country, recruited staff, and undertaken assessments. These assessments are providing essential data to guide implementation and measure progress. Examples (not exhaustive) include: assessments on livestock migration and value chains; agro and non-timber forestry; and conflict sensitivity. Procurement is underway, includingfor the workstream that aims to kick-start the fishing sector in Upper Nile State through increased access to boats, nets, and solar-powered refrigeration.

WFP’s approach involves providing targeted communities with graduating levels of resilience assistance, in select communities, in three counties under SSHARP geographies (classed as priority two (on a scale of five) under South Sudan’s UN-led Humanitarian Needs and Response Plan (HNRP)). Two of the three counties are also targeted by THRIVE. Communities move through General Food Distribution Plus (GFD+, which combines standard unconditional food assistance with additional voluntary activities such as training on vegetable gardening, baking, and nutritional information sharing); Asset Creation and Livelihoods (ACL); and then Smallholder Agricultural Market Support (SAMS) as communities become increasingly less dependent on support. Shocks faced during the transition can be catered for with a once off delivery of food or cash or (in extremis) regression to the previous stage. Over three years, a community will move from GFD to ACL, ACL+ SAMS, and eventually SAMS only by the final year. Reporting at end March shows that 30,440 people have received conditional assistance from WFP against a milestone of 40,000. 16,090 are female and 1.9% are disabled people.
[note] South Sudan: Humanitarian Needs and Response Plan 2025 (December 2024) | OCHA

Partners under this output have been co-ordinating to ensure complementarity in both approach and beneficiary selection. THRIVE and IMC have developed a joint mapping tool so that beneficiaries receiving protection assistance can be referred to THRIVE for livelihood support, while IMC’s economic empowerment approach is aligned with THRIVE work. WFP and THRIVE have established strong working relationships to avoid duplication via a joint beneficiary selection process, and identify complementary activities so that beneficiaries receiving food assistance from WFP may be referred to livelihoods or market strengthening activities provided by THRIVE. Also, livelihoods interventions from WFP link to the market strengthening work of THRIVE.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

BEJ received an uplift of £1.5m in financial year 2024/25 from HQ’s Resilience and Adaptation Fund (RAF), which was spent by THRIVE. To spend this funding before the FY24-25 year end, THRIVE scaled-up existing interventions to avoid mobilisation delays for new activities. RAF projects included the construction of aggregation and storage facilities for fishing communities, 1,000 people trained on post-harvest management and catch practices, and 18,200 people gained access to veterinary supplies. To improve risk management and preparedness for climate shocks, 200 farmers were supported to establish flood resistant or adaptive vegetable gardens, and 700 farmers were supported with fodder production and land management practices. These results are captured under the RAF logframe and do not contribute to SSHARP AR scoring.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons have been learned about consortium management; THRIVE has already undergone consortium restructuring due to multiple failures. The BEJ team has agreed an action plan with GOAL (consortium leader) to ensure the restructuring is effective.

RECOMMENDATION: THRIVE to complete all action plan targets as agreed and BEJ to scrutinise closely progress on outputs, and financial and programme management.

Output Title	Humanitarian actors better demonstrate approaches that are inclusive, accountable to affected populations, and value for money.
Output number:		5	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of analytical products produced to support humanitarian strategic planning, and annual prioritisation (REACH)	12	18. Exceeded. / As of end of March, IMPACT has published and disseminated 18 analytical products, with an additional 14 products pending dissemination.
Number of assets built, restored, or maintained as a % of planned. (% of km roads and dkyes) (WFP).	80%.	70%. Met under difficult conditions. / This was met but the SSHARP attribution of 80% was erroneously calculated when the logframe was finalised. The % is capturing the proportion of the 826km of roads and dykes that WFP is rehabilitating that is UK funded and completed. All SSHARP funds were spent but this amounted to 70% of the total.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on creating the enabling environment for high quality humanitarian assistance delivery in South Sudan. It includes: contributions to data and evidence; coordination of the sector; policy and advocacy efforts; ensuring accountability to affected people; the humanitarian airline, UNHAS; road maintenance; and dyke construction and maintenance. The output scores an A+ because the data and evidence workstream exceeded expectations, the airline scored highly against its objectives, and the road and dyke construction was achieved despite a very narrow window for the work to go ahead, involving an impressive set of risk mitigation activities.

This intervention will become increasingly valuable in the context of reduced aid funding – it will provide the evidence to direct scarce funding where needs are highest. The INGO IMPACT (REACH) has made good progress in collecting and using data to influence decision making and delivery of humanitarian aid.
- REACH is on track to produce 32 analytical products within year one, with 18 products published and disseminated by April 3. These include an Integrated Public Health Rapid Assessment (IPHRA) in Internally Displaced Persons (IDPs) sites within Rubkona County, an emergency qualitative food security assessment in Aweil East, and a SMART Survey in Malakal. These assessments help the humanitarian response target the right places and people. For example, SMART surveys are a primary way of assessing and monitoring the nutritional status of populations affected by emergencies or humanitarian crises, and the data they produce allows humanitarian actors to know what assistance is needed and where, which can include directing life-saving assistance to acutely malnourished people.
- They are also refining their Emergencies Monitoring System (EMS) which flags current hotspots where interventions should be prioritised. This is regularly disseminated widely.
- Through IMPACT’s co-chairing of the Needs Analysis Working Group (NAWG), they are well-placed to ensure that the evidence it brings is brought to the attention of the Inter-Cluster Coordination Group and other decision-making fora.
- In October, they sent 13 analysts to the Integrated Phase Classification (IPC) analysis, supporting the classification of acute food insecurity and acute malnutrition for the country.
- Following the release of the IPC data, IMPACT made tailored presentations for multiple decision-making stakeholders in South Sudan on the food security situation. These used data from EMS and field work in Jonglei and Northern Bahr el Ghazal states as well as IPC data.
IMPACT has developed a research workstream on accountability to affected populations (AAP); a key theme of this output. During this reporting period, IMPACT began a qualitative deep dive into the experiences of female returnees displaced from Sudan, and their integration into host communities in South Sudan. This assessment will support the implementation of other SSHARP activities, including improvements to the provision of GBV services. Also on AAP, UN partners have community feedback mechanisms; information-sharing programmes support communities to make informed decisions. For example, WFP internally shares analysis and results from process monitoring and feedback collation, which ensures that actions are taken in response to recommendation. At outcome level, results are shared with partners to enable corrective actions at field level, with results also informing operational guidelines. Actions are systematically tracked to ensure evidence-based programme adjustments. This is all with a view to ensuring results-based programming and decision making.

This output also focuses on the logistics required to enable the humanitarian response, predominantly through the funding of WFP’s airline (UNHAS) and their road improvements initiative. Road improvements help to reduce the proportion of aid that is delivered by air, and therefore improves value for money. Given the poor state of the roads across the country, the airline remains critical to food delivery, as well as for donors, implementing partners, and BEJ staff travelling outside of Juba. Indicators show good performance from WFP on logistics:
- During the reporting period, UNHAS provided air transport services to 239 organisations.
- 97% of customers were satisfied with UNHAS services as of February 2025 (up 1% from 2024 and 2% from 2023).
- UNHAS responded to 100% of all medical and security evacuations and 100% of ERRM’s emergency response requirements.
- WFP spent 100% of the SSHARP CDEL budget for 2024/25 on road and dyke rehabilitation, resulting in 578km of (mainly) roads and dykes being improved (and some dyke construction from scratch).
In parallel to the programme, BEJ focuses advocacy and influencing on strengthening accountability of the government to protect civilians, improve access, and break the cycle of dependency. This is part of a wider donor push for greater government accountability and responsiveness. These include strengthening the government’s role in service delivery by pushing for greater domestic investment in services and building of he necessary enabling policy environment and systems.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

SSHARP allocated £5m of an uplift in funds to UNHAS. This helped to bridge a funding gap allowing UNHAS to secure stable aircraft contracts and maintain essential services through Q1 of 2025. It is essential that UNHAS remains operational given that there are no reliable commercial options serving remote areas of South Sudan, with many roads being impassable due to flooding and checkpoints/conflict. UNHAS remains the sole air service for the humanitarian community in South Sudan and the only way to reach many of the places in need of assistance. In rainy season some airstrips are completely inaccessible and so helicopters are used.

As a result of the forthcoming reductions in aid from other development partners (mainly the US), we have worked with IMPACT to re-prioritise their activities for year two so that: i) it remains a viable institution; and ii) it can be positioned as central to the South Sudan humanitarian architecture, in particularly in guiding increasingly scarce resources. This means identifying where the data needs are most acute, who needs the data, when decisions are being made and acting efficiently to ensure these decisions are underpinned by evidence. Examples of this are a planned increase in frequency and distribution of the EMS to guide rapid response systems, and information management for the reduced cluster system to guide the medium-term response.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

RECOMMENDATION: Some missed opportunities were identified with regards to influencing decision making with data and evidence - a renewed focus on stakeholder management and influencing is required for IMPACT. This will be evidenced by narrative in the quarterly reports that explain who is using the outputs and what decisions they are seeking to influence. Such tracking/monitoring is missing from narrative reports to date.

LESSON: Given the strict parameters for spending CDEL, extraordinary risk mitigation and advanced planning was required by WFP to spend SSHARP’s CDEL budget with financial probity. In the future and prior to agreeing CDEL spend, FCDO must consider carefully the constraints of those funding requirements, with their impacts on timing, which were compounded by South Sudan’s rainy season timing. WFP had less than four months to spend £22m as activities could only be conducted in a narrow window of when ground was dry enough and before the end of the UK financial year. Unspent funds could not be reprogrammed. Mitigation actions were:

- To open up the number of projects within scope; WFP identified nine projects (up from four) for expenditure. This allowed SSHARP funds to be moved towards higher value works (such as Pibor road).
- The number of contractors was increased so they could work simultaneously; weekly invoicing was implemented.
- Close collaboration with BEJ allowed for operational issues to be highlighted and mutual problem-solving. BEJ was particularly involved in strengthening WFP’s conflict sensitivity approach, which was a vital part of risk mitigation.
D: VALUE FOR MONEY (VfM)

Key cost drivers and performance

The largest cost drivers across SSHARP are WFP’s purchases of food, cash to transfer (and almost as high are the logistical costs of transferring that cash), and road improvement costs. This is, in part, because WFP delivers some of the highest spend items across various SSHARP components. Across other components, staff costs are in the top three cost categories; WFP staff costs are the fourth highest cost category. For IOM (SSHARP’s second largest component), the leading cost driver was the cost of the onward transportation for those crossing from Sudan (boats and planes).

It is too soon to measure VfM performance. That said, a great number of outputs have been achieved, measured and communicated on the rapid emergency response side, and by WFP and UNICEF. These stand out as more efficient partners after the first few months of operating. WFP spent over 50% of SSHARP’s year one budget and is assessed as the strongest performer in terms of VfM. WFP managed to absorb an in-year uplift of £30.3m; spent £22m on CDEL under strict conditions; meet, or be on track to meet, most of its output milestones under outputs 2 and 5; make good progress on output 4; and submit timely reports containing high quality data and explanations. That said, FCDO CDEL constraints meant that WFP had to contract 19 contractors to work simultaneously, and we incentivised them to rush the process. It would likely have represented better VfM to have focused on a smaller number of projects at any given time, which would have enabled clearer project and financial management.

In parallel to the programme, BEJ focuses its advocacy and influencing objectives on strengthening government accountability to protect civilians, improve access, and break the cycle of dependency. This is part of a wider donor push for greater government ownership and responsiveness. The more success we have in this endeavour, the greater the VfM gains will be because all these objectives smooth the path for outputs to yield outcomes.

VfM performance compared to the original VfM proposition in the business case

The programme team has developed a VfM strategy for SSHARP that sets out principles for collecting evidence to assess to what extent the programme represents VfM, as well as allowing for evidence-based decisions to be made throughout the duration of SSHARP. The programme team has developed a draft VfM framework (that sits alongside the logframe), with indicators across the FCDO five Es indicators. Some of these are for the BEJ team to measure, and some are for partners. Each partner is developing its own set of indicators to track, capture, and communicate VfM, but to make the framework comprehensive, a set of common indicators has been circulated to partners to determine which ones they can measure. VfM indicators have been designed so that most partners should be able to track performance against most of the indicators. The indicators are listed below and by 11 April 2025 we should know which partners have agreed to measure these. The purpose is to be able to draw some comparisons, while noting that operations and contexts are different. The SSHARP vfm framework will evolve in line with contextual and operational changes.

The indicators proposed for the framework are:
- Economy Indicator 1.1 - Difference in exchange rate used to convert USD to SSP between UN rate and the market rate.
- Efficiency Indicator 2.1 - Average cost to transfer ratio (non-transfer costs/value of cash transferred).
- Efficiency Indicator 2.2 - Percentage of people reached, within the timeframe agreed.
- Efficiency Indicator 2.3 - SSHARP coordination – indicator to be confirmed and FCDO to calculate.
- Effectiveness - Indicator 3.1 - Average percentage of outcome targets met across partners (disaggregated by output - prioritise, prevent, protect and evidence).
- Equity Indicator 4.1 - Percentage of SSHARP indicators that are disaggregated by sex, age and disability.
- Equity Indicator 4.2 - Percentage of HNRP priority counties targeted in SSHARP.
- Equity Indicator 4.3 - Percentage of partners (including downstream partners) with a functioning community feedback mechanism.
- Equity Indicator 4.4 - Average satisfaction survey scores disaggregated through community feedback.
- Cost Effectiveness Indicator 5.1 - Ratio of SSHARP budget spent on long-term, sustainable response activities vs reactive response activities.
- Cost Effectiveness Indicator 5.2 - Average cost per beneficiary for ICF activities.

The framework is consistent with the indicative VfM proposal in the Business Case.

Assessment of whether the programme continues to represent value for money

In the context of aid cuts and repeated crises in South Sudan, the VfM case for the programme is continually increasing. The clear need for transition acceleration and doubling down on resilience and livelihoods is also clear, not least given how unsustainable the humanitarian sector in South Sudan is; and this will only increase as funding is cut. Therefore, keeping our attention and funding in these areas is also vital to maintaining VfM for SSHARP.

E: RISK

Overview of risk management

The current SSHARP risk appetites remain the same as at business case approval, with the exception of Public Service Delivery, which was amended from “receptive” to “cautious” in October 2024 following a BEJ review. All SSHARP risks remain within the BEJ appetite, though not within global FCDO appetite for “Strategy and Context” and “Policy and Programme Delivery”. This reflects the complex and difficult operating environment in South Sudan.

Risk category	Strategy & / Context	Policy & Programme / Delivery	Public Service & Operations	People	Safeguarding	Financial & Fiduciary	Reputational
FCDO	Receptive	Receptive	Cautious	Cautious	Cautious	Cautious	Cautious
BE Juba	Eager	Eager	Cautious	Cautious	Receptive	Receptive	Receptive
SSHARP	Eager	Eager	Cautious	Cautious	Receptive	Receptive	Cautious

SSHARP’s programme risks are reviewed on a quarterly basis by the programme team. Each risk has a risk lead responsible for engaging other BEJ leads and SSHARP programme team members (who are responsible for feeding in changes to risks that are being actively managed by their implementing partners). Programme staff sequence their engagement with implementing partners to ensure that risk registers are fully reviewed in time to feed into the quarterly SSHARP risk review. Every time the SSHARP team engages with implementing partners during meetings (at a minimum on a quarterly basis but meetings have been much more frequent), risk management is a standard agenda item. The SSHARP team has also built productive close relationships with mplementing partners, which has resulted in partners being more transparent on risks they are actively managing.

The table below shows the severe and major risks that are being actively managed by the SSHARP programme team. On the one hand, over 2024/25 the severity of risk one (politics and economics) has increased, reflecting the evolving political dynamics – and economic downturn/catastrophe - in South Sudan. This risk is severe, but within SSHARP’s appetite. However, as a matter of good practice and to ensure visibility across BEJ, the risk was escalated to the Development Director. On the other hand, the residual risk for risk three (associated with climate shocks) has reduced from severe to major. We were able to reduce this risk by implanting a series of actions recommended by the new climate and environment advisor in BEJ: Actions include:
- regular flooding updates informing policy teams of flooding forecast, with predictions extending 60 days ahead;
- health and education facilities overlayed with the flooding map;
- participation in after-flood reviews to ensure feedback influences this year’s response; and
- BEJ teach-in with INFLOW (UK-funded research project, which has developed the new flood forecast model) to discuss last year’s flood season, lessons learned, and future flooding in the context of increasing climate risks and impacts. This will enable internal conversations around future policy and programming within the context of delivering a more effective and efficient humanitarian response.

A recent addition to the overall SSHARP risk register is the risk associated with US aid reductions. SSHARP’s year two budgets are being considered considering this emerging risk, including taking into account the viability of delivery partners who may have been reliant on US funding.

Risk Description	Risk Category	Residual Risk
Economic and/or political deterioration reduces partners' ability to operate and increases humanitarian needs, resulting in SSHARP being unable to deliver at the scale required.	Strategy & Context	Severe
US funding changes mean SSHARP cannot deliver intended impact because: partners close down; the enabling environment for assistance is reduced; UK funds are reallocated to fund critical humanitarian needs, reducing emphasis on transition and resilience; programme management capacity is stretched; and overall humanitarian needs rise.	Strategy & Context	Major
Climate shocks increase overall needs and reduce physical access and mean SSHARP is unable to adequately respond to humanitarian needs.	Strategy & Context	Major
South Sudan is ranked 5th globally for sexual exploitation, abuse and harassment (SEAH) risks in humanitarian operations (SEARO 2025). SSHARP partners lack capacity and/or policies, procedures, systems or monitoring for prevention, identification, and management of SEAH cases, putting people at risk and exposing BEJ to reputational damage.	Safeguarding	Major
Ineffective monitoring and reporting of infrastructure projects under SSHARP (WFP/IOM) restricts BEJ from ensuring accurate financial information and increases the risk of SSHARP underspend and procurement fraud.	Financial & Fiduciary	Major

Due Diligence

New or refreshed Due Diligence Assessments (DDA) were completed on seven of SSHARP’s delivery partners as part of SSHARP’s mobilisation. The DDA for OCHA’s South Sudan Humanitarian Fund, and the Norwegian Refugee Council (ERRM lead) were still valid from HARISS (the predecessor to SSHARP).

The process for finalising these DDAs took longer than envisaged – resources were strained across the parallel mobilisation of multiple partners in parallel with closing of HARISS. Key findings from these DDAs have identified 90 recommendations to address across SSHARP partners. Findings also feed into the SSHARP portfolio risk register. Action plans have been agreed with all partners. The BEJ programme team review action plans quarterly.

Partners have made good progress to address DDA recommendations, with several partners addressing a large majority of the recommendations via their tailored action plans. Most recommendations categorised as “Major” fall within the “Governance & Control”, “Ability to Deliver” and “Safeguarding” pillars. There is one severe risk under SSHARP, which relates to UNICEF’s internal governance structures following an internal audit. Following this audit, UNICEF is now implementing more robust processes and has strengthened, and increased the frequency, of its engagement with partners.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Financial Performance

100% of SSHARP’s original ODA allocation for 2024/25 was spent in eight months. SSHARP was also successfully able to absorb uplifts from HQ and underspend from other parts of BEJ. 100% of the £22m in CDEL was spent. These statistics mask mixed performance among partners, though. The UN is better able to spend and the iNGOs struggled, sometimes passing underspend to the UN.

In-year budget uplifts amounted to £35.89m in RDEL (including firming up of £2.75m at risk funding and £24.5m for responding to impacts of the Sudan crisis), of which £30.3m was allocated to WFP. £25.3m was for procurement and pre-positioning of humanitarian food assistance for returnees, refugees and host communities. £5m was allocated to UNHAS to fill a funding gap. £1.5m of the uplift was from the RAF and spent by THRIVE. SSHARP therefore spent over a third of its total budget in year one; only £3.7m of the allowed 10% headroom now remains for absorption of additional funds in outer years. A business case addendum will need to be put to Ministers in 2025 to acquire more headroom, either by requesting an uplift to the overall amount of the business case or by converting the remaining CDEL to RDEL.

The business case states that up to 40% (£120m) of SSHRAP ODA will be classed as ICF. The programme team needs to improve how ICF is tracked so that progress against this spend can be measured accurately. In 2024/25, an estimated £28m of SSHARP’s spending was categorised as ICF, but this needs to be more systematically and rigorously tracked. The figure includes resilience and livelihoods spending, flooding response, and infrastructure.

Commercial

Within the reporting period the programme team has worked hard to mobilise nine implementing partners (four UN, one International Agency and four iNGOs). The programme has also utilised the UN Standby Partnerships Mechanism to mobilise five technical consultants for the WHO to support the cholera outbreak. The evaluation and audit (EEAL) component has not yet been mobilised. This sums to 11 components under SSHARP, 10 mobilised.

Mobilising most partners took longer than envisaged – most proposals were complex and required intense engagement with partners to agree proposals and budgets acceptable to FCDO for signing of multi-year agreements. Another factor that delayed mobilisation for some partners was that finalising DDAs took longer than envisaged.

Given the change in context (UK ODA uncertainty and US funding reductions), the process for agreeing implementing partners’ year two strategies, workplans and budgets has been more difficult than originally planned. Partners will not have full certainty over year two budgets as we enter year two; we expect to confirm year two plans in the first quarter of year two (it should have been March).

The BEJ team robustly review all partners’ financial reports and spending risks. Technical advisers are also consulted. Anomalies are clarified with the partner and reports are resubmitted if required (this is very often the case). The programme team escalates risks and issues so these can be discussed and mitigated transparently, and at the right level. This involves fraud and safeguarding incidents. All payments are approved by the Programme Responsible Owner (PRO) following compliance with rules. In addition, the PRO only approves payment if there is an audit trail that demonstrates that the programme team have reviewed financial reports as well as progress reports, where relevant.

Partners’ performance

While most partners will meet their financial year spending targets, they have found it challenging to provide realistic forecasts. The programme team has spent a disproportionate amount of time obtaining accurate forecasts throughout the year. Following engagement with the BEJ programme team, most partners have progressively improved on forecasting throughout the implementation phase. One INGO partner that manages a consortium has consistently performed below expectations, and an action plan for improvement has been mobilised with clear timelines for assessing progress.

All partners are reporting quarterly on progress via a short, simple monitoring template the programme team issued to them all, which is the same for all and avoids extensive narrative that is not useful (which is how reporting was received under HARISS). The reports are prescriptive on what information is and is not required. This has significantly enhanced the BEJ team’s ability to capture the important elements of progress. Improvements are still required on delivery chain mapping.

Asset monitoring and control

All NGO partners maintain asset registers and have policies in place for asset management. For UN organisations (including SSHF, as funds are channelled through OCHA) and ICRC, assets are managed in accordance with UN/ICRC policies and procedures. As asset disposal cases arise, the BEJ team works with the partner and in line with the FCDO’s PrOF guidance to identify feasible options for disposal, including auctioning assets or donating to other organisations funded by FCDO. A recommendation from HARISS was to increase the rate of spot checks BEJ carries out. This has begun under SSHARP, but the current political and security situation makes this more challenging.

G: MONITORING, EVIDENCE AND LEARNING

The evidence base for informing effective adaptation and resilience programming in conflict affected states remains comparatively weak, which is true for all countries experiencing conflict and associated weak governance. Through its evaluation component, SSHARP will contribute to expanding and informing the evidence base; SSHARP will test the efficacy of specific adaptation and resilience activities, the outcomes of which will be subsequently evaluated. This will enable us to gain a deeper understanding of how effective specific activities have been, and will help us to identify the most successful actions as we pivot focus away from humanitarian programming towards development. The interventions will then use real-time learning to tailor the design across the years. Without studying this and adjusting as we go along, we are not likely to succeed. The evaluation planning is underway; the ToRs have been submitted to the internal framework that will organise procurement, which has rated them as “excellent”.

In addition to the evaluation, the BEJ team conduct field visits. In October 2024, the team went to Rubkona to see resilience work delivered by GOAL under a previous BEJ resilience programme. This provided useful learning for THRIVE. Notably, the team found that businesses supported five years ago were still operating, now without assistance. The factors that have enabled this to happen are being discussed. The businesses included a tailoring shop, vegetable seller, and grain millers who had been supported with capital, training and equipment. The tailor had taken on an additional member of staff and had been able to purchase an additional sewing machine.

The BEJ team plan up to four field visits for SSHARP monitoring per quarter, and to date are achieving two per quarter. It is necessary to over-plan because external factors (usually insecurity in the states) often require trips to be cancelled. Across the lifetime of SSHARP, to date the team has been to Rubkona (THRIVE, October 2024); Bentiu (IOM, November 2024); Abyei (emergency response context, December 2024); and Renk (all UN partners, February 2025). We have also monitored ICRC and SSHF in Juba. Trips outside Juba are made by air using UNHAS because the roads are both impassable and insecure. Because of the instability of South Sudan and its being red on FCDO travel advice, the team take strict precautions signed off at HQ. In some cases, this involves having a close protection unit from the UN; all travel requires travelling with body armour. The security situation in South Sudan as of March 2025 has put these field visits on hold.

Date of last narrative financial report	Component name	Date of last audited annual statement (dates from HARISS)	Due during this reporting period.
02/04/2025	WFP	26/04/2024	None
31/01/2025	UNICEF	06/12/2024	None
26/02/2025	IOM	31/12/2023	None
N/A	ICRC	31/12/2023
04/03/2025	IMC	30/06/2023	None
N/A	SSHF	11/04/2024
17/02/2025	ERRM	08/05/2024	None
21/03/2025	IMPACT	31/03/2022	None
07/03/2025	GOAL	31/12/2023	None