## PSVI Programme Annual Review FY 24-25

Title: Preventing Sexual Violence in Conflict Initiative (PSVI)
Programme Value £ (full life): £16.41m		Review date: 19/09/2025
Programme Code: 301576	AMP start date: 13/09/2022	AMP end date: / 31/03/2027

Summary of Programme Performance
Year	22-23	23-24	24-25
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301576/documents
DevTracker Link to results framework:	D0007530.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme
The Preventing Sexual Violence in Conflict Initiative (PSVI) continues to play a pivotal role in addressing the increasing prevalence and global challenge of Conflict Related Sexual Violence (CRSV).
This year marked a critical phase in consolidating programme achievements, refining strategic approaches, and preparing for the future of PSVI beyond 2025. With continued delivery across seven priority countries and strategic engagement in emerging conflict zones, the programme has demonstrated agility, resilience, and a deep commitment to survivor-centred approaches. The external Monitoring, Evaluation and Learning (MEL) partner has played a key role in strengthening evidence and impact assessment, while field visits and partner consultations have enriched our understanding of on-the-ground realities.
There are more countries in the world today engaged in conflict than at any time since World War II. The United Nations Office of the Special Representative of the Secretary General on Sexual Violence in Conflict (OSRSG) produced its annual report in 2024, which noted a 50% rise in UN-verified reported CRSV over the last year. Though this could be due to an increase in reporting, it highlights the need for the PSVI programme to continue. With that in mind, the programme has been extended for an extra year with £3.85m funding for FY 25-26. As a result, we have taken a proportionate approach to this review, which is based on inputs from the independent MEL partner review of implementation against the PSVI strategy, partner quarterly and annual reporting and monitoring visits by the PSVI team. A comprehensive programme closure report will be completed later in FY 25-26. This forthcoming report will offer an in-depth assessment of overall programme performance, including outcomes from FY25-26.
At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition. The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, which centre on establishing long-term partnerships based on mutual interests and respect. For PSVI, this means a greater emphasis on monitoring and evaluation, to measure impact and continuing to build strong partnerships with implementing partners, encouraging catalytic and impact-driven work.
Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme score is A, which represents a significant accomplishment, particularly within the current global context. Amid increasing geopolitical instability, a concerning rollback on human rights protections, and at the latter end of the FY, widespread reductions in international aid, maintaining high standards in a programme focused on preventing sexual violence in conflict is both challenging and critical. This rating reflects the programme’s resilience, strategic relevance, and continued impact in advancing survivor-centred approaches, accountability mechanisms, and international policy engagement. It is a testament to the dedication and effectiveness of the team, implementing partners and International Alliance countries in upholding the UK’s leadership on this vital issue.

Highlights from this FY include:

Justice and accountability:
- PSVI-supported projects contributed to landmark legal and reparations progress. In Kenya, through UN Women and their downstream partner, Partners in Justice International (PJI), mentoring contributed to the prosecution of four police officers for crimes against humanity, including sexual violence, moving toward trial. PSVI spoke to PJI beneficiaries in a different context who confirmed the value of this mentoring.
- In Kosovo, more than 1,700 CRSV survivors are accessing reparations benefits through a CRSV reparations commission supported by UN Women. Significant progress has been achieved by All Survivors Project in supporting access to justice for male CRSV victims in the national transitional justice process in Colombia. Since the review period, 104 men were accredited as victims of sexual violence, which was recognised by the Special Jurisdiction for Peace (JEP). The accreditation was carried out in relation to macro-case 11of the JEP on gender-based violence, including sexual violence, but also to case 08 of the JEP, particularly the Gran Magdalena sub-case, concerning crimes committed by the armed forces in association, collaboration, or tolerance with paramilitary groups. Sisma Mujer consolidated a strategic litigation model that effectively addressed the context of the JEP, identified the main challenges, and proposed concrete strategies to overcome the obstacles faced by women. Additionally, they developed a litigation strategy specifically designed to address cases within the ordinary justice system. As a result, cases were litigated and represented before the JEP and before the ordinary justice system.
- Sustainability of UK-Funded tools: The Murad Code (IICI) and Stigma Toolkit for Justice (Synergy for Justice), though not funded this year, continue to shape global practice. The Murad Code was implemented or referenced in 12 countries, influencing national justice systems, CSO practices, and donor guidance. The Stigma Toolkit informed, highlighted and advocated for changes to the formal justice system that are now being advocated for by survivor groups in South Sudan and the toolkit is now being piloted in multiple countries by different justice actors and survivor networks, showing sustained impact beyond initial funding.
- Survivor-centred reparations:
  - A visit to the Global Survivors Fund’s work in Guatemala demonstrated how co-created reparations projects can foster community resilience and healing. Survivors reported feeling supported and listened to, with the reparative approach influencing government engagement and advocacy efforts. A recent visit to GSF's former downstream partner, Nadia’s Initiative in Iraq, confirmed these findings. The project took place outside the scope of this Annual Review - between September 2020 and February 2024, but the PSVI team wanted to hear reflections on its impact. Before the enactment of the Yazidi Survivor Law in 2021 and its subsequent implementation, Nadia’s Initiative delivered Interim Reparative Measures to survivors of CRSV and facilitated their engagement with the Iraqi government. Survivors participated actively at every stage of the process.
  - GSF continued to deliver strong results with their leadership in survivor centred reparation in other contexts too. Data collected showed that the interim reparative measures improved survivors’ overall quality of life, including their personal relationships, self-esteem, and financial wellbeing. The medical treatment, livelihood support and financial compensation provided strengthened survivors resolve and rehabilitation. Collective measures were also a success, such as the installation of a memorial garden for Yazidi survivors in Iraq, launched with Nadia’s Initiative. These measures contribute to honouring survivors and victims and recognising the abuse they were subjected to. The measures also create a ripple effect beyond survivors’ own lives; as the project progressed, survivors noted greater appreciation and recognition from their communities as their reparative measures - such as funding for small businesses and rebuilding homes - touched the lives of others in their towns and villages, showing how the project also began to enhance societal acknowledgement of survivors’ sacrifices. This was confirmed by speaking to Nadia’s Initiative in Iraq, although more work needs to be done to support the return of survivors currently living in Internally Displaced Persons camps.
- International influence: Advocacy efforts contributed to the UN Sixth Committee’s agreement to begin negotiations on the Crimes Against Humanity Convention in 2028–29. The UK’s leadership ensured gender-sensitive and survivor-centred provisions were considered, reflecting PSVI’s strategic influence on international legal frameworks.
- Survivor networks and advocacy: The Mukwege Foundation facilitated the creation of a new coalition of survivor networks in Uganda and the creation of a document with survivor priorities, enabling unified advocacy and direct engagement with government stakeholders. Workshops in Uganda and Colombia empowered survivors to articulate demands and influence policy, including through public events and international fora.
- Justice system strengthening: In South Sudan, through Steward Women, mobile courts helped reduce case backlogs and restored faith in justice systems. In the DRC, TRIAL International’s legal support led to nine active judicial proceedings, despite severe conflict disruptions, demonstrating the effectiveness of agile programming and local partnerships.
- Innovative psychosocial support: In Ethiopia, the Helpful Active Listening (HAL) model gained national and international recognition for its community-based approach to trauma recovery. Survivors reported improved wellbeing and resilience, and the model is now being considered for replication in other contexts.
- Strategic partnerships and influence: UN Women’s Gender Justice Platform catalysed international momentum on CRSV accountability, including influencing treaty negotiations and embedding survivor-centred approaches in transitional justice systems across multiple countries.
Major lessons and recommendations for the year ahead [1/2 page]

Prioritise sustainability and catalytic impact:
As we enter a low ODA world with fewer resources available, PSVI must focus on interventions that unlock systemic change and outlast UK funding. PSVI should invest in catalytic partnerships that can scale, replicate, or influence others. This means maintaining relationships with past implementers to track and promote the ongoing impact of previously funded work. This approach allows the UK to maintain leadership on CRSV and gender justice without relying on large-scale funding. In a low ODA world, where direct funding is constrained, the UK’s voice and convening power become even more critical.

Survivor-centred design requires time, ensure this is built in to avoid pressures on project teams:
Feedback from partners that FCDO funding mechanisms should better accommodate multi-year projects could significantly enhance impact, and would allow for more strategic planning, deeper survivor involvement and flexibility to adapt. Mukwege Foundation noted that delays in the project start date due to due diligence and onboarding procedures resulted in a shorter timeframe to engage survivors and plan activity, which placed pressure on teams and challenges to implementation. Projects managed at post regularly reported the difficult nature of short-term grants due to the lengthy project set up admin and the importance of relationship-building with the implementing partner. While noting internal procedures such as due diligence assessments are an essential part of the funding process, factoring in a longer lead-in time would allow to incorporate this initial process, ensuring a smooth running of the project and a clearer impact story.
Leverage strategic funding relationships to maximise impact and influence:
In a constrained funding environment, PSVI should continue to explore how strategic funding relationships can be used not only to deliver programme outcomes but also to advance broader UK objectives on CRSV and gender justice. This includes:
- Balancing support between large-scale implementers and smaller, agile organisations: Smaller organisations often demonstrate deep contextual knowledge and can deliver high-impact, survivor-centred interventions with limited resources. While larger partners offer scale and reach. PSVI should seek a balanced portfolio that maximises impact without overburdening programme management capacity.
- Using funding relationships to drive strategic influence: PSVI should actively link funding decisions to strategic goals, ensuring that partnerships reinforce UK priorities on CRSV accountability, survivor voice, and international legal reform. This includes leveraging relationships to promote survivor-centred approaches and CRSV equities in other FCDO programmes and influencing cross-cutting areas such as counterterrorism, stabilisation, and peacebuilding. This will help mainstream survivor-centred approaches and ensure CRSV is not siloed but addressed holistically across UK foreign policy.
4. Continue to ensure flexibility in programme management:
Although PSVI must adhere to compliance controls, flexible funding mechanisms enable partners to pivot activities quickly where necessary, as demonstrated by TRIAL International’s effective localised and flexible delivery model. Scenario-based planning should be embedded in project design to encourage partners to develop multiple implementation scenarios that would help maintain momentum during changing conditions.
An example of this benefit is shown in the DRC case study. The project was severely disrupted by the surge in violence in eastern DRC beginning in January 2025, marked by the rapid advance of the M23 armed group, backed by Rwandan forces which led to the collapse of local justice institutions and a sharp deterioration in security conditions. Despite this, the programme team and TRIAL International acted quickly and administered an uplift of £50k. This uplift ensured the delivery of emergency support to victims, witnesses and human rights defenders under immediate threats from the escaped convicted criminals. TRIAL supported three partner NGOs to enhance their ability to identify and assist victims and witnesses under threat. With reinforced skills and coordination mechanisms, the NGOs successfully implemented emergency protection measures and conducted a preliminary mapping of human rights violations reported since January 2025 across several territories in South Kivu. This example shows the success of agile programming as the programme team were able to quickly mobilise an uplift and work with implementers to achieve positive results.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Not all victims of CRSV survive, but for those that do, there are profound impacts on their physical and mental health, their ability to participate fully in society, and their ability to fulfil their potential. More generally, CRSV undermines poverty reduction, gender equality, and conflict resolution. In addition, it perpetuates armed conflict. When motivated by political, military, or economic objectives to control territory or resources, CRSV is frequently and often deliberately used to target civilians, inflicting long-term trauma and humiliation, fracturing families and the social fabric, triggering displacement, and fuelling armed actors’ activities.

Over the last few years, there has been a marked increase in global instability and conflict which had a devastating impact on the lives of those effected and led to heightened geopolitical risks and increased tensions across multiple regions. In 2023, the United Nations Office of the Special Representative of the Secretary General on Sexual Violence in Conflict (OSRSG) produced its annual report, which noted that the outbreak and escalation of conflict exposed civilians to heightened levels of CRSV. The report highlights the importance of support for survivors of CRSV, emphasising the negative impact stigma has in perpetuating further harm.

The PSVI programme Theory of Change, launched with the strategy in 2022, provides an evidence-based conceptual framework for how the UK Government and other stakeholders can contribute to addressing CRSV through diplomatic, development, humanitarian, and defence interventions. The programme’s desired impact (as outlined in the programme’s logical framework) is that ‘women, men, girls, boys and people of diverse SOGIESC are at reduced risk of conflict-related sexual violence, those that are affected by it are able to access quality and survivor-centred support, services and justice, and those who perpetrate it are held to account‘. This is supported by the programme outcome: ‘Global response to and prevention of CRSV is strengthened, in a holistic and survivor-centred way’. The below section provides more detail as to how current PSVI programming is contributing to the expected outcome indicators.

This year, the PSVI Monitoring Evaluation and Learning (MEL) partner conducted a review of the Theory of Change and Results Framework, which focused on relevance, effectiveness and learning, and outlined opportunities to clarify causal pathways and better define the UK’s role in delivering change to tackle CRSV. As a result of this review, and internal reviews conducted by the PSVI team, we are in the process of updating the Theory of Change. This is not a review of the essential elements, which are still considered sound. Instead, this will be to update with lessons learned from the current programme, any insights and evidence that can be drawn from recent conflicts, such as Ukraine, and to clarify and simplify the causal pathways for change by the FCDO operating in a more challenging geopolitical context, including reducing ODA and deprioritisation of gender issues around the world. This review was not deemed to be required for this financial year, but will be ready to support implementation of the next PSVI Strategy.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Outcome Indicator 1: Strengthened global response to CRSV, through improved coordination among states, strengthened international frameworks

The PSVI programme made significant strides in strengthening the global response to conflict-related sexual violence (CRSV) through diplomatic engagement, multilateral coordination, and legal framework development. A key achievement was progress on the draft UN Crimes Against Humanity Convention. The UK played a leading role in advocating for a new convention, with gender-sensitive language and survivor-centred provisions, including the recognition of forced marriage and pregnancy, and the rights of children born of CRSV. Funded activities contributed to increased engagement with civil society and Governments on the draft convention to achieve an increase in co-sponsorship of a resolution calling for treaty negotiations. These efforts culminated in the UN Sixth Committee agreeing to commence formal negotiations in 2028–29, a milestone that reflects the UK’s sustained leadership in this space.

Additionally, the UK continued its active involvement in the International Alliance on PSVI, despite no longer holding the Chair or Vice-Chair roles. The UK supported Colombia and Ukraine in their leadership roles and contributed to shaping the Alliance’s future direction through a strategic review. The Alliance expanded with new members and issued a joint declaration reaffirming commitment to CRSV prevention and survivor-centred responses. These actions demonstrate improved international coordination and a strengthened global framework for addressing CRSV.

Outcome Indicator 2: Strengthened justice systems at the national and international level, and increased access to justice for survivors

The PSVI programme exceeded expectations in strengthening justice systems and improving access to justice for survivors. Through partnerships with UN Women, TRIAL International, and others, the programme supported capacity-building initiatives in multiple countries. For example, in the DRC, TRIAL trained over 220 magistrates and 98 human rights defenders, and provided legal assistance to 740 survivors, leading to nine active judicial proceedings. In particular, four of these proceedings led to criminal trials that were held in 2024. The favourable judicial decisions rendered by the military courts of South Kivu in the Donat case (first-instance trial) and the appeal trials in the Ndarumanga, Kokodikoko and Bralima cases marked significant advances for CRSV victim communities in the province and led to important jurisprudential developments. These included the first worldwide domestic conviction for the crime against humanity of forced pregnancy, and the first form of judicial reparation (socio-economic, psychological, and educational support) issued in DRC for children born of rape.

In Iraq, International Organisation for Migration (IOM) supported the implementation of the Yazidi Survivors Law through technical assistance and capacity building.

UN Women’s Gender Justice Platform delivered 108 events and trained or mentored 553 individuals (68% women) across countries like Colombia, Kenya, Kosovo, Ethiopia, South Sudan and Ukraine. These sessions focused on survivor-centred justice, intersectionality, and gender-responsive transitional justice mechanisms. In Kenya, mentoring contributed to the prosecution of four police officers for crimes against humanity, including sexual violence, moving toward trial. In Kosovo, more than 1,700 CRSV survivors are benefitting from reparations through a CRSV reparations commission that has received sustained support from the Gender Justice Platform.

All Survivors Project successfully organised and held two survivor-centred access to justice jornadas (legal and psychological support sessions) for a total of 117 male victims in June and July 2024. In addition, a JEP-focused jornada was held for 68 male victims in March 2025. These jornadas have been key to the achievement of the project outcomes as they have enabled: (a) informed decision-making by each of the victims as to which justice options they would like to pursue; (b) their consolidation as an organised group of male survivors from the region of Magdalena; and, (c) victims to receive timely updates on the status of each of their cases before the different mechanisms.

TRIAL Bosnia and Herzegovina delivered measurable impact by securing landmark court victories that strengthened access to justice for survivors of CRSV, advancing the institutionalisation of reparations through sustained advocacy, and enhancing regional cooperation on transitional justice. These results demonstrate both strong value for money and continued relevance of the programme in addressing survivor needs and reinforcing rule of law in BiH.

Although not funded during the year in review, the programme showed sustainability of former UK-funded work through dissemination and use of the Murad Code, the Stigma Toolkit and Mukwege Foundation Guidebook. These tools are helping embed survivor-sensitive practices in justice systems, contributing to long-term systemic change.

Outcome Indicator 3: Improved support to survivors and survivor voice at the centre of policy making, demonstrated through UK funding for survivors, and survivor engagement in UK Survivor Advisory Group (SAG).

The PSVI programme continued to place survivors at the heart of its work, both in terms of direct support and policy influence. The Global Survivors Fund provided interim reparative measures to 2,221 survivors (through multiple donor funding) across 8 countries (In 2024, GSF activities (in total) accompanied 42 partners in 26 countries), including financial, psychosocial, and medical support. In Guatemala, the PSVI team observed the co-creation of reparations projects with survivors, highlighting the programme’s commitment to survivor-led design. In Iraq, the PSVI team spoke to former downstream partner Nadia’s Initiative to assess impact one year after that particular reparations project had closed.

Survivor voices were also amplified through the Survivor Advisory Group (SAG), which met more frequently in FY24-25 and contributed to shaping UK policy positions, including on the draft Crimes Against Humanity Convention. Workshops in Colombia and Uganda delivered by Mukwege Foundation enabled survivors to develop advocacy strategies and present their demands to stakeholders, including governments and international organisations.

The Murad Code, again though not funded by PSVI in FY 24-25, was implemented or referenced in 12 countries, with over 350 practitioners trained to date since the PSVI conference in 2022. Its principles were integrated into national justice systems, CSO practices, and donor guidance. The Stigma Toolkit, developed by Synergy for Justice, although not funded by PSVI in the year in review, was piloted in multiple countries by different justice actors and survivor networks. It is also now being used by survivor groups in South Sudan to advocate for changes to the formal justice system. These initiatives reflect a deepening of survivor-centred approaches and a tangible way in which survivor voices influence justice and policy processes. The Mukwege Foundation Guidebook, although not funded by PSVI in the year in review, continues to be used by more users than ever, with the Foundation using it to inform proposed legislative changes in Ukraine.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The PSVI programme should continue as it remains closely aligned with key UK Government priorities and represents value for money through strategic budget management, high-impact delivery with a survivor focused outcome and a strong emphasis on support to survivors. Feedback indicates the programme is crucial for sustaining global action on CRSV. Ongoing UK leadership is vital amid reduced aid spending, increased CRSV prevalence, and setbacks in women's and girls' rights. The programme was due to end this FY, though it will continue and be extended into FY25-26 with a budget of £3.85m. While no budget has been received for outer years, this review provides strong evidence that PSVI funding should continue for years to come.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Strengthened international response to CRSV; coordination of international community; and improved international legal frameworks to tackle CRSV.
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Progress on the draft UN Crimes Against Humanity convention to strengthen the international legal framework on CRSV, demonstrated by increased references to gender and CRSV in draft text.	October 2024 decision on the draft Crimes against Humanity Treaty incorporates gender and CRSV.	Achieved
1.2 International coordination on CRSV strengthened, demonstrated by engagement by states and other partners joining the International Alliance on CRSV.	2nd High Level Ministerial meeting scheduled/held chaired by another state.	Achieved

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 1.1: The UK has continued to strongly support the elaboration and progress of a Crimes Against Humanity Convention which would strengthen the prevention and prosecution of crimes against humanity, including CRSV and other forms of gender-based violence. In November 2024, the UK welcomed agreement reached at the UN Sixth Committee to convene a conference to negotiate the convention in 2028 and 2029.

Throughout the last two years, the UK and its partners have advocated for the strengthening of the CRSV and gender elements of the draft treaty and to ensure the text is gender competent. Specifically, the UK has called for:
Strengthening the preamble to highlight the importance of a survivor-centred approach to punishing Crimes Against Humanity;
Incorporating into the Convention the inhumane act of forced marriage and amending the current definition of forced pregnancy;
Calling for the strengthening of provisions covering the rights of victims and witnesses, including children. This includes expanding the scope of ‘victims’ to include children born of conflict related sexual violence.

Indicator 1.2: The UK handed the Chair of the International Alliance to Colombia for 2024. In this period the UK was Vice-Chair, alongside Australia. Three new members were welcomed to the Alliance during this time. International Alliance members issued a statement to welcome the UN Secretary-General’s 2023 report on conflict-related sexual violence. The statement issued on 19 June 2024, the International Day for the Elimination of Sexual Violence in Conflict.

On 25-26 November 2024 Colombia hosted the International Alliance on PSVI. This meeting was attended by Lord Collins, the Prime Minister’s Special Representative for PSVI. He called for greater international action in response to increasing rates of CRSV globally and committed to putting a survivor-centered approach at the heart of our response. Following the meeting, attendees agreed a declaration which reaffirmed their shared commitment to the prevention of, and victim and survivor-centred responses to, conflict-related sexual violence.

In January 2025, Ukraine took over as Chair of the International Alliance, with Colombia continuing to engage as Vice-Chair. Japan has since joined as co-Vice-Chair. Ukraine has played an active role in fostering international co-ordination on CRSV during their tenure, including hosting a launch event in January during which they detailed their roadmap for the year, outlining their ambition for regular working-level meetings and more frequent high-level meetings.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The output did not change, though the milestone was amended to be clearer and more targeted. A full logframe review should be undertaken in FY25-26 as outlined in the recommendations, particularly for these indicators since such progress has been made.

Following the milestone agreement achieved at the UN Sixth Committee in November 2024 to commence formal negotiations on the draft Crimes Against Humanity Convention in 2028/2029, the PSVI Team will focus future outputs on preparing for upcoming negotiations.

2025 was the first year that the UK was neither Chair nor Vice-Chair of the International Alliance on Preventing Sexual Violence in Conflict since its inception, however we remained strongly engaged, including by taking on a role to review the International Alliance to understand if the Alliance continues to be a useful forum; if it is achieving its aims and engaging effectively with other key actors; and if any adjustments need to be made to strengthen its impact. We will continue to work to support international coordination on CRSV through the Alliance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Regarding the draft Crimes Against Humanity Convention, the UK has advocated strongly for a survivor-centred approach. For example, the UK developed its proposals through consultation with survivors and civil society, including at our Wilton Park event in March 2023. Moving forward, survivor engagement throughout the treaty negotiation process is crucial and must remain a priority for the UK and all states moving forward

The previous Annual Review recommended consideration to how the UK might continue to contribute to the Alliance, noting the rotation of the chair role. We retained close alignment with the Chair and Vice-Chairs and played a key role in shaping the future direction through leading a review of the International Alliance. A key action for FY 2025 – 2026 will be ensuring that the recommendations of this review are shared with members and taken forward.

Output Title	Strengthened CRSV justice and accountability processes at the national level and increased awareness among states of their responsibilities under international law, through information and analysis; best practice sharing; and capacity building for states.
Output number:		2	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Increased awareness of responsibilities and international frameworks surrounding CRSV at State level, demonstrated by number of states engaging with UK funded guidance.	Guidance reflected in democratic debate/proposed / actual legislative changes in at least 1 additional country	Exceeded
2.2 Strengthened justice and accountability processes at the national level demonstrated through: strengthened analysis and best practice sharing; number of capacity building programmes for states to support them to build better judicial mechanisms to prosecute CRSV.	No. of capacity building programmes completed. At least one partner country shows evidence of improved police, judicial mechanisms to support CRSV.	Exceeded
2.3 Number of UN Women staff, investigators, prosecutors and other transitional justice practitioners trained or provided with mentoring support on intersectional discrimination, survivor-centred approaches or CRSV accountability, disaggregated by sex	No. of prosecutors/magistrates/transitional justice/informal justice administrators trained by UN Women	Exceeded / 553 (68% women)
2.4 Number of multi-stakeholder events (including policy makers and practitioners) convened by the UN Women Gender Justice Platform to enable knowledge and lessons exchange related to gender and transitional justice. Number of participants at multi-stakeholder events convened by the Platform to enable knowledge and lessons exchange related to gender	25% of training events include the right level of participants. (Examples include mid-career officials in the justice system. Senior CSO staff in CRSV support CSOs.).	Exceeded / 108 events

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 2.1: the Mukwege Foundation made significant progress towards this milestone, though the UK did not fund this work in FY 24-25. This milestone provides an opportunity to reflect on the sustainability of UK funding, which is clear to see with this example of the success of the Guidebook on State Obligations for CRSV.

The guidebook has reached 1,400 unique visitors a month and it been translated into four languages. Mukwege Foundation used the Guidebook to conduct two gap analyses on legal and domestic implementation in Uganda and Ukraine, and recommended updates to domestic law based on treaty ratification. In Ukraine, implementing reparation legislation is a key advocacy goal, with Mukwege Foundation and survivors co-creating strategies to support this.

The Colombia activity proceeded with strong participation from survivors representing the PSVI Survivor Advisory Group (SAG), the SEMA network, and local survivor groups from Colombia. In Uganda, survivors developed a Ugandan Call to Action based on the SEMA Global Call to Action and identified their advocacy priorities. A key advocacy goal is increasing the Ugandan government’s implementation of issuing birth certificates for children born of wartime rape, for which the Mukwege Foundation and survivors are currently working on developing an actionable advocacy plan. Feedback from participants found that these workshops significantly increased survivors' ability to advocate for their demands and hold States accountable for their legal obligations related to CRSV under international law. During the Colombian PSVI Conference, 10 public statements and presentations were delivered by seven survivors. At the public event in Kampala, three survivors participated in the panel to present their demands to over 25 stakeholders, including representatives from the government, embassies, civil society organisations, and religious leaders. Reflections on lessons learned are noted in the relevant section.

Additional to the Guidebook and contributing towards sustainability of PSVI funding is the Murad Code project. PSVI funded initial work with the Institute for International Criminal Investigations (IICI) for the release of the Code and strategy on supporting implementation. IICI are now being supported through funding from the Canadian government to continue to ensure widespread compliance with the standards captured in the Code.

Also, funding to TRIAL International in Bosnia prepared and presented the Guidance for a thoughtful and unified approach to supporting victims of war torture in Republika Srpska. This Guidance was presented in three local administrative units: Derventa, Prijedor, and Bratunac and distributed to over 40 authorities. TRIAL successfully collaborated with several local administrative units, leading them to consider improvements in implementation of the Law based on their initiatives.

Indicator 2.2: Iraq International Organisation for Migration (IOM) provided technical assistance and capacity building to the Ministry for Labour and Social Affairs to facilitate a survivor centred dialogue about accountability for genocide and crimes against humanity. They also provided capacity building trainings to the same Ministry, NGOs, relevant community organisations on prevention and addressing trafficking in persons and referral of cases to specialised institutions. IOM’s work contributed to advancing transitional justice by strengthening Iraq’s institutional framework for Yazidi survivors through providing Mental Health and Psychosocial Support (MHPSS) assistance to beneficiaries of the Yazidi Survivors Law (YSL). Progress in Iraq under this indicator has been significant. The work demonstrates how PSVI funding can catalyse institutional reform while ensuring direct psychosocial assistance, aligning with international reparations standards. Continued support should prioritise embedding trauma-informed protocols in reparation delivery and ensuring that symbolic recognition measures accompany material benefits to fully restore survivors’ dignity. Additionally, flexibility to adapt activities in response to shifting institutional contexts - such as the closure of international mechanisms - ensures continuity of survivor-centred support while strengthening national ownership and sustainability.

Through UN Women, the UK supported survivor-led and gender-responsive transitional justice capacity building through technical assistance, mentoring, and policy engagement. This included:
  - Improving civil society capacity and therefore engagement with the Special Jurisdiction for Peace (JEP) in Colombia;
  - Enhancing the gender-responsiveness of draft legislation on transitional justice in Ethiopia, through the deployment of a gender expert to the Ministry of Justice to support the transitional justice policy process;
  - Training and mentoring sessions in Guatemala for individuals in national civil society organisations and institutional stakeholders, focused on survivor-centered approaches and CRSV accountability;
  - Mentoring support to legal advocates and civil society representatives in Kenya to support the development of advocacy strategies grounded in intersectionality and survivor-centered principles. This work was specifically targeted for the Baby Pendo case, the first crimes against humanity case to be brought in the Kenyan national courts where 11 police officers have been charged with international crimes, including sexual violence during the 2017 post-election violence.
  - Extensive training and consultation sessions to identify pathways for strengthening institutional mechanisms and survivor protection, while reinforcing gender sensitivity across the transitional justice system in Kosovo.
  - In South Sudan, through a downstream partner, UN Women conducted stakeholder briefings, awareness raising workshops, and lobby meetings to promote understanding of international humanitarian law and national mechanisms for accountability, learn about the provisions of the new laws for CRSV accountability, and advocate for women's leadership in newly established transitional justice bodies.
TRIAL held two training sessions for 220 magistrates in Bukavu. 98 human rights defenders from four South Kivu NGOs were trained during several training sessions. A pool of 19 lawyers were trained in Bukavu in June 2024. Participants demonstrated significant knowledge gains and expressed full satisfaction through pre- and post-assessments during training sessions held in the first two quarters. TRIAL analysed the draft law on establishing specialized mixed chambers and submitted its assessment to Inter-Institutional Commission for Assistance to Victims and Support for Reforms, (CIA-VAR) with constructive comments and specific recommendations.
TRIAL submitted concrete recommendations to Professor Taylor Lubanga, Chargé de mission of the DRC Head of the State in charge of the cooperation with the International Criminal Court, in support of his initiative to establish a special criminal court with a mandate to investigate and prosecute international crimes.

All Survivors Project organised technical support and capacity strengthening for macro case 11 judges and lawyers in Colombia on CRSV against men and boys, participants noted it was “very educational and illustrative”. They also organised access to justice jornadas, which a survivor said helped to “take off a weight, a stigma”.

Sisma Mujer in Colombia, through training, technical support, and constructive dialogue with judicial operators and public officials, led to institutions being equipped with tools to provide care with gender-based approach. Sisma Mujer reported that this process not only improved the immediate institutional response to victims but also contributed to the gradual transformation of institutional practices and cultures, laying a solid foundation for the sustainability of the progress made in justice for women survivors of violence in the context of the armed conflict.

In 2024, the OSRSG, through UN Action and UN Team of Experts continued supporting national authorities, including in PSVI focus countries, to strengthen the rule of law to enhance accountability for CRSV. UN Action and UN Team of Experts operate through the CRSV Multi-Partner Trust Fund (MPTF), a pooled funding mechanism that enables coherent, inter-agency responses and collective impact to CRSV. While the specific attribution of UK funds may not be isolated, they play a vital role in supporting and strengthening the overall initiative.

For the UN Team of Experts, in Colombia, an expert was deployed to assess judicial system technical needs for addressing accountability for CRSV, while in the DRC, two experts conducted an urgent assessment in response to rising CRSV, identifying priority areas for intervention. The UN Team of Experts also continued its long-standing support to Guinea where in late July, a landmark verdict convicted eight former junta members for crimes against humanity, including sexual violence, and awarded reparations to survivors. In October, the UN Team of Experts held an after-action review with OHCHR and UNDP to reflect on lessons learned and strengthen future accountability efforts. In addition, to address the global need for more domestic prosecutorial units capable of handling CRSV cases, the UN Team of Experts hosted the first International Conference of Prosecutors on Accountability for CRSV to exchange practical insights, best practices, and challenges in delivering comprehensive justice for CRSV survivors in national courts.

UN Action conducted a Monitoring, Analysis and Reporting Arrangements (MARA) 2.0 Needs Assessment to evaluate the existing MARA architecture and explore areas which can be improved to enable the MARA to better meet its objectives. In addition, in July 2024, UN Action piloted the Framework for the Prevention of CRSV in Kyiv, Ukraine. The ‘Practice-based Symposium on the Prevention of CRSV’ convened over 60 participants focused on secondary prevention – the prevention of further harm to communities and survivors after CRSV has occurred. The UN Action Secretariat also presented the Framework and learnings from the pilot on several occasions, including at an online event for the UK’s PSVI International Alliance.

Indicator 2.3 and 2.4: The UN Women project supported survivor-led and gender-responsive transitional justice through technical assistance, mentoring, policy engagement, survivor engagement, critical capacity building, and strengthening legal frameworks. Activities ranged from embedding gender expertise in law-drafting processes, to facilitating survivor engagement in justice mechanisms, to building capacities of legal practitioners and victim advocates, to engagement with civil society organisations and Governments on the draft Crimes Against Humanity treaty to achieve an increase in co-sponsorship of the draft resolution calling for treaty negotiations.

This project has been largely on track and has continued to over-achieve in impact for each indicator by a significant margin.

Key challenges included administrative delays in transferring funds to UN Women country offices and UN Women’s lengthy partner selection process, resulting in delays for some activities. Despite these challenges, activities were completed within the project timeline.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Slight wording amendments to the milestone took place, though no major changes.

Initially, spending was delayed in South Sudan and following communication and approval from the SRO, we agreed to reduce the budget line to further support UN Women funded activity in Colombia, aligned with PSVI objectives. This was not a significant change and therefore does not warrant further action.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Mapping the sustainability of PSVI funding has been challenging but necessary to understand the full scope of the initiative, beyond its funding. As we look to a lower ODA world, it will be important that PSVI remains in regular contact with previous implementers to understand and meaningfully engage with how the work is continuing, even if not through funding.

Quarterly meetings with UN Women provide oversight of the work and provide a forum for discussing delivery and challenges. Regular written reporting is comprehensive. Given the scale of the project, efforts are underway to focus reporting on impact, following the framework of the proposal and outputs. These actions were implemented this year after the last annual review, including more frequent meetings and impact-orientated reporting during the year.

However, more progress can be made on specific qualitative reporting, though this must be managed proportionately given the size of the project. For example, convening a variety of downstream partner reporting calls to assess delivery could be done without adding too much administrative burden.

Overall, activity under this indicator is highly effective, and contributes to long-term capacity building for strengthened accountability for CRSV in country.

Output Title	Enhanced access to quality and survivor-centred support and service for survivors and children born of CRSV, and strengthened pathways to survivor centred justice and accountability.
Output number:		3	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Survivor-centred Investigation and documentation principles used globally. Murad code guidelines adopted by multiple states and CSO's.	13 countries implement the Murad Code. Additional countries endorse Murad Code; ii. Minimum Murad Code standards adopted by investigators in at least 3 of the 13 countries.	Partially Achieved – 12 countries
3.2 Stigma faced by survivors within justice systems reduced	Findings from pilot testing form the basis for recommendations on how to reduce stigma related to CRSV in the criminal and alternative justice system; ii. Recommendations rolled out in at least one country criminal justice system; iii. Methodology for reducing stigma in alternative justice system developed.	Exceeded
3.3 Number of survivors directly supported in a holistic and survivor-centred manner through UK funded projects, including the Global Survivors Fund and the ICC's Trust Fund for Victims.	2500 survivors identified in FY24-5 continue to benefit. ii. Additional 2500 survivors benefitting by March 2025.	Achieved
3.4 Survivor voices in policy making strengthened within UK and international fora, demonstrated through number of survivors participating in the Survivor Advisory Group, and International Alliance, and number of UK consultations with survivors.	Survivors' networks incorporate survivors in sustainable roles including as paid staff or trained volunteers. 2. Survivors actively contributing to the development of CRSV policy through sustained quarterly meetings with PSVI team. 3. UK consults survivors on draft CAHC resolution.	Exceeded

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 3.1: PSVI continues to mainstream adherence to the Murad Code in policy and programme engagements across the board. For example, they have worked with British Embassy Kyiv and the PSVI Team of Experts to build awareness of the Murad Code amongst those responsible for investigating and prosecuting conflict-related sexual violence in Ukraine.

Although PSVI did not fund the Murad Code this fiscal year, the following examples demonstrate ongoing impact since the 2022 PSVI conference, with more states—including new adopters—now implementing the code.

Implementation of the Code at country level includes:
- Canada: Global Affairs Canada is the donor of the current phase of the Murad Code project (2024-26/7).
- US: In 2024, former US administration Vice President Harris announced the launch of the Dignity in Documentation Initiative, providing funding for global, integrated, and holistic CRSV documentation programming in line with the standards set out in the Murad Code.
- South Sudan: Having met Nadia Murad at the PSVI 2022 Conference, a senior military officer has acted as a national champion for the Code. South Sudanese military justice institutions have taken steps - supported by the UN and key figures in the armed forces - to integrate principles of the Murad Code into the investigation and adjudication of CRSV cases, despite legal and structural limitations.  This was supported by UNMISS and Synergy for Justice - using another PSVI tool which incorporates the Murad Code - the Stigma in Justice Toolkit.
Engagement with national war crimes teams on Murad Code Competencies: Netherlands and Canada both reported use and informal incorporation and use of the Murad Code in their work.

Implementation of Code – investigators and other information-gatherers/users implementation:
- Through its “helpdesk”, the Murad Code project team offers stand-by advisory and technical assistance on implementing the Code. To date, IICI have delivered sessions with over 350 practitioners working on SCRSV.
- Syria: Lawyers and Doctors for Human Rights (LDHR) have used the Code to strengthen their forensic medical documentation practice and since the transition on 8 December 2024, have been training first responders and members of the humanitarian clusters on the Murad Code.
- Mexico: UNHCR Mexico have championed the Code within the GBV Subworking Group for Refugees, Asylum-Seekers, and Migrants; IICI has delivered a helpdesk with the group.
- Kosovo: UNDP Kosovo delivered training for journalists on gender and conflict sensitive reporting. The training methodology was designed based on the Code.
- Nigeria: Explore Humanitarian Aid Initiative have delivered a training on the Code for their research team.
- Myanmar: safeGBVreporting initative (spearheaded by UNFPA) referenced the Code as a key resource for INGOs documenting CRSV in two practice guidance notes produced in 2023/24
- Cote d’Ivoire: Delivered an informational session with Ivorian journalists, who have implemented the Code into their approach to interviewing survivors/covering CRSV issues.
Indicator 3.2: Steward Women (SW) in South Sudan advanced this objective by facilitating case mediation through traditional chiefs in family courts. Their active involvement proved effective for resolving disputes and fostering family and community cohesion. Capacity building sessions enhanced the chiefs' mediation skills, resulting in fewer family disputes and strengthening restorative dispute resolution within communities. The SW project saw increased reporting of cases at the legal aid clinics, an increased number of survivors accessing justice and an increased number of perpetrators being jailed. The project also trained justice actors and local chiefs. They used live radio talk shows to discuss the impact of stigma and access to justice for CRSV survivors, with comprehensive information on their legal rights included. The listeners during the call-in times asked questions or made contributions on the topics under discussion and the talk shows contributed to awareness raising on the realities of stigma faced by survivors at the community level.

Deploying mobile courts in remote areas and locations with high case backlogs has enhanced access to justice for survivors and helped reduce the number of pending cases. However, establishing static courts in these regions is necessary for long-term sustainability. The expenses associated with mobile court deployment are considerable, and may present financial challenges for the government.

Reflecting on the sustainability of UK funding, the Synergy for Justice toolkit project (of which funding from the UK ended prior to FY24-25), contributed to this indicator. For the annual review, the review lead held a meeting with Synergy and learned that the toolkit is now being piloted in Occupied Palestinian Territories (OPT), Ukraine, Nepal, Central African Republic and Colombia. In OPT, they are working through the High Judicial Council and Attorney General’s Office training judges and prosecutors on stigma and producing guidelines for understanding and adjudicating sexual violence cases, with training scheduled for October 2025 in Istanbul. Synergy are also planning to host a session at the annual International Criminal Court Assembly of State Parties meeting to understand gaps in the judicial system for children affected by CRSV, to potentially develop a compilation of case studies highlighting best practices for engaging with child survivors.

Pilot testing of Synergy’s conflict-related sexual violence (CRSV) Stigma Toolkit in South Sudan provided key findings that informed recommendations for reducing stigma related to CRSV within both criminal and alternative justice systems. Through survivor workshops and advocacy planning sessions held between September 2023 and March 2024, survivors identified stigma, fear of reprisals, and harmful societal attitudes as major barriers to justice. Targeted recommendations include community awareness campaigns, survivor-led advocacy, and reforms to customary courts (COTAL) to include legal focal persons. These recommendations have begun to be rolled out in South Sudan’s justice system, with survivor networks actively promoting these reform plans to civil society and government stakeholders. Furthermore, a methodology for reducing stigma in alternative justice systems has been developed, focusing on integrating legal expertise into customary proceedings and training COTAL members on survivor-sensitive practices. These efforts mark progress toward reducing stigma in both criminal and alternative justice mechanisms.
Indicator 3.3: highlighted here is work by the Global Survivors Fund, who supported 2,221 survivors (1518 female, 703 male) in FY24-25 through their interim reparative measures (IRM), which provides survivors compensation, livelihood support, education grants, support to set up businesses, financial management training, psychological support, and access to medical care. Survivors supported is likely much higher than numbers received in reporting given benefits are also seen by children affected by CRSV and other survivor family members.

As part of monitoring for this Annual Review the programme PRO and review lead travelled to Guatemala to observe GSF activity, specifically the cocreation model whereby GSF create IRM projects hand-in-hand with survivors.

The majority of victims of Guatemala’s armed conflict (1960 – 1996) were indigenous Mayans, who suffered targeted atrocities, including sexual violence. In 2016, a landmark court case convicted two former military officers for crimes against humanity, marking the first time a national Guatemalan court criminally recognised sexual violence as a weapon of war. The court awarded 18 reparations designed with survivors, such as education, health, and land initiatives, to promote justice and healing for indigenous communities.

The Guatemalan Government has not yet implemented reparations, making timely action crucial given victims are aged 70–90. Since state-led reparations remain unrealised, the Global Survivors Fund is providing interim support. Survivors reported that “sadness is still there, but it is not the same because of all the support we have had” and repeatedly thanked GSF for listening to them and holding space to amplify their voices in meetings with Government and other CSOs. The project will be £1.5m across 3 years, with phase one commencing in FY25-26. The visit was an example of successful survivor-centred programming, and further reporting will take place at the programme closure review.

Additionally, Medica Zenica in Bosnia supported 236 survivors through a provision of 725 services– 475 psychosocial and psychological services and 250 legal services. These services aimed to strengthen the engagement of safe houses and faith-based organisations (FBO) in six local communities to mobilise community activities to reduce stigma and ensuring access to rights and services of CRSV survivors on local levels.

One of the survivors who received support through the project and who was empowered and psychosocially strengthened, started openly speaking up and was one of the speakers in the podcasts that was implemented within the Awareness raising joint online campaign - https://www.facebook.com/share/v/17MCSTCvWB/.

Indicator 3.4: Incorporating a survivor-centred approach has continued to be deeply embedded in PSVI’s strategic approach, particularly through our ongoing collaboration and consultation with PSVI Survivor Champions and the Survivor Advisory Group (SAG). In FY24-25 we have increased the frequency of meetings of the SAG, from two to three virtual meetings. Meetings are delivered with interpretation into Spanish, French and Arabic with an average of 10 –12 participants attending each meeting, an increase from 8-10 in FY23-24. Through these discussions, PSVI had the opportunity to provide updates on PSVI activity and seek inputs, including on how the SAG can help inform and shape PSVI efforts to address CRSV. This has included continued consultation with Survivor Champions and SAG on the draft Crimes Against Humanity Convention. PSVI funding has also supported SAG members to be increasingly involved in shaping international efforts to address CRSV. In November 2024, the UK funded the Mukwege Foundation to host a dedicated workshop for over 20 members of the SAG and SEMA network in Colombia. The objective was to increase survivors’ capacity to advocate for their demands and to hold States accountable for their legal obligations relevant to CRSV. At the end of the workshop, survivors from SEMA, SAG, together with representatives of Colombian survivors, agreed on 5 advocacy priorities which were presented by SAG members at the International Alliance PSVI Meeting. During the PSVI Conference, 10 public statements and presentations were delivered by seven survivors. Additionally, from March 4–6, 2025, a three-day capacity-building and advocacy strategy workshop was held in Kampala, Uganda for 22 survivors and 10 allied CSOs. During this workshop, survivors developed a Ugandan Call to Action based on the SEMA Global Call to Action and identified their advocacy priorities. These workshops significantly increased survivors' ability to advocate their demands and hold States accountable for their legal obligations related to CRSV under international law. At the public event in Kampala, three survivors participated in the panel to present their demands to over 25 stakeholders, including representatives from the government, embassies, civil society organisations, and religious leaders.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No significant changes were made to the output indictors in FY24-25, only updates to wording – as published on devtracker.

A reduced level of activity was delivered under indicator 3.1 due to limited capacity within the PSVI team.

For 3.3, we did not make a contribution to the Trust Fund for Victims this financial year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress was made with engaging the SAG in both PSVI policy development as well as with international fora. This included supporting consultation with SAG and international organisations including UN Action to relaunch the Stop Rape Now campaign, and funding the Mukwege Foundation to host a workshop for members of the SAG and SEMA in Colombia and Uganda to strengthen survivors’ advocacy and accountability efforts regarding CRSV at the International Alliance high level meeting.

Recommendations and lessons learned for future engagement with survivors include:

- Whenever engaging survivors in workshops/meetings ensuring that a significant lead in time is accounted for to ensure that the process of engagement can be fully consultative. Bringing survivors in from the outset to shape the topic of discussion, set the questions and frame the discussion is key.
- Need to better consider how the IA engages survivors across the international community and what the UK role is in relation to SAG when engaging the International Alliance.
- Positive feedback received from US colleagues on the powerful impact of the SAG for their involvement in the IA. Need to consider how to best use the SAG as a tool of advocacy amongst key state actors to shift dial on CRSV reduction.
Output Title	Increased data and evidence available and used to inform efforts to address CRSV and strengthen standards and practice on prevention and response, and increased capacity building on CRSV across HMG.
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 Capacity and capability of governments and grassroots organisations in focus countries to tackle CRSV strengthened, demonstrated by number of projects in focus countries supported.	i) 1000 more survivors receive psychological trauma support in Ethiopia. ii) Survivor recipients in Ethiopia in 23-24 satisfied with trauma support received. iv) Appropriate community based psychosocial support model identified.	Exceeded / 1,200 survivors supported through Daughters of Charity HAL
4.2 Number of UK experts deployed to focus countries to strengthen prevention and response to CRSV	i. FCDO capacity to deploy PSVI Team of Experts (TOE) increases. ii. Capacity building and knowledge development of key stakeholders in at least 2 additional PSVI focus countries by March 2024 supported by deployments of the PSVI Team of Experts	Achieved / Three deployments, one of which was deployed to South Sudan, a PSVI focus country, and the other to Israel and the Occupied Palestinian Territories, a Foreign Secretary Priority Country, and a PSVI country of concern. One desk-based deployment on the Murad code in UK Defence.
4.3 Number of experts commissioned to carry out research and evidence building around CRSV related issues.	Evidence from existing "What Works To Prevent Violence Against Women and Girls” Programme utilised to strengthen responses.	Partially Achieved
4.4 Learning and evaluation of what works to tackle conflict related sexual violence and drive global change captured and used	Monitoring Evaluation and Learning (MEL) partner reports on time and to an acceptable standard of quality.	Achieved

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 4.1: in Ethiopia 1200 survivors accessed support through an adapted version of community-based psychological support called Helpful Active Listening (HAL). These survivors gained access to counselling through two trained case managers from the local health centre. Provisions like emergency multipurpose cash support and basic hygiene materials were provided by the project to complement these efforts. There were 120 HAL Circles each supporting 10 survivors (1200 individual survivors in total). The inspiring work carried out by Daughters of Charity gained international recognition: How Tigray war rape victims turned to Rwandan genocide survivors to heal | Mental Health | Al Jazeera.

Indicator 4.2: Deployments of the PSVI Team of Experts (ToE) supported the progression of the milestones for both indicators. The PSVI ToE was deployed three times this year:

South Sudan – To support United Nations Mission (UNMISS) in South Sudan in implementing the project “Advancing Accountability for Sexual Gender Based Violence-Conflict Related Sexual Violence (SGBV-CRSV) Crimes in South Sudan: Achieving Impact Through a Victim-Centered Approach,” which is funded by Norway. The expert supported the development of written guidance on the protection of victims and witnesses throughout the judicial process.
Several lessons learned were gleaned from this deployment, including around ensuring enough time for in-person meetings and subsequent product development, as well as best practice for managing deployments through a third party.

Israel/OPTs – a member of the PSVI ToE conducted a deployment to explore how the UK could best add value to the international response to reports of CRSV. This work has informed future programming and efforts by the PSVI team and Posts.
Lessons learned include early engagement with posts to ensure collective buy-in on the deployment and sufficient lead-in time to arrange ToE programme and logistics. Recruitment and contracting of the ToE was challenging given new recruitment process and timelines with Palladium at the outset of future deployments. This issue is now resolved as we now understand the new process.

Desk-based deployment on the Murad Code in UK Defence – a member of the PSVI ToE conducted a review of how the Murad Code could strengthen HMG practice and another on implementing the Murad Code in the Ministry of Defence.
Lessons learned include needing time to carefully outline terms of reference between teams when sharing a deployment.

Through UK support, the Team of Experts and UN Action respectively facilitated the rollout of the SRSG’s Model Legislative Provisions and Guidance on Investigation and Prosecution of Conflict-Related Sexual Violence and the Framework for the Prevention of CRSV in South Sudan. PSVI funds the UN Team of Experts to advance capacity building, technical support and knowledge building initiatives in various conflict-affected states, with a view to ensuring enhanced accountability for CRSV, including a Prosecutors conference in The Hague, which convened global prosecutors, practitioners and experts to support knowledge/experience sharing.

Indicator 4.3: Desk-based deployment on the Murad Code in UK Defence – a member of the PSVI Team of Experts conducted a review of how the Murad Code could strengthen HMG practice and another on implementing the Murad Code in the Ministry of Defence.

Indicator 4.4: the MEL partner has been integral to the PSVI team’s success this FY, contributing insightful products such as the strategy review, leading workshops and our previous annual review. These have helped shape the future strategic direction of the initiative. Reports were produced through monthly meetings to establish priorities and leverage MEL expertise.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Minor wording changes on the milestones were made and approved prior to the annual review.
Because ToE deployments are dependent on demand and team capacity, a risk of significant underspend was identified against the budget allocation for the PSVI Team of Experts (ToE). This was identified early and the decision was made to reallocate funds to other PSVI activity. However, this did result in fewer ToE deployments.

On MEL, the programme team should ensure any MEL expertise gained from the external partner is institutionalised.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

There continue to be challenges regarding the utilisation of the PSVI Team of Experts, particularly due to the substantial capacity required from FCDO Desks and Posts to host and subsequently draw on the expertise of a deployed expert. Key lessons include ensuring clear understanding of the resources involved in advance and agreeing a roadmap detailing the involvement and expectations of desks and posts before, during and after a deployment. Deployments with minimal logistical complexity such as desk-based deployments and virtual interviews could also be considered.

Recommendations for the year ahead include:
- Develop a quick guide for desks and posts to understand the resources involved in supporting and utilising the deployment of an expert. Conduct early engagement with posts to ensure collective buy-in on the deployment and sufficient lead-in time to arrange the expert’s programme and logistics.
- Developing a roadmap for the recruitment process for project managers to ensure timelines are realistic and achievable from the outset. This is partially completed, but important to include in inducting new project managers. Ensure enough time for in-person meetings and subsequent product development in designing a deployment and considering the complexity of any field work.
- Develop options for minimising the complexity of deployments, the role of third parties and risk management and the option for desk-based and virtual assessments and conributions of expertise.
## VALUE FOR MONEY (1 page)

Key cost drivers and performance

Two significant underspends were reported for the PSVI Team of Experts (ToE) and MEL partner allocations (due to changes in team priorities affecting activities). These were identified early and funds were reallocated to other PSVI activity to ensure good Value for Money (VfM). The programme showed flexibility in budget adjustments. For example, managers redirected saving to support survivors and witnesses of CRSV who were at risk of reprisals after a prison break in Eastern DRC. Similarly, delays in UN Women spending in South Sudan led to a budget reduction, approved by the SRO, with the funds redirected to support UN Women activities in Colombia, consistent with PSVI objectives.

Partners have taken steps to appropriately manage cost drivers, including:
Staff and management costs: For the PSVI ToE, the cost per hour for an expert is standardized across the roster and benchmarked to market rates.
- Best practice in procurement of goods and services: UN Women applies their organisation’s “Procurement and Contracts Management Policy” for the procurement of all goods and services thereby ensuring the procurement process is competitive and robust.
- Ensuring the majority of PSVI funds go towards survivors: Global Survivors Fund spent 80% of their budget on their social mission (delivering interim reparative measures to survivors) and we scrutinise spend as a GSF board member.

The total budget was £3.85m, and the final spend was £ £3,851,984. which means we there was an overspend by almost £2k, which equates to just 0.05%, which is far below the 10% tolerance threshold as set out in FCDO KPI guidance. The overspend was agreed before the spend was made, resulting from strong relationships, accurate budget management, forecasts and monitoring throughout the year.

Global Survivors Fund work demonstrates significant value for money, with modest amounts of financial support enabling survivors to enact transformative change in their lives. For example, in the Democratic Republic of the Congo, individual transfers were not large: USD 800 enabled survivors to start small businesses, access medical care, and regain financial independence. These impacts also have a ripple effect, benefiting survivors’ families and wider communities. By co-creating projects with survivors, GSF also ensures resources are directed to measures that have immediate, tangible, and lasting results, while also laying the groundwork and creating an evidence base that can be leveraged for state-led reparations in the future.

The Daughters of Charity (DoC) project achieved savings during Ethiopia's macroeconomic reforms beginning in July 2024, which shifted the country to a market-based foreign currency system. This reduced foreign exchange shortages and narrowed rate spreads, allowing DoC to redirect savings toward survivor livelihood support. By leveraging internal management expertise instead of external consultants, further cost reductions were realised e.g., DoC staff delivered HAL method training and managed case-services at no extra cost. The integration of livelihood initiatives into the psychosocial support programme was enabled by: 1) Exchange gains from significant Birr devaluation, and 2) Reallocation of funds from donor-covered activities. These changes addressed survivors’ economic and psychosocial needs, introducing three new objectives to improve their sustainability and resilience.

As per the recommendation of the previous annual review, better gender disaggregation of data has begun, but partners should be required to go further in disaggregating data and reporting this regularly to inform planning for future programming.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The key risk that emerged during this period is similar to previous years: Fragile operating contexts.

As outlined in the risk register, there is a risk that due to changes in operational environment, suppliers may fail to deliver outcomes. For example, outbreak of conflict, worsening of conflict, change in political situation. As stated previously, there were multiple scenarios where conflict inhibited delivery of programming, and the close working relationships between the PSVI team, Post managers and implementers ensured the continued delivery and success of the programme.

As an example of best practice, DRC TRIAL International responded to increased security risks in South Kivu last financial quarter, after M23/AFC's military offensive and territorial occupations including Bukavu. To keep the project conflict-sensitive and do no harm, the organisation:
• Updated its conflict analysis more frequently, relying on near-daily exchanges with local partners and field-based protection actors, and integrating inputs from coordination platforms such as INSO, OCHA, and the Protection Cluster;
• Temporarily suspended or relocated activities in areas under military occupation or affected by active conflict (notably in Bukavu, Kalehe, and Walungu), prioritizing remote support modalities and safer zones where feasible;
• Adopted stricter criteria for beneficiary engagement, in line with the organization’s security protocols, to avoid exposing individuals or communities to retaliatory risks or manipulation by parties to the conflict;
• Strengthened collaboration with transitional justice and humanitarian actors to ensure alignment with emergency response priorities and avoid duplication or harmful overlaps in a volatile and fast-moving context.

TRIAL identified an unintended consequence of an increased risk of re-traumatisation or stigmatisation of victims and community actors in areas newly occupied by M23/AFC, where judicial actors and civil society organizations associated with past accountability efforts have been directly targeted. TRIAL initiated consultations with affected partners to reassess safety protocols and was able to swiftly organise, with the help and financial contribution from FCDO, vital emergency assistance to victims and human rights defenders under immediate threat. The project has thus been adapted to minimize harm while remaining responsive to the rapidly evolving conflict dynamics.

Safeguarding:
The programme’s commitment to adopting a survivor-centred approach is a key component in managing safeguarding effectively. By actively involving survivors in the design, planning, and implementation of interventions, the programme has ensured that safeguarding measures are not only robust but also deeply informed by the lived experiences of those most affected. Additionally, a survivor-centred approach also builds trust between the survivors and the implementing partners, crucial for effective safeguarding, as it encourages survivors to engage with the programme and report concerns and/or risks.

Following the last Annual Review, the PSVI team has taken pro-active steps to strengthen management of risk. The PSVI team established quarterly risk reviews take place at the programme level, with project managers expected to flag changes to risks to the PRO and SRO throughout the project cycle. Through robust mitigation and strong management several risks were successfully closed this reporting year. The overall programme risk continues to be moderate, which is within the FCDO acceptable risk appetite.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

This programme presents significant management challenges due to its numerous projects and complexities involved in supporting and engaging vulnerable groups of survivors. Alongside narrative and financial reporting - which the PSVI Team assesses as largely satisfactory - regular meetings have been established between partners and programme managers, taking place with PSVI and Post (where appropriate) colleagues on a monthly or six-weekly basis. These meetings address various aspects of programme delivery, including progress against the workplan, proposed programme modifications with their underlying rationale, and potential risks and impacts.

The FCDO engages with partners using two different modalities to achieve programme objectives. The first modality is funding to local NGOs and CSOs. FCDO funding supports these organisations to deliver outputs on the FCDO logframe.

However, challenges with reporting emerged in relation to IOM, as there is a cross FCDO-IOM agreement that IOM can use their own reporting templates. This resulted in inconsistencies and gaps in submitted information due to different internal reporting templates. To address these concerns, BE Baghdad increased in person engagement with IOM and the PSVI team undertook a field visit to Iraq, where they met directly with IOM, beneficiary organisations, and survivors. Through these consultations, the PSVI team were reassured of the positive impact and effectiveness of IOM’s activities on the ground. Nevertheless, the team recommends that, for future delivery, the standard reporting template to be used is thoroughly confirmed by both sides at the beginning, and regular communication channels are maintained to enable closer monitoring of risks and ensure a rapid response should circumstances require it.

The second modality is through larger multi-donor funds, such as GSF, UN Women and the UN Multi Partner Trust Fund (OSRSG Team of Experts and UN Action). These organisations provide proposals and use their own logical frameworks, and the UK contributes with other donors to the achievement of these logframes. They do not report against specific outcomes or indicators of the PSVI programme. These are important strategic relationships for the UK and the principles of collaboration and burden sharing which underpin these partnerships are also important. Nevertheless, contributing to larger multi-donor fund logframes results in gaps between reporting requirements of the FCDO and reports received from these partners. These are exacerbated because there are often changes to the original proposals and/or changes that result from the difficult contexts. Building and maintaining relationships with these partners is key for effective reporting in these multi-donor funds, which has been improved this year given a more consistent PSVI programme team. Considerations are needed on a proportionate way to strengthen impact reporting, especially to make the case for future funding proposals.

OSRSG - Multi-Partner Trust Fund (MPTF), UN Action and UN Team of Experts: Data concerning impact (as opposed to inputs) of UK funding remains limited. This could be addressed by encouraging MPTF to adapt their logframes to emphasise impact measures (such as the quality or utility of training) rather than input measures (such as the number of people trained), or by better understanding the logic of their theory of change. Additionally, there is some overlap between the FCDO and MPTF logframes, and more detailed, impact-oriented reporting in these overlapping areas could be encouraged. While recommendations from last year’s annual review were pursued, staff changes within the PSVI team affected continuity in the relationship management and communication channels, which reduced oversight.

UN Women: Quarterly (and sometimes more frequent) meetings with UN Women have strengthened oversight and provided a platform to address project delivery and challenges. Reporting is now more focused on impact and aligned with proposal frameworks, making it more effective since the last annual review.

Global Survivors Fund: Monthly meetings with GSF maintain accountability and an effective partnership, allowing quick responses to new developments. The UK remains on the board, providing direct involvement in GSF's internal processes and strategy.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

There were two field visits conducted for this review in August and September 2025, so while not undertaken in FY 24-25, it informed the review. A MEL strategy is recommended for the year ahead, to ensure monitoring visits are planned and strategic, and at different points in the year as the last annual reviews recommendation to conduct more field visits was not fulfilled and therefore remains.

Since the last annual review:
- A programme-costed-extension has taken place, ensuring the continuation of impact of the programme. The extension is aiming to streamline the programme to have fewer implementing partners, in line with previous recommendations, and is incorporating flexibility to respond to emerging government priorities and continuing to build on recommendations from previous reviews.
- This annual review has shown that the PSVI programme continues to map sustainability of its previous funding (through the Guidebook, Murad Code and Stigma Toolkit) and should continue to remain up to date with work that was previously PSVI funded, by incorporating regular catch ups with relevant organisations. As per the recommendations for this review, more can be done on mapping impact, but the sustainability of funding is evident.
- Programme management has been simplified after restructuring the team into policy/engagement and programming/expertise groups. In the year in review, staff decreased from three programme managers and one PRO with six Post pot managers, to two programme managers and one PRO. This does ensure that programming knowledge is streamlined and deepened within the team but does risk capacity issues. Given the complexity of working with survivors, the PSVI team should review staffing needs for ongoing programme management.
- A guidance document was developed and disseminated for Post managers to better inform roles and responsibilities between PSVI team and Post, and requirements for managing smaller grants, and a standard agenda for partner meetings.
- The MEL partner produced a review of the theory of change and logframe, which informed final edits to the logframe milestones for this FY, but more work should be done to ensure they take account of contextual changes for the coming year. The programme aims to encourage global change and boost international action on CRSV by working through partners. While the logframe takes an innovative approach in this sense, the annual review process shows that its effectiveness is hard to measure. The team should seek expert advice on redesigning the milestones for the next financial year to better demonstrate UK impact and ensure project-level logframes align with the those of the overall programme. The logframe should also be regularly updated and actively used.
- Regular partner meetings should be organised to ensure all partners are aware of wider UK goals and funding, and to encourage cross fertilisation of learning, ideas, gaps and sharing of good practice across implementers and with policy colleagues.