## Annual Review Template

Title: Women and Girls Health: The Ending Preventable Deaths of Mothers, Babies and Children Support Programme
Programme Value £ (full life): £15,000,000		Review date: 14/09/2025
Programme Code: 301582	AMP start date: 14/09/2023	AMP end date: 01/01/2031

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	B
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301582 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301582 Documents (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW
Description of programme
The EPD Support Programme is an essential component of the UK’s approach to helping reduce preventable maternal, newborn and child mortality.

Context
The FCDO published the ‘Ending the Preventable Deaths of Mothers, Babies and Children by 2030’ Approach Paper in 2021, setting out the UK’s commitment to help end preventable maternal, newborn and child deaths. The Approach supports global efforts in line with Sustainable Development Goal (SDG) targets to reduce the global maternal mortality ratio to less than 70 per 100,000 live births, and to end preventable deaths of newborns and children under 5 years of age.  It focuses on key issues affecting the health of women, babies and children: health systems; gender, equity and rights; and the wider determinants of health (including poor water, sanitation and hygiene; malnutrition and the impacts of climate change).

Since October 2024, this approach now operates under the name of ‘Healthy Women, Children and Newborns (HWCN): A Coordinated Approach to Ending Preventable Deaths’ and the approach will be referred to as HWCN throughout this report.

Country engagement and programming
Though the Approach can be leveraged across all countries where the UK government has a presence, we have a smaller set of more intensive partnerships, referred to as ‘flagship’ countries, which are the key targets for the EPD Support Programme. Currently, these are Bangladesh, the Democratic Republic of Congo (DRC), Ethiopia, Kenya, Malawi, Nepal, Nigeria, Pakistan, Sierra Leone, Somalia and South Sudan. Our engagement and programming efforts also remain flexible to provide tailored, but more limited, partnership and support to countries in protracted crisis, such as Yemen, Syria, Iraq and Afghanistan.

Monitoring, evaluation and data
The Approach utilises a monitoring and evaluation plan that supports effective analysis and a balanced approach to results. We have developed dashboards for each flagship country to provide a bespoke picture of the health landscape in each country. These focus on impact and help communicate the national picture of causes and trends in mortality, FCDO country activities targeting mortality reduction, and FCDO programmatic support. They provide a holistic perspective on country health outcomes and are used as an analysis tool to support course correction and forward planning.

The EPD Support Programme and Global Health Centre of Expertise
The EPD Support Programme sits within a grouping of Centrally Managed Programmes (CMPs) under a ‘Centre of Expertise’, which contribute to the overall agenda through targeted support, including on nutrition, WASH, SRHR, climate and health, health systems and research and innovation. This coordination is integral to the FCDO’s multisectoral way of working, providing a demand-driven platform for programmes to coordinate support.

The programme was designed to provide short and long-term technical assistance (TA) to complement bilateral and multilateral UK investments, policy and diplomacy efforts. TA support so far has been supplied by DAI, through FCDO’s Expert Advisory Calldown Service 2 (EACDS2) framework. This was an interim arrangement for 2024/25. Going forward, TA support will continue to be supplied by DAI, selected after a competitive tender process through FCDO’s Global Development Delivery (GDD) framework. (See Output 4 for detail).

In the context of the programme and TA delivered under the EACDS2 framework, long term technical assistance refers to a year long contract, and will be referred to as HWCN Long Term TA consultant throughout the rest of this review. TA that is contracted for less than a year is characterised as short term TA, and will be referred to as HWCN Short Term TA consultant throughout the rest of this review. In addition, there are 4 programme funded HWCN advisers referred to as HWCN advisers.

The TA mainly uses local experts, is context specific and demand driven, and works hand in hand with the existing portfolio, country governments and other partners’ efforts. The programme design allows it to be responsive and flexible to country context. Separately but complementary to this consultancy-based TA offer, the programme offers funding for a small number of long-term, in-house HWCN adviser roles to support the work of flagship Posts.

Whilst the programme targets 11 flagship countries, there is scope to broaden out where opportunities arise. The programme included a Strategic Flexible Fund to support discrete, catalytic work, but this will be de-prioritised in the year ahead (See Output 2 for detail).

Key achievements supported by this programme during the reporting year include:
- Completion of Climate and health vulnerability assessments in Kenya, Nigeria and Somaliland.
- Deployment of 3 UKHSA Public Health Rapid Support Team (PHRST) specialists to provide surge support to the mpox outbreak in the DRC in October 2024. The surge support was first provided by a European nation and welcomed by Africa CDC.
- Key actions towards tackling maternal mortality, including development of county action plans on maternal health interventions in Kenya and progress towards national-level strategy on addressing the causes of maternal mortality in Malawi.

Summary supporting narrative for the overall score in this review

Overall, the programme scored an B based on achievement of milestones. This is considered an accurate reflection of a programme that overall delivered a quality service and continued to build proof of concept, despite some areas for improvement and quantity of delivery that did not meet expectation due to commercial framework issues. Going forward, the programme will be delivered via the GDD framework and will be an essential component of the FCDO’s Global Health Centre of Expertise (CoE). The CoE will cohere x-HMG action on global health, support modern health partnerships and help end preventable maternal, child and newborn deaths.

Output 1 on high quality technical assistance provided to flagships scored an A. This was judged to be appropriate to the current indicator methodology (recommended for review next year), reflecting the overall strong quality of the TA delivered, despite lower than expected quantity. This has paved the way for effective delivery via the GDD framework.

Output 2 on flexible use of funding to respond to country and global needs scored an A. Clear continued achievements in terms of the use of the Strategic Flexible Fund element of the programme to support targeted, catalytic activities. However, planned activities focused on specific FCAS (Fragile & Conflict Affected States) could not go ahead and there is more work to do to ensure that a robust equity lens is threaded through programme delivery.

Output 3 on ownership by FCDO leadership, sharing of learning and reaching the most marginalised scored a C. The programme has continued to make progress, but not enough and more needs to be done to explicitly articulate the “how” around reaching the most marginalised; and to establish a more robust mechanism to capture diplomatic engagements.

Output 4 on the successful use of consultancy frameworks scored a C, given commercial delays and delivery pause. At time of writing, after a long delay, the signing of a new GDD contract is imminent.

Major lessons and recommendations for the year ahead

Delays in transferring to the GDD framework and the conclusion of portfolio delivery under EACDS2 have meant that the programme has not had as significant an impact this period as was expected. However, demand for technical assistance remains high and the programme has continued to receive good feedback as a flexible, demand-driven mechanism that aligns with the UK’s modern partnership approach.

Specific recommendations:

EPD programme team should continue to pivot the programme to align with growing FCDO priority areas, including health financing and climate. This will be taken forward within the existing parameters of the programme scope and design but will be given additional focus within TA discussions and assignment design with interested teams.

More focus in TOR design and development stage of assignments to think through and clearly articulate who and how assignments will practically engage with organisations, that look to ensure that work is impacting upon the poorest and most marginalised.

EPD programme team needs to establish a better mechanism for capturing instances of FCDO diplomatic engagement and equity work within all assignments throughout the year. This should become part of ongoing programme M&E and could use stablished M&E instruments to better capture e.g. key question at quarterly check-ins, question within HWCN stocktake commission.

Re-assessment of how instances of flexible funding will be captured going forward. With uncertainty over the availability of the Strategic Flexible Fund, the programme should consider capturing a wider suite of flexible programming, that encompasses all elements of the programme e.g. instances of TA supported within non-flagship countries, number of health financing TA assignments supported.

Continued engagement and conversations with countries on their current priorities and needs, in changed context of reduced overall ODA and new country business planning. Conversations will help to inform how bottleneck analysis and HWCN country Action Plans will be used and updated going forward to guide programme decision making.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change for the programme is in the Figure above. The outcomes are still valid for the programme. The outputs of the long and short-term consultants are still evolving – particularly in light of the portfolio delivery pause - but remain valid at time of writing.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact	Improved health of poorest and most vulnerable women, children, and adolescents, contributing to reductions in maternal, under five, and neonatal mortality rates in 11 flagship countries
Indicator(s)		Milestone(s) for this review	Progress
Reduction of 5% in average maternal, newborn and child mortality rates in the 11 EPD flagship countries by 2026.		Next Review 2026	N/A - Not applicable for this annual review
Improvements of 5% in Universal Health Coverage Index indicators across the 11 EPD flagship countries by 2026. / NB Indicators of Universal Health Coverage cover Reproductive maternal newborn child health, Infectious Diseases, Noncommunicable Diseases and Service capacity and access		Next Review 2026	N/A - Not applicable for this annual review but dashboard developed to help consistent tracking of data (see summary section above).

Outcome 1	Increased flagship government commitment and capability on ending preventable deaths, through increased integration of priorities to help end the preventable deaths of women, babies and children.
Indicator(s)		Milestone(s) for this review	Progress
Evidence of increased flagship government shift and strategic alignment, through official government commitments and declarations to action towards ending preventable deaths agenda.		3	Exceeded: 5 / Kenya (2): / 1. HWCN Long term TA consultant led engagement with senior Ministry of Health leadership – including Director of the Department of Family Health and Head of the Division of Reproductive, Maternal, Newborn, child and Adolescent Health (RMNCAH) - to develop targeted action plans for two counties – Isiolo and Marsabit - on maternal and newborn health interventions. / 2. HWCN Long Term TA consultant led engagement with Ministry of Health Head of Division resulted in completion of Climate Change and Health Vulnerability and Adaptation Assessment (CCHVA) and Health National Adaptation Plan (HNAP) workplan. / Somaliland (1): / 1. HWCN Long Term TA consultant supported drafting and endorsement of the Somaliland Health Sector Coordination Framework (HSCF), led by the Ministry of Health Development (MoHD) with support from partners. This provides a structured mechanism to align stakeholder efforts, reduce duplication, and enhance accountability. While operationalisation is pending, the framework offers a strong foundation for harmonised planning and donor coordination. / Nigeria (2): / 1. HWCN Short Term TA consultant lead on design of Nigeria’s Social Action Fund (SAF), working with national and subnational teams to implement in pilot states, to inform national scaleup. The SAF approach has been developed with Ministerial inputs, focusing on health, WASH, food, nutrition and economic security. Government appointed new Coordinator for SAF, showing commitment to carry through implementation. / 2. FCDO Nigeria health team and HWCN Adviser worked with the government of Nigeria and partners to deliver Nigeria’s first climate and health vulnerability and adaptation assessment, and to complete the Health National Adaptation Plan. FCDO has also led work with Federal Ministry of Health to engage with States to develop and deliver their own climate and health adaptation plans.
Evidence of improved willingness from governments to engage with UK thinking and support on policy/influencing issues.		3	Exceeded: 8 / Bangladesh (1): / 1. Technical workshop conducted by UNICEF in February 2025, with technical leadership from HWCN Short Term TA consultant, to review and reflect on the implementation of previous National Strategy on WASH in Healthcare Facilities (2019-2023) and inform the upcoming strategy. Representatives from Ministry of Health and Family Welfare (MOHFW), Ministry of Local Government and Rural Development (MOLGRD), Ministry of Housing and Public Works (MOHPW) attended and showed willingness to commit to the implementation of the new National WASH in Healthcare Facilities strategy (2025-2030). Draft now endorsed by FCDO and UNICEF Bangladesh. / Somaliland (3): / 1. Key priority areas for programme support were jointly defined between the Ministry’s Director General and the Director of Planning, the FCDO Health Adviser and the HWCN Long Term TA consultant, (including strengthening sector coordination, nutrition and community health data management, M&E, public financial management), demonstrating interest and engagement by government at input level. / 2. Working in collaboration with the FCDO Gender and Human Rights Advisers, the HWCN Long Term TA consultant supported the inclusion of gender-sensitive and rights-based provisions into the draft Health Act, including the requirement for informed consent for Caesarean section. Recommendations were well received by the Ministry of Health Development (MoHD), though still requires institutionalisation. / 3. The HWCN Long Term TA consultant supported the MoHD in integrating findings from Climate and Health Vulnerability Assessment into district and regional health planning processes. TA was also provided to embed climate risk indicators into existing monitoring and evaluation frameworks. / Nepal (1): / 1. Ministry of Health and Population (MoHP) hosted a Human Resources for Health (HRH) meeting, focusing on the HRH landscape in Nepal. Participants included the British Embassy and the HWCN Short Term TA consultant. Subsequent meetings between the consultant and the Secretary of the MoHP showed keen interest in updating HRH fact sheet and emphasised Ministerial support to review HRH quotas. / DRC (1): / 1. Initial consultations and a workshop - including HWCN Short Term TA consultants, FCDO representatives, and government officials - on the National government Plan for Quality of Care. The revised draft of the National Strategic Plan for Quality of Care, produced by HWCN Short Term TA consultants, was acknowledged by the Secretary General of the Ministry of Health. A priority in the revised strategy is improving quality of services provided to mothers and children (including strengthening midwifery skills in primary health care). Government validation of the strategy expected in August 2025. / Nigeria (2): / 1. The HWCN Adviser and FCDO health team have played pivotal role—both as co-chair of the Health Development Partners group and as a bilateral donor—supporting the design and governance of the SWAp. The HWCN Short term TA consultant worked closely with government on its design, including the Coordinating Minister’s Chief of Staff, Head of Sector Wide Approach Coordination Office, Director of Nutrition, and the new dedicated Fund coordinator. / 2. The HWCN adviser has leveraged national and subnational platforms to advocate for increased government utilisation of the UK’s investment in the Child Nutrition Fund. This initiative has successfully leveraged significant domestic commitments, including a ₦2.5 billion ($1.6 million) allocation from the Nigerian Federal Government alongside $2.2 million in match-funding from 11 states for nutrition commodities.

Outcome 2	Galvanised collaborative action and coordinated global advocacy within FCDO networks and civil society institutions, to affect country government activities and commitments towards EPD.
Indicator(s)		Milestone(s) for this review	Progress
High level dialogues between governments and joint advocates for mobilising political will towards actions and commitments on preventing maternal, newborn and child mortality. Joint advocates to include governments, FCDO teams (posts and central) and civil society organisations.		4	Exceeded: 10 / Kenya (1) / 1.Engagements between HWCN Long Term TA consultant and Netherlands Ministry of Health have resulted in clear direction on co-funding the Climate Change and Health Vulnerability and Adaptation Assessment in Kenya. / Malawi (3): / 1. HWCN Long Term TA consultant engagement with senior academics in obstetrics and gynaecology has resulted in plans to co-design a national-level strategy on addressing the main causes of maternal/perinatal mortality. Strategy development will involve collaboration with clinicians and professional associations, with the intention of influencing practice across the sector and Ministry of Health policy. / 2. HWCN Long Term TA consultant engaged with Kamuzu Central Hospital, Amy Foundation and Centre for the Development of People to spearhead an initiative to promote access to reproductive health services for intersex people, transgender men and lesbian women. / 3. HWCN Adviser, in partnership with Save the Children International, has held engagements towards roll out of 5-year initiative to build climate resilient health systems nationally, and in 6 vulnerable districts in southern Malawi. Have ensured strong focus on protecting women, children and newborns from climate related diseases and climate health impacts. Wider stakeholder engagement has included MoH, Department of Climate Change and Meteorological Services (DCCMS), and local governments, to ensure national ownership. / Somaliland (4): / 1. HWCN Long Term TA consultant engagement with the London School of Economics (LSE) and Ministry of Health Development and initiated a dialogue on the development of a legal framework on women's consent for Caesarean sections. / 2. HWCN Long Term TA consultant meeting with Plan International Country Director resulted in Plan agreeing to engage directly with Deputy Minister including on sector coordination, expanding maternal and child health services and strengthening delivery of primary health care. / 3. HWCN Long Term TA consultant engagement with representatives from UK DHSC towards collaboration under the Global Health Workforce Programme helped to kickstart integration of HWCN priorities into plans for workforce strengthening initiatives. / 4. HWCN Long Term TA consultant participation in FCDO Better Lives Programme Mission (April 2025) - High-level strategic and technical meetings, including Quarterly Review Meeting and joint field visits with the Ministry of Health Development Team and partners. Strengthened partner coordination, clarity on aid prioritisation and data harmonisation. / Nigeria (2): / 1. The HWCN Adviser facilitated collaboration between the Nigerian Government, UK Government, and the World Bank, towards mainstreaming nutrition objectives and culminating in the launch of a Global Compact/Coalition on Nutrition Integration at the 2025 Paris N4G summit. / 2. Joint funding from the EPD Flexible Fund, FCDO Nigeria’s bilateral health programme and the Climate and Health CMP helped convene government and non-government stakeholders, under the leadership of the Federal Ministry of Health and the National Council on Climate Change, to integrate health ambitions into Nigeria’s Nationally Determined Contributions 3.0 - a crucial step towards unlocking Green Climate Fund resources, reducing greenhouse gas emissions and adapting to climate change impacts.

The programme is built on an assumption that consultants – particularly long-term - can use their technical expertise, contextual understanding, and political know-how to galvanise action across FCDO, partners, and governments. Despite the delivery pause which meant we were unable to mobilise as many assignments as expected, this assumption continues to hold.

Progress reports provide evidence that consultants are continuing to stimulate the kinds of conversations and engagements that pave the way towards greater awareness, advocacy and action. There is every reason to expect a continuation of this once the programme is mobilised via GDD, particularly given the additional scope provided by GDD for long-term consultants (the EACDS2 arrangement having entailed a maximum duration of 12 months).

As it moves to GDD, the programme’s learning function will continue to interrogate the individual, organisational and systemic changes that these engagements contribute towards, as well as the ways in which the long-term consultants are able to steward this process from initial conversations to concrete commitments and actions.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
As reflected elsewhere in this report, there have been delays in transferring the programme to the GDD framework; and a pause in portfolio delivery once duration and spend ceilings were met under the interim EACDS2 arrangement, as well as wider external factors (e.g. ODA reduction to 0.3%). The programme’s flexible, demand-led design has also continued to present challenges in anticipating demand and spend with a high degree of accuracy. However, the programme is considered a “best practice” mechanism for working with embassies that supports close partnership with governments, adapted to country context to ensure sustainable results. Despite challenges this year, the programme has still managed to deliver some excellent support, presenting value for money and catalytic benefits for health. As a proof of concept of how a fully demand led programme could function, the programme has been a success and is well positioned to take the lessons learned from this year to scale up delivery under the new GDD contract. As mentioned above, the programme remains a core element of the FCDO’s Global Health Centre of Expertise, which is a vital mechanism for ensuring strategic, multisectoral delivery that represents good value for money and helps maximise UK impact. There remains a clear demand for targeted technical assistance for system change, both from FCDO flagship Posts and central teams. The programme will be well-placed to meet this going forward, and given its broad thematic scope, to adapt its focus as needed. With this in mind, it is recommended that the programme should continue.

## C. DETAILED OUTPUT SCORING

Output Title	High quality Technical assistance provided to flagship countries
Output number:		1	Output Score:	A
Impact weighting (%):		45	Weighting revised since last AR?	Yes, revised down by 15%

#	Indicator(s)	Milestone(s) for this review	Progress
1.1	Number of consultants successfully meeting or exceeding assignment objectives and deliverables as a measure of capability and impact in their roles’	85%	Achieved – 100% / (From feedback for 9 out of 9 TA assignments and 3 out of 4 PFPs)
1.2	Number of HWCN flagship country action plans completed	11	Partially Achieved – 10/11 completed (Ethiopia still in progress)
1.3	Scoring of TA by implementing client, based upon: / 1) TA process / 2) TA provision	1) TA process > 75% satisfaction 2) TA provision > 75% satisfaction	Exceeded - / Average score of 4.5 (90%) / Average score 4.3 (86%)
1.4	Number of completed TA deliveries that have a post-completion follow up to assess the medium-term impact of implementation and convey lessons learned (between 6 months and 1-year post-TA) (starting 2nd year)	2	Achieved– 3 post assignment completion follow ups completed (Improving Health Coordination in Malawi, Designing of a Programme Implementation Coordination Unit in Malawi, Common Metrics for Health Systems Strengthening)
1.5	Percentage of completed consultancies concretely feeding into FCDO posts ongoing and future thinking towards HWCN work	>60% of completed consultancies	Exceeded – 91% (10 out of 11 assignments)

Briefly describe the output’s activities and provide supporting narrative for the score.
During the Annual Review period, the programme has had 9 TA assignments completed or ongoing via the EACDS2 framework. The flagship countries involved are Bangladesh, DRC, Kenya, Malawi, Nigeria, and Somalia/Somaliland. We also have 4 internal Programme Funded adviser roles embedded, in Ethiopia, Malawi, Nigeria, and Somalia/Somaliland, with a further role to be recruited in Bangladesh, following an enforced pause in recruitment due to the UK Government’s announcement regarding reduction in ODA spend.

1.1 The measuring of whether consultants have met agreed KPI’s is assessed both through qualitative feedback collected at midpoint check in (only long-term assignments), and scores on feedback survey after assignment completion. Successfully meeting objectives is defined as minimum 3/5 on the feedback survey scale for completed projects, or qualitative feedback for those not completed. All assignments that have taken place during the Annual Review period have received positive feedback regarding the achievement of KPI objectives and milestones. Some example qualitative feedback included:

- ‘performed exceedingly well, able to drive good rapport with Ministry of Health team.’
- ‘assignment achieved its objectives although faced some hurdles with the leadership... had to be creative in delivery approach when working with country health management.’
- ‘a key convener in the development partner space and a trusted partner of the government.’
- ‘leant into large number of areas and has given them a significant capacity boost.’
One assignment on Common Health Metrics underwent adjustment of its KPI’s, due to acknowledgement of setting overly ambitious objectives at the outset, and the mutual decision to conclude the assignment earlier than originally contracted. The assignment involved working with WHO, and objectives had reliance on multiple stakeholders, which contributed to not meeting ambitious objectives. With adjusted and more realistic expectations and objectives to suit the pace of progress, all final objectives were achieved, and the assignment managed to achieve good political buy-in, which is fundamental towards future success. Lessons on realistic objective setting and flexibility during assignment have been discussed. Additionally, assignments that involve engagement and buy-in from government have tended to face delays in securing approvals or gaining traction. This should be better considered within assignment design and timescales going forward.

For the Programme Funded roles, we replicated the feedback process, with all programme funded roles judged to have been successfully meeting their objectives to date, and in some cases exceeding assignment objectives.

1.2 10/11 HWCN flagships have now completed a specific HWCN Action Plan, with Pakistan and South Sudan finalising their Plans during this AR period, in addition to the 8 received last AR (which some have been updated since). These articulate country health context and priorities, and how Posts intend to use TA to complement existing activities towards reducing maternal, newborn and child mortality. Ethiopia has completed a draft Action Plan, although it is still to be finalised. Action Plans will remain active documents and will continue to be updated as priorities evolve, although they may require significant adaptation, as country plans and priorities are significantly impacted by ODA cuts and country business planning carried out over the past year.

1.3 Scoring for this is drawn from the EACDS2 Lot 4 Service User Satisfaction and Feedback Survey. The two specific questions relating to this indicator are ‘Quality of support’ and ‘Overall level of satisfaction’. The survey was designed with each question having a maximum score of 5 for total satisfaction. Eight feedback forms have been received so far, and the average satisfaction score for Quality of Support was 4.5 (90%) and Overall level of satisfaction was 4.3 (86%), showing an overall high level of satisfaction with the TA process and delivery support through the programme.

1.4 Post-consultancy follow-ups are completed to help inform whether consultancies are having a lasting impact on thinking at Post. 3 follow-ups were completed in the period, for Improving Health Coordination in Malawi, Designing of a Programme Implementation Coordination Unit in Malawi and Common Metrics for Health Systems Strengthening. All 3 assignments have reflected positive and ongoing impact post-consultancy completion. It was noted that assignments have led to higher commitment from Ministries and seen momentum to continue the work, though next steps are still in progress. For some assignments the progress has been impacted by other external factors, such as elections.

1.5 All the previous indicators only included TA assignments from this AR period. However, this indicator 1.5 includes the cumulative of all assignments throughout the entirety of the programme (including from the 1st year of the programme). This is because the indicator is capturing the longer-term impacts and sustainability of assignment delivery and learning. Assignments that were completed during the previous review period can remain very relevant and influential on ongoing thinking within Country Posts and Central teams. Hence why previous year assignments are included in this specific indicator.

From qualitative feedback on the Malawi Climate and Health Short Term TA consultancy, that was completed during the last Annual Review period, it is likely that this will not feed into the future work of the FCDO post, due to issues with assignment delivery and quality. However, the other 8 feedback forms received from Posts have all indicated that they would be making use of and integrating knowledge gained from assignments into their ongoing and future work.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Changes to outputs

Output 1.1 and Output 1.3 from previous year were removed, due to process focus.
Output 1.1 from this review had indicator text amended, to focus on assignment objectives and deliverables rather than KPI’s.
Output 1.3 from this review had indicator milestone revised down from 80% to 75%, to better reflect scoring against a 1-5 scale, and that a 4/5 score reflects strong performance.
Output 1.5 was previously Output 4.1 in 1st Annual Review.

Planned changes

No changes planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There has been light touch work to better map TA within a country, rather than just capturing individual assignments. Tracking of TA across all TA health draw downs, as well as comparing with the needs articulated within specific Country Action Plans, can help to develop an overall country health narrative. Greater focus on this could allow for a more coordinated, multisectoral evaluation of overall health impact. There have not been any further climate specific assignments this year, so previous recommendation cannot be assessed, but recommendation remains valid consideration going into next programme review period.

Future recommendations:

- Indicator 1.2 and Country Action Plans should be reviewed within the period. Most Action Plans were agreed pre-0.3% ODA announcement, and ongoing country business planning exercises, so should be reviewed and updated if required. If the Action Plans are assessed to have become outdated, assessment should be given to whether the indicator requires amending.
- For assignments that require government buy in or sign off, additional timescales should be better anticipated and built into assignment design.
Output Title	Flexible use of programme funding to respond and capitalise on identified additional opportunities for furthering global work towards ending preventable deaths, both centrally and in Posts.
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	Yes, revised up by 5%

#	Indicator(s)	Milestone(s) for this review	Progress
2.1	Number of instances of using flexible funding to provide Short-Term Technical Assistance or provide strategic funding opportunities to improve health outcomes of mothers, babies and children. Responding to requests from:1) Crises in non-flagship country contexts / 2) FCDO Central teams / 3) HWCN flagships	1) 1 additional consultant or similar technical assistance in an FCAS country context. 2) 3 additional instances of using strategic funding to support FCDO Central Teams to further HWCN opportunities 3) 3 HWCN flagships	Partially Achieved - Have engaged with Post in Yemen but not yet supported any activity within Business Case list of FCAS countries. However, there has been support provided to HWCN flagships that are FCAS countries – DRC, Nigeria, Somalia/Somaliland. / Exceeded 5 – WHO Climate snapshots, Save the Children N4G advocacy, N4G reception, CFS interpreter translation support, Stillborn Alliance Conference. / Achieved 4 – Supported flexible funding in DRC, Kenya, Malawi and Nigeria.
2.2	Percentage of TORs, assignment objectives and workplans that incorporate a clear equity lens towards creating increased equity.	50%	Exceeded – 67% / 6 out of 9 assignments show equity lens articulated within the design of the assignment TOR, workplan and objectives.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme was designed to work flexibly to respond to new and changing demands from colleagues at country Posts and central teams, and capitalise on catalytic opportunities for impact towards improving the health outcomes of mothers, babies and children.

2.1.1 There has not been any assistance provided to FCAS country contexts, outside of the 11 flagship countries. Initial exploratory discussions did take place with Post in Yemen, but without a specific opportunity to support at that time. However, work has been supported in flagship countries that are defined as FCAS contexts by the World Bank classification. There have been 2 instances of support in both Nigeria and DRC: one instance of TA and one of flexible funding. Additionally, there has been long term TA support in both Somalia/Somaliland and Nigeria.

2.1.2 This has been achieved through 5 instances of support through the flexible fund component of the programme:

- Funding to support the WHO in developing Science and Policy snapshots for use at the Global Conference on Air Pollution held in Cartegena, Colombia in March 2025. This led to development of 35 high quality, accessible knowledge products to support evidence-based decision-making on air pollution, energy and health. The snapshots helped facilitate discussion at the Conference. WHO extended gratitude to FCDO for the support in making this initiative possible and providing global policy area support.
- An Accountable grant with Save the Children to conduct essential advocacy work in advance of the Nutrition for Growth (N4G) summit in Paris in March 2025. This included engaging with global nutrition leaders, parliamentarians, youth and civil society representatives, and played a significant role throughout the summit, including participation in the opening and closing ceremonies of N4G. The work received positive feedback from France’s special envoy on nutrition. Work has continued post-summit to help mobilise country commitments and accountability around implementation.
- Funding to host a Global Compact side event at the Nutrition for Growth (N4G) summit at the British Residence in Paris in March 2025. The reception was in advance of the launch of the Global Compact on Nutrition Integration. The UK co-hosted the reception with the World Bank, Government of Nigeria, and IFAD, and helped to raise the profile of the Nutrition Integration Compact and galvanise Compact signatories. The Compact was successfully launched with 80+ countries and organisations signing up to join.
- Funding to cover interpretation costs at Committee on World Food Security (CFS) annual event in Rome in October 2024. Funding for English, Spanish and French interpretation services allowed for amplification of messaging provided by speakers at the event, key towards mobilising support in advance of the Paris N4G summit and raising the profile of nutrition integration.
- Funding to sponsor health representatives at the International Stillborn Alliance Conference in Colombo, Sri Lanka in November 2024. Sponsoring allowed attendance of participants to collaborate with experts in the field of stillbirth and neonatal mortality on key policy areas, areas for greater global action and global success stories on stillbirths, which could be used to enhance stillbirth policy action in home countries.
2.1.3 This was achieved through 4 instances of flexible funding support in HWCN flagships:

- Sponsored the deployment of 3 UKHSA Public Health Rapid Support Team (PHRST) specialists to provide surge support to the mpox outbreak in the DRC in October 2024. The specialists joined the Africa CDC-organised response in Kinshasa, providing specialist epidemiology and infection control input into the regional response. The surge support was the first provided by a European nation and was publicly welcomed by Africa CDC.
- Funding for hosting of 2 workshops in Marsabit and Isolo Counties in Kenya, to agree costed action plans to accelerate reduction in maternal, newborn and neonatal mortality in September 2024. The workshops helped support the County Health departments prioritisation on reducing mortality. The developed plans from the workshop were disseminated and provide a roadmap to mobilising domestic and external resources to address prioritised RMNCH interventions.
- Sponsored an Air Pollution workshop in Malawi in January 2025, alongside the University of Birmingham, focused on convening key health personnel to discuss research gaps, air quality management challenges and how these can be collectively addressed. The workshop convened key personnel from the Ministry, Academics and donors to agree areas for collaboration to reduce air pollution.
- Hosting a state level workshop on climate and health adaption planning in Nigeria in March 2025. The workshop included all State Health Commissioners and key climate and health focal points, to educate on climate and health basics and adaption planning, build leadership and introduce available resources, towards accelerating climate work to reduce preventable deaths. Every state (37) attended, and the workshop helped to catalyse climate action planning.
2.2 Increasing equity within health is an essential element of our delivery. Greater effort has been made over the last year to ensure that an equity lens is applied (where relevant) within the design and delivery of assignments, including clear articulation within TORs and workplans. From reviewing assignment TORs and workplans, 6 out of 9 assignments this year have a clear articulation of how greater equity is being addressed and embedded within the assignment delivery. This includes examples such as:

- Kenya (Long Term TA) - ‘Providing technical assistance to counties to integrate Reproductive Health activities including ending preventable deaths, women and adolescents, SRHR, social inclusion and gender equality in health and nutrition programming.’
- Somaliland (Long Term TA) - ‘Support the Gender and Human Rights initiative...towards ensuring that women and girls are protected by law to seek the heath and psychosocial care they need, free from blame, stigma, and social exclusion. This will include understanding the extent to which the national legislation supports informed consenting by women to obtain caesarean section.’
- Nigeria (Social Action Fund) - ‘SAFs can accelerate poverty reduction through providing communities with funding and support to make prioritised investments in community assets. They are a ‘Community Driven Development’ (CDD) approach... From design output, has ensured focus on inclusive CDD, with specific focus on women and youth voices, and promotion of their income generation opportunities.’
- Bangladesh (WASH in Health Care Facilities) - ‘Analysis should fully embrace GESI (Gender Environment and Social inclusion) and in particular focus on supporting women and girls, poverty reduction and disability issues... The issue of disabled users should also be considered. In the assessment and evaluation reports, all data must be disaggregated (ideally by age as well as gender).’
Additionally, the programme transferred funding to UNFPA Mali, through our Post in Mali, to carry out a review and recommendations for amendment of Reproductive Law 02-044. The law is under review, and funding helped to identify some key recommendations for increasing the coverage and equity of the law. This included recommendations to extend protections, improve accessibility and guarantee individual rights.

The work of our Programme Funded roles has not been captured in the same way for this indicator, as they do not have the same assignment design through TORs and workplans. Additionally, due to recruitment time lengths, some job descriptions for Programme Funded roles were written in early 2024. However, as EPD programme advisers, equity and work towards reaching the poorest and most marginalised was an essential consideration and rationale in the design of the roles and remains central within their delivery. Ways to better capture this element will be considered for the next review.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Changes to outputs

2.1.3 - Indicator text amended from 'any additionally identified opportunities' to 'flagships.'

2.2 - Indicator changed from previous focus on hiring specific equity and FCAS roles. Instead, focus now on capturing equity articulation and work within assignments.

Planned changes

Indicator 2.2 will have a higher target percentage in future years, to reflect that equity should be a clearly articulated component of most assignments (and assignments without an equity lens should only be very focused pieces of work and largely the exception.)

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

From the previous Annual Review, the approach to integrating equity has changed. Previous intention to hire a specific Programme Funded role to focus on equity across the EPD programme portfolio has been changed to now focus on the articulation and implementation of clear equity language into assignment design and workplans. This has shown good success (as shown in indicator 2.2), but work remains to make equity considerations an even more essential element of assignment design and delivery.

The programme team put some resource into proactively generating demand on the offer of the strategic flexible fund, resulting in several catalytic opportunities supported (shown in indicator 2.1). This did include discussions with FCDO non-flagship Posts (Yemen, Guinea-Bissau) on potential opportunities. Wider support was provided to Mali, a non-flagship, although this was via money transfer rather than the flexible fund.

Future recommendations:

- Should be consideration given to the current wording of indicator 2.1, and its focus on the strategic flexible fund component of the programme. Current funding for the strategic flexible fund remains uncertain for the next programme review period. As part of the FCDO shift towards a flexible TA and deep partnerships model, indicator 2.1 could look to incorporate a broader suite of support (flexible funding, TA, policy advice).
- Target percentage of assignments with equity focus should be raised, given its importance to successful delivery and impact towards ending preventable deaths.
- Consideration should be given to how equity work within the internal Programme Funded Roles can be better captured and measured, either through revised wording to the existing Indicator 2.2 or an additional Indicator.
Output Title	Strengthening joined up approach and collaboration towards HWCN priorities, at global and national level.
Output number:		3	Output Score:	C
Impact weighting (%):		20	Weighting revised since last AR?	Yes, revised up by 10%

#	Indicator(s)	Milestone(s) for this review	Progress
3.1	Instances of FCDO diplomatic engagement informed by the EPD Support programme – social media posts, strategic comms, specific meetings around HWCN work.	5	Not Achieved: 3 / Kenya / Deputy Director Development and Head of Human and Social Development Team in Nairobi prioritised climate and health in Post’s strategic plan and advocated for Ministerial commitment on climate and health through direct engagement with the Principal Secretary for Public Health. / Malawi / The High Commissioner attended a rally that was organised to create awareness on road safety. Given the link to child mortality, HWCN Long term TA consultant wrote the High Commissioner’s speech. / HQ/flagship network / Development Directors participated in a HQ-led Steering Committee meeting in December 2024. The Committee comprises of the HWCN Hub, representatives from flagship posts, central departments including geographical, the Head of Profession for Health and members of Global Health Directorate’s senior leadership team.
3.2	Number of events and meetings held across country contexts and consultants that specifically focus on sharing of experiences and learnings towards improving outcomes for women, child and newborn health.	6	Achieved: 6 / Oct 24: HWCN Long Term TA consultants learning meeting / Nov 24: Malawi pause and reflect session / Feb 25: HWCN Long Term TA consultants learning meeting / March 25: Learning Session (Engaging Governments in FCAS) / May 25: Learning Session (FCAS Health Systems) / August 25: Development of International Maternal Newborn Health Conference (IMNHC) abstract on HWCN approach
3.3	Proportion of pieces of work targeting the poorest and most marginalised and engaging/consulting with a wide range of actors, including women’s rights organisations and organisations of persons with disabilities.	60% of consultancies	Not achieved – 33% / Clear targeting and associated engagement explicitly articulated in Terms of Reference and/or workplans for 3 out of 9 TA assignments (in Malawi, Nepal and Nigeria).

Briefly describe the output’s activities and provide supporting narrative for the score.

3.1 Review of the work of long-term consultants in Kenya and Malawi noted instances of FCDO diplomatic engagement informed by the programme (listed in the table above). In addition, a Steering Committee meeting provided an opportunity for strategic engagement with a senior audience (HQ-based and across flagship Posts), with the programme featuring as an important component of wider UK efforts on this agenda.
3.2 There were 6 learnings events held by the supplier during the Core Services contract period (February 2024 to February 2025) – reflected below for completion although only 3 counted towards milestone achievement for this annual review cycle:

The Malawi and Kenya long-term consultants' knowledge exchange session in May 2024 was documented in last year’s review. Following its success, a second was held in August 2024, where the consultants shared learning on the similarities and differences between the assignments. For example, the consultant in Kenya was working with FCDO as an individual consultant, whereas the consultant in Malawi was embedded in FCDO during this assignment. The consultants shared how these differences impacted the effectiveness of their work in terms of information access and stakeholder management.

The impacts of the various models were discussed and investigated further in a Long-Term Technical Assistance consultant learning meeting in October 2024, which engaged all three long-term consultants (Kenya, Malawi and Somaliland), FCDO central team, FCDO country post colleagues, and the core service provider.

One more Long-Term Technical Assistance consultant learning meeting was conducted in February 2025 before the conclusion of the core services contract, and the discussion led to the production of a learning product around typologies of long-term advisers (independent adviser, adviser embedded within FCDO country office, adviser embedded within government, adviser embedded within a development partner). The opportunities and limitations of all types of support were elaborated, to help inform future assignment planning.

In November 2024 the supplier facilitated a country-specific (Malawi) pause and reflect learning session, bringing together stakeholders including the FCDO Post responsible for the long-term and short-term Technical Assistance. The discussion focused on how the consultants could complement each other in achieving the programme objectives.

In addition to these supplier-led learning events, the EPD programme team worked with Posts to establish an informal community of practice mechanism, to support Learning Sessions on topics of interest. Sessions took place in March and May 2025, focused on the challenges related to operating in fragile (FCAS) contexts, including working with host governments and supporting progress on health systems. Representatives from Posts attended to absorb and share learning, including consultants and Programme-funded health advisers. The systems-focused Learning Session was delivered by HWCN Long Term TA consultant in Somaliland.

Finally, our 4 programme funded Posts (HWCN advisers), in collaboration with the central programme team, worked to develop an abstract on the HWCN approach for submission to the International Maternal Newborn Health Conference (IMNCH) 2026. This involved numerous sessions of discussion of experiences and progress towards maternal and newborn health in Malawi, Nigeria, Somalia and Ethiopia, before collaboratively drafting and submitting an overall abstract that captured the HWCN approach, with specific case studies for action and impact within each country.

3.3 From our increased focus on equity work within the FCDO, we know that early articulation within the design phase of key groups and stakeholders to engage with is essential towards integrating equity effectively. Making change and progress on equity is very hard to do but is essential towards making fair and sustainable progress on health. We want this programme to have equity properly integrated, so we have set a very high bar for what is accepted as a good demonstration of articulating who and how the assignment will engage with, to ensure equitable delivery that reaches the poorest and most marginalised. This will be a continued focus under the new GDD contract.
As stated in Indicator 2.2, we strengthened efforts to ensure that an equity lens was applied (where relevant) within the design and delivery of assignments, including engagement with a wide range of actors. However, from reviewing assignment TORs and workplans, only 1/3 assignments this year have explicitly articulated how will target the poorest and most marginalised and engage with a range of actors:

- Malawi (Long Term TA) - “Engagement and support for groups representing sexual minorities”. "Meeting with [...] Ivy Foundation, which is working towards the creation of awareness especially for intersex persons to create a better environment which caters for their needs and is more understanding of their differences."
- Nepal (Subnational Human Resources for Health) – “The HRH Expert will employ a coherent use of technical support, policy dialogue and collaboration efforts that foster frank and practical exchanges on HRH that will ultimately create a more conducive environment for the expansion of basic health services and towards improved universal health coverage metrics. Monthly workplans and reports show specific targeting of debate on provision to slum areas, and for specific groups at risk including the elderly”.
- Nigeria (Social Action Fund) - "(SAFs) are a ‘Community Driven Development’ (CDD) approach, with communities themselves identifying local priorities for development... SAFs can improve health and education outcomes and economic welfare at the village and household level... improve participation, agency, and voice in community development – contributing to a stronger social contract... from design output, has ensured focus on inclusive CDD, with specific focus on women and youth voices, and promotion of their income generation opportunities”.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

3.1 - Indicator wording revised to make a clearer link between diplomatic engagement and the programme, and therefore easier to measure. However, more proactive monitoring is required (see below).

3.3 - Indicator was adjusted downwards to be more realistic. The milestone has not been met this year and requires even more of a concerted effort going forward.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s Annual Review recommended that the programme team and supplier should nudge inclusion of a focus on the most marginalised groups within TORs (acknowledging that the ultimate content of the TOR is up to Posts); and ensure that consultation with grassroots women’s organisations and organisations representing marginalised groups was part of long-term consultant TORs. As reported above, some progress has been made on these fronts. However, there is more work to do.

Future recommendations:

Strengthening of diplomatic engagement element as part of the ongoing formalised monitoring and evaluation of the overall HWCN Approach. As things stand, this is not adequately/systematically captured.

Consideration of equity-focused resource/capability e.g. reconsideration of a dedicated programme-funded or consultancy role could have a positive impact.

Output Title	Successful use of Consultancy frameworks, to provide high quality and well managed Technical Assistance
Output number:		4	Output Score:	C
Impact weighting (%):		10	Weighting revised since last AR?	Yes, revised up by 5%

#	Indicator(s)	Milestone(s) for this review	Progress
4.1	Successful management of multiple framework consultancies between EACDS to GDD at the same time, before full transition to use of GDD only (1st-2nd year only)	Successful management of both EACDS and GDD consultancies simultaneously, while maintaining a high standard of overall portfolio management. All new consultancies to be commissioned through GDD framework.	N/A - Not applicable for this annual review. As outlined in previous annual review, transfer to GDD was expected in autumn 2024, with transition period from EACDS2 to GDD between then and the end of February 2025. However, developments - including the UK Government’s ODA reduction announcement – resulted in unanticipated delays. We were also required to pause any new activity via EACDS2, given the finite nature of the timeline and spend ceiling under interim arrangement. Therefore, there has been 100% use of EACDS2 framework, for TA purposes, since mobilisation of the EPD Support Programme in autumn 2023.
4.2	Successful transition between Technical Assistance framework offers where deemed appropriate - EACDS to GDD (by end of 2nd year)	100% use of GDD framework	N/A – As above, not applicable for this annual review. EACDS2 core services (portfolio management) contract concluded on 21st February 2025, with 3 individually managed assignments still to run to their conclusion at the time of writing. Transfer to GDD now expected by September 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

As per the previous Annual Review, in lieu of the GDD framework coming on stream (designed to support longer term, higher value contracts), we decided upon use of the EACDS2 framework as an interim measure, with the intention to transfer to the GDD framework as soon as possible. Unfortunately, the commercial process to transfer to GDD has involved multiple delays, including due to internal commercial personnel changes and the UK Government’s ODA reduction (0.7 to 0.3) announcement in early 2025. It is now the expectation that a contract will be signed with a GDD supplier in September 2025.

In the meantime, we were required to conclude the interim arrangement via EACDS2, given the arrangement’s finite period (12 months) and spend ceiling (£1m). The core services (portfolio management) contract with EACDS2 supplier DAI came to a conclusion on 21st February 2025, alongside agreement for live (individually managed) assignments to run to their conclusion (of which three remain at the time of writing).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As above regarding output during this reporting year. This output will require review for next year, given that the programme will imminently begin 100% delivery via the GDD framework.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Future recommendations:

GDD framework scope and capacity (Rolled over from first Annual Review given delays to framework transfer) – draw on our existing experience with EACDS2 to ensure a robust and immediate stewardship role for the GDD supplier; utilise the GDD’s longer-term assignment potential to help Posts to maximise the strategic impact of the work; and consider opportunities for the supplier to take on additional elements e.g. stewardship of the programme’s Strategic Flexible Fund.
## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost driver for this programme is the cost of consultants and internal programme funded staff, and this review shows that, although programme delivery has been inconsistent and not at the quantity expected, these resources are being well utilised and countries appreciate the flexible resource.

VfM performance compared to the original VfM proposition in the business case

Economy

Consultant type	TA Instances	Average monthly cost of each consultant (basic pay only -excludes expenses)	Percentage of Local consultants
Long Term Consultants	3	£12,560	67% local consultants (100% regional)
Short Term Consultants	6 (5 in flagships)	£12,392 / (£13,604 for just flagship TA)	83% local consultants in flagships
Programme Funded Staff	4	£4,080	2 Country Based Staff / 2 UK Based Staff

The programme uses a mix of external TA from consultants, provided through the EACDS2 framework, and internal FCDO Programme Funded staff, to deliver flexible, demand driven work. Typically, in-house roles tend to provide a lower cost alternative to externally sourced consultants, as reflected by the average salary figures in the table above, though these vary by country. We deliver using a mix as hiring Programme Funded staff is not always possible and can involve long time lags, and so consultants tend to be more suitable for more discrete pieces of work. When using external consultants, costs are constrained by the EACDS2 framework daily fee rates, which are set based upon prior experience and expertise, to ensure value for money. Assignment expenses are discussed and agreed before contracting, to ensure they are appropriate and link to assignment delivery e.g. required travel for an essential workshop linked to the assignment. Additionally, the use of local consultants (as reflected in the table above) has helped to limit expenses on travel and accommodation, while tapping into local expertise.

Overall, the programme experienced underspend again in Year 2, partly caused by over ambition in the budget from the original Business Case, but also from internal and external factors. Commercial issues with the programme meant that delivery on new assignments via the EACDS2 framework was put on hold in December 2024. We were able to contract 2 further assignments, but only through making exemption cases to commercial and framework teams, that satisfied the time-sensitivity clause of the framework. Once mobilised via GDD, consistent delivery is expected during next year of the programme cycle.

Efficiency

The programme has been set up to provide different delivery options, to maximise outputs. The benefit of internal programme funded roles is familiarity with the FCDO context and internal structures and resources. Additionally, long term TA (consultant or Programme Funded roles) allows the flexibility to work across a variety of different issues, in support of a multi-sectoral approach. Short term TA has also delivered to expectations, though many have required longer than anticipated to deliver outcomes, often due to requiring government buy-in or approvals. This should be better considered at the design stage.

Strong programme delivery efficiency is demonstrated by high scoring across Output Indicators 1.1, 1.3, 1.4 and 1.5, that provide a reflection of TA delivery quality and impact. 100% of assignments from this review period (consultants and Programme Funded roles) have been evaluated as meeting or exceeding objectives and deliverables (as captured in Output Indicator 1.1) Our Programme Funded roles have received good feedback on their ability to navigate and influence both across FCDO internally, but also with external partners, including governments, to influence policy and thinking.

Effectiveness

The effectiveness of assignments has overall been consistently strong, with positive feedback from Posts on the impact and usefulness of assignments. All 3 Long Term consultants had good success and impact in developing internal and external relationships and driving action in particular policy areas, proving to be an effective delivery mechanism. Unfortunately, more Long-Term consultants have not yet been able to start, due to the issues with the commercial elements of the programme.

As reflected in Outcome Indicators 1 and 2, which capture policy reform and increased engagement directly informed by TA delivery, there are good examples across the portfolio of assignments proving effective in increasing political will and advancing thinking. Having dedicated resource to lead on engaging with Ministers in these areas has also helped with strengthening relationships and encouraging receptiveness to FCDO thinking.

The programme has not been able to deliver the number of assignments anticipated and desired over the past year, because of internal and external factors on delivery. However, with the new TA facility being signed imminently, it is hoped that delivery can recommence at pace and establish a consistent rhythm for future years.

Equity

Equity is a key consideration within this programme, ensuring that interventions are helping to reach the poorest and most marginalised. The offer of targeted TA is designed to offer a mechanism unlocking key blockers and gaps within health systems, to ensure equitable access for all. The programme has a gender equality marker and looks to incorporate a specific gender element into consultancies.

Demand for technical assistance is driven by requests from HWCN flagship Posts, on what is the greatest need and what would have the greatest impact. Discussion and development of assignments includes work to ensure an equity lens is applied to all interventions. As reflected by Output Indicator 2.2, 67% of our TA assignments have a clear articulation of equity lens within their TOR, workplan and objectives. However, Output Indicator 3.3 shows that we are lagging behind on assignments that clearly articulate plans to engage with a wide range of actors to make sure the voices of the poorest and most marginalised are heard. Further work is required to make sure that all assignments articulate, and more specific focus is given to stating with whom, and how, consultants will engage.

Cost-effectiveness

For relatively modest outlay, the programme has shown it can have significant impact on making advances in priority policy areas, unlocking bottlenecks, developing relationships with key interlocutors and establishing future roadmaps. As the FCDO shifts towards an increased focus on TA programmes and smaller programme budgets, instead of large-scale service delivery, the programme is an example of the catalytic effect these programmes can have on making progress in challenging contexts. The programme has also demonstrated a strong ability to work in respectful partnership with flagship countries, given its ability to be adaptable and flexible to targeted health needs. Feedback from Posts has mentioned how the support has helped them to leverage and develop relationships with country governments, in allowing them to pivot and respond to new government requests and priorities.

Assessment of whether the programme continues to represent value for money

The programme has faced many challenges with delivery, and the total number of assignments is below expected to this point. This has been due to a combination of internal and external factors. However, the modest number of assignments delivered has demonstrated that, for a relatively small FCDO investment, the programme can deliver strong, catalytic health outcomes. The demand driven, flexible and multisectoral design has allowed HWCN flagship Posts and Central teams to access the expertise needed to make progress and tackle bottlenecks in priority policy areas. This has led to significant progress in policy and relationships with key partners, that have enduring benefits towards developing modern partnerships and addressing the needs of the poorest and most marginalised. It is therefore a model for all other programmes in the next spending review period. As the programme moves onto the GDD framework, learnings from these first assignments should be embedded, and the programme should remain agile to respond to growing and changing priorities. Therefore, given the clear impact to date, and the growing focus on TA delivery, it is our judgement that the programme continues to demonstrate value for money and should remain a key delivery mechanism for FCDO’s global health objectives.

E: RISK

Overview of risk management

SHORT RISK NARRATIVE
The overall risk rating of the programme is moderate. Most risks established in the programme business case are still relevant to the programme, and ongoing review and mitigations against each risk remain essential. The risk register and overall risk rating is reviewed periodically. Risk is also reviewed with our external partner through verbal meetings and quarterly presentations, to highlight and manage existing risks and any potential emerging risks to delivery. An additional risk was added during the Review Period around the need for securing sufficient budget for this programme in future years, considering the ODA reductions. Sufficient mitigation controls have been put in place to manage this. The main risks of the programme, along with mitigation actions, are listed below.

Risk Description	Likelihood	Gross Risk	Mitigation Strategy	Residual Risk
Strategy and context
Risk of underspend means intended impact of the programme not delivered, and risk of future budget reduction or non-approval.	Highly Likely	Severe	Effective visibility of pipeline established through HWCN Action Plans and collaboration with flagship health advisers, to provide an awareness of future TA requirements and needs. Collaboration with Health Systems and Climate teams to firm up programme spend, and working to create robust pipeline of TA requests ahead of GDD transfer and budget confirmation. Programme ready to be responsive and flexible to additional demands.	Major
EPD support programme financial budget is too small to make the TA effective.	Unlikely	Minor	FCDO is moving towards an influencing and innovations approach - HWCN fits well with this organisational culture shift. The programme will utilise all the relevant tools and levers to ensure the effectiveness of TA. The EPD Support programme also represents just one programme within the Global Health Centre of Expertise and the wider strategic portfolio of HWCN.	Minor
HWCN does not stay on the agenda for FCDO in health and the TA input is not backed up with senior buy-in.	Possible	Major	HWCN is in all key health strategies. The approach with the flagships has current buy-in and the HWCN Hub are building on this. Global Health remains a clear government priority, and the HWCN agenda is well aligned to priorities on partnerships, climate, systems, TA delivery.	Minor
Safeguarding
TA providers present a safeguarding risk in countries when they are visiting and working.	Possible	Severe	The lead agency hiring TA will carry out the necessary safeguarding checks and due diligence assessments - this will be part of the TORs. There will be a shared understanding between flagships, provider and HQ on how to mitigate risks and deal with safeguarding issues, should they arise.	Moderate
Policy & Programme Delivery
The outputs do not lead to the outcomes wanted due to other external factors - complex political economy, elections, geopolitics, crises, conflict, pandemics, USAID cuts and reduction of overall global aid context etc.	Likely	Major	External factors are a big risk to achieving overall aims. However, some of the outcomes will strengthen a countries’ response to a crisis. Use of political economy analyses and flexibility of approach, tailored to changing context, will help mitigate this to some extent, though external factors will remain a key impact on delivery.	Major
Country governments and health partners do not cooperate with FCDO around the aims of the programme e.g. coordination and alignment.	Likely	Major	In some countries, the focus of the TA will be exactly on mitigating this risk and improving the coordination and alignment between partners that country office staff may not have the time to do. We are looking to ensure that programme activity is all country led, and in some circumstances may actively involve the buy in of country governments or other partners, to ensure buy in and ownership.	Moderate
Country offices cannot adequately access the centrally managed investments in health, nutrition, WASH, climate and SRHR.	Likely	Moderate	The HWCN approach has been set up to better link global & central work with the country level. The Global Health Centre of Expertise has been designed to allow for a better system and means of communication between HQ and flagships towards access to the full suite of HWCN related programmes. The availability and access to programme assistance has been set up to be used by Country Offices when the timing and demand suits them best.	Moderate
The right skills of people delivering TA cannot be found [or extensive delays affect credibility/timeliness], or the assignment objectives are at risk of not being fully met.	Possible	Major	The framework agreements include a large range of organisations, widening the scope of finding the right people. In addition, FCDO will use its own extensive networks to identify consultants. There has been regular engagement with framework supplier and country offices to allow successful assignment management, to identify early risks and implement mitigation strategies and lesson learning. New contract under GDD should also provide added resource and scope for sourcing consultants.	Moderate
The delivery of large amounts of TA to 11 countries (short and long term) is too difficult to manage from programme management perspective.	Possible	Moderate	The stewardship function of the consultancy firm should help mitigate this risk by carrying out the administration around the TA. Capacity within the Central team is being prioritised, to properly resource and drive programme delivery.	Moderate
Disruption caused by transition of consultancy management frameworks, which has been delayed due to commercial issues and factors outside of our control, and the central management of consultancies running on different frameworks simultaneously for a period.	Highly Likely	Major	Decision to change frameworks driven by new framework being more suited towards the programme technical assistance needs, but not being available during the initial stage of the programme. Taking advice and direction from Commercial on how to manage disruption to framework transfer timeline due to ongoing delays. Clear communication with flagships on timing and reasoning for transition is being followed. New contract expected imminently.	Moderate
People
FCDO does not retain enough staff at Post with the expertise to give technical oversight to the TA or HQ does not have the requisite programme experience or capacity to effectively manage the complete portfolio of consultancies.	Possible	Moderate	Although unpredictable, there are no clear signs that health staff will be reduced at post. The EPD team will lobby to maintain the current health staff in flagships to enable this effort to function and will continue to review the suitability of each HWCN flagships, should the health picture at Post change. This initiative adds to the argument to keep health expertise in country. New programme funded posts help to support this knowledge retainment at Post.	Moderate
Financial & Fiduciary
Need to secure ongoing budget approval for the programme beyond 25/26, while signing a multi-year contract with Supplier.	Possible	Major	Health is a clear priority, and delivery through the EPD Support programme is viewed as a key mechanism. Have installed clear break points within the programme Supplier TOR and contract, and caveats to allow for change in direction, that help to mitigate possibility of not securing future year budget.	Minor

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Expert Advisory Calldown Service 2 (EACDS2) framework
The expectations for delivery, commercial and financial performance of our supplier were set out in an agreed Core Services contract. This was countersigned by FCDO and the supplier on 20 February 2024; and included expectations for the management of the programme portfolio. As reported in last year’s Annual Review, the supplier produced to a high standard the Operating Principles document and a Monitoring, Evaluation and Learning (MEL) strategy, in collaboration with the EPD programme team.

Throughout the Core Services contract, objectives were met by the supplier. KPI’s for programme management and consortium were met to a good level. These are primarily based around delivery of individual support to assignments and overall management of the portfolio. Assignments have been well supported and have delivered to a good standard. This is reflected in Output 1.1 (number of consultants successfully meeting or exceeding assignment objectives), with 100% of current or completed assignments meeting satisfactory delivery against assignment objectives and deliverables. The supplier held regular check ins with both the supplier assignment leads and recipient teams during assignments, to track progress towards meeting deliverables, and assess any current or upcoming risks.

There have been occasional delays experienced between the original assignment TORs being proposed, and assignments starting. FCDO can share a portion of this responsibility, as there have been issues with staff capacity and available Delegated Procurement Officer (DPO) resource to support with contracting. There have also been instances of recipient teams requesting an interview phase, before agreeing to a proposed candidate, which added additional process time, as well as discussions around where consultants can be hosted. There has also been an instance of an assignment end date being missed by the supplier, resulting in a contract extension process having to be switched to the signing of a new contract, causing a delivery service gap. However, generally the timeliness of assignment contracting and tracking of assignment timelines has been satisfactory.

For the duration of the Core Services contract, monthly meetings continued to take place between the supplier and EPD team to discuss and update on decisions regarding ongoing assignments, progress live workstreams, discuss risks, and provide financial updates. There were also quarterly progress meetings between supplier and EPD team, for more formal overview of the portfolio of assignments, including consolidated results reporting, assessment of performance, any key risks and learnings. There were ad hoc meetings to progress and kick-off individual assignments where necessary. Supplier participation and leadership of meetings, particularly quarterly reviews, was to a highly satisfactory standard.

Following conclusion of the Core Services contract in February 2024, DAI have managed to a good standard the remaining assignments (in DRC, Nepal and Nigeria) that we agreed will run to completion as individual call down contracts under EACDS2.

The supplier has provided timely and quality reporting of financial spend and forecasting has been to a high standard. FCDO receives an indicative forecast of expected billing for the rest of the quarter and projection to the end of contract year at the end of month 1 of each quarter. FCDO then receives an updated forecast at the end of month 3, detailing expected outturn for the quarter, and an updated forecast. This has been to an expected standard. Quarterly consolidated billing of eligible charges has been submitted by the supplier, with accompanying expenses proof where required, by the month end of the following month after the end of the previous quarter, as agreed.

Individual consultant rates have been constrained within the existing EACDS2 framework, which has FCDO approved rates for consultant levels of expertise. Consultant expenses have then been agreed through consultation between supplier, recipient team and EPD team, with the aim of keeping to a minimum requirement and ensuring highest level of value for money and restriction of air travel and fuel usage.

Transfer to Global Development Delivery (GDD) Framework
As outlined in Output 4, unfortunately the transfer process involved multiple delays, due to some major external events (including UK General Election) and variable Commercial support due to personnel changes.
We had kickstarted the process of transferring to GDD back in January 2024, so that once our EACDS2 core services arrangement contract ended in February 2025 we would be able to seamlessly transition onto the GDD framework without a gap in delivery. However, due to multiple delays to the GDD transfer, this became impossible. We did explore the possibility of an extension under EACDS2 to cover the gap, but this was not possible either.
This has resulted in a significant delivery pause between the EACDS2 core services arrangement and GDD. The programme has remained without a commercial delivery contract from March 2025 to mid-September 2025. This has primarily been due to multiple issues with the Commercial support provided to support the GDD transfer process. Unavailability and lack of capacity have caused consistent delays to the transfer, which has led it to be impacted by wider external events that otherwise might have been avoided, and which have enforced further delays. This is the primary reason for an overall score of B demonstrating how important smooth running commercial processes are to a programme’s delivery and impact.

With GDD contract signing expected imminently in September 2025, we will work with Supplier to quickly mobilise portfolio delivery.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The HWCN approach has established clear Monitoring and Evaluation strands, that allow us to effectively communicate the HWCN narrative in flagship countries. Individual flagship country dashboards, that highlight the National Picture of causes and trends in mortality metrics, FCDO country activities towards reducing mortality, and overall programmatic support, provides an invaluable tool for communicating the landscape of health in countries. These dashboards have received excellent feedback from colleagues at Post and in the UK.

The country activities aspect of the dashboard is informed both by country Action Plans and the HWCN Stocktake Commission. The stocktake asks flagship Posts to periodically reflect programme, policy and diplomatic activities aimed at making progress, to allow us to develop an in-depth narrative of FCDO actions across health. The commission has received Director approval for its monitoring of results.

Through our EACDS2 contract, our supplier (DAI) has also supported us with contributions towards our overall Monitoring and Evaluation of the programme and the approach. This has included ongoing support and advice on individual assignments, quarterly presentations delivered to the central EPD team across the complete portfolio of TA assignments, and detailed inputs and reflections provided as part of this programme Annual Review.

No field visits were taken by the direct programme team, though numerous trips to flagship countries took place during the period that had a HWCN lens or focus e.g. Global Health Director visit to Nigeria to discuss climate and HWCN work. With greater delivery expected during the next review period, a future programme visit should be considered.

We have managed to meet with staff at Post during their visits to the UK and have met with all 4 programme funded advisers in person. In addition, we have had numerous virtual conversations with advisers in HWCN flagship posts, including regular check-in calls as a group, to share lessons and feedback on the effectiveness of the programme’s offer.

Evidence
The programme has a clear focus towards helping the poorest and most in need within populations. Its focus on Sub-Saharan Africa and South Asia targets nations with some of the highest levels of maternal and child mortality. This fits well with the ‘Leave no one Behind’ agenda, and we look to capture evidence on targeting and practically planning to reach the poorest and marginalised (Indicator 3.3). However, the programme has not done enough to date to clearly embed the equity piece into assignments and reporting. Relevant variables of age, sex and disability not been incorporated firmly enough into early TORs and assignment design to be adequately measured across all assignments. The programme has the availability for completing an independent evaluation, via an impartial, external consultant. However, this was not undertaken this year due to uncertainty over the availability of programme budget and long periods of non-delivery.

Learning
Our supplier has developed a Knowledge, Management and Learning (KML) strategy for capturing and disseminating learnings from the programme portfolio. This has included a meetings/activities tracker, bespoke material (such as a TA typology document) and regular meetings with consultants and recipient teams. This has allowed capturing of assignment level learning from across the portfolio. To help share these lessons and learnings, meetings have also taken place between different stakeholders, including EPD team, supplier, long term consultants, health advisers in HWCN flagship posts and programme managers across the suite of programmes within the Global Health Centre of Expertise.

The programme has identified many key learnings on what leads to successful and impactful TA work, including early defining of key stakeholders to engage, sufficient time to engage and influence, strong mix of both technical and influencing experience and capacity from Post to support and drive initiatives. These lessons will continue to inform the programme going forward, and provide helpful wider learning to the FCDO, as a wider suite of programmes look to pivot towards a more flexible, TA centred approach.

Date of last narrative financial report	19/08/2025	Date of last audited annual statement