## Annual Review

Title: UK Support to the International Finance Facility for Education (IFFEd)
Programme Value £ (full life): Up to £180m		Review date: 18/11/2025
Programme Code: [AMP ID#] 301585	AMP start date: 01/12/2023	AMP end date: 31/03/2028

Summary of Programme Performance
Year	2025	2026
Overall Output Score	A	A
Risk Rating	Moderate	High

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005760.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005763.xlsx

## A: SUMMARY AND OVERVIEW

Description of programme

Learning poverty is a major challenge in Lower Middle-Income Countries (LMICs), which are home to over 900 million school-aged children – half of the world’s total and more than three times the number found in Low Income Countries (LICs). Of these, 148 million remain out of school, accounting for over half of the global out-of-school population. Additionally, 78% of young people in LMICs (around 464 million) lack basic secondary education skills. As countries transition to LMIC status, they lose access to the most concessional financing from Multilateral Development Banks (MDBs), making it difficult to meet education funding needs through domestic resources or to borrow at higher, non-concessional rates.

The International Finance Facility for Education (IFFEd) is an innovative finance mechanism designed to address this gap. IFFEd provides guarantees and grants to MDBs, enabling them to offer LMIC governments new, additional, and affordable loans for education reform and implementation.

IFFEd began operations in 2024, with initial funding from the UK, Sweden, and Canada. Its objective is to mobilise over $1 billion in additional finance during its initial phase (2024–2028), prioritising educational opportunities for disadvantaged children and young people, including girls and boys living in poverty, those affected by rural-urban divides, disabilities, or other forms of marginalisation. By 2030, IFFEd aims to unlock $3 billion, helping to close the education funding gap and advance Sustainable Development Goal (SDG) 4.

In response to global challenges, including overseas conflicts affecting security and prosperity, the UK increased defence spending to 2.5% of GDP from 2027. This will be funded by a reduction in the UK’s Official Development Assistance (ODA) budget, which will be reduced to 0.3% of Gross National Income (GNI) by 2027. To mitigate pressure on ODA budgets in outer years of the spending round, FCDO finance team made a request to frontload the last two year’s budgets of the programme (FY26/27 and FY27/28) into FY25/26. IFFEd Secretariat and contributors’ capacity to leverage additional financing will be crucial for sustainability of the mechanism in a global context of constrained ODA budgets.

Progress and Achievements

Having become operational in September 2024, the focus of the past year has been on IFFEd’s transition from its foundation to starting implementation. Last year’s annual review highlighted the successful establishment of the facility, initial donor commitments and the development of key governance structures. In FY25/26, IFFEd has made good progress in operationalising its model, with the following achievements.

Operational Milestones:
- Frontloading of IFFEd ODA budgets from FY26/27 and FY27/28, ensuring financial certainty and enabling accelerated project delivery.
- Engagement with additional MDBs, notably the World Bank (IBRD), which is expected to formally join as a participating MDB by Q4 FY25/26.
- Discussions with the Islamic Development Bank (IsDB) on the possibility of joining.

Development and adoption of the IFFEd Accreditation Policy and successful annual credit rating renewal, retaining an Aaa rating with Moody’s and AA+ with Standard & Poor (S&P). The credit rating indicates the creditworthiness of the new IFFEd organisation, i.e. its ability to honour the guarantee payments to which it is legally committed. Formulation of the Education Impact Strategy, providing a clear framework for project selection and impact measurement.

Donor Mobilisation and Strategic Partnerships:
- Lobbying of additional donors, with progress underway to secure new sovereign and philanthropic contributions. Discussion are ongoing in particular with Australia, Germany, Denmark, France, Finland, and Qatar. A contribution from Korea has been agreed.
- Collaboration with the Jacobs Foundation (JF) to develop a philanthropy guarantee. A public-private partnership for a ‘Swiss Window’ is close to finalisation. with CHF 10 million each from JF and Swiss Development Corporation (SDC) potentially supporting $175m million in additional financing.

Project Endorsement:
- The IFFEd board endorsed preliminary investment cases for four projects, with full investment cases for two of the four investment cases expected to be finalised and submitted for board approval in December 2025.
- A FCDO and IFFEd joint visit to ADB HQ in Manila helped to strengthen project oversight and partnership and to ensure high quality of investments (including visits to the flagship AQUIRE programme).

Governance and Risk and Programme Management:
- Mobilisation of the board (in person and virtual meetings held quarterly), establishment of a fraud and audit committee and ongoing work to fully establish the education committee and in-house education support.
- Recruitment of three staff to support financial management, with prioritisation of recruiting education technical roles underway.
- Strengthened monitoring, evaluation and learning systems (MEL), with the results framework completed as part of the Education Impact Strategy.

Summary supporting narrative for the overall score in this review

For 2025, we set ourselves an outcome target of unlocking $1.5bn in new additional and concessional MDB education finance (from a baseline of $1bn). This was moderately not achieved, with $1.2bn likely to be unlocked in the first half of 2026. Reasons for undershooting the target include shrinking aid budgets globally, competing demands from other sectors and a lack of donor familiarity with guarantees which has been addressed by lobbying and sensitisation. The UK has supported this effort through numerous events and engagements at EWF, Global Economic Forum, and WB meetings. Gordon Brown, IFFEd’s founder and Honorary President, continues to be a strong global advocate. IFFEd, with support from its three founding contributors, will continue to lobby donors. We are optimistic that the instrument will attract additional contributions in 2026, albeit less than originally anticipated.

Overall progress against outputs is A. Of 7 outputs, one scores A+ (30%), one scores A (20%), and five score B (all 10%). Given the larger weights of the high-scoring outputs, the overall output score is A. Outcome and output progress is discussed in sections B and C, respectively.
Lessons and recommendations for the year ahead

IFFEd’s transition from mobilisation to implementation has provided valuable lessons. These lessons were captured in the previous review completed in 2024, and they remain valid for IFFEd’s delivery. Key lessons learned to date and recommendations for the year ahead are:

IFFEd’s innovative financial mechanism is even more important in the current global context. With an annual financing gap of $97bn for SDG4 and declining ODA budgets, combining ODA with guarantees is an even more attractive instrument to unlock additional education finance. IFFEd does just that, and does with exceptional cost-efficiency, with a leverage of $7: $1 of ODA invested in IFFEd unlocks $7 in new additional concessional MDB finance. This is the highest leverage of any development finance instrument.

Recommendation: Lessons learned from IFFEd should be shared so that the model can be replicated in other sectors. The IFFEd FCDO team is currently in discussions with colleagues in the International Financial Institutions Department (IFID) to explore a multi-sector and multi-MDB platform, modelled on the IFFEd financial mechanism.

Close FCDO collaboration with partners is essential. FCDO has established effective relationships with partners to progress complex issues and particularly in the start-up phase.
- Country engagement: FCDO visited ADB in Manila. We now understand each other better, notably on FCDO project expectations. Looking forward, as the pipeline develops ensure regular visits including to countries with planned investments and close engagement with staff at post.
- Linking with the Centre of Expertise and CMPs, such as WWHGE, EdTech and drawing on expertise on climate resilience to provide evidence and to ensure quality MDB investments.
- FCDO are talking to the World Bank, including through UKMIS in Washington. We are aligned with UKMIS, who have a direct relationship with relevant bank staff.
- FCDO has established a good relationship with Canadian and Swedish counterparts, allowing us to coordinate policy positions and pool technical expertise.
- FCDO will continue to engage with GPE and ECW to ensure geographic and thematic alignment and complementarity between the three instruments.

Recommendation: ensure that FCDO has sufficient capacity, including education advisory inputs, to continue engaging with existing and new (World Bank, Islamic Development Bank, project countries) stakeholders and to manage risks as IFFEd becomes operational.
Recommendation: ensure joint HQ-Post assessment and cultivating country demand for IFFEd loans, scoping pipeline options and assessing project viability.
Recommendation: prioritise engagement with IFFEd, ADB and WB on accelerating the development of the project pipeline in 2026 and ensuring the design of quality projects that meet FCDO priorities and standards.

Development of IFFEd in-house expertise: while progress has been made in recruiting finance specialists, the focus must now shift to building technical education capacity as projects transition from preliminary investment cases to full implementation. Donor-provided education advisory support has been beneficial, but it is key that IFFEd develops its own expertise to ensure impactful project design and delivery.

Recommendation: as soon as the Swiss host state act is obtained, IFFEd must recruit education expertise in 2026. FCDO to consider secondment of Education Adviser to the IFFEd Secretariat, in discussion with the Secretariat and considering availability of Education Advisers.

The FCDO logical framework for IFFEd will be further strengthened and refined in the coming year. This will focus on unpacking impacts in relation to SDG 4, in line with the type of projects that are implemented and MDBs’ MEL plans. In addition, all indicators will be reviewed to ensure they are specific and can be measured consistently over time.

Recommendation on risk and mitigation: IFFEd should add to each quarterly board meeting an agenda item on risk and mitigation, so that risks and mitigation can be better managed collectively between IFFEd and contributors.

Recommendation on FCDO education adviser secondment to IFFEd: in the past few months, we have been able to allocate education advisory capacity to IFFEd. This needs to continue as the pipeline develops. Going forward and subject to workforce constraints, we would recommend a full time EA be allocated to IFFEd by GED.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

In IFFEd’s theory of change and logical framework, the impact is to ensure inclusive and equitable quality education and promote lifelong learning opportunities for all (SDG 4). As implementation gathers pace, further work will be done to unpack which indicators will be used in the logical framework, as this will depend on the type of programmes that are funded by MDBs (see Section G for more information on refining the FCDO logical framework).

The outcome is increased affordable education finance committed by participating MDBs. The outcome indicator is the value of IFFEd-enabled funds committed by MDBs. The outcome baseline is $342 million in guarantees and $106 million in grants, from three founding donors, unlocking $1bn in additional affordable MDB finance. This remains the current position.

The 2025/26 outcome milestone is to achieve $1.5bn in unlocked MDB finance. It is unlikely that this will be achieved in the current financial year. Instead, IFFEd is likely to secure new contributions in 2026 that will take the MDB financing to $1.2bn. Therefore, the outcome milestone for 2025/26 has moderately not been achieved.

There are several reasons for not achieving the outcome milestone. Many donors are reducing their aid budgets. There are competing demands from other sectors, in particular climate and humanitarian. And some donors are not familiar with guarantees, meaning it is taking time to explain the new model. In addition, some donors do not issue guarantees for legal reasons.

However, IFFEd, with support from its three founding contributors, continues to lobby donors and we are confident that the instrument will attract additional contributions in 2026, albeit at a slower pace than was originally anticipated. Outputs are detailed and scored in Section C below.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue, both based on its own merits and in the context of the wider portfolio. On its own merits, the programme is only moderately not meeting expectations with respect to the annual outcome milestone. Progress on attracting additional donor contributions is slower than anticipated. However, lobbying efforts have generated an extensive list of potential contributors so we are confident that in 2026 at least one or two additional donors will join IFFEd.

In the context of the wider portfolio, IFFEd has become even more important. While FCDO’s overall education budget is being reduced, IFFEd’s initial budget allocation of up to £95m in grants and a £100m guarantee has been protected. IFFEd’s relative weight in FCDO’s education portfolio has therefore increased. The reason for this is IFFEd’s exceptional cost-effectiveness (see section D on value for money).

## C. DETAILED OUTPUT SCORING

Outputs	Logframe milestones for this review (2025/26)	Progress
Output 1 (weighting 30%): Grant funding provided to make participating MDB loans more concessional	Second tranche of £25m disbursed	A+: Output moderately exceeds expectations: more than £25m will be disbursed.
Output 2 (weighting 20%): Higher quality MDB projects through FCDO engagement	Four quality projects / approved by the board	B: Output moderately does not meet expectations: only 2 quality projects approved by the board.
Output 3 (weighting 10%): IFFEd secures additional sovereign donor and/or philanthropic / grants and guarantees	Onboard one additional / sovereign donor and/or philanthropist	A: Output meets expectations: USD $2m contribution to paid-in capital secured from the Republic of Korea.
Output 4 (weighting 10%): Agree better coherence and collaboration between IFFEd and Global Partnership for Education (GPE) where both are operating in LMICs, and work towards possible long-term co-financing	Written agreement in place	B: Output moderately does not meet expectation: discussions are ongoing but no written agreement yet.
Output 5 (weighting 10%): IFFEd has education expertise to engage with MDBs on education policy and impact	Senior education expert / recruited	B: Output moderately did not meet expectations. Delays in the completion of the Swiss host state act mean that recruitment has started but is not completed yet.
Output 6 (weighting 10%): Better quality Asian Development Bank (ADB) projects through FCDO secondment	ADB secondment recruited in summer 2025	B: Output moderately did not meet expectation. Candidates did not meet the mark in the first recruitment attempt. Second recruitment attempt taking place in November/December 2025.
Output 7 (weighting 10%): Populated results framework focused on learning and marginalised groups	Populated results framework approved by Board	B: Output moderately did not meet expectations. A results framework has been approved by the board but is yet to be populated.

Overall output score

Outputs have been revised since the last annual review, following recommendations to refresh FCDO’s logical framework to ensure relevance to IFFEd’s results framework. This was completed in February 2025. This review assesses delivery against the revised outputs.

Overall progress against outputs is A. Of 7 outputs, one scores A+ (30%), one scores A (20%), and five score B (all 10%). Given the larger weights of the high-scoring outputs, the overall output score is A.

For each output: supportive narrative for the score, lessons learned and recommendations:

Output 1 (30%): Grant funding provided to make participating MDB loans more concessional: A+

In 2025/26, we will disburse more than initially envisaged (by frontloading our grant disbursement). Even if we do not frontload the full remaining £35m, we will still disburse more, hence a score of A+ (moderately exceed expectation).

The payment forecast for IFFEd has undergone change, with the grant budget from FY26/27 and FY27/28 frontloaded into this financial year in response to the reduction in ODA budgets from 2027. This decision aligns with FCDO’s priority to frontload funds to multilateral institutions, ensuring delivery against the UK’s global priorities and the Sustainable Development Goals.

To date, a total of £60m has been disbursed to IFFEd: $18m (£15m) paid-in capital contribution and £45m in grant contributions (£20m in FY24/25 and £25m in July FY25/26). Some of the remaining £35m, frontloaded from FY26/27 and FY27/28, will be disbursed, subject to early disbursement opportunities. This funding will support the first generation of IFFEd projects.

Lessons and recommendations for output 1: grant disbursement schedule is on track. In frontloading our funds from outer years, additional pressure has been put on ADB and the Secretariat to accelerate the pipeline, which has stretched their capacity to deliver in the early stages of implementation.
Output 2: Higher quality MDB projects through FCDO engagement: B

Two quality projects are likely to be approved by the board in December 2025, falling short of the target of four projects and meaning the output moderately does not meet expectations. We expect that the two outstanding projects will be approved although delayed.

FCDO and IFFEd jointly coordinated a visit to ADB headquarters in Manila to observe project delivery first-hand. This visit provided valuable insights, highlighting the importance of in-person engagement and deepening understanding of operational approaches.

We have engaged extensively with ADB on the standard and priority areas that contributors would like to see addressed in investment cases (projects that are strategic, evidence-based, inclusive, climate responsive, and measure learning). We have made good progress during the Manila visit on aligning our respective understanding. The IFFEd board has endorsed the preliminary investment cases for four projects:

- Strengthening public schools (primary and secondary education) project in Karnataka.
- Accelerating Manpower Investment for Livelihood (TAMIL) in Tamil Nadu (Technical, Vocational Education and Training (TVET)).
- Advancing Quality, Inclusive and Resilient Education Secondary education (ACQUIRE) in the Philippines (secondary education).
- Expanded Social Assistance Project (ESAP) in the Philippines (conditional cash transfer programme to incentivise poor parents to send their children to school). However, ESAP has been postponed following ongoing discussions on the scope of the project and target beneficiaries. It will be re-designed and re-submitted to the IFFEd board as a preliminary investment case in 2027.

The full investment cases will be finalised for ACQUIRE, and Karnataka Schools and submitted for board approval in December 2025. ACQUIRE is expected to increase in size with ADB proposing tripling its value to reach more schools and demonstrate scaling ambitions.

ADB has identified several potential projects for the second phase of IFFEd-funded projects. Preliminary investment cases for these projects are expected to be presented to the board in Q4 of FY25/26.

Lessons and recommendations for output 2: we are establishing a good relationship with ADB and learning to align our respective education expertise. We will continue to work with ADB on project design and implementation so that the process becomes more efficient.

Output 3 (weighting 10%): IFFEd secures additional sovereign donor and/or philanthropic grants and guarantees: A

Output meets expectations: USD $2.1m contribution to paid-in capital secured from the Republic of Korea. In addition, progress has been made in lining up many potential new contributors. Progress is as follows:

- Switzerland Development Corporation (SDC) remains committed to supporting IFFEd’s Swiss Window, indicating that it could contribute CHF 10 million (USD12m) in matching the contribution from Jacobs Foundation already committed.
- The upcoming partnership between the World Bank and IFFEd, which will allow IFFEd to fund projects in Africa, is a key step towards Ireland hopefully joining IFFEd’s donor coalition, as Ireland prioritises projects in Africa.
- Norway continues to show interest in IFFEd and is considering a contribution.
- Germany’s Bundesministerium fuer Wirtschaftliche Zusammenarbeit (BMZ) is exploring the possibility of providing grant funding. It is unable to provide guarantees at this point.
- Several other donors are being lobbied and we are confident that commitments will be made, though securing these may take longer than hoped.
- The IFFEd team has been working with Jacobs Foundation (JF) and made progress in developing a philanthropy guarantee, including joint meetings with highly-rated banks that could function as guarantor to JF. If this takes off, it will mean that IFFEd is mobilising private sector guarantees for education, which would be highly innovative and groundbreaking.

IFFEd agreed with the Credit Rating Agencies Moody’s and S&P on a target of unlocking $3bn by 2030. Currently, IFFEd has unlocked $1bn in affordable lending for education in LMICs. Achieving the $3bn target by 2030 will require an additional $261m in cash contributions (paid-in capital and grants). Given current experience, the IFFEd 2030 target is ambitious and we will discuss with IFFEd whether it is realistic.

Lessons and recommendations for output 3: as discussed, attracting more contributors is challenging. However, this is not only due to shrinking aid budgets and competing priorities. The IFFEd guarantee mechanism is new for many donors and needs to be explained. FCDO, together with the other two founding contributors, will continue to support IFFEd lobbying at the highest level.

Output 4 (weighting 10%): Agree better coherence and collaboration between IFFEd and Global Partnership for Education (GPE) where both are operating in LMICs, and work towards possible long-term co-financing: B

Output moderately does not meet expectation: while discussions are ongoing between GPE and IFFEd on geographic and strategic alignment and co-financing, no joint concept note has been produced yet and progress on co-financing in Bangladesh is on hold pending Bangladeshi elections in Spring 2026. Hence output moderately did not meet expectations.

Lessons and recommendations for output 4: in 2026 IFFEd will continue discussions with GPE and ECW to ensure alignment and coherence globally and at country level, and explore potential for co-financing in Bangladesh.

Output 5 (weighting 10%): IFFEd has education expertise to engage with MDBs on education policy and impact: B

Delays in the completion of the host state act mean that recruitment for the senior education expert is well under way but not yet concluded. The job is advertised staff will be in place by early 2026, hence a score of B: output moderately did not meet expectations. Three staff have been recruited to support financial management. Completion of the host state act will enable permanent onboarding of education advisers.

Lessons and recommendations for output 5: we expect the Swiss host state act to be obtained in early 2026 and education experts to be recruited. We have used our networks to circulate the job description and to encourage strong applicants to apply. We also recommend exploring an FCDO education secondment to IFFEd in Geneva.

Output 6 (weighting 10%): Better quality Asian Development Bank (ADB) projects through FCDO secondment: B

Recruitment rounds for an Education Adviser took place in summer 2025 but candidates did not meet the bar. The secondment will not be recruited in the reporting period of 2025; hence the output moderately did not meet expectations (B). A second recruitment round is taking place in November/December 2025 for a secondment starting in April 2026. This is a particularly challenging time for recruitment given the FCDO 2030 change management process.

Lessons and recommendations for output 6: No specific recommendation.

Output 7 (weighting 10%): Populated results framework focused on learning and marginalised groups: B

IFFEd has completed the results framework as part of its Education Impact Strategy and this was approved by the board, but the framework is yet to be populated, hence the output moderately did not meet expectations (B). Further work is required to develop detailed monitoring, evaluation, and learning systems, which will be done once IFFEd has recruited education experts.

Lessons and recommendations for output 7: the results framework will be fully developed in 2026 once IFFEd has recruited education expertise.
## D: VALUE FOR MONEY

1. IFFED continues to represent excellent value for money under the four ES: economy, effectiveness, efficiency and equity. This is notwithstanding the fact that it is delivering more slowly than expected against its outcome and output targets and scoring a B overall.
2. Economy: IFFEd uses existing MDB systems rather than setting up a new large parallel structure. As such, its operating costs are limited to its trustee functions and those of a small secretariat. Key cost drivers are staff, administrative expenses, and financial management costs. Under business-as-usual assumptions, IFFEd is expected to show positive net income in time for the end of the first replenishment period (2024-2027). This means that following the initial period of seed funding from donors and philanthropists, IFFEd is expected to become self-financing by 2027. This will be through interest earned on paid-in capital and grants provided by donors and philanthropists.
3. Efficiency: IFFEd represents a very efficient use of scarce ODA resources. It makes donor grants go further. $1 of grant financing alongside guarantees can unlock $7 of concessional education financing because IFFEd combines guarantees and grants in a game-changing way. Guarantees allow MDBs to expand investments in countries without having to make large ODA grant commitments as only 15% of the guarantees are paid-in. The grant component of 10% of unlocked finance allows MDBs to lower the cost of financing for countries, making it concessional on terms (around 3% interest rate) that are mid-way between IDA terms (1.4%, highly concessional for LICs) and IBRD terms (4.5%, not concessional). IFFEd will not provide concessional loans to countries with debt sustainability problems. The unlocking of seven times the amount of donor cash assumes that guarantees provided by IFFEd are multiplied by the MDBs by a factor of four.
4. Effectiveness: given its high leverage of 7, with a start-up guarantee amount of $270m (from the three founding donors), of which only $40m is paid-in cash) IFFEd has been effective in unlocking $1bn of new additional and affordable education finance for LMICs.
5. Effectiveness: in addition to unlocking new additional education finance with a very high leverage, IFFEd is also working on the quality and impact of projects, with a focus on using the best evidence of what works and focusing on those most in need. It will take some time to develop a quality pipeline. In 2028 FCDO will consider an evaluation to take stock and lesson learning. The IFFEd secretariat is recruiting a team of three education specialists. FCDO is seconding an education advisor to the Asian Development Bank to support programme quality and delivery. IFFED will also benefit and contribute to the research and knowledge that exists as public goods across the global education ecosystem, including on the evidence of what works for learning, data, and system strengthening.
6. Equity: the UK, together with partner donors Canada and Sweden, has ensured that the IFFEd Framework Agreement has a strong focus on marginalised groups. For IFFEd to issue a guarantee to an MDB, the MDB must submit investment cases that demonstrate a strong focus on marginalised groups.

E: RISK

Overview of risk management

The risk rating of the programme has been increased from moderate to high reflecting the new global context of constrained ODA resources with competing priorities and the fact that the project is moving to implementation with a limited pipeline and capacity constraints. In the last annual review we identified three risks:

Insufficient donor buy-in: this risk has materialised. Getting additional donor contributions on top of the three founding donors (UK, Canada, Sweden) is challenging, with only one country (Korea) to date making a commitment. Shrinking aid budgets and increased competition for ODA have made IFFEd fundraising slow. Mitigation: FCDO will continue to support IFFEd in onboarding more donors. IFFEd is also hiring fundraising expertise to expand lobbying capacity. FCDO will stand ready to support those efforts at the highest level, including by Ministers and Gordon Brown, and the UN Special Envoy for Global Education.

Insufficient interest from LMIC governments: this risk has not materialised. Several countries are interested in borrowing for education against the IFFEd guarantee. These countries include the Philippines, India, Bangladesh, Papua New Guinea, Mongolia and Pakistan. Mitigation: no mitigation needed.

IFFEd-supported projects do not achieve their intended impact: this risk has not materialised. The existing pipeline of four projects with the ADB has a clear focus on disadvantaged groups. Mitigation: no mitigation needed. We will continue to work with ADB to ensure that projects focus on disadvantaged groups.

In the reporting period for this annual review several new risks were added to the risk framework, some of which materialised:

Credit risk downgrade. This risk did not materialise. IFFEd Retained it's Aaa rating with Moody’s and AA+ rating with S&P, reflecting good financial governance.

Recruitment delays. This risk materialised. No education experts could be recruited until the Swiss Host State Act is obtained for IFFEd. This has been delayed due to competing pressures in the Swiss government. It is important for IFFEd to have education expertise to engage on project quality, results measurement and engaging in the global education architecture. Mitigation: no mitigation required. The state act has been delayed and is expected to be obtained at the beginning of 2026. IFFEd has now commenced recruitment in anticipation of the Host State Act being obtained shortly..

Misalignment with other education instruments. This is risk did not materialise. IFFEd is in dialogue with the Global Partnership for Education (GPE) and Education Cannot Wait (ECW) to ensure geographic and thematic alignment. Mitigation: IFFEd will continue this dialogue to ensure ongoing alignment and is exploring co-financing opportunities with these other organisations.

Slow onboarding of the World Bank. This risk materialised. Onboarding of the World Bank is important to expand IFFEd’s project pipeline and geographic reach, especially in Africa. Onboarding is happening at the end of 2025 but has been slow. As a result, identification of IFFEd World Bank projects has been delayed into 2026. Mitigation: to ensure that projects are approved in the first half of 2026, IFFEd will engage closely with the World Bank.

Insufficient understanding by ADB of donors’ project requirements. This risk materialised. It has a taken a long time for ADB to understand donor project requirements (projects that are strategic, evidence-based, inclusive, climate responsive, and measuring learning). However, alignment between IFFEd donors and ADB was achieved at the end of 2025. Mitigation: FCDO will continue to engage with ADB in 2026 on project design and implementation, including through an FCDO education adviser secondment to ADB in Manila.

Next year we will monitor the following risks:

Insufficient donor buy-in: this will continue to be a risk in 2026. Mitigation: FCDO will provide lobbying support at the highest level to attract two additional contributors.

IFFEd-supported projects do not achieve their intended impact: while this risk did not materialise in 2025, we will continue to monitor it in 2026. There is now good understanding between donor and ADB project expectations. Mitigation: FCDO will continue to engage with ADB, including through mutual visits in Manila, London and project countries, and the FCDO secondment to ADB in Manila.

Credit risk downgrade. IFFEd needs to attract more donors to demonstrate growth and political support beyond its current base of three founding donors. Mitigation: founding donors will provide high-level political support to attract two additional donors.

Misalignment with other education instruments. Mitigation: dialogue between IFFEd, GPE and ECW will continue to ensure alignment and complementarity. We will try to identify one co-financing opportunity.

World Bank project pipeline: Once the bank has joined IFFEd by December 2025, we will identify first IFFEd World Bank projects, in particular in Africa. Mitigation: FCDO will prioritise discussions with the World Bank to identify at least two initial projects in 2026.

FCDO staffing gap: with staff changes under the FCDO 2030 reform agenda, there is a risk of the FCDO team leading on IFFEd delivery being under-resourced. Mitigation: FCDO management to consider appropriate resourcing of the IFFEd team in 2026.

Recommendation: IFFEd should add to each quarterly board meeting an agenda item on risk and mitigation, so that risks and mitigation can be better managed collectively between IFFEd and contributors.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

FCDO manages this programme in line with the Programme Operating Framework (PrOF), ensuring appropriate management of budget, risk management and tracking of delivery. The FCDO programme team is made up of a Grade 6 Senior Responsible Officer, Grade 7 Programme Responsible Officer and Economist and HEO Programme Manager. The programme team works closely with the IFFEd secretariat to ensure smooth programme delivery on both sides of the programme. In the past few months, we have been able to allocate education advisory capacity to IFFEd. This needs to continue as the pipeline develops. Going forward and subject to workforce constraints, we would recommend a full time EA be allocated to IFFEd by GED.

The IFFEd secretariat is made up of a team of finance experts and economists with significant MDB and programme management experience. As mentioned previously in this review, the secretariat will be increasing its in-house expertise in education with the planned recruitment of several experts in the sector.

Financial management remains strong, with regular oversight processes in place.

G: MONITORING, EVIDENCE AND LEARNING (MEL)

IFFEd is still in the early stages of delivery, having only become operational in 2024. Endorsed projects have not yet entered the implementation phase, so there is currently no evidence available to assess IFFEd’s impact on education outcomes. The priority to date has been establishing monitoring, evaluation, and learning (MEL) systems, which will be adopted as projects transition from design to implementation.

IFFEd’s MEL systems are being strengthened through the Education Impact Strategy, which outlines IFFEd’s Theory of Change and results framework, and identifies the indicators that will be used to measure progress.

Further work is ongoing to develop robust MEL processes in collaboration with participating MDBs. The Asian Development Bank (ADB) is currently reviewing its evaluation strategy, which is expected to contribute to these efforts. Additionally, recruiting education technical experts will enhance the programme’s capacity to generate evidence and integrate learning throughout the project cycle.

Finally, the FCDO logical framework for IFFEd will be strengthened and refined in the coming year. This will focus on unpacking impacts in relation to SDG 4, in line with the type of projects that are implemented and MDBs’ MEL plans. In addition, all indicators will be reviewed to ensure they are specific and can be measured consistently over time.
Date of last narrative financial report		Date of last audited annual statement