## Annual Review Template

Title: Samartha (“Empowered”): Enhancing Gender & Human Development Outcomes through Systems Strengthening
Programme Value £ (full life): £ 38.8m		Review date: December 2025
Programme Code: 301596	AMP start date: December 7, 2024	AMP end date: March 31, 2030.

Summary of Programme Performance

Year	2023/24	2024/25
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004936.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006213.xlsx

## A. SUMMARY AND OVERVIEW

Description of programme
Enhancing Gender and Human Development Outcomes through System Strengthening (Samartha) is a seven-year bilateral programme of the British Embassy Kathmandu (BEK), designed to strengthen Nepal’s federal systems for delivering responsive and resilient social services, particularly in health and education. The programme focuses on improving intergovernmental planning, budgeting, and coordination to enhance service quality, promote inclusive citizen participation, and strengthen preparedness for emergencies. By targeting systemic reforms and inclusive service delivery, Samartha aims to advance gender equality and human development outcomes, contributing to Nepal’s long-term goal of becoming a stable and prosperous middle-income country.
Samartha’s Business Case (BC) was approved for a total amount of £38.8 million, and it’s governed by a memorandum of Understanding (MoU) singed between Government of Nepal and the BEK on 28 August 2024. The programme original model combines technical assistance, targeted financial aid, a Breakthrough Initiatives and Innovation Fund (BTII), an independent oversight function and BEK-led strategic influencing and convening. Its geographic scope is limited to Madhesh and Lumbini provinces, with the original ambition of supporting 50–100 local governments, together with bespoke policy and technical support to federal and provincial governments. Learning is embedded as a cross-cutting outcome, with adaptive management and evidence generation central to delivery.
Alongside the GoN, Samartha is delivered via two main implementing partners: Adam Smith International (ASI), which leads technical assistance to strengthen social services planning, delivery and resilience across government; and Ecorys, which manages public financial management (PFM) technical assistance, fiduciary risk assessment, independent programme oversight, and the BTII fund. Both partnerships began in January 2025, so this is a light-touch Annual Review (AR) that mostly focuses on learning from the programme’s inception phase.

Local Context
During the reporting period, Nepal faced several destabilising events that significantly shaped the operating context for the Samartha programme. The year was marked by persistent fiscal and governance challenges, including reduced intergovernmental transfers and growing audit irregularities at the local level, which affected service delivery and planning capacity.
In September 2025, the so-call “Gen Z uprising” brought long-standing frustrations over corruption and nepotism to the fore, sparking a national crisis. The subsequent resignation of the Prime Minister, damage to federal institutions, and destruction of government infrastructure nation-wide, including at the subnational level, severely affected public service delivery and prompted the relocation of several ministries. An interim government now faces the dual challenge of reconstruction and preparing for new federal elections, scheduled for March 2026, all while managing public expectations and fiscal strain.
Despite these uncertainties, and indeed linked to sources of public distrust, the prevailing demand for governance reform and accountability—driven by youth mobilisation—aligns closely with Samartha’s objectives around good social sectors’ governance, inclusion and resilience. The programme’s embedded technical assistance and cluster-based approach position it to help local governments rebuild responsive systems, with a focus on diagnostics, stakeholder engagement and tailored interventions that tackle key systems bottlenecks to improve efficiencies, reach and relevance to citizens when it comes to the delivery of basic services.
Confirming the Nepal’s vulnerability to a range of crises, a cholera outbreak in Madhesh Province during August 2025, fuelled by contaminated water sources amidst severe drought, further strained local health systems and highlighted the urgent need for improved water, sanitation and emergency preparedness—areas central to Samartha’s resilience agenda.
Looking ahead, it is likely that Nepal’s local context will continue to present unpredictable but manageable risks, provided effective mitigation measures are in place (see Section E). At the same time, the strong public resonance of issues such as accountability, inclusion, and climate-related challenges creates opportunities for Samartha to advance its broader objectives, as well as BEK’s portfolio-level priorities, supporting systemic reforms that respond to the evolving demands of Nepalese society.

UK and International Context
Nepal’s development landscape has been reshaped by shifting donor priorities and declining global aid flows. The sudden closure of 34 USAID-funded programmes in early 2025 following its dissolution disrupted essential initiatives in health, education, public financial management, disaster resilience, and social inclusion, resulting in medicine shortages, stalled teacher training, and impact to youth employment and NGO operations. The USAID funding cuts also constrained partnerships and joint programming, reducing resources available for sectoral reform. For Samartha, this intensifies pressure to deliver with fewer financial levers, increasing reliance on strategic influencing, innovation, and technical support.
Shortly after, the UK’s reduction of Official Development Assistance (ODA) from 0.5% to 0.3% of Gross National Income (GNI) by 2027 led to a 15% budget cut for FCDO’s bilateral aid in Nepal for FY 2025/26. Several programmes were impacted, including Samartha, which faced major reductions in TA budget and a decision to exit FA (immediately in health, progressively over two years in education). This also implied a reduction in scope in Samartha’s PFM-focused TA, eliminating the requirements for bespoke fiduciary risk management related to FA. Finally, a planned accountable grant nearing signature to support social accountability and citizens’ engagement and voice in social sectors was paused and then permanently abandoned due to uncertainties about future financing.
Despite these global aid shifts, Samartha remains a core element within BEK’s evolving portfolio, positioned to contribute to economic transformation, human capital development, and resilience. Crucially, Samartha is designed with adaptive mechanisms to respond to the changing development landscape, ensuring its continued relevance and effectiveness even as financial levers are reduced.

Summary supporting narrative for the overall score in this review
The programme has been awarded an ‘A’ score in this Annual Review, reflecting robust progress during its inception phase despite considerable contextual challenges—including political instability, changes to ODA, fiscal constraints and programme management issues (see Section F). Samartha successfully transitioned from design to implementation readiness, delivering key quality inception and early implementation outputs, including an adapted theory of action, diagnostic studies, piloting technical assistance in two local governments, supporting major planning exercises in education and starting a few initiatives under the BTII fund. These efforts have established a solid foundation for full-scale implementation. The programme demonstrated agility in responding to disruptions, maintained alignment with BEK’s portfolio priorities, and positioned itself as a critical enabler of system reform and resilience within Nepal’s social sectors.

Major lessons and recommendations for the year ahead
Nepal’s political landscape is experiencing a generational transformation, with the Gen Z movement bringing longstanding demands for transparency, accountability and inclusive governance onto a more visible political playground. These dynamics are set to influence post-election priorities, placing greater emphasis on equity, accountability, climate resilience and digital transformation (linked to the role of contemporary means of communication). While this environment presents opportunities for progressive reforms, it also introduces volatility in leadership and resources allocation, which can disrupt local planning cycles.
To remain effective, Samartha must adopt a deliberately adaptive approach that strengthens local governance systems over the long term, while ensuring flexibility in programme delivery. This requires embedding rapid political economy analysis (PEA) into programme planning, fostering robust institutional partnerships at the bureaucratic level to safeguard continuity, and integrating innovation to enhance evidence-based decision-making—particularly through the increased use of digital tools and the cultivation of a data-driven culture. Whether via its TA functions or through BEK’s own programme team, Samartha should also position itself as a neutral facilitator championing GEDSI and resilience by supporting local governments to institutionalise systems for quality, inclusive services, and by creating space for civil society engagement to harness youth energy and innovation for inclusive development. These approaches must be formalised by the end of the current UK fiscal year (31 March 2026).
Internal migration and rapid urbanisation, combined with slow progress in Nepal’s federalisation agenda, have deepened inequities in Nepal’s social sectors, impacting both urban and rural areas. Policies have lagged behind demographic shifts, resulting in service gaps and heightened vulnerabilities, especially in Lumbini and Madhesh. Challenges such as mental health issues, changing patterns of disease and exclusion are prevalent in areas marked by concentrated poverty and high mobility. Diagnostics highlight new education barriers—particularly for girls—that tie directly to labour market prospects, with exclusion now shaped by traditional norms alongside evolving migration and demographic trends.
Both rural and urban settings in Nepal are marked by tensions and vulnerabilities arising from demographic transitions, persistent social norms, and uneven access to services. Addressing these requires Samartha to adopt a balanced, GEDSI-informed approach that supports LGs in adopting responsive strategies for all marginalised populations, ensuring comprehensive service delivery across health, education and cross-cutting areas such as , nutrition, WASH and social protection, recognising the interconnected needs of communities in rapidly changing environments.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
Samartha’s original Theory of change projects the acceleration Nepal’s transition to inclusive, resilient, and locally owned social sectors by addressing governance, equity, and sustainability constraints. The logic assumes that if the GoN is supported to streamline federal coherence, improve fiscal arrangements, strengthen sub-national delivery systems, and foster civil society accountability, then basic social services will become better resourced and functional, improving human development indicators, with enhanced human capital acting as one of the key drivers behind Nepal’s shift to middle-income status. To deliver this, the programme focuses on four intermediate outcome area:
1. Enhanced governance at federal, provincial and local levels enables social services to fulfil constitutional mandates through more effective planning, budgeting and spending.
2. Access to quality services broadens for excluded and marginalised groups in selected provinces and localities, by putting sectoral plans into action and embedding gender equality and social inclusion in local delivery.
3. Demand and accountability for social services grow, as citizens become more empowered and informed to challenge decision-makers and claim their basic rights.
4. Planning and preparedness for emergencies, including public health crises, are strengthened, improving disaster response and ensuring continuity of social services.
As a deliberately adaptive programme, Samartha’s ToC has been operationalised into a practical, component-level ToC for ASI to use for the delivery of their TA interventions, organised into three mutually reinforcing workstreams that align with the original design:
1. Governance and Policy Reform: Enhancing data use, prioritising social budgeting, and strengthening delivery systems.
2. Quality and Inclusive Access: Integrating GEDSI principles, improving multi-sectoral service delivery, and adopting quality standards.
3. Preparedness: Supporting local governments to develop business continuity plans for emergencies.
Demand-side and social accountability interventions are not included for this reporting period in the operational ToC, given the suspension of the AG meant to drive them, and therefore not reflected in the intervention-level ToC. However, BEK plans to integrate this additional workstream (linked to intermediate outcome area 3 of Samartha’s BC) in future workplans, once the ODA allocations are clarified by the FCDO (See Management Section F for details).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
This reporting period encompassed the inception phase and initial implementation steps. A process-focused results framework was developed to outline plausible pathways to outcomes, with progress tracked accordingly. Data shows outputs were delivered as planned, establishing a solid foundation for future impact. However, it remains too early to determine if Samartha is definitively on track to achieve its intended outcomes and impact.
Despite ODA reductions, early efforts were directed at building a robust programme foundation—developing strategies, key documents and piloting approaches. FA was pledged only to the education sector during this phase, supporting equity results-based financing towards the School Education Sector Plan (SESP). Moving forward, full implementation is planned to begin in a phased approach, starting in around 16 local governments across Lumbini and Madhesh. As mentioned, with BEK portfolio priorities and approaches having shifted, FA will no longer feature beyond UK FY2026/27, with the emphasis on a modern partnership framed around mutual priorities and facilitated through demand-led technical assistance.
Figure 1. Samartha ToC as per Business Case
Figure 2. Samartha's Revised ToA

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
In this reporting period, BEK responded to the reduced ODA allocation by resetting its portfolio, refining thematic priorities and geographic focus for greater impact and alignment with UK’s priorities. The portfolio reset put enhanced focus on economic transformation, improved human capital and enhanced climate resilience—while recentring the geographical scope to Madhesh, Lumbini and the Kathmandu Valley. This strategic shift amplifies Samartha’s role in advancing the human capital agenda and resilience outcomes, enhancing its relevance within the broader BEK’s updated portfolio and FCDO’s priorities.

Based on expected outcomes, the ToC and emerging evidence from inception, there is sufficient justification for the programme to continue. However, delivery approaches may need to be adjusted to maintain momentum and optimise results in resource-constrained context.

## C. DETAILED RESULTS APPRAISAL

Samartha operates as an adaptive programme and therefore adopts an adaptive annual review approach. This report evaluates results across four key performance areas: (1) Delivery, (2) Contribution to Meaningful Change, (3) Actionable Learning, and (4) Fitness for Purpose.

The proposed scores for this annual review are as follows:

Performance Area	Weighting	Score
Delivery	40%	A
Actionable learning	25%	A+
Contribution to Meaningful Change	25%	Not scored
Fitness for Purpose	10%	Not scored

C1 DELIVERY

As part of the delivery during this reporting period, five primary output areas were established during the inception period, each with pre-agreed process indicators and assigned sub-weighting within the C1 performance area (see Annex A for details):
1. Inception deliverables for TA – 40% weighting
2. Inception deliverables for design of Financial Technical Assistance and Evaluation (FTAE) function and BTII interventions – 20% weighting
3. SESP Joint Financing Agreement – 10% weighting
4. Technical Assistance pilots in Lumbini and Madhesh provinces – 15% weighting
5. Joint reviews of the Health and Education sectors – 15% weighting
Output 1: Inception Deliverables for TA (40%)
This output scored A. As main TA suppliers, ASI have made good progress in establishing and operationalising the Samartha TA component. During the inception phase, the programme completed all core deliverables, including setting up the Kathmandu office, mobilising the core team and embedding technical experts at the federal level and in two pilot LGs (Kamala Municipality in Madhesh and Rapti Sonari Rural Municipality in Lumbini). It developed key strategic documents such as the Theory of Change, Theory of Action, provisional draft of an adaptive results framework, Value for Money (VfM) strategy and risk register, alongside diagnostic studies and political economy analyses at federal, provincial and local levels. These informed the selection of 16 local governments where the design of tailored interventions and early implementation will phase in during the remainder of the first year of contract.
Implementation readiness was strengthened through the creation of tools and methodologies, including the Strategic Programming and Partnership Framework, Proxy Means Testing toolkit for scholarships, a Provider Behaviour Change Communication framework for respectful maternal care (but which could be applied more broadly to promote a client-centred approach to social service delivery), and a pre-feasibility study on gender-based violence response. Pilots tested approaches for evidence-based planning, maternal health audits, GEDSI sensitisation and disaster preparedness, generating insights on opportunities and bottlenecks for the scale-up of successful interventions.
Despite significant political disruptions in late September 2025, ASI demonstrated agility by conducting rapid situational assessments and adjusting timelines accordingly. Staffing changes, including within the core team, created short-term disruption, but were managed effectively by ASI to maintain continuity and ensure timely achievement of quality deliverables, and ASI have come out of this period with a stronger team. The team actively engaged in policy dialogues, supported the Ministry of Health and Population (MoHP) and the Ministry of Education, Science and Technology (MoEST) in planning and budgeting processes at both national and subnational level, and coordinated with other BEK programmes to ensure strategic coherence. Overall, ASI has successfully transitioned from design to implementation readiness.

Output 2: Inception Deliverables for FTAE function and BTII Interventions (20%)
This output rated B. The performance around this output was impacted by a dramatic change in scope compared to the original ToR, both related to short-term ODA reduction, but more importantly the shift away from FA as part of the portfolio reset. This implied that one of the core areas of the FTAE ToR, focusing on extensive fiduciary risk management on behalf of the UK, was dropped – leaving only a smaller, outward-facing PFM analytical function to leverage Ecorys’ team specific areas of expertise. Moreover, with the prospective closure of FA and the paused onboarding of an AG implementing partner for the social accountability component, the coherence function that Ecorys was supposed to play was also paused indefinitely. These changes have massively reduced the ambition of this contract, resulting in this performance sub-area showing less satisfactory results than originally anticipated. This does not represent an appraisal of Ecorys’ performance (suppliers’ performance is discussed in section F), but it reflects a reduction in scope of this component.
Adapting to these changes, during the inception phase Ecorys focused on established the operational foundation for PFM analytical work and for the management of BTII grants, As a part of the FTAE deliverables, key analyses were completed on fiscal federalism, public financial management reforms, governance structures in health and education, fiduciary risks at local levels, and budget trends across tiers of government.
The BTII fund management approach was operationalized through the Grant Management Manual, which establishes governance structures, operational procedures and financial controls for grant management, disbursement, monitoring and compliance. To date, partnership agreements have been signed with FHI 360, the British Council, Inclusive Development Partners (Alice International Inc.), and local organisations such as the NGO Karkhana Samuha and the consultancy firm Herd International.

Grantee
FHI360	Piloting clean air initiatives at the local level
British Council	Appraising the role of AI in local education planning and basic education
Alice International, Inc. / Inclusive Development Partners	Youth-led problem solving for inclusive education planning and employing youth participatory action research for the same.
Karkhana	Piloting digital education and upskilling initiatives for marginalized girls in Madhesh
Herd International	Policy and legislative work on health taxes and human resources for health + burden of disease study

Despite these achievements, the operationalization of BTII as an effective and adaptive tool took longer than anticipated, primarily due to the extended time required to onboard implementing partners and approaches to due diligence and financing that appear too risk-averse relative to the purpose of the grants. This will require a review to ensure that in the future this instrument is fit for swift granting processes with proportionate approaches to fiduciary risk management.

Output 3: SESP Joint Financing Agreement (10%)
This output is scored A. Samartha successfully positioned BEK as a key contributor to sector-wide financing and governance through the SESP, with FCDO becoming the newest party of the Joint Financing Agreement (JFA). BEK, through Samartha, has committed £1 million in financial aid for each of Nepali FYs 24/25 and 25/26, based Disbursement Linked Indicators (DLIs) linked to strengthening the equity index across 150 local governments (LGs).
Besides joining the JFA, BEK was nominated to hold co-chair responsibilities for the Joint Financing Partners’ group, Global Partnership for Education (GPE), and the Local Education Development Partner Group (LEDPG). Since taking on this role, BEK has coordinated and co-chaired the Mid-Term Review Mission of the SESP and the Joint Review Mission (JRM), both of which were concluded in November. BEK hosted 4 LEDPG meetings in its premises and will be coordinating and co-hosting the 4-day GPE mission in December. Samartha TA through ASI supported the development of the Provincial Programme Implementation Procedures (PIPs) and Local Education Plans’ (LEPs) appraisals in Lumbini and Madhesh, as well as providing technical expertise to the government in Gandaki and Bagmati provinces - reinforcing demand-driven and evidence-based planning. The expert appraisal process ensured the integration of climate resilience and GEDSI indicators, along with appropriate budgeting, through the LEP appraisal framework. Despite minor delays caused by political unrest, activities were delivered efficiently and remained aligned with sector priorities.

Output 4: Technical Assistance Pilots in Lumbini and Madhesh Provinces (15%)
This output is assessed “A”. The short pilots effectively tested and validated the TA approach, confirming its adaptability and relevance. With targeted adjustments informed by pilot findings (see C2), the approach now provides a practical, evidence-based toolkit for developing strategies tailored to local needs and conditions, supporting adaptive scale-up across different contexts.
The TA pilots tested systems-strengthening models in two LGs: Kamala Municipality in Madhesh and Rapti Sonari Rural Municipality in Lumbini. These pilots explored ways to improve governance, service quality and resilience by employing participatory methods and “Bridge the Gap” workshops to identify factors enabling LGs to adopt evidence-based, locally owned plans. Key interventions included equity-based micro-planning, budget absorption analysis, maternal health bottleneck assessments, provider behaviour audits, and the joint development of guidelines for enrolling Out-of-School Children and awarding targeted scholarships.
Through these activities, the pilots highlighted systemic challenges such as inadequate emergency preparedness, persistent inequities and disconnect between budgets and actual needs. As a result, they produced validated frameworks and practical guidelines for inclusive planning, quality improvement, and resilience building. Strategic lessons underscored the necessity of functional governance, closing the gap between data and action, integrating GEDSI principles and embedding resilience within local systems. Notably, Rapti Sonari succeeded in integrating actions into its budget due to an aligned political environment that prioritised human development, whereas Kamala’s political constraints limited progress and consensus-building.
Output 5: Joint Reviews of the Health Sector (15%)
This output is graded “A” as activities were delivered on time and to a high standard. BEK played a leadership role in sectoral reviews, reinforcing health system efficiency, equity, accountability and evidence-based decision-making. In health, BEK chaired the development partners’ forum and supported preparations for the National Joint Annual Review (NJAR) of the health sector for Nepali Fiscal Year 2024/25, including agenda setting and evidence synthesis, and strategic dialogue with MoHP and provincial authorities, with support from ASI.
The NJAR showcased achievements like early rubella elimination, 94% HPV vaccine coverage, swift outbreak responses, and more basic hospitals. However, challenges persist, including high maternal and neonatal mortality, limited services to manage and prevent non-communicable diseases (NCDs), suicide prevention, and financial protection, with over half of total health costs paid out-of-pocket. BEK helped set strategic priorities to boost efficiency, improve budget absorption, reform health insurance and modernise procurement and approaches to partnership. Strategic emphasis was placed on tackling NCDs, mental health and emerging challenges such as antimicrobial resistance, while empowering LGs and using digital health to enhance efficiency, governance and accountability.
BEK played a pivotal role in promoting alignment of partners’ technical assistance with Nepal’s Health Sector Strategic Plan (2023–2030). Outcomes from Joint Consultative Meetings in November supported harmonised, less fragmented donors’ support to the health sector. In Madhesh and Lumbini, Samartha has stated testing approaches to strengthen intergovernmental health systems’ governance and improve care quality. While statements point to appetite for relevant reforms, bottlenecks and perverse incentives remain significant: BEK remains committed to driving evidence-based reforms, fostering equity-focused initiatives and strengthening resilient health systems, as Nepal moves towards LDC graduation and faces declining global health funding. This commitment underpins its ongoing sectoral leadership, with Samartha becoming a tool to create the adequate influencing space.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
All recommendations from the previous annual review have been successfully implemented, apart from one: “Samartha should provide support, particularly through its planned Accountable Grant under Intermediate Outcome Area 3, for innovative interventions and modalities aimed at expanding civic space and reorienting citizens’ actions toward locally relevant demands for basic social services. This includes facilitating networks, promoting local deliberation, and fostering engagement between local governments, the public, and other relevant stakeholders.” Implementation of this recommendation was paused due to uncertainties on future funding linked to the reductions in ODA allocations and the associated portfolio reset exercise within BEK. Nevertheless, it is anticipated that this outcome area will ultimately be incorporated into the main contract, provided that future ODA allocations to BEK make it financially viable within the wider portfolio.

The following key lessons and recommendations have been identified through this review process:

Local governance functionality is essential for effective TA: Experience from the pilot phase demonstrated that the effectiveness of TA is closely linked to the, readiness, functionality and inclusivity of local governance systems. In Rapti Sonari, robust governance structures enabled pilot TA interventions to be absorbed and translated into actionable, budgeted plans. Conversely, in Kamala Municipality, political gridlock and weak institutions significantly limited the impact of TA, underscoring that technical support alone cannot overcome systemic governance barriers.
Based on this lesson, Samartha TA (through ASI) should immediately introduce Governance Readiness Assessments as a prerequisite for comprehensive TA support (followed by routine appraisals). This will allow classification of LGs by operational capacity and political stability, enabling tailored support, prioritisation of high-readiness contexts, and targeted risk mitigation plans for politically challenging environments. Routine appraisal of governance readiness should be institutionalised to ensure resources are allocated efficiently and impact is maximised.

Bridging the Gap Between Data and Action: The review identified a persistent gap between the availability of data (e.g., HMIS, EMIS) and its practical use in planning and budgeting at the local level. Many local governments lack the capacity or incentives to analyse and apply evidence, resulting in misaligned budgets and underutilised grants.
While being careful as not to create substitution or dependency, Samartha TA should ensure a dedicated focus on providing hands-on support to help local actors translate evidence into actionable plans. This involves building a data-oriented culture, strengthening capacity for data interpretation, embedding evidence-based decision-making into planning cycles. This may also include the introduction of practical, contextually meaningful tools and incentives for performance-linked budgeting to ensure resources respond to documented needs. These efforts should leverage plans for testing flexible, outcome-based granting models in the education and health happening at the national level, with the support of the FTAE component.

GEDSI Integration Remains Superficial at Local Level: Insights from the inception reports and diagnostics studies confirm despite robust that policy and legal frameworks for GEDSI, practical implementation at the local level remains patchy and often superficial. Marginalised groups, such as Musahar women, Dalits, and people with disabilities, continue to encounter substantial barriers to accessing education, health and other essential services, with obstacles are both physical (infrastructure gaps) and institutional (gaps in data, awareness and agency).
Samartha should evolve its approach to fully integrate GEDSI across all interventions, ensuring it is a core principle of system strengthening. This could include strengthening the capacity of local sectoral committees to use disaggregated data, operationalising existing GEDSI policies through targeted action learning, institutionalising regular GEDSI audits, and enhancing the participation of marginalised groups in planning and monitoring processes. ASI should test approaches from the next programme year using the next planning cycle as entry point (March-June 2026).

Disaster Preparedness and Business Continuity Planning are Fragmented: Both Kamala and Rapti Sonari lack sectoral Business Continuity Plans (BCPs), and more broadly their disaster preparedness efforts appear fragmented, incoherent and focused on reactive practices. As illustrative examples, health facilities were not equipped to handle gender-based violence (GBV) cases during emergencies, and schools lacked reopening protocols for flood-prone areas. Broadly, system-wide fragility undermines resilience and risks disproportionately affecting vulnerable populations during crises.
Samartha TA must support LGs in developing and testing cross-sectoral BCPs that cover basic social services delivery during crises (by June 2026), with a focus on health and education and specific provisions for multi-hazard preparedness and response. These BCPs should be linked to practical table-top exercises that LGs can integrate within a culture of preparedness.

Urbanisation and Migration Create New Service Delivery Challenges: Nepal’s rapid urbanisation and increasing internal migration are reshaping the demands on LGs, with new pressures on service delivery. The review finds that existing policies and planning frameworks have not fully adapted to these demographic shifts, resulting in service gaps in urban areas even as populations continue to be left behind in rural communities. Without targeted strategies, there is a risk that vulnerable groups—especially those in informal settlements or with high mobility—will continue to face barriers in accessing essential services.
From the next contract year (April 2026), Samartha should support LGs to develop and pilot interventions that are responsive to the realities of urban growth and migration. This includes strengthening outreach in urban health and education, integrating the needs of mobile populations into local planning, and promoting the use of disaggregated data to inform resource allocation. Facilitating collaboration and peer learning between municipalities can also help share effective approaches for managing urbanisation, rural-urban continuum of services (especially in health) and migration-related issues.

Cross-Sectoral Gaps in Drivers of Human Development: Despite Samartha’s broad mandate to strengthen broader social sectors, the review finds that critical cross-sectoral areas such as nutrition, WASH, and climate resilience have not received sufficient diagnostic analysis. These domains are key drivers of human development outcomes.
To address this gap, Samartha should prioritise dedicated diagnostics and PEA around on key determinants of human development, ensuring these cross-cutting issues are systematically understood and addressed (by March 2026). Building on this knowledge, the programme should support pragmatic, multisectoral interventions that leverage the integrated structures of smaller subnational government units, encouraging collaboration across sectors to address the interconnected nature of these challenges. This will help ensure that future programming is capable of delivering more holistic, sustainable improvements in human development outcomes.

Operational Bottlenecks in Grant Management: Operationalising BTII grants during this reporting period took longer than expected due to delays in onboarding implementing partners, largely caused by the complexity of processes of respective organisations as well as the process outlined in the Grant Management Manual (GMM).
Ecorys (FTAE) should document the challenges faced during this phase and review the GMM to identify areas for simplification and improvement. If necessary, the manual should be revised to streamline procedures and accelerate future grant management cycles, ensuring proportionate risk management and timely and efficient implementation of BTII initiatives.

C.2 ACTIONABLE LEARNING

Samartha is designed as a flexible, systems-strengthening programme, with learning at its core. In this reporting period, the programme carried out a range of assessments, including Political Economy Analysis (PEA), provincial and local diagnostics and a GEDSI analysis. These activities have generated valuable insights. This section brings together those findings and sets out practical steps to ensure that learning leads to adaptive, politically informed actions in future programming. The quality of learning outputs (reports, diagnostics, PEAs and pilot analyses) is considered excellent, reflected in the proposed score under this area (A+).

Embedding Continuous, Politically Informed Learning
One of the most significant insights emerging from the review is the confirmation of original Business Case’s assumptions that governance realities such as executive dominance, elite capture and informal patronage shape service delivery outcomes more than technical gaps. This highlights the importance of Samartha institutionalising politically informed learning as a fundamental part of its approach. Rather than focusing solely on technical solutions or individual skills, the programme must address systemic barriers to rational decision-making, ensuring that transformational technical assistance tackles the root causes of inefficiency and inequity.
To ensure that interventions remain contextually relevant and politically feasible, the programme should institute annual PEA cycles alongside ongoing, applied micro-PEA. Maintaining a live risk-opportunity log will help track how political dynamics evolve over time. The insights gathered through these processes must be systematically incorporated into quarterly strategic reviews and annual workplans, supporting “Stop-Go-Adapt” decision-making. This approach will help reduce implementation risks by grounding strategies in the realities of governance and allowing for timely adaptation (programmatic and geographical) as circumstances change.

Moving Beyond Compliance to Evidence-Based Planning
Local planning tools, such as School Improvement Plans (SIPs) and sectoral plans, are often treated as compliance exercises disconnected from budgeting and decision-making. This limits their potential to drive equity-focused resource allocation. Samartha can address this by using HMIS, IEMIS and NWASH data, along with programme diagnostics, to demonstrate the value of evidence-driven planning.
LGs should be supported through structured learning forums that help them understand and interpret disaggregated data. These forums should also guide them in embedding GEDSI considerations into their annual plans and budgets. By doing so, planning will become a meaningful strategy for inclusive development, rather than just a procedural requirement.

Prioritising Learning on Inclusion and Equity
The review highlights that GEDSI strategies remain symbolic in most local governments, with minimal budgets and weak institutionalisation. However, positive outliers such as functional Parent-Teacher Associations (PTAs) and inclusive school models prove that context-sensitive approaches can succeed.
Samartha should document and disseminate success stories, such as the Janata Model School and Girls’ Inclusive Education Network (GIEN) initiatives, through peer-learning platforms at the political level, including financing and sustainability implications. These examples can serve as practical templates for replication, fostering a culture of inclusive governance and service delivery across diverse contexts.

Strengthening Feedback Loops Between Local Evidence and Policy
Federal policies and conditional grants often fail to reflect local realities, creating rigidities that undermine service delivery. These constraints are further compounded by top-down fiscal transfer mechanisms, which frequently restrict local governments’ ability to allocate resources efficiently and respond to pressing social sector needs, particularly in education and health. As a result, local authorities struggle to make contextually appropriate decisions, limiting their capacity to address equity gaps and prioritise interventions for the most marginalised communities.
Samartha must position itself as a knowledge broker, systematically channelling ground-level evidence to federal and provincial actors. Active participation in thematic working groups and policy dialogues across and between sectors will enable the programme to advocate for flexible, need-based grant mechanisms and GEDSI-responsive standards, taking advance of timid but meaningful central appetite. This approach will ensure that national frameworks become more practical and responsive to sub-national needs.

Applying Learning to Adaptive Engagement and Capacity Building Strategies
The review confirms that willingness and capacity among local governments vary widely: less willing LGs often have greater needs. This calls for a nuanced engagement strategy.
Samartha should use the Multi-Criteria Assessment Framework (MCAF) to refine LG selection annually, balancing prescriptive support with tailored solutions. By prioritising high-need areas while maintaining collaboration with proactive LGs, the programme can reduce the risk of failure and maximise impact and create a peer-learning / peer-pressure environment that challenges underperforming LGs to adopt solutions that worked elsewhere.

C.3 CONTRIBUTION TO MEANINGFUL CHANGE

This review primarily examines the inception phase, and it is important to note that it is still too early in the programme’s lifecycle to draw conclusions about meaningful change. The diagnostic studies, PEA and initial pilots conducted in two contrasting LGs have offered valuable early insights that are informing the design of targeted interventions. These activities have contributed to localised improvements in local planning processes, introduced equity-focused micro-planning, and begun to stimulate dialogue around GEDSI integration and resilience. However, any substantive assessment of impact or sustained change will only be possible at the next review point, once the programme has progressed further and more evidence becomes available.

C.4 FITNESS FOR PURPOSE

Samartha’s approach remains highly suited to Nepal’s evolving political and social context, especially in light of reduced ODA funding. Its flexible design and evidence-driven planning are expected to enable the programme to adapt effectively to financial constraints, ensuring that limited resources are channelled where they are most needed. This adaptability directly addresses pressing governance gaps and supports priority human development outcomes, particularly for marginalised and urban poor communities.
Samartha’s continuation within a reduced ODA portfolio is underpinned by its centrality to BEK’s revised portfolio, which retains an explicit pillar for human capital. Moreover, in line with BEK’s broader priority areas, Samartha will apply an urban lens as an additional perspective across its interventions, reflecting a deliberate move towards addressing the rural-urban continuum in densely populated areas of the Terai. This approach ensures that emerging urban challenges, as well as ongoing rural needs, are addressed in tandem, reinforcing system-wide reforms for inclusive and resilient service delivery across both rural and urban contexts.
Despite ODA cuts, Samartha’s targeted technical support and strategic influence is expected to continue to drive value, prioritising governance readiness, deepening GEDSI integration and embedding resilience across sectors. Ongoing adaptive management and cross-sector collaboration position the programme to remain impactful and relevant, delivering sustainable improvements in governance and human capital development where they are most needed.

## D: VALUE FOR MONEY

Key cost drivers and overall VFM performance
The programme’s key cost drivers rotate around management fees, operational costs and financial aid disbursements. During this reporting period, a foundational framework for a comprehensive VfM strategy was established and will be monitored annually with flexibility to adapt for the highest benefits.
Building on last year’s preparatory phase, Samartha has advanced in delivering economy by localising resources for technical assistance. This approach has optimised the management and operational costs while enhancing contextual relevance. The planned “young professional” development scheme will notably embed recent graduates in intervention sites to support planning and budgeting cycles, providing practical assistance at minimal cost, while fostering local capacity.
Efficiency is tracked through timely delivery and budget absorption rates. Costed workplans embedded in the Payment By Results (PbR) structure has ensured alignment of activities with the engagement of the delivery team, while FA disbursements towards the SESP on a reimbursable basis mitigate fiduciary risks for the BEK. Embedding Key Performance Indicators (KPIs) in the suppliers’ contracts and exercising it during the reporting period have strengthened accountability and performance.
It’s too early to appraise effectiveness, but the assumption is that a contextualised Theory of Action based on a sound results’ logic will facilitate the linkage between activities and intended outcomes across all workstreams. As the programme gradually progresses towards implementation, it will conduct regular appraisals to ensure Samartha remains relevant and fit for purpose. An embedded innovation, learning and evidence (IEL) framework supports adaptive programming, enabling the programme to discontinue less-effective interventions and retain those that deliver the greatest impact, repurposing geographies if required.
Equity is a core principle embedded throughout Samartha’s design and implementation. The programme places a strong emphasis on improving access to basic services for women, girls and marginalised communities. GEDSI considerations are integrated across all aspects of the programme, including interventions, staffing and partnerships. Disaggregated data (by gender, caste, disability and geography) will be collected and used to inform programme design and monitor equity outcomes. Recruitment practices prioritise applicants from target areas, including from marginalised backgrounds, and particularly at the subnational level, while GEDSI responsibilities are embedded into all staff roles.

Assessment of whether the programme continues to represent value for money
Given the early stage of the programme, a more comprehensive VfM assessment is expected in the next annual review cycle. Nevertheless, Samartha’s subnational and sectoral engagement across health, education and the broader social sectors create a strong foundation for a cross-sectoral portfolio approach aimed at driving transformative systems change, in line with the vision of BEK’s recent portfolio reset. The presence of other BEK programmes within Samartha’s selected LGs amplifies this potential, offering opportunities for collaboration and synergy. This convergence will enable joint planning, resource optimisation and shared learning, fostering integrated strategies that strengthen governance and improve service delivery, ultimately maximising impact and ensuring coherence across programmes.

## E: RISK

Samartha’s overall risk rating is set at Major, with all risk categories falling within BEK’s risk appetite. Key programme partners, ASI and Ecorys, maintain risk registers in compliance with FCDO requirements, updating them through quarterly reports or on an ad-hoc basis when immediate escalation is necessary.
Samartha programme risk register in this reporting period shows a diverse risk profile with major risks related to Strategy and Context and Policy & Programme Delivery, while Reputational and Financial & Fiduciary risks are deemed to be moderate, given size and duration of FA support. USAID’s shutdown, UK’s ODA cuts and broader shifts in donor countries’ priorities have generated significant instability, impacting contextual realities within which Samartha must operate. The changed funding landscape has caused gaps in human development, inclusion and governance programmes that Samartha could have complemented to in the development ecosystem of Nepal.
Nepal faces heightened political uncertainty following unrest in September 2025, the installation of an interim government, and federal elections set for March 2026. These developments pose significant contextual risks, likely to slow local decision-making and disruption in intergovernmental relations. The interim government’s short-term focus on electoral preparations means reduced capacity for long-term reforms, with possible delays in local budget approvals and fiscal flows. To evaluate the impact on operations and delivery, ASI recently undertook a rapid PEA. The next annual review will examine how the evolving political landscape has influenced programme priorities, implementation speed and delivery mechanisms, providing insights into how governance dynamics affect operational effectiveness and risk management, or create opportunities for improve performance.
Due to reductions in ODA budgets, Samartha’s overall FA to the GoN through FY 2025/26 is projected to be significantly lower than originally planned. The available funding will be primarily directed to the education sector, focusing on a single outcome-based DLI under the sectoral plan (SESP). A robust fiduciary risk monitoring framework led by multilateral development banks (ADB and WB) has been endorsed by all JFA partners. As these measures provide appropriate fiduciary risk assurance to BEK, the programme has secured a waiver from conducting a full fiduciary risk assessment, instead relying on existing mechanisms to meet FCDO requirements and evaluate GoN’s broader financial propriety.

Update on Partnership Principles
BEK reviews its Partnership Principles annually, a process that underpins all FA disbursements. The Partnership Principles—approved in February 2025—remain unchanged, with no novel concerns identified for FA disbursements compared to the previous year. The latest assessment has highlighted improvements in fiduciary performance across all areas of the Government of Nepal, as demonstrated by BEK’s internal FRAs/ASPs and the most recent Public Expenditure and Financial Accountability (PEFA) review. While this points to improved management of fiduciary risks, concerns remain regarding public sector effectiveness and delivery capacity, requiring close monitoring in terms of their potential impact on VfM.

## F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

During this reporting period, Samartha completed its mobilisation phase by signing two major funding instruments. The first GDD commercial contract was signed with ASI for the main TA component, supporting the GoN. The second GDD commercial contract was signed with Ecorys UK Ltd to provide financial technical assistance and evaluation (FTAE) services to BEK and to the GoN, as well as a fund management function for the BTII. As previously mentioned, due to reductions in ODA, the originally planned AGA award for delivering Intermediate Outcome Area 3 was paused, despite having identified a delivery partner. It is expected that this component will be now integrated in the main commercial TA function provided by ASI, pending decision on total ODA allocations.
The first six months of the TA component delivered by ASI (February–July 2025) served as inception phase, during which ASI mobilised its core team, established programme management structures, and delivered key inception outputs (see Section C). ASI have also subcontracted Plan International to provide education systems TA support and technical leadership.
At the final stage of the inception period, ASI’s team underwent significant staffing changes that included the departure of core members and the team leader. Communication and workforce management practices were deemed sub-standard by BEK, and this was communicated formally to ASI. ASI HQ’s robust engagements and mitigation measures addressed these risks, and all positions have now been filled with a degree of workforce quality that reflects the expectation by BEK. A “bridge” contract amendment process, incorporating revised workplans and activities for August 2025–March 2026, has been completed. Engagement with BEK since the start of implementation has significantly improved, with deliverables largely satisfactory and financial reporting well managed. Nonetheless, early staffing gaps decelerated delivery of early implementation, reduced external stakeholder engagement and limited programme visibility. Recent progress has improved on those trends.
With ASI expanding its pool of experts at both central and provincial offices, the procurement of programme-funded assets has gradually commenced. The BEK programme team will ensure compliance with asset inventory maintenance and will conduct regular monitoring, with updates to be captured in the next annual review. A four-wheeler has been transferred from the RMEL programme to Samartha, with positive VfM implications.
During the three-month inception phase of the FTAE component, Ecorys mobilised its team and also established its office in Kathmandu. Inception deliverables included devising workplans, timelines, risk register, delivery chain map and exit strategy to guide implementation. The local team comprises of a Team Leader and technical experts, while the Project Director and Programme Manager are stationed in the headquarters.
Budget reductions required reprioritisation of activities, and reprofiling of activities to future years. A contract amendment process, reflecting these changes and revised workplans, is now complete. Programme management performance has been broadly positive, with timely submission of reports, deliverables, and financial forecasts. KPI scores for inception and implementation have been satisfactory. However, stakeholder engagement and risk communication with BEK were not as proactive as expected during the early stages: this was addressed through formal communication channels and improved frequency of programme management meetings.
The BTII fund management function initially faced delays due to contractual issues related to planned agreements with UN agencies. As a result, the programme decided to move forward with alternative arrangements and has now gained momentum: as mentioned above five interventions are currently being implemented under this fund.
Samartha has committed FA contribution of £1 million for each of the past and current fiscal year of the GoN, channelled through the Ministry of Education, Science and Technology (MoEST) for the Equity DLI under the SESP. BEK will formally join the JFA in November 2025, being a de-factor member since late 2025[1].
[1] The delay in formal JFA amendment has been related to the uncertain legal status of one of the signatories (USAID, following its closure), as the JFA can only be amended with unanimous agreement of existing signatories.
The previous review captured narratives on preliminary scoping activities aimed at understanding contextual realities in regions targeted by Samartha, delivered by The Asia Foundations (TAF). In December 2024, the accountable grant with TAF concluded successfully, with all agreed deliverables completed.
The following illustrates the overall financial position of the programme as of Nov 2025.
Component Name	Overall budget	Cumulative Spend / (Nov 2025)	Remaining Balance
TAF (AGA)	£298,775	£298,775	0
Citizen Engagement (AGA TA)*	£5,526,225	£0	£5,526,225
Independent Oversight + BTII (FTAE)	£5,000,000	£147,206	£4,852,794
Education TA (PFP)	£275,000	£48,323	£226,677
FA	£15,700,000	£0	£15,700,000
Main TA	£12,000,000	£137,359	£11,862,641
Total	£38,800,000	£631,663	£38,168,337

* Paused

The programme’s cumulative spend stands at £631,663 against a total budget of £38.8 million, reflecting less than 2% utilisation to date. While this appears low, it aligns with the programme’s transition into its core implementation phase, where delivery is expected to gain momentum. The scoping study component (TAF) has fully utilised its allocation, and both FTAE and the main TA components are showing gradual progress. With the shift to full implementation, absorption and delivery rates are anticipated to accelerate significantly in the coming months.

## G: MONITORING, EVIDENCE AND LEARNING

Samartha adopted a three-pronged approach to MEL during this reporting period: strategic oversight and field monitoring by BEK, an embedded IEL component within the TA partner ASI, and independent oversight of FA and BTII fund monitoring by Ecorys.
BEK provided high-level oversight to ensure alignment with portfolio priorities and adaptive management principles. This included regular reviews of programme progress, risk assessments and targeted field visits to Madhesh and Lumbini provinces to both oversee and support early programme interventions. These engagements enabled BEK to validate implementation readiness, assess contextual risks and ensure MEL processes informed strategic decision-making for the main implementation phase. BEK’s role was critical in maintaining coherence between programme delivery and the UK’s evolving development priorities even amidst uncertainty. Joint field visits with donor agencies and implementing partners have further strengthened BEK’s relationships with key provincial stakeholders, ensuring greater acceptance and accountability despite an artificially short-term horizon linked to uncertainties around future ODA settlement.
ASI operationalised a dedicated IEL framework as part of its TA mandate. The IEL strategy emphasises continuous learning loops: planning, monitoring, sharing and adapting anchored in diagnostic studies, PEA, hyper-local assessments, among other tools. It prioritises triangulation of government data systems (HMIS, IEMIS) with programme-generated evidence to strengthen decision-making at all tiers of government. Key components include structured learning forums, peer-to-peer platforms and the testing of practical tools for translating policy and data into actionable plans. This approach ensures adaptive management is embedded across governance, service delivery and resilience interventions. The current reporting cycle has primarily served as a preparatory phase for the learning agenda, focusing on the conceptualisation and design of the IEL framework. This groundwork ensures that future reports provide progresses, meaningful evidence of adaptive programming and innovation in practice, aligned to a bespoke results’ logic. The next reporting period is expected to demonstrate the traction gained and deliver insights as the programme advances into full-fledged implementation.
Ecorys’ role in the MEL framework has mostly rotated around the management of the BTII fund. Activities included developing a Grant Management Manual, establishing compliance protocols, governance structures and monitoring systems, and conducting fiduciary risk assessments to safeguard UK funds channelled through BTII’s recipients. Independent reviews and risk audits reinforce accountability and can help inform programme adaptation.
Ecorys also provided fiduciary risk insights for FA towards the SESP, though BEK also relied on third-party support through the PFM Facility managed delivered by Alinea under BEK’s Public Financial Management/ Multi-Donor Trust Fund II (PFM/MDTF II) programme.

Date of last narrative financial report	Main TA (ASI) – November 2025 / FTAE (Ecorys) – November 2025	Date of last audited annual statement	N/A

## ANNEX A: Transitional Result Framework (Inception to Implementation)

Context	The annual review of the second implementation year transitions from planning and mobilisation to early implementation and establishing a comprehensive structure of learning with tangible outputs. It includes revised workplans, pilot-tested tools and structured MEL systems. In the second year of implementation, Samartha has evolved into a more focused, adaptive, and evidence-driven initiative, ready for broader scale-up. The following areas reflect a shift from foundational setup to early-stage implementation, i.e. inception. 1. From mobilisation to operational delivery: TA inception deliverables completed, including structured workplans, governance diagnostics, and stakeholder engagement. 2. Scoping studies to strategic implementation and result-oriented frameworks: Analytical studies informed revised programme design, governance structures, and tractable issues, including MEL/VFM framework. 3. From broad scope and concepts to focused priorities and practical tools/pilots: Pilots in provinces tested models, equity-focused interventions, and resilience assessments; alignment with UK ODA budget changes.
Change control	Outputs from the previous annual review have been actioned (two on-going out of three), marking a transition from mobilisation to early implementation. The earlier outputs were foundational, while this year’s outputs reflect the current operational context and demonstrate how the programme has progressed toward active delivery and results.

Output 1	Inception deliverables of Technical Assistance
Impact Weighting	40%
Milestones for the review	Progress
1.1 Refine programme design through operational delivery, conduct analytical studies, propose governance and reporting structures, and identify tractable issues to support across federal and subnational governments.	1.1.1 Conducted provincial kick-off meetings and workshops in Lumbini and Madesh, enabling operational insights. 1.1.2 Engaged with federal MoHP and reviewed sectoral strategies to identify governance gaps. 1.1.3 Drafted revised Year 1 workplan based on operational realities and stakeholder consultations. 1.1.4 Identified tractable issues such as PAC and ICAC activation at LG level, and GRB implementation. 1.1.5 Proposed updated SOPs and guidelines for local-level accountability mechanisms. / 1.1.6 Tactical approaches pilot tested in Kamala and Rapti municipalities to support annual planning, with learnings shared with stakeholders to inform future programming.
1.2 Finalize the strategy, design, and management of the Implementation Phase, including its strategic direction, budget allocation, results framework, and clearly defined output-level indicators to guide delivery and measure programme performance.	1.2.1 Defined clear deliverables and outputs for each activity, aligned with BEK’s strategic priorities. 1.2.2 Integrated VfM considerations across all activities. 1.2.3 Proposed a phased approach second implementation year onwards, with indicative workplans and adaptive planning mechanisms. 1.2.4 Embedded GESI and MEL considerations into the implementation strategy.
1.3 Develop a robust Monitoring and IEL framework during the Inception Phase, refining the Results Framework to align with the Theory of Change and VfM Schedule, including justified output, outcome, and impact indicators.	1.3.1 Drafted a comprehensive MEL concept note outlining internal and external coherence roles; alignment of MEL with programme ToC and DLI frameworks. 1.3.2 Developed a VfM framework with indicators across Economy, Efficiency, Effectiveness, Equity, and Cost-effectiveness. 1.3.3 Devised structures of quarterly integrated reviews, annual dissemination events, and partnership roundtables.

Output 2:	Inception deliverables of MEL and BTII interventions
Impact Weighting	20%
Milestones for the review	Progress
2.1 Establish foundational understanding of the programme, including a macro-level analysis of fiscal federalism, public financial management (PFM) reforms, and sectoral governance in health and education	2.1.1 Conducted macro-level analysis of fiscal federalism, highlighting weak implementation and over-reliance on conditional grants. 2.1.2 Reviewed PFM reform trajectory, including PEFA assessments, TSA, SuTRA, CGAS, and PAMS systems. 2.1.3 Analysed sectoral governance structures in health and education, including decentralisation challenges and overlaps in mandates. 2.1.4 Identified fiduciary risks at local levels through CIAA and OAG reports. 2.1.5 Mapped federal health and education budget trends and intergovernmental fiscal transfers.
2.2 Revise scope of work aligning with the UK’s ODA budget, refocusing efforts on Components 1 (Fiduciary Risk Management) and 3 (BTII Fund Management)	2.2.1 Developed a revised Year 1 workplan and deliverables aligned with BEK’s strategic priorities. 2.2.2 Component 3 (BTII Fund Management) remained fully operational, with due diligence, proposal reviews, and financial oversight mechanisms in place. 2.2.3 Grants Management Manual (GMM) developed for programme governance, operational procedures, and financial controls to guide BTII grant management, disbursement, monitoring and evaluation.

Output 3:	SESP Joint Financing Agreement
Impact Weighting	10%
Milestones for the review	Progress
3.1 BEK to join the SESP Joint Financing Agreement (JFA) established as a key milestone to strengthen coordinated financing and accountability mechanisms in the education sector – to formalise collaboration among development partners and the government, aligning resources with national priorities and enabling pooled funding for strategic interventions.	Between October 2024 and July 2025, ADB (then SESP focal point) initiated the formal appraisal process to onboard FCDO into the Joint Financing Partnership. Approvals were secured from the Ministry of Education, Science and Technology (MoEST), Ministry of Finance (MoF), and all existing JFA partners—World Bank, ADB, UNICEF, Finland, Norway, USAID (at the time), and GPE. In August 2025, ADB submitted the final draft JFA, including amendments for FCDO’s inclusion, to the Ministry of Finance. FCDO is expected to formally sign the JFA by year-end. However, USAID’s exit from the sector and GPE’s withdrawal as a JFA signatory have delayed the signing process. / With agreement from MoEST, FCDO as JFP committed £1 million for DLI-based financing (DLI 2.3c of the SESP), enabling the government to meet its equity index improvement targets for 150 LGs for FY 24/25.
3.2 BEK to undertake the role of the co-chair of SESP SWAp including the JFA and LEDPG – a leadership role reinforcing BEK’s commitment for collaborative governance and strategic oversight in the education sector.	The BRM held in April 2025 noted that the European Union and FCDO (BEK) would serve as focal point and co-focal point, respectively starting August 2025, for the JFP and LEDPG group in FY2025/26. BEK’s leadership role includes supporting coordination among partners, co-chairing the JRM and BRM for this financial year hosted by MoEST, facilitating the Mid Term Review (MTR) of the SESP, hosting the Local Education Development Partner Group meetings at the embassy, facilitating dialogue with government counterparts, and ensuring alignment with sector priorities.
3.3 Samartha to support the Provincial Programme Implementation Procedure (PIP) and Local Education Plan (LEP) Appraisal Procedure in Lumbini and Madhesh to enhance coordination between sub-national governments, align sectoral priorities and improve joint planning, evidence-based decision-making, including the overall resource allocation.	The PIP, hosted by CEHRD and supported by FCDO, UNFPA, and UNICEF in Madhesh and Lumbini, delivers structured orientation sessions for provincial and local governments on current education policies, laws, guidelines, standards, and annual implementation frameworks. / FCDO and its TA partner, ASI, participated in all preparatory sessions, contributing to detailed discussions and training on the development, appraisal, and quality assurance of Local Education Plans (LEPs) to ensure alignment with provincial and national priorities. / On day 4 of the PIP session, FCDO and ASI will support targeted capacity-building sessions on LEP development and appraisal, emphasizing comprehensive, coherent, and inclusive planning with a strong GESI and climate adaptation focus, aligned with provincial sector plans and medium-term expenditure frameworks. / Additionally, FCDO and ASI will assist CEHRD in facilitating training on social audits, school improvement planning, school mapping, infrastructure standards, and comprehensive school safety. The program also covers teacher management, professional development, financial transparency, and equity measures, culminating in interactive Q&A sessions to reinforce learning and accountability. / The PIP launch was delayed by one month, from September to October 2025, due to disruptions caused by the September protests.

Output 4:	Technical Assistance pilots in Lumbini and Madhesh provinces
Impact Weighting	15%
Milestones for the review	Progress
4.1 Facilitated "Bridge the gap" workshops and governance diagnostics	Conducted participatory planning workshops in Kamala and Rapti Sonari, translating evidence into action. Included diagnostics on governance functionality, budget absorption, and planning systems.
4.2 Equity and Quality Interventions in Health and Education	Conducted maternal health bottleneck analysis, practice audits, PBCC assessments, and developed guidelines for OOSC enrolment and targeted scholarships to improve inclusive service delivery; delivered GEDSI-responsive planning and budgeting orientations for local officials.
4.3 Resilience and Emergency Preparedness Assessment	Assessed systemic fragility in disaster preparedness and business continuity; developed synthesis report and recommendations for integrated, inclusive resilience planning.

Output 5:	Joint reviews of Health and Education sectors
Impact Weighting	15%
Milestones for the review	Progress
5.1. Support Health National Joint Annual Review (NJAR)	Established the National Joint Annual Review (NJAR) steering and technical committees. The BEK’s health adviser is also chair of the health development partners’ forum, joining the steering committee / BEK will participate in pre-NJAR activities including subnational visits and evidence synthesis for the FY 2024/25 health sector review. / Agreement on the broader agenda and methods for the NJAR (November 2025), focusing on reviewing strategic directions and emerging challenges in and beyond the health sector.
5.2 Support Education Joint Review Meeting (JRM)	As a JFA, participated and contributed to the School Education Sector Plan’s Joint Review Mission (JRM) held in October, as well as the Budget Review Mission (BRM) held in April at the Ministry of Education Science and Technology. FCDO, as part of the JFP group, participated in the joint assessment of SESP progress, contributed to technical and financial discussions, and helped shape the agreed actions of the Aide Memoire for the sector. / For FY2024/25 and FY2025/26, BEK (FCDO) committed GBP 1 million per year as DLI-based financing, supporting key sector priorities and enabling the government to meet agreed targets under the SESP / BEK contributed to discussions on strengthening governance, financial management, and monitoring and evaluation systems. This included supporting the development of the SESP Communication and Engagement Strategy, improvements in EMIS, and advancing the GESI agenda through the establishment of Girls and Inclusive Education Networks (GIENs) / The BRM noted that the European Union and FCDO (BEK) would serve as focal point and co-focal point, respectively, for the JFP group in FY2025/26. BEK’s leadership role includes supporting coordination among partners, facilitating dialogue with government counterparts, and ensuring alignment with sector priorities