## Annual Review Template

Title: Amplifying Movements, Organisations and Activism to End Violence and Support Gender Equality in Sierra Leone (MOVE)
Programme Value £ (full life): £850,000		Review date: September 2024-August 2025
Programme Code: [AMP ID#] 301602	AMP start date: 20 September 2023 (programme start)	AMP end date: / 28 February 2027

Summary of Programme Performance
Year	2024	2025	2026	2027
Overall Output Score	A	A+
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-301602/documents
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005820.xlsx

A. SUMMARY AND OVERVIEW
Description of programme

Amplifying Movements, Organisations, and Activism to End Violence and Support Gender Equality in Sierra Leone (MOVE) aims to strengthen Sierra Leone’s women’s rights movement and girls’ activism to prevent and respond to sexual and gender-based violence (SGBV). In partnership with feminist hub and funder ‘We are Purposeful’ (‘Purposeful’), the British High Commission Freetown (BHC) funds participatory grant-making that provides small, flexible grants to grassroots women’s rights organisations (WROs) and movements. The programme shifts resources and decision-making to women and girls, especially survivor-leaders, enabling locally led action against violence.

Through an Accountable Grant Arrangement (AGA) the programme is investing £850,000 over three and a half years (2023-2027) to:
- Provide core, flexible, multi-year grants to partners, accompanied by support to help build capability, knowledge, and sustainability among grant recipients.
- Support movement and coalition building.
- Drive advocacy and connections with campaigns both in Sierra Leone and globally.

Summary supporting narrative for the overall score in this review
This review covers Year 2: six months under the first tranche of grants (Sept 2024–Mar 2025) and six months under the second tranche disbursed at the beginning of this financial year (FY 2025/26).

Operating context: The national and global operating context remains challenging. Grant partners act as frontline responders to SGBV in their communities, including child and forced marriage and female genital mutilation/cutting (FGM/C), often filling gaps left by underfunded state systems. Despite political commitments, rollback of rights and shrinking civic space persist, increasing the risk of backlash against activists and threatening progress on gender equality. MOVE remains critical to sustaining progress and resilience.

Strategic alignment: MOVE aligns with the Foreign, Commonwealth and Development Office’s (FCDO) International Women and Girls’ Strategy (2023) and UK priorities on locally led development. It tests partnership models and generates learning on enabling locally owned delivery. The programme is generating valuable learning on the enablers and barriers across FCDO culture and systems in supporting a locally led approach with civil society, through quality funding to local actors, and rooted in partnership principles of mutual interest, respect, accountability, and learning.

Partnership performance: Year 2 focused on grant renewal, capacity building, and safeguarding amid civic space pressures. The final year should prioritise advocacy, national engagement, and institutional learning for FCDO.

Major lessons and recommendations for the year ahead[1]
[1] A consolidated list of all recommendations is in Annex B.
Grants enable activism in hard-to-reach areas, that otherwise may not have received FCDO funding, and foster collaboration. All grant partners are shifting norms and behaviours in their communities and playing critical roles in responding to reports of SGBV by engaging to support and signpost survivors to access the care they need.

As SGBV response and prevention remains underfunded, many grant partners are now better resourced than Government service providers, resulting in many filling gaps in systems or covering the costs of basic supplies. Purposeful should support grant partners’ advocacy with national and local government to address systemic gaps and support a revival of the functioning of the Gender Based Violence (GBV) coordination structures which are needed to drive and monitor implementation of national policies. The BHC should consider how to support this in the most effective way possible, for example by working through or convening others, platforming partners, and sharing findings with Government directly.

Grant partners show growing interest in meet survivors’ requests on livelihoods to support their recovery and help vulnerable women and girls achieve the financial independence needed to leave, and not return to, homes that are unsafe. This activity is not monitored as part of the logframe and there is a risk that without specialist support and rigorous prioritisation that grantee partners’ attention and resources are directed towards areas where they have less impact than hoped for. To address this, Purposeful should explore strategic and operational partnership opportunities with actors with expertise in livelihoods and extreme poverty, who may be able to work directly with grant partner communities, or build capability among grant partners through dedicated convening time.

Unregistered groups have formalised for legitimacy and sustainability. The programme was designed to be able to resource unregistered groups, to prevent unnecessary “NGO-isation” of activism. However, the three grantees that were initially unregistered have since registered. Risks of the programme contributing to a proliferation of organisations in competition for scarce resources are offset by the increased partnership and collaboration cited and shared by grantees, and a recognition that current levels of SGBV prevention and response work are still insufficient to meet the scale of local need.

The partnership between Purposeful and the BHC has tested the flexibility of FCDO approaches and found barriers to supporting locally led and owned delivery. Some relate to low tolerance of variance and risk at both the Centre and at Post on financial forecasting and reporting; others relate to central systems and incentives related to contracting, accounting rules, and asset management. These should be considered by both BHC Freetown and central FCDO teams to inform ongoing refresh of systems and policies in a way that removes barriers to locally led delivery.

1. The programme has the potential, and should look, to generate valuable learning on:
  1. How institutional donors like the FCDO can support more locally owned and led delivery, through more equal programmatic partnerships and core funding. Learning goals have not been fully met due to BHC capacity constraints and the related output (5) is at risk of not meeting end of programme targets unless this is addressed. SRO time should be focused on capturing and sharing learning on local leadership and SGBV prevention.
  2. What works and doesn’t work to reduce SGBV, including FGM/C, in Sierra Leone.
  3. Partner outcome stories of change, to demonstrate the value of such approaches. These could be better collected and collated to track collective achievements across: SGBV response; perpetrator prosecutions; prevention of child marriages and FGM/C cases; free legal support provided; and FGM/C practitioners who have agreed to “drop the knife” and no longer perform FGM/C. This could likely be achieved using AI as part of a low-cost approach to MEL

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The Theory of Change (ToC – Annex A) is designed to address a societal problem: women and girls do not enjoy equal rights in Sierra Leone and experience high levels of SGBV. MOVE aims to address this by supporting onwards granting for flexible three-year funding to both established WROs and nascent activist groups, in combination with support to strengthen capacity, coalitions, movements, and advocacy. The logic of the ToC and programme design is supported by evidence on how best to achieve gender equality, empower women and girls, end violence, and an analysis of the challenges and barriers to this. [2] The last Annual Review set out developments of the logframe since business case stage. No changes have been made to the logframe in the last year.
[2] For example: https://www.mamacash.org/wp-content/uploads/2024/07/REPORT-40-YEARS.pdf; https://www.globalfundforwomen.org/wp-content/uploads/2024/06/The-Active-but-Underfunded-Role-Young-Women-and-Girls-Play-in-Crises-Web-1.pdf; https://wearepurposeful.org/wp-content/uploads/2024/01/The-Politics-of-Transnational-Convening-Spaces.pdf; https://wearepurposeful.org/wp-content/uploads/2023/12/Black-Tuesday-publication-2023-291123-VLR.pdf

The intended impact of the programme is to support “cultural conversations and narratives [to] shift to prevent and respond to SGBV in Sierra Leone.” There is one impact indicator: “Systems/movement analysis (conducted by Purposeful) captures change effected in ecosystem of women’s rights.”

There are three milestones to help monitor this indicator:
- September 2024: 19 grant partners identified, and grants awarded [MET].
- September 2025: partner reporting indicates positive shifts [MET]
- September 2026 movement analysis demonstrates positive shifts in the women and girls' rights ecosystem in Sierra Leone[3] [early indications of this being MET]
  [3] As per logframe: Positive shifts may include reported decreases in violence at the community level, survivors accessing response services and justice, increased awareness and implementation of the laws which protect against violence, increasing discourse and commitment at different levels around the abandonment of female genital mutilation (FGM).
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Outcome 1: / Enhanced collective action by diverse WROs and movements in Sierra Leone to tackle SGBV and its drivers, focusing on priorities they determine important, including holding the line against rollback.
Indicator(s)	Milestone(s) for this review	Progress
Quantitative: # of grantees active	15	Moderately exceeded: All 19 grant partners remain active
1.2 Qualitative: reporting on how access to core, flexible, multi-year grants have supported increased ability to deliver relevant and impactful interventions and advocacy.	15 grant renewals	Moderately exceeded: All 19 partner grants were renewed in Q3 this year, affirming their continued commitment and contribution to the movement.
1.3 Qualitative: Evidence of successful interventions/engagements of grant partners - at least 19 examples over programme lifetime.	10 examples	Moderately exceeded: 13 examples

All outcomes moderately exceeded and programme is on track to achieve expected outcomes and impact. Evidence of successful interventions covered a range of areas and results, demonstrating that flexible resources are directly linked to sustained action. Examples pulled from the formally reported stories of change included the following and are not exhaustive – many more similar interventions were shared by grantees during interviews and which are not yet captured in formal reporting: the handling of protection cases (at least 36); conviction of SGBV perpetrator (1); prevention of child marriages (2); free legal support for 12 GBV-related cases, including domestic violence, inheritance disputes and abandonment; Soweis agreeing to stop cutting (at least 24).

The following stories of change are selected to demonstrate the range of work being done since the grants were received:

WAADO - Perpetrator conviction and FGM abandonment: WAADO’s presence in Waterloo has made the community a central reporting hub for SGBV. They have handled at least 36 protection cases, including a sexual penetration case[4] where the perpetrator was convicted after WAADO’s referral to the Family Support Unit (FSU). Monthly coordination meetings with the Ministry of Gender and Children’s Affairs and FSU have strengthened their collaboration on case referrals, follow-up on child maintenance issues, and community sensitisation on SGBV and harmful practices. The Ministry has acknowledged WAADO’s role and now actively engages them in district-level coordination efforts. WAADO also raised awareness among Soweis[5] in Mabiokandor on the dangers of FGM; three Soweis subsequently publicly committed to stop cutting. Others now advocate for a “bloodless rite”.
[4] This phrasing is the legal definition of rape of minors in Sierra Leone.
[5] Soweis are the most senior members of the Bondo Society and lead the initiations into the society (including but not limited to performing FGM/C).

PUDWAF - Challenging early marriage and sexual exploitation: PUDWAF’s awareness sessions across communities in Pujehun exposed risks faced by adolescent girls, including predatory relationships with bike riders who exchange gifts for sex. Following the dialogues, parents and teachers began reporting these interactions more actively to the One Stop Centre and Police (in collaboration with PUDWAF). One community formed a monitoring group of mothers and teachers to prevent child exploitation and ensure girls remain in school. PUDWAF’s consistent engagement has turned awareness into community-led surveillance and protection.

WARDSU - Introducing safeguarding mechanisms in tertiary institutions: WARDSU convened safeguarding coordinators from five universities to develop internal policies and referral pathways for students experiencing harassment or violence, in a context where sexual harassment (including ‘sex for grades’) often goes unreported. After the sessions, one Dean committed to introducing an anonymous reporting box on campus and designating faculty focal persons for safeguarding. WARDSU’s work is setting a precedent for integrating safeguarding into tertiary education spaces, where sexual harassment often goes unreported.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Outputs 1–3 scored A/A+/A+, Output 4 scored B, and Output 5 scored C (this output is unweighted). Lower scores reflect BHC capacity constraints and prioritisation, which should be addressed to secure the maximum value and learning opportunities under the programme.

Social change is inherently long term and difficult to monitor and measure, particularly through an approach that prioritises flexibility and responsive, grassroots-driven interventions. However, the ToC logic remains sound, and the programme continues to demonstrate value for money, even with a missed opportunity to generate administrative efficiencies through what could have been core funding to the partner. This programme offers a significant contribution to BHC Freetown goals on promoting and protecting rights, modernising development cooperation, resourcing and strengthening the women’s rights movement, and preventing and responding to SGBV (as well as wider FCDO strategic objectives set out in Section A). Given the above and the high rates of violence in Sierra Leone, the programme should continue.

New Recommendations:
The ToC and logframe should be reviewed and the team should consider updating the impact statement, and revising impact-level indicators, to better reflect the community and systems changes that are emerging. The outcome level indicators should also be reviewed to ensure these metrics clearly contribute to the overall theory of change and understanding of impact. This, in addition to recommendations in the MEL section to more fully capture grantee partners’ outcomes, will strengthen the programme’s demonstration of impact.

## C. DETAILED OUTPUT SCORING

Output Title	WROs and women’s/girls’ groups are resourced to operate to tackle SGBV and its drivers, through grant making by redistributing resources to WRO and girls’ activism in flexible and appropriate ways
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Successful participatory grant-making (PGM) process as part of inception period	Learning generated on participatory grant-making (by Sept 2024)	No milestone for this period. Indicator complete.
1.2 # of WROs and girls groups receiving flexible, multiyear grants, disaggregated by: registered/unregistered; those led by young women/girls; those led by women with disabilities; and by location. Including amount of funding transferred.	15 grant renewals (by Sept 2025)	Moderately exceeded: 19 grantees received renewed grants. 18 grant partners are led by women, 3 are led by women with disabilities, and 10 are led by young women. Further disaggregation of location is available and reported in the first AR. The 3 initially unregistered groups received an increased amount, based on impressive performance in Y1.
1.3 Qualitative: Flexible, multiyear funding redistributed enables grantees to sustain and respond	Grant partners report improved outcomes from use of flexible, core funds including on ability to respond and sustain work (by Sept 2025)	Met. Both written reporting and meeting with grant partners confirm improved outcomes as a result of the grant and wider support

Briefly describe the output’s activities and provide supporting narrative for the score.
The output has met or moderately exceeded targets and is on track for end-of-programme targets. The programme has successfully directed resources to women, girls, activists and community-based organisations, often working in underserved parts of Sierra Leone and who wouldn’t otherwise have received UK funding.

All three (c.16%) of the grantees that were initially unregistered have since registered as Non-Governmental Organisations (NGOs). This appears to be a strategy to overcome the limitations of working as unregistered activists in a wider system and culture where formalisation is expected and rewarded. Reasons cited for registering included: 1) securing the perceived legitimacy to access communities and to call an audience with district level officials – much of which is made contingent on being registered; and 2) a focus on financial sustainability, and an understanding that registration would increase eligibility for wider sources of funding after the grant ends. Risks of the programme contributing to a proliferation of organisations in competition for scarce resources are offset by the increased partnership and collaboration cited and shared by grantees, and a recognition that current levels of SGBV prevention and response work are still insufficient to meet the scale of local need.

Grant partners that were initially unregistered groups shared some of their logistical challenges in accessing grant funding including: taking on personal financial risk and responsibility by opening a personal account in which to receive the grant funds (which was not mandated by Purposeful); travelling up to 50km to take out cash; and not having somewhere safe to keep petty cash and so using own funds to cover any unexpected costs until the next major cash withdrawal. Poor phone signal in rural areas (and sometimes no signal for up to three days) was reported as a barrier to using mobile money. Purposeful could consider alternative options to increase accessibility, potentially in consultation with financial service providers.

Grant partners report that flexible funds have allowed them to respond to urgent survivor cases and expand coverage into new geographies to support more survivors. They also describe sustaining core staff, improving visibility in their communities and reducing burnout:

“as a result of the funding, we have been able to address issues of violence by reporting, following up on cases, and even providing financial assistance to survivors.”

“Previously, a lack of funds restricted our movement to schools and communities, but the grant enabled us to cover these expenses. Our standing in the community has improved. People now view us as role models, recognising and drawing inspiration from the positive changes in our lives.”
Partner reporting and interviews attest to the positive effect of stipends in boosting confidence, morale, and attracting additional team members: some grantees interviewed noted that they had included budget lines for stipends for the first time this year, and at Purposeful’s suggestion, after not having considered it in the first year. Stipends are allowing activists, many of whom are themselves survivors, to invest in business or education, to support their welfare and professional development. Stipends could be seen as inadvertently encouraging formalisation of activities by turning volunteers into staff, and as a challenge for sustainability of the approach. However, grantees are typically investing the stipends into activities to support livelihoods and professional development and which should therefore reinforce their long-term organising capacity beyond the end of the grant and programme. Purposeful should consider elements such as this as part of exit planning.

“I used my salary to enrol into the university. This has always been my dream but at some point, I got stuck when I got pregnant and I had no support to continue my education.”

In interviews, grantees shared reflections on financial management. One partner had adopted a new financial management procedure which they felt was more robust as result of the support. Others noted with appreciation that Purposeful did not always ask for Annual Audited Accounts if proportionate, which can be an expensive service costing almost £1000 – or up to one third of the smaller grant values.

Beyond the direct work on SGBV prevention and response, which is detailed under output 2, many grantees interviewed noted new or ongoing work to on economic empowerment and livelihoods. This was cited as important to both prevent violence by increasing the status of women and girls within homes and communities, and to provide financial independence for women and girls to leave homes and relationships in which they are unsafe. This increased focus on livelihoods could reflect the grant enabling grantees to stabilise and expand their work to a wider range of needs. However, and particularly for younger and newer grantees with less experience of direct community engagement, there is a risk that this expansion comes at a pace that detracts from, or reduces, the quality of initial and core work on SGBV.

Several grant partners spoke of production and sale of reusable menstrual hygiene kits for both their own use and as a livelihood in which they assessed to be successful. The 2024 Annual Review notes other activities such as gara tie-dyeing, soapmaking, and sewing. Purposeful’s reporting doesn’t cover these activities in detail or assess their effectiveness. The current approach to identifying livelihood opportunities appears primarily based on consultation with survivors on what they would like to/or feel able to do. Purposeful may not have the organisational expertise or interest in livelihoods for grant accompaniment to support effectiveness (e.g. market analysis or training). There is a risk that without this expert support, survivors will default to what they have seen/heard of others doing historically, rather than what would be effective to generate sustainable income.

Describe any changes to this output during the past year, and any planned changes as a result of this review. No changes were made and none are planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous review:
- [7] For the BHC team to remain open to adaptive practices and intentionally engaging in equitable partnership practices. MET: see justification under output 5.
- [8] Working through flexible funding to small, grassroots organisations and with a feminist intermediary supports FCDO’s locally-led development agenda and the Foreign Secretary’s modernising development priority. Being mindful about the selection of intermediaries is critical to ensuring this work is done well. N/A: This was a lesson recorded as a recommendation.
- [9] For Purposeful to work with grant partners to sense-check whether planned interventions around skills building and livelihoods best address their aims and empower communities. MODERATELY NOT MET: This should continue to be monitored over the final year.
- [9B] The BHC team should explore opportunities to collaborate and promote mutual benefit from BHC private sector development programmes. NOT MET: deprioritised due to human resource constraints and other priorities.
Lessons:
While the project was designed with the flexibility to resource unregistered groups and activists and not to actively encourage formalisation of activity, grantees found that their ability to access communities, government power holders, and additional funding was limited by this and so pursued registration.
New Recommendations:
Purposeful to provide ongoing/further help to grantees to prioritise their efforts and limited resources in a way that speaks to their comparative advantage; to include exploring partnership opportunities with development actors with expertise in livelihoods and extreme poverty, who may be able to work directly with grantee communities or build capability among grantees in this space through dedicated convening time.

Output Title	Grant Accompaniment builds power, knowledge, and capabilities among grantees to take action to tackle SGBV.
Output number:		2	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 % of grantees who report a change in their ability (inc. knowledge and skills) to take action to tackle SGBV and/or deliver interventions or advocacy (disaggregated by location).	50% of grantees (by Sept 2025)	Substantially Exceeded / Almost three out of four grant partners (approximately 70%) report increased ability to take action, with strengthened skills in safeguarding, financial management and survivor-centred / advocacy. Grant partners are resourced and institutionally stronger, which should support the sustainability of their activism. / Key Data Source: quantified qualitative data from learning calls and visits.
2.2 Qualitative: annual self-reported change from grantees, through stories, imagery and other qualitative methods (including increased impact as well as learning from challenge/'failure').	10 grant partners stories (by Sept 2025)	Moderately exceeded: 13 examples of change reported which cover change and challenges.

Briefly describe the output’s activities and provide supporting narrative for the score
The output has moderately or substantially exceeded targets and is on track for end-of-programme targets. All partners interviewed reported core activity to shift understanding, attitudes, and behaviours at a community level to support SGBV prevention, alongside direct response work to cases of SGBV. Written reporting confirms this to be the case among all partners. Many reported using law and legal rights as an entry point in communities, using resources developed by the programme and grantee L.A.W.Y.E.R.S. to build understanding of the rights of women and girls, relevant new laws, and penalties for SGBV. Several reported engaging specifically with women with disabilities and their communities, who learned for the first time that they are entitled to free medical care and property ownership under the Persons with Disability Act (2011). The sessions were reported to have empowered participants to report abuses and changed community perceptions about people with disabilities.

Interviews with grant partners and observation of a convening confirmed that grantees had a good understanding of pathways to change in their communities, and how to engage a range of power holders (for example elders, religious leaders, Mammy Queens). Many have applied this understanding to community suggestions to engage primarily in schools - to directly reach girls at risk and to build trust. Some are engaging in schools with existing school safety committee structures and clubs; where they report that their efforts are complimentary and they provide a community liaison link and alternative trusted person to report to. Many report that even where there are assigned female teachers to report to, they (as civil society actors) are the preferred route. This was put down to confidence that they would not “compromise the case” by settling the matter within the community and failing to report to the police, unlike teachers or other authority figures who may be perceived to.

One partner reported that they had effectively influenced school systems to start putting in place the mandated approach to safer schools: “Teachers have since started designating focal persons for reporting violence in schools.” Others are directly filling gaps, for example on school clubs, parental engagement, and reporting pathways, particularly in primary schools where gaps are most prevalent. Grantees reported engaging with district level authorities to determine gaps and identify underserved villages where they could best direct efforts. While this is meeting an important need it also risks undermining national systems and policies.

Grantees recognise their role in SGBV response to be one of signposting and supporting survivors to access specialist care and services. However, interviews with grant partners revealed that the policy approach to survivor centred care, as set out in the National Referral Protocol,[6] is being interpreted and applied at a district level in a way that runs counter to the principles of survivor centred care. The referral protocol is clear that professional case management should be provided to ensure survivors have access to the services they want and need and in the right order of priority (including immediate medical services). However, contrary to the principle of survivor centred care, several grantees reported that survivors must report at a local Family Support Unit (within a police station) to generate a report in order to access free healthcare treatment, and without which survivors are turned away from state healthcare providers and Rainbo services. This referral approach to healthcare was perceived by grantees as a way for health providers to protect themselves against possible accusations of failing to secure evidence that might be needed to support a potential prosecution, and grantees shared a perception that courts preferred the police station to be the first port of call and that deviating from this could jeopardise a case. The BHC recognises this is not how the system should function and will explore ways to raise such feedback with services and authorities.
[6] https://mbsseknowledgeplatform.gov.sl/wp-content/uploads/2022/09/National-Referral-Protocol-2024.pdf

Drug stockouts in Government-run One-Stop-Centres are also reported as common, with survivors frequently asked to pay for supplies at private pharmacies and grant partners often covering these costs. Grant partners also report that the FSUs are so under resourced that they usually require survivors (or partners) to cover the costs of fuel and stationery, or even to provide or arrange transport, for police officers to investigate and record an SGBV case. This risks survivors missing the 72-hour window in which to access time-sensitive medical services as well as undermining the principle of survivor centred care. With case management located in hospitals, and police reporting being the gateway to that service, grant partners are effectively providing initial and interim, if not total case management, for survivors - gap filling, often without the relevant expertise and training to do so.

Grantees try to secure prompt services for survivors by taking them to either one of the state-run One-Stop-Centres for SGBV response, or NGO-run Rainbo Centres, both of which are based in hospitals and have an FSU and counselling services on site. However, these can be significant distances away from the communities in which grantees are working, and the focus on securing successful prosecution often drives grantees to the closest police station to have the best chance of reprimanding perpetrators, particularly where they are not based in the community where the offence has taken place. Grant partners report a major gap in the provision of safe alternative accommodation for survivors and for women and girls at risk. One organisation reported that girls in need of refuge housing were staying at the home of the CEO due to a lack of other options. This in itself could pose safeguarding risks

As part of wider work, Purposeful hosts webinars that are accessible to global activists and movements. A webinar was observed during the review, on the topic of supporting youth activism to end SGBV (including a representative from one of the MOVE partners). The session was inclusive – providing live interpretation into a range of languages including American Sign Language. It generated insights that included how activism can be healing for those who find in it a network and a community of survivors who share their experience on a personal basis but can also help reframe it as part of a systemic pattern of violence and abuse that can, and will, happen in all contexts without action.

Describe any changes to this output during the past year, and any planned changes as a result of this review. No changes were made and none are planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous annual review:
[3] Grant accompaniment, including movement building, should continue as a central aspect of the programme, alongside onwards granting. Purposeful should ensure this is flexible to the needs of grantees, identifying opportunities to strengthen work, including through feminist education, coordination, and supporting grant partners to focus on ‘what works’. MET.
- [4] BHC/FCDO should continue to make effective use of trusted, established intermediaries to support a values-driven approach. For MOVE this means the BHC continuing to engage with Purposeful on grant accompaniment that helps grant partners to shift social norms and tackle the drivers of SGBV and inequality. N/A: this is a lesson captured as a recommendation.
- [10] Update output indicator 2.1. Purposeful and the BHC should review feedback from grant partners to identify trends or noticeable features across the diversity of the grantees. ONGOING: Purposeful continues to identify trends across grantee experiences. Logframe wording should be updated as part of wider recommendations on the logframe.
- [11] The programme should maintain flexibility in grant accompaniment, convening and advocacy activities for Purposeful to responsively deliver aspects of their feminist education to progress dialogue on rights and inclusion issues. Where there is opportunity to do so, this should help shift social norms, reduce stigma, and support actors to tackle the root causes of inequality. MET/ONGOING: a feminist political education convening for frontline responders and media practitioners held in June 2025 and a feminist leadership focused convening held in November 2025 demonstrated this in action.
- [12] As grant partners naturally come with differing levels of experience and skills, the accompaniment plan should provide tailored support and a more structured offer for some of the more nascent groups with limited capacity, for example on facilitation and training or empowerment approaches – with significant mentoring and support to ensure sustainability. If relevant, tailored support based on location should be provided as part of the accompaniment plan. MET: Grant partners are now clustered in categories to receive different levels of support that meets needs; one-on-one support and coaching is still available to all partners.
Lessons:
- Grantees are now sometimes better resourced to deliver an SGBV response than the Government actors responsible and are gap filling services that Government actors should be providing.
- In bringing survivors together to engage in activism, and through the principles of feminist leadership, which includes empathy, the programme might be generating healing benefits for grantees that aren’t formally measured.
- Online workshops and sessions can be made accessible to people with disabilities and non-native English speakers, in a cost-effective way. This is something that FCDO and its partners could all learn from and apply to support inclusion and openness agendas.
New Recommendations:
1. Purposeful convenings could usefully build grantee understanding of: SGBV response policy and protocols; the expectations of different service providers; the principle of survivor centred care; and grantees’ roles in signposting and community liaison rather than as SGBV responders and service providers, unless they are sufficiently trained and qualified. To support this, the BHC could explore further collaboration with the education sector/education programming to build grantees’ understanding of the policy/systems structures that should be in place in schools and recommendations for how to engage with schools, including engaging key partners in the School-Related GBV Coordination Committee. Purposeful could explore setting up a reporting system through the Ministry of Basic and Senior Secondary Education and continue to encourage grant partners to make/maintain contact with district level education leads.
2. Purposeful could support grantee partners to take their first hand understanding of the weaknesses in SGBV referral and response pathways and services to the district and national level and advocate for more effective gender-based budgeting that allocates sufficient resourcing to national governments ambition and strategic direction and policy commitments. This should cover gaps between policy and practice. The BHC should explore opportunities to use available levers to encourage clarity and coordination, and highlight issues related to SGBV national prevention and response, including to support the revival of the national level GBV coordination structure needed to drive and monitor implementation of national policies.

Output Title	Coalition and movement building strengthens movements for action to tackle sexual and gender- based violence and its drivers in Sierra Leone, including bringing in new actors.
Output number:		3	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 # of times grantees brought together to share learning and/or collaborate/coordinate	5 convenings (by Sept 2025)	Substantially exceeded: 8 convenings have been held to date.
3.2 # of new relationships/collaborations reported as a result of MOVE convening (self reported)	5 (by Sept 2025)	Moderately exceeded: 6 collaborations reported as case studies and 3 further examples cited.
3.3 % of grant grant partners who report a change in collaborative actions within the movement (self and peer reporting)	33% of grantees (by Sept 2025)	Substantially exceeded: 79% of grantees. / 15 of the 19 MOVE grant partners reported new or strengthened collaborations, significantly / exceeding the 33% target.

Briefly describe the output’s activities and provide supporting narrative for the score.
The output has moderately or substantially exceeded the targets and is on track to hit end-of-programme targets.

Eight convenings have been held from the programme start to the end of the review period, as follows:
- Panel Orientation in Freetown, January 2024
- MOVE Launch in Freetown, April 2024
- Skills Strengthening Convening in Bo, September 2024
- Skills Strengthening Convening in Makeni, September 2024
- Training of Trainers on Gender Laws in Freetown, December 2024
- Knowledge and Skills Strengthening Convening in Freetown, April 2025
- Safeguarding Focal Persons Convening in Freetown in Freetown, May 2025
- Media Practitioners and Frontline Responders Convening in Freetown, June 2025
These include a convening on safeguarding and bolstered safeguarding content in several others, meeting the recommendation in the last annual review for Purposeful to ensure grant accompaniment and convenings continue to centre safeguarding concerns and strengthen practice. In interviews with grantees, several mentioned that the safeguarding convening had been of particular value.

Many grantees are working in partnership with each other and beginning to work collectively and share resources and support to deliver shared goals to end SGBV. Examples of reported collaborative actions include the case studies below. These collaborations cut across advocacy, survivor referral, safeguarding, and school-based prevention, demonstrating a widening and more interconnected movement:

Community of Practice (CoP) and Rainbo Initiative – Survivor Referral Collaboration: Following the Safeguarding and Knowledge Strengthening Convenings, CoP and Rainbo Initiative established a working relationship to support survivors of SGBV. Through this collaboration, CoP provides transport refunds and food support to survivors who are referred to Rainbo for medical and legal services. This joint effort ensures survivors receive comprehensive care and demonstrates how MOVE has fostered practical inter-organisational linkages within the ecosystem of both access to response and justice.

Gender Awareness Program (GAP), the Ministry of Gender and Children’s Affairs, and Family Support Unit (FSU) – Joint Training on GEWE Act: GAP has been collaborating closely with the Ministry of Gender and Children’s Affairs (MoGCA) and the FSU to train Chiefs, Mammy Queens, and Soweis on gender norms and the Gender Equality and Women’s Empowerment (GEWE) Act. This partnership emerged after the Gender Laws Training of Trainers (ToT) convening, where GAP connected with Ministry officials. The collaboration has strengthened Government-Civil Society engagement at district level and resulted in community leaders’ increased understanding of gender laws and their role in protecting women and girls

Women’s Advocacy and Agricultural Development Organisation (WAADO) and
District Family Support Units (FSUs) – Strengthening Referral Pathways:
WAADO has built strong relationships with FSUs and the MoGCA through monthly coordination meetings that began after the MOVE convenings. Through these meetings, WAADO has become a recognised referral hub for SGBV cases in Waterloo, working directly with police and Government officials to ensure justice for survivors. The collaboration has led to faster case responses and stronger coordination between community-based organisations and formal authorities.

Youth Movement for Sustainable Development (YoMSuD) and Religious Leaders – Joint Advocacy Against SGBV: YoMSuD has developed a collaborative relationship with religious leaders through town hall meetings convened after the Purposeful partner convenings. These engagements have encouraged faith leaders to incorporate messages on ending violence against women and girls in their sermons and community outreach. This partnership demonstrates the movement’s ability to bring new actors, religious and traditional leaders, into collective advocacy for gender equality.

Action for Community Task (ACT) and Forum Against Harmful Practices (FAHP) – Joint School Engagements and Advocacy: ACT and FAHP have initiated joint engagements in schools to strengthen students’ knowledge on FGM/C, SGBV prevention, and gender laws. The partnership was established during the Knowledge and Skills Strengthening Convening, where both organisations identified overlapping areas of work. Their collaboration ensures harmonised messaging in schools and reinforces district-level coordination in the fight against harmful traditional practices.

WARDSU and University Administrations – Campus Safeguarding Mechanisms: Following Purposeful’s Safeguarding Convening, WARDSU formed collaborations with University Coordinators and Deans to establish safeguarding and reporting systems on campus. At IPAM, the Dean approved an anonymous suggestion-box system for GBV reporting, marking the start of a university-level response mechanism inspired by MOVE learning.
Reports, interviews and partner visits revealed further examples of collaboration. For example:
WAADO and MBSSE – collaboration to finalise the GBV Referral Pathways Manual for schools.
- IYWDG and Rainbo – disability-inclusive SRHR and GBV awareness campaigns.
- GADNet and Community Chiefs and Soweis – joint community declarations to abandon FGM/C and adopt bloodless rites.
- Many grantees confirmed collaborating with L.A.W.Y.E.R.S., often seeking advice on cases.
Grant partners shared how the convenings are shifting partner behaviour towards a collective advocacy approach, which prior to the programme had not been common. This was attributed to competition for funding and a lack of alignment on certain issues, including LGBT+ rights and whether pregnant girls should be permitted to attend school. The feminist teachings and convenings by Purposeful have been instrumental in shifting the views of grantees towards an appreciation of, and understanding of, human rights for all. In an interview, when asked about their views on LGBT+ rights a grantee responded: “we are human rights defenders and LGBT [people] are human, so we defend them.” One partner spoke about the challenges of collective advocacy: “coordinating partners is difficult. You need a narrative of why collective advocacy matters as a way to leverage the expertise of the network so that all are playing to their strengths.” In their view, collective advocacy work on sexual and reproductive health and rights in the last year had shown how this way of working was possible, and why it added value, setting a new precedent for grantees.

Some grant partners were actively sharing resources. One gave an example of sharing bikes to reduce costs and increase access to rural communities. In this arrangement, one partner owned a bike and the other contributed an agreed rate for fuel and upkeep. Another partner demonstrated a lack of instinctive approach to sharing resources with the wider movement. The grantee had partnered with a media agency to develop podcasts on FGM, and which they felt were successful in shifting norms and attitudes in their communities, but they were reluctant to share the content for other grant partners to use.

Describe any changes to this output during the past year, and any planned changes as a result of this review. No changes were made and none are planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous annual review:
- [13] Grant partners should be supported to access existing materials and information where available, rather than create their own where this would reduce duplication and ensure consistency of approach. The BHC and Purposeful should explore whether proportionate links can be made with any existing working groups or coordination groups (such as the GBV working group). MET: A simplified version of laws relating to SGBV was produced and provided to all partners, and which grant partners report using and finding useful.
- [14] Ahead of the next grant disbursement, the BHC and Purposeful should work with grant partners to map which groups are collaborating with schools and where, and explore opportunities to join up with other partners, programmes and share learning across grant partners and within districts. ONGOING: In May 2025 Purposeful shared a list of grant partners working in schools. There remains a risk of duplication, parallel reporting structures, and potential conflicting messaging.
- [15] Participation in international fora could be used more strategically if BHC receives more notice and seeks out opportunities for engagement at high-level events. Purposeful should share such plans for each quarter with the BHC in each quarterly report. Further, Purposeful should help grant partners to more systematically disseminate learnings and outcomes to better embed learning and strengthen movements. N/A: there has been no subsequent attendance at international conferences.
Lessons:
Many grantees interviewed referenced or alluded to the value of an intergenerational approach to partnership at a community level - and that for younger activists, working with older more established grantees helped build their legitimacy and secure access. The convenings were reported as being key to understanding which other actors might already be working with an adjacent community or where there were possibilities for partnership. All grantees spoke of the value of peer learning offered not just through the convenings but through active partnerships and working together.
New recommendations:
Purposeful to actively encourage grant partners to share other and new materials, such as the podcast on FGM. This could be covered at a convening or in the context of advocacy on certain issues.

Output Title	Safe and accessible reporting pathways for safeguarding concerns within the programme.
Output number:		4	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Qualitative: Level of trust from grantees in Purposeful's reporting mechanisms	Development of questions/tool to assess/monitor and set a baseline (by Sept 2024) / High trust levels demonstrated during conversations with grantees (by Sept 2025)	Moderately Not met: A safeguarding survey to measure trust in reporting mechanisms was developed early in the reporting period but wasn’t piloted until November 2025, after initial safeguarding sessions had been run. The survey was decided in September to be anonymous and to replace an in-person format for gathering feedback. No baseline has been set following this. Initial feedback demonstrates high levels of trust in reporting mechanisms.
4.2 Qualitative: Strengthened capacity of grant partners to manage and respond to safeguarding concerns.	Self-reported change in awareness of safeguarding approaches for grantees (inc. recognition of own approaches as safeguarding) (by Sept 2025)	Met: / 96.2% of grant partners expressed confidence in Purposeful’s safeguarding reporting systems, with an average rating of 4.65/5. / 88.5% participants rated their safeguarding knowledge as high after the convening, against a baseline of 0. / Key Data Source: Note: Purposeful Safeguarding Convening - Feedback Report

Briefly describe the output’s activities and provide supporting narrative for the score.
The output has met or moderately not met targets but is on track for end-of-programme targets.

The BHC commissioned the FCDO-funded Violence Against Women and Children HelpDesk to support development of a safeguarding assessment tool, drawing on best practice and identifying suitable options. In September, informed by this review, Purposeful’s experience with data collection, and a recognition of power dynamics, the BHC and Purposeful agreed that an online, anonymous survey would be piloted at the November 2025 convening, preceded by a framing session to mitigate power dynamics and social desirability bias. The BHC would administer and analyse the data. Purposeful drafted survey questions in October; after BHC input, the survey was piloted in November. Initial results show strong trust in reporting mechanisms and positive feedback on safeguarding support, though further analysis is needed to understand limited negative responses. A baseline will now be set by February 2026 (missing the September 2024 milestone).

Following the April 2025 convening, grant partners appointed safeguarding focal points. A dedicated Safeguarding Convening in May brought together 26 representatives (22 MOVE, 4 Wati Kura)[7] to strengthen safeguarding knowledge, reporting practices, and institutional capacity. Purposeful and the BHC reinforced zero-tolerance for SEAH and shared best practice on child protection and safeguarding for grantees and their communities.
[7] Wati Kura is a Purposeful initiative, co-funded by the Embassy of Ireland, which moves money to the grassroots movement to end FGM. Their work is closely aligned with the goals of MOVE and there is value in having these partners in the same spaces when different project budgets and logistics allow.

Key findings from the post-convening feedback demonstrate clear advances in both awareness and trust:
- High levels of trust in Purposeful’s reporting mechanisms: 96.2% of grant partners expressed confidence in Purposeful’s safeguarding reporting systems (average rating: 4.65/5). Qualitative responses highlighted Purposeful’s transparency, professionalism and strong survivor-centred approach as key reasons for trust.
- Improved knowledge: Safeguarding knowledge rated “high” rose from 0% pre-convening to 88.5% post-convening. Partners reported stronger understanding of SEAH, power dynamics, ethical reporting, confidentiality, and referral procedures, and now view safeguarding as an inclusive, ongoing organisational responsibility, extending beyond child protection to encompass staff, volunteers, and communities.
- Contextual Recognition: Participants identified existing activities and values as safeguarding measures and committed to reviewing or establishing policies, codes of conduct, and reporting mechanisms. Many noted that their organisations are “becoming safer spaces for reporting concerns”.
- Commitment to Continuity: Partners requested ongoing support (refresher trainings, tools, logistical help) and pledged to lead internal trainings and policy reviews.
During interviews, grant partners shared appreciation for Purposeful’s approach to building safeguarding capacity in a way that supports activists to keep themselves safe, as well as their target communities. Grantees showed good understanding of steps to follow if there is a threat to staff in terms of understanding the threat, informing authorities and the Purposeful safeguarding lead, and removing the staff member from the situation/geography if the threat appeared serious. One major safeguarding issue was reported this year, of an activist whose safety had been threatened by traditional authorities and police. The activist and grantee shared how Purposeful gave fast and hands-on support to risk assess the situation, leading to agreed action by the activist to comply with the demands of authorities in paying a fine, followed by temporary relocation and access to legal advice. In an interview, one grantee shared some confusion/difficulty relating to the correct protocols related to images of survivors taken and shared as part of evidence collection and SGBV response. This has been shared with Purposeful.

Describe any changes to this output during the past year, and any planned changes as a result of this review. No changes were made and none are planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the last review:
[5] [16] [17] The BHC team should prioritise the development of the assessment tool in the next quarter, exploring whether support could be drawn down from a helpdesk or the Safeguarding Resource and Support Hub. Future convenings should allocate more time to safeguarding earlier in agendas and Purposeful should ensure all guidance for grantees sets out very clear expectations within FCDO’s position and more broadly for best practice (including regarding child protection and appropriate relationships). As part of the grant accompaniment, Purposeful should utilise tools from the Safeguarding Resource and Support Hub that could support grant partners in strengthening approaches. MET.
Lessons:
- As grantees continue to work on sensitive issues, and civic space continues to close within a wider context of the rollback on rights, robust approaches to safeguarding grantees will remain of high importance to the programme.
- As bolstered safeguarding support has been rolled out, Purposeful and the BHC have reflected on the importance of clarifying the difference between protection responses and organisational safeguarding. As awareness has increased, grant partners have increased their reporting of ‘safeguarding concerns’ – most times these are community SGBV or protection cases, rather than safeguarding. Purposeful have shared learning on the importance of using, and supporting grant partners to use, the different terms and concepts to avoid any confusion or jeopardising future funding relationships – whilst maintaining openness of safeguarding reporting and Purposeful’s support in responding to protection cases.
New Recommendations:
1. Purposeful to consider connecting with some of the international organisations named in new FCDO guidance on protecting human rights defenders, with a view to securing future advice and support if an activists safety cannot be secured within Sierra Leone.
2. Purposeful to integrate content on protocol/handling of images and evidence as part of protection and safeguarding approaches.
3. BHC to update the logframe to reflect use of the survey rather than discussion to measure 4.1 and prioritise analysis of the survey responses, including sharing this back to Purposeful and grantee partners, in early 2026.

Output Title	Learning on impactful partnerships between bilateral donors, like FCDO, and women's rights/feminist organisations, in line with FCDO strategic commitments to provide more support to WROs.
Output number:		5	Output Score:	C
Impact weighting (%):		0%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Qualitative: Joint assessment by Purposeful and FCDO on management of key programmatic issues - to support flexible, core, multiyear support to grant partners, enabling grant partners to prioritise time/resources for critical work, and provide assurance to FCDO and accountability for funds, in line with the PrOF. See logframe annex for checklist of issues.	Joint assessment against checklist issues (by Sept 2025)	Moderately not met. No specific joint assessment taken, but key issues on the checklist are discussed in quarterly programme meetings.
5.2 Qualitative: FCDO and Purposeful generate learning from the partnership - debrief/reflective discussions held after key events/convenings; learning recorded	Annual learning note (co-created) (by Sept 2025)	Substantially not met: The learning note from the last annual review has not yet been finalised. / The timeframe for this milestone should have been updated so that learning notes are produced after the annual review.

Briefly describe the output’s activities and provide supporting narrative for the score.
The output has moderately or substantially not met the targets and is at risk of not hitting end-of-programme targets.

The learning on partnerships is of key interest to the wider FCDO, as it seeks to deliver the new approach to development, which includes a shift from International Intervention to Local Leadership. The fundamental barrier to generating this learning systematically has been a lack of capacity and the de-prioritisation of this output as a result. There is an opportunity to use the last year of implementation to address this by generating the planned learning products and sharing these learnings with the wider FCDO network, in particular the working groups on local leadership and delivery.

Purposeful’s wider work with feminist movements and activists globally is also generating valuable insights into how bilateral funders can best resource this work. A webinar hosted by Purposeful on supporting youth activism to end SGBV, and observed as part of the review, shared some powerful reflections including: “funders should treat lived experiences as capacity and expertise” and that “sexual violence doesn’t discriminate, but funding approaches do.” The webinar reinforced the importance of supporting young survivors and activists as the ones who will be taking the fight to end GBV forwards.

In interviews, Purposeful confirmed that they saw the BHC as an ally and equal partner, bringing different expertise and skills to the table and that it been transformative at an interpersonal level. Both the BHC and Purposeful gave examples of where they had worked to find flexibility across the systems and where there were hard walls that they “couldn’t partner their way around”. These related to pinch points around financial forecasting and reporting; risk and contracting, asset management and are unpacked further in section F and captured as lessons there.

A specific discussion on output 5.1 in advance of this Annual Review has not taken place, however management of key programmatic issues are continually discussed by the BHC team and Purposeful, including in quarterly meetings. A review of these should take place jointly by the next quarterly meeting. However, interviews conducted as part of this Annual Review, alongside the initial assessment below, suggests that progress is positive. The following areas are identified in the logframe annex as foundations for this assessment and are updated on below:

- Financial management (PrOF rules 22, 23, & 24):[8] financial management standards have been met. However, some issues remain in financial reporting and profiling of budgets as discussed in section F. Agreement was reached on asset management, as reported in the last Annual Review.
  [8] FCDO’s Programme Operating Framework (PrOF)
- Reporting (PrOF rules 19 & 20): the quality and consistency of narrative reporting has improved significantly since the last Annual Review and is sufficient to provide oversight, manage risks, and support decision-making. Joint work is required to sustain and enhance the utility of these reports. Significant learning is shared through reporting and other monitoring. The BHC and Purposeful have moved towards six monthly reporting periods, with quarterly reports alternating between detail from grant partners and Purposeful.
- Branding and comms (PrOF rule 11): The visibility statement has been well implemented, with the teams able to agree branding exemptions to mitigate any unintended harms or risks to activists. Most grant partners welcome visible links to the BHC and have included UK international development branding on assets and communications materials. However, there was an example of a larger grant not being recognised as UK funding (and which was branded instead as Purposeful funded). Lack of visibility of support to the SGBV response system has wider implications for the BHC’s partnerships. The programme prioritises local leadership, equal partnership, and seeks to shift power and conventional ‘donor-recipient’ power dynamic. The BHC continues to reflect these principles in their external communications related to the programme, recognising that centring the UK rather than empowered local actors could undermine these objectives.
Records of the July meeting with Purposeful confirm that the programme/projectised nature of MOVE has not changed how Purposeful relates to grantee partners, and they have maintained the essence of the Survivor Solidarity Fund (SSF). However, despite flexibility within the programme, wider funding does not currently meet the movement’s needs for flexible funding for responsive (and often sensitive) advocacy. Some of these issues may relate to the different expectations of what quality and core funding would look like in practice, as flagged as a lesson in the last annual review. This might have been avoided through drawing up an initial set of principles around how the partnership would work in practice and holding each other to account on these.

A learning note from the last Annual Review period has not yet been finalised due to BHC staff capacity. The last Annual Review also recommended that the learning notes were developed following the sign off Annual Reviews not before, however the recommendation to update the logframe was not actioned. However significant shared learning has been generated, including evidenced in meeting notes and BHC feedback/inputs into central initiatives and discussions. For 16 Days of Activism Against Gender-Based Violence, Purposeful published an article on the Importance of Flexible Funding in Survivor-Led Organising[9]. The article was prepared during the reporting period of the Annual Review, and published outside of it, and evidences a number of the lessons on partnership generated over the period.
[9] The Importance of Flexible Funding in Survivor-Led Organising | by Purposeful | Dec, 2025 | Medium

Describe any changes to this output during the past year, and any planned changes as a result of this review.
As above and as per the last Annual Review (AR), the milestone for indicator 5.2 should be changed to ‘after each annual review’, so that learning can be gathered through the AR process.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the last review:
- [18] It is recommended that the milestone for indicator 5.2 is changed to ‘after each annual review’, so that learning can be gathered through that process. NOT MET: due to capacity constraints.
- [19] Developing meaningful and equitable partnerships with women’s rights organisations may require a shift in traditional ways of working, with more recognition of the experiences, priorities and strategies of WROs, and donor responses being shaped by this. The BHC team should continue to engage and share learning on this agenda within FCDO through the community of practice and advisory networks. ONGOING.
- [20] Outcomes from joint learning are still emerging. These should be identified in collaboration. It is recommended that the BHC and Purposeful jointly define the objective, focus, and audience of learning notes and produce this by the end of quarter four. ONGOING: A first draft learning note was developed in September but more needed to take this forward.
- [26] To maximise opportunities, reduce requests for information, and provide the necessary oversight and assurance for BHC, Purposeful should ensure forward plans and changes are communicated in good time. BHC should ensure that requests are well managed, provide partner(s) adequate time, and add value. MET/ONGOING.
- [28] It is suggested that Purposeful explore a dedicated role for MOVE programme management and communications with BHC, to enable other members of the team to focus on accompaniment, advocacy, and delivering activities. MET.
- [29] The quality of narrative reports is variable and need more clarity on the results and impact supported, as well an improvement in the quality of drafting, in order to demonstrate effectiveness and best represent the work of grantee partners. Flexibility of moving from quarterly to six monthly narrative reporting from grantees will only be possible if supported by high quality reports, clear results, and other forms of monitoring and continued regular engagement. ONGOING: there were improvements in reporting but some ongoing issues with quality of financial reporting.
Lessons: Grant arrangements and limitations
- The programme Business Case sets out that the MOVE programme is designed to address a problem set relating specifically to the lack of long term, flexible and core funding for WROs and movements globally and in Sierra Leone, and a reliance on (insufficient) as well as short-term project support. While core funding was envisaged at design stage for both Purposeful and their grantees, a standard programme management arrangement has been used with Purposeful while core funding was provided to grantees. As such, the programme has not tested and benefited from the full flexibility of FCDO systems, nor generated the full lessons and proof of concept related to FCDO ability to provide direct bilateral core funding to civil society organisations as intended.
- A combination of factors appear to have led to this: 1) the business case did not make explicit that core funding was expected for both Tier 1 and Tier 2 partners; 2) staff turnover in the BHC (new SRO, PRO, and wider programme management expertise) and in Purposeful meant that this initial intention was not a shared understanding of all colleagues; 3) the financial case confirmed that an Accountable Grant Arrangement (AGA) would be used and did not clearly articulate the envisaged mobilisation and delivery mechanism; 4) the use of this AGA template potentially initiated an “auto pilot” towards the default grant arrangement and requirements, when there weren’t alternative or specific guidance and templates for core funding and; 5) the partner taking a defined projectised approach as default.
- The last AR identified lessons around the value of an intermediary organisation like Purposeful. These still hold. The programme has usefully demonstrated how difficult it is to do things differently. This is attributable in part to a lack of institutional nudges and guidance to support the shift to local leadership and locally led delivery through consideration of core funding, and that the onus is on programme teams to more fully explore and apply the flexibility of FCDO systems (often constrained by risk appetite or internal processes).
- Beyond the standard accountable grant arrangement, both partners worked in the spirit of moving towards a more equal partnership in which power and resources were transferred to Purposeful and onwards to their grantees. However, a more formalised framework for engagement or articulation of a set of terms or principles for engagement might have been beneficial and helped both partners have a shared set of expectations and criteria for what good looked like in the context of their partnership.
New Recommendations:
1. FCDO Centre for Delivery (CfD) to review this Annual Review and consider new templates and guidance on core funding for NGOs which make it clearer and easier for teams to explore as an option and alternative to more a projectised funding arrangements. FCDO CfD to review existing templates and revised language in a way that supports more equal partnerships. The BHC should seek a discussion with CfD and consolidate any PrOF updates or advice into the last year of the programe.
2. As above and as per the last AR, BHC to update the milestone for indicator 5.2, so that learning can be gathered through the AR process.
3. BHC to focus SRO time on learning, and to use this to generate the learning products with Purposeful and disseminate these with relevant groups across the FCDO through shared sessions with Purposeful. The teams could explore re-weighting this output to reflect the importance of wider learning.
## D: VALUE FOR MONEY
Key cost drivers and performance
In line with global evidence, central policy steers, and comparative centrally managed programmes, the Value for Money (VfM) case for this programme is not based on cost per beneficiary calculations. This approach would undermine the Theory of Change (ToC) which seeks to move away from ‘buying outcomes’ through short-term project funding and towards investments which will have wider social and economic value which sustains long after funding ends.

Economy: The key costs for the programme are the onwards granting, direct grant-making costs, grant accompaniment (including grantee support and learning), salaries, and overheads. Consistent with the last Annual Review, grant-making is the largest proportion of spend (approx. 45% of total spend to date, with approx. 99% of this for onwards granting). Admin and overheads constitute approx. 14% of the total spend to date. The remainder of the budget is for grant accompaniment, coalition building, and advocacy activities.

Efficiency: As set out in the last AR, efficiency assessments should be based on the ability to translate inputs of grant-making and accompaniment into outputs of resourcing WROs, building capacity, and strengthening coalitions. Based on the above economy assessment, the current process provides good VfM due to the balance between grant-making funds and administrative costs. However, this overall measure of efficiency remains lower than expected due to ongoing significant admin and staffing input in managing the programme. Some efficiency gains were made over the last year, but these were largely offset by time spent on new financial management issues as a result of: a purchase order error at the level of central systems; and the shift from payment in advance to payment in arrears as a result of resourcing accounting challenges and low tolerance of financial variance. Time spent addressing these issues has had an opportunity cost on effectiveness on output 5, and across the 38 recommendations generated by the last AR. This review intentionally recommends fewer and more focused actions which are assessed to be proportionate to grant size.

Effectiveness: The Business Case and last AR set out the effectiveness case and VfM of core, flexible, multi-year funding for WROs.[10] This programme has continued to reach organisations (at least 19) doing vital work at local, grassroots levels – organisations beyond the normal reach of FCDO systems. As such the programme continues to demonstrate good effectiveness against intended outcomes. The three initially unregistered groups have since registered, in part as a way of securing future funding and resourcing their ongoing activism. The minimal approach to capturing grantee partners’ impact through case studies acts as a limit on the extent to which the full impact of grant partners is being captured. There is a recommendation [18] to address this under MEL. Output 5 has not been delivered due to active de-prioritisation in a context of low BHC staff capacity. There is a recommendation [11] to consider assigning a weighting this outcome to reflect the importance of the programmes learning for the wider development sector in its final year.
[10] OECD (2024), Bridging the Gap for Women’s Rights Organisations: Canada’s Support through the Equality Fund: http://www.oecd.org/dac/gender-development/OECD-report-on-womens-rights-organisations.pdf

Equity: Equity is a foundational VfM consideration for MOVE and the programme continues to support historically hard-to-reach communities and organisations (including rural communities; unregistered groups; those led by, and representing, women with disabilities, young women and girls; and those led by survivors of SGBV). In practice, fiduciary risk has not been shared as equally between the BHC and Purposeful as intended, due to low tolerance for financial variance by FCDO central teams and the BHC and resourcing accounting challenges which led to a shift to payment in arrears rather than advance. This was not intended and runs counter to the programme intentions to provide quality funding as part of a more equitable programme partnership.

Cost-effectiveness: The programme is based on evidence on the impact feminist movements and WROs have on effecting change and tackling violence.[11][12] The low cost, flexible approach of MOVE and the range of interventions supported continues to suggest MOVE’s potential as a ‘best buy’ programme. However, as per outputs 1 and 2 and the MEL section, more could be done to ensure efforts and resources are directed towards the most effective interventions.
[11] MamaCash (2020), Feminist Activism Works: A review of select literature on the impact of feminist activism in achieving women’s rights: https://www.mamacash.org/en/literature-review-feminist-activism-works
[12] Kerr-Wilson, A., Gibbs, A., McAslan Fraser E., Ramsoomar, L., Parke, A., Khuwaja, HMA., and Jewkes, R. (2020), A rigorous global evidence review of interventions to prevent violence against women and girls, What Works to Prevent Violence Against Women and Girls Global Programme, Pretoria, South Africa

VfM performance compared to the original VfM proposition in the business case
The business case indicators on VfM replicate many of the logframe indicators, which already provide proportionate opportunities to assess VfM. The original efficiency assumptions based on working through an established fund have not been fully realised due to the set-up of the grant as a programme rather than core funding. While efficiency is less than the proposition in the business case, the last AR recorded benefits from this: close partnership between the BHC and Purposeful, a strong brand for MOVE, sense of community for grantees, a participatory grant-making process, and greater learning. The programme team and Purposeful have an opportunity to consider whether an upfront time investment in changing the arrangements to core funding would generate sufficient gains throughout the remaining year to be worthwhile.

Assessment of whether the programme continues to represent value for money
It is assessed that the programme continues to be a sound VfM investment for the BHC, particularly considering the high cost of SGBV on wider social and economic progress. The programme has met or exceeded most anticipated outcomes and outputs. BHC’s partnership with Purposeful delivers the outcomes and impact intended. Beyond this it also provides significant contextual insights into civil society/civic space and how the global rollback on rights is playing out in Sierra Leone.

Recommendations from the previous annual review:
- [21] BHC should work with Purposeful to ensure that interventions with good evidence of effectiveness are prioritised and that these are well-designed by partners. Where interventions have promising, but limited, evidence of effectiveness grant partners should be supported to assess effectiveness and share learning. Conversely, BHC and Purposeful should not fund approaches proven not to be effective in preventing VAWG, unless these are well-considered as part of a multi-component approach.[13] ONGOING: Through grant accompaniment Purposeful work with grant partners to tailor plans, however more could be done to prioritise evidence-based interventions (or generate learning on work with limited existing evidence).
  [13] Kerr-Wilson et al, (2020) A rigorous global evidence review of interventions to prevent violence against women and girls.
- [22] It is proposed that a new VfM approach is developed (including the above recommendations), with a streamlined set of quantitative and qualitative indicators drawing on readily available data where possible six months before the next Annual Review. NOT MET: due to capacity.
- [23] BHC and Purposeful should explore opportunities to disseminate learning and bring on other funders to this work. Purposeful and grant partners should continue to consider the sustainability of this work and how to continue activity beyond the end of BHC funding. ONGOING: Ongoing discussions, including in October with Co-CEOs.
- [24] It is recommended that a proportionality formula is set as an economy indicator to ensure grant-making activity remains the highest priority funding allocation, drawing on learning from other contexts. NOT MET: due to capacity constraints, although an initial approach to proportionality was developed following the last Annual Review.
New recommendations:
1. BHC to ensure that any new approach to monitoring VfM should be proportionate to the size of the grant. A minimal approach could be taken that articulates which of the existing logframe indicators are being used to track the five “Es”. Alternatively, one or two additional indicators – integrated into the partnership assessment approach for ease – could work. Lessons could be sought by the BHC from a central programme supporting the Equality Fund on how its VfM has evolved.
2. The BHC and Purposeful should explore what efficiency savings could be achieved in the last year of implementation and decide whether to transition to core funding (if BHC risk appetite would support this) or expand the efficiency gains possible under current arrangements, for example through a transition to six monthly financial reporting.

E: RISK
Overview of risk management
The MOVE programme continues to operate in a complex and high-risk environment, with overall residual risk assessed as Major. This reflects the challenging context of entrenched gender norms, civic space pressures, some of which have increased since programme inception, and the programme’s higher-risk, higher-return approach to locally led funding. This is compounded by shifts in the UK’s strategic approach to development and ODA and changes to the global aid system. While most risks remain within the programme’s stated appetite – receptive for strategy, delivery, and fiduciary categories, and cautious for safeguarding and people – pressure points persist at the upper end of these thresholds.

The BHC team keeps a record of programme risks by maintaining a risk register and reviews these risks frequently. Potential risks are discussed at quarterly meetings with Purposeful, and the risk register is also formally reviewed on a quarterly basis during internal meetings, updating the register as needed. Following the last Annual Review, a delivery chain risk map was developed, highlighting risks throughout the delivery chain and evidencing the diversity of grantee partners.

The programme has largely operated within appetite, though strategy/context and safeguarding risks remain at the upper limit. No increase in appetite above corporate appetite is proposed at this stage. If civic space pressures escalate, a temporary adjustment to receptive appetite for safeguarding (related to safety of activists) may be considered, subject to senior approval. Residual risk targets for end-2025 include maintaining safeguarding at moderate with improved assurance and lowering fiduciary risk to minor-moderate following resolution of HERA issues and IATI compliance.

Context and Strategy Risks: The most significant risk remains the non-linear progress on gender equality and movement outcomes. This is reflected in Sierra Leone’s patriarchal norms and stalled legislation such as the Safe Motherhood Bill and the recent passing of the Child Rights Act without reference to FGM. These may represent areas of localised rollback risks as part of global trends on the rights of women and girls. The programme’s limited scale and timeframe compound this challenge, create a risk of perceived failure in a global context in which maintaining current progress should arguably be seen as a sign of success. This risk is tolerated within appetite, given the programme’s design and ambition.

Financial and Fiduciary Risks: Financial risk remains a priority area, with three active risks: downstream fiduciary variability, resource accounting friction (as per section F), and a newly prominent risk relating to HERA issues. The latter stems from mislabelled project codes and unclear central guidance, which delayed resolution and created compliance uncertainty. Broader fiduciary risks are mitigated through enhanced due diligence, quarterly finance clinics, spot checks, and the arrears payment model introduced in 2024. Achieving IATI compliance remains a critical target. Purposeful is currently updating whistleblowing, anti-fraud, anti-bribery and anti-corruption policies which are actively being reviewed and approved by their Board.

Delivery Risks: Risks around Purposeful’s staff turnover related to leadership and staffing transition should reduce by end 2025, when the revised internal structure is expected to be in place. These changes have posed challenges to institutional memory and established ways of working in the partnership over the reporting period but have been managed as detailed in Section F.

Safeguarding Risks: Safeguarding risks remain moderate, but close to the appetite limit. The risk level may increase further over the next year, due to potential backlash against activists as they begin – or scale up – work on sensitive issues like FGM. Closing civic space and localised rollback may increase this further. Purposeful’s organisational safeguarding approach is robust, and work detailed under Output 4 has built downstream grant partners capacity building and policy assurance. Purposeful will integrate FCDO Reporting Concerns into internal and partner-facing safeguarding materials.
Due Diligence and Assurance
The enhanced DDA conducted in 2023 identified minor risks across most pillars and moderate risk for safeguarding. These findings are reflected in the risk register, alongside progress on mitigation actions such as safeguarding workshops and accompaniment plans. The BHC Team maintain a due diligence recommendations tracker in their Delivery Plan. One action remains outstanding related to compliance with IATI publishing requirements. Purposeful committed to achieving this by June 2025, but progress has stalled following the departure of the lead staff member responsible for this task.
This programme is aligned to the Paris Agreement and is considered low risk with regards to climate and the environment. The programme does not fund fossil fuels or counter the ambitions of the climate goals of any countries it works in.

The programme is compliant with key equalities obligations, and the Gender Equality Marker (Principal) and the Disability Inclusion Marker (Significant) remain valid, given the core objectives of the programme and delivery over the last year.

Recommendations from the last review:
- [25] The BHC and Purposeful should continue to engage in institutional and sector-wide discussions on how risk is understood and conceptualised in the face of a rollback of rights. BHC should continue to monitor shrinking civic space and adapt advocacy approaches to protect activists and address backlash. ONGOING.
- [27] Purposeful should ensure compliance and begin publishing to IATI within six months (by June 2025). NOT MET.

New Recommendations:
1. Purposeful to confirm timeline for compliance with IATI publication.
2. In line with the PrOF the BHC should undertake a proportionate and light touch review of the DDA 2026, and relevant aspects refreshed if necessary.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
The MOVE programme continues to support 19 grantee partners, with adjustments to grant sizes in the second tranche of funding to reflect evolving needs and performance. This flexibility remains central to MOVE’s locally led approach, enabling grant partners to adapt to context-specific challenges while maintaining alignment with programme objectives. Between September and November 2025, the BHC Team undertook a programme review in line with the BHC’s internal Portfolio Excellence Plan. Broadly this highlighted good practice on programme documentation and compliance, safeguarding, and fraud, risk, and financial management. It recommended that the Delivery Plan is updated and used more as a live programme management tool.

Programme management in 2025 has faced significant capacity challenges on both Purposeful and BHC sides. Although additional staffing was approved for Purposeful to strengthen grant oversight and assurance, the organisation has experienced some staff turnover (including four staff directly engaged in the programme departing since January 2025), due to an organisational restructure under a new co-CEO, the return of some staff from Purposeful-funded higher education, and others having left to begin their own initiatives - often with an ongoing level of partnership and connection with Purposeful. Purposeful is currently undergoing a restructure, which will see returning staff assume programme management responsibilities, aiming to restore stability and expertise. This turnover has resulted in a loss of institutional knowledge and required both partners to invest time in building relationships to ensure continuity and shared understanding of programme objectives. At times this has been challenging for the BHC in determining the right point of contact within the organisation, but Purposeful has drawn from “a deep bench” of staff with earlier and engagement with the programme to provide cover, if not continuity of engagement with the BHC. Grant partners all reported good collegiate relationships with Purposeful and a smooth transition of support throughout staff turnover.
The BHC team also experienced internal staffing constraints in Quarter One, with the Programme Manager moving to another team. Subsequently the BHC team is comprised of the Senior Responsible Owner (SRO/Lead Adviser) and Programme Officer (subsequently appointed as PRO) managing the programme. This, in the context of wider pressures, has forced prioritisation of critical issues; for example, limited progress was made on many of 2024 AR recommendations during this period. In discussions between partners, both the BHC and Purposeful have reflected that the previous AR may have set too high an ambition given the small scale of the programme resource. Despite these challenges, regular formal and informal engagement between BHC and Purposeful has continued, including quarterly meetings and ad hoc meetings depending on the issue. These meetings remain critical for addressing operational issues, conveying corporate messages, and managing risk.
Financial Performance and Reporting
Financial management and forecasting have improved but remain a key challenge. The programme initially operated on a payment-in-advance model, but during the first year shifted to payment-in-arrears. This change was driven by:
- Difficulties reconciling grant spend under resource accounting rules
- Quarterly payment and forecasting requirements aligned with standard practice
- Challenges for Purposeful in accurately accounting for grantee spend on a quarterly basis.

The previous model created administrative burdens for the BHC on reconciliations and a risk of transferring payment in ‘advance of need’. Moving to arrears resolved these issues, but placed more financial risk on Purposeful. As grant burn rates became clearer and partnership practices bedded in, forecasting accuracy improved for both partners.

Quarterly reports provide detailed financial data from grantees, ensuring transparency, financial management assurance, and mitigating risk. However, BHC scrutiny remains intensive due to strict internal governance, low tolerance for variances (from central directorates), and occasional quality issues in Purposeful’s submissions (e.g., spreadsheet errors causing underreporting). These errors undermine confidence, reinforcing detailed reviews.

Limited flexibility under resource accounting and variance rules continues to challenge the provision of genuinely flexible core funding. While the BHC has pragmatically managed this with receptive risk appetites and with leadership support, greater understanding across the office is needed on why standard practices may not fit this type of programme. Purposeful has suggested adopting approaches used by other donors, such as bi-annual reporting, which could improve forecasting and reduce administrative burden. Both the BHC and Purposeful remain committed to finding solutions and maintaining open dialogue. Some challenges stem from the original grant structure and missed opportunities for core funding. Lessons noted in the previous AR – such as the value of an inception period – remain relevant.

For much of the year, the Programme Officer was also engaged in resolving HERA-related issues, including incorrect budget codes and an incorrectly recurring monthly prepayment. Resolution was slow due to capacity limits, unclear guidance, and delays in securing a consolidated view across different central teams, creating prolonged uncertainty around programme finances.

Narrative Reporting
Narrative reporting has continued quarterly and provides valuable context and analysis. The programme has shifted towards six-monthly reporting by agreeing that quarterly reports will alternate between detail on grantee partner activity and detail on Purposeful-driven activity. Continuation of this is reliant on sustained high-quality reports and maintaining regular engagement. Purposeful have raised that the level of engagement from the BHC on narrative reports can be overwhelming and add pressure to a stretched team. Both partners have had open dialogue on this and south to establish mutual understanding and expectations regarding comments/questions on narrative reports. Given the extensive level of learning calls and reporting done by grantee partners, both the BHC and Purposeful agreed it would be poor partnership practice to request further information from grant partners if not essential. Reports would benefit from clearer articulation of results and impact to better demonstrate effectiveness and represent grantee achievements, as highlighted in the last AR and in section G – particularly to support partners’ shared desire to demonstrate the critical importance of supporting WROs as part of Purposeful’s philanthropic advocacy, especially in the context of a shrinking ODA landscape.

Lessons and Recommendations
Recommendations from last annual review:
- [30] Purposeful should provide an updated asset register to BHC and work with the partner to ensure the security of these assets over the next quarter and before the next grant disbursement. Going forward, the BHC should ensure that the principles and objectives governing their asset management approach are well communicated, emphasising the need for accountability to the UK taxpayer and the communities they are intended to support. N/A: Purposeful decided to fund all assets and reallocate the funding, therefore no asset register is needed.
- [31] BHC and Purposeful should continue open dialogue on financial and programme management challenges. ONGOING.

Lessons:
MOVE’s experience this year reinforces the complexity of managing a locally led programme within FCDO’s compliance framework. Despite its relatively small budget, MOVE has required significant staff time due to tailored agreements, advocacy engagement, and the need for adaptive management. Both partners should maintain open dialogue on financial and programme management challenges, explore options to reduce administrative burden, and strengthen assurance mechanisms.

Recommendations for next year:
1. It is recommended that the BHC reviews recent updates to the PrOF in line with FCDO’s objectives on local leadership and considers how to apply these to the programme. The team should also engage FCDO central teams (Centre for Delivery and Commercial Grants Hub) on: 1) the systems barriers to local leadership and core funding for civil society identified (financial forecasting and reporting, contracting, accounting rules, and asset management); and 2) the need for clear escalation routes for complex systems issues that cannot be resolved by any one team.
2. It is recommended that both the BHC and Purposeful work together to come to a mutual understanding on financial management reporting needs, to reduce administrative burdens and provide assurance.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
The BHC has maintained active monitoring and learning through check ins and quarterly meetings with Purposeful, reviewing reporting and risk, participation in convenings, and grantee visits across districts (Kambia, Port Loko, Western Area Urban, Bombali and Moyamba) since September 2024. These engagements, including some with senior leadership, have strengthened relationships, programme oversight, and provided opportunities for direct learning from partners.

The last Annual Review recommended that the BHC team should join Purposeful’s learning visits to reduce burdens on grant partners and duplication. However, Purposeful have expressed preference for the BHC not to participate in these, citing the potential for BHC presence to change the dynamic of learning and that many learning ‘visits’ are now hybrid/not in person. While BHC visits have been ad hoc this period, a more intentional, structured approach for the final phase is recommended – including identifying key partners to meet, districts to visit, and themes to assess in the last phase of the programme, in partnership with Purposeful and grant partners.

Purposeful’s MEL approach remains flexible and partner-driven, which grantees value. In the convening observed as part of this review, an interactive session was used to decide learning headings for the next and final round of outcome/impact harvesting. This demonstrated the shared approach to decision making that Purposeful that take with grantees. However, there is a risk that the headings chosen don’t lead to products that fully capture and aggregate the scale of work and impact on SGBV at a community level. This may need to be compiled separately.

Despite recognising the implicit value of funding women’s rights organisations, there is understandable appetite and interest in their individual and respective impacts to prove concept and justify ongoing expenditure – including to support advocacy efforts. Outcome stories of change are important in demonstrating how grantees are using the funding to deliver change, but currently are limited in number and detail. As part of this review, grant partners shared further stories of change which could be collected more routinely through ongoing conversations with partners. The last AR recommended more formal assessment of outcomes and impacts, with a HelpDesk review suggesting options for proportionate but additional ways to further measure social change – outcome harvesting appears to remain the most valuable option. No further MEL methods have been incorporated at this stage due to capacity limits and prioritisation. AI tools could be considered to extract and collate impacts as part of a low resource approach. The quality of the stories could also be improved to ensure clarity for non-expert audiences unfamiliar with the context

The absence of an updated Demographic and Health Survey is highlighted as a sector-wide risk that limits progress tracking across violence and related programming. It is outside the programme’s scope to engage directly on this, but partners should monitor, and draw on, alternative data sources emerging from other partners or research institutions where available.

Evidence
The programme remains based on, and contributing to, a growing body of evidence on the relationship between women’s rights organisations and feminist movements and impact on addressing SGBV, promoting gender equality, and holding the line on rollback of rights. Both teams continue to track the evidence base and incorporate into the programme approach – this has substantially focused on understanding the changing dynamics of rollback of rights and has led to new partnerships and alliances to hold the line beyond the scope of this programme. Purposeful have published several learning and evidence documents (not funded from this programme), including on resourcing movement building,[14] transnational convening spaces,[15] the role of young women in crisis,[16] and resistance to anti-rights movements.[17] These have been of significant value to informing the BHC’s approach to this programme and wider advocacy.
[14] https://wearepurposeful.org/wp-content/uploads/2023/12/Black-Tuesday-publication-2023-291123-VLR.pdf
[15] https://wearepurposeful.org/wp-content/uploads/2024/01/The-Politics-of-Transnational-Convening-Spaces.pdf
[16] https://wearepurposeful.org/wp-content/uploads/2024/03/The-Active-but-Underfunded-Role-Young-Women-and-Girls-Play-in-Crises-Web.pdf
[17] https://wearepurposeful.org/wp-content/uploads/2025/05/Until-Everybody-Is-Free-rfs.pdf; https://wearepurposeful.org/wp-content/uploads/2025/07/LGBTQI-FINAL.pdf; https://wearepurposeful.org/wp-content/uploads/2025/07/FUNDERS-BRIEF.pdf

Learning
As set out in the previous AR and Purposeful’s learning agenda, learning is at the heart of this partnership and programme. Learning insights have particularly been used to shape the grant accompaniment of the programme. However, interviews with Purposeful confirmed that the learning agenda had been stripped back to core/minimal activities, in part due to a limited MEL budget. The programme would ideally have included a bigger budget for monitoring and evaluation to generate this and more fully resource the learning component.

Grant partners should be better supported to understand what systems should already be in place, and their own role in referral protocols, as well as to learn from the evidence base on what works and target their work to maximise impact, whilst acknowledging and respecting their expertise and contextual understanding. More learning reflection could be included on what works (and doesn’t work) in shaping grantee partners’ activities and this is a particular area where grant partners can learn from each other and share expertise and experience. This is already happening in some areas/relationships and is facilitated by the movement building aspects of the programme.

There is an opportunity to capture learning on what works to shift attitudes and behaviours to FGM/C in Sierra Leone and across the Mano River area (including Liberia and Guinea) where the practice is prevalent. An increasing number of grant partners are working on this issue and are exploring a range of approaches - from alternative livelihoods to rites of passage into adulthood performed by secret societies (Bondo) without cutting: “Bloodless Rites”. Grantees are also exploring the impact of a range of messaging from physical and emotional harm of FGM/C, the heightened risks of complications in childbirth, to the reduced sexual satisfaction for couples. A regional approach to learning and movement building would help to share lessons in what does and doesn’t work to address FGM/C, including the risk of unintended impacts; for example one grantee that was majoring on the physical harm messaging was not aware that this drove medicalisation of the practice elsewhere. A regional approach could also support awareness of, and efforts to address, emerging regional dynamics, whereby girls in Guinea are reported to travel to Sierra Leone for Bondo, and where girls from Sierra Leone (where child marriage has recently been made illegal) are now reported to cross the border into Guinea for marriage. The Forum Against Harmful Practices is a grantee under the programme and would be a key partner in building this regional approach and movement.

Learning continues to be shared within FCDO and the wider sector by both partners. In November 2025, Purposeful published a learning piece on the importance of flexible funding in survivor-led organising which draws on insights from the previous year.[18] The BHC team has leveraged opportunities to highlight programme and partnership lessons, including through internal discussions and putting forward partners to take part in strategic discussions (for example at Wilton Park). The BHC have fed in to updates to the FCDO’s PrOF guide on both locally-led development and consultation with representative groups. Both the BHC and Purposeful have agreed to develop a focused advocacy plan for the final phase of MOVE, sharing learning as part of influencing global funding for WROs. To leverage further learning, BHC should join one of the emerging working groups on local leadership, to shape ongoing reviews of FCDO policy and systems to better support local leadership and to share learning with the wider network. Learning on partnerships under output 5 has been held back by BHC capacity constraints, and there is a recommendation to increase SRO time on the programme to deliver this.
[18] https://we-are-purposeful.medium.com/the-importance-of-flexible-funding-in-survivor-led-organising-d99a9313ba87

Recommendations from last annual review:
- [1] BHC and Purposeful should continue open dialogue to identify proportionate and flexible modalities which provide adequate assurance for UK compliance requirements. Learning on this should be shared by the BHC within relevant FCDO communities of practice and cadres. MET.
- [2] There is more to do to translate MOVE’s learning and practice into wider influencing and advocacy – BHC and Purposeful should consider how to best leverage the partnership and learning, including ensuring impact is demonstrated with a robust theory of change and results framework/story. ONGOING: attention to this should be maximised in the final year of the programme, including finalising learning notes.
- [6] The BHC and Purposeful teams should continue to prioritise learning and demonstrating impact, including reviewing the theory of change, assumptions, and ensuring that future milestones and output indicators are jointly developed to best assess reporting on how access to grants has supported impactful work. The programme would benefit from more formal assessment and both Purposeful and the BHC team should explore opportunities to bring in additional light-touch MEL approaches, especially to measure outcome-level change in the coming period. The logframe should be updated to reflect recommendations from this document, six months before the next Annual Review. MODERATELY NOT MET.
- [32] Purposeful will conduct learning visits to all grant partners in their communities to deepen understanding of impact, context, challenges and opportunities, as well as enable the delivery of tailored accompaniment. FCDO should join these visits wherever possible to support their own monitoring and learning, whilst reducing the burden on grantees by avoiding duplicative visits. ONGOING.
- [33] It is recommended that the MOVE ToC is reviewed annually or at the mid-point of the programme to ensure that the interventions and causal pathways are mapped. NOT MET: although the ToC appears to remain valid.
- [34] The BHC and Purposeful should incorporate a limited number of additional MEL methods to ensure the social change driven by grant partners is captured to demonstrate the impact of giving flexible funding to WROs in support of the ToC. A form of outcome harvesting would be well suited to the responsive nature of grantees’ work or the examples that support milestones in the logframe could be adapted to most significant change case studies. Additionally. The BHC and Purposeful should explore whether there are opportunities to gather external views or evidence to complement partners’ self-reporting, six months before the next Annual Review. NOT MET.
- [35] The team should continue to track the evidence base and incorporate knowledge on what works into the programme, as well as contribute learning from the programme to the global evidence base. ONGOING.
- [36] Grantee partners, alongside Purposeful and the BHC, should be encouraged to learn from what does not work and grantees should be supported to test strategies and tactics to aid learning. ONGOING: but more should be done to systematise this.
- [37] There is early learning for the MOVE programme on community-level impact, as well as institutional learning for both partners on how participatory funders and movement builders, and bilateral donors can work together. The BHC and Purposeful should continue to discuss what tools and narratives will support this internal information sharing and influencing, including as per Output 5. MET/ONGOING.
- [38] It is recommended that the next annual review(s) is conducted by a colleague external to the BHC (e.g. through a 10%) to facilitate a more independent assessment and draw out wider learning for the BHC and Purposeful teams. MET: The reviewer was independent to the team, but chosen for their historical and current role – as the former Sierra Leone Social Development Adviser and programme designer and as the current policy lead on local leadership.

New recommendations
1. The BHC and Purposeful should prioritise collection of high-quality outcome stories and share learning on locally led delivery within FCDO. AI could be tested as a way of collating these.
2. Purposeful to conder ways to: better support grantees to understand the particular trends and dynamics in Sierra leone on SGBV; to build a local evidence base on what works to address these; and to learn from the global evidence base on what works to end SGBV. This is important to maximise impact.
This Annual Review was conducted in line with FCDO’s PrOF and ‘How to Note on Reviewing and Scoring Projects’. The review was led by a Social Development Adviser (who was previously posted in Sierra Leone) as part of a 10% contribution, with support from the PRO and SRO. The review methodology included:
- A desk review of key documents.
- A visit to Sierra Leone, to participate in/observe a convening and gather feedback from grant partners, through interviews with key Purposeful staff and four grant partners, conversations with several other grant partners throughout the two-day convening, and visits to three partners’ offices/spaces for discussions. A visit to one partner was cut short when they received a young woman requiring support – demonstrating firsthand how vital safe spaces for young people and survivors are.
- Review of draft report by the SRO, Team Leader, BHC Advisers, and Purposeful.
A significant part of this review was derived from the contribution of our grant partners and Purposeful staff, including through discussions and reports submitted – for which we are grateful.

Date of last narrative financial report	15 October 2025	Date of last audited annual statement	June 2025

Annex A: Theory of Change

Annex B: Consolidated List of Recommendations
1. The ToC and logframe should be reviewed and the team should consider updating the impact statement, and revising impact-level indicators, to better reflect the community and systems changes that are emerging. The outcome level indicators should also be reviewed to ensure these metrics clearly contribute to the overall theory of change and understanding of impact. This, in addition to recommendations in the MEL section to more fully capture grantee partners’ outcomes, will strengthen the programme’s demonstration of impact.
2. Purposeful to provide ongoing/further help to grantees to prioritise their efforts and limited resources in a way that speaks to their comparative advantage; to include exploring partnership opportunities with development actors with expertise in livelihoods and extreme poverty, who may be able to work directly with grantee communities or build capability among grantees in this space through dedicated convening time.
3. Purposeful convenings could usefully build grantee understanding of: SGBV response policy and protocols; the expectations of different service providers; the principle of survivor centred care; and grantees’ roles in signposting and community liaison rather than as SGBV responders and service providers, unless they are sufficiently trained and qualified. To support this, the BHC could explore further collaboration with the education sector/education programming to build grantees’ understanding of the policy/systems structures that should be in place in schools and recommendations for how to engage with schools, including engaging key partners in the School-Related GBV Coordination Committee. Purposeful could explore setting up a reporting system through the Ministry of Basic and Senior Secondary Education and continue to encourage grant partners to make/maintain contact with district level education leads.
4. Purposeful could support grantee partners to take their first hand understanding of the weaknesses in SGBV referral and response pathways and services to the district and national level and advocate for more effective gender-based budgeting that allocates sufficient resourcing to national governments ambition and strategic direction and policy commitments. This should cover gaps between policy and practice. The BHC should explore opportunities to use available levers to encourage clarity and coordination, and highlight issues related to SGBV national prevention and response, including to support the revival of the national level GBV coordination structure needed to drive and monitor implementation of national policies.
5. Purposeful to actively encourage grant partners to share other and new materials, such as the podcast on FGM. This could be covered at a convening or in the context of advocacy on certain issues.
6. Purposeful to consider connecting with some of the international organisations named in new FCDO guidance on protecting human rights defenders, with a view to securing future advice and support if an activists safety cannot be secured within Sierra Leone.
7. Purposeful to integrate content on protocol/handling of images and evidence as part of protection and safeguarding approaches.
8. BHC to update the logframe to reflect use of the survey rather than discussion to measure 4.1 and prioritise analysis of the survey responses, including sharing this back to Purposeful and grantee partners, in early 2026.
9. FCDO Centre for Delivery (CfD) to review this Annual Review and consider new templates and guidance on core funding for NGOs which make it clearer and easier for teams to explore as an option and alternative to more a projectised funding arrangements. FCDO CfD to review existing templates and revised language in a way that supports more equal partnerships. The BHC should seek a discussion with CfD and consolidate any PrOF updates or advice into the last year of the programe.
10. As above and as per the last AR, BHC to update the milestone for indicator 5.2, so that learning can be gathered through the AR process.
11. BHC to focus SRO time on learning, and to use this to generate the learning products with Purposeful and disseminate these with relevant groups across the FCDO through shared sessions with Purposeful. The teams could explore re-weighting this output to reflect the importance of wider learning.
12. BHC to ensure that any new approach to monitoring VfM should be proportionate to the size of the grant. A minimal approach could be taken that articulates which of the existing logframe indicators are being used to track the five “Es”. Alternatively, one or two additional indicators – integrated into the partnership assessment approach for ease – could work. Lessons could be sought by the BHC from a central programme supporting the Equality Fund on how its VfM has evolved.
13. The BHC and Purposeful should explore what efficiency savings could be achieved in the last year of implementation and decide whether to transition to core funding (if BHC risk appetite would support this) or expand the efficiency gains possible under current arrangements, for example through a transition to six monthly financial reporting.
14. Purposeful to confirm timeline for compliance with IATI publication.
15. In line with the PrOF the BHC should undertake a proportionate and light touch review of the DDA 2026, and relevant aspects refreshed if necessary.
16. It is recommended that the BHC reviews recent updates to the PrOF in line with FCDO’s objectives on local leadership and considers how to apply these to the programme. The team should also engage FCDO central teams (Centre for Delivery and Commercial Grants Hub) on: 1) the systems barriers to local leadership and core funding for civil society identified (financial forecasting and reporting, contracting, accounting rules, and asset management); and 2) the need for clear escalation routes for complex systems issues that cannot be resolved by any one team.
17. It is recommended that both the BHC and Purposeful work together to come to a mutual understanding on financial management reporting needs, to reduce administrative burdens and provide assurance.
18. The BHC and Purposeful should prioritise collection of high-quality outcome stories and share learning on locally led delivery within FCDO. AI could be tested as a way of collating these.
19. Purposeful to conder ways to: better support grantees to understand the particular trends and dynamics in Sierra leone on SGBV; to build a local evidence base on what works to address these; and to learn from the global evidence base on what works to end SGBV. This is important to maximise impact.