## Annual Review

Title: Knowledge for Development and Diplomacy
Programme Value £ (full life): £5m		Review date: Nov 2025
Programme Code: [AMP ID#] 400006	AMP start date: 17 Nov 2023	AMP end date: 31 Mar 2027

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003786.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005664.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Knowledge for Development and Diplomacy (K4DD) is funded and led by the International Science and Technology Directorate of the Foreign Commonwealth and Development Office (FCDO) and delivered by a consortium of development and diplomacy knowledge institutions. The Institute for Development Studies (IDS) is the lead partner. The consortium includes the University of Birmingham, Liverpool School of Tropical Medicine, the University of Manchester, the Royal United Services Institute, and the Association of Commonwealth Universities. The programme is funded through an Accountable Grant, which commenced in mid-October 2023 and will run until end-March 2027.

K4DD aims to provide timely evidence and learning to FCDO staff, which can be used to improve the impact of new and existing programmes and policies. Outputs are also - where possible - published on K4DD’s public-facing website, so they can be used by the wider development and diplomacy communities.

The service, which is open to all FCDO staff and free-at-the-point-of-use, comprises:
1. A Helpdesk, which allows staff to request Rapid Evidence Reviews, i.e. written syntheses of evidence on a specific topic or issue, produced within four weeks. Staff can also request Emerging Issues Reports (which go into greater breadth and depth and are completed within eight weeks) and Rapid Bibliographies (a list of sources with short abstracts). Finally, although not part of its formal offer, the Helpdesk now produces monthly Evidence Summaries on three topics (Humanitarian, Conflict, and Health) and is in the process of developing them on two more topics (Food & Agriculture and Education). These are lists of new evidence, with high level summaries and links.
2. An Expert Challenge and Learning Service, which offers two types of facilitated learning events. Expert Challenge Sessions are one-off seminars, bringing together a panel of internal and external experts for engagement and discussion on an issue or set of issues. Evidence and Policy Clinics take place over several months. Through a series of facilitated workshops, these bring together FCDO teams with external experts and are used to develop evidence-informed analysis of policy and programming challenges - and potential interventions.
3. Learning Products, i.e. bespoke outputs (such as presentations or resource packs) which are created to communicate selected outputs from the Helpdesk and Expert Challenge and Learning Service to FCDO staff and externally.

K4DD has been designed to respond to the evidence needs of staff from across FCDO, and for this it utilises both ODA and non-ODA funding.

This review covers the period from 1st October 2024 to 30th September 2025.

Summary supporting narrative for the overall score in this review

This programme scores an A, i.e. it has met expectations for the past year. Each of its three outputs scored an A, and its innovative and well-received AI tools trial represented a significant additional achievement: the trial is delivering value not only for K4DD but also for FCDO and HMG staff and the wider evidence synthesis community.

K4DD continues to deliver a well-used and highly valued Helpdesk. Although the number of Rapid Evidence Review units completed during the Annual Review period is below target, the service exceeded its target on numbers of Emerging Issues Reports – and the service delivered all RERs and EIRs that were requested (and were within scope). Reports have far exceeded their targets on quality and timeliness, and have covered a huge range of topics - many of which align with FCDO priorities such as irregular migration, climate and nature, and humanitarian. The breadth of topics covered can be explored by visiting the resources section of the website. K4DD’s Evidence and Learning Service has become more established and there has been increasing demand for its one-off Expert Challenge Sessions and longer-term, multi-event Evidence and Policy Clinics. Numbers of events completed have fallen slightly short of target, but a good number are in progress. Feedback from participants has been very positive and has far exceeded targets. Take-up of K4DD reports and other products by the wider development and diplomacy communities has been strong, with over 50,000 downloads from the externally facing website over the review period. As well as being on track to achieve its intended outputs, mid-point case studies indicate that K4DD is on track to achieve its intended outcomes and impacts: there are good examples of its services improving capabilities and being used to inform decision-making. K4DD has been flexible and responsive to significant changes in its operating context (for example, HMG’s planned reduction in ODA spending, and a diversification in the themes on which it receives commissions). The programme is a key part of the FCDO evidence offer and represents excellent value for money.

In addition to delivering on its core expectations (as set out above), this year K4DD has completed an innovative trial of the use of AI tools in the production of its evidence review products. The learning from the trial will not only benefit the programme itself but has also been used in well-received AI-focused events in FCDO and the wider HMG analytical community, and there has been good engagement with an IDS blog drawing upon its findings.

Major lessons and recommendations for the year ahead

Numbers of ODA and non-ODA commissions should be monitored closely, and communications should be tweaked to influence levels of demand where necessary.

The recent trend towards a more diverse range of commissions (with a particular increase in science and technology-focused queries) points to the need to a) support researchers with training and guidance in this area and b) better understand the requirements and needs of the FCDO staff who are commissioning these, since they tend to represent a new group of K4DD users.

Findings from the AI tools trial should continue to be disseminated and used to inform dialogue with partners on the role of AI tools in evidence reviews. Recommendations from the trial should be incorporated into Helpdesk work processes.

To reduce delays to scheduling, the Learning Service should continue to emphasise to users the importance of maintaining momentum when planning events. This could be done by referring prospective customers to the existing written guidance, and during early planning conversations.

The programme should explore the potential of convening K4DD-initiated online learning events - on FCDO priority topics - which would be open to both FCDO staff and external audiences. These would encourage access to K4DD’s existing reports, facilitate learning, and raise awareness of K4DD and its services both within and outside FCDO.

As part of its monitoring, evaluation, and learning activities, the programme should continue to build a strong bank of case studies which illustrate pathways to intended outcomes and impact.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

K4DD aims to improve the impact of development and diplomacy policy and programmes – primarily within FCDO, where service demand originates, but also in the wider development and diplomacy world.

The programme’s activities and outputs (i.e. Helpdesk reports, Expert Challenge and Learning Service events, and Learning Products) are designed to:
- support high-quality, relevant, and timely learning
- create opportunities to stimulate discussion and reflection among FCDO staff and K4DD partners
- strengthen knowledge and networks within FCDO and with K4DD partners

As a result, individuals, teams, and the organisations involved will gain improved capabilities, and effectively use quality evidence and learning to inform and improve their programmes and policies.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Performance data gathered so far tell us that K4DD is producing high quality and timely outputs as expected. These data are set out in Section C. Mid-point case studies illustrate pathways to the intended outcomes and impact. For example:
- For the UK-Kenya Tech Hub, timely access to a Rapid Evidence Review provided credible research that helped to shape its flagship Small and Medium Enterprise financing programme.
- A Rapid Evidence Review on the African Union’s peace and security architecture has helped inform FCDO’s evolving approach to engagement with the AU - contributing to how the UK supports conflict prevention, governance, and mediation on the continent.
- Through Expert Challenge Sessions and a Rapid Evidence Review, K4DD has helped FCDO move from isolated insights to a shared, evidence-based understanding of serious and organised crime in Africa. The sessions created trusted spaces for FCDO teams and external experts to reflect, debate, and collectively shape strategic direction.
K4DD will continue to build a collection of these case studies, and at the end of the programme a subset will be selected for a deeper dive to show how it has influenced and contributed to higher level changes (such as improved capabilities, evidence use, and improved programme and policy design).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

K4DD should continue. It is meeting demand for evidence reviews, learning events, and learning products. It is a key part of the evidence offer within FCDO and complements its other services well. There is good evidence that the programme represents excellent value for money.

## C. DETAILED OUTPUT SCORING

Output Title	K4DD outputs are produced to quantity, quality, and timeliness standards.
Output number:		1	Output Score:	A
Impact weighting (%):		45%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Quantity: Number of Rapid Evidence Reviews (units), and Emerging Issue Reports delivered per year	Rapid Evidence Review units: 220 / Emerging Issues Reports: 6	Rapid Evidence Review units: 173 / Emerging Issues Reports: 8 / The figures above comprise: / Q3 24/25: 30 RER units & 1 EIR / Q4 24/25: 48 RER units & 3 EIRs / Q1 25/26: 48 RER units & 1 EIR / Q2 25/26: 47 RER units & 3 EIRs
1.2 Timeliness: Percentage of Rapid Evidence Reviews and Emerging Issue Reports delivered within the timeframes agreed with service users	75%	98% (n=41) / The figures above comprise: / Q3 24/25: 100% (n=7) / Q4 24/25: 100% (n=10) / Q1 25/26: 100% (n=18) / Q2 25/26: 83% (n=6)
1.3 Quality: Percentage of Rapid Evidence Reviews and Emerging Issues Reports rated in the top two out of five quality grades among survey respondents	60%	85% (n=39) / The figures above comprise: / Q3 24/25: 71% (n=7) / Q4 24/25: 90% (n=10) / Q1 25/26: 88% (n=16) / Q2 25/26: 83% (n=6)
[note] Most Rapid Evidence Reviews are single unit reviews. Occasionally a review will be a double unit review. For the purposes of the Annual Review, we measure units, not numbers of reviews. All Emerging Issues Reports are single unit reports.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is about the K4DD Helpdesk, through which FCDO staff can request Rapid Evidence Reviews (RERs) and Emerging Issues Reports (EIRs).

Between 1st October 2024 and 30th September 2025, 173 RER units and 8 EIRs were delivered, against targets of 220 RER units and 6 EIRs. Overall, K4DD has not met its target on quantity of RER units but has exceeded its target on quantity of EIRs. The service delivered all RERs and EIRs that were requested and were within scope.

K4DD is exceeding its targets on both timeliness and quality. 98% of reports for which feedback was gathered were delivered within the agreed timeframes, compared to a target of 75%. 85% of reports for which feedback was gathered were rated in the top two quality grades, compared to a target of 60%. Note that these figures are based on feedback for 41 (timeliness) and 39 (quality) of the completed reports.

Qualitative insights collected through the mid-point case studies exercise revealed the following reflections from Helpdesk users:

“The report provided access to timely, expert and tailored analysis wrapped in a fantastic package”

“It’s so great to have access to external experts for quick turnaround reports of this type”

“The report consolidated a large amount of information in a clear way. It was very useful to have case study examples that as a team we can draw on. The report provides us with an excellent starting point for future research”

Although not part of its formal offer, the Helpdesk now produces monthly Evidence Summaries on three topics (Humanitarian, Conflict, and Health) and is in the process of developing them on two more topics (Food & Agriculture and Education). These are monthly lists of new evidence, with high level summaries and links. They represent excellent value for money (all five can be produced with the equivalent resource to one Rapid Evidence Review) and have been very well-received by the Heads of Profession that commissioned them.

The review period saw the following progress, which underpinned the achievements of the Helpdesk:
- K4DD was officially launched on 30th September 2024: over a period of two weeks in October, the service carried out a range of carefully planned communications activities. These included targeted emails, additions to regular circulars (such as Around the World and the RED Director’s update), social media posts, and the publication of blogs, talking heads videos, and newsletters.
- Although K4DD’s non-ODA offer could not be promoted in the above launch (due to an absence of budget at that time), subsequent communications to diplomacy-focused audiences appear to have been successful: in recent months the service has seen a significant increase in non-ODA commissions, particularly in the science and technology area.
Key challenges for the Helpdesk during this period were:
- Fluctuations in demand, which are observed when analysing Helpdesk commissions on a weekly basis - but which even out over a quarterly basis. These could have been linked to events such as Country (and central Directorate) Business Planning.
- Planned reductions in HMG’s ODA spending, announced in February 2025, have led to a more uncertain context.
- The patchy and unpredictable nature of non-ODA funding, particularly for the first six months of the review period. (The programme did not have non-ODA funding from October to December 2024. In January 2025 it was awarded a modest allocation of non-ODA funding for spend by end-March 2025. However, in April 2025 a healthy non-ODA budget for use by end-March 2026 was confirmed.)
- The trend for an increased number of queries on themes that are new-to-K4DD, such as science and technology, points to a need to a) develop the consortium’s capacity and capabilities and b) better understand the requirements and needs of the FCDO staff who are commissioning these.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the output indicators or targets in the review period. We do not recommend any changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the second Annual Review.

The first recommendation from the previous Annual Review was about the need to manage Helpdesk demand, e.g. by redirecting out-of-scope requests to other evidence services and keeping the scale of review requests to within the allocated research time. These principles have been applied, and although demand has fluctuated on a week-by-week basis, the service has consistently been able to meet that demand.

The second recommendation from the previous Annual Review was to explore the potential for AI tools to be used in K4DD’s Helpdesk reviews. K4DD secured funding from within FCDO and a formal trial was carried out between September 2024 and April 2025. This has been a highlight for the programme this year, with recommendations to be applied to Helpdesk operations from October 2025 onwards.

Lessons learned this year, and recommendations for the year ahead, are:

1. Numbers of ODA and non-ODA commissions should be monitored closely, and communications should be tweaked to influence levels of demand where necessary.
2. The recent trend towards a more diverse range of commissions (with a particular increase in science and technology-focused queries) suggests there is a need to a) support researchers with training and guidance in this area and b) better understand the requirements and needs of the FCDO staff who are commissioning these, since they tend to represent a new group of K4DD users.
3. Findings from the AI tools trial should continue to be disseminated and used to inform dialogue with partners on the role of AI tools in evidence reviews. Recommendations from the trial should be incorporated into Helpdesk work processes. These include:
- Develop and communicate a K4DD position statement on use of AI in research.
- K4DD researchers to develop new approaches involving a combination of AI-informed and non-AI-informed methods and be supported to identify and mitigate ethical and legal risks.
- K4DD researchers to document the research process to record how AI tools have been used and be supported to critically evaluate the outputs of AI tools.

Output Title	Learning is enhanced through effective engagement with the Expert Challenge Sessions, Evidence and Policy Clinics, and Learning Products
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Quantity: number of Expert Challenge sessions delivered per year	4	2 completed / 3 in progress / The ‘completed’ figure above comprises: / Q3 24/25: 1 / Q4 24/25: 1 / Q1 25/26: 0 / Q2 25/26: 0
2.2 Quantity: number of Evidence and Policy Clinics delivered per year	2.5	2 completed / 2 in progress / The ‘completed’ figure above comprises: / Q3 24/25: 1 / Q4 24/25: 1 / Q1 25/26: 0 / Q2 25/26: 0
2.3 Quality: % of EPC and ECS that report effective engagement and learning among participant sample	60%	100% / The figure above comprises: / Q3 24/25: 100% (n=8) / Q4 24/25: 100% (n=7) / Q1 25/26: N/A / Q2 25/26: N/A
2.4 Quality: % of participants reporting ECS/EPC events were effective in building shared understanding across groups	60%	100% / The figure above comprises: / Q3 24/25: 100% (n=8) / Q4 24/25: 100% (n=7) / Q1 25/26: N/A / Q2 25/26: N/A
2.5 Quantity: number of Learning Product units delivered per year	12	7.5 units completed / 8.75 units in progress / The ‘completed’ figure above comprises: / Q3 24/25: 1.5 / Q4 24/25: 3.25 / Q1 25/26: 1.25 / Q2 25/26: 1.5

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is about the K4DD Learning Service, through which FCDO staff can request Expert Challenge Sessions (ECSs), Evidence and Policy Clinics (EPCs), and Learning Products (LPs).

Between 1st October 2024 and 30th September 2025, two Expert Challenge Sessions were completed, and three others were in progress, against a target of four completed ECSs. Two Evidence and Policy Clinics had been completed, and two were in progress, against a target of 2.5 completed EPCs. 7.5 units of Learning Products were delivered, with 8.75 further units in progress, against a target of 12 completed LPs. Overall, although K4DD has not met its targets on completed ECSs, EPCs, or LPs, the numbers in progress suggest that K4DD will catch up on delivery expectations. It is worth noting that the programme’s reporting cycle is based on the April to March period, and had the Annual Review period aligned with this, the targets would likely have been met.

Feedback on the completed ECSs and EPCs indicates that participants in all of them experienced effective engagement and learning, and that all respondents reported that ECS/EPC events were effective in building shared understanding across groups.

Qualitative insights collected through the mid-point case studies exercise revealed the following reflections from Learning Service users:

“The Expert Challenge Session [on Migration and Serious and Organised Crime] gave us the opportunity to discuss this important issue with a wide range of researchers, and experts, and will influence policy debate about migration, human smuggling and trafficking”

“Great mix of presentation, discussion and use of the mural board… [The Expert Challenge Session on Health Equity was a] good opportunity for us to step away from our inboxes and think about an important issue and how we can better implement it”

The review period saw the formal launch of K4DD, which helped to underpin the achievements of the Learning Service. In addition, there was the following Learning Service-specific progress:
- The service held its first in-person event: a very well-received Expert Challenge Session on Serious and Organised Crime in Africa, hosted at RUSI.
- There was a notable increase in interest in the service, likely linked to communications and greater awareness of its offer, as well as the service becoming more established.
Key challenges for the Learning Service included an absence of non-ODA funding for the first three months of the review period, and an uncertain context caused by planned reductions in HMG’s ODA spending, which were announced in February 2025. Learning Service-specific challenges included:
Scheduling and FCDO capacity: FCDO staff have been enthusiastic and engaged with the planning for Learning Service events, but busy calendars and staff turnover have resulted in delays to scheduling. This is a key reason why more ECSs and EPCs have not yet been completed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the output indicators or targets in the review period. We do not recommend any changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the second Annual Review.

The previous Annual Review recommended that the EPC guidance should be updated to reflect the longer-than-originally-anticipated time that EPC activities typically take to be completed. This has been actioned.

This year, it is recommended that:
1. To reduce delays to scheduling, the Learning Service should continue to emphasise to users the importance of maintaining momentum when planning events. This could be done by referring prospective customers to the existing written guidance, and during early planning conversations.
2. The programme explores the potential of convening K4DD-initiated online learning events - on FCDO priority topics - which would be open to both FCDO staff and external audiences. The content would be based on recently commissioned K4DD reports, and discussion would be led by expert panellists from within and outside HMG. It is envisaged that the events would encourage access to K4DD’s existing reports, facilitate learning, and raise awareness of K4DD and its services both within and outside FCDO.

Output Title	Wider learning and use of evidence is enhanced through effective uptake and use of K4DD products.
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Uptake: % increase in number of downloads of reports and products in the IDS OpenDocs repository	15% increase	53,251 downloads / The figure above comprises: / Q3 24/25: 4,342 downloads / Q4 24/25: 7,817 downloads / Q1 25/26: 14,484 downloads / Q2 25/26: 26,608 downloads / This is the first full year for which data have been collected, so it is not possible to measure year-on-year change.
3.2 Uptake: % increase in number of K4DD engagements on X, BlueSky, and Linkedin	40% increase	4,405 engagements / The figure above comprises: / Q3 24/25: 1,677 engagements / Q4 24/25: 960 engagements / Q1 25/26: 1,047 engagements / Q2 25/26: 721 engagements / This is the first year for which data have been collected, so it is not possible to measure year-on-year change.
3.3 Uptake: % increase in number of citations of published Rapid Evidence Reviews & Emerging Issue Reports	20% increase	4 citations / This is the first year for which data have been collected, so it is not possible to measure year-on-year change.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is about uptake and use of K4DD outputs by the wider development and diplomacy communities, which is a key objective of the programme.

Between 1st October 2024 and 30th September 2025, K4DD reports, and other products were downloaded from the website 53,251 times. The same period saw a total of 4,405 engagements on the programme’s social media channels (LinkedIn and BlueSky, which has been used by IDS instead of X since February 2025), and four recorded citations. Possible reasons for the low number of citations are that a) journal articles – through which citations are recorded - typically take many months to be published, and b) article authors may cite primary studies included within a K4DD review, rather than the review itself. K4DD was formally launched at the beginning of the Annual Review period, and so this is the first year for which data have been collected, and it is not yet possible to measure year-on-year change.

As described in Output 1, the review period saw the formal launch of K4DD, which included external communication activities. These encouraged the awareness and use of K4DD outputs by the wider development and diplomacy communities. In addition, there was the following external uptake-specific progress:
The publication permissions rate has been improved by adding a question on this to the Helpdesk commissioning template.

Key challenges for the external uptake and use of K4DD reports and products were:
Engagement via social media platforms. Initially, X was the primary means of social media engagement; IDS has now moved to BlueSky and this has resulted in lower engagement figures. LinkedIn is now the primary means of social media engagement; this is proving successful, but it will take time to build up presence.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Other than recording engagement on BlueSky rather than X (since IDS’s X accounts have been discontinued), there have not been any changes in the past year. We do not recommend any other changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

This is the second Annual Review.

The previous Annual Review recommended that options for improving the publication permissions rate for Helpdesk outputs should be explored. The Helpdesk introduced a new question to the commissioning template, so now people are asked before work starts whether they are content to publish or not, or whether they want to take a decision after the report is complete. This has had a positive effect on numbers of reports approved for publication.

This year, it is recommended that the programme should continue to monitor the publication permissions rate.
## D: VALUE FOR MONEY

Key cost drivers and performance
K4DD’s key cost drivers are:
- Programme management and administrative overheads: fees and expenses associated with IDS’ operations and management of K4DD.
- Researcher time and expertise: direct financial commitments for engaging researchers, which varies depending on request complexity, required expertise and availability.
- Programme Delivery and Quality Assurance: costs associated with organising Learning Services, managing turnaround times for special reviews, and M&E for programme effectiveness and value for money.
VfM performance compared to the original VfM proposition in the business case

Business Case proposition on Economy – focuses on average cost per rapid evidence review (RER), benchmarked against similar programmes; overheads and management costs as a percentage of programme spend; the value of in-kind contributions and other savings by delivery partners.

Performance: K4DD’s average cost per RER is highly competitive. This RER synthesis model offers access to research and expertise at a lower cost, compared to higher costs typically associated with direct contracting of subject matter experts or commissioning bespoke research. K4DD unit costs are fixed and transparent (dating back to 2016), providing clarity on expenditure but also benchmarked favorably against similar models, despite inflation. As well as its regular RER reports, the service now produces monthly thematic Evidence Summaries on three (soon to be five) topics. Five monthly evidence summaries are delivered within a single RER unit, reflecting substantial VFM.

K4DD is committed to minimizing overheads and management costs as the management structure is deliberately lean, with a small central team working closely with FCDO. Leadership is further subsidized by IDS, contributing additional staff and resources without recouping these as direct programme costs. The Director of Evidence and Impact supplements his minimal annual days allocated to the programme with IDS overhead-funded time, lowering the chargeable proportion of senior management costs.

K4DD benefits from in-kind contributions and cost-savings provided by delivery partners by leveraging the specialist advice and expertise of its standing team and wider expert networks, both within and beyond the core consortium at no extra cost.

Finally, K4DD’s flexible budgeting approach means that each unit can encompass multiple outputs such as four blogs per Learning Product, thereby optimizing resource use and ensuring that more learning and evidence is disseminated across FCDO for each unit of investment.

Business Case proposition on Efficiency – Customer satisfaction with rapid evidence reviews; quality checks by FCDO's K4DD Technical Lead of a sample of rapid evidence reviews; average turnaround time for a standard (6-day) rapid evidence review.

Performance: Over the years, K4DD has refined and advanced its processes and structures, building on those established by its predecessor, K4D, resulting in high levels of both efficiency and effectiveness. Updated guidance notes for the helpdesk and ECLS services were released in July 2025. Standard completion time for RERs is six to twelve days; and for urgent requests, the K4DD team is committed to meeting policy deadlines, including work on weekends and bank holidays as required.

Regarding customer satisfaction, responses from the helpdesk users have been extremely positive. For the period under review, 85% of users who provided feedback have rated the perceived quality, clarity and usefulness as “excellent” and “very good”, meaning their needs have been fully, or largely met.

The K4DD governance system facilitates process efficiency through collaboration between FCDO and IDS, allowing for prompt and joint decision-making regarding incoming queries. This arrangement ensures that FCDO’s needs are prioritized across K4DD’s offering.

Business Case proposition on Effectiveness – Percentage of rapid evidence review requested (customers) who report using findings in decision-making; qualitative evidence that rapid evidence reviews influence policies, HMG influencing or programme designs.

During the review period, 35% of customers who provided survey feedback in the immediate period after receipt of their RER said that they had already used the report to inform policy decisions. 42% indicated that they had used the report to inform programme or project design. 75% had shared the report with colleagues, and 60% had used the report to inform internal discussions. K4DD also solicits survey feedback from Helpdesk users six months after receipt of reports. Unfortunately, response rates are low. However, the programme has interviewed users to record qualitative stories of change in influencing policy, programmes and other HMG priorities, and two of these are described below.

One story of change highlights K4DD’s RER on the African Union’s peace and security architecture played a vital role in shaping the FCDO’s approach to working with the AU. The review validated the observations of FCDO staff, and prompted FCDO to shift its strategic focus, moving away from purely technical support to prioritising AU’s political use of early warning, encouraging dialogue and enhancing mediation. The credibility of the K4DD RER also enabled FCDO to confidently adjust its programme portfolio and facilitated better coordination with partners like the World Bank, ensuring efforts were aligned and not duplicated. Importantly, this work influenced the development of an upcoming Business Case for future engagement with the AU, demonstrating a direct progression from evidence to strategic influence. Beyond operational changes, the process fostered a cultural shift within the FCDO, encouraging a move from focusing solely on capacity gaps to co-designing initiatives based on shared priorities with the AU. This approach anchored UK support in mutual trust and interest, marking a transition to a more proactive and equitable partnership, underpinned by evidence-based learning.

Another story of change focuses on a K4DD RER which accelerated the development and expansion of Kenya’s SME financing programme. The review identified key barriers and enabled the Hub to confidently scale its operations from 11 to 22 countries, double training numbers and foster collaboration with banks and government bodies. This RER led to a substantial increase in debt financing for participating SMEs, validated its strategy and strengthened stakeholder engagement, K4DD’s timely and rigorous input transformed anecdotal insights into actionable knowledge, empowering the Tech Hub to drive meaningful and lasting change for SMEs in Kenya.

BC proposition on Equity – number of rapid evidence reviews and challenge sessions on topics that enhance equity, e.g., social protection, girls’ education and women’s economic empowerment; customer satisfaction with these challenge sessions and rapid evidence reviews; number of rapid evidence reviews and expert challenge sessions that consider gender, disability or wider social inclusion.

K4DD has developed 34 Rapid Evidence Reviews (RERs), 1 emerging Issues Report (EIR) and 1 Evidence Policy Clinic (EPC), addressing various gender-related topics, including women’s political empowerment, pathways to women's economic involvement in social protection, mapping evidence on gender equality and social inclusion data, women's economic empowerment, the impacts of climate change on women and girls, and indicators of gender equality in education and sexual and reproductive health, among others. In addition to addressing these cross-cutting issues, K4DD demonstrates its commitment to equity by engaging with a broad spectrum of topics that encompass diverse geographical regions and areas of concern, focusing on both major development and diplomatic challenges. These requests span diverse regions, including Africa, South America, Asia, North America, and countries like Senegal, Argentina, Paraguay, Ecuador, Cuba, Mexico, India, Pakistan, Jordan, Malawi, Tanzania, Saudi Arabia, UAE, and Bosnia and Herzegovina. The consortium of K4DD brings together a wide range of expertise, facilitating inclusive and comprehensive perspectives.

Alongside its thematic offerings, K4DD addresses both ODA and non-ODA requests, ensuring it remains a comprehensive service accessible to all users. This strategy is especially relevant as FCDO undergoes strategic changes with the shift to 0.3%. Retaining a non-ODA budget enables equitable access for a range of stakeholder groups.

Assessment of whether the programme continues to represent value for money
Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, there is sufficient evidence to support the continuation of the K4DD programme.

From a VFM perspective, the programme demonstrates strong performance across the core 4Es pillars. Overall, the stories of change provide compelling qualitative evidence that K4DD’s Rapid Evidence Reviews and facilitation of ECS have materially influenced policy, HMG’s approach, and programme design. They highlight the value of evidence-based learning in supporting strategic realignment, collaborative policymaking, and more effective and equitable partnerships. When considered as part of the wider departmental portfolio, K4DD’s flexible, responsive, and cost-effective service model continues to deliver strategic value, underpinning key priorities and supporting evidence-based decision making across FCDO and HMG. There is no need for restructuring or closure; on the contrary, K4DD’s programme’s strengths and positive outcomes suggest that it should be maintained and, where appropriate, further leveraged as a central component of FCDO’s evidence and learning offer. Continued investment in K4DD will ensure that FCDO and HMG remain well-positioned to respond to emerging policy changes with high-quality, timely and equitable services.

E: RISK

Overview of risk management

The overall risk rating for K4DD is ‘Moderate’ and it remains unchanged since the last Annual Review. All risks and mitigations outlined in the Business Case continue to be relevant.

During this Annual Review period, the FCDO programme team have continued to review and update the risks register on the Aid Management Platform (AMP) in line with PrOF rules and the current risk profile of the programme in the reporting period.

Risk management in the programme is implemented through established protocols for regular identification, assessment, and escalation when required. The K4DD governance structure includes weekly meetings with implementing partners, weekly check-ins with the FCDO programme team, and quarterly Advisory Group meetings. These processes support risk identification, mitigation, evaluation of mitigation strategies, and monitoring of emerging risks to maintain accountability and ensures the programme operates within its defined risk appetite.

Key risks this year include:

Reduced demand during a period organisational change Whilst the consortium is able to respond to changing priorities, it is a risk that requires considerable monitoring and communication between IDS and FCDO.

Non-ODA availability: K4DD had no non-ODA budget for much of the preceding fiscal year which meant that requests were rejected. This created a precedent of uncertainty that is impacting demand especially as K4DD received a healthy non-ODA budget this financial year. Additionally, the non-ODA allocation for this year is significantly higher than the original baseline which creates a risk of underspending. If not fully utilised, it may signal inefficiency or the lack of viable projects, which could deter future funding opportunities and could impact the programme’s ability to secure non-ODA funding in future years. FCDO and IDS have worked collaboratively to effectively communicate the availability of funds, ensuring that stakeholders are aware of the increased budget and encouraged to submit requests.

Emerging themes: K4DD has observed new themes emerging as Government priorities evolve. There is a growing focus on science and technology topics, which are new to K4DD. Risk management is supported through the governance structure where these issues are examined and solutions are considered, such as enhancing the consortium’s capacity and capabilities in these areas; initiating informal discussions with new users to understand their needs and requirements; and maintaining adaptability as these changes continue.

The key risks above, and the wider set of programme risks identified in the risk register, have remained within the appetite, and will be monitored to ensure that mitigation measures remain appropriate and proportionate. All risks considered to be above the appetite are escalated to the Head of Department through the K4DD SRO.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Budget Overview:

Year 1 (Q3 & Q4 FY24/25)

	Allocated Budget	Total Spend	Variance	Comments
ODA	£750,000	£616,614	£133,886	Since there was no non-ODA for most of this FY, ODA spending exceeded the baseline of £1.2m per year, which would be £600k for two quarters. K4DD met these financial targets during the period.
Non-ODA	£64,000	£63,469		K4DD received a small amount (£60,000) of non-ODA in Q4 of last FY to be spent by March 2025.

Year 2 (Q1 & Q2 FY25/26)

	Allocated Budget	Total Spend	Variance	Comments
ODA	£700,000	£508,000	£192,000	£700k is half the annual allocation, exceeding the £600k baseline for two quarters, since K4DD received £1.8m (£1.4m ODA/£0.4m non-ODA) instead of the recommended £1.5m yearly. Q2 spend is currently a forecast only, as actual figures were unavailable when drafting this report.
Non-ODA	£200,000	£140,000		£200k represents half of our annual allocation for non-ODA this FY.

FCDO performance highlights:
K4DD’s total budget for its life span is £5m distributed based on a BC suggestion as follows:
- £0.5m - Inception phase
- £1.5m - Year 1 (20% of which is non-ODA)
- £1.5m - Year 2 (20% of which is non-ODA)
- £1.5m - Year 3 (20% of which is non-ODA)
To date, K4DD has utilised 44% of its total budget, a notable achievement given the challenges encountered during the inception phase, including a delayed launch that limited visibility and service delivery, absence of non-ODA funding in Year 1, fluctuating demand, ODA reductions, shifts in government priorities, and newly arising themes and pivots.

FCDO’s governance framework has supported this progress through regular weekly meetings and check-ins, providing proactive financial guidance to the IDS team, and transparent risk communication, which facilitates the development of rapid mitigation strategies. These consistent interactions ensure that the FCDO team remains fully apprised of all programme risks and can escalate issues as necessary.

Partner performance highlights:

IDS consistently exhibits robust financial performance management. After multiple refinements to the financial report's format, the team has produced a comprehensive document that offers enhanced transparency and clarity regarding expenditure performance.

Due to the dynamic nature of demand, forecasts must be continually revised to maintain accuracy, particularly in the context of current budget reductions. This process is supported by ongoing, open communication within the IDS team, who continue to display adaptability and proactive engagement in addressing changes and implementing recommendations from the FCDO programme team.

Conclusion:
The programme has demonstrated strong overall performance, with IDS showing effective grant management, flexibility, and transparency in the implementation of K4DD, all of which have supported the smooth operation of the programme to date. The collaborative governance structure particularly regarding financial reporting and communication has been instrumental in addressing challenges such as budget limitations and variable demand.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Monitoring and evaluation activities can be summarised as follows:

Output 1: Helpdesk

K4DD records data on the numbers and characteristics of all Rapid Evidence Reviews and Emerging Issues Reports that are requested and completed. This information is sent to FCDO each week, and any concerns are flagged and discussed at a weekly check-in meeting. The information is also summarised and reported on in quarterly reports.

In addition, two surveys (one immediately post-report completion, and one six months later) are sent to Helpdesk customers. The first survey captures data on the relevance, quality, timeliness of the service, and the data are summarised and reported on in the quarterly reports. This survey, and the second survey, also capture data on customers’ use or intended use of their RER or EIR. These data are analysed alongside insights from an annual round of key informant interviews. Learning - focusing on how the Helpdesk reports have supported FCDO’s work, what the most significant contributions have been, and the enabling conditions and barriers to applying learning from the reports – will be presented annually.

Finally, whenever a review receives poor feedback (whether through the formal feedback process or informally), the team explores the reasons for this and captures learning in order to make improvements.

Output 2: Expert Challenge and Learning Service

K4DD records data on the numbers and characteristics of all Expert Challenge Session and Evidence and Policy Clinics. The information is summarised and reported on in quarterly reports.

Then, for each event delivered in the first year of the programme, tools including feedback forms, key informant interviews, and documentation review are used to explore the quality of design, the quality of the process, and the effectiveness of the process. Information is presented in summary reports for each event.

All events to date have been highly rated by participants, but if poor feedback is received for future events, the team will explore the reasons for this and capture learning in order to make improvements.

Output 3: External Engagement

External engagement will be monitored through a combination of:
1. Downloads of reports and other products from the K4DD website
2. User analytics from K4DD’s BlueSky and LinkedIn accounts
3. Citations of published Rapid Evidence Reviews and Emerging Issues Reports
Pathways to Outcomes and Impact

As well as the output monitoring data described above, as the programme progresses the K4DD team will collect and analyse data on whether K4DD is leading to higher-level changes (such as improved capabilities, evidence use, improved programme and policy design). Information and user testimonies will be provided when evidence of early and medium-term outcomes is observed. Some of these have recently been compiled as we are now at the programme mid-point. At the end of the programme a series of deep-dive case studies will explore how K4DD has influenced and contributed to higher level changes.

Annual Review approach

The Annual Review has been written by the FCDO programme team, with review and contributions from the IDS team, and an FCDO member of the Advisory Group.

Evidence

Monitoring has been progressing as expected so far. A formal evaluation is not planned.

Learning

See above for planned learning activities on the Helpdesk and Expert Challenge and Learning Service.

In addition, this year K4DD ran a trial of the use of AI tools in the production of its evidence review products. Learning from the trial will be incorporated into the Helpdesk’s work processes, as well as being shared more widely with FCDO, HMG, and external researchers and research commissioners.

Date of last narrative financial report	31 July 2025	Date of last audited annual statement	31 March 2025