Programme Completion Review

Title: UK Emergency Humanitarian Response to the Earthquakes Affecting Turkey and Syria
Final Programme Spend £ (full life): £15.24m (30/06/2024)	Review Date:	June 2024
	Start Date: 08/02/2023	End Date: / 30/06/2024

Summary of Programme Performance

Year	2023-2024
Programme Score	A
Residual Risk Exposure Rating	Moderate

DevTracker Link to Business Case (and any addendum):	DevTracker Programme GB-GOV-1-400009 Documents (fcdo.gov.uk) / D0004691.odt (live.com)
DevTracker Links to all logframes used during programme lifetime:	DevTracker Programme GB-GOV-1-400009 Documents (fcdo.gov.uk) / D0004813.xlsx (live.com)

A. Summary and Overview

Context
On the 06 February 2023 two major earthquakes struck southeast Turkey near the Syrian border, impacting 13 million of Turkey’s 85 million citizens, 50,399 people were reported killed, 108,000 injured and 3 million displaced, although actual numbers were likely higher. There was widespread damage and destruction to more than 298,000 buildings and 220,000 businesses across 10 provinces. Access to Water, Sanitation and Hygiene (WASH) services was severely impacted for people living in the earthquake-affected region. The earthquakes damaged 365 km of potable water supply lines, 500 km of water networks, 200 km of sewer networks, four water treatment plants in affected areas as well as seven wastewater treatment facilities. Overcrowded temporary accommodation centres, limited access to water and sanitation facilities, critical hygiene and dignity items, lack of clean drinking water, improper waste and debris management in temporary settlements including in the city, posed risks to outbreaks and other health hazards. The earthquake created widespread and acute humanitarian needs exacerbating the existing needs in the region where 1.7 million of the total 3.5 million Syrian refugees hosted by Turkey reside. Due to the unprecedented scale of the disaster, the Government of Turkey requested international humanitarian assistance and the UN subsequently launched a Flash Appeal seeking $1 billion (£791 million) from February to May 2023.

Description of the programme and achievements
The British Embassy in Ankara responded to the crisis in a timely and proportionate way. £17 million was allocated for a nine-month period to support coordinated life-saving humanitarian assistance and early recovery work. The UK’s humanitarian response focused first on the provision of urgent lifesaving assistance, namely immediate life-saving rescue, and provision of shelter and emergency medical assistance. Later, national and international humanitarian assistance was scaled-up to help meet the basic needs of disaster-affected populations in support of the Government of Turkey’s (GoT) relief efforts through principled humanitarian relief and protection for vulnerable groups and support to early recovery.
[note] £17m includes £4.7m support to the people affected by the earthquake inside Syria.

To complement the government-led earthquake response, and based on evidence from needs assessments, the FCDO provided funds to humanitarian partners to implement timely relief interventions in health, protection, water, sanitation, and hygiene and stabilisation interventions in waste management, social services for vulnerable groups and cash to meet basic needs. FCDO also provided support to strengthen the overall international humanitarian response architecture, specifically enabling services to promote accountability and maintain the dignity of people affected by earthquakes, and support to bolster UN staff capacity through the Standby Partnership (SBP) as well as Humanitarian to Humanitarian (H2H) networks.

The UK’s allocation was divided into three humanitarian workstreams:
Immediate rescue, relief and medical needs were met through the deployment of specific UK humanitarian capabilities (£6.05 million):
- £1m for International Search and Rescue (ISAR): 77-person rescue team with canine crew deployed to the hardest hit Hatay province.
- United Nations Disaster Assessment and Coordination (UNDAC): UK members of the United Nations Disaster Assessment Coordination members deployed to Adiyaman and Malatya to support assessment and coordination.
- £0.5 for Humanitarian Stabilisation Operations Team (HSOT): deployment of HSOT team.
- £1.58m for HSOT Non-Food Items (NFIs): Airlift first shipment relief shelter items:
  - 9,535 people supported in Turkey through the delivery of blankets and tents delivered to the GoT’s Disaster and Emergency Management Presidency (AFAD).
  - 7,190 people supported in Syria through the delivery of tents, blankets, kitchen sets, solar lanterns, water cubes and hygiene kits.
- £1.15m for the Ministry of Defence (MoD): MoD Type 2 Field Hospital.
- £1.82m for UK-Med: Deployment of Emergency Medical Team (EMT) UK-Med Type 1 healthcare facility and health care staff
  - 20,342 people in the earthquake zone received health care.

National and international humanitarian partners implemented life-sustaining humanitarian relief activities in support of GoT efforts (£10.4 million):
- £5m UK Aid Match to Disaster Emergencies Committee (DEC) Appeal for Turkey (£2.5m) and Syria (£2.5m) on February 14, which leveraged a total £143m for multi-sector emergency response and recovery activities, including healthcare, shelter, NFIs, food and water.
- £1.8m to the Turkish Red Crescent (TRC) through The International Federation of Red Cross and Red Crescent Societies’ (IFRC) Appeal for Multi-Purpose Cash Approach for 19,744 people and WASH support for 40,000 people as well as engagement with communities (6.43% of the allocation).
- £1m for United Nations High Commissioner for Refugees (UNHCR) to ensure access to protection for 12,384 refugees affected by the earthquakes with specific needs.
- £1.2m to United Nations Children’s Fund (UNICEF) to protect 26,632 (23,837 children and adolescents and 2,795 care givers) from exploitation, abuse, and neglect. In addition, provision to 424,856 (206,210 females, 214,636 males), children and family members with immediate, sustainable access to safe drinking water.
- £1.4 for United Nations Development Program (UNDP) to increase access to social care and protection services for 1,648 people affected by the earthquakes with special needs and increase capacity for waste management.

The overall humanitarian response was strengthened through the provision of enabling services, surge support and HMG advocacy (£0.55 million):
- £0.1m for the Humanitarian-to-Humanitarian Network (H2H) The network provided independent open-source services to support responding agencies with a variety of tasks. These included translation and training in humanitarian standards, needs assessment and analysis, mapping displacement flows, and community engagement mechanisms.
- £0.45m for the Standby Partnerships’ surge mechanism to reinforce UN agencies with coordination and technical expertise to increase capacity and increase effectiveness.

The programme was designed as a flexible mechanism to respond to the February 2023 Turkey-Syria earthquakes, and it exceeded the majority of its anticipated impact, outcome and output targets. This was mainly due to the scale of the disaster, the needs on ground, the positive variations of the exchange rate, and an adaptive pivot from emergency response to early recovery and rehabilitation. Overall, programme moderately exceeded the expected results, scoring an A+.

Major lessons learned and recommendations for future programming:
Programme data, partner progress and post distribution monitoring reports, and British Embassy Ankara (BE Ankara) team field visits across 2023 and 2024 identified a range of lessons learnt which will be mainly considered under BE Ankara’s upcoming Building Refugee Resilience in Turkey (BRRIT) programme. These are summarised below:
Capabilities
Humanitarian information and analysis expertise is best placed on the ground early in the response: In a large-scale complex response, accurate information is essential to inform operational and programmatic decision-making. This information is best if it comes from the situation on the ground. Although a Humanitarian Affairs Officer (HAO) was assigned to the Response in London from the beginning, an HAO was not deployed to Gaziantep until the 3rd of March. This delay in field deployment led to the Humanitarian Advisor (HA) in Gaziantep being stretched between multiple meetings and geographies. It is recommended, under a no regrets approach, that an HAO is deployed immediately to the field to strengthen the breadth of information collation and its timely analysis and flow for decision-makers on the response, especially regarding potential partners’ operational capabilities and priority needs, as well as to relieve the HA to be able to focus on operational advice or decision-making.

Speed of deployment of UK ISAR is critical: AFAD requested International Search and Rescue teams at 06.16 GMT on the 6th of February, and the decision to deploy UK ISAR was made on the same day. In slower time FCDO should consider a more formal arrangement with AFAD to further streamline UK ISAR deployment.

Standing up the MOD Field Hospital is resource intensive: the bilateral support of a Field Hospital to the Turkish government was well received, strengthened political ties and provided vital emergency health care. Nonetheless, this activity against the response budget and staffing capacity was resource intensive. The deployment of a Civ-Mil advisor to BE Ankara significantly eased the coordination burden on the humanitarian team and an early decision to hand over the Field Hospital to Turkish Medics on the 28th of February reduced the overall cost of the operation significantly. It is recommended that in future responses Civ-Mil capacity is deployed alongside the Field hospital and there is early agreement on the budget contributions from FCDO for this activity.

Funding and Partnerships:
When a response straddles two countries across different directorates, initiating and maintaining clear communication between all aspects of programme operations, especially programme management, should be prioritised.
Where Governments are strong in disaster response and if existing humanitarian architecture is not in place, UN humanitarian mechanisms may be slower to stand up. Turkey has a strong government and disaster response mechanism, bilateral relationships between agencies and political entities are strong.BE Ankara already had in place a strong bilateral relationship with AFAD, which helped to facilitate early NFI deliveries. UK response activities strengthened UN structures through funding UNDAC Positions and towards the end of the Acute Stage through funding 2 SBP positions in strategic priority areas for the FCDO and the response. It is recommended that BE Ankara continue to strengthen their relationships with AFAD, and UNDAC to ensure future responses, either bilateral or UN-coordinated can be quickly and effectively supported by the FCDO.

Agencies with pre-existing centralised agreements had to be chosen as partners for response, as initiating local partnerships could not be done quickly enough to serve the people in need. The response coincided with the end of the FCDO’s financial year and meant that funding needed to be released quickly. As Post did not have any ongoing bilateral funding arrangements with partners, UN and the IFRC were chosen because these agencies have pre-existing centralised agreements in place, and they were well-placed to deliver the programme. Partnerships worked well, yet the option to work with humanitarian partners on the ground was restricted by the time it would take to conduct the appropriate due diligence assessments. It is recommended that BE Ankara considers an internal risk facility in its new business case and maintains relationships with strong humanitarian partners in the country and, if standing programme management capacity is secured, considers developing a more strategic partnership with local NGOs.

How this report was conducted
This report was conducted drawing on regular FCDO field monitoring visits and partners’ interim and final reports, which were reviewed and discussed with partners. A comprehensive lessons learned exercise was separately undertaken through key stakeholder debriefs and supplemented through a desk review of key response documentation.

Actions following approval of this report
The UK Emergency Humanitarian Response to the Earthquakes Affecting Turkey and Syria programme will be closed in line with FCDO’s Programme Operating Framework (PrOF) guidelines. Programme assets remained under the ownership of lead delivery partners in line with FCDO central agreements. All partners will continue to utilise these assets for good developmental purposes; and any underspend will be returned to FCDO within eighteen months of the programme’s end date (i.e., by 31 December 2025).
- Ensure that the annual audited accounts and financial statements linked to the final year of the programme’s expenditure are received and reviewed from all partners by June 2025, i.e., within 12 months of the programme closure. Action: PRO.
- Ensure that any unspent funds remaining under all components, after paying all outstanding liabilities for activities, are settled as soon as possible and any remaining funds are transferred to FCDO’s central contingency fund at latest by Dec 2024. Action: SRO.
- Set up a Lessons Sharing Session for BE Ankara and HRG colleagues to share achievements, lessons and recommendations for future programming and humanitarian response by Sep 2024. Action: PRO.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£17.2m including £4.7m that was spent on Syria Earthquake.	£15.24m (30/06/2024)
Timeframe	9 months. 08 February 2023 till 31 December 2023.	The total programme timeframe, from BC sign-off (08/02/2023) to closure (30/06/2024) is 15 months
Impact: Urgent and basic needs of people affected by the earthquake are met
Impact indicator: / # beneficiaries reached by humanitarian assistance	Turkey + Syria 401,212	Turkey + Syria 1,101,252 / Turkey 761,373
Outcome: Immediate rescue, relief and medical needs are met with UK humanitarian capabilities.
Outcome 1: / # people affected by the earthquake receiving health treatment (included people rescued)	Turkey 18,000 / No initial target for Syria	Turkey 20,342 / Syria 23,506
Outcome 2: / # people receiving immediate NFI (tents and blankets)	Turkey No initial target set / No initial target set for Syria	Turkey 14,874 / Syria 31,130
Outcome 3: / # beneficiaries of receiving basic humanitarian assistance (access to social services, protection, cash assistance, food assistance)	Turkey 86,158 / No initial target set for Syria	Turkey 201,301 / Syria 65,970
Outcome 4: / # of people benefitting from the WASH intervention	Turkey 266,600 / No initial target set for Syria	Turkey 524,856 / Syria 219,673

Overall assessment of programme outcomes

The project impact is: Lives saved, suffering prevented or alleviated, and dignity preserved for people affected by the earthquake

Impact indicator is:
# beneficiaries reached by humanitarian assistance
The programme was effective in terms of value for money considerations; since it enabled a rapid and timely response to address increased humanitarian needs, specifically among the most vulnerable refugee and non-refugee women, men, girls, boys and people with disabilities. The number of beneficiaries reached by humanitarian assistance is 1,101,252 compared to the starting target of 401,212 individuals.

The 4 outcome indicators exceeded expectations:
Outcome 1 describes how people affected by the earthquake were supported in terms of health. The response timeline was crucial for this emergency intervention. ISAR, UK-Med and MoD were complementary in providing a mobile field hospital and operating through mobile clinics. This shows capacity to operate in an integrated response led by the host government. The combined efforts of the 3 entities led to results moderately exceeding expectations.

Outcome 2 emphasizes that the provision of NFIs delivered by HSOT through MoD was good value for money. It delivered NFIs direct to Turkey for distribution in Turkey as well as to Care Syria for the Syrian people affected by the earthquake in Syria. Outcome 2 moderately exceeded expectations.

Outcome 3 shows how with FCDO funding, through different mechanisms (Social services, protection, cash assistance, food assistance) people could increase their access to basic humanitarian assistance. TRC is implementing in Turkey the largest cash-based approach programme in the world, which was utilised to provide additional cash to earthquake-affected people. UNICEF’s strong relationship with their line ministry allowed them to work effectively and efficiently, especially in terms of child protection by setting up more than 20 hubs. The cash-based approach was appropriate for the Turkey context with markets functioning and proved to be one of the most effective components, with both DEC and IFRC exceeding their initial targets. Outcome 3 substantially exceeded expectations.

Outcome 4 was the best outcome in term of VfM. The early support to the water plant in Hatay and the creation of additional water networks allowed UNICEF and the Municipalities to deliver clean water to over 420,000 people. IFRC/TRC distributed water containers to 10,000 households, while DEC-funded projects delivered related hygiene NFIs. Outcome 4 substantially exceeded expectations.

There is good evidence that the programme has effectively helped save lives and improved the quality of life for the most vulnerable. It has also helped prevent a worsening humanitarian crisis and maintained stability.

The UK’s response to the earthquakes was successful and the emergency programme achieved its initial aims to address the most urgent needs. A successor multi-year development/recovery programme, Building Refugee Resilience in Turkey (BRRIT) has been designed with a particular focus on refugees, building on the lessons learned and investments made through this programme. Multi-year predictable funding helps partners to better plan and be more strategic in addressing recovery needs that underpin the recovery situation in Turkey after the February 2023 earthquakes.
THEORY OF CHANGE

   INPUT

Up to £17millions (circa £5m to Syria) provided multi-sectoral assistance to most affected and vulnerable. FCDO supports well established humanitarian partners in a coordinated response.

Skills development, matchmaking, job transition programmes to increase livelihood options of local communities will be implemented.
UNDP
People affected by the earthquake are benefitting from medical care.
ISAR, MOD
UK-Med, DEC
Increasing access to basic needs to people affected by the eathquakes.
UNICEF, IFRC, DEC
The most vulnerable groups and refugees affected by earthquakes with specific needs are protected and receive social
services.
UNDP, UNHCR, UNICEF, DEC
Capacity of the government increased to respond to protection needs after the earthquake.
UNDP

Improve food security for people affected by the earthquakes.
DEC
Humanitarian assistance is effective, coordinated, principled and accountable according to core humanitarian standard.
SBP, HSOT, H2H, IFRC

Capacity for routine municipal waste management as well as basic waste management for temporary settlements will be enhanced.
UNDP

Immediate rescue, relief and medical needs are met with UK humanitarian capabilities. National and international humanitarian partners implement life-sustaining humanitarian relief activities in support of GoT efforts.

Lives saved, suffering prevented or alleviated dignity preserved for people affected by the earthquakes.

The FCDO’s approved Theory of Change outlines the needs that the programme aims to address, the inputs and processes provided by the UK, the outputs to be delivered by implementing partners, and the expected outcomes and impact. The Theory of Change was appropriate during the life of the programme with all well-established partners. Two additional outputs were added to the logframe (the logframe was not completed at the signature date of the Business Case). The Theory of Change only evolved a little from the original to provide more detail as the context changed to ensure the early recovery activities were appropriate and clearly understood.

## C: Detailed Output Assessment

Output 1		People affected by the earthquake are benefitting from medical care
Output Score		Outputs met expectations (A) (4 outputs had no starting targets)
Impact weighting (%)		28%	Impact weighting revised since last AR?	N/A

Output Indicator 1	Starting Target		Final Logframe Target	Final Result Achieved
# trained equipped ISAR staff operational in Turkey	77 rescuers deployed + 4 dogs		77 rescuers deployed + 4 dogs	77 rescuers deployed + 4 dogs
1.2 # MoD Type 2 field hospital, / # of UK-Med Type 1 healthcare facility	1 MoD Type 2 field hospital established. / 1 UK Med Type 1 health care facility established.		1 MoD Type 2 field hospital established. / 1 Type 1 UK-Med health care facility established	1 MoD Type 2 field hospital established. / 1 UK-Med Type 1 health care facility established
1.3 # of people receiving Primary Health Care (PHC) support	No initial target for MoD/UK-Med, only 18,000 people supported with health interventions. / DEC no initial target set		21,000 / MoD/UK MED: 18,000 / DEC: 3,000	27,348 / MoD/UK MED: 17,175 / DEC: 10,173
1.4 # of children treated in the UK-Med Type 1 health care facility	N/A		2,685	2,685
1.5 # of people who receive stabilization support for further referral via the UK-Med Type 1 health care facility	N/A		284	284
1.6 # of women and children referred for further treatment through UK-Med Type 1 health care facility	N/A		77 children and 121 women	77 children and 121 women

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The UK humanitarian response initially focused on urgent lifesaving. The national and international humanitarian assistance subsequently scaled up to meet the basic needs of disaster-affected populations, and the humanitarian response was strengthened to support GoT relief efforts. Immediate lifesaving rescue operations, provision of shelter and emergency medical assistance through UK ISAR, MoD, and UK-Med and DEC are included in the output 1.

The overall output score is A, indicating that the output met expectations in terms of achieving its target.
[note] Note, as per the Business Case, ISAR support was funded through a FCDO Centrally Managed Programme (CMP), Emergency Deployments Team 2 (EDT2) (301054), however the results are reported here in line with the logframe. The MoD and UK-Med activities were jointly funded through this programme and the Emergency Deployments Team 2 (EDT2) (301054) CMP. This programme contributed £320,000 whereas £1,190,629 was contributed by the CMP EDT2.

Output 1.1: International search and rescue support was requested by the Government of Turkey through AFAD and an official request for support was announced through the Virtual OSOCC (Virtual On-Site Operations Coordination Centre). The UK ISAR team deployed to Turkey arriving on the 7th February 2023 at FCDO and returned on 15th February. The UK ISAR response included 77 personnel from 14 Fire & Rescue Services including 4 search dogs, 5 USAR medical professionals known as UMT, 1 Structural Demolition Engineer and 1 Vet with all associated equipment for an INSARAG-Classified Heavy Rescue Response. This also included a 24-hour dedicated UK reach back team of a further 8 personnel in the UK Incident room. The deployment time was crucial in the context, and it is what has been measured with this indicator output. This output met expectations.

Output 1.2: 1 MoD Type 2 field hospital and 1 UK-Med Type 1 health care facility were established. This output indicator met expectations.

The Turkish government’s international assistance request was for Type 2 EMT capabilities, which was met through a combination of the UK Emergency Medical Teams (UK-Med) ’s Type 1 health care facility and the UK Ministry of Defence (MoD) Type 2 field hospital, which deployed for a three-week period.

The UK-Med EMT’s response was supported by the UK MoD which provided transportation for initial team members from the UK and the shipping of equipment and supplies for establishing the Type 2 field hospital.

UK-Med formally began service delivery in the Type 1 health care facility on February 14. Mobile teams were also mobilised as part of the UK-Med response between February 20 and April 14, reaching over 2,700 people from 41 villages who were not able to access the main facility. In total, UK Med provided consultations for 7,048 patients throughout the response through the Type 1 health care facility and outreach teams. UK-Med activities ceased on April 14 and the UK-Med departed Turkey on April 20.

As Turkish community health workers had scaled up their outreach services by mid-April it was agreed between UK-Med, the Ministry of Health and FCDO to cease activities by mid-April and utilise the remaining budget for essential equipment and supplies for Türkoğlu district hospital. The needs were defined with the hospital in June and the formal handover of the donation was marked by an event on September 22, 2023, at Türkoğlu hospital, attended by a high-level delegation from the BE Ankara, representatives from UK-Med and the hospital’s management team.

Output 1.3: The output initially focussed solely on Primary Health Care (PHC). Combining the UK-Med’s Type 1 health care facility and the UK MoD Type 2 field hospital, 17,175 patients were received in total during the project period, with UK-Med treating 41% of the caseload. In addition, the UK-Med Type 1 health care facility provided non PHC services: 2,685 children were treated in, 284 people received stabilization for further referral and 77 children and 121 women were referred for further treatment, bringing the total of people benefitting from medical care to 20,342. This output indicator, moderately exceeded expectations.

Output 1.4: This was an output indicator added after the concept note submission to have a better picture of the medical response required. A total of 2,685 children were treated by UK-Med, of which 76% were in the UK-Med Type 1 facility and 24% seen through mobile teams of health care staff. This accounted for 55% male and 45% females for the paediatric cases, and 1,174 (44%) were under the age of 5 years. The main diagnosis for patients under the age of 18 were upper respiratory tract infection (467 children), acute respiratory infection (388), minor injury (246), vomiting and diarrhoea (187) and skin disease (133). This output indicator met expectations.

Output 1.5: UK-Med stabilized and made 284 referrals of patients to other health facilities, namely those in Turkish towns within a few hours distance which remained functional. This included 208 adults (84%) and 76 children (16%). The most common referral was for patients with acute mental health issues (33 people), minor injury (31), musculoskeletal pain (29) and skin disease (18). Twelve patients required long term rehabilitation support including 7 adults and 5 children. This output indicator met expectations.

Output to 1.6: A total of 77 children under the age of 18 were referred, including for minor injury (13), acute mental health issues (6), acute respiratory infection (4), dental pain (4) and skin disease (4). As well, 121 women were referred to other services including 4% of pregnant women. The main diagnosis for referrals included musculoskeletal pain (18), acute mental health issues (12), minor injury (8) and moderate injury (6). This output indicator met expectations.

Lessons learned in delivering output 1:
- Working in an integrated manner, assistance to the Turkish health system was delivered by supporting both the Turkish EMTs and local health authorities to deliver on their priority of ensuring access to health care in the immediate period following the earthquakes. The adaptability of UK-Med/ISAR/MoD services combined with engaging Turkish staff and local counterparts was vital to building trust and removing cultural barriers and sensitivities with patients, increasing accessibility to the services for patients.
- Close coordination with health authorities in Türkoğlu allowed UK-Med to develop a clear exit strategy for the response as the health system began to recover and health workers returned to post, thereby allowing UK-Med's services to be gradually reduced until they were no longer required.

Recommendations for future programming from output 1:
In the event of a future humanitarian response requiring health interventions by UK-Med and/or MoD, dedicated resource should support the importing of equipment and supplies (e.g. with customs waivers) with due consideration for use of commercial or military assets to ensure rapid use of assets and delivery of emergency response health programme.

Output 2		Increasing access to basic needs to people affected by the earthquake
Output Score		Outputs met expectations (A) (4 outputs had no starting targets)
Impact weighting (%)		42%	Impact weighting revised since last AR?	N/A

Output Indicator 2	Starting Target		Final Logframe Target	Final Result Achieved
2.1 # of water container distributed	3,600 water tanks (HH)		10,000 (HH) water containers	10,000 water container distributed benefitting 40,000 individuals.
2.2 # of hygiene kits distributed (IFRC/DEC Turkey + Syria)	DEC Turkey no initial target was set, Target was set after 3 months of operations / DEC Syria no initial target set		DEC Turkey 27,100 / DEC Syria 31,794	27,100 / 31,794
2.3 # people (children and families) in earthquake affected areas with (immediate and sustainable) access to safe drinking water (UNICEF+ DEC Syria)	UNICEF 263,000 (revised CN May 2023) / DEC Syria no initial target set		UNICEF 263,000 (revised CN May 2023) / DEC Syria 219,973	UNICEF 424,856 (206,210 females, 214,636 males) / DEC Syria 219,973
2.4 # of people benefiting from NFI distribution (HSOT)	HSOT for Turkey. No initial target set for HSOT in Turkey / HSOT for Syria, no initial target set / DEC Turkey no initial target set / DEC Turkey No initial target set		9,535 people benefitting from distribution of 1,907 tents / 23,840 people benefitting from 23,840 blankets / 7,190 people were supported with distribution of 1,438 tents, 16,980 blankets, 866 hygiene kits, 1200 water purification cubes and 512 coverage kits were delivered in Turkey and handed over to Care Syria / 5,339 (target set after 3 months of operations) / 24,940	9,535 people benefitting from the distribution of 1,907 tents (5 people per tent) / 23,840 people benefitting from 23,840 blankets / 7,190 people were supported with distribution of 1,438 tents, 16,980 blankets, 866 hygiene kits, 1200 water purification cubes and 512 coverage kits were delivered in Turkey and handed over to Care Syria / 23,400 / 24,940
2.5 # of people receiving multipurpose cash assistance (DEC)	DEC Turkey No initial target set / DEC Syria No initial target set		12,476 (Target was set After 3 months of operations) / 31,530	77,000 individuals / 31,530
2.6 # people receiving supported with cash assistance (IFRC)	12,299 individuals		12,299 individuals	19,744 individuals

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Increasing the access to basic services became quickly one of the priorities to be addressed. The cash intervention played an important role in supporting people to access the basic services. The overall output score is A, indicating that the output met expectations in terms of achieving its targets.

Output 2.1: 10,000 water containers were distributed to 10,000 HH (see table below) benefitting 40,000 individuals. IFRC/TRC made a change in their initial approach from 3,600 community-based water tanks to 10,000 household containers and filters with no cost implication.

Item	Province	# of Unit in HH
Water container	Hatay	1,000
Water container	Kahramanmaraş	2,500
Water container	Gaziantep	1,500
Water container	Malatya	-
Water container	Adiyaman	5,000
Water container	Osmaniye	-
Total		10,000

Output 2.2: Target was set after 3 months of operations for both Turkey and Syria. Overall, 27,100 people were supported with hygiene supplies in Turkey and 31,794 people were supported with hygiene supplies in Syria meeting expectations.

Output 2.3: With FCDO funding, 424,856 people were reached with clean water. The funds allocated were used for pipes, chlorination devices, chlorine transfer equipment, and were strategically used in new water supply networks, repairing earthquake damaged water supply networks, debris removal operations of Hatay Metropolitan Municipality’s General Directorate of Water and Sewerage Administration (HATSU). Chlorination systems in container cities prevented epidemic diseases, while the provision of missing spare parts ensured efficient operation in drinking water treatment facilities. Additionally, access to clean water, quality improvement, water quality testing was addressed, benefitting 164,115 individuals (81,894 women and 82,221 men) including 43,490 children. This was done through quality improvement of water and purchased materials for wastewater treatment plants and sewer lines. The earthquake-induced failures were promptly addressed, emphasizing the significance of these initiatives in the region’s water and sanitation infrastructure recovery. UNICEF’s support to HATSU underscored the critical role of water and sanitation initiatives in disaster recovery efforts.

While the initial target was 263,000 people, the number of people reached with access to clean water is 424,856 people. This output exceeded the expectations.

Output 2.4:
HSOT in Turkey: no initial target was set, however 9,535 people benefitted from distribution of 1,907 tents and 23,840 individuals benefitted from 23,840 blankets.
HSOT supplies for Syria: no initial target was set; however, 7,190 people were supported with distribution of 1,438 tents, 16,980 blankets, 866 hygiene kits, 1,200 water purification cubes and 512 coverage kits. These were delivered in Turkey and handed over to Care Syria.
DEC Turkey: No initial target was set. The target was set after 3 months of operations to 5,339 people supported, final results show 23,400 people supported.
DEC Syria: has no initial target set. However, 24,940 individuals were supported with NFIs.
This output met expectations.

Output 2.5 and 2.6: The use of cash became quickly instrumental in the response as markets were functioning quickly after the disaster.
DEC Turkey: No initial target was set, the target of 12,476 was set after 3 months of operations with a final result of 77,000 individuals supported by multi-purpose cash assistance (MPCA). Cash assistance gave people cash payments or vouchers so that they could choose how to meet their own needs. It allowed people to take a more active role in their own recovery and was demonstrated to be an effective form of assistance in situations where the economy is functioning, and markets are open.
IFRC Turkey: IFRC was able to raise substantial amount of funds for the response, mobilising over 5,000 volunteers. The multi-purpose cash assistance remained a priority and preferred modality to support the affected population to meet their basic needs as they could utilise their existing cash transfer programme to provide additional funding to existing beneficiaries. This was in line with the positive outlook on recovery of markets and feasibility of cash and voucher assistance to support the affected population based on findings from multiple markets assessments conducted after the earthquakes.
DEC Syria: There was no initial target set for Syria, however, 31,530 people were supported with MPCA. Providing families with cash or vouchers gave them the ability to decide what to spend the money on, to make sure it met their particular needs. Many DEC members and their partners have used cash assistance to support people in north-west Syria affected by the earthquakes. Cash assistance was particularly useful to people where markets were still working and was more efficient, as it did not require transporting large quantities of food or other goods. However, with food prices soaring, many vulnerable people whose livelihoods have been impacted could not afford to pay for basic household needs.
Both output indicators met expectations.

Lessons learned in delivering output 2:
The flexible approach the FCDO adopted in our funding IFRC/TRC allowed them to re-adjust their target from the initial concept note to reflect the dynamic needs on the ground. They increased their WASH and cash distribution activities to address the priority needs more adequately. Rather than creating dependency on aid, cash assistance enabled families to choose what to spend the money on and planned for how and when to spend it. Cash assistance also stimulated local demand and boosted the economy, contributing to the overall recovery process. The programme was also adapted to meet increased demand during Ramadan.

Recommendations for future programming from output 2:
The speed with which markets bounced back to full functionality meant that cash-based assistance was the most appropriate form of relief. It was particularly appropriate for the most vulnerable, such as people with disabilities and older people, whose needs were not always met by traditional aid packages: giving them the flexibility to pay for the specific items that they needed. In the aftermath of the earthquakes, vouchers which could be spent in local supermarkets were one of the quickest and most efficient ways to get immediate support to people in urgent need. People used the vouchers to buy food, hygiene items like detergents and cleaning products, and items for babies. Cash-based programming should be considered a priority response modality in future responses.

Output 3		The most vulnerable groups and refugees affected by earthquakes with specific needs are protected and receive social services.
Output Score		Outputs met expectations (A)
Impact weighting (%)		13%	Impact weighting revised since last AR?	N/A

Output Indicator 3	Starting Target		Final Logframe Target	Final Result Achieved
3.1 # people with access to safe spaced, protection, and support hubs (UNICEF)	18,000 (12,600 children + 5,400 caregivers)		18,000 (12,600 children + 5,400 caregivers)	26,632 (23,837 children and adolescents and 2,795 care givers)
3.2 # people accessing social services at 5 rehabilitated centres / +3 women solidarity centres connected with shelters for women (UNDP)	1,500		1,500	1,648
3.3 # of social workers deployed at MOFPSS (UNICEF)	19		19	19
3.4 # of cases followed by UNICEF social workers	430 (as per July 2023)		430 (as per July 2023)	2,027 (1,007 girls – 1,020 boys)
3.5 # of refugees supported with special protection needs funds (UNHCR)	4,800		4,800	12,384
3.6 # of individuals receiving mental health and psychosocial support (MHPSS) (DEC)	DEC Turkey No initial target set. / DEC Syria no initial target set		945 target was set after 3 month of operations) / 8,201	6,450 / 8,201

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

FCDO’s funding was instrumental in the delivery of integrated protection services to children and caregivers through the Child, Adolescent and Family Support Hubs in partnership with CSOs. The “hub modality” expands on the child friendly spaces approach of UNICEF, an approach widely used in emergencies globally as a first response to children’s protection needs and an entry point for working with and empowering affected communities, including adolescents, youth and women. The hubs respond to the right to protection, mental health and psychosocial wellbeing, learning, development and participation of boys and girls, whilst building their resilience and that of their communities.
The overall output score is A, indicating that the output met expectations in terms of achieving its targets.

Output 3.1: FCDO’s support was instrumental to the procurement of supplies for the hub facilities and outreach service points (i.e. 12 generators, 5,299 Psychosocial Support (PSS) kits, and stationaries), contribution to recruitment/salaries of frontline workers and running costs related to 25 static and mobile hubs and the activities and services they provide to children and caregivers in 7 affected provinces. This benefitted at least 26,632 individuals (15,195 female; 11,437 male) including 23,837 children and adolescents (13,257 girls; 10,580 boys) with child protection and GBV prevention and response services.
The initial target was set to support 18,000 people (12.600 children + 5400 caregivers) and ended with a final result of 26,632 (23,837 children and adolescents and 2,795 care givers). This output indicator moderately exceeded expectations.

Output 3.2: This indicator reflects the number of people that have access to social services within the UNDP project where 1,648 individuals accessed social services at rehabilitated centres including women solidarity centres connected with shelters for women. This output indicator moderately exceeded expectations.

Output 3.3: A total of 19 frontline workers were funded by FCDO and deployed to identify and provide services to children affected by the earthquake, including children without parental care due to the earthquake. As a result of FCDO’s support, the ‘Children are Safe’ teams reached 2,027 children (1,007 girls, 1,020 boys) with follow-up support and the foster care units supported the review of the 320,970 foster care applications that were received by the MoFSS post-earthquake. This output indicator met expectations.

Output 3.4: The initial target was set at the end of July as it was impossible to predict in advance how many cases front line workers could follow. The target was set at the midterm point of the project, with 430 cases being followed. The final result showed 2,027 cases followed, almost 5 times more than the original target. This output indicator met expectations.

Output 3.5: The types of assistance provided to address health, education, security, and other needs using the Special Needs Funds (SNF) included, one-time emergency household assistance (pest control, assistance after fire/flood, one-time rental support, and real-estate commission), rental assistance up to 3 months (and additional 3 months if the relevant protection risk persists), emergency accommodation, covering the emergency time period before accessing the existing state sheltering solutions, transportation expenses for hospital appointments, transportation expenses from one city to another depending on the protection risk, expenses for facilitating school enrolment (including one or two-time school materials, uniforms, transportation for enrolment process, exam application fees), certified notary fee including for certificates of death, birth, graduation, diploma, power of attorney, etc., medical devices (such as wheelchairs, hearing aids, orthosis, prosthesis, glasses, etc. based on doctor report or permission) and medication for one-time assistance in life-threatening conditions, exhaustible medical support related to the protection risk, School equipment, clothing, and other non-food items. Overall, more than 12,000 refugees were supported with special protection needs funds against the target of 4,800. This output indicator exceeded expectations.

Output 3.6: Through direct FCDO funding to UNICEF, almost 23,763 children (including 13,257 girls; 10,506 boys) benefited from Mental Health and Psychosocial Support (MHPSS) interventions and services through 25 static and mobile hubs/service delivery points that addressed distress and trauma and strengthened their coping and resilience mechanisms in safe learning and play environments. Furthermore, the hubs have proved a model of integrated, cross-sectoral and multi-generational service delivery, addressing the multifaceted and complex needs of children and their caregivers through the delivery of a package of services. This includes parenting support and skills programmes, counselling, MHPSS, case management, GBV prevention/response and Prevention from Sexual Exploitation and Abuse (PSEA) risk mitigation, mother/baby corners with breastfeeding, nutrition and ECD counselling, adolescent learning and skills programmes, as well as referrals to specialized services.
[note] These children are also counted under the output indicator 3.1
DEC Turkey had no initial target. A target of 945 beneficiaries was set after 3 months of operations bringing the total results to 6,450. Trauma among the population was critical during the post-earthquake and remained an important activity.
DEC Syria: No initial target was set for Syria, but the project ended up supporting 8,201 people.
This output indicator met expectations.

Lessons learned in delivering output 3:
- The success of UNICEF’s child protection programme was due to 1) the establishment of hubs in strategic locations in temporary accommodation centres and container cities in the second half of 2023 increased the reach of service delivery points; 2) the cross-sectorial integrated service delivery modality (due to cross-sectorial referrals to children from other programmes as well) and 3) enhanced mobile outreach efforts which enabled to reach more beneficiaries than initially planned.
- While UNDP exceeded expectations in terms of its final results, FCDO observed a common trend across almost all UNDP-funded projects during monitoring visits through discussions with beneficiaries, that these beneficiaries were not among the most vulnerable groups affected by the earthquake. The key lesson is that the targeting criteria was not clearly defined when the MOU was signed, indicating that the programme did not include vulnerability targeting.
- UNDP was the only partner requiring a no-cost extension. This was requested due to delays in procurement. The delay in procurement for the delivery of two accessibility centres was attributed to suppliers prioritizing government-funded programs and price volatility. Although this extension allowed UNDP more time to complete the project, it did not affect the disbursement of funds, as these had already been spent during the project's lifetime. The extended implementation period provided FCDO with additional data for this specific project yet is not ideal during an emergency response.
- This large-scale sudden-onset disaster resulted in significant displacement of a large refugee population. Registration serves as the gateway for refugees to legalize their stay in Turkey, and to access rights and to benefit from social safety nets, health services, employment rights, and education. Therefore, support during a response for continued registration and protection services is critical.

Recommendations for future programming from output 3:
- FCDO's funding played a crucial role in delivering integrated protection services to children and caregivers through the Child, Adolescent, and Family Support Hubs, in partnership with CSOs. The "hub modality" builds on UNICEF's child-friendly spaces approach, a widely used strategy in global emergencies that serves as an initial response to children's protection needs and as a gateway for engaging and empowering affected communities, including adolescents, youth, and women. These hubs address children's rights to protection, mental health, and psychosocial well-being, as well as learning, development, and participation for both boys and girls, while also fostering resilience in them and their communities. It is recommended to replicate that model for larger scale emergency.
- Although UNDP's results align with the agreed project, there is some uncertainty on whether UNDP is the most appropriate agency for this type of emergency intervention due to the delivery delays in reaching beneficiaries. It is recommended that for this specific type of project, the targeting criteria for future programming should be clearly defined during funding negotiations.
- In the aftermath of the earthquakes, UNHCR demonstrated its capacity to respond quickly to a large-scale emergency, being among the largest and fastest providers of in-kind assistance just a few days after the disaster. This highlighted the importance of maintaining a strong preparedness and emergency response capacity in the region.

Output 4		Capacity of the government increased to respond to protection needs after the earthquake
Output Score		Output met expectations (A)
Impact weighting (%)		2%	Impact weighting revised since last AR?	N/A

Output Indicator 4	Starting Target		Final Logframe Target	Final Result Achieved
4.1 # centres refurbished and renovated for women, elderly and people with disability	2 centres		2 centres	2 centres
4.2 # centres established to increase municipalities’ response capacity	2 new centres		2 new centres	2 centres
4.3 # of temporary units accessible by PwD, elderly and women (UNDP)	mobile units (31/12/2023)		3 mobile units.	3 mobile units
4.4 Diversity of referrals made by mobile centre (UNDP)	5		5	7
4.5 Gender responsive operational procedures developed and in use in all Mobile and Renewed centres to respond to the needs of persons with disabilities, the elderly, refugees, and vulnerable women UNDP	1		1	1

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
Access for Persons with Disabilities (PwD) was a high priority during this response. UNDP's role was more focused on the early recovery phase. FCDO supported a request from UNDP to grant a no-cost extension (with no financial implications) until February 28, 2024. This extension was needed due to the volatility of supply prices and the priority that all suppliers gave to government-funded projects, which caused procurement delays. Although the funds were allocated and spent before the project's original end date, the delivery of the Karamanmaras project took place in mid-December, and the Hatay project was delivered in early February. Despite these delays, the project was ultimately delivered on time, and the no-cost extension helped to gather additional data on the intervention.

The overall output score is A, indicating that Output 4 met expectations in terms of achieving its targets. The output score is based on what the output delivered during its lifetime.

Output 4.1: Two centres in Kahramanmaraş underwent extensive refurbishment in collaboration with the Kahramanmaraş Metropolitan Municipality; Women’s Counselling Centre and Accessible Living Centre. The Accessible Living Centre offers vital social care services specifically designed for the elderly and individuals with disabilities and their care givers. UNDP provided materials for the following workshops textile and tailoring, tile and ceramic, jewelry design and candle, wheelchair and repair maintenance, life skills. As of 29 February 2024, this centre provided daily support to 120 individuals. In addition to the Accessible Living Centre, a Women's Counselling Centre has also been revitalized with office supplies to better cater to the needs of the women.

Output 4.2: Two new accessibility and gender sensitive centres were established through collaboration with both the Hatay Metropolitan Municipality and Adıyaman Municipality. These centres offer valuable services tailored to the needs of women, the elderly, and individuals with disabilities. The centre in Adıyaman provides service to 600 individuals on a weekly basis. The centre in Hatay has initiated the services as of 21 February 2024 and the location of the centre is becoming a hub for similar services as various NGOs are being located in the neighbouring slots. UNDP provided office supply and psychosocial training for the center’s staff. The center provides vocational courses and counselling session to women, and makes referrals to Social Aid Foundation, Provincial Directorate of Family and Social Services, Courthouse, İşkur, as necessary. This output indicator met expectations.

Output 4.3: Three mobile units, mobile vehicles with 15 seats, were provided to Adiyaman, Hatay and Kahramanmaras municipalities to provide easy and free access for PWD. The vehicles have been useful in transporting sick and elderly to the centres, and ensured regular and easy access of those who are leaving in far districts. This output indicator met expectations.

Output 4.4: Seven types of referrals were made in the centres for pensions of persons with disability, food support, coal allowance, social support, care service salaries, psychosocial support, and business support against a target of 5. In total, 960 people were referred to different services during the programme lifetime. This output met expectations.

Output 4.5: A gender responsive operational procedure was developed to outline minimum standards in social service provision in post disaster settings. These guidelines are used by Kahramanmaras, Adiyaman and Hatay municipalities, who respond to the needs of persons with disabilities, the elderly, refugees, and vulnerable women. Overall, the guidelines helped improve the quality of services. This output met expectations.

 Lessons learned in delivering output 4:
Although UNDP's results align with the agreed project plans, this is not a life-saving project. FCDO should consider in the future whether UNDP is the most suitable agency for this type of emergency intervention, as their projects typically focus on development, even when labelled as ‘Early Recovery’.

Recommendations for future programming from output 4:
FCDO humanitarian response programmes should maintain focus on targeting the most vulnerable people affected by the disaster and alleviating the acutest humanitarian needs. For future programming, it will be important to clearly define the target population to ensure that those who are most in need receive the necessary support and for partners to use vulnerability targeting.

Output 5		Skills development, matchmaking, job transition programmes to increase livelihood options of local communities will be implemented:
Output Score		Output met expectations (A)
Impact weighting (%)		2%	Impact weighting revised since last AR?	N/A

Output Indicator 5	Starting Target		Final Logframe Target	Final Result Achieved
5.1 Number and type of capacity building trainings for centre staff	3		3	3
5.2 Number of care staff received trainings (only unique beneficiaries)	84		84	139 (69 women)
5.3 Number of formal partnerships for skills development and job transition programmes	10		10	10
5.4 Number of people vocationally trained in sectors of relevance in the earthquake region	510 (at least 40% women)		510 (at least 40% women)	1,162 (791 women)
5.5 Number of complementary measures for target groups provided to businesses	20		20	18
5.6 Number of people who received certificates on professional care services	100 (at least 40% women) (31/12/2023)		100 (at least 40% women) (31/12/2023)	88 (78 women)
5.7 Number of career services facilitated and job placements attained	100 (at least 40% women) (31/12/2023)		100 (at least 40% women) (31/12/2023)	324 (230 women employed)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
Following the earthquakes in February 2023, the labour market and employment has been significantly affected, especially in the provincial centres of Adıyaman, Hatay, Kahramanmaraş and Malatya. Between June-September 2023, UNDP field coordinators conducted a market analysis through qualitative methods such as interviews and meetings on June-September 2023. The findings were used for designing training programmes to fill the skills gap in the fields of IT, care services, food processing, construction supplies industry, hairdressing etc.

The overall output score is A, indicating that the output met expectations in terms of achieving its targets. The output score is based on what the output delivered during its lifetime.

Output 5.1: The functional capacity of three municipalities (Hatay, Adiyaman, Kahramanmaraş) to efficiently administer and provide services within the centres have received substantial support. This assistance has encompassed the development of suggested models for the organisation, physical capacity, and service provision as well as workflows and manuals, which have been complemented by two comprehensive face-to-face training sessions. These initiatives were aimed at ensuring a customised and responsive approach to addressing the diverse needs and vulnerabilities of citizens. 139 service providers from different institutions received training. These initiatives were aimed at ensuring a customised and responsive approach to addressing the diverse needs and vulnerabilities of citizens and to build coordination with the social service provision system within the province. This output indicator met expectations.

Output 5.2: Care staff was one of the most required skills in the immediate period after the earthquake. The initial target was set to train 84 beneficiaries, the final results show 139 beneficiaries were trained (165%), of which 69 were women. This output indicator moderately exceeded expectations.

Output 5.3: Ten MoUs have been formally signed between various Municipalities, Chambers, and UNDP Turkey, marking a significant collaboration aimed at the development and execution of customised vocational training programmes, business development services and mentorship. This output indicator met expectations.

Output 5.4: In collaboration with stakeholders in the business ecosystem, detailed analyses of labour demand and supply were conducted. These assessments informed the project's activities and served as a foundation for decision-making. The need for upskilling and reskilling was identified, leading to the procurement of necessary equipment and the delivery of training sessions. In total, 59 training sessions were provided, reaching 1,062 individuals. Initially, the target was to support 510 people, with at least 40% being women. The final result surpassed expectations, supporting 1,062 people, of whom 791 were women, representing 68%. Some of the trainings were on Qualified Interaction Specialist training, CSS and HTML, Barista, Textile/Straight Stitch, Overlock, Software Languages, Java and Python, Hairdressing, Computer Operation Course, and Carpet Designer. This output substantially exceeded expectations.

Output 5.5: Eighteen businesses and institutions received specialised business development services, which included business concepts, strategies, and leadership. Recipients of trainings included Organised Industrial Zones (OIZ), Chambers of Commerce and Industry, Women’s Cooperatives, in various cities in the earthquake affected area. While the initial target was set at 20, only 18 entities received complementary measures, meaning only 90% of the target was reached. This output indicators moderately did not meet expectations.

Output 5.6: 88 individuals received training on care services and corresponding certification, 78 being women and 10 being Syrian men. While the number of women receiving certification totalled (78) exceeded the target of 40% at 89% of the total, the total number of 88 people was less than the target 100. This output indicator moderately did not meet expectations.

Output 5.7: As a direct result of the career services facilitation interventions, 324 individuals secured employment, including 230 women (71%). The initial target was set to support 100 (at least 40% women) people. This output indicator substantially exceeded expectations.

Lessons learned in delivering output 5:
The added value of this output is highlighted by the significant proportion of women among the beneficiaries of these projects. Despite this achievement, field visits revealed that FCDO rarely encountered Syrian refugees affected by the earthquake, except in one centre operated by a Syrian NGO. Furthermore, most of the women beneficiaries appeared not to be directly affected by the earthquake, from a low socio-economic level or appeared to be the most vulnerable.

Recommendations for future programming from output 5:
FCDO projects should outline more clearly the most vulnerable group(s) to be targeted and prioritised for assistance.

Output 6		Capacity for routine municipal waste management as well as basic waste management for temporary settlements will be enhanced
Output Score		Output moderately exceeded expectations (A+)
Impact weighting (%)		2%	Impact weighting revised since last AR?	N/A

Output Indicator 6	Starting Target		Final Logframe Target	Final Result Achieved
6.1 Number of business continuity plans for municipal waste management services in temporary settlements developed	2		2	4
6.2 Number of Street Sweepers provided to Municipalities in Need	2		2	2
6.3 Number of Dust Abatement System Provided	1		1	1
6.4 Number of Waste Containers Provided	330		330	550

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

In terms of solid waste management, which is directly linked to sanitation and health, four provinces had clear understanding of their investment and organisational structuring needs. The municipalities are required to develop their five-year strategic plans in 2024, and the earthquake-focused solid waste management plans are being used to draft these strategic plans. As they have a roadmap and defined investment priorities, efficient use of resources should be enabled. Moreover, other municipalities in the region will be able to use the report’s structure as a basis.
The overall output score is A+, indicating that the output moderately exceeded expectations in terms of achieving its targets. The output score is based on what the output delivered during its lifetime.

Output 6.1: Four earthquake-focused solid waste management plans were prepared for the municipalities of Adıyaman, Hatay, Kahramanmaraş and Malatya to ensure the continuity of sustainable waste management which exceeded the initial goal of two business continuity plans. This output indicator substantially exceeded expectations.

Output 6.2: Two street sweepers, part of the urgent waste management equipment, were procured and promptly delivered to the municipalities severely impacted by the earthquake. The delivery of these street sweepers was timely and helped address immediate waste management needs. This output indicator met expectations.

Output 6.3: A dust abatement system was procured and provided to Adıyaman Municipality to reduce dust and asbestos emissions during controlled demolition of damaged buildings. The dust abatement system was delivered in mid-January, with the funding disbursed before the end of the project. However, suppliers prioritised government-funded projects, which caused delays in delivering items ordered outside these government-funded plans. This was one of the reasons the FCDO granted the UNDP a no cost extension until February 28, 2024. This output indicator met expectations.

Output 6.4: 550 waste containers were procured and promptly delivered to municipalities severely impacted by the earthquake: the waste containers were utilised in both residential areas and formal displacement sites. The output indicator substantially exceeded expectations.

Lessons learned in delivering output 6:
FCDO made an unplanned visit with the municipality to a new container city for Syrian refugees where FCDO-funded garbage containers were being used. Residents of the camp were content with these facilities and the camp was clean. The provision of garbage containers, while reducing public health and environmental risk, had the additional benefit of contributing to release acute pressure on waste management needs faced by the municipalities.

Recommendations for future programming from output 6:
In natural disasters, close to conflict areas or where large numbers of refugees may be hosted and affected, it is recommended to use and frequently update a sensitivity lens to mitigate potential tensions between communities and do no harm.

Output 7		Improve food security for people affected by the earthquake
Output Score		Output moderately exceeded expectations (A+)
Impact weighting (%)		4%	Impact weighting revised since last AR?	N/A

Output Indicator 7.1	Starting Target		Final Logframe Target	Final Result Achieved
# of people benefiting from food assistance (parcels and voucher)	DEC Turkey no initial target set / DEC Syria no initial target set		46,138 (target set after 3 months of operations) / 34,440	63,000 / 34,440

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The DEC recalibrated its target for food assistance mid-way through the duration of the intervention, but still significantly exceeded its target. The DEC as a coalition of UK NGOs utilised the funding in an impactful way in the first phase of response through its presence on the ground, existing well-established relationships with downstream partners, reach and technical capacity.

The overall output score A indicated that the output moderately expectations in terms of achieving its targets although no initial targets were set.

Output 7.1:
DEC Turkey, no initial target was set. However, after three months of operations, a target was established at 46,138 people, with the results showing that 63,000 people received food assistance. In the aftermath of the earthquakes, the Turkish Red Crescent, using a range of funding sources, led the provision of hot meals to help people survive. DEC member charities and partners also stepped in to provide additional support to help meet the high level of need. In the first six months of the response, over 63,000 people received food assistance in Turkey through emergency food parcels and vouchers for food through DEC funding.

In Syria, soaring food prices and insufficient income meant millions of families were struggling to make ends meet, during the worst economic crisis Syria had ever seen. Food prices rose dramatically after the earthquakes in the worst affected areas and remained high. In one area of north-west Syria, the price of bread increased by 20% week-on-week. Prices for staple ingredients, like lentils, oil and rice, continued to soar. This meant most people were dependent on food provided by non-governmental organisations and charities. Many DEC charities used appeal funds to provide food over several months to make sure support was substantial and long-term. This output indicator substantially exceeded expectations.

Lessons learned in delivering output 7:
While the earthquakes caused devastation in both Turkey and Syria, the context and situation in the two countries differs significantly. DEC member charities base their decisions on what aid to provide and where depending on the needs on the ground and where other support is being provided. DEC funding has proven to be a crucial flexible funding mechanism for DEC members.

Output 8		Humanitarian assistance is effective, coordinated, principled and accountable according to core humanitarian standard
Output Score		Output met expectations (A)
Impact weighting (%)		7%	Impact weighting revised since last AR?	N/A

Output Indicator 8	Starting Target		Final Logframe Target	Final Result Achieved
8.1 # technical specialists and coordinators deployed (SBP)	2		2	2
8.2 # humanitarian advisers deployed (HSOT)	3		3	3
8.3 # of report informing humanitarian response (H2H)	3		3	3
8.4 # of information dissemination established by NS (National Society (IFRC)	4		4	5
8.5 # of community feedback report collected (IFRC)	4		4	24
8.6 # community feedback collected (IFRC)	26,500		26,500 / FCDO contributed 6.43% (around £115,200 or 128,837CHF) to Engagement with Community and accountability which included consultations, coordination and leveraging between the call centres and report writing.	1,118,753 / FCDO contributed 6.43% (around £115,200 or 128,837CHF) to Engagement with Community and accountability which included consultations, coordination and leveraging between the call centres and report writing.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
The expert resourcing outputs that included SBP and HSOT HAs were appropriately designed and delivered commensurate with the ambition of the response. H2H has proven to be a flexible and appropriate modality designed to reinforce the accountability needs of the affected population: the tools and reports developed were well disseminated and promoted withing the humanitarian community to help ensure people’s needs were met in the most effective and efficient way possible and to enable adjustments to the assistance provided. The IFRC/TRC component with the National Society’s network and reach through its mobilisation of 70,000 volunteers enabled significant amount of community feedback to be collected and analysed.

The overall output score is A indicating that the output met expectations in terms of achieving its targets.

Output 8.1: UN agencies benefitted from access to short-term specialist coordinators and technical experts to help initiate and improve effectiveness of earthquake disaster response activities in Turkey. Two experts were funded by FCDO: one P3 Child protection Officer in support to UNICEF for 3 months (March to June 2023), and one Emergency Coordinator in support to UNFPA for 3 months (March to June). This helped the two agencies to kick start their intervention and recruit longer term staff without facing a critical gap in human resources. This output indicator met expectations.

Output 8.2: One HSOT Humanitarian Advisor (HA) was deployed to support British Embassy Ankara, in the setting up, monitoring and closing of the emergency response to the earthquake in Turkey (note: while there was only one HA position, 3 Has performed this role over different periods of the response). The HAs focused on Government/Strategic Partnerships in Ankara and overall operational coordination and oversight and working as the focal point linking FCDO in London with the field to ensure clear, coordinated action and messaging on the humanitarian response. One HSOT HA was deployed to Gaziantep to work within local coordination structures in the affected region and provide eyes and ears on the ground for contextual analysis; one additional HSOT HA in London was focused on supporting submissions and information requests. This output indicator met expectations.

Output 8.3: In Turkey, selected H2H partners produced independent reports on the needs and gaps in community engagement. These reports helped increase awareness of humanitarian standards through training and provided access to key documents, guidance, and tools in local languages. Additionally, they helped gauge public acceptance and collect feedback from social media, established dialogue with communities, and delivered training on the prevention of sexual exploitation, abuse, and exploitation ({PSEA). H2H is centrally managed under the Humanitarian Enablers Programme by the Humanitarian Response Group in London.

Among all projects submitted there were 3 projects approved for Turkey:
- CHS Alliance: Project in Turkey supported the post-earthquake response to deliver aid that meets quality and accountability standards in line with the Core Humanitarian Standards (CHS).
- CDAC, Clear Global and Insecurity Insight: Project in Turkey and Syria provided contextual data on information and communication in the response, improved responders’ ability including affected people in decision making and enhancing communication with and accountability to diverse stakeholders.
- Ground Truth Solutions: Project in Turkey conducted qualitative research to inform humanitarian actors with the views of affected people and frontline workers about the quality and effectiveness of the response.

This output indicator met expectations.

Outputs 8.4 – 8.6: 6.3% (around £115,200) of FCDO allocation was dedicated to all community engagement and accountability (CEA) indicators which included consultations, coordination and leveraging between the call centres and report writing. IFRC/TRC re-adjusted the percentage as initially set to respond to the major priorities needs of the people (increasing WASH and MPCA but still retained a percentage for CEA).
This output indicator moderately exceeded expectations.

Lessons learned in delivering output 8:
- The lessons learned from Monitoring and Evaluation (M&E) exercises indicate that surveyed households did not feel that they were fully informed about all aspects of the cash programmes. Many recipients reported that they were not informed about the available complaint and feedback channels. In order to ensure transparency and accountability, further communication efforts were reinforced.
- The independent analyses, information, and services provided by H2H were valuable to implementing organisations and decision-makers. They promoted inclusion, localisation, and accountability to affected populations.
- The HSOT HAs were a critical deployment reinforcing staffing capacities at both Ankara and field level to ensure a robust response. However, a key resource missing was a dedicated Senior Programme Manager.

Recommendations for future programming from output 8
- The IFRC/TRC CEA team were committed to verifying announcements and updates with key institutions to prevent misinformation and ensure clarity. Their efforts included actively tracking rumours through manual monitoring of social media and collecting field observations from deployed staff. Additionally, this monitoring helped to assess social tensions and their potential impact on response efforts.
- The H2H Fund activation following the Turkey/Syria earthquakes provided a comprehensive set of products and services to foster improved communication, community engagement and accountability among international actors involved in the response, while improving quality and supporting gaps in logistics and program implementation. This included an ecosystem mapping that provided clear value to international actors seeking to foster a response rooted in communication and community engagement.
- The programme had multiple components and a Senior Programme Manager was surged from across the FCDO global network and provided invaluable support. It is recommended for future emergency responses that programme management as well as humanitarian advisory support is essential for managing a future programme.

D: Value for Money

The benefits of the UK humanitarian response to the earthquakes in Turkey are the lives saved, suffering alleviated, and upholding of dignity of the affected populations. The Programme Operating Framework states that “VfM means that we should aim for the best feasible programme to achieve maximum impact. For example, this would mean a speedy response in the case of humanitarian crises work, where time is of the essence. A speedy response in cases like this is essential where the interventions impact outweighs cost savings which may have been secured with slower paced procurement”. In this programme, the relevance for FCDO is in how quick the programme was able to mobilise resources and in identifying the right quality of delivery partners who were able to provide the most appropriate life-saving response in a cost-effective manner.

Output 1 (ISAR, UK-Med, MoD, DEC Syria):
ISAR: the VfM aspect for this intervention together with MoD interventions was the timely deployment.
Following a direct request from the Government of Turkey to the UK for urban search and rescue, the UK ISAR Team was deployed due to its unique UK standby capacity in ISAR managed under a long-term agreement through the Emergency Deployments 2 (EDT2) programme in HRG. This deployment tested UK ISAR capabilities, with the last earthquake deployment in 2015 into Nepal. UK ISAR demonstrated that it has the ability to deploy a highly effective heavy team with equipment in an excellent response time. Since the recovery phase from Covid-19 duties, UK ISAR has been preparing for such a testing deployment and demonstrated intent to improve with the fastest response team since 2001.
MoD/UK-Med: In response to another direct request to the UK for medical teams with surgical capacity, MoD deployed its standby mobile Type 2 field hospital with surgical capacity. The UK EMT was deployed, via FCDO’s partner UK-Med, because of its standby emergency health capacity to mobilise to a rapid disaster response managed under a long-term agreement through the Emergency Deployments 2 (EDT2) programme in HRG. We assess that this output achieved good value for money since it enabled a rapid and timely response to address increased humanitarian needs.

Output 2 (UNICEF, IFRC, DEC, HSOT):
UNICEF: By rapidly leveraging existing partnership with local authorities, UNICEF’s support to repairing earthquake-damaged systems was more cost-effective than typical delivery modalities common in first phases of humanitarian responses (e.g. Water trucking, provision of bottle of mineral water). We assess this output as good value for money.
BRC/IFRC/TRC: TRC delivers humanitarian assistance at low cost through locally based volunteers. Cash transfers rely on local markets, which were fully functional very quickly after the earthquakes, to supply competitively priced food and domestic items and are more cost effective than the supply-chain logistics for imported in-kind relief and are therefore reaching more people with the same budget.
TRC was a highly efficient first-responder able to mobilise a strong local network of over 11,000 local staff and more than 200,000 community-based volunteers working at 264 branch offices across the country. TRC’s cash-based initiatives rely on market efficiencies for distribution of relief to beneficiaries rather than humanitarian logistics. Support for a common cash delivery platform, utilising the existing ESSN platform, across all sectors of the earthquake response brought efficiencies in software development and maintenance and a reduction in duplication/inclusion/exclusion errors in beneficiary targeting. We assess the output as good value for money.
DEC: DEC Members were able to mobilise funds as soon as the DEC Appeal was launched. An evaluation of cash assistance carried out by one DEC member agency Tearfund shows that 98% of people who received cash said they were able to meet some, most or all of their emergency needs with markets fully functional. We assessed this output as good value for money..
HSOT: Tents, blankets, and hygiene kits were drawn from the FCDO’s stockpile of core relief items and airlifted by the MoD (RAF) to the earthquake zone. With no procurement required, this enabled a rapid and timely response. We assess that this output achieved good value for money.

Output 3 (UNDP, UNHCR, UNICEF, DEC):
UNDP: The effectiveness of targeting vulnerable groups remains questionable with limited attention to equity. The centres for disabilities opened only at the end of the project following delays in procurement and subsequent no-cost extension. This indicator is assessed as poor value for money.
UNHCR: In 2023, UNHCR established partnership agreements with 16 NGOs and national authorities, including two international NGOs that were actively involved in the earthquake response. Approximately 25% of the operational funds (in line with grand Bargain commitments) of UNHCR were allocated under these partnership agreements. UNHCR conducted its consolidated procurement planning and logistics coordination and closely monitored its supply and logistics services in 2023, improving its performance for delivery of goods and services on time. This indicator is assessed as good value for money.
UNICEF: 12,000 USD covered a training of 100 non-protection frontline workers. The cost per non-protection frontline worker trained is 120 USD. AFAD frontline workers reach a wider population (adults and children) that are concentrated in one area such as container cities. The cost per social worker deployed is around 2,400 USD per month including salaries and benefits (as of December 2023). Therefore, with FCDO’s contribution, the costs per child at risk was 1.26 USD. The service cost per individual benefitting from hubs was 22.6 USD calculated from the total expenditures of the 25 UNICEF’s downstream partner’s (ASAM) hubs by the number of beneficiaries within the duration of this contribution. UNICEF leveraged partners’ (MoFSS, civil society) contributions through use of their infrastructure, vehicles, in-kind support, knowledge products, and the collaborative sharing of human resources with other sectoral programmes, including Municipalities and Provincial Department of Social Services, as well as using the same implementing partners to pool together resources to reduce costs to improve the economy of the interventions. This indicator is assessed as good value for money.

Output 4 (UNDP):
The earthquake impacted the capacities of authorities to provide social care services with staff, facilities and equipment severely impacted. The equity aspects were most important in assessing value for money with the intention to target the most vulnerable groups (elderly, children, women and people with disabilities). This intervention achieved its aims and the indicator is assessed as good value for money.
Output 5 (UNDP):
With women and hidden vulnerable groups such as people with disabilities disproportionately more affected by disasters, equity was the key driver of this output. The Accessible Living Centre was specifically designed for the elderly and individuals with disabilities and their care givers; and women accounted for 73.63% of the participants in the vocational trainings hosted at the rehabilitated Women's Counselling Centre.

Output 6 (UNDP):
The project provided 2 street sweepers, 1 dust abatement system, and 550 waste containers, as well as waste management plans for Adıyaman, Hatay, Kahramanmaraş and Malatya metropolitan municipalities, hosting a population of over 5 million. Considering the high number of beneficiaries, the project provided good value for money.

Output 7 (DEC): With DEC Members able to mobilise funds as soon as the DEC Appeal was launched, DEC members responded at speed to address food security needs. We assessed this output as a good value for money.

Output 8 (SBP, HSOT, H2H, IFRC)
SBP: The aim of the Standby Partnership programme is to provide the necessary expertise in a timely manner. To improve programme effectiveness, funding was provided to boost the capacity of partners in emergency coordination and specific technical expertise in Child Protection, and Sexual Reproductive Health. We assessed that this output achieved good value for money since it enabled a rapid and timely response to address increased humanitarian needs and helped the 2 agencies to kick start their intervention and recruit longer term staff without facing a critical gap in HR. This output was assessed as good value for money.
HSOT: Three consultants from HSOT were deployed rapidly on a no regrets basis to support BE Ankara in ensuring response, M&E (including field visits) and project closure. This output was assessed as good value for money.
H2H: Funding for the Humanitarian-to-Humanitarian (H2H) program aimed to increase the effectiveness of aid by giving those affected by earthquakes a greater voice in how assistance would have been provided ensuring that recommendations for aid delivery were locally owned and sustainable. H2H partners played a crucial role in increasing awareness of humanitarian standards and offered training and reported on the prevention of sexual exploitation, abuse, and exploitation. The independent analyses, information, and services provided by H2H were invaluable to implementing organizations and decision-makers. These contributions promoted inclusion, localisation, and accountability to affected populations. Therefore, we assessed this output as good value for money.
IFRC: Several important updates and announcements from various government institutions were adapted to promote concise messaging and shared via Kızılaykart Facebook page in four languages (Turkish, English, Arabic, and Farsi). From 6 February until 15 December 2023, the TRC call centres received 1,118,753 calls regarding the earthquake. The immediate needs identified through community feedback channels (social media analysis and observations made by TRC based on call centre calls) during the immediate aftermath informed the appropriateness of the response. This output was assessed as good value for money.

E: Risk

The Overall risk rating of the programme remained, ‘Moderate’, reflecting the context risk of a humanitarian intervention operating in natural disaster. The identified risks particularly around delivery varied depending on the external operating environment and the delivery model. Well-established programme management practices underpinned the programme’s risk management approach. Partners routinely engaged with respective government counterparts at the local level to discuss challenges, risks, and mitigation strategies. At the closure of the programme, it is recommended to close all risks, except for finance and fiduciary risks. These will remain open as we expect to receive reconciled financial statements from partners, particularly UN organisations, during the financial closure period of the programme.

Throughout the life of the programme, risks were overseen in the first instance by the Programme Team (including PRO) and reported to the SRO. An escalation process was established, which included (if necessary), risks to be escalated to the Head of Mission where they were likely to materialise or breach FCDO Turkey risk appetite. Reviewing the risk register and appropriate mitigating actions remained an integral part of regular reviews and no evidence of fraud, terrorism financing, money laundering/corruption, and safeguarding was found. Key programmes risks are assessed below:

The FCDO primarily mitigated risks working through partners, whose risk management systems have been assessed by FCDO to be of an appropriately high standard. FCDO Turkey had a high-risk appetite for the programme given outstanding humanitarian needs, although judged that the programme was moderate risk only. Funds were channelled to partners with a clear response mandate. We assessed partners to have adequate capacity to mitigate these risks. The programme supported awareness and reporting mechanisms for fraud, corruption and Prevention of Sexual Exploitation and Abuse, but there remained residual risks around these issues. Further details were included in the programme risk register, but we considered that partners had adequate systems, procedures, and mitigation measures in place.

Fiduciary Risk: Cash could be more at risk of theft and easier to divert, while cash transfers pose different corruption risks. At the same time, cash could be subject to corruption including by aid agencies and staff through staff colluding to transfer money and divert funds. However, cash programming in Turkey is a well-established and mature modality for humanitarian response.
DEC developed a specific collaboration with a third party to support the implementation of accountability and monitoring and evaluation activities. Moreover, IFRC and DEC set up a complaint and feedback mechanism that allowed beneficiaries to raise complaints and provide feedback confidentially. IFRC/TRC have robust tracking systems at all stages of the supply chain from procurement to distribution and robust risks matrix in place. Over 85% of the funds to the IFRC/TRC are for a cash-based intervention. The data protection, monitoring, feedback, and distribution mechanisms were effective controls against financial and fraud risks. Risk of fraud in the cash-based intervention was assessed as low due to robust mitigation measures.

Safeguarding: In humanitarian contexts there are always safeguarding risks due to the lack of appropriate assurances/measures to identify and prevent violence, exploitation, or abuse and all forms of physical or emotional violence or abuse and financial exploitation, abuse of authority and blackmail. Such risks were mitigated by conducting enhanced due diligence assessments on safeguarding for all partners which demonstrated that partners had measures in place to detect, investigate, and report on any safeguarding issues.
All programme partners had robust policies to prevent and address misconduct and have made strong corporate commitments to safeguarding that have been assessed as part of enhanced due diligence processes. Humanitarian partners committed to zero tolerance on bullying, harassment and sexual exploitation and abuse, and were required to report any credible allegations of fraud or abuse. Partners committed to strengthen prevention and mitigation of sexual violence; and survivor-centred approaches. Humanitarian partners have also undertaken enhanced due diligence to assess organisational safeguarding policies and processes. In the earthquake response, programme activities included creation of safe spaces for protection of women and children and reduction of risks of violence. The programme established a mechanism for safe referral of women and children at risk and victims of abuse, violence, and exploitation. The programme supported protection activities that prevented violence against boys, girls, and women, with a focus on GBV and provision of mental health and psychosocial support. Numerous humanitarian actors, including the Turkish Red Crescent had toll free feedback/complaint call centres for reporting of any safeguarding concerns. The feedback mechanisms were widely publicised to increase awareness. Activities by H2H partners in the programme increased awareness, advocacy and built the capacity of humanitarian actors on the protection of sexual exploitation, abuse, and harassment (PSEA).

Strategy & Context: Overall, the humanitarian context remained uncertain throughout the implementation phase with notable risks around aftershocks and limited funding for the response from the international community. The programme team effectively mitigated this risk by working with all stakeholders to prioritise humanitarian response based on the needs of the affected population and flexibility for scale-up and down when needed. Programme partners collaborated closely with government departments and officials to effectively address humanitarian response delivery challenges on the ground. The BE Ankara team established strong working relationships with all relevant government departments.

People: People risk (internal and external) was assessed at moderate level. To quickly mobilise the humanitarian response, BE Ankara filled temporary positions and utilised the Humanitarian Support Operations Team (HSOT) to fill the logistician, humanitarian affairs, and communications gaps within the development team. In parallel, multiple Standby Partnership Personnel were also deployed to the UN organisations with support from the FCDO’s Humanitarian Response Group.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summary performance of partners and FCDO
Following ministerial approval on 7 and 14 February 2023, the programme team swiftly mobilised the programme funds against the approved submissions. This was in line with the Programme Operating Framework (PrOF) rules which allowed exemptions for delivery of life saving humanitarian support ahead of business case development and approval. Given the need to respond quickly to minimise loss of life and prevent transmission, the FCDO called upon standby expertise in the UK and funded DEC, IFRC and UN Earthquake Appeals.

The quality and scope of all programme deliverables were according to the standards and specifications, and any changes owing to context were made in coordination with other humanitarian partners and with approval of the BE Ankara team. Interventions and beneficiary targeting details were harmonised, to a greater extent. This was achieved through a detailed review of the partners’ concept notes and proposals to confirm inclusion and completeness of assessment, assumptions, and risk analysis with mitigation measures, workplan and contingency plan, as well as clear linkages with resources requested.

Direct procurement
No new direct procurement through a commercial tender or framework was feasible under this programme due to the urgent nature of the emergency response and limited duration of the humanitarian intervention and overall life cycle of the programme.
The only commercial contract managed under the programme was an existing contract with a commercial supplier centrally managed by the FCDO’s headquarters (under the Humanitarian Emergency Response Operations and Stabilisation programme), which allowed FCDO to draw down capabilities such as procurement, logistics, and contracted experts to supplement FCDO technical humanitarian capacity.

Indirect procurement
The rapid onset of the earthquake disaster caused acute needs demanding an urgent response. This greatly restricted the time for selecting and processing commercial contracts and accountable grants with partners. The FCDO’s humanitarian team was in direct contact with operational humanitarian organisations in the earthquake zone. With reference to UN and IFRC Emergency Appeals, informal negotiations were held with various responding organisations and project concept notes were accepted from the best positioned agencies. The selection of humanitarian partners to implement the programme was based on their presence, the relevance of their proposed activities and a quick judge of their response capacity. The choice of partners was reinforced by trust from ongoing global partnerships, and rests on assurance from framework agreements that are in place with the selected agencies to facilitate rapid contracting to initiate implementation.

Following a direct request from the Government of Turkey to the UK for urban search and rescue, the UK ISAR Team was deployed due to its unique UK standby capacity in SAR managed under a long-term agreement through the Emergency Deployments 2 (EDT2) programme in HRG. Based on their appropriateness to meet needs and immediate availability with no procurement, tents, blankets, and hygiene kits were drawn from the FCDOs stockpile of core relief items and airlifted by the RAF to the earthquake zone to meet urgent needs.

On another direct request to the UK for medical teams with surgical capacity, MoD deployed its standby mobile Type 2 field hospital with surgical capacity. The UK EMT was deployed, via FCDO’s partner UK-Med, because of its standby emergency health capacity to mobilise to a rapid disaster response managed under a long-term agreement through the Emergency Deployments 2 (EDT2) programme in HRG.

Given the unique capacities of specialist organisations in the Humanitarian-to-Humanitarian network, under the centrally managed Humanitarian Enablers Programme, the Humanitarian Response Group activated rapid funding for members of the H2H network to provide demand-driven, strategic products and services for humanitarian responders and FCDO to improve effectiveness of relief operations.

£5 million was allocated to the UK’s DEC Appeal as match funding. The DEC launches appeals in response to humanitarian emergencies around the world. The DEC is made up of 15 members charities who are experts in humanitarian aid and specialise in different areas of disaster response. They come together to speak with one voice and make fundraising more efficient when an appeal is launched. Appeals are launched within 24 hours of a disaster when there are both significant humanitarian needs and media interest. The DEC raised over £143 million since the appeal launch (including the £5 million in UK aid match) to support Syria and Turkey in the wake of the devastating earthquake.

The cost of the DEC Secretariat is modest, with its core operating costs met by its member agencies. It is able to make use of 3% of FCDO’s funding to cover its overheads costs. DEC caps overheads for its member agencies at 7%. These costs cover quality assurance, financial management, and reporting, including serious incident reporting requirements. DEC funds INGOs using its own grant allocation processes and eleven DEC charities were responding, either directly or through local partners, and have been among those helping to save lives and provide emergency relief.

The Red Cross Movement (BRC/IFRC/TRC) was selected because TRC is an auxiliary to government and first responder with full humanitarian access throughout the earthquake zone. The TRC has trained, equipped teams working from operational bases in affected areas with demonstrated capacity to provide immediate relief in disasters in Turkey. The FCDO has a strong relationship with the British Red Cross and negotiated a memorandum of understanding for contributions to IFRC emergency appeals. All funds provided to IFRC are channelled through the British Red Cross Society (BRCS) based on a standard MoU arrangement. There is a valid Due Diligence Assessment (DDA) in place with BRCS, and a Central Assurance Assessment (CAA) in place with IFRC, to whom BRCS would transfer the funds. IFRC then transferred and accounted for resources provided to the TRC based on IFRC standard reporting procedures. Oversight of this funding was provided through the IFRC regional office in Budapest.

UNHCR having field units and partners in place, remained best placed to expand existing specific-needs assistance programmes to rapidly respond to the EQ. The FCDO has a global relationship with UNHCR and negotiated a Memorandum of Understanding for contributions to IFRC emergency appeals.

UNICEF had a longstanding presence in Turkey, a well-established field office in Gaziantep and partnerships with authorities in 5 earthquake affected municipalities to facilitate quick delivery of disaster assistance. The FCDO has a strong global relationship with UNICEF and negotiated a Framework Arrangement for restricted contributions from the UK to UNICEF for programmes, projects, and activities.

UNDP has been operational in Turkey since the 1950s, and has built solid partnerships with the government ministries, municipalities, and private sector to support quick start-up and implementation of activities. The FCDO has a global relationship with UNDP and negotiated a Framework Arrangement for restricted contributions from the UK to UNDP for programmes, projects, and activities.

Indirect procurement accounted for the full £17 million spend, through MOUs and contribution agreements with international humanitarian partners that have proven previously reliable, accountable, and effective.

Key cost elements that affected the overall price for different programme arrangements
- Procurement of Supplies (MPCA, Shelter, NFIs and Health and Food): Procurement of inputs (NFIs, shelter material, medical supplies, and value of cash transfers) was likely to constitute the main cost driver of this short humanitarian response programme. Priority was given to Government funded projects, at the expense of all other responders. FCDO agreed with UNDP for a no cost extension. Delays in procurement due to congested supply chain and volatility of the market prices was the main reason to grant a NCE to UNDP. There was no impact in finances as funds were already committed.
- Human Resource Costs: Management Fees and salary costs of technical experts and service providers including administration cost and reimbursable costs (such as office and subsistence related costs).
- Exchange Rate Fluctuations: Adverse movements in exchange rates could have impacted on the programme’s ability to deliver results. Budgets were based on sterling commitments and managed in line with the FCDO budget policy.
- Transport: Some areas had difficult terrain, particularly the worse affected provinces. Transport of supplies in particular were likely to entail a higher cost in these areas (average inflation rate for 2023 in Turkey was at 58.94%)

The FCDO ensured open book accounting for cost transparency and set out clear expectations for its delivery partners on driving VfM. FCDO programme delivery experts in BE Ankara and monitoring teams were continuously engaged to ensure that a) costs reflected market prices; b) overheads were reasonable and in-line with fee caps pre-determined against the central frameworks; and c) delivery partners had the capacity to implement the programme effectively. Delivery partners were responsible for managing local taxation issues and changes in costs due to currency fluctuations, inflation (currently around 60%).

Assurances obtained on capability and capacity to deliver.
As highlighted above, there was good evidence that all selected and proposed partners had the technical capacity and strong governance structures to deliver quality humanitarian aid representing VfM. The programme team held regular review meetings with each partner. Partners had clearly defined reporting timelines (implementation and closure) against milestones/targets with a focus on compliance to risks and financial management requirements. Delivery chains were comprehensively mapped and agreed with all partners to highlight key risks across fund flows. Prior to entering agreements, FCDO ensured a satisfactory level of due diligence for assurance that each partner had the requisite capacity to deliver, account for funds and report. Any risks within tolerance levels identified were included in the risk matrix, mitigated, and managed.

Programme-level approach to monitoring and evaluation
Due to the limited life of the programme i.e., initially nine months and later sixteen months, the programme opted to rely mainly on partner reports and visits by the BE Ankara team for programme monitoring. Considering the nature of immediate relief, response, and recovery interventions under an overall short duration of programme interventions, i.e. less than a year, a standalone independent monitoring component was not feasible to be included in the programme. The Development Section at BE Ankara had regular assessment of partner progress, access to the programme sites and relevant donor and government counterparts. The programme had a formal multi-tiered monitoring system for all programme components, to manage both technical and delivery aspects of programme response. The proposed implementing partners predominately used their own internal monitoring systems. Most programme partners conducted programme specific Post Distribution Monitoring (PDM) surveys as part of respective underlying delivery arrangements, which were shared with the BE Ankara team. The PDM reports generated significant evidence for the effectiveness of programme interventions. A range of monitoring tools were deployed including:
- Logical framework targets and key performance indicators.
- Regular progress meetings provided updates on the progress of the programme, these was followed by meeting readouts to formalize all progress update.
- FCDO staff field visits during the programme implementation allowed staff to monitor the implementation of activities by partners and informed the programme team on the challenges and the evolution of the needs and context in the target areas.
- Financial audits were in place for partners where required and feasible to mitigate fiduciary risk.
- Programme Completion Review.

Each delivery partner proposed a detailed monitoring framework as part of the proposal. A robust monitoring system was put in place for all outputs of the programme to assess performance against the logical framework and agreed KPIs, designed and led by the programme partners with oversight from the FCDO programme management team. A mix of both attribution and contribution KPIs was agreed early on during the finalisation of the logical framework. All tools were linked to the Theory of Change and described the data requirements, data sources, data collection and analysis, and how monitoring would be undertaken. The information produced were used to inform the FCDO Programme Completion Report; and to ensure learning, course correction and programme excellence. Dates for programme reports from each partner were detailed in MoUs and Contribution Agreements which were fully adhered by all programme partners.

Date of last narrative financial report	DEC – July 2023 / UK Med – Feb 2024 / IFRC – August 2024 / UNDP – July 2024 / UNICEF – July 2024 / UNHCR – December 2023	Date of last audited annual statement	IFRC – Feb 2024 / UNDP, UNICEF and UNHCR – Expected March 2025