## Annual Review Template

Title: The Democratic Republic of Congo - Green Growth Programme
Programme Value £ 20.64m		Review date:
Programme Code: 400011	AMP start date: 02/11/2024	AMP end date: 15/11/2029

Summary of Programme Performance
Year	2024/2025
Overall Output Score	B
Risk Rating	Major

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Logical Framework

A. SUMMARY AND OVERVIEW

Description of programme

The Green Growth programme will support the development of a more productive and climate-smarter agriculture sector, delivering jobs and supporting a more diversified economy. It is separated into four components;

- Component 1 (Improving the business climate): A non-ICF component will work to overcome the binding policy constraints faced by agri-businesses that require champions and reform at the centralised or provincial government level.
- Component 2: Growing climate smart agri-businesses: An ICF component will work directly with agricultural firms to test and embed new business models and technologies required for smallholder farmers to implement climate-smart agricultural practices.
- Component 3 (Scaling finance for agri-businesses): An ICF component will create deep partnerships with a small number of banks, financial intermediaries and/or fund managers to increase access to finance for agribusinesses
- Component 4 (Monitoring, evaluation and learning): This component will invest in the long-term monitoring, evaluation and learning function of the programme
Changes in UK ODA have resulted in key changes to this programme, notably a reduction in financing. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

The programme has scored a B. Due to the changes of ODA and subsequent budget review the programme has been significantly delayed.

Early programme activities were focused on the procurement of programme components. Many of the milestones associated with this procurement activity were met, however later milestones were not achieved due to ODA changes and budget reviews.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

The Programme continues to be procured. The Theory of Change is unchanged.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Ministries are better equipped to incorporate climate change into sectoral policies to boost investment and better manage climate risks.
Output number:		1	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
Successful procurement process for Component 1 & 2 supplier	Terms of reference and sourcing strategy document finalised. Engagement with the market has taken place. Invitation to tender has been issued. Tenders are marked and assessed. Contract with C1 & C2 supplier is in place. Supplier has begun its inception phase, in preparation for delivery.	Terms of reference and sourcing strategy document finalised. / Market engagement with potential suppliers has taken place. / Invitation to tender has been issued. Procurement continues.

The procurement process for Components 1 and 2 of the Green Growth Programme commenced with the completion of the Terms of Reference and sourcing strategy. Initial market engagement was undertaken to assess supplier interest and capacity, followed by the issuance of the invitation to tender. Bid submissions were received and evaluation is continuing in line with established criteria.

Given ODA budget announcements procurement was paused which has resulted in an unforeseen delay to delivery of our planned objectives.

Output Title	Agribusiness trail business plans and activities to reach new markets that support smallholder farmers to implement new climate smart techniques in keeping with sustainable land use plans.
Output number:		2	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
Successful procurement process for Component 1 & 2 supplier	Terms of reference and sourcing strategy document finalised. Engagement with potential suppliers has taken place. Call for bids has gone out to the market. Bids are marked and assessed. Contract with C1 & C2 supplier is in place. Supplier has begun its inception phase, in preparation for delivery.	Terms of reference and sourcing strategy document finalised. / Engagement with potential suppliers has taken place. / Call for bids went out to the market.

Briefly describe the output’s activities and provide supporting narrative for the score.

As above.

Output Title	Greater volumes of financial products designed and disbursed to agri-businesses from financial institutions for climate-smart activities.
Output number:		3	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
Successful procurement process for Component 3 supplier	Scope of Requirements documents finalised. Engagement with potential suppliers has taken place. Call for bids has gone out to the market. Bids has been assessed and marked. Agreement is in place with supplier. Supplier is delivering relevant deliverables in inception phase.	Significant market engagement and request for proposals to meet outcomes for component 3 in process of being sent out for bids.

Briefly describe the output’s activities and provide supporting narrative for the score.

A reduction in ODA funding necessitated a reassessment of budget allocations and programme scope, resulting in delays to timelines. We are continuing the process of selecting a supplier to deliver this component.

Output Title	Successful procurement process for third party monitor
Output number:		4	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
Successful procurement process for third party monitor	Terms of reference and sourcing strategy document finalised. Engagement with the market has taken place. Invitation to tender has been issued. Tenders are marked and assessed. Contract with third party monitor is in place. Supplier has begun its inception phase, in preparation for delivery.	This has been delayed given changes in ODA.

Briefly describe the output’s activities and provide supporting narrative for the score.

The procurement process for the Monitoring and Evaluation (M&E) component advanced to the final stages of preparation, with the Terms of Reference nearly complete and strong interest expressed during initial engagement with potential suppliers.

However, following a reduction in the overall ODA budget, we are in the process of reassessing how best to deliver this component.

## D: VALUE FOR MONEY (1 page)

No spend has taken place under this programme this year.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk rating for this programme is Major. This recognises the context of operating in DRC. This programme will be implementing activities which are new for the FCDO in DRC; this is also factored into the risk rating. The programme will take a responsible approach to these risks by maintaining robust risk registers, which will include effective mitigations and clear avenues for escalation should a risk require it.

A risk register has been created outlining gross risks, mitigating measures and residual risks, and will be updated as we finalise agreements with partners. It will then be maintained and updated at least quarterly for the programme. Major and severe risks, or quickly evolving risks, will be reviewed more often and any risks falling outside of the BEK risk appetite will be escalated to the Development Director and Ambassador.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

NA

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

NA

Date of last narrative financial report	NA	Date of last audited annual statement	NA