## Annual Review of the UK’s contribution to the Reserve Account of the IMF’s Resilience and Sustainability Trust

Title: Annual Review of the UK’s contribution to the Reserve Account of the IMF’s Resilience and Sustainability Trust
Programme Value £ (full life): £44,090,383.13		Review date: 4 August 2025
Programme Code: [AMP ID#] 400012	AMP start date: 04/05/2023	AMP end date: 30/03/2026

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400012 Documents
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The Resilience and Sustainability Facility (RSF) is an IMF lending facility that provides loans to developing countries, including at concessional rates for the most vulnerable countries. It sits within the Resilience and Sustainability Trust (RST). The loans support countries to address long-term structural challenges that will improve their prospective Balance of Payments stability. To date, most RSF loans have focused on addressing climate-change related challenges. One RST programme has focused on addressing pandemic preparedness.

The UK’s £44mn ODA contribution facilitated Special Drawing Rights (SDR) loans by the UK to the RSF of SDR 1.8bn (circa £2bn), by providing the cash contribution needed to establish a satisfactory level of reserves. These reserves allow for the management of RSF credit risk, ensure that the reserve asset status of SDR contributions is maintained and safeguard IMF resources.

Summary supporting narrative for the overall score in this review

Since the 2024 Annual Review, the IMF has continued to deliver a strong portfolio of RSF programmes across a range of geographies. The programme has scored an A overall for the period under consideration. Reform measures established under the programmes are generally considered to be well-tailored and aligned with countries’ own domestic plans. Consultations with UK overseas missions report mixed successes regarding IMF collaboration with development partners in country, with IMF engagement focussed upon review missions rather than ongoing integrated delivery.

The IMF has initiated 8 new RSF lending programmes since the last review and committed an additional SDR 4.4bn. This has meaningfully contributed to the development of climate resilience in some of the most vulnerable countries, though the rate of programme agreement has slowed somewhat relative to the first 18 months of the programme. Achievement of reform measures by the originally scheduled date of completion stood at 76% at end June 2025, indicating substantial progress in implementation of reforms, though there is still room for improvement in setting the appropriate level of programme ambition for each individual country and in driving timely implementation.

Strong fiduciary measures have assured that reserves are adequate to safeguard Fund resources in a variety of stress scenarios. The IMF are confident that resources are adequate to meet near-term demand for the facility, estimated between SDR16bn and SDR20bn (circa £16.3bn and £20.3bn).

Major lessons and recommendations for the year ahead

A number of aspects of the RST will be explored through the IMF’s upcoming Comprehensive Review of the RST.

Given the tranched nature of RSF disbursements and the fact that RSF programmes do not include a disbursement at programme approval, the level of disbursements and the evidence of reform measure success will accelerate in the coming year, as more programme bed in.

A key area for the IMF to consider in more depth in the year ahead is how to better tailor RSF programme ambition and timescales to the capacities of the authorities in each country. In particular in small island developing states and in fragile contexts, the completion of ambitious reform measures within the relatively short time horizon of an RSF programme, while simultaneously delivering reforms of the underpinning UCT programmes, must continue to be carefully calibrated.

The IMF is generally working effectively with traditional partners, such as Ministries of Finance and Multilateral Development Banks (MDBs) in the development and delivery of RSF arrangements. Given the broad and complex nature of resilience related reform measures however, a deeper and more consistent integration into countries’ development architecture is merited, sustaining engagement through climate finance roundtables and expanding the IMF’s presence in relevant coordination forums.

With regards reform sustainability, more emphasis should be placed on how the IMF and other partners can support authorities to maintain the gains achieved under an RSF programme and ensure that the ambitions of the programme continue to be pursued and implemented after individual programme completion. In the event that a successor RSF programme is requested, it must build on the foundations achieved in the initial program. We see an important role for IMF surveillance operations in overseeing continued reform implementation, reinforced by capacity development where needed. The donor coordination mechanisms established through the RSF would ideally also be pursued by other partners beyond the end of the RSF programme.

Whilst reform measures in RSF programmes generally align well with countries’ policies, ongoing consideration should be given to the correct balance of mitigation-focused and adaptation-focused reforms. The right balance will depend on the individual country’s economic profile and the level of vulnerability that that country faces.

The FCDO should ensure that its climate-related technical assistance offer to partner countries aligns closely with the RSF reform measures and provides additionality to the capacity development that is supported by the IMF. To this end, where appropriate, FCDO should look to engage at an early stage with climate roundtables and other climate action coordination mechanisms in-country.

We continue to encourage the IMF to explore more flexible models for donors to contribute to the RST’s fundraising needs without being too rigid on the division of financing between the reserve account and loan account for any individual contributor.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

INPUT	ACTIVITY	OUTPUT	IMPACT/OUTCOME
UK makes contribution to the RST. The IMF disburse loans via the RST to vulnerable countries on concessional lending terms with long-term maturity.	IMF and country agree policy conditionality on loans, ensuring that the regular disbursals of RST finance are only delivered once programme benchmarks are completed by the borrowing country.	Strengthened public financial management related to climate change/pandemics. E.g., for climate - Identification of climate vulnerabilities and financing needs. Stronger country policies relating to renewable energy and transition. Stronger climate-based investment management.	Countries with RST programmes are more resilient to climate variability and pandemic risk, and thus capable of more sustainable patterns of economic growth, financial stability and resilience. Economic and human loss is reduced during crises including pandemic/epidemic disease and climate-related events.

The Theory of Change (ToC) set out in the business case in 2022 remains valid. As the global economic environment continues to place considerable pressure on the public finances of vulnerable countries, the RSF provides additional financing dedicated to reforms that improve climate resilience. Considering the profile of countries that are accessing RSF lending and the impact/ outcome statement of the Theory of Change, it will be important to ensure that adequate emphasis is placed on elements of RSF programmes that support adaptation activities.

It is too early to draw inferences about the impact and outcome of the RSF agenda as a whole, given that only 3 programmes had completed by end 2024. Establishing a mechanism between authorities and cooperating partners to sustain the gains of RSF programming will be vital to ensuring sustained impact of the reforms and financing.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Due to the nature of the programming to date, impacts will be delivered almost exclusively in the area of resilience related to climatic events, rather than pandemic preparedness.

The programme is, on aggregate, on track to contribute to the expected outcomes, with some variance in the success levels in individual lending programmes. Achievement of reform measures to the timescale set out in the original programmes sits at 76%.

The IMF anticipates that 13 RSF arrangements will be approved during FY2026, implying new commitments of about SDR 5.2bn (circa £5.3bn). The RST Comprehensive Review in FY 2027 will be an important opportunity to take stock of the successes and challenges of the programme, make any design amendments required and consider the medium-term level of demand for the facility.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The main ambition of the RSF - to build countries’ resilience to Balance of Payments shocks arising from climate change - aligns very clearly with the UK’s priorities. The unique financial structure, which allowed the £44mn ODA contribution to leverage resources in the region of £2bn made it a very strong proposition.

The UK continues to be a very strong advocate for climate action, as was evidenced most recently at London Climate Action Week. An ambitious climate and nature agenda is one of FCDO’s six priorities. This agenda includes:
- Mitigation, whereby ambitious Nationally Determined Contributions lay the ground for successful COP30 outcomes,
- Finance, whereby UK leadership unlocks greater volume and quality of climate and nature finance from the global financial system
- Adaptation, whereby more LDCs and SIDS have increased capability and finance to respond and adapt effectively to climate risks and impacts.
The RSF tangibly contributes to each of these ambitions.

## C. DETAILED OUTPUT SCORING

Output Title	Number of RST programmes implemented
Output number:		1	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of RST programmes agreed and implemented since the interim review	Function of demand [circa 10 per annum].	8 programmes were agreed between the interim review and end-June 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

There continues to be strong demand from borrower countries for RSF programs - as at end February 2025, about 30 countries were interested in an arrangement. The IMF stepped up its human resourcing significantly to respond to the challenge of delivering a significant volume of programmes that required climate expertise. Although the rate of agreement of new programmes is somewhat lower than the rate over the initial 18 months of RSF implementation, the 8 programmes agreed in this period included two maximum-access programmes (Egypt and Pakistan, SDR1bn [~£1bn] each) and one programme related to pandemic preparedness, all of which will have required considerable design input.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output metric maps to output 3 from last year’s review. The division between programmes related to climate change Balance of Payments (BoP) stability and pandemic preparedness BoP stability has been dropped. This reflects that the focus of demand for RSF programmes has been very heavily weighted toward climate change programmes and that the IMF, guided by the Board, has focused human resourcing uplifts in the area of climate expertise.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The previous review identified the risk that climate expertise could be diverted from other key work, like routine surveillance and noted that this should be considered when setting the appropriate scale of ambition on this output going forward. Continuing to adopt a measured approach to resourcing- balancing the need to respond to the high level of programme demand against competing demands of those IMF staff with climate expertise (e.g. incorporating climate risks into surveillance and forecast activities, ensuring that UCT programmes have the flexibility to respond to major climate shocks and forecasting activities) will be important.

Ensuring that those countries that are most vulnerable to climate change (e.g., as measured by the ND-GAIN vulnerability index) and meet the eligibility criteria for the RST are supported to attain a RST program is important.

Output Title	Volume of RST resources committed
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	New metric included

Indicator(s)	Milestone(s) for this review	Progress
Volume of RST resources committed since the interim review	4.8bn SDR (~£4.9bn)	4.4bn SDR(~£4.5bn)

Briefly describe the output’s activities and provide supporting narrative for the score.

The milestone for this metric was set based on an assumption that a rate of resource commitment similar to that observed in the initial 17 months of the programme would be sustained.

A measure of the overall volume of finance disbursed has not been included as a target output measure here, as the separate output on the proportion of reform measures implemented performs a similar function. This reflects that RSF disbursements are directly related to the attainment of specific RSF reform measures. As at end-February 2025, total RSF disbursements had reached approximately SDR 3.3bn (~£3.4bn).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was added to the review this year to reflect the importance of good use of the RSF’s available lending finance. Given the scale of demand from borrowers, it’s important that the IMF keep pressing to deliver new arrangements where countries meet the qualification criteria, thereby making use of the SDR that were voluntarily channelled by donor countries. Of course, the rate of resource commitment is not purely within the gift of the IMF and will depend upon the pace of discussions with authorities on both RSF arrangements and the underpinning UCT-quality programmes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The volume of finance made available continues to be guided in most cases by the norm of 75% of quota access or, in the case of particularly high-quality packages, the maximum access of 150% of quota or SDR 1bn [~£1bn] (whichever is lower). In some instances, programmes to the value of 75% access are agreed in the knowledge that a programme of similar value will likely be requested as a successor programme. The appropriateness of these proportions of quota access should be considered through the RST Comprehensive Review, along the relationship between the volume of RSF financing lent and the volume of finance required to meet climate-related Balance of Payments risks.

Output Title	Reserve Adequacy is maintained in the Reserve Account
Output number:		3	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Reserve Coverage	10% reserve coverage benchmark	Projected minimum net reserve coverage of 11% of credit outstanding

Briefly describe the output’s activities and provide supporting narrative for the score.
Ensuring that adequate reserves are maintained to cover potential non-repayments is a key safeguard measure to mitigate credit and liquidity risk for the RST. The Reserve Account primarily provides this function, although there is provision for the Deposit Account to act as a backstop to the reserve account in an extreme tail risk scenario.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The IMF updated its assessment of reserve adequacy relative to that presented at the time of the Interim Review. The updated model includes:
- A higher-than-expected medium term interest rate (SDRi). The SDRi rate is assumed to eventually return to the long-term average of 3%
- An updated assumption of SDR24.6bn [~£25.03bn] for pledged loan resources
This level of reserve coverage is lower than that projected at the time of the Interim Review, but remains above the 10% benchmark. This is mostly due the upward shift in projected SDRi path resulting in a higher cost to subsidising lending to Group A countries.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

It is important that the annual resource adequacy papers and the upcoming Comprehensive Review of the RST continue to revisit reserve adequacy as underpinning assumptions may change and the cost of the interest rate subsidisation for Group A lending fluctuates.

Output Title	Reforms that enhance Balance of Payments resilience implemented by borrower country
Output number:		4	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	The weighting was increased from 25% to 30%, reflecting the shift in focus from establishing the RST facilities to implementation.

Indicator(s)	Milestone(s) for this review	Progress
Proportion of / reform measures that are / implemented by borrower countries	85%	76% of the approved reform measures scheduled to be completed on or before 30 June 2025 were implemented.

Briefly describe the output’s activities and provide supporting narrative for the score.

A distinctive feature of RST programmes, which differs from other IMF lending, is the direct dependency of a disbursement on the delivery of a specific reform measure. This links this output to the volume of RSF finance disbursed.

Implementation of reform measures (against the originally scheduled timeframe) has fallen somewhat short of the milestone. The shortfall reflects factors such as administrative capacity constraints and political challenges in delivering high-ambition reforms. It should be noted that, through delayed or rephased implementation, many of the 24% of reform measures that were not implemented may yet be achieved.

Through the RST Comprehensive Review in FY2027, the IMF is likely to consider in detail the success of reform measure implementation. The UK will encourage the IMF to look at the variation in this metric between geographies and between different categories of borrowers- e.g. considering how the rate of reform measure implementation differs for SIDS, fragile states, according to RST grouping etc.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Again, the distinction that was previously drawn for this output between climate reform measures and pandemic preparedness reform measures has been dropped, reflecting that all but one RST programme relates to climate change BoP risks.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

It is still early to make inferences about reform measure implementation, but it seems that in some instances those countries with particularly low administrative capacity are struggling to meet the ambitions and timescales of the RST programmes. Greater calibration to capacity in these cases may be required.

In a similar vein, the comprehensive review should give consideration to lengthening the RST programs or developing upfront a clear sequencing to a successor RST program to allow countries the necessary time to adopt reforms in a way that is truly sustainable and impactful.

Output Title	Alignment of RST programmes with approaches of internal and external partners
Output number:		5	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	The weighting was increased from 10% to 15%, reflecting the shift in focus from establishing the RST facilities to implementation.

Indicator(s)	Milestone(s) for this review	Progress
Evidence of close working / with development partners in / relevant countries	Qualitative feedback from FCDO economists and climate advisors.	Met. Assessment from posts on IMF-WB coordination was more variable, but generally positive. / Deeper IMF-WB coordination is being piloted in some RST countries, in particular Madagascar and Tanzania.
Evidence of close working / with development partners in / relevant countries	Clear coverage in RST documentation of climate-related activities being carried out by development partners that supports or complement the RSF program.	Met. Delivery coordination with other development partners has been outlined in most RSTs but with varying depth of alignment. RDB co-delivery is particularly strong in south Asia and the Caribbean and Energy reforms align most regularly with bilateral donors.
Evidence of alignment of / RST programme with / domestic plans of borrower / governments	Evidence of a discussion between IMF Staff and the authorities of the country’s own climate policy objectives- as set out in the RST documentation.	Met. IMF staff notes consistently update on engagement with government partners. RST updates clearly align and build on national climate policies and plans.
Alignment of RST programme ambitions with IMF Capacity development work and climate diagnostics	Evidence from FCDO network.	Met. There is evidence of drawing on C-PIMAs where these have been delivered in RST countries. WB Country Climate Development Reports have been drawn on at design stage but there is less evidence of them iteratively informing delivery if published post-arrangement.

Briefly describe the output’s activities and provide supporting narrative for the score.

Based on feedback from the FCDO network overseas, RSTs were found to complement wider existing strategic and programmatic coordination well (10 out of 12 FCDO survey respondees scored 5 or above on a scale of 1-7) and coordinated MDB support of different country climate objectives was particularly effective (all scored 5 or above out of 7)

Where available, IMF and World Bank analysis were drawn on to frame and inform arrangements, though this was somewhat inconsistent. New guidance has been issued on delivering enhanced IMF-WB cooperation in priority countries.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output was amended somewhat this year to reflect the formalisation of WB-IMF cooperation through the Enhanced Cooperation Framework for Scaled Up Climate Action and the commitment to pursue joint policy matrices in a small number of pilot countries.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Where the IMF has led climate roundtables, particularly in its ‘pilot countries’, they have often led to considerably improved donor coordination in the support required to deliver the reform measures. Mixed success was reported on climate finance roundtables.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
Administrative costs, which are funded primarily through investment income from the reserve account contributions, are projected to be in the region of SDR 25mn per annum.

VfM performance compared to the original VfM proposition in the business case

The case for investment in the climate resilience of vulnerable countries is as compelling as ever and, as above, constitutes a top priority for FCDO.

The strong reserve position of the RST and the associated strong investment returns have allowed the IMF to maintain the 2.25% cap on lending to Group A countries, which represents a more concessional offer than was set out in the original business case.

Assessment of whether the programme continues to represent value for money

By providing the requisite 2% contribution to the RST’s reserve account, the UK’s £44mn ODA contribution facilitated on-lending of SDR worth in the region of 40 times that amount, the reserve account contribution to the RST represents excellent value for money. At the same time, when it comes to the Comprehensive Review of this facility, we encourage the IMF to explore financing approaches that allow for greater flexibility in how individual donors can contribute to the different accounts of the RST.

E: RISK

Overview of risk management

The overall risk level of the programme is moderate, which matches the risk appetite.

Risks related to policy and programme delivery are broadly common to all UK lending to the IMF and are mitigated through the IMF’s robust management frameworks. The UK Executive Director to the Fund and their office, as Board representatives, are responsible for working with a range of UK government departments, as well as IMF staff and management, to ensure that any risks are mitigated.

There is a risk that amplified global economic risks undermine elements of the RST programming. Globally, macro-financial and fiscal risks are amplified, which has contributed to financial volatility. These trends may pose a risk to the ability of countries to shore up their long-term BoP resilience.

There is a risk that governing authorities of borrowing countries misuse the funds and do not abide by the conditionality associated with the programmes. This risk is mitigated considerably by RST design features. Under the RSF, disbursements are tied to the delivery of specific reform measures, the success of which are judged by the IMF Board through regular review processes. The risk is further mitigated by the requirement that an on-track upper credit tranche-quality programme (a macroeconomic programme designed to resolve Balance of Payments problems and provide adequate safeguards) must accompany an RSF programme. UCT programmes often contain conditions related to transparency, anti-corruption methods etc.

There is a significant risk to the delivery of high-ambition programmes in LICs, SIDS and fragile states that have limited administrative capacity. This would mean that reform measures are not achieved in time, or possibly not achieved at all within the life of the programme, and the associated disbursements not granted. Mitigation of this risk involves constant calibration of the ambition and timing of reform measures to ensure that they are proportionate to capacity and realistically deliverable.

There are minor risks associated with the RST’s investment strategy. These include the risk that RST funds are invested in poor-performing assets that sustain losses over multiple years. There’s also a reputational risk involved, which would arise were RST funds invested in assets that aren’t managed in accordance with sound Environmental, Social and Governance principles. These risks are mitigated through close scrutiny by the Board of the Fund’s investment strategy, and by the liquid nature of the investments that the Fund invests in.

There is a moderate credit risk associated with the programme. This is the risk that RST loans perform badly (i.e. that countries are not able to repay funds that they have been lent) and there are numerous arrears and defaults that threaten the financial integrity of the Trust. This risk is mitigated by the Fund’s multi-layered safeguarding framework, the maintenance of a strong level of reserves and the established status of the IMF as a ‘preferred creditor’. It is also mitigated by the requirement that an applicant country’s debt position be sustainable, according to the Fund’s debt sustainability assessment.

There are also moderate risks associated with the strategy and context of the programme. Political risks include the risk that proposed programmes support countries who do not share UK values, development priorities, and respect for human rights or that programmes are approved for countries with UK sanctions regimes in place. These risks are strongly mitigated by the fact that programme approvals require a Board majority and there is alignment amongst many significant shareholders at the Board on the primacy of key values.  There are also risks to the sustainability of reform measures related to political risks in borrower countries, including through changes in administration, within the life of the RSF programme. The UK continues to support the IMF in enhancing and embedding political economy into its analysis and program design.

Other risks that were flagged in the RST interim review include “risks related to program design include the potential duplication of other International Financial Institutions’ (IFIs) work, delays in implementation of reforms under the concurrent UCT-quality program owing to large and frontloaded access to RST financing, and challenges associated with expanding structural conditionality to new areas, including designing and monitoring programs and mission creep”. Continued iteration of the approach to RST programmes and the introduction of design changes to eliminate dual-purpose reforms and deepening of reform measures to entrench commitment to the policy direction are amongst the mitigation approaches, alongside a focus on alignment and coherence across IFI support.

There is also a human resources risk - that the RST may have inadequate resourcing, or that staff with climate expertise are drawn away from other key functions at the IMF. There is also a risk that IMF staff may be over-stretched by high levels of program demand and program activity and shifting member priorities. This risk, including the risk to IMF staff wellbeing will need to be kept under constant review.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The IMF provides a significant volume of reporting on its RST lending operations. Each individual RST programme is considered on its own merits by the IMF Board, informed by a detailed case. The progress of the programmes against its reform measures and the associated disbursements are also considered by the Board during the six-monthly programme reviews.

The IMF published in May, their 2025 Update of Resource Adequacy of the Poverty Reduction and Growth Trust, Resilience and Sustainability Trust, and Debt Relief Trusts. This included considerable detail on the resource adequacy of the RST, including detail on the volume of bilateral contributions, the reserves position and demand projections. Providing this information in a format more amenable for analysis would help with external scrutiny.

The IMF Board are frequently appraised of emerging and ongoing risks at programme and portfolio level. IMF finances are governed by strict auditing and transparency rules.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The interim review of the RST that was issued by the IMF ahead of the previous annual review- Interim Review of The Resilience and Sustainability Trust and Review of Adequacy of Resources- provided a strong starting point on monitoring and evaluation of the programme and led to Board endorsement of a small number of design and operational changes. A more comprehensive review of the RSF is scheduled for Financial Year 2027 and will provide the opportunity for any more substantive changes to the design that are required.

The Independent Evaluation Office of the IMF are in the process of conducting a review of the IMF’s approach to climate change. Their review will include a survey of member countries on matters related to climate change, including the experience of countries that are participating in, or have participated in, RST programmes.

In parallel to the IMF’s own review cycles, a consultation with the network of UK staff working in the overseas network, situated in countries that received an RST programme, were consulted for their independent views of RST progress to date. This process built on the findings of a similar exercise last year.

With regards monitoring, an area that will require further thought by the Fund and shareholders is how the success of RST programmes can continue to be evaluated beyond the life of the programme. This may require embedding some follow-up on the success of RST reform measures through the IMF’s regular surveillance activities.

Date of last narrative financial report	Quarter ended / 31-01-2025	Date of last audited annual statement	30-04-2024