## Annual Review Template

Title: Resilience, Adaptation and Inclusion in Nepal (RAIN) Programme
Programme Value £ (full life): £38.5 million		Review date:
Programme Code: 400018	AMP start date: 20/06/2024	AMP end date: 30/03/2030

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400018 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400018 Documents

A. SUMMARY AND OVERVIEW
Description of programme

The up to £38.5 million Resilience, Adaptation and Inclusion in Nepal (RAIN) is a six-year programme (April 2024-March 2030) that will strengthen the Government of Nepal (GoN)’s climate change adaptation, mitigation, and disaster risk management efforts, and help make social protection systems more adaptive and shock-responsive. This will reduce losses and damage and build the resilience of the most vulnerable communities at risk of natural hazards (climate-induced and earthquake). RAIN has five components:

Component 1 - Technical Assistance and Strategic Learning Unit (TA/SLU): Delivered by Mott MacDonald, this component provides demand-led technical assistance (for example through embedded staff using coaching approaches) to the three tiers of Nepal’s government to strengthen climate adaptation and disaster risk management systems and to help them access climate finance.

Component 2 – Climate finance: Under this component, RAIN will support Nepal to improve its access to climate finance as well as effective channelling to and utilisation of resources at the local level. Several implementing partners in RAIN will work towards this outcome. This includes the TA/SLU (as above) and the Asian Development Bank (ADB) who are currently designing a Green and Resilient Financing Facility (GREFF) which RAIN intends to provide funding for when it goes live (expected in 2027). This will be a vehicle for securing, leveraging, and managing coordinated delivery of climate finance from multiple sources (e.g. Green Climate Fund (GCF), bilateral donors) towards the priorities of Nepal’s National Adaptation Plan (NAP). The British Embassy Kathmandu (BEK) is working closely with ADB on the design of the facility, laying the foundations through our technical assistance work with Mott MacDonald, including helping to build a strategic prioritised pipeline of projects.

The RAIN business case also envisaged a partnership with the UN Capital Development Fund (UNCDF) on their Local Climate Adaptive Living Facility (LoCAL) programme. BEK provided funding for this in the first year of RAIN, but a decision had to be taken to pause support for this during FY24/25 as a Financing Agreement between the GoN and UNCDF could not be reached in time to ensure timely spend in the UK fiscal year. Further details and next steps are covered below.

Component 3 - Early Warning, Early Action, Adaptation, Community Resilience, Localisation and Inclusion: An NGO consortium, led by People in Need (PIN), is supporting vulnerable communities and local governments to become more resilient to disasters through interventions which improve preparedness, access to early warning systems and strengthen delivery mechanisms on early action and adaptation measures (including nature-based solutions).

Component 4 - Adaptive Social Protection: The World Bank provides technical assistance to make Nepal’s social protection systems more adaptive to enhance the resilience of poor and vulnerable populations to cope with shocks. This includes support to implement shock responsive social protection (SRSP) guidelines and to strengthen the necessary government information systems.

Component 5 - Start Fund Nepal (SFN): Delivered by Start Network, RAIN contributes to this pooled fund (with national and international NGO membership) to enable rapid, locally led humanitarian responses (including anticipatory action) to small and medium-scale disasters (floods, landslides, earthquakes, heatwaves and cold waves). This promotes local leadership and strengthens the capacity of national and local NGOs to complement government response to crisis.

This review covers the period of November 2024-October 2025 (Total Spend £2.8m). This includes the inception phase from November 2024 to April 2025 and the implementation phase from May to October 2025.

During this period there were two significant changes in the operating context:
- The UK government’s decision in February 2025 to reduce Overseas Development Assistance (ODA) to the equivalent of 0.3% GNI by 2027 has resulted in changes to this programme (including on geography and scale). This Annual Review reflects that the programme had to refocus resources. ODA allocations globally and the impact on programmes are still being worked through. Once these are decided centrally, the programme team will consider how best to adapt the programme, work plans and results targets to ensure the budget allocated for RAIN delivers value for money and maximises its impact.
- The widespread violence following Generation Z instigated (Gen Z) protests on 8/9 September 2025 and subsequent political transition had an impact on delivery and work plans. Some programmatic activities were paused to ensure the safety and wellbeing of RAIN implementing partners and those participating in and benefiting from the programme. Other activities had to be delayed, paused or reduced in scope, especially those relevant to government agencies as the latter’s priorities shifted during and in the aftermath of the crisis. An interim government is in place with elections scheduled in March 2025. The programme team continues to use a comprehensive risk management approach, analysing and assessing the context and risks for the programme during this period of uncertainty. This is informed by ongoing analysis from BEK’s political transition team.

Summary supporting narrative for the overall score in this review
Scoring for this review: The programme receives an A in this annual review.

The programme has adapted well to the reduction in Official Development Assistance (ODA), shifting GoN priorities, and disruptions caused by the September political unrest. RAIN has proactively engaged on the policy front and provided demand-driven technical assistance at federal, provincial, and local levels that systematises government initiatives in disaster risk reduction and accessing international climate finance. Through close collaboration with 19 local governments across Madhesh and Lumbini Provinces, vulnerable communities exposed to both natural and climate-induced hazards were supported through bespoke initiatives on risk reduction, recovery, relief and climate change adaptation. These initiatives included formation and capacity building of community disaster management committees and planning, design and implementation of safe shelters, demonstrating through construction nature-based solutions for climate adaptation like multipurpose recharge ponds, green and grey structures for embankments, and agroecology interventions. All initiatives were carried out in close collaboration with local governments to encourage capacity and knowledge transfers to both local communities, who are directly benefiting from these interventions, and local officials. However, there are important lessons learnt (refer to the section) on both system strengthening and ensuring sustainability and scaling across local governments.

RAIN also weaved together several initiatives on disaster preparedness from the federal level to communities in areas of early warning and risk communication. In collaboration with both Department of Hydrology and Meteorology (DHM) and the National Disaster Risk Reduction and Management Authority (NDRRMA), multiple rainfall and water-level sensors and forecast measures to address heat waves and floods have been rolled out, targeting vulnerable communities. Simultaneously, 72 community-based disaster management committees have been trained, equipped and linked to these early warning systems. This preparedness system linking DHM/NDRRMA to the local governments and communities will need to be expanded across the country and tested through several real-life disaster scenarios to ascertain their effectiveness. However, early signs are encouraging. RAIN initiatives have encouraged closer collaboration between DHM and NDRRMA and several communities in Madhesh have already began benefiting from this system.

Through consistent efforts from RAIN (and other development programs), the Government of Nepal has taken important steps on climate finance. Both Ministry of Finance (MoF) and the Ministry of Forests and Environment (MoFE) have advanced efforts to work with Direct Access Entities (DAEs) to secure funding from the Green Climate Fund (GCF), and initiated discussions on accessing resources from the Fund for Responding to Loss and Damage (FRLD). Accessing funds from both entities will require project development by DAEs and enabling efforts from both ministries. Our next initiatives will focus on building capacities for project development and identifying solutions to tractable legal and institutional hurdles.

RAIN responded to floods and droughts in Madhesh through Start Fund Nepal (SFN) and the Early Action Consortium, disbursing £434,000 in pre-agreed financing. Progress has been steady on shock-responsive social protection, marked by the Government of Nepal’s January 2025 approval of implementation guidelines. Following the approval of the guidelines, NDRRMA and MoHA have provided training on the standards in September, and provincial and local engagement for implementation is planned for November and December.

A focus on inclusion, disability, and gender has underpinned the implementation phase, and the results are described in the outcomes and outputs section. The results framework for the outputs and outcomes indicators has milestones set for March 2026, so this is a review in transition, with a fuller Annual Review (AR) due to be conducted in May-June 2026 to capture results aligned with the UK financial year 2025-2026 and beyond.

Major lessons and recommendations for the year ahead

Lesson 1: System strengthening will require deep government partnership through both co-creation and co-ownership of interventions. / Achieving system strengthening outputs and ensuring impactful disaster management and climate change adaption will require deep collaboration with government institutions at all three tiers. Experience from past year shows that this will be an iterative process, guided by adaptive management attuned to both realities on the ground, institutional priorities and a shifting development paradigm. / Key insights include: / Moving from financial aid to capacity-building models takes time and sustained dialogue. This shift requires proactive communication, patient reorientation and early, wide and transparent engagements across government agencies. / Successful initiatives need multi-sectoral (multi-ministerial) coordination which is not a given and require dedicated interventions and constant learning. / For technical assistance interventions, high staff turnover and lack of handovers, and tight schedules of senior officials requires the institutionalising support, detailed documentation, and proactive planning. / Many local governments have been willing to co-finance (though in some instances commitments were delayed after the September unrest), supporting ownership and co-creation.
Recommendations: / Maintain regular engagement and document agreements for continuity. / Promote neutrality. Position the programme and partners as facilitators of collaboration. / Continue to support government ownership. Provide timely information to government stakeholders to enable informed decision-making while balancing transaction costs through clear roles and annual priority-setting. / Increase focus on subnational levels through participation in governance forums and targeted capacity-building.
Responsible: Climate and Resilience Team (Green Growth Group) and implementing partners with engagement from the Group Head and Development Director as appropriate.	Target date: by March 2026 and ongoing

Lesson 2: Learning through evidence and political economy analyses to inform programming / Building resilience against natural hazards is a primary goal of the RAIN programme including the access to international climate finance by working across the three spheres of government. Political economy analyses and contextual evidence from issue-based approach needs to be worked out with RAIN implementing partners, such that programmatic activities are informed by PEAs.
Recommendations: / Ensure governance inputs inform systems strengthening and technical assistance to GoN on access to climate finance, institutional strengthening of NDRRMA and wider disaster management systems and policy gap analysis at the provincial level. / Engage with wider process for scanning governance opportunities across the BEK portfolio. / Ensure regular lesson sharing opportunities with other BEK programmes, particularly Samartha, on influencing government planning, budgeting and delivery processes.
Responsible: Climate and Resilience Team (Green Growth Group), Green Growth Group Governance Advisor (working closely with other governance and political colleagues across BEK)	Target date: by January 2026 and ongoing

Lesson 3: Prioritisation and adaptive management / The programme demonstrated strong adaptability during periods of uncertainty, including ODA reductions and the September 2025 unrest. RAIN’s multi-partner design enabled swift reprioritisation and flexible approaches, such as shifting modalities within the Early Action consortium. Scenario planning and responsive work plan adjustments were key to maintaining progress.
Recommendations: / Enhance collaboration: Maximise synergies between partners and link interventions for greater impact. / Focus on value: Regularly assess cost-effectiveness and potential for long-term systems strengthening. / Align and update: Review programme theory of change and priorities to reflect evolving contexts and lessons learned.
Responsible: Climate and Resilience Team (Green Growth Group)	Target date: by March 2026 and ongoing

Lesson 4: Linking individual early action, DRR and adaptation interventions to systems strengthening. / Different initiatives on early action, DRR and adaptation have been carried out at all three levels in close collaboration with government agencies. However, on their own, they are unlikely to amount to more than the sum of their parts. Especially in vulnerable local governments and communities, despite the benefits, sustainability will be hard to ascertain. Similarly, some of the initiatives, especially in climate adaptation, need to move beyond demonstration and into replication and wider adoption.
Recommendation 4 / Identify opportunities and push for policy/legislative changes at the local and provincial level to institutionalise interventions (e.g. Community disaster management committees). / Include dedicated interventions and theory of change on demonstrations and replications. Activities could include joint learning visits for practitioners and policy makers, developing and sharing procurement specifications for specific interventions and development of federal standards. / Cross-team collaboration: Share learning with Local Infrastructure Support Programme (LISP) team and partners on types and designs of climate change adaptation infrastructure. / Investments in early warning, early action and adaptation will be carefully designed and implemented at the local level to ensure provincial co-investment to strengthen disaster risk reduction and management systems to achieve outcomes and value for money.
Responsible: Climate and Resilience Team (Green Growth Group) with Service Delivery Group GSDG) and BEK RAIN partners	Target date: End of March 2026

Lesson 5: Coherence between RAIN partners, other BEK programmes and other donors / The foundations have been laid for synergistic working between different RAIN partners (eg. TA/SLU and early action consortium, PIN and WB on social protection, holistic responses with SFN and early action consortium) but this can be strengthened. As BEK’s wider portfolio moves out of inception/early implementation phases there are opportunities for stronger collaboration.
Recommendations: / Ensure more regular programme board discussions to identify more opportunities for collaboration and share lessons. / Work with BEK GEDSI Advisory Group and Evidence and Knowledge (E & K) Hub to explore areas where evidence and inclusion can inform programming choices especially with regards to local leadership, empowerment and agency for at-risk marginalised and vulnerable communities including people with disability. / Explore synergies with RIVA (eg. on mapping women’s rights organisations already working on climate resilience, disaster preparedness, migration and early warning systems), Samartha (including on new areas to explore further like air pollution/black carbon agenda), LISP (lesson learning on community and local government engagement and climate adaptation practices), GGN (continued on climate finance) and SJP (gender-based violence considerations).
Responsible: Climate and Resilience Team (Green Growth Group) with relevant colleagues from BEK	Target date: March 2026

Lesson 6: GEDSI integration in the programme / The RAIN project successfully integrated Gender Equality, Disability, and Social Inclusion (GEDSI) across disaster risk reduction, early warning, and climate adaptation interventions. Actions such as inclusive early warning systems, disability screening, GEDSI analysis, and participatory planning ensured that vulnerable groups were actively engaged and supported. The PIN/DCA consortium has been particularly effective with a GEDSI strategy and consortium-wide working group which provided a strong foundation for systematic inclusion. RAIN partner participation in the BEK GEDSI working group has also been helpful. However, we know mainstreaming inclusion remains a continuous process that demands structured implementation. There needs to be a continued focus on institutionalising GEDSI across all RAIN programme components.
Recommendations: / As above, work with BEK GEDSI Advisory Group and explore synergies with the Rights, Inclusion, Voice and Agency (RIVA) Programme. / Continue to leverage data for action (e.g. using disability screening and vulnerability mapping to inform early action and link communities to social protection schemes). / Strengthen inclusive communication. Expand accessible early warning channels and integrate GBV risk mitigation measures. / Showcase and scale best practices. Document and share examples of inclusive approaches (eg. mobility training, childcare during emergencies, accessible venues) to influence policy and replication. Develop clearer strategy for how these best practices are widely shared so they can be replicated and contribute to wider systems strengthening. / Build local capacity. Continue training Community Based Organizations (CBOs), women’s rights organisations and local government on GEDSI and inclusive disaster preparedness. Ensure the quality and impact of the training is tracked (rather than number of trainings). / Apply recommendations from GEDSI analyses across programme components (or more widely as applicable). / Complete GEDSI learning exercises by March 2026 to inform year 2 planning.
Responsible: Climate and Resilience Team (Green Growth Group) with RIVA team and BEK GEDSI Advisory group (1), PIN/ Dan Church Aid (DCA) consortium (2,3,4,5), TA/SLU (4,7), all RAIN partners (6)	Target date: June 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The RAIN Programme Theory of Change (ToC), developed for the business case, was refined in Quarter 2 of 2025 through workshops with BEK and its partners. This clarified change pathways, further elaborated outcome and impact statements, and aligned component-level ToCs using a nested approach to show how activities contribute to programme-level outcomes. Indicators were updated to meet SMART criteria. ToCs from the Business Case and the revised one are included below.

In the next period, Component 5 is expected to be formally integrated into the programme’s ToC and Annual Results Framework (ARF), enabling systematic tracking of progress and clarifying how its interventions contribute to broader change through RAIN. Under Component 2, support for the LOCAL programme delivered by UNCDF is currently not proceeding. The programme team will consider implications for the programme and its Theory of Change once there is clarity on budget availability in early 2026.

Commitment from GoN has been achieved and progresses through other aspects of RAIN (including commitment from local and provincial governments to fund Nature-based Solutions (NbS) and safe shelters). Political unrest in September caused minor delays to governance activities, but adaptive management – remote engagement and revised timelines – ensured continuity. As RAIN is in early implementation, outputs have focused on systems, capacity building, and initial interventions. These outputs provide the foundation for progress toward outcomes in the next phase.

TA SLU: Outputs include endorsement of the Emergency Operation Centre Standard Operating Procedures (EOC SOP), formation of governance bodies, and training for post-disaster recovery. These outputs are driving progress toward outcomes of stronger disaster governance and anticipatory action, with early signs in SOP approval, improved coordination, and climate finance proposals advancing.

PIN: Outputs include the establishment of 72 Community Disaster Management Committees, 145 task forces, early warning systems (sirens, sensors, IVR), and heat early action reaching 150,000 people. These outputs strengthen preparedness and forecasting, advancing outcomes of safer communities and inclusive early warning. Adaptation outputs – NbS, safe shelter planning, disability-inclusive measures – are positioning local governments to achieve resilience outcomes, with early signals such as activated early action and co-financing commitments. Climate change adaptation initiatives are also being designed through a bottom-up consultation process to prioritize locally led adaptation schemes building on the LLA (Locally Led Adaptation) Principles.

World Bank: Outputs include guideline amendments initiated, institutional clarity for an Integrated Social Registry, and system design underway. These outputs enable progress toward outcomes of scalable, shock-responsive social protection and integrated information systems, supported by policy dialogue and technical exchange.

Start Fund Nepal: Outputs include activation of drought and Acute Watery Diarrhoea (AWD) alerts, reaching 47,000 people with water trucking, digital vouchers, and health facility support. These outputs advance outcomes of timely, locally led humanitarian response and stronger preparedness systems, with early progress seen in faster activation times and anticipatory action integration.

The Theory of Change is illustrated overleaf. The fourth output on stakeholder engagement will be revised to sustainability and scaling up with an emphasis on learning and connection with wider BEK portfolio and maximise impacts across the components across RAIN,
RAIN Theory of Change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

RAIN’s contributions toward the four outcome indicators and related progress are summarised below. As it’s the first year of implementation, progress towards outcomes for the TA/SLU and SRSP components remains limited. However, more information tracking progress will be included in the next Annual Review, which will be brought forward to June 2026. However, for the Start Fund Nepal (SFN) and Early Action Consortium components, there has been notable progress towards the outcomes.

Outcomes	Indicators	Milestones for Review (Baseline)	Progress
Outcome1: / Inclusive systems strengthened such that GoN can better use its own fiscal resources to allocate, spend and monitor its interventions on Climate Finance (CF), Disaster Risk Reduction and Management (DRRM) and Climate Change Adaptation (CCA)	# Relevant policy frameworks, operational directives and standard operating procedures (SoPs) developed and implemented by all levels of governments on CF, DRRM and CCA	Following results of policy analysis (Jan 2026)	**Outcome progress will be reported in the subsequent Annual Review in June 2026 as all milestone indicators are until March 2026 (covering FY 2025/26) **
	Value (NPR/£) allocated and spent for DRRM and CCA in target local and provincial governments supported by RAIN TA SLU	'Following results of policy analysis (Jan 2026) - which will assess implementation gaps of existing policies inc. budget allocation and expenditures in selected provincial and local governments.
Outcome 2: / Inclusive systems strengthened such that GoN can better access international climate finance to meet the goals of its National Adaptation Plans (NAP), nationally Determined Contributions (NDC), Long-term Strategy (LTS) and National Climate Change Policy (NCCP)	# / value (NPR/£) of climate finance proposals approved / Volume (NPR/£) of public finance mobilised for climate change purposes as a result of International Climate Finance (ICF) (ICF KPI 11)	5 GCF approved projects in portfolio (through entity: UNDP, Asian Development bank (ADB), Alternative Energy Promotion Centre (AEPC), International Union for the Conservation of Nature (IUCN), Food and Agriculture Organization (FAO), as of July 2025	**Outcome progress will be reported in the subsequent Annual Review in June 2026 as all milestone indicators are until March 2026 (covering FY 2025/26) ** / As the UNCDF work is currently not proceeding, this indicator will be removed for future reviews.
	Value of climate finance channelled through UNCDF-designed Performance Based Climate Resilience Grants (PBCRG) mechanism / Volume (£) of public finance mobilised for climate change purposes as a result of ICF (ICF KPI 11)	Proposal approval record from Direct Access Entity (DAE)/Green Climate Fund (GCF)
Outcome 3: / Communities are more resilient to disasters through improved preparedness, access to early warning systems, and strengthened delivery mechanisms on early action, and adaptation measures	% Community members that took recommended early action after they received the risk communication messaging	Programme records, Baseline, Midline, Endline, Annual reports, Monitoring report, partner report	As per the Post Distribution Monitoring (PDM) for flood response: / 84.4% reported receiving early warning messages / 98.7%; took early action and relocated to safe places
	# early warning systems established or strengthened with government ownership of forecast based early action protocols to address risks from multi-hazards	Programme records, Baseline, Midline, Endline, Annual reports, Monitoring report, partner report	- 72 Community Disaster Management Committees (CDMC) set up (with 21 CDMCs having functional Early Warning Systems (EWS) taskforce) / - 3 participatory mapping exercises completed to strengthening EWS dissemination mechanism. / Provincial multi-hazard Early Action Protocol (EAP) being drafted to strengthen anticipatory action in Lumbini and Madhesh Provinces.
Outcome 4: / National and Local Non-governmental Organization (NGO) humanitarian action is timely, proactive, coordinated, needs-driven, and locally-and evidence-led.	# national and local NGOs who receive direct (and indirect) funding	% of SF Nepal projects reporting that at risk or crisis affected populations informed the project	- 2 national and local Non-Government Organizations (NGOs) received direct funding (33%) / - 5 national and local NGOs received indirect funding (69%)
	% of anticipatory projects that reached at-risk populations ahead of the peak of the crisis	100%	These indicators will be changed as not relevant
	% of Start Fund Nepal (SFN) projects reporting that at risk or crisis affected populations informed the project	100%	These indicators will be changed as not relevant

RAIN is already contributing to impact indicators by reaching the most vulnerable and marginalised communities at risk from hazards such as floods, heatwaves and droughts with early action and timely humanitarian response through SFN and PIN consortium.

Impact	Impact indicator	Progress against indicators
Improved resilience of at-risk, vulnerable and marginalised communities to anticipate, adapt, prevent, and absorb climatic and non-climatic shocks. Government of Nepal (GoN) has improved systems and institutional capacity in place to support communities.	# of people who have benefitted from implementation of Climate Finance, Climate Change Adaptation and Disaster Risk Resilience Management related policies at the local, provincial and federal level to build resilience against climatic and non-climatic shocks. Crisis-affected people are supported by a well-funded and locally-led humanitarian response. # people supported to better adapt to the effects of climate change as result of International Climate Finance (ICF KPI 1)	-SFN will reach approximately 703 people with disability out of 75,190 beneficiaries of which 37,291 are women (tentative as of Oct 2025) / -PIN consortium has reached 6427 individuals (3230 men, 3197 women and 108 people with disability) directly; / On heatwave early action reached 34208 (including 4121 people with disability) people indirectly via drought response; 80426 indirectly (tentative as of Oct 2025)

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

In the context of ODA reductions described above, the FCDO is implementing four development shifts: from donor to investor, from service delivery to system strengthening, from grants to expertise and from international intervention to local action. RAIN, with its focus on unlocking climate finance and work on locally led adaptation, systems strengthening and engagement of local actors (both local communities as well as three tiers of government) reflects this approach. The British Embassy Kathmandu (BEK) has also reviewed and reset its portfolio, with economic transformation, climate and resilience, and strengthening human capital as the three priority outcomes. Underpinning these outcome areas are enabling investments on accountability, inclusion, digitisation and development effectiveness. In the context of these choices and based on progress made to date, RAIN will continue to be part of the BEK portfolio. However, once the budget for both the Nepal portfolio and RAIN programme specifically is confirmed, we will consider if any changes or restructuring of the programme are needed to ensure good value for money and alignment with the principles and shifts described above.

## C. DETAILED OUTPUT SCORING

Output Title	Inclusive Government of Nepal (GoN) systems supported via RAIN TA and learning (incl. policy frameworks, operating procedures, guidelines) in Climate Finance, Disaster Risk Reduction and Management; and Climate Change Adaptation
Output number:		1	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
# Relevant policy frameworks, operational directives and standard operating procedures (SoPs) drafted by government on Climate Finance, Disaster Risk Resilience Management and Climate Change Adaptation and influenced by Gender Equality, Disability and Social Inclusion (GEDSI) considerations	2 Developed and 2 Revised (Component 1)	Standard Operating Procedures (SoP) for Emergency Operations Centres (EoC) drafted and endorsed by GoN on 17th Oct 2025 / Revised National Framework on Anticipatory Action (AA) and started development of Multi Hazard Early Warning System (MHEWS) Directive. / Milestone Met: A
# local and provincial governments receiving support to establish and operationalise policies and procedures for Climate Change Adaptation, and Disaster Risk Reduction and Management	As per actual and to be defined by policy gaps and needs assessment	ToRs developed to finalise Provincial Climate Change Policy and Strategic Action Plan for Madhesh and Lumbini / Operationalisation of Provincial Climate Change Coordination Committee (PCCCC) underway / Milestone Partially Achieved (not on track): B
Evidence that Social Security Allowances (SSA) and Prime Minister’s Employment Programme (PMEP) guidelines amended to enable it to be shock-responsive	As per actual (Component 4)	Disaster Sensitive Social Security and Relief Distribution Standards (DSSSRDS) endorsed in January 2025. / Milestone Achieved: A
# Concept notes or funding proposals drafted for vertical climate funds with RAIN TA SLU support	2 (Component 1)	RAIN TA and National Trust for Nature Conservation (NTNC) have signed a Memorandum of Understanding (MoU) to support NTNC to develop a GCF full funding proposal for $10 million. Concept note for this has been approved by MoF and GCF. / Technical inputs provided for Nepal Investment Mega Bank (NIMB) concept note (CN) on Nepal Climate Financing Facility. The CN has been submitted to National Designated Authority (NDA). / Discussion is ongoing with MoFE/NDRRMA/AEPC to support AEPC to develop full funding proposal to Fund Responding to Loss and Damage (FRLD). / Milestone Met (On track): A
Value (NPR/£) of Performance-based Climate Resilience Grants (PBCRG) disbursed to participating local governments annually	As per actual (Component 2)	MoU with UNCDF terminated within the inception period. No progress. / Milestone not met: C

Briefly describe the output’s activities and provide supporting narrative for the score.

This output covers Technical Assistance (TA) to the Government of Nepal (GoN) under RAIN across the federal, provincial and local levels. Three current RAIN partners are delivering activities as agreed in the workplan. This covers the inception phase (November 2024-April 2025) and early implementation (May-October 2025).

Technical Assistance and Strategic Learning Unit (TASLU):
This component is delivered by Mott MacDonald (MM) via a commercial contract. As part of the inception phase, MM has delivered RAIN’s Project Strategy GEDSI Strategy, including the Theory of Change (ToC), conducted political economy analyses and costed the work plan for implementation. During inception phase, MoFE received support (embedded staff) for finalising the Nationally Determined Contributions (NDC 3.0).

During implementation phase (May-October 2025), MM focused on the themes below:

Federal Engagement: Two staff members have been embedded in the National Disaster Risk Reduction and Management Authority (NDRRMA). They are supporting Reconstruction to Resilience (R2R) initiatives, including the training of local government officials on accessing reconstruction grants in Jajarkot and West Rukum in Karnali province. TA has been provided to upgrade the Reconstruction Information Management System (RIMS) and the development of Standard Operating Procedures (SoP) for Emergency Operations Procedures (EoCs). The TA has also supported the revision of the National Framework for Anticipatory Action (AA). Support to MoFE focused on identifying areas of support on climate-related policies in the province and initiating work to help the GoN access FLRD funds. In the next review, detailed review on technical assistance will be conducted to categorise the type of technical assistance provided and measure its impact. This will be categorised as coaching and mentoring, one off technical inputs and training to staffs and review if it leads to dependency or strengthen systems.

Climate Finance and Adaptation: There is an agreement with the Ministry of Finance (MoF) to support the Direct Access Entity (DAE) – National Trust for Nature Conservation (NTNC) in drafting a Green Climate Fund (GCF) proposal to access USD 10 million through an MoU. However, there has been a significant delay in embedding a climate finance expert at MoF, as the selected expert joined another organization on short notice. Currently, the required expertise is being managed remotely by an international climate finance expert, complemented by a local climate change expert and the deputy team leader, who are directly working with NTNC on the GCF proposal.

In addition, the Ministry of Forests and Environment (MoFE) requested support on loss and damage; as such, the climate change expert will also contribute to developing methodologies for assessing economic and non-economic losses, and setting up a financial flow mechanism on loss and damage.

The format for proposals to the Fund for Responding to Loss and Damage (FRLD) launched at the Conference of the Parties (COP30), with the formal call for proposals expected to be announced in December 2025. MoFE has requested assistance in preparing an FRLD proposal. Initial discussions on this support are underway; RAIN will provide support helping the GoN prepare the proposal (but not provide direct drafting support). With a June 2026 deadline for the proposals, this will be a priority for the first half of 2026.

Provincial and Local Engagement: Two staff members have been embedded in Madhesh Province’s Ministry of Home Affairs and Communication and Ministry of Forests and Environment, and one staff member is embedded in Lumbini’s Ministry of Forest and Environment. Support in Madhesh has focused on information and data management to equip the provincial Emergency Operation Centres (EoC). An assessment of the Local Disaster Climate Resilience Framework (LDRCF) has been delayed due to protests. An assessment of policy needs and gaps in climate change, disaster risk reduction, and management is in progress. There are plans to increase joint activities with the PIN/DCA early action consortium next financial year (considering budget availability and the wider Nepal political transition context). For climate change, the identified priorities include activating the Provincial Climate Change Coordination Committee (PC4), finalizing the Provincial Climate Change Strategy and Action Plan, and providing inputs to the Environment Protection Act.

Local Climate Adaptive Living Facility (LoCAL):
This component was implemented by UNCDF under a Memorandum of Understanding (MoU) and remained active for six months, during which planning activities and field visits to proposed sites in Lumbini Province were conducted to engage with local governments.

However, due to delays and lack of progress in finalising a financing agreement between UNCDF and the Ministry of Finance (MoF), BEK closed this component in April 2025, following discussions with UNCDF. This decision was communicated to Government of Nepal (GoN). Discussions on how take forward the climate finance mobilisation (domestic and international) component are planned for early 2026.

Shock-Responsive Social Protection (SRSP):
This component is delivered by the World Bank through a Memorandum of Understanding. A significant achievement has been the endorsement of the Disaster Sensitive Social Security and Relief Distribution Standards (DSSSRDS) and the orientation of provincial Disaster Risk Reduction (DRR) focal points on their content, jointly with NDRRMA and MoHA. Procurement of a vendor to provide technical assistance to the GoN on the Integrated Social Registry (ISR) is underway. This has been approved at the secretary level at MoHA. Dialogue for the revision of guidelines for the Social Security Allowance (SSA) and the Prime Minister Employment Programme (PMEP) is also underway. However, due to Gen Z protests, several activities are delayed.

For this technical assistance success would mean designing, endorsing and integrating the integrated social registry (ISR) within the social protection systems led by the Department of National ID and Civil Registration (DoNIDCR) and coherence with SSA and PMEP by end of March 2027. For scalable SRSP operations, we envisage sufficient regulatory changes and GoN action. The next review will critically appraise the progress and the pathways required for success from both GoN commitment and WB’s delivery.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is the second Annual Review of the RAIN programme, and the output statement remains the same as the first review, focussed on process indicators. The indicator for LoCAL will be removed for the next review period. BEK will discuss internally and with GoN how to take forward the objectives set out under the climate finance component. We will follow progress of the LoCAL programme closely. If there is good progress and strong performance of the pilot and the Government considers this a strong vehicle for BEK support towards climate finance objectives, then BEK may reassess and consider further support in future years (including factoring in budget availability, programme performance and value for money considerations).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous AR. Recommendations for 2025/26 are as follows:

-Ensure RAIN TA implementing partners have written letters (consent) from the relevant ministries, departments and authorities at the federal and provincial ministries before starting activities.

Action: Climate and Resilience Team with RAIN implementing partners

-On climate finance workstream led by TASLU, further discussions with MoFE and MoF are needed to agree on the role and placement of embedded staff. We will consider value for money and the best way of working so they can effectively contribute to the agreed activities on accessing and using both domestic and international climate finance

Action: Climate and Resilience Team with TASLU

- Review the Theory of Change and consider alternative options to achieving the climate finance objectives stated in the Business Case, taking into consideration budget availability and value for money.

-RAIN TASLU operates as a demand-driven mechanism to support government priorities. To strengthen coherence in planning and implementation, there is need in some areas of work to improve clarity on some areas of support and ensure alignment with available resources. This can be achieved through more frequent and structured communication—preferably in writing—and by using a collaborative approach to confirm needs and expectations. Streamlining communication channels will help foster stronger partnership. Overall, a learning is that changing modalities of support from financial aid to more technical assistance is taking time to generate the demand and achieve buy-in for the coaching/enabling approach.

Action: Climate and Resilience Team with by January 2026 and ongoing

Output Title	Capacity built across all levels of GoN on Disaster Risk Reduction and Management, Climate Change Adaptation, Shock Responsive Social Protection, GEDSI integration, and are better able to support communities
Output number:		2	Output Score:	B
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
# people trained: / Component 1: Government Officials in Climate Finance, Disaster Risk Resilience Management and Climate Change Adaptation, (provincial/local) on Recovery to Resilience and Resilience Management Information Systems / Component 2: Government Officials in Climate Change Adaptation and Performance-based Climate Resilience Grants (PBCRG) / Component 3: Community members in early warning, early action and Climate Change Adaptation / Component 3: Government Officials in inclusive early action and Climate Change Adaptation / Component 4: Government Officials in Shock-Responsive Social Protection, Social Security Allowances, and Prime Minister's Employment Programme guidelines / Component 5: Organisational Strengthening to Local and National NGOs / # Individuals and organisations informed by International Climate Finance technical assistance (ICF TA KPI 2)	Individuals: 305 / 275 (Component 1) / 30 (Component 3, government officials) / 25 (Component 4, LLs) / TBC (Component 5) / Organisations: 72 / 10 (Component 1) / 10 (Component 3) / 10 (Component 4) TBC / 32 (Component 5)	84 (10 female and 74 male) provincial and local government representatives trained under Reconstruction to Resilience (R2R) activities in Karnali (Component 1) / 52 (16 female and 36 male) government officials and 94 (37 female and 57 male) people from CSOs/CBOs and Civil Society Network (CSN) trained on forecasting inclusive early warning and early action (EW-EA) / (Component 3) / 238 (55 female and 183 male) government officials trained on Disaster-Responsive Shock Security and Relief Distribution Guidelines (DSSSRPS) (Component 4) / 32 (12 female and 20 male) people trained on alert note writing and 35 (10 female and 25 male) people trained on forecasting (Component 5) / 13 local governments trained under Reconstruction to Resilience (R2R) activities in Karnali (Component 1) / 2 DAEs receiving support (NTNC and NIMB) (Component 1) / 30 CSOs/CBOs trained in early action and early warning (Component 3) / 16 Local and National NGOs (LNNGOs) trained in alert note writing and 12 LNNGOs on forecasting for heatwave and cold wave (Component 5) / Cumulative: 535 people (Female:140 and Male: 395) and 73 organisations trained / Milestone Met: B

Briefly describe the output’s activities and provide supporting narrative for the score.

TASLU (Component 1) conducted training on Post-Disaster Recovery Tranche Release for local governments in Jajarkot and Rukum West, in partnership with NDRRMA, equipping 81 representatives from 13 local governments and three provincial officials with the necessary post-disaster recovery knowledge and skills in Karnali Province. This will support strengthening local capacity to implement recovery activities collaboratively with NDRRMA, thereby advancing the broader goals of the Recovery to Resilience (R2R).  TASLU engaged with 2 DAEs (NTNC and NIMB) on climate finance during this review period.

LoCAL (Component 2): UNCDF also started the process of Climate Vulnerability and Community Risk Assessments (CVCRA) to inform the choices of adaptation schemes and developed a guideline for the types of infrastructure to build climate resilience but was not able to start any capacity building work on the PBCRGs.

The PIN consortium (Component 3) provided training to 30 government officials on early warning and inclusive risk communication. 30 Community-Based Organisations (CBOs) and Civil Society Organisations (CSOs) were trained on early warning and early action, including disability sensitisation, through the Civil Society Platform (CSP), benefiting 83 participants.

Start Fund Nepal provided an alert note writing training (needed to access SFN funding) to 16 Local and National Non-Government Organisations (LNNGOs), with 32 participants, and 12 LNNGOs were trained in forecasting for heat waves and cold waves, with 35 participants.  15 government officials were trained on the Disaster-Responsive Shock Security and Relief Distribution Guidelines (DSSSRPS), hosted by the NDRRMA, with the involvement of 7 Disaster Risk Reduction (DRR) focal persons from the seven provinces, including officials from the MoHA.

This output scores a B at this point as to date we have only been able to report on the number of people trained. However, in the next review period there will be information that enables us to if capacity has been built. The output will be revised and integrated to component outputs to measure the impact of training including approaches, assessment of learning, and use of training needs assessment.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is the second Annual Review of the RAIN programme, and the output statement remains the same as the first review focussed on process indicators. As a result of this review, an additional indicator for specific RAIN partners training and capacity building needs may be added, if required for clarity and milestones might be changed to make it clear and specific to the indicators being accessed. We will also review indicators to ensure they capture the quality of and results achieved as a result of the training.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous Annual Review. Given this is the first year of RAIN’s implementation, there are no specific recommendations for this output as training and capacity building for individuals and organisations have just started. Reflection and feedback from the training and capacity building sessions will be critically appraised for the period of implementation between November 2025 to March2026 to inform lessons and recommendations.

As captured in the major lessons above, this is an area where we will seek opportunities for further shared learning with other BEK programmes as well as other donors (like ECHO) providing embedded staff support and capacity building support.

Recommendations for 2025/26 are as follows:

-This output will be revised and integrated in the outcome and output specific indicators and milestones as part of the RAIN MEL framework adjustments. The changes will entail having proxy indicators and measurement metrices to access the capacity built for sustained impact after trainings are delivered across the RAIN portfolio.

Action: Climate and Resilience Team with RAIN implementing partners

Output Title	Communities (including marginalised and most vulnerable groups) supported on early warning and early action and increase adaptive capacity to natural hazards and shocks
Output number:		3	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
# people enrolled in Social Protection Schemes	750	Disability screening was completed in all 12 core local governments. 3874 people screened. 65 subsequently received disability cards. 228 people are in the referral stage and will be enrolled in social security schemes. / MoU signed with 12 local governments for data collection, identification, verification and recording (IVR) of landless, Dalits and informal settlers and data of 15,791 to be processed to be enrolled in social security scheme. / Milestone Met: A
# risk mitigation and adaptation measures aimed at reducing the risk of hazard and enhance preparedness at local and community level	10	Construction of 4 safe shelters underway in Madhesh; renovation completed for 3 safe shelters / 19 Nature Based Solution (NbS) and 5 agroecological sites under implementation across Madhesh and Lumbini / Milestone Met: A
# hazard observation installed / upgraded at sub-basin / provincial level	Upon demand from GoN	5 meteorological stations and 3 hydrological stations installed in collaboration with Department of Hydrology and Meteorology (DHM) / 5 heat sensors installed that measure temperature, humidity and air pollution / Milestone Met: A
# Inclusive Risk Communication Channels and Early Action Protocols conceptualised	As per actual	1 innovative risk communication and dissemination channel has been installed and is in testing phase (Smart Flood Tower) / Interactive Voice Recording (IVR) has been broadcast for those who cannot read DHM mass SMS (during Flood response 2025) / Early Warning messages delivered through sign language videos for people with hearing disability (during flood response 2025) / Milestone Met: A+
Value (NPR/£) of the grants provided to CBOs	As per actual	19 (£295k) adaptation schemes under implementation across Madhesh and Lumbini / Milestone Partially Met: A

Briefly describe the output’s activities and provide supporting narrative for the score.

This output captures the results from the Early Warning, Early Action, Adaptation, Localisation and Inclusion component of RAIN. The lead partner for this component is People in Need (PIN), in consortium with Dan Church Aid (DCA), Community Self Reliance Centre (CSRC), Prerana, Youth Innovation Lab, the UK Met Office, and the Red Cross Red Crescent Climate Centre (RCCC). An Accountable Grant was signed with PIN, with a start date of 1st November 2024 and an end date of 31st October 2029, valued at £10 million.

This review covers the inception phase from November 2024 to April 2025 and the implementation phase until October 2025. For the inception phase, the consortium delivered the following outputs: Theory of Change (ToC), Adaptive Results Framework, GEDSI Strategy, Communication and Advocacy Strategy, Community Feedback and Reporting Mechanism (CFRM), Safeguarding Reporting, Value for Money (VFM) Framework and Stakeholder Engagement Reports and Targeting.

Progress on the sub-themes has been highlighted below for the implementation period from May to October 2025.

Early Warning and Early Action: 5 Automatic Weather Stations (AWS) and 3 Water Level (WL) sensors have been installed at the request of the Department of Hydrology and Meteorology (DHM). Standard Operating Procedures (SoP) for the mobilisation of the Early Action Fund (EAF) were drafted for heatwaves and floods. Five experimental low-cost sensors for temperature, humidity, and air pollution were installed in Gaur, Rautahat, in Madhesh Province, alongside a heat mural.

A Smart Flood Tower was installed in Roshi Khola and is under testing and assessment to establish a flood early warning system in the Banganga river basin in Lumbini, which has been jointly concluded with DHM. The Smart Flood Tower is a community-based flood information system that receives real-time water level data from sensors from nearby DHM flood monitoring systems and visually communicates risk through color-coded beacon lights. Optional sirens provide auditory warnings, especially useful at night or during poor visibility. These towers are strategically placed in vulnerable and populated areas, ensuring wide-area visibility and access to all, including low-literate and multilingual communities.

A prototype Virtual Reality (VR) toolkit with an interactive flood awareness learning and game has been developed and was trialled in November (lessons learned to be covered in the next review). Automated sirens will be installed in 6 local governments across Madhesh and Lumbini provinces in collaboration with NDRRMA by December 2025. A 5-day training for DHM from the UK Met Office is planned for November.

Community Resilience and Adaptation: To safeguard communities from flood risks, three safe-shelter renovations have been completed, and contracts for constructing four additional shelters in Madhesh Province are finalised. To address climate-induced water challenges—both excess and scarcity—19 Nature-based Solutions (NbS) schemes are underway. These include multipurpose recharge ponds designed for groundwater replenishment and channelling water for winter crop cultivation, alongside flood protection systems that combine grey and green infrastructure. In some locations, water will also be diverted for irrigation. Building on this, five agro-ecological villages are planned to diversify agricultural practices and enhance climate resilience. These villages will utilise water from the recharge ponds, strengthening adaptive capacity and reducing vulnerability to climate hazards. Contracting for these schemes was completed by October 2025.

RAIN will also pilot the Climate Resilience Measurement for Communities (CRMC) tool, a data-driven process, complemented by a web-based tool and mobile app, which helps communities to evaluate and measure how resilient they are to climate hazards. Using the results they can identify and implement resilience-building interventions. The PIN/DCA consortium are partnering with the Zurich Climate Resilience Alliance on this who have developed the tool. RAIN consortium members have completed training to utilise the platform in preparation. The pilot roll out will begin in Barhathawa Municipality, Madhesh Province in late December 2025.

Localisation: Civil Society Organisations (CSOs) and Community-Based Organisations (CBOs) have been trained in early warning and early action, benefiting 83 participants. Disability sensitisation training was also conducted for CSOs and CBOs. Due to political and reputational risks associated with CSOs/CBOs in the current uncertain context prior to elections, the consortium has shifted from sub-grants to sub-contracts as initially envisaged. This is to ensure timely implementation of interventions. However, community user groups will continue to be engaged in delivering activities to ensure an inclusive approach and the intention is to move to a sub-granting modality in future years when conditions allow. To strengthen capacity, the consortium is using a CSO assessment tool to identify training needs and link efforts with community user groups for effective delivery. In the next review, we will appraise how RAIN is empowering local actors to take local action across adaptation, early action, early warning and inclusion. For this review, local leadership has not been captured adequately due to change in modality from sub-grants to sub-contracts to implement activities at the local level but engagement with CSOs/CBOs and user groups has been prioritised as part of implementation.

Inclusion: Disability screening camps were completed across all 12 core local governments, where 3,874 persons with disabilities were screened. Of these, 65 have been enrolled in Government of Nepal’s (GoN) social security scheme, and 228 are in the process of obtaining disability identity cards.
Additionally, data for 15,791 landless individuals have been collected for enrolment in GoN social security schemes. Emergency assistive devices were distributed using stocks from the previous UK funded disaster resilience programme (Strengthening Disaster Resilience and Responding to Humanitarian Emergencies).

For scaling up, disability screening in early action will be expanded at the provincial level beyond RAIN’s working local governments to advocate for allocating budgeting for screening camps and influencing local governments to finance mobility and assistive devices for people with disability to access safer locations when early warnings are issued. An article on ‘Why Disability Screening Matters for Early Action’ has been published in Prevention Web.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is the second Annual Review of the RAIN programme, and the output statement remains the same as the first review focussed on process indicators. As a result of this review, an additional indicator on number of grants provided to CSOs/CBOs is not relevant for this review and may be revised or kept the same for the next review period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from last year.

Recommendations for 2025/26 are as follows:

-Engage with Civil Society Organisation (CSOs)/Community Based Organisations (CBOs) whilst delivering interventions across adaptation, community resilience, early warning and inclusion using sub-contracting modality to ensure that there is adequate exposure thus building capacity and satisfying their training needs on procurement, compliance and safeguarding.

Action: Early Action consortium and Climate and Resilience Team by March 2026.

- The formation of Community-Based Disaster Management Committees (CDMCs) should follow a sequential approach across river basins and local governments, ensuring comprehensive coverage. These committees must address multiple hazards, including floods, heatwaves, cold waves, droughts, and fires. Additionally, strong linkages between CDMCs and local government structures are essential to enhance coordination and sustainability.

Action: Climate and Resilience Team with Early Action consortium by March 2026. Support through TA/SLU as appropriate.

- Ensuring the sustainability of Community-Based Disaster Management Committees (CDMCs) is critical for maintaining last-mile early warning systems and effective risk communication. Strengthening medium- to long-term capacity in collaboration with local and provincial governments will be essential, particularly by establishing strong linkages with Emergency Operations Centres (EOCs). Incorporate mechanisms for lesson learning and knowledge sharing into the Year 2 work plan to reinforce these connections.

Action: Climate and Resilience Team through PIN consortium by March 2026.

-Interlinkages between heat sensors, heat murals and virtual reality tool need to be ensured for effective disaster education at schools, wards and also at the community level where applicable alongside upstream-downstream linkages and interconnectivity with risk communication channels and multi-hazard sirens, rainfall and water level sensors. This can be achieved by designing exposure visits for ward chairs, DRR focal persons, people with disability and select CDMC members. A stocktake and lesson learning exercise on the heat sensor and virtual reality tool trials should inform the way forward.

Action: Early Action consortium and Climate and Resilience Team by June 2026.

Figure 1: Overview of RAIN targeting of local governments in Madhesh and Lumbini provinces

Output Title	National and local NGOs supported to respond to small to medium scale humanitarian emergencies in a timely manner
Output number:		4	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (March 2026)	Progress
# crisis alerts raised and activated (across RAIN components 3 and 5)	4 alerts raised of which 2 are anticipatory	Start Fund Nepal raised 4 alerts: Early Action Flood Alert (Anticipatory), Drought Response, Diarrhoea Response, Flood Response (4 alerts of which 1 is anticipatory) / PIN consortium responded to 3 events heat waves, drought and flood response of which 1 is anticipatory / Milestone Met: A (7 alerts raised and 2 are anticipatory)
Value (£) financing disbursed for anticipatory action and response (across RAIN components 3 and 5)	As per actuals	£368k disbursed by SFN of which 50k financing disbursed from SFN for anticipatory flood alert / £66k from PIN consortium for heat wave, drought and flood alerts / Milestone Met: A

Briefly describe the output’s activities and provide supporting narrative for the score.

This output covers activities from RAIN components 3 and 5 where the primary focus is responding to small scale emergencies with a key focus on anticipatory action covering Start Fund Nepal and Early Warning-Early Action consortium respectively.

Start Fund Nepal (SFN):
This component is implemented by Start Network, with Care Nepal as host agency, supporting UK capabilities for disaster response and promoting local leadership. SFN includes 16 national and 15 international NGOs. An Accountable Grant of £500k was signed on 17 April 2025, ending 31 March 2026. Nearly 70% (£350k) of funds are allocated to the disbursement pot for humanitarian response and early action activities across Nepal.

From April to October 2025, SFN members raised and activated four alerts, disbursing £368k:
- Flood Early Action in Far-West Nepal (June) – NEEDS Nepal & CRS (£50k)
- Drought Response in Madhesh Province (July) – Care Nepal & VCN with NFGN (£140k)
- Diarrhoea Response in Birgunj (September) – Doctors Without Borders & Aasman Nepal (£25k)
- Flood Response in Madhesh and Koshi Provinces (October) – KIDRAC, HUSADEC, CRS, Mandwi & VCN (£153.19k)

Start Fund members activate responses within 72 hours, complete activities in 45–60 days, and reach affected communities within five days. For this period, decisions were made within 42.5 hours on average, reaching communities in 12 districts and 29 local governments. Data for diarrhoea and flood responses are tentative; full analysis will follow in the next annual review. SFN targeted marginalized groups under ‘Leave No One Behind,’ aiming to reach 703 people with disabilities among 75,190 beneficiaries, including 37,291 women.

Humanitarian responses have been timely and appropriate, with adequate real-time and post-distribution monitoring. However, activities for drought response in Madhesh had to be re-designed and postponed following the September unrest (due to security and duty of care concerns). This delayed implementation of time-sensitive activities such as provision of WASH services and shallow and deep bore-hole construction. The diarrhoea response was also delayed by a few weeks due to the protests.
An infographic with further details can be found on page 21.

Early Warning-Early Action Consortium
This component is implemented by a PIN-led consortium and includes an ‘Early Action Fund (EAF)’ which can be mobilised rapidly based upon weather forecasts and projected impact. For this review period, this fund was used to anticipate and respond to a heat spell in Madhesh (June 2025), provide a targeted drought response (August-October 2025) and immediate support to flood impacted families (October 2025) in RAIN’s working local governments. Post Distribution Monitoring (PDM) has been completed and number of people reached has been highlighted in the infographic on page 22. Some highlights from PDM included reporting from 94.8% beneficiaries that flood response was timely and 94.3% were satisfied with the items distributed. Mobilising Female Community Health Volunteers (FCHVs) through door-to-door visits proved to be a highly effective way of reaching marginalised populations including the poor, people with disabilities, and women. FCHVs when properly trained and supported, are trusted messengers to the most vulnerable (senior citizens, women, children, pregnant, lactating, adolescent girls and people with disability) and are capable of spreading awareness before, during and after disasters.

All activities were coherent within the geographies (local governments and wards) across Madhesh and were de-conflicted with SFN and activities were designed in consultation with provincial and local governments with concurrence from the District Disaster Management Committees (DDMCs). Despite delays due to political unrest, activities were completed by November 2025. £66,092 was disbursed for heat wave (£ 2140), drought (£ 8515) and flood (£55,437) responses. Overall, the output has achieved its objectives for this review period and has contributed to RAIN’s programmatic targets.

For heat waves, 17,470 people were reached through 30 Female Community Health Volunteers (FCHVs) and mobile water distribution served 16,738 people. 128 FCHVs raised awareness on droughts, reaching 80,426 people. During the onset of floods, 7900+ interactive Voice Recording (IVR) messages were disseminated and 3400+ people with disability received sign language early warning video alerts. 1000 HHs received dignity kits and Non-Food Items (NFIs). Data disaggregation for local governments across the hazards is illustrated in the figure on page 22.

        Figure 2: Infographic on Start Fund Nepal Responses 2025

        Figure 3: Early Action Consortium Details
Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is the second Annual Review of the RAIN programme, and the output statement remains the same as the first review focussed on process indicators. As a result of this review, an additional indicator on number of beneficiaries reached disaggregated by disability across geographies will be linked with the respective outcome statement.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous Annual Review. Recommendations for 2025/26 are elaborated below.

-Ensure that there is consistency on cash for work, distribution of food and non-food items, digital water vouchers remuneration using digital cards and/or vouchers for payment as PIN consortium’s approach on cash distribution has high fiduciary risk as opposed to SFN’s Cash and Voucher Assistance (CVA) approach.

Action: SFN and PIN/DCA with BEK Resilience Advisor by March 2026.

-Some inconsistencies in knowledge management, active learning, communications and approach towards post-distribution monitoring was seen across SFN, though not completely within their control as members use their own corporate policies and approach but there is an opportunity to streamline with SFN Secretariat providing thematic leadership to all SFN members and non-members before and after implementation of alerts.

Action: Climate and Resilience Team by March 2026.

-Community Feedback and Response Mechanism (CFRM) tools across RAIN needs to be consistent and streamlined across both SFN and PIN/DCA consortium. Whilst partners have tools to report cases of fraud, corruption, Gender Based Violence (GBV) and Sexual Exploitation Abuse and Harassment (SEAH) and follow existing partner organisational policies but it can be further strengthened by better aligning with FCDO’s policies on Reporting Concerns such that it’s well understood by all partners.

Action: Climate and Resilience Team by March 2026.

Output Title	Stakeholder engagement and collaboration supported, and evidence-driven learning culture fostered to enable collaborative policy reforms and adaptive decision-making
Output number:		5	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (March 2026)	Progress
# learning products developed and disseminated by RAIN SLU	2 Learning Products	Terms of Reference (ToR) developed for Joint Learning Review (JLR) and GEDSI-EWS learning for Madhesh for 2 learning products / Policy Brief on Fund for Loss and Damage (FLRD) and for Climate Finance Unit (CFU) identifying international experience and concrete recommendations for Nepal / Milestone Me (On Track): A
# of policy dialogues, knowledge exchanges, events and workshops conducted (including learning events conducted by Start Fund Nepal for their members and non-members)	4 (Component 1) / 10 (Component 4) / 5 (Component 5)	1 high level policy dialogue on DRRM held in August 2025 (Component 1) / 1 training on DSSSRDS with provincial focal points in NDRRMA and local level workshops to be organised in Nov-Dec 25 (Component 4) / 3 Knowledge exchange visits to Rwanda, Turkey and Italy for 16 GoN staff on SRSP completed and 10 episodes on social security aired on television (Component 4) / 1 workshop on risk financing for SFN in May 2025 and 2 trainings to SFN members on forecasting and crisis anticipation (Component 5) / Milestone Met (On Track): A

Briefly describe the output’s activities and provide supporting narrative for the score.

This output covers knowledge management, learning, and communication across the RAIN programme, alongside policy dialogue, workshops, and knowledge exchange events as part of Technical Assistance (TA) for GoN. Most activities entail developing learning products that are widely shared and disseminated with wider stakeholders, including other development partners, civil-society organisations, non-government actors and the Government of Nepal (GoN). Given that the review period covers progress of RAIN partners across the five components and the milestones are set for March 2026, there has been progress on developing joint learning agendas and ToRs for joint learning, but activities have not started yet. A policy brief on accessing the Fund for Loss and Damage (FLRD) and recommendations for CFU is being finalised with dissemination plans.

Under the World Bank work stream, a high-level policy dialogue was chaired by the Home Minister and NDRRMA Chief Executive in August 2025. The discussion focused on institutional gaps and policy reforms to the current Disaster Risk Reduction and Management (DRRM) Act. Training for local-level representatives on Disaster-Responsive Shock Security and Relief Distribution Guidelines (DSSSRPS) has been delayed but plans are now in place for early 2026. Other RAIN partners have the opportunity to collaborate and participate. A Training of Trainers (ToT) was delivered in September 2025 to seven provincial DRR focal persons, including MoHA and NDRRMA officials.
In 2025, government officials engaged in key international learning initiatives to strengthen social protection and economic inclusion systems. Four officials attended the South-South Learning Forum on Economic Inclusion in Kigali, Rwanda (February 10-14), three officials participated in the Adaptive Social Protection Core Course in Rome, Italy (March 24-27), and nine officials undertook a study visit to Türkiye (May 20-24) to learn from its experience in implementing the Integrated Social Assistance System (ISAS).

Start Fund Nepal conducted two training and capacity-building sessions for 16 national NGOs on alert note writing and forecasting of heatwave and cold wave during this review period for 16 national NGOs and organised a workshop on risk financing in May 2025.

For the next review, this output will be revisited, and greater emphasis will be placed on portfolio learning and influencing across RAIN components. This will test if learning events led to impact or influence delivered and if knowledge exchange events helped RAIN to achieve policy shifts and change in perception or attitude towards policy reform contributing to outcomes.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is the second Annual Review of the RAIN programme, and the output statement remains the same as the first review focussed on process indicators. As a result of this review, an additional indicator for specific RAIN partners knowledge management and evidence sharing might be added, if required for clarity and milestones will be changed to make it clear and specific to the indicators being accessed. Further indicators will be added to help assess the effectiveness and quality of the training and actions taken as a result.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous Annual Review.

Given this is the first year of RAIN’s implementation, there are no specific recommendations for this output as some learning reviews, analysis and diagnostics have not started nor disseminated to wider stakeholders. Lessons for the period of implementation between November 2025-March2026 will be critically appraised and reported in the next annual review.
## D: VALUE FOR MONEY

Key cost drivers and performance

RAIN is in early implementation, with strong foundations for value for money (VfM) and emerging results across the 4Es. Systems for financial oversight, adaptive management, and inclusive design are operational, supported by tools such as the Programme Management Dashboard and GEDSI strategies. While quantitative reporting is partial, early evidence indicates positive progress on cost control and delivery efficiency, alongside institutional milestones that signal long-term impact. Key risks include political instability, overstretching of embedded staff, and scope creep from government requests, which may affect VfM performance if not managed proactively. Accelerating VfM reporting – particularly cost benchmarks, equity metrics, and effectiveness outcomes – will be essential in the next phase. Closing data gaps and sustaining progress toward systemic change and inclusive impact remain critical to achieving the VfM proposition set out in the Business Case.

Economy: TA SLU management costs remain within benchmark (19% vs ≤20%), and unit costs (£20.26 and £19.79 per staff hour) align with comparable FCDO projects. PIN maintains lean MEL costs (1.6%) and competitive procurement, while SFN leverages host agency infrastructure to keep overheads at 10%, enabling 90% of resources to reach direct delivery. However, municipal co-financing delays for NbS and safe shelters pose sustainability risks. Work is underway to enhance WB and SFN reporting against benchmarks in the next period.

Efficiency: Adaptive planning has enabled continuity despite major disruptions. TA SLU established collaborative structures such as Steering Committees and Technical Taskforces, while PIN reports cost-per-beneficiary efficiency (£9.62 for climate adaptation) and maintains an acceptable direct-to-indirect cost ratio (70/30). SFN demonstrates good response timeliness, averaging 42.5 hours against a 72-hour target and fund transfers enabling activity initiation within five days. WB and SFN results indicate use of adaptive approaches, and reporting against quantitative indicators for performance-based management will be included in the next period.

Effectiveness: TA SLU has already achieved a key milestone with endorsement of SOPs for Emergency Operation Centres, moving towards implementation by NDRRMA, and advanced work on anticipatory action frameworks and Multi-Hazard Early Warning System directives. Climate finance pipeline development is progressing, with NTNC and NIMB concept notes advancing to GCF stages. PIN operationalised real-time dashboards, demonstrating early progress towards outcomes. SFN and WB show partial evidence of improved policymaking and institutional arrangements.

Equity: GEDSI integration is evident through the GEDSI Action Plan. PIN delivered disability screening for 440 individuals and introduced accessible feedback mechanisms, while SFN exceeded targets for local actor representation in allocation committees (60% vs 52%). Disaggregated beneficiary data and detailed commentary on equity progress is expected to be available in the next period.

VfM performance compared to the original VfM proposition in the business case

As envisaged in the Business Case, RAIN had established common indicators for VfM across the 4Es. VfM indicators will be tracked and integrated into the results framework. The approach covers four dimensions: Economy, by monitoring and transparently reporting key cost drivers such as capped programme management costs, benchmarking TA/consultant fees, and unit costs across government levels; Efficiency, through evidence of collaboration across BEK programmes and components, and M&E reports distinguishing adaptive and traditional delivery; effectiveness, by assessing improved climate policymaking, cost per grant, and cost per dollar of climate finance leveraged; and Equity, by tracking inclusivity indicators, targeting for anticipatory financing, and progress in adaptive social protection systems. RAIN partners have established VfM indicators across the 4Es, which will be tracked annually to inform an overall cost-effectiveness analysis.

Assessment of whether the programme continues to represent value for money

The RAIN programme continues to represent strong VFM and has completed its inception phase (albeit pausing of LoCAL component due to lack of financing agreement with GoN) and started implementation. Under RAIN Start Fund Nepal (SFN) remains the vehicle to respond to small to medium scale emergencies and is supporting policy reform to protect at-risk population from climatic and non-climatic shocks and increase access to climate finance and incrementally improve access to shock responsive social protection systems across Nepal.
E: RISK

Overview of risk management
Risk management under RAIN has remained active, proportionate and responsive to Nepal’s evolving political and civic context. During the reporting period, the overall risk level for the RAIN Programme remained classified as “Major,” with all risk categories falling within the British Embassy Kathmandu (BEK)’s defined risk appetite. The programme maintains a monthly update of its risk register and closely monitors the implementation of mitigation measures. In line with formal reporting requirements, implementing partners regularly review and update their own risk registers and take appropriate mitigation actions. This routine review process ensures that contextual, fiduciary, safeguarding, and programmatic risks are continually monitored, re-rated and mitigated through early action. Where urgent escalation is necessary, BEK or its partners raise risks for discussion outside the standard reporting cycle

Over the past year, risk exposure has been shaped primarily by three drivers: (i) challenges in Government engagement in the context of high turnover of staff, (ii) the fluid political environment following civic protests and government reshuffles in Sept 2025; (iii) the 0.3% FCDO ODA adjustment; and (iv) heightened sensitivity around civic space following the “Gen Z” protests and current political transition period.

The risks observed during this period have been diverse, with the majority falling under the categories of ‘Strategy and Context’ and ‘Policy and Programme Delivery.’

Strategy and Context
The political unrest in September 2025, the formation of an interim government, and the upcoming federal elections scheduled for March have created a highly uncertain operating environment for the programme. These contextual risks may result in significant operational and delivery challenges. Election-related restrictions, such as the election code of conduct period, could halt or limit activities for several weeks. Decision-making at all levels is expected to slow as the interim government prioritizes election preparations. Ongoing risks also include frequent turnover of officials, unclear delineation of roles across federal, provincial, and local tiers, and weak intergovernmental coordination—all of which can delay programme delivery and undermine resilience-building efforts.

Mitigation measures include continuous monitoring of political developments, proactive engagement with MoF, MoFE, MoHA, and NDRRMA, and adaptive work planning to front-load activities before the election code of conduct takes effect. Partners are instructed to adopt low-visibility approaches during sensitive periods and adhere to “do no harm” principles. Steering Committee and Programme Board meetings, along with monthly contextual reviews, will help maintain momentum toward delivering workplans across RAIN partners. In addition, there is a broader risk of more limited government capacity to respond to a large-scale humanitarian shock, increasing the risk of a compound crisis. RAIN retains its Internal Risk Facility as a programmatic vehicle in place should such a shock occur and the government ask for assistance (budget availability dependent). Residual risk remains major, and the risk appetite is receptive.

Safeguarding
Given the programme’s focus on working with vulnerable and marginalised populations through long delivery chains, safeguarding risks during the reporting period were anticipated to be significant. Key risks include sexual exploitation, abuse, and harassment (SEAH), exclusion of marginalised groups, and weak reporting mechanisms.

Mitigation measures prioritise prevention, detection, and reporting through monthly risk reviews, mandatory safeguarding training for all partners every six months, and cascading safeguarding standards throughout the delivery chain. Additional measures include spot checks, integration of qualitative indicators into results frameworks, and enforcement of survivor-centred response protocols. Health and safety provisions during construction activities include insurance coverage, first-aid kits, and hazard assessments. Duty of care protocols and business continuity plans are in place to address potential civic unrest.

Gender Equality Duty and Public Sector Equality Duty commitments continue to be upheld. The programme also maintains a low climate and environmental risk profile, consistent with Paris Agreement alignment; all activities have minimal emissions footprints and integrate environmental awareness into TA and grants guidance where relevant. Activities comply with the UK Environment Principles Policy Statement (EPPS) in the design of Nature-based Solutions (NbS). All required government approval processes have been completed to ensure compliance and prevent adverse environmental impacts.

These actions aim to reduce safeguarding risks to a ‘Major’ level, with a cautious risk appetite.

Policy and Programme Delivery
Delivery risks arise from delays in securing government buy-in, election-related disruptions, and partner-specific challenges such as UNCDF’s exit and Mott MacDonald’s planned withdrawal from the development sector. With the interim government focused on election preparations, decision-making at federal and other levels is expected to slow, which could impact programme delivery.

Additional risks include a slow implementation pace and unclear or competing priorities expressed by government stakeholders. Mitigation measures include continuous formal (through Technical and Steering Committees) and informal engagement with the GoN (MoFE, MoF, NDRRMA, DHM, complemented by scenario planning and adaptive work plans. BEK and partners will maintain light-touch engagement as appropriate during the election period.

During this review period, one major delivery risk around the UNCDF LoCAL programme was terminated as there was a very high likelihood the required fiscal transfer could not happen in line with agreed timelines, presenting high risks to planned expenditure. The funding was therefore reprioritised to other partners and interventions in support of climate change objectives. However, a risk remains around the programme overall not meeting the specific climate finance objectives the LoCAL programme would have addressed. Alternative delivery options for the climate finance component are being explored and the Theory of Change may need to be reviewed accordingly.

Residual risk for this category remains ‘Major,’ and the risk appetite is receptive.

Financial and Fiduciary
Fiduciary risks relate to the potential misuse of funds. Key risks include weak financial management (particularly by Community Based Organisations (CBOs) and Civil Society Organisations (CSOs) and national NGOs); fraud; aid diversion; and limited oversight of multilateral partners. These risks are compounded by complex delivery chains and reliance on sub-grants. Mitigation measures include:
- Comprehensive due diligence and delivery chain risk mapping
- Regular spot checks and independent audits
- Mandatory quarterly financial reporting by partners
- Robust internal controls and targeted training for downstream actors

BEK will monitor Value for Money (VFM) indicators and enforce fiduciary clauses in MoUs. The residual risk remains high, and risk appetite is cautious.

Reputational
Reputational risks stem from potential misuse of UK funds by politically affiliated CBOs, CSOs, local NGOs, and subcontractors during election periods, as well as from perceptions surrounding UK support for humanitarian response. Mitigation measures include shifting from sub-granting to subcontracting during this sensitive period, strengthening due diligence on political affiliations, and ensuring transparent communication between partners and BEK. Capacity-building for local actors and adherence to ICAI recommendations on localisation will remain central, underpinned by a risk-averse approach. With these measures in place, residual risk is moderate, and risk appetite remains cautious.

Public Service and Delivery Operations
Operational risks include disruptions due to civic unrest, inadequate business continuity planning, and weak duty-of-care protocols. Mitigation involves requiring partners to develop and share continuity plans, conduct safety assessments, and implement clear triggers for pausing activities. BEK will actively monitor partner compliance and guide during high-risk periods. Residual risk is major, and appetite is receptive.
People
Human resource risks include delays in recruitment, high staff turnover, and challenges in retaining skilled personnel across RAIN’s implementing partners. Mitigation includes enforcing KPIs for staff retention, prioritising recruitment timelines, and maintaining strong onboarding processes with adequate due diligence and safeguarding protocols. Partners are encouraged to provide incentives for embedded staff and to ensure continuity through rapid replacement strategies in the event of turnover. Residual risk remains moderate, and appetite is cautious.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
During this Annual Review period (November 2024-October 2025), the RAIN Programme spent £2.8 million.

Technical Assistance and Strategic Learning Unit (TASLU):
1st November 2024-31st October 2029 (Total Contract Value: £7.05 million)

The Technical Assistance and Strategic Learning Unit is being delivered under a commercial contract by Mott MacDonald (MM). To date, the total expenditure stands at £1,042,384, which includes an inception payment of £508,712 (November 2024-April 2025) and an implementation payment of 271,385.64 (May-July 2025). The implementation payment is tied to key milestone deliverables agreed between MM and FCDO. Contract Key Performance Indicators (KPIs) were assessed in November, and the inception report was submitted on 22 May 2025.

Annual audit Terms of Reference (ToRs) are scheduled for agreement in December 2025. The asset register and delivery chain mapping are regularly updated, with the latest update in August 2025, and financial forecasting is reviewed during monthly catchups. A spot check on assets was conducted in March 2025, and recommendations were shared with the MM team. Additionally, MM proactively reported active risks and mitigation measures linked to work plans in September and October, resulting in reduced financial spend for FY 2025/26.

Date of last narrative / report	25/11/2025	Date of last audited annual statement	TOR being finalised for the first audit

Local Climate Adaptive Living Facility (LoCAL)
Date (Total MoU Value £1,200,000)

An MoU was signed with UNCDF for the execution of the Local Climate Adaptive Living Facility under a UN framework arrangement. However, the project was closed earlier than anticipated due to extended and unclear timelines that did not align with the project’s TOC at that stage. Continuing with the project would have introduced significant risks to the planned expenditure and was unlikely to deliver value for money.

As the MoU falls under the framework arrangement, the audit will be conducted in accordance with UN provisions. Consequently, the expenditures related to this project will form part of the UN Board of Auditors’ Report for FY 2025–26. The audit report is scheduled for publication in July 2026 and will be formally analysed in August 2026.

The accounts are currently being finalized at UNCDF Headquarter level. The exact expenditure figure is pending confirmation; the tentative expenditure stands at approximately £65,000. This expenditure relates to activities and spend which had been committed before the FCDO informed UNCDF of the intent to terminate the agreement early.

Date of last narrative financial report	15/05/2025	Date of last audited annual statement	NA

Early Warning, Early Action, Adaptation, Community Resilience, Localisation and Inclusion 1st November 2024-31st October 2029 (Total AG Value: £10 million)
The Accountable Grant (AG) for this partnership is managed by People In Need (PIN). To date, total expenditure stands at £514,668.43, comprising an inception phase payment of £210,890 (November 2024-April 2025) and an implementation phase payment of £303,777 (May-July 2025). For FY 2025/26, a total allocation of £2.6 million has been approved.
Payments are released upon submission of quarterly financial statements, supported by corresponding progress reports. The Terms of Reference for the annual audit are scheduled for agreement in December 2025. Key financial management tools—such as the asset register and delivery chain mapping—are regularly updated (most recent update: August 2025), and financial forecasting is reviewed during monthly coordination meetings.
Following the September unrest, the PIN consortium demonstrated proactive risk management by sharing active risks and associated mitigation measures linked to workplans during September and October. Political uncertainty has impacted delivery timelines; however, as a proactive measure, the team provided weekly progress updates on ongoing activities. This approach reflects strong compliance with accountability standards and adaptive programme management practices.
Date of last narrative financial report	Due end of November	Date of last audited annual statement	TOR being finalised for the first audit

Shock Responsive Social Protection (SRSP) 24th September 2024 -31st March 2030 (Total MoU Value: £10 million)

An Administrative Agreement (AA) for this partnership was signed with the World Bank (WB), under which £1,160,000 was disbursed in three tranches. In alignment with the agreed reporting framework, biannual reports were submitted by WB in March 2025 and September 2025, covering progress against planned outputs, expenditure, and committed funds. Additionally, monthly catch-up meetings were conducted to review implementation progress, assess emerging risks, and monitor financial status.

Date of last narrative financial report	24/09/2025	Date of last audited annual statement*	08/09/2025

*The WB’s External Auditor carries out an annual “single audit” of the trust fund system. This is a set of audited accounts for the Trust Funds portfolio and a statement of assurance about the internal control systems that govern trust funds. FCDO accepts this in lieu of audited accounts for each trust fund. The FCDO International Financial Institutions Department (IFID) reviews the single audit each year on FCDO’s behalf and will flag any issues arising to post.

Start Fund Nepal (SFN) 17th April 2025-31st March 2026 (Total AG Value: £500k)

The Accountable Grant (AG) for this partnership is managed by Start Network, with the Start Fund Nepal (SFN) Secretariat hosted by Care Nepal. As per the AG agreement (17 April 2025–31 March 2026), the full amount has been disbursed in three tranches. Advance payments were provided to enable rapid access to funds, ensuring SFN members can respond quickly to small and medium-scale emergencies.

Quarterly financial and narrative reports have been submitted on schedule, covering April-June 2025 (submitted 31 July) and July-September 2025 (submitted 30 October). The Terms of Reference (ToR) for the annual audit (April 2025–March 2026) are currently under discussion with SFN. Key compliance tools, including the asset register and delivery chain mapping, are regularly updated (last update: August 2025), and financial forecasting is reviewed during quarterly coordination meetings. SFN has demonstrated proactive risk management by sharing active risks and mitigation measures linked to workplans for September and October, particularly in relation to immediate humanitarian response activities. This reflects strong alignment with accountability and adaptive management principles.

Date of last narrative financial report	30th October 2025	Date of last audited annual statement	ToR and timeline for the audit is being discussed.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
As the programme has been in its early delivery phase, monitoring has focused on validating initial activities and establishing systems for adaptive management. During the review period, five programme socialisation and monitoring visits have been completed across Madhesh, Karnali, and Lumbini provinces.

At the portfolio level, the Technical Assistance and Strategic Learning Unit has led development of the Adaptive Results Framework and supported refinement of nested component-level frameworks and establishment of indicator tracking and reporting systems. In parallel, PIN monitored anticipatory action pilots and resilience-building activities in Madhesh and Lumbini, and delivered baseline assessments in eleven local governments, which have identified critical gaps in early warning systems and safe shelter provision. Inclusive field consultations informed locally led adaptation actions with participation from government and vulnerable communities. Local governments pre-financed some adaptation schemes, which the programme later scaled up. However, in some cases, co-financing was not possible due to the Gen Z movement and fires in government offices, prioritizing recovery work.

World Bank has tracked progress on SRSP guideline dissemination and Integrated Social Registry development, alongside regulatory amendments and initiation of the Public Expenditure and Institutional Review, with timelines adjusted following the September unrest. SFN has activated alerts for drought, AWD and floods due to heavy rains and monitoring visits have reviewed implementation quality and governance, including decision-making speed (which has averaged 42.5 hours).

Evidence

Across the RAIN portfolio, evidence has been increasingly disaggregated by gender, age, and disability, strengthening inclusive programming and guiding adaptation. Baseline assessments and monitoring have highlighted major gaps in early warning awareness, safe shelter access, and language preferences, which has informed programme design. Start Fund Nepal and the PIN consortium have collected beneficiary data to integrate gender and disability considerations; GEDSI analysis by PIN has informed disability screening camps linking individuals to social security services, while its baseline in eleven local governments has shown that over half lacked early warning knowledge and most preferred local-language messaging – evidence that is now driving inclusive risk communication and Community Disaster Management Committee (CDMC) formation.

PIN and DCA have also built their adaptation programmes on the LLA principles. SFN has used regular peer-to-peer learning reviews and post-distribution monitoring to adapt programming. Two Post Distribution Monitoring (PDM) exercises for flood early action and drought response have been completed by SFN.

The World Bank is currently drafting the Public Expenditure and Institutional Review (PEIR), which will add to the evidence base on the policy and institutional reforms necessary to advance adaptive social protection in Nepal. Similarly, the TA/SLU has supported endorsement of SOPs for Emergency Operation Centres, advanced directives for Multi-Hazard Early Warning Systems and the Anticipatory Action Framework, and initiated upgrades to the Reconstruction Management Information System under Recovery to Resilience – evidence from these processes is being used to augment programme planning.

Learning
Learning across RAIN components has begun, despite delays caused by the September protests, which postponed the second Programme Board meeting. The Strategic Learning Unit (SLU) has developed Terms of Reference for the Joint Learning Agenda after consultation with Component partners to focus on adaptation and inclusion for this fiscal year, and this will be commissioned in December to build evidence and inform programming decisions. The SLU has also initiated a GEDSI review, expected by March, and launched a learning exercise on integrating inclusion into early warning systems in Madhesh Province. These steps create a structured approach to capturing lessons and embedding adaptive management across the programme.

Early insights highlight that adaptive planning has been essential to maintain delivery during political disruption, while governance reforms such as the Emergency Operation Centre SOP demonstrate the value of securing early institutional ownership. For PIN, learning has focused on the importance of inclusive and accessible communication in local languages. The World Bank’s experience shows that cross-country exchanges accelerate policy reform, but institutional clarity and coordination remain critical for rolling out integrated social protection systems. Start Fund Nepal’s learning underscores the need for stronger local ownership and timely dissemination of post-distribution monitoring results to close feedback loops and improve anticipatory action.

Looking ahead, learning aims for the coming year include operationalising the Joint Learning Agenda, continued work to embed GEDSI principles across all components, and ensuring that evidence and lessons guide adaptive management and inform programming choices and influencing priorities for FY 2026/27.

As part of the next review, RAIN will critically appraise its portfolio monitoring approach and learning strategy to connect to robust portfolio learning and impact. This will be supplemented by innovative approaches adopted by Samartha and RIVA programmes.

RAIN 2024 Recommendations:
Government Engagement: The programme team engaged closely with the Government of Nepal early in the design stage of the programme (prior to business case approval). However, frequent changes within the government and the number of stakeholders to be engaged (multiple ministries) still created some challenges in terms of continuity of relationships and meant that issues re-emerged or new issues emerged which needed to be discussed and resolved before GoN approval could be secured. This affected the timeliness of the negotiations process. It was a helpful strategy for BEK to negotiate a package of programmes to be approved, so the government had a clear overview of BEK’s new portfolio and the support the UK is providing.
Progress observed RAIN AR 2025: The Climate and Resilience Team, alongside RAIN partners, continued to engage extensively with the GoN (NDRRMA, MoHA, MoFE, MoF, DHM) to agree priorities, work plans and secure buy-in in the early implementation phase. At times this has been challenging due to a number of staff changes for government counterparts, the GoN’s perception of the complexity of the programme (with multiple partners) and the challenges of coordination (securing the time of senior officials across multiple government entities and need to accommodate different styles and priorities). There was a long delay in securing a Steering Committee meeting (initially planned for March/April 2025) due to a combination of factors (difficulty in securing government official time with the multiple stakeholders involved and multiple staff changes). While the governance of the programme was covered/negotiated in the Programme Document agreed with the MoF, government interlocutors at the relevant line ministries wished for further elaboration and clarification of roles and responsibilities. While these discussions took longer than anticipated, the programme now has a detailed Programme Operating Manual. / The 1st RAIN Steering Committee took place on 28th October 2025. The Government had decided this should be at Secretary level (MoHA, MoFE). Some follow-up actions were ongoing at the time of this AR, but are anticipated to be completed by end of December 2025. While the process has taken more time than anticipated, it has surfaced clear preferences and ways of working have been agreed going forward which should simply the process for engagement with GoN on the programme in future years (e.g. it has been decided that work plans and budget information will be reviewed and approved in a Technical Committee led by the NDRRMA CEO before going to the Steering Committee- still co-chaired by MoHA and MoFE) for formal endorsement.
Action: The RAIN team will negotiate with GoN to ensure that the RAIN Programme Operating Manual gets endorsed in the next Steering Committee meeting that has a provision of the RAIN Technical Committee approving RAIN’s overall workplan and presenting it to the Steering Committee in future meetings. Action: Climate and Resilience Team (Green Growth Group) by. December 2025.
Partner mobilisation: RAIN has 4 intrinsically linked components to be delivered initially by 5 partners. Mobilising partners in parallel and in the final year of predecessor programmes is already proving valuable in terms of coherence, the ability to learn lessons and establish coherent ways of working and work plans. The recommendation for the first year of the programme is to build on this positive early start and spirit collaboration amongst partners. A programme board will be established as a formal forum for engagement, ensuring coherence and space for lesson learning and course correcting. In addition, the BEK team will continue to encourage relevant partners to collaborate and join up on shared objectives and outcomes. This includes collaboration and coordination with other BEK partners and programmes (for example UNCDF’s work on LoCAL and BEK’s LISP programme on climate resilient infrastructure, the RAIN TA Facility/SLU and the Samartha TA provider on systems strengthening, and the PIN consortium and other relevant BEK programmes on inclusion). Active engagement in the BEK Roundtables process will also ensure coherence with BEK’s overall portfolio and approach.
Progress observed RAIN AR 2025: RAIN partners continued to collaborate well and share information, both formally (through the Programme Board) and informally. Following the reduction in ODA ant the footprint of BEK’s overall portfolio, organic opportunities to collaborate were limited. However, RAIN and the Security and Justice Programme overlap in some local geographies in Madesh. Both programmes are delivered by People in Need who are actively looking for synergies and complementarities for interventions (for example on Gender Based Violence prevention). There are also shared geographies with Samartha, which provides technical assistance for social sector systems strengthening. In addition, lesson sharing is planned between LISP and RAIN partners on climate adaptation and linking communities and local government planning.
The BEK Climate and Resilience team will continue to ensure internal cross-collaboration between RAIN partners and with the rest of the portfolio on joint working and learning across Madhesh and Lumbini. Action: Climate and Resilience Team (Green Growth Group) by March 2026

Annex:

Alternative VFM across all RAIN components to supplement the concise version above.

A commercial partner, an international NGO, a UN agency, a multilateral development bank and a network of international NGOs implement the RAIN programme. Given the diverse partners, the SLU is reviewing the common economy, efficiency, effectiveness, and equity, considering overall cost-effectiveness across Value for Money (VFM) assessments, which are described below.
Technical Assistance and Strategic Learning Unit (TASLU)’s VFM approach applies a comprehensive framework with indicators across Economy, Efficiency, Effectiveness, and Equity, enabling systematic tracking from inputs to impact. Economy focuses on managing programme and unit costs to deliver technical assistance and learning support, while Efficiency measures the cost per policy or training and collaboration across components. Effectiveness assesses the implementation of policies and directives supported by RAIN TA SLU, and Equity ensures GEDSI integration into policies and tracks participation by marginalised groups. Although VfM assessment will begin in the next quarter when data becomes available, this structured approach provides a clear basis for reporting achievements against adaptive results.
Local Climate Adaptive Living Facility (LoCAL)’s mechanism was designed to enhance the Economy by strengthening regional and national capacity in planning, budgeting, and procurement, ensuring efficient use of resources and quality investments through Performance-Based Climate Resilient Grants (PBCRGs). It aimed to deliver Efficiency by leveraging existing governance structures to minimise overheads and duplication, while piloting PBCRGs in two rural municipalities to enable scalable climate-resilient investments. The approach sought Effectiveness by aligning local interventions with NDC and NAP priorities, promoting inclusive and gender-responsive planning, and attracting additional climate finance for long-term resilience. Finally, Equity was embedded through participatory processes and GESI-focused measures, ensuring benefits reach vulnerable groups, including women and persons with disabilities. However, these outcomes could not be measured as the MoU was curtailed after six months, limiting implementation and assessment of VfM results.
The Early Warning, Early Action, Adaptation, Community Resilience, Localisation and Inclusion component has Non-Project Attributable Costs (NPAC) of 8%, with 92% of costs allocated to direct project delivery. In the economy, overheads are kept below 20%, MEAL costs are at 1.6%, and procurement follows transparent, competitive processes with regular market reviews, while shared resources and fuel monitoring reduce operational costs. Efficiency is demonstrated by an alpha ratio above 80% across outputs, with a cost-per-beneficiary of £9.62 for climate adaptation and £236,015 per sub-basin for early warning system upgrades, supported by robust monitoring systems and adaptive management. Effectiveness is evident through key milestones such as 26 local governments (10 in Lumbini and 16 in Madhesh) using risk data for fiscal planning and 30 officials trained on inclusive early action, alongside progress on integrated early warning systems and provincial early action plans. Finally, equity is embedded through GEDSI strategies, disability-inclusive design, and participatory planning, tracked via disaggregated indicators and reinforced by accessible feedback mechanisms. These measures ensure that activities achieve timely, cost-efficient, and inclusive resilience outcomes.
The VFM of the Shock Responsive Social Protection (SRSP) component has been analysed across the four pillars, supported by measurable indicators. As per the MoU, 81% of costs are for Technical Assistance (TA) for GoN, whereas 19% for overheads. On the economy, consultant and TA costs have been benchmarked against local and international standards, ensuring competitive rates, while hosting arrangements and shared logistics have kept overheads below 20%, allowing over 80% of the GBP 780,000 disbursed so far to be directed toward technical delivery. Efficiency is demonstrated by timely fund utilisation, with 80% of available resources committed by September 2025, and adaptive planning that enabled rapid mobilisation of workshops and technical support despite recent political disruptions. For effectiveness, progress is evident through institutional milestones such as the July 2025 decision granting MoHA and DoNIDCR the mandate for an integrated social protection system, and advancement of the Integrated Social Registry (ISR) - key indicators of policy reform and institutional strengthening. Finally, equity is embedded through inclusive provincial-level dissemination workshops and policy dialogues, ensuring representation of local actors and targeting mechanisms that prioritise vulnerable households, consistent with the RAIN GEDSI and LNOB principles.
Start Fund Nepal (SFN) demonstrates strong VFM in terms of the timeliness, quality, and appropriateness of localised humanitarian interventions. From an economic perspective, SFN maximises resources by leveraging the host agency’s infrastructure for HR, finance, and logistics, enabling nearly 70% of funds to flow directly into project delivery (disbursement pot), and ultimately 90% of resources to direct delivery with 10% overheads. Strategic procurement and local sourcing further reduce costs while supporting the local economy, as seen in interventions that prioritised essential water and health supplies over high-cost infrastructure. On efficiency, SFN consistently outperforms global standards, with funding decisions averaging 42.5 hours against the 72-hour benchmark and rapid fund transfers enabling partners to initiate activities within 5 working days. This speed is complemented by transparent, member-led decision-making and co-funding commitments that enhance sustainability. In terms of effectiveness, SFN’s anticipatory and rapid responses have delivered measurable impact, including early containment of diarrhoeal outbreaks and timely water support. At the same time, robust monitoring systems track indicators such as time to assistance and beneficiary satisfaction to ensure accountability and learning. Finally, equity remains central to SFN’s approach, with strong representation of local and national NGOs 13.5% of funds were directly transferred to local and national NGOs) in governance structures and project consortia, targeted outreach to marginalised groups, and inclusive feedback mechanisms that uphold ‘Leave No One Behind’ principles reaching approximately 703 people with disability out of 75,190 beneficiaries of which 37291 are women.