## UPDATED Programme ARF
Revised RAIN Portfolio ARF (Updated 2nr Feb, 2026)
IMPACT | Impact Indicator 1 |  | Baseline | 2025-10-31 | 2026-10-31 | Note: Reporting period Year 1: Until 31 Oct 2025 Year 2: 1 Nov -31 Oct 2026
Improved resilience of at-risk, vulnerable and marginalised communities to anticipate, adapt, prevent, and absorb climatic and non-climatic shocks. Government of Nepal (GoN) has improved systems and institutional capacity in place to support at-risk communities. | # of people who have benefitted from improved resilience through implementation of disaster resilience, climate adaptation and social protection policies to build resilience against climatic and non-climatic shocks (including crisis-affected people through locally led response and early action) (Disaggregated by gender, PWD, Dalit and Indigenous groups (where possible)) | Planned |  | N/A for reporting | N/A for reporting (reported as actual, where possible across the portfolio)
Achieved
| # people supported to better adapt to the effects of climate change as result of International Climate Finance (ICF KPI 1) |  | Source:
To be calculated across RAIN portfolio, census data
Outcome 1 | Outcome Indicator 1.1 |  | Baseline | 2025-10-31 | 2026-10-31 | Assumptions
Inclusive systems strengthened such that Government of Nepal (GoN) can better access international climate finance to meet the goals of its National Adaptation Plan, Nationally Determined Contributions, Long Term Strategy and Climate Change Policy and uses its own fiscal resources to allocate, spend and monitor its interventions on resilience, adaptation, climate finance and social protection | # relevant policy frameworks, operational directives and standard operating procedures (SoPs) developed and implemented by federal, provincial and local governments on resilience, adaptation and social protection (Disaagregated by organisation/level of government) | Planned |  | 1 (NDRRMA implmented SoP of Emergency Operating Centres in Nepal) | 1 (AA Framework implemented by NDRRMA) | - Federalism continues to provide incentives that support delivery - No large-scale disasters or policitial disruption divert attention from delivery - Federal Government agree on climate finance standard operating procedure - uitable windows of opportunity to drive evidence-based policy can be found​
Achieved
Source:
Programme records, policy document and evidence of implementation. Narrative reporting of steps towards and maturity scales to be used in reporting - SLU Analysis.
| Outcome Indicator 1.2 |  | Baseline | 2025-10-31 | 31 Oct 2026
| Value (NPR/£) allocated and spent for disaster risk management and climate adaptation at the federal, provincial and local governments (against baseline) (Narrative reporting to discuss attribution) | Planned |  | N/A for reporting | N/A for reporting
Achieved
Source:
Federal budget and provincial budget records, key informant interviews
| Outcome Indicator 1.3 |  | Baseline | 2025-10-31 | 31 Oct 2026
| # of decisions, policies, programming, organisational approaches etc. informed by learning and capacity building (practices/ processes/methodologies/policies/ regulations etc.) adopted, evidencing RAIN legacy in supported organisations (used as a proxy for sustainability /system strengthening and disaggregated by organisation where change is taking place, i.e. ministry, department and agency) | Planned |  | N/A for reporting | Reported as actual, where possible
Achieved
Source:
via key informant interviews
| Outcome Indicator 1.4 |  | Baseline | 2025-10-31 | 31 Oct 2026
| Value (NPR/£) of climate finance proposals approved Volume (NPR/£) of public finance mobilised for climate change (ICF KPI 11) | Planned |  | N/A for reporting | N/A for reporting
Achieved
Source:
Proposal approval record from DAE/GCF, in compliance with ICF methodology
Outcome 2 | Outcome Indicator 2.1 |  | Baseline | 2025-10-31 | 2026-10-31 | Assumptions
Communities are more resilient to disasters through improved preparedness, inclusive access to early warning systems, and strengthened delivery mechanisms on early action and adaptation measures | % of community members that took recommended early action after they received the inclusive risk communication messaging across multiple hazards | Planned | 8.8% | 35% (of respondents surveyed in reporting period) | 85% (of respondents surveyed in reporting period) | - Community Based Organisations (CBOs) are able to absorb capacity improvements, and work with communities to implement jointly identified activities that support resilience - Provincial Governments (PGs) are using the knowledge, data and support system available for better decision making and responsiveness at the provincial level - Local Governments (LGs) are empowered enough to assess and improve the resilience of vulnerable communities - Vulnerable groups are targeted and able to participate and that ‘no one is left behind’ ensuring the programme is localised and inclusive - Communities through CBOs are able to demand and advocate for improved response from local government - Local governments are willing to support the most vulnerable before, during and after any shocks
Achieved
Source:
Programme records, Baseline, surveys of community members
| Outcome Indicator 2.2 |  | Baseline | 2025-10-31 | 31 Oct 2026
| % of people reporting improvements in perceived safety from hazards as a result of inclusive disaster resilience and climate adaptation measures (compared to baseline) |  | 44% | 50% | 70%
Achieved
Source:
Programme records, Baseline, surveys of community members
Outcome 3 | Outcome Indicator 3.1 |  | Baseline | 2025-10-31 | 2026-10-31 | Assumptions
Humanitarian response and early action delivered by local actors is timely, proactive, coordinated, needs-driven and promote local leadership | % of RAIN humanitarian responses and early action interventions that are timely, proactive and needs-driven in consultation with at-risk communities | Planned |  | 70% of interventions where crisis affected and at-risk population are consulted and receive support within 3-5 days (Component 5 and Component 3) | 75% of interventions where crisis affected and at-risk population are consulted and receive support within 3-5 days (Component 5 and Component 3) | - Empowerment of excluded groups leads to more inclusive decision-making​ - Local and National NGO responders in locations (or able to move to them) to respond to most frequent crises - Agencies have equal weighting of decisions and equitable weighting of opportunity - Agencies make available time to perform Governance functions - LNNGOs complete the due diligence assessments and are eligible to access funding - LNNGOs are operational in the areas where alerts are raised - LNNGOs submit proposals when the SF is activated - LNNGO proposals are selected by the project selection committee - Donor openness: reassessment, due diligence and capacity/ development of NGOs to meet requirements - Donors are interested and have available funding to support pooled funding mechanism
Achieved
Source:
Programme records, KII
| Outcome Indicator 3.2 |  | Baseline | 2025-10-31 | 31 Oct 2026
| % representation of local and national NGOs in decision-making (allocation and selection) meetings ensuring transparent and inclusive humanitarian response (localised and coordinated) (demonstrating local leadership for agency and decision making) | Planned |  | 50% representation of local actors in allocation meetings 30% representation of local actors in selection meetings | 52% representation of local actors in allocation meetings 50% representation of local actors in selection meetings
Achieved
Source:
Programme records, KII
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2025-10-31 | 2026-10-31 | Assumptions
Government of Nepal (GoN) ’s systems supported, and capacity and knowledge strengthened via RAIN Technical Assistance in Climate Finance, Climate Change Adaptation, Disaster Risk Reduction and Management, and Shock Responsive Social Protection | # Relevant policy frameworks, operational directives and standard operating procedures (SoPs) drafted by government and supported by RAIN TA SLU on CF, DRRM and CCA and influenced by GEDSI considerations # climate policies informed by ICF TA (ICF TA KPI 3) | Planned |  | 1 (SoP of Emergency Operating Centres in Nepal) | 5 (Anticipatory Action Framework for NDRRMA, 2- PCCSAP for Madhesh and Lumbini provinces; MHEWS Operational Proceedure, Federal level; SOP for Provincial EOC (Madesh)) | - GoN accept embedded staff to improve capacity for service delivery and policy implementation - No large-scale disasters divert attention from delivery
Achieved
Source:
Framework documents and policy drafts. GEDSI and CCA sensitivity to be led by relevant Tech/cross-cutting Expert (using AI/qualitative scanning software)
| Output Indicator 1.2 |  | Baseline | 2025-10-31 | 2026-10-31
| # of people whose capacity has been built and % individuals are reporting improved knowledge and skills in resilience, adaptation and social protection through RAIN technical assistance (disaggregated by topic, organisation, gender) | Planned |  | 48 Individuals (DDA and Tranche release (Illam)) As per actual (component 4) | 322 Individuals (Tranche release in Karnali Province; DDA in Karnali Province; DDA and Tranche release in Salyan; RMIS and roll out in Kavreplanchowk; RMIS training and roll out in Surkhet); 'Post-disaster relief distribution' guideline-Technical annex in Kathmandu; CCA and DRR in Lumbini Province) As per actual (component 4)
Achieved
Source:
Training records, tracker survey
| Output Indicator 1.3 |  | Baseline | 2025-10-31 | 2026-10-31
| # of concept notes and /or funding proposals drafted to access international climate finance | Planned |  | N/A | 2 (GCF proposal for NTNC; FRLD proposal for AEPC)
Achieved
Source:
programme records / drafted concept note and/or funding proposal
| Output Indicator 1.4 |  | Baseline | 2025-10-31 | 31 Oct 2026
| Integrated Social Registry (ISR) established and operational for Adaptive and Shock Responsive Social Protection (ASRSP) | Planned |  | Narrative on dialogue and consensus building completed and evidence of testing and use of ISR and link with Digital Lending Operation | Narrative on dialogue and consensus building completed and evidence of testing and use of ISR and link with Digital Lending Operation
Achieved
Source:
Programme records, KII
| Output Indicator 1.5 |  | Baseline | 2025-10-31 | 31 Oct 2026
| # of organisations supported by ICF technical assistance (ICF TA KPI 2) (TA interventions delivered by technical staff embedded in GoN, e.g. coaching and knowledge transfer, policy advice, stakeholder engagement) (disaggregated by TA type/modality) | Planned |  | 6 organisations directly supported (narrative reporting to include modality of technical assistance provided and progress to outcomes) | 6 organisations (same) directly supported (narrative reporting to include modality of technical assistance provided and progress to outcomes)
Achieved
Source:
Programme records, KII
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2025-10-31 | 31 Oct 2026 | Assumptions
Communities (including marginalised and most vulnerable groups) are supported on early warning and early action and have increased adaptive capacity to natural hazards and shocks | # of people covered from early warning systems at the basin level in Madhesh and Lumbini (Including newly installed hydro-met stations in river basins providing early warning service to at-risk communities) (disaggregated by gender) | Planned |  | 200k people covered | 550k people covered | - Local Government officials are willing and able to utilise learning - Local governments are willing and able to implement jointly identified solutions - Community based organisations and local governments are able to work together on disaster risk management and early action - Department of Hydrology and Meteorology (DHM) and NDRMAA takes the shared ownership to handle the two-ways communication channels - Vulnerable groups are willing to be enrolled in the government led social protection schemes
Achieved
Source:
Programme records
| Output Indicator 2.2 |  | Baseline | 2025-10-31 | 2026-10-31
| # of adaptation measures aimed at reducing risk and enhancing climate resilience of at-risk communities (disaggregated by gender and disability) | Planned |  | Community consultation and site finalisation | 32 NbS and 7 Safe shelters constructured or retrofitted
Achieved
Source:
Programme records, census data
| Output Indicator 2.3 |  | Baseline | 2025-10-31 | 2026-10-31
| # of at-risk and vulnerable people reached through inclusive risk communication channels (including integrated voice response and multi-hazard sirens) (disaggregated by gender and disability) | Planned |  | 10k people reached with inclusive messaging across multiple hazards (heatwaves, cold waves, droughts and floods) | 174k people reached with inclusive messaging across multiple hazards (heatwaves, cold waves, droughts and floods)
Achieved
Source:
Programme records
| Output Indicator 2.4 |  | Baseline | 2025-10-31 | 2026-10-31
| Value of co-financing disbursed by federal, provincial and local governments to sustainably scale up early warning, early action, adaptation, inclusion and localisation | Planned |  | As per actual | As per actual
Achieved
Source:
Programme records, KII
| Output Indicator 2.5 |  | Baseline | 2025-10-31 | 2026-10-31
| # of people screened for eligibility to enroll in government social protection schemes (Disaggregated by gender and disability) | Planned |  | 2,500 people with disabilities and 8,000 landless screened At least 100 linked with government social protection systems | 3,500 people with disabilities and 12,000 landless screened At least 100 linked with government social protection systems
Achieved
Source:
Programme records, screening and enrolment data
| Output Indicator 2.6 |  | Baseline | 2025-10-31 | 2026-10-31
| # of community members, government officials, individuals from CSOs/CBOs with improved knowledge of early warning, early action and adaptation and % of individuals scoring above the defined competency threshold | Planned |  | # people, as per actual; 70% of participants meeting the minimum threshold for improved skills and knowledge | # people, as per actual; 70% of participants meeting the minimum threshold for improved skills and knowledge
Achieved
Source:
Training records, tracker survey
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2025-10-31 | 31 Oct 2026 | Assumptions
National and local NGOs rapidly and proactively deliver quality and lifesaving assistance to communities responding to small to medium scale humanitarian emergencies in a timely manner, including anticipatory action | # of crisis alerts raised and activated (including anticipatory action) | Planned |  | 3-Raised and acitvated alert, including 1 anticipatory alert raised and activiated | 5-Raised and 4 acitvated alert, including 2 anticipatory action alert raised and activated | - Decision-making is unbiased and driven by affected population needs over organizational benefit - Familiarity and confidence in Start Fund mechanism: standard and anticipation window - Agencies have an equal weighting of decisions and equitable weighting of opportunity - Timely engagement of FOREWARN expert and provide forecast analysis
Achieved
Source:
Programme records, Salesforce alert data
| Output Indicator 3.2 |  | Baseline | 2025-10-31 | 2026-10-31
| # of at-risk and crisis-affected people directly and indirectly reached through early action and response support (e.g. cash/voucher assistance, WASH support, NFI kits, psychosocial counselling, nutrition support, winterisation, risk communication etc.) (Disaggregated by gender and disability) | Planned |  | As per actual (Component 3) 48,729 people (Component 5) | As per actual (Component 3) 56,933 (Component 5)
Achieved
Source:
Programme records, Salesforce alert data
| Output Indicator 3.3 |  | Baseline | 2025-10-31 | 2026-10-31
| % of recipients who report that the assistance was delivered in a timely manner and responsive to their needs | Planned |  | Minimum 90% (for Component 3) Minimum of 80% (for Component 5) | Minimum 90% (for Component 3) Minimum of 90% (for Component 5)
Achieved
Source:
Post Distribution Monitoring analysis
| Output Indicator 3.4 |  | Baseline | 2025-10-31 | 2026-10-31
| # of people from organisations whose capacity has been built (in writing alert notes, proposal writing, forecasting) and % of participants receiving training reporting that their knowledge and skills have been enhanced | Planned |  | As per actual | People (as per actual) from 31 organisations with 70% of participants meeting the minimum threshold for improved knowledge and skills (Component 5)
Achieved
Source:
Training records, tracker survey
| Output Indicator 3.5 |  | Baseline | 2025-10-31 | 2026-10-31
| Value of funding disbursed for anticipatory action and response and % of funding disbursed to local actors (FCDO’s Indicator on Pre-Agreed Financing) | Planned |  | As per actual (for both Component 5 Component 3 consortium) and 75% of funding disbursed to local actors | As per actual (for both Component 5 Component 3 consortium) and 75% of funding disbursed to local actors
Achieved
Source:
Programme records
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | 2025-10-31 | 31 Oct 2026 | Assumptions
Portfolio learning and collaboration mechanisms supporting system strengthening using data, innovation and evidence to inform stakeholder engagement for policy change, influence adaptive decision-making and pathways to scalability and sustainability | # learning products developed and disseminated (e.g. case studies, evaluation briefs, risks watches, reviews and diagnostics) (disaggregated by topic) | Planned |  | 2 (across all RAIN components) | 8 (across all RAIN components) | - Organisations incl. GoN, Local and Provincial are willing and able to utilise learning - Policitical buy-in and funding available to scale innovation solutions - SFN project awarded agencies adapt learning and generated evidences - Bilateral utility of connecting with other platforms and networks and openness to do so. - SFN projects are not awarded simultaneously in multiple geographic location and beyond the monitoring capacity of SFN secretariat. - Cross learning sharing between FOREWARN members and SFN members
Achieved
Source:
Programme records
| Output Indicator 4.2 |  | Baseline | 2025-10-31 | 2026-10-31
| # of individuals and/or organisations reached by RAIN learning products and uptake from wider stakeholders (both government and non-government) (disaggregated by learning topic; types of organisations reached) | Planned |  | As per actual | Organisations = 99 (Component 1: 45, Component 3,4: 16 local NGOs + 7 provincial government, Component 5: 31 I/NGOs) People = as per actual
Achieved
Source:
Programme records, e.g. count of document uploads, distribution list
| Output Indicator 4.3 |  | Baseline | 2025-10-31 | 31 Oct 2026
| # of policy dialogues, knowledge exchanges, learning events and collaborative workshops between RAIN partners conducted to support policy reform in resilience, adaptation and social protection (disaggregated by topic) | Planned |  | As per actual | 12 (across all RAIN components)
Achieved
Source:
Programme records
| Output Indicator 4.4 |  | Baseline | 2025-10-31 | 2026-10-31
| # of inclusive innovations in resilience and adaptation developed and tested for scalability and uptake-potential by government and non-government actors | Planned |  | N/A | 4 innovations (tested for functionality, scalability and sustainability)
Achieved
Source:
Programme records, KII