Business Case – Amended November 2023

Summary Sheet

Portfolio/ Business/Country Plan Summary: / The programme aims to increase clean electricity access, particularly by the poor, in Pacific Island Countries (PICs). It is aligned with the UK’s Pacific Approach, which is framed around: / The UK as a long-term, honest, and reliable partner, working with PICs to improve their resilience. / Supporting PICs to grow their economies sustainably, create jobs, and lifting themselves out of poverty. / Delivering results under the Australia-UK Strategic Infrastructure and Development Dialogue (SIDD) of increased investment in renewable energy in PICs aligned to the British Investment Partnerships (BIP) approach.

Title: Pacific Clean Energy Programme
Programme summary: / The objectives of the Pacific Clean Energy Programme (PCEP) are increased and equitable access to affordable and reliable electricity, and reduced carbon emissions in PICs. This may lead to improved health and new economic opportunities, particularly for poor people. It will also help put PICs on green development pathways and improve their economic security. PCEP will achieve this by increasing investment in renewable energy generation and transmission. It is strongly aligned with UK strategic priorities in the region and by working with likeminded donors it will strengthen the UK’s influence and relationships in line with our BIP approach. PCEP has two components: / 1. Regional Clean Energy Investment Fund (RCEIF): UK investment would help capitalise a blended finance fund, leveraging financing from public and private sources, and also support local project developers develop a pipeline of projects. It would support increased renewable energy investment, a transition out of costly diesel generation and improved access to electricity in ODA-eligible PICs. FCDO has identified a preferred fund manager and has third-party assessment of its proposal and is in dialogue with a likeminded donor about co-investing. (Estimated at up to £16.5 million). / 2. Papua New Guinea Clean Energy Investment (PCEI): UK funding will enable an ongoing Australian programme to scale up and reach additional poor households without access to electricity through innovative technologies for off-grid electrification. (Estimated at up to £3.5 million). / The beneficiaries will be the increased number of people and businesses with access to clean energy on Pacific Islands, PIC governments due to reduced diesel fuel imports and the global population due to lower greenhouse gas (GHG) emissions.
What is the rationale for UK Aid spending? / Global action on climate change is urgently needed and a strategic priority for HMG. / By supporting PICs increase the use of renewables for power generation and reduce use of diesel and other polluting fuels, PCEP will align with strategic objectives and steers in the: International Development Strategy, Integrated Review Refresh 2023, Pacific Strategy, and the UK-Australia Strategic Infrastructure and Development Dialogue. It will also contribute to HMG’s imperative of reducing global dependence on Russian fossil fuels. / The UK’s comparative advantage is our strong relationships in the Pacific region and with Australia, our ability to work collaboratively with other donors and private investors, and our ability to support innovative investment models. We are well positioned to leverage PCEP to crowd in public and private capital for renewable energy investment in PICs. / Through AUKUS, the UK is working more closely with Australia in the Pacific on strategic defence and security issues. Our bilateral partnership with Australia is deepening, and PCEP can help us better support and influence Australia’s energy and climate policy and programmes across the region.
Programme Value: Up to £20 million. Of this, approval for £3.5 million was given in April 2023, and an additional £16.5 million is being sought now as set out in the business case addendum.		Country/ Region or Sector: Pacific
		Joelle Jenny, Director Southeast Asia and Pacific Directorate (SEAPD) / I confirm that Departmental processes for BC review have been followed. Any use of non-fiscal CDEL will be subject to further approval processes, including submission to the Financial Transactions Board, the Investment Committee and the Financial Director, April 2023 / Ben Mellor, Director India and Indian Ocean Directorate (IIOD) Business Case Amendment – I am content to approve this amendment. We have sought to simplify management and accountability lines through myself and Charlotte Coles being the responsible Directors and Deputy Directors for this programme. I have agreed with the team that close working and consultation with Pacific Development Unit and the Oceanic network will continue throughout the lifetime of the programme. February 2023 / Jenny Bates, Director General, Indo-Pacific / This amendment increases the total value of the programme to £20 million and requires DG approval. I am content to approve the amendment on the basis there is a window of opportunity to launch this innovative clean energy fund alongside a like-minded donor. This will enable the fund manager to raise further capital. We hope the fund is successful in reaching target size thereby creating the first ever clean energy private equity fund in the Pacific.
Contact names		Mary Hunt & Gabriel Montagu-Pollock
Threshold for final approval of Business Case: Director General, Indo-Pacific
Date of Approval of Concept Note:	21/07/2022	Name and role of Approver; Ministers Milling and Goldsmith
Date of Approval of Business Case:	12/04/2023 / (PNG Component only) / 19/12/2023 / (RCEIF Component)	Name and role of Approver: / Joelle Jenny, Director SEAPD; Read-Webb (BIPD) / Jenny Bates, Director General, Indo-Pacific
Programme Code: 400021	AMP Start Date: 17/5/2023	AMP End Date: 31/03/2030
Overall programme risk rating:	Major
Vault Number:	Save this document in Vault with the correct metadata (‘Business Case’) to allow for publication to Devtracker. Note that FCDO programme teams that do not use Vault (i.e. legacy FCO), should follow existing processes for saving information.
[note] The end date is conditional on a robust exit plan matching this timeframe being developed for the UK investment in RCEIF. If this is not possible without a significant loss in value for the investment, approval to extend the end date may be sought at the same time as approval for funding for the RCEIF component is sought.

Acronyms:
ADB: Asian Development Bank	NEA: National Energy Authority
AIFFP: Australian Infrastructure Finance Facility for the Pacific	NDC: Nationally Determined Contribution
AGA: Accountable Grant Agreement	NZD: New Zealand Dollar
AUD: Australian Dollar	ODA: Oversea Development Assistance
AUKMIN: Australia UK Minister Meeting	PCEP: Pacific Clean Energy Programme
BII: British International Investments	PCREEE: Pacific Centre For Renewable Energy & Energy Efficiency
BIP: British Investment Partnership	PG: Pollination Group
CDEL: Capital Departmental Expenditure Limit	PEAF: Pacific Energy Access Fund
CO2: carbon dioxide	PIC: Pacific Island Country
DCA: Development Cooperation Agreement	PIDG: Private Infrastructure Development Group
DFAT Department of Foreign Affairs & Trade	PIF: Pacific Island Forums
ESIP: Environment & Social Infrastructure Programme	PK: Pawarim Komuniti
EU: European Union	PNG: Papua New Guinea
FCDO: Foreign, Commonwealth & Development Office	PPL: PNG Power Limited
FTE: Full Time Equivalent	PPP: Purchasing Power Parity
FTSB: Financial Transactions Steering Board	PRIF: Pacific Regional Infrastructure Facility
GBP: Great British Pounds	PRO: Programme Responsible Owner
GDP: Gross Domestic Product	PrOF: Programme Operating Framework
GHG: greenhouse gas	PV: Photovoltaic
GNI: gross national income	RBF: Results Based Finance
HMG: Her Majesty’s Government	RCEIF: Regional Clean Energy Investment Fund
HMT: His Majesty's Treasury	RDEL: Resource Departmental Expenditure Limited
ICF International Climate Finance	SEAPD: South East Asia & Pacific Directorate
IEA: International Energy Agency	SIDD: Strategic Infrastructure & Development Dialogue
IRENA: International Renewable Energy Agency	SIDS: Small Island Developing States
KPI: Key Performance Indicator	SRO: Senior Responsible Owner
kWh: kilowatt hour	TA: Technical Assistance
KTF: Kokodo Track Foundation	TEA: Transforming Energy Access
MEL: Monitoring Evaluation & Learning	TIDES: Transforming Island Development through Electrification and Sustainability
MELCB: monitoring, evaluation, learning and capacity building	UNDP: United Nations Development Programme
MoU: Memorandum of Understanding	USD: United States Dollars
MWH: megawatt hour	VFM: Value For Money

## Strategic Case

Strategic and Political Context
The Pacific region faces long-standing development challenges, compounded by the economic impacts of Covid-19 which are reversing development gains. The Pacific Island Forum’s (PIF) new 2050 Strategy for the Blue Pacific Continent, set out priorities and a long-term approach to tackle the many challenges, including climate change. The Pacific region is important for the UK as outlined in the 2023 Integrated Review refresh, and in the development of a cross-HMG UK Pacific Strategy 2023-30. This region is critical to our security, and we are ambition to work with likeminded partners to promote democracy, human rights and freedom. The risk of instability and regional vulnerability exacerbated by the Russian-Ukraine conflict’s impact on energy prices, the ever-increasing intensity of the climate crisis, and the consequences of Covid-19 heightens the case for action.
[note] Published on 11 July 2022

Across the pacific donors are stepping up engagement. Australia has long been the single largest bilateral donor to the region, with A$1.06bn budgeted for 2021-22. The US have more recently announced a new package of support for the region including re-opening the US Embassy in the Solomon Islands and rolling out additional electricity and energy investment in the Pacific. The World Bank opened a new North Pacific regional hub (Federated States of Micronesia, Marshall Islands, and Palau) and increased its commitment from US$76.9m in 2016 to US$ 486.2m in 2023. The ADB committed US$852.7m in financing for the Pacific region in 2021. China provided a nearly US$3.15bn to the Pacific between 2008 and 2020, however this fell to US$188m in 2020 after it peaked at US$334m in 2016. The UK is a founding member of the Partners in the Blue Pacific Initiative which launched in June 2022, along with the US, Australia, New Zealand and Japan. Ambitious and effective partnerships are critical to how we approach the Pacific region. We are working closely with the US and Australia on security and resilience issues, to support peace and stability throughout the Pacific region.
[note] World Bank (2023), New World Bank Regional Hub Signals Growing Commitment to the North Pacific.
[note] Approximately 37% of this went to Covid-19 response while 30% was for immediate budget support. ADB, Work in the Pacific.
[note] Lowy Institute: Pacific Aid Map

Development context
The 22 Pacific Island states and territories are diverse in terms of geography, population, cultural heritage, political status, and level of economic development. The population of the Pacific Islands exceeds 14 million, of which the Melanesian states of Papua New Guinea (PNG), Fiji, and the Solomon Islands constitute the majority. The remainder of the region consists of small states and territories, some with tiny populations such as Tuvalu, Niue and Tokelau. Size of population is an important influence on politics, political stability, and government effectiveness. Geography is also important, with some PICs having predominantly rural populations, with many communities only accessible along bush tracks or by boat. This dispersal represents a barrier to central government authority, the delivery of services (including electricity connections), and economic development. Other determining factors of state functionality, and in turn economic development, include cultural heritage, history, access to natural resources and the structure and patterning of local institutions. Imports are expensive given their remote location, and the cost of diesel particularly so. leading to pressure on PIC budgets and some of the highest energy tariffs in the world.

Living standards are generally low and notably so in PNG and Solomon Islands, where 40% and 27% of the population are below the international poverty line of $2.15/day (see Table 1). In the United Nations Development Programme’s (UNDP) Human Development Index (HDI) for 2021/22, Vanuatu ranked 140, PNG 156, Fiji 99 and Solomon Islands 155. All four countries have lost ranking positions since the 2018 HDI report, with the Covid-19 crisis a contributary factor. Arguably only two of the nine independent Pacific countries, Samoa and Tuvalu, could be considered ‘stable’ democracies. PNG, Vanuatu, Tonga and Nauru have a consistent record of changing governments constitutionally, but to differing degrees have encountered corruption, weak central authority, lack of accountability and social unrest. PNG and Fiji have politically-influential military forces - the latter’s have been involved in four coups since independence in 1970, the most recent in 2006. Solomon Islands had a civil war that required regional intervention and currently has regional peacekeepers deployed.

See Annex A for a map of the PICs and more detail on their development and political economy context.

Table 1: Headline Poverty Statistics across Pacific Islands
	Population, 2021	Land Area, 2020	People living below $2.15 a day, 2017 PPP *	People living below $3.65 a day, 2017 PPP *	People living below $6.85 a day, 2017 PPP *	GDP per capita, 2021	Human Development Index, 2021
Units		km2	% of population	% of population	% of population	2017 PPP Current $	Value / (Rank, out of 191 )
Fiji	924610	18270	1.3	12.4	52.6	11381	0.73 / (99)
Kiribati	128874	810	1.7	19.4	68.8	2128	0.62 / (136)
Marshall Islands	42050	180	0.9	6.1	31.4	6550	0.64 / (131)
Micronesia, Fed. Sts.	113131	700	16	40.7	74.8	3642	N/A
Nauru	12511	20	1.4	14.1	51.5	13125	N/A
Vanuatu	319137	12190	10	35	76.2	3057	0.61 / (140)
Palau	18024	460				15145	0.77 / (80)
Samoa	218764	2780	1.2	10.5	43.3	6080	0.71 / (111)
Solomon Islands	707851	27990	26.6	61	88.5	2649	0.56 / (155)
Tonga	106017	720	1.1	8.8	35.3	6749	0.75 / (91)
Tuvalu	11204	30	3.6	19.6	56.6	5410	0.64 / (130)
Papua New Guinea	9949437	452860	39.7	67.7	90.2	4040	0.56 / (156)

Source: WB, World Bank Development Indicators and UNDP, Human Development Index.
* Poverty data is not available in the same year for all countries. The reporting year for each country is: Fiji, Kiribati, Marshall Islands & Vanuatu (2019), Tonga (2015), Samoa & Micronesia (2013), Solomon Islands & Nauru (2012), Tonga (2010), and Papua New Guinea (2009).
**The HDI has four broad human development groups, 'Low human development’ (Rank 160 - 191), ‘medium human development’ (Rank 116 – 159), ‘high human development’ (Rank 67 – 115), and ‘very high human development’ (Rank 1- 66).

Climate change and emissions
PICs are amongst the most climate vulnerable countries in the world, and climate change will make some of them increasingly uninhabitable. Due to the low-lying nature of some PICs, as sea levels rise salt water will permeate into the aquifers that provide drinking water. A rising ocean brings higher tides and flooding which leaves soil saline, reducing crop yields and weakening trees. Climate change related extreme weather events will become more frequent and severe, damaging homes and infrastructure. Coral reefs, which supports our tourism and nurtures the fish-stock, are perishing as the ocean warms and acidifies. Logging and mining increase silt, soil and nutrient run-off from the land onto the reefs, killing inshore fisheries.
[note] IPCC_AR6_WGII_Chapter15.pdf

PICs have not caused climate change but face the consequences and must adapt. The Pacific Island region contributes less than 0.03 percent of the world’s total greenhouse gas emissions, and an even lower proportion if historical emissions are considered.
[note] Low Carbon Development shared the Pacific island way | Pacific Environment (sprep.org)

Renewable Energy Needs
Renewable energy needs in PICs have been estimated at almost $1 billion. Successful transition to widespread use of renewable energy in PICs has the potential to significantly improve welfare for households and businesses, including in terms of their access to light and power, and health. It could also greatly improve the trade balance, allowing scarce foreign exchange to be used for better purposes than importing fuel. It could also substantially reduce the vulnerability to shocks in the price of fossil fuels in the world markets, improving economic security.
[note] IMF (2021), Unlocking Access to Climate Finance for Pacific Island Countries.

Political leaders in PICs generally recognise the need for increased renewable energy investment and are supportive of this. For example, the Chair of the Association of Small Island States, PM Fiame of Samoa, highlighted clean and renewable energy as one of the areas where she would continue to focus the group’s efforts. The Asian Development Bank has identified the Pacific Islands as having the highest infrastructure needs across the Asia-Pacific, requiring investments of 9.1% of GDP from 2016 to 2030.
[note] ADB (2017), Meeting Asia’s Infrastructure Needs

There are innumerable reports and studies which look at the energy challenges of the PICs. One key distinction is particularly important – between PNG, Fiji and Samoa, and the remaining PICs. PNG is a huge country with an extremely challenging topography and relatively few good roads or communications of any kind outside of the major towns. PNG also has abundant fossil fuel resources, which is a primary export for the country. While smaller, Fiji and, to a degree, Samoa share PNG’s complex and challenging topography. The consequence of high mountains and valleys is an abundant potential for hydroelectric power, which is reflected in the relatively high share of electricity from renewable sources for these countries. Most of the remaining PICs have a relatively low share of renewables in the electricity mix reflecting the lack of significant hydro resources and are heavily reliant on imported diesel (see Table 2).
[note] See Price (2022b, 2022a) for helpful reviews of the literature.

Rates of electrification in PNG are below global averages and only between 10% and 15% of individuals are connected to the national grid or diesel operated mini grids. A similar figure is found in the Solomon Islands where only 16% of households are connected to the electrical grid. A higher figure – around 60% and 73% of the population– have access to electricity once off-grid solar products are considered in PNG and Solomon Islands, respectively. This is the lowest access rate amongst PICs (see Table 2) and significantly below the global average electrification rate of 89%. Consequently, there is a substantial need for investment to improve electricity access.
[note] Rawali-M-Electricity-Access-Challenges-and-Solar-Energy-Opportunities-in-PNG.pdf (apvi.org.au)
[note] World Bank, The Electrifying Power of Results-Based Financing in Solomon Island.
[note] PNG+Off-Grid+Report.pdf (ifc.org)

In 2019 the IFC reported a dynamic market, with substantial opportunities for private companies willing to operate in a challenging environment. The solar lighting market in PNG was estimated to be $259 million a year based on an average household spend of $16 per month on lighting at that time and expected to grow over the coming years.
[note] Going the Distance: Off-Grid Lighting Market Dynamics in Papua New Guinea, IFC 2019.

The demographics of PNG make off-grid solar systems an appropriate and cost-effective means to increase access to electricity. It is more cost effective for remote rural populations to generate electricity locally than to connect with the national grid.

Import dependence
With the exception of PNG, most PICs are heavily import dependent, with imports typically between 40-100% of GDP (Prasad, 2021). With the exception of PNG and Fiji, most PICs do not have significant fossil resources. Fuel is arguably their most important import, costing between 10-20% of GDP and constitute a substantial proportion of overall imports (see Table 2). This makes PICs extremely vulnerable to fluctuations in world prices since this translates directly into higher prices, not just for fuel, but for most goods. Fuel needs to be paid for in foreign currency.

Aside from PNG and Fiji, many PICs are small (both in population and area) and relatively remote. It is important to point out the order of magnitude differences between different countries. The Solomon Islands has a population of 707,851; Tuvalu and Nauru both have populations below 15,000 (see Table 1). Thirty-fold differences in population size matter both for demand and what it is feasible to supply, as do one-thousand-fold differences in land area (Solomon Islands has a land area of 28,000km2; Tuvalu’s is 30km2). With small, and often relatively poor and sparsely distributed populations, the overall size of the market for energy is limited in most locations. This means that there are few, if any, economies of scale in generation, often leading to high costs of generation, transmission and distribution of electricity. Even before price rises due to the Russia-Ukraine war, PICs faced some of the highest energy prices in the world, with 4 of the 5 most expensive places in the world for a kWh of electricity being Pacific Islands.
[note] These were Solomon Islands, Vanuatu, Cook Islands, and Micronesia according to Cable.co.uk, which maps the price of electricity per KWh in 230 countries. General high costs are also widely evidenced, see IFC (2021), Powering the Pacific: A Guide to investing in Renewable Electricity Generation in the Pacific and WB (2014), Hardship and Vulnerability in the Pacific Island Countries.

Other than countries with extractive resources, the mainstay of the economy for PICs is agriculture, with foreign exchange coming from exports of coconuts/copra, sugar, coffee, cocoa, pineapples and other tropical fruits. Tourism also plays an important role in some countries (e.g. Fiji and Vanuatu). Remittances for migrant workers is another importance source of foreign exchange (see paragraph 197). Several PICs are heavily reliant on overseas aid.

Barriers to renewable energy
Since a large part of their import bill is for energy imports (primarily fuel), many PICs are interested in exploiting the potential of their renewable energy resources to reduce the cost of energy and to reduce their dependence on imported fuel. Most PICs have substantial potential for solar and, in selected locations, wind and tidal power. Some PICs have potential for geothermal, the larger PICs also have potential for bioenergy production and a few larger PICs have significant potential for hydroelectricity. Renewables represent an important opportunity to lower the cost of energy and reduce the high bill for the importation of fossil fuels. However, there are major constraints to delivering renewable energy projects, particularly in smaller and poorer PICs. The main constraints include:
[note] International Renewable Energy Agency, 2021
[note] AWS Truepower, 2009
[note] See Table 2 in IFC (2021) for a detailed exposition of the renewable resources available in various PICs.

Geographically dispersed nature of market
In general, PICs suffer from the small size and dispersed nature of the market. Almost all elements of renewable energy systems must be imported. This means that they are costly due to the high cost of transport to PICs. In places with large clusters of population, larger and more efficient types of generation can be used and the average costs are lower, so such systems can become commercially viable. However, for small communities, the number of consumers for any system is likely to be limited and the average cost is high. The more remote and dispersed households are, the higher average costs will typically be due to smaller and less efficient types of generation and higher transmission costs. Countries with higher levels of income will have greater demand and as a result lower average costs. The uptake of systems from the private sector will be much higher in urban areas where energy costs are lower and economic opportunities greater. However, particularly for poorer PICs, it is likely that the bulk of the population will not be able to afford the full commercial costs of energy from renewable energy systems such as household solar and mini-grids. This is the reason why the many renewable energy systems – particularly those serving poorer communities - have been paid for, in large part or entirely, by donors. Given the commercial risks, most mini-grid developers prefer to provide systems for communities or public facilities which are paid for directly by donors. This guarantees payment and avoids the risks associated with commercial transactions with poor consumers.

On the other hand, once the initial hurdle of supply costs is addressed, the cost of operational and maintenance of renewable systems will be lower than diesel generations given costly imported diesel and maintenance of their moving parts,

Debt
Many PICs are highly indebted. The Russia-Ukraine crisis and the Covid-19 pandemic severely affected fuel import prices, international trade and tourism, contributing to debt levels in several PICs rising sharply – Fiji, Vanuatu and Palau all have debt-to-GDP ratios greater than 70%. Seven low-income PICs – Kiribati, Marshall Islands, Micronesia, PNG, Samoa, Tonga and Tuvalu – are at high risk of debt distress and have limited headroom to take on commercial loans for energy infrastructure.

According to analysis from the Lowy Institute, most of the debt held by Pacific nations is with multilateral financing organisations rather than with bilateral countries. Since 2016, China’s aid and lending to the region has been in sharp decline. Tonga, Samoa, and Vanuatu remain among the world's most indebted countries to China to date, however, China has recently restructured the loans to maintain affordability.
[note] An explanation for the decline of China’s aid in the Pacific | Lowy Institute

High initial capital cost
Whilst renewables tend to have low marginal costs of supply since as they do not require fuel, they do have significant up-front capital costs. The cost of household solar can be prohibitive for many households in some PICs. While the percentage of households below the absolute poverty threshold of $2.15/day is low for most PICs, the percentage of households below $6.85/day – a threshold much closer to the standard of living needed to be able to afford household solar– is high in some PICs (see Table 1). Consequently, although renewables and solar in particular are growing in PICs, the demand comes primarily from the better off part of the population. Low income communities may need an anchor investor, such as a hotel or other business to reach affordability thresholds.
[note] There are exceptions such as biomass.

Finance
PICs have several constraints that inhibit private investment. These include small markets, weak regulatory environments, including non-competitive State-Owned Enterprises in the energy sector, limited financing options, high debt levels in some PICs, and information failures. Therefore, PICs by themselves have limited ability to attract sustained private investment and a patient and long-term approach to address renewable energy needs is required. Experience from several countries suggests that the size of the capital subsidy, either from donors or from taxpayers, must be significant for renewable energy projects to be viable commercially and to attract private capital. However, the greater the proportion of public funding in any project, the lower the proportion of additional funds leverage and, importantly, the lower the return to public funding. Progress towards renewable energy targets thus far would have been slower had it not been for the substantial quantities of development partner support and foreign capital invested in the sector in recent years. While capital is necessary, evidence suggests that it is far from sufficient for success and technical support is also required. Furthermore, according to Convergence, global climate blended finance has reached a ten-year low and decreased by 55% in 2022, of that flows from the private sector are also declining.
[note] Price, Roz (2022), Private Sector Investment in the clean energy sector in the Pacific Islands.
[note] Convergence (2023), State of Blended Finance 2023.

Lack of bankable projects
A lack of renewable energy projects are developed and taken to a bankable stage by project developers in PICs, despite abundant natural resource. Reasons for this include the weak capacity of project developers, limited financing options to cover development costs, and risk aversion by project developers linked to the lack of dependable finance for projects. Establishment of a clean energy investment platform will there also need to work closely with developers to start building up a pipeline of investable projects.
[note] A project is bankable when its risk-return profile meets investors' criteria and is sufficiently developed to secure financing to implement the project.

Table 2: Headline Energy Statistics across Pacific Islands
	Access to clean fuels and technologies for cooking, 2020*	Access to electricity, 2020	CO2 emissions per capita, 2019	Fuel Imports **	Renewable energy consumption, 2019
Units	% Of population / (Rural/Urban)	% Of population / (Rural/Urban)	Metric Tons	% Of merchandise imports)	% of total final energy consumption
Fiji	51 / (28/70)	100	2	16	26.5
Guam	N/A	100	N/A	N/A	3.0
Kiribati	10 / (0/17)	92 / (96/88)	1	14	41.0
Marshall Islands	64 / (1/85)	99 / (100/96)	4	N/A	11.7
Micronesia, Fed. Sts.	13 / (3/34)	83 / (79/97)	2	30	1.8
Nauru	100	100	5	N/A	0.6
Vanuatu	8 / (2/21)	67 / (58/96)	1	N/A	31.9
Palau	100	100	14	24	0.3
Samoa	37 / (29/65)	100	1	16	34.2
Solomon Islands	9 / (1/37)	73 / (72/77)	1	17	48.4
Tonga	84 / (81/94)	100	2	21	1.8
Tuvalu	71 / (36/93)	100	1	17	8.2
Papua New Guinea	9 / (4/37)	60 / (57/84)	1	17	53.1

Source: WB, World Development Indicators.
*Access to clean fuels and technologies are defined in accordance with WHO guidelines for indoor air quality: household fuel combustion. This includes households primarily relying on electricity, biogas, natural gas, liquefied petroleum gas (LPG), solar or alcohol fuels for cooking.
** Fuel import data is not available in the same year for all countries, the reporting year for each country is: Fiji & Samoa (2021), French Polynesia & Kiribati (2020), Palau & Solomon Islands (2018), New Caledonia (2015), Tonga (2014), & Micronesia, Fed. Sts (2013), Papua New Guinea (2012), and Tuvalu (2008).

Donor landscape
The Pacific, in per capita terms, is the most aided region in the world. One reason for this is that is relatively costly to deliver aid in the Pacific, due to the isolated marine environment and the limited potential for scaling interventions (particularly infrastructure) because of population size and geography. Another is that donors tend to operate in as many countries as possible for strategic reasons, hence smaller economies tend to receive more aid per capita. Several studies have found that aid projects in the Pacific are, on average, less effective than in the rest of the developing world.
[note] Dornan and Pryke (2017), Foreign Aid to the Pacific: Trends and Development in the Twenty-First Century.
[note] Feeny and Vuong (2017), Explaining Aid Project and Program Success: Findings from Asian Development Bank Interventions. Wood, Otor, and Dornan (2020), Australian aid projects: What works, where projects work and how Australia compares.

In 2021, the Pacific Island small states received $639 per person (excluding PNG which received $119), which compares to $53 per person for Sub-Saharan Africa. Across the pacific, PNG was the least aided country per capita, though is still highly aided in a global context.
[note] World Bank, World Development Indicators.

There are existing multilateral and bilateral donor programmes in the Pacific, some of which are explicitly designed to support the development of clean energy. Quality is an issue with some of them. Estimated climate finance needs, however, far exceed support available. The IMF estimates that PICs face a sizeable climate financing “gap”, estimated to be almost $1 billion or annual spending needs of between 6.5% to 9% of GDP. Across the region the Green Climate Fund (GCF) has become the dominant climate fund in the Pacific.
[note] IMF (2021), Unlocking Access to Climate Finance for Pacific Island Countries. The IMF finds that PICs need about 9 percent of GDP annually on average for climate adaptation investments under a “risk-intolerant” strategy aimed at building coastal protection infrastructure that limits average economic losses below 0.01 percent of GDP. Tiedemann and others (2021) find that the small Pacific islands need on average about 6.5 percent of GDP of additional annual infrastructure investment, based on an input–outcome costing methodology for reaching UN Sustainable Development Goals by 2030. Their estimates are based on and consistent with Hallegatte, Rentschler, and Rosenberg (2019), Nicholls and others (2019), and Rozenberg and Fay (2019).

The main types of funding are direct investment in renewable power infrastructure, increasing private investment, capacity building for policymaking and institutional and regulatory frameworks, information collection and dissemination, project development support and seed funding early-stage projects. Most donor funding in 2020 was provided to PNG, Solomon Islands and Fiji, although aid per capita is unevenly spread across the region. The two main multilateral organisations with active programmes are the Asian Development Bank (ADB) and the World Bank. The largest bilateral donors are Australia, New Zealand in the South Pacific and the US and Japan in the North Pacific. To date, MDB funding has focused on debt for larger infrastructure, and bilateral aid on grant for small projects. Very few programmes attempt to promote the involvement of the private sector. Details of the main investment, capacity building and information sharing programmes can be found in Annex B.
[note] Support for the Solomon Islands was focused on one project, Tina Hydro.
[note] Lowy Institute: Pacific Aid Map

Australia announced an expansion in their Australian Infrastructure Financing Facility for the Pacific (AIFFP) to AUS$4bn in 2022, and the Pacific Climate Infrastructure Financing Partnership as a new stream within AIFFP to increase support for medium and large-scale, climate-related infrastructure projects. However, much of this remains unspent as AIFFP have struggled lending at this scale to date.

Although there is a high level of donor support, there are still gaps which the UK is well placed to contribute towards, in line with PIC priorities. Given the regions vulnerability to climate change and high ambition on energy transition, a greater flow of funding to the Pacific region is needed. As co-chairs of the GCF in 2024, the UK will be well positioned to seek synergies between RCEIF and the GCF in terms of catalysing private investment in the region.

UK Strategic Objectives

PCEP is aligned with the strategic objectives and steers in several FCDO initiatives and planning documents, which are set out below. and also contributes to HMG’s imperative of reducing global dependence on Russian fossil fuels and reach SDG7 on universal access to electricity and proportion of renewables.

International Development Strategy and White Paper
The UK’s International Development Strategy 2022 sets out our approach to being a patient development partner. It prioritises tackling climate change as a top international priority and the importance of delivering honest and reliable infrastructure, through a new British Investment Partnership (BIP) approach that represents the UK’s commitment to build stronger, more transparent economic partnerships based on high quality, sustainable investment.

Set out in the strategy is a vision that by 2030 Small Island Developing States (SIDS), will have the economic and climate resilience not only to graduate from ODA with sustainable economies, but also to withstand economic and climate shocks. This programme helps deliver on that ambition.

These objectives are further underscored in the White Paper on Development that reaffirms our commitment to the SDGs, to working closely with partners and the private sector to meet our development and climate objectives.

Integrated Review
The UK’s Integrated Review Refresh 2023 identified the Indo-Pacific as geographic priority region and set out that the UK will deepen our engagement with PICs and support regional resilience in the Pacific. Climate change and sustainable development are identified as thematic priorities.

Pacific Strategy
Against this backdrop, HMG has developed a new strategy for the Pacific. It will see the UK step up our engagement as a long-term, honest, and reliable partner, working with PICs, to ensure that by 2030 they are more resilient. The strategy focuses on three main areas where we are can make a catalytic contribution: i) climate resilience; ii) leveraging the new £15 million 2021-24 Pacific CSSF programme; and iii) strengthening the UK’s soft power offer.

UK Development Partnerships in the Indo-Pacific
The UK and Australia agreed to closer cooperation to offer clean, reliable and transparent finance for investment in infrastructure during the Australia-UK Ministerial Meeting (AUKMIN) in January 2022. Following the agreement at AUKMIN, an officials-level UK-Australia Strategic Infrastructure and Development Dialogue (SIDD) in March 2022 identified energy transition as a mutual priority alongside other initiatives for cooperation across the Indo-Pacific. Following the SIDD, UK and Australian officials jointly developed a pipeline of potential projects for cooperation and co-investment including this initiative for clean energy in the Pacific. The report was then submitted to UK and Australian Ministers in May 2022. The Australia Foreign Minister, Penny Wong, has endorsed UK-Australia investment cooperation in the Indo-Pacific and has welcomed the UK’s support for clean energy in the Pacific, including renewables in PNG. Along with G7 partners, Australia has been prioritised as a key partner under our British Investment Partnerships (BIP) approach where we seek to strengthen our impact through collaboration with like-minded allies.

Proposed Intervention: Pacific Clean Energy Programme
The evidence highlights that access to affordable energy is a major challenge to the PICs. PICs are highly vulnerable to climate change and face among the most expensive electricity costs in the world. Most of the PICs, with exception of PNG, are energy importers with costly diesel representing as much as 10 to 20% of GDP in some parts of the Pacific. This drains foreign exchange reserves and increases economic vulnerability. The lowest access to grid connected electricity in the region is in PNG (10-15% of the population) and Solomon Islands (14-20%). Clean energy transition and expansion offers PICs new solutions to address rising energy costs and access without harming the planet. Renewable energy consumption across the PICs is below 40% of total final energy consumption (Table 2, except for PNG, Solomon Islands and Kiribati), so a significant gap remains for an at-scale clean energy transition. Increased renewable energy consumption is considered to have a positive effect on economic growth, catalysing wider social benefits.
[note] IFC (2021), Powering the Pacific: A Guide to investing in Renewable Electricity Generation in the Pacific and WB (2014), Hardship and Vulnerability in the Pacific Island Countries.

This programme of up to £20 million over just under 7 years will reduce carbon emissions and improve access to affordable clean energy in ODA-eligible Pacific Island Countries and will contribute to delivery of the climate resilience pillar in the new Pacific strategy. The programme will have two components: RCEIF and PCEI.

RCEIF
FCDO received two separate proposals from Camco and Pollination which seek cornerstone equity investment to establish new blended finance funds focused on in PICs. Both proposals have two components which seek to address key constraints to renewable energy sector development of a lack of bankable projects and a lack of finance: (i) a facility to support local project developer develop a pipeline of bankable clean energy projects; and (ii) a fund to raise finance from public and private sources and invest in renewable energy generation and transmission infrastructure. As well as being financially sustainable, the RCEIFs would reduce carbon emissions, by providing an alternative to diesel generation, and improve access to electricity.

PCEI
Pawarim Komuniti (PK) is an existing Australian funded programme, delivered under the PNG-Australia Partnership, to support access to clean energy in rural and remote communities throughout PNG and help PNG reach its target of 70% electrification by 2030. It works through civil society organisations (CSOs) to reach remote and marginalised communities not served by government systems. Australia’s Department of Foreign Affairs and Trade (DFAT) has approved up to AUD 20 million (approximately £11m) of grant funding under PK, with an option to increase this commitment. There is an opportunity for FCDO to provide funding to DFAT in order to scale up its provision of off-grid solar in communities it is already working in, and to increase its reach by providing off-grid renewable energy to additional communities. PK aims to:
1. Provide rural households, community services facilities and businesses with reliable and affordable access to clean energy services;
2. Support government, development partners, civil society and the private sector with information on successful off-grid electrification models; and
3. Support women and girls by enabling accessible and inclusive clean energy projects that contribute to improved educational and safety outcomes.

It does this by providing grants (between PGK 500,000 to PGK 5 million per project, approximately £120K – £1.2m) to CSOs which have access to and relationships with remote communities.

PK is one of several programme areas that come under Australia’s PNG Economic and Social Infrastructure Program (ESIP). PK also works closely with the National Energy Authority (NEA) through the Small Power Systems Regulatory Framework in relation to registration and licensing requirements, noting at this stage the government is yet to finalise the regulation framework. In the absence of this regulation, off-grid electrification projects, such as mini-grids, of a size greater than individual household solar and cannot commence. Therefore, to date, PK has only delivered household solar, street and WaSH facility lighting, community solar and solar vaccine fridges. FCDO funding will be used to fund off-grid renewable energy projects through PK, this will predominately be household and community solar but may also include mini-grids in later years should regulations allow.
[note] Off-grid electrification refers to stand-alone power systems that provide households, businesses, public, or community services with clean energy. Current regulations prevent mini-grid systems and as a result PK off-grid refers to systems that generate less than 1MW of power and are outside the PNG Power Limited (PNG’s national power authority) exclusivity zone or areas which are demarcated for future grid extension.

In addition to this, FCDO funds will be used to pilot innovative new approaches, improve e-waste management and incorporate lessons learnt from other FCDO contexts, such as Africa. By doing these things, FCDO funding could help improve the effectiveness and sustainability of the whole programme.

Compliance with Assurances/ Legislation
FCDO compliance, project assurance and financial oversight rules (the Programme Operating Framework) will be followed in the design and delivery of this programme.

Climate and Environment. PCEP is aligned with the Paris Agreement by helping PICs to take a low-carbon development pathway. It will generate carbon savings by, for example: supporting expansion of renewable energy generation rather than fossil fuel generation to meet the energy needs of PICs; reduced import and use of diesel fuel; and use of less polluting construction practices. The programme will not invest in fossil fuels and will instead contribute to a transition towards renewable energies. There is a risk of e-waste (for example expired batteries) being generated as a result of this and the partner DFAT programme, however the programme will develop environmentally sound approaches to managing this, including recycling where feasible. All implementing partners will monitor environmental risks and take serious efforts to prevent environmental harm being caused as a result of improving access to energy.

International Climate Finance (ICF). PCEP will be scored 100% as UK ICF and reported against ICF key performance indicators (KPI): 2.1 – number of people with improved access to clean energy; 2.2 – number of social institutions with improved access to clean energy; 6 – greenhouse gas emissions reduced or avoided; 7 – installed capacity of clean energy; 11 – volume of public climate finance mobilised; and 12 – volume of private climate finance mobilised.

Gender Equality. Improved, modern energy supply can disproportionately improve women’s socio-economic status by reducing the time and effort involved in household chores and alleviating the health risks associated with current energy practices. To comply with the Equality Act 2010 responsibilities set out in the Public Sector Equality Duty, PCEP and its implementing partners will: uphold standards and principles relating to non-discrimination and no harassment or victimisation, as well as international human rights provisions; consider the benefits for females and marginalised groups when prioritising, designing and delivering projects; include key performance indicator relating to gender (e.g. proportion of jobs created going to women); and collect data and disaggregate its results by gender, income group, and other relevant characteristics where possible.
[note] Gender and Energy, UNDP, 2013

Disability. The inclusivity of projects towards people with disabilities will be considered as part of project prioritisation, design and delivery. Data will be collected and results disaggregated by disability where possible.

Conflict and fragility. PCEP will be working in countries that are fragile and where there is a risk of conflict. An outbreak of conflict could hinder the delivery of the programme, though this is partially mitigated by the programme geography spread. Competition over control of energy resources could add to conflict risk, though projects are unlikely to have a substantial effect because they are geographically disbursed and not large scale. Conflict risk will be considered by implementing partners before individual projects are approved.

Counter Terrorism Financing. We judge the risk of funds being diverted to terrorist groups as low. The programme will mostly use established international organisation or bilateral government channels to provide support. All implementing partners will be required to pass due diligence or fiduciary risk assessments, demonstrate the robustness of their due diligence and monitoring processes for downstream partners, and have a strong track record of delivery.

Safeguarding. In line with FCDO’s policy, partners will be required to have appropriate safeguarding policies and procedures in place. We will work with implementing partners to ensure upstream project design builds in the highest safeguarding standards. FCDO will provide information on how to raise safeguarding concerns related to the programme. A risk register that will identify any safeguarding risks will be created and we will work with partners to put in mitigating actions to manage and minimise any risks that may arise. The FCDO has diplomatic posts across six of the Pacific Island Countries and the management arrangements will include monitoring in the region.

The Partnership Principles. The chosen delivery mechanism for PCEP is mostly the private sector and CSOs, and has a low degree of proximity to PIC governments. Only a small proportion of the budget (expected to be 0-2%) will be direct support to PIC governments and will be in the form of capacity building assistance. As such it is not deemed necessary, for the purpose of this programme, to assess and monitor the commitment to the Partnership Principles of governments in countries where PCEP will operate.
[note] Partnership for Poverty Reduction, Re-Thinking Conditionality, 2005 White paper on International Development. The four partnership principles set out in the white paper are: i) A commitment to reducing poverty and achieving the Millennium Development Goals (now the Sustainable Development Goals); ii) A commitment to respecting human rights and other international obligations; iii) A commitment to strengthening financial management and accountability,and reducing the risk of funds being misused through weak administration or corruption; and iv) A commitment to strengthening domestic accountability.

Risks
There is a substantial opportunity to increase renewable energy generation and to reduce diesel generation in PICs. PCEP could help this.

A lack of bankable projects at an appropriate speed is the greatest risk to programme objectives being achieved. To mitigate this, the RCEIF component will support project developers to develop a pipeline of projects and the PCEI component will both support existing projects that are able to scale up quickly and develop new ones. The RCEIF TA component and FCDO diplomatic network will be used to engage with PIC governments to address constraints to project development.

There is a risk of weak investor appetite for an investment fund, which could mean the fund being smaller (or not viable), require higher fee rates to cover its cost and take longer than anticipated to reach first close. FCDO will engage with other donors to encourage investment from them and could also consider providing its finance on more concessional terms to increase public and private investor interest, but we would need to be convinced that doing so represents VFM. FCDO will only invest in RCEIF if is deemed to have generated sufficient capital following first close.

There is a reputational risk of PCEP being perceived as benefitting financiers and the fund manager disproportionately. Careful structuring that lets FCDO share in profits (which can then be redeployed in future ODA projects) and links fund manager remuneration with social and development performance, and careful communication of this will be crucial.

Significant political economy challenges compound the economic constraints of renewable energy in the Pacific and pose a risk to the viability of PCEP. This is influenced by the respective context and affect rules on procurement, tariff setting, the demand for renewable energy vis-à-vis imported diesel, land rights etc. In particular there is the potential for anti-competitive responses from utilities from renewables coming online. FCDO will work with implementing partners to leverage local expertise and delivery as much as is possible and ensure an understanding of political contexts is mainstreamed throughout programming. PCEP will also undertake targeted political economy studies where relevant.

More details on these and other risks can be found in the Management Case.
Working with Partners
The PCEI component: PCEI will be implemented through DFAT PK programme in PNG, and FCDO will work closely with them at the strategic level to deliver it. DFAT have a substantial presence in PNG to manage security, logistics and delivery in the PNG environment, and the overall approach will be further strengthened by FCDOs experience on off-grid renewables and sustainability aspects.

The PCEIF component: The main bilateral donors which have expressed potential interest in setting up a clean energy investment fund are New Zealand (NZ) and the US’ Development Finance Corporation, while Australia have ruled out any interest. NZ have indicated a desire to take a first-loss position while the US has noted an interest in more senior debt tranches. FCDO and MFAT have agreed to work together to create synergies between PCEP and existing programmes in the region. FCDO are in discussions with several donors about the possibility of co-investing in the investment fund, together with private sector investors.

Alongside PCEI, RCEIF also presents an opportunity to work in partnership with members of the Partners in the Blue Pacific Initiative, launched in June 2022, on ‘Climate Change Resilience, Adaptation, and Disasters’.
[note] Partners in the Blue Pacific (PBP): joint statement, September 2022.

Impact and Outcomes
The impact of this programme is reduced GHG emissions, increased private investment in renewables and improved economic growth, health and poverty reduction from increased clean electricity use and deployment of savings from lower fossil fuel imports in the PICs.

This will be achieved through activities focussed on expanding public and private investment in clean energy generation and distribution.

The outcomes of the programme are:
- Access to electricity is increased, particularly of poor and marginalised communities.
- Share of renewables in the national energy mix is increased.

It will work in tandem with existing FCDO funded initiatives such as the Transforming Energy Access (TEA) Platform to draw on evidence, technology and business model innovations and lesson learning, and align with FCDO’s wider Energy Transition campaigns. It will also contribute to the Ayrton Fund clean innovation commitments by testing, demonstrating, and scaling approaches to renewable energy and smart delivery (e.g. through island mini-grids).
[note] The Ayrton Fund supports clean energy research, development and demonstration to accelerate the clean energy transition in developing countries.

It will contribute to HMG’s ambition to strengthen security and economic partnerships across the Pacific region, including with Australia. This programme is core to the British Investment Partnerships approach, as prioritised in the International Development Strategy, and will demonstrate UK commitment to demonstrating a democratic alternative to the influence of malign actors in the region, while supporting Pacific Island countries’ development needs and act as a pathfinder on private finance mobilisation in the region.

## Appraisal Case

The Appraisal Case is divided into four sections. The first considers a high-level assessment of the options for UK programming. The second appraises the options to deliver the three component parts of the programme. The third is the theory of change. The fourth analyses the costs, benefits, and Value for Money (VFM) of the proposed programme structure.

High Level Options
As part of the process of developing the Concept Note, the design team held an options workshop and evaluated a range of options to deliver the outcome of improving access to clean energy in the Pacific. These could be grouped into three broad categories:
- Do nothing.
- Technical assistance: including feasibility studies, innovation support grants and technology prizes.
- Mechanisms to support capacity building and knowledge sharing: this could either be a standalone UK programme or providing additional funding to an existing programme such as those identified in the strategic case. It would include direct support for building institutional capacity as well as data collection and dissemination of market information.
- Financial support mechanisms: many financial mechanisms were considered ranging from fully commercial instruments such as loans and equity investments, to grants and subsidies including credit lines to banks, guarantee facilities and other forms of concessional finance.

The main evaluation criteria used were:
- The extent to which an option addresses the need to increase the number of people with access to a clean electricity supply;
- Complementarity with other donor activities in the region; and
- The demand placed on FCDO implementation capacity.

The outcome of the evaluation resulted in the preference for a combination of initiatives grouped into two components: RCEIF and PCEI. This appraisal explores the options for both of these components.

Component 1: Regional Clean Energy Investment Fund

The evidence base suggests that there is a substantial need for renewable energy finance in the PICs, with gaps particularly at the smaller scale end of the market.

There is strong evidence of need for scaling clean energy investment in the Pacific region, with an estimated $5.9 billion of financing requirement over the period to 2030 to meet Nationally Determined Contribution (NDC) targets. Financing flows into renewable energy are currently not at the required scale to reach targets, with most investment coming from public funds. Evidence also suggests that financial markets for renewable energy are not scaling rapidly in the Pacific, so we cannot assume private finance can scale sufficiently to meet the funding gap, and public subsidy will be required. There is a lack of diversified clean energy funds that can attract investor finance. There is a lack of aggregation of small-medium sized projects, which is preventing investment in them at scale. Investment is often supported by a range of IFI instruments as well as by specialist public finance infrastructure funds that seek to develop blended finance approaches to clean energy development. These mostly target medium-large scale projects. On the supply side, there is a lack of capable developers able to bring new projects to the market and barriers to entry.
[note] IRENA (2020), IRENA and Pacific Community Announce Joint Efforts to Boost Recovery.

PCEP received clearance for its PCEI component in April 23’. At the time, the larger component of the programme, RCEIF, required more analysis and design work before options could be recommended. Sufficient analysis on the RCEIF proposals has now been done by FCDO staff, British International Investment (BII) and Pacific Regional Infrastructure Facility (PRIF) to recommend options. PRIF is a multi-donor coordination platform in the Pacific that aims to enhance coordination of partner investments in the Pacific and provide technical advice on infrastructure development and sustainable management. This analysis is weaved throughout the options appraisals below and which will appraise the following issues:
[note] The governments of Australia and New Zealand have commissioned PRIF to produce an independent assessment of TIDES and PEAF

  1. The choice of investment Fund.
  2. How should support for project developers be delivered?
  3. Which type of financing should FCDO consider?
  4. What type of CDEL should be used?

On the choice of investment fund, the following options were considered:

  1. Option 1: Do Nothing.
  2. Option 2: Recommended, Transforming Island Development through Electrification and Sustainability (TIDES). Invest up to £15.5m CDEL in TIDES, split between a facility to support the development of renewable energy projects and a facility to finance the construction renewable energy projects and hold them as investment assets. Up to £1m for monitoring, evaluation, learning and capacity building (MELCB) from independent suppliers.
  3. Option 3: Pacific Energy Access Fund (PEAF). Invest up to £15.5m CDEL in PEAF, split between a facility to support the development of renewable energy projects and a facility to finance the construction of renewable energy projects and hold them as investment assets. Up to £1m for MELCB from independent suppliers.
  4. Option 4: Both TIDES and PEAF. Split a total investment of up to £15.3m CDEL between TIDES and PEAF. Up to £1.2m for MELCB from independent suppliers.
  5. Option 5: Alternative approach, e.g. solicit bids from other fund managers.

Different fund management options have been considered, including UK supported funds, bilateral funds, multilateral funds, and regional private funds. The main UK supported fund options are BII and the Private Infrastructure Development Group (PIDG). Neither is currently focused on the Pacific Islands or likely to expand there in the short-to-medium term and tend to focus their direct investments in larger projects than those likely to emerge in the PICs. As such, they were disregarded as options.
[note] BII is the UK’s Development Finance Institution (DFI). It is 100% owned by FCDO, operating at arm’s length, and invests across a range of sectors including energy, infrastructure, manufacturing, and agriculture. Under BII’s new strategy it is expanding to the Indo-Pacific region with a focus on climate funds. The initial focus of the expansion in the Indo-Pacific is on Vietnam, Philippines, Indonesia, Cambodia, and Laos and it is unlikely to have the capacity to explore Pacific Island clean energy investment opportunities in the short to medium term.
[note] PIDG is a multilateral fund, to which the UK is the largest contributor, with a specific focus on supporting early stage or higher risk infrastructure projects, including renewable energy. PIDG does not have operations in the Pacific and is unlikely to expand there in the foreseeable future.
[note] However, we are exploring with BII the possibility of transferring FCDO’s investment in RCEIF to them in the medium-to-long term. See under Issue IV.

The main multilateral fund manager operating in the region is the Asian Development Bank (ADB), to which the UK is already a major contributor. Existing multilateral and bilateral funds tend to focus on larger infrastructure investments rather than smaller, more localised solutions which is the more cost-effective approach for providing access to electricity for many off-grid locations, particularly remote ones. As such, they were also disregarded as options. The remaining options, which will be assessed in more detail, are set out above.

Supporting a private fund for the Pacific region is judged to be more effective for targeting both the small and medium sized project end of the market, where there is a particular gap, and for improving electricity access. There are a small number of climate specific investment funds operating or interested in operating in the region using a combination of public and private funds. Two of these – Camco and Pollination – have made proposals to establish and manage new funds:
- Camco is proposing to launch TIDES, a blended finance fund with a target of US$100 million of public and private finance. Camco is a specialist climate and impact fund manager. FCDO has a current investment with Camco in its Renewable Energy Performance Platform – this operates in Sub-Saharan Africa and many design similarities to TIDES.
- Pollination is proposing to launch PEAF, a blended finance fund with a target of US$250 million of public and private finance. Pollination is a specialist climate change investment and advisory group. The origination of this proposal was supported by the NDC Partnership, including through a UK grant from BEIS.

A PRIF assessment concluded both proposals were VfM, but TIDES was deemed the stronger proposal and an initial assessment from FCDO and BII corroborate these findings. Broadly our assessment noted that CAMCO has significantly more industry experience than Pollination with a dedicated and established fund manager with experience of launching similar structures elsewhere. We see the primary risk facing both proposals to be exit risk given the nascent, illiquid market, however CAMCO recognises and proposes refinancing at the SPV/investee level as a liquidity pathway, though both are risky and largely untested in the PICs. We also recognise that TIDES’ support for the developer ecosystem better aligns with our objectives. On fees, both indicate typical fee structures for the investment vehicle, though pollination has high rates for DevCo which may lead to significant capital erosion. We would also expect all fund managers to invest their own capital in the structure, such as TIDES $2m, but need to understand how this will be funded. We note that fundraising timeline (6 months) and amounts may be optimistic, more needs to be done to understand the minimum viable size and realistic timeline for first close.

The PRIF assessment conducted significant market analysis to compare TIDES to several comparator funds to assess its value for money. Both proposals were deemed to mobilise further private finance through refinancing, increasing the cumulative pool of private capital mobilised. The PRIF concluded that TIDES is situated as a “Fund of Funds” targeting new segments of the market, traditionally unfamiliar segments of the market which would struggle to attract private finance without concessional support though would have a larger development impact. Correspondingly TIDES has a sizeable development facility to ensure there is an adequate pipeline and ensure the fund is feasible.

A summary of the TIDES and PEAF proposals and their key terms can be found in Annex C.

Options 2-4 all include monitoring, evaluation and learning (MEL) from an independent supplier. This important for: assessing programme performance, continuous learning and programme improvement, and to enabling a performance related element for the investment manager’s remuneration. The Management Case explains the MEL approach that the programme will take in more detail. Some capacity building and technical assistance interventions, for example for government and regulators, will be delivered independently of the investment manager because it may be in areas where the investment manager does not have competence, due to potential conflicts of interest and due FCDO’s commercial rules for proposals that have not been through a competitive tender.
[note] Another approach is to provide technical assistance to government and regulators through the facility associated with the fund manager that will also provide support to project developers, and to operate this facility on a not-for-profit basis. This option will be considered.

Due diligence will be undertaken by FCDO to ensure the fund manager incorporates appropriate environmental and social safeguards such as strengthening supply chain reporting. An appropriate Safeguarding Policy will be agreed with TIDES, relevant donor partners, and the FCDO central teams. FCDO will leverage lessons from an existing FCDO investment with Camco in its Renewable Energy Performance Platform. Camco have noted they will adapt existing safeguarding policies for TIDES. Such as their Environmental and Social Safeguards Policy (E&S Policy), aligned to the IFC Performance Standards (IFC PS), International Human Rights and International Labour Organisation (ILO) treaties and other international best practices; alongside their Investment Framework, which governs all funds under management and portfolio investments. Camco is also accredited member of the Green Climate Fund. On gender, Camco currently apply a 2x framework across all their investments and are apply have put in place a gender-based analysis plus (GBA+).
[note] Green Climate Fund: Camco.
[note] Camco, Approach to diversity and gender-smart climate finance and investmentv.

On the question of how support for project developers should be delivered?
1. Option 1: Do Nothing
2. Option 2: Recommended, Integrated with the investment fund. Provide up to £3-7m CDEL for a facility integrated with the investment fund and delivered by the investment fund manager. This amount is included within the £15.5m mentioned in issue I above. The facility would build the capacity of local project developers and support them develop a pipeline of bankable projects through a combination of repayable financing and technical assistance. The cost of the technical assistance and financings would be repayable if projects reach financial close. This option would complement an FCDO investment in TIDES or PEAF but would be viable even if FCDO did not invest in them so long as they reach financial close from other sources.
  [note] Further analysis of the RCEIF proposals is needed before selecting an amount.
  [note] The local project developers that receive support will be in the private sector.
3. Option 3: Independent project development facility. Provide up to £4-8m CDEL for a facility to directly develop bankable projects and/or indirectly support (e.g. through loans and capacity building) existing local project developers develop bankable projects. Fees would be generated by selling projects on to investors (which could include but not be limited to TIDES and PEAF), and these would be used to develop further projects. The £15.5m mentioned in issue I above would need to be reduced by £4-8m if this option were selected. This option would be strong if further analysis shows that a lack of bankable projects, but not a lack of finance, is a binding constraint to delivering renewable energy projects.

A lack of bankable projects from developers is a binding constraint to the delivery of renewable energy infrastructure. Developing a pipeline of good quality projects is critical to RCEIF having impact, and donor funding is needed to support this. As such Option 1 is rejected. Furthermore, FDCDO took initial advice from BII and concluded that it is unsurprising that neither proposal can demonstrate deep pipelines at this point, and we have attached little weight to the indicative pipeline at this stage. However, Camco have been active in raising a profile and building connections through TIDES, it has signed a broad memorandum of understanding with Canberra-based ITP Renewables who have a long track record in the Pacific working on similar projects.

The TIDES proposal includes a sizeable developer capability facility which is integrated into their deal sourcing strategy into one integrated platform. The market development facility (a proposed $30 million in total) would consist of TA grants, Development loans, and Results-Based finance (RBF) grants. This would be used to develop a pipeline of projects and the RBF component would provide subsidies for mini-grid development. The intent is to broaden technical and financial skills currently acting as a constraint to developing bankable projects.

Any funding is repayable at financial close and recycled as a revolving grant facility, but the TA can be expected to attract broad interest as there’s no requirement to commit to progress projects and it’s no-cost to users for projects that don’t proceed. Therefore, FCDO will closely monitor and work with the fund manager to ensure that delivery of the facility is within budget.

Pipeline

The pipeline of projects in the clean energy investment funds will include renewable independent power producers (IPP) generation selling to the utilities to expand the reach of existing utilities; and standalone mini-grid systems appropriate to small island communities where this is more cost effective than expanding the national grids. Initial estimates of viability gap funding requirements per household to meet affordability requirements in previously unserved areas are high - so mini-grids systems will be piloted at first, and we expect commercial projects will often need to be supported by an off-taker such as businesses or schools. Guiderails will be discussed and agreed on establishing the funds to ensure adequate consideration of development as well as commercial considerations.

TIDES has several design features to ensure they are adequately structured to manage the key constraints to operation in the Pacific. These include:

  1. Small and dispersed populations: TIDES will apply lessons learnt from REPP and will finance its multiple projects with DPs via a standardised SPV and contracts, to ensure cost-efficiency. Additionally, the rural nature of many Pacific communities necessitates distributed renewable energy. To ensure financial viability, FCDO will trial financing the affordability gap through TIDES’ RBF component for distributed renewable energy.

  1. Immature capital markets/limited funding appetite: TIDES will bundle projects, leverage ‘blending’, and leverage experience from similar projects to de-risk projects.

  1. Limited developer presence/interest and capacity: TIDES will leverage partner relationships, for example, TIDES has partnered with SPC and consulted widely with stakeholders across the Pacific. This has resulted in the Pacific Energy Ministers forum adopting a resolution to support the TIDES blended facility approach. Tides also includes a TA facility, and development loans, and expedited (6 month) project approval, to address specific barriers.

  1. Diverse and heterogeneous markets across the Pacific: TIDES has been designed with flexibility at its core. TIDES will fund technologies across the technology spectrum, that is: large scale utility scale projects; C&I projects; and off grid mini grids. Additionally, TIDES will be able to deploy both debt and equity instruments.

The Renewable Energy Performance Platform (REPP), was a UK-funded programme managed by Camco, set up in 2015 and similarly aimed to provide clean, reliable, and affordable electricity across Sub-Saharan Africa (SSA) and in line with SDG7. REPP, in a similar vein to TIDES, targets small-scale and distributed renewable energy who may traditionally several barriers to finance their products.

REPP provides an indication on the types of projects that TIDES may focus on, albeit adapted to the Pacific context. As of 31 March 2023, REPP had supported 42 projects spanning 20 countries across seven technologies namely solar home systems, solar PV mini-grids, solar PV-powered batteries, grid-connected solar PV, geothermal, run-of-river hydroelectric power and on-shore wind. Across investments, 29% was in mini-grid projects, a practical solution to more isolated communities not connected to the grid and the World Bank ranked REPP as the second most active investor in mini-grids in SSA.

REPP’s annual report provides several case studies from which TIDES could build in the Pacific, see pages 40-48. Several examples are in the box below.
[note] REPP Report and Financial Statements 2022-23.

REPP Project Case Studies

REPP has invested USD 6 million to support the development and construction of a 13.7MWp portfolio of solar-hybrid isolated grids in the Democratic Republic of the Congo (DRC). (NARU Case Study).

Bboxx is a UK-founded data-driven super platform that provides its customers with access to innovative products and services, from plug-and play solar home systems (SHS), solar-powered water pumps, clean cooking and e-mobility solutions to cash-loan funding. To date, REPP’s investment in PEG Africa and subsequent investment in Bboxx has led to 128,000 units installed and in active use, connecting more than 643,000 people to electricity for the first time, and mitigated more than 65,000 tCO2 emitted. (Bboxx Case Study).

Three large-scale heavy fuel oil (HFO) IPP plants in Madagascar are being hybridised with solar PV thanks to a USD 6m bridge loan from REPP to developer LIDERA Green Power. will purchase power from the PV projects and then on-sell to the national utility. The project is expected to deliver significant socio-economic benefits to Madagascar’s economy and population by reducing the country’s reliance on expensive HFO and providing job opportunities during the construction and operation of the plant. (Malile Case Study).
There has been an increasing number of privately financed renewable energy projects in the Pacific at this scale. Sunergise, with funding from private funder SunFunder, has scaled up rooftop solar projects totalling 2.4MW in Fiji and Vanuatu. Similarly, there have been several solar plus storage projects in the region, such as SMA Solar, in collaboration with Solar Pacific Energy Corporation (SPEC) large-scale solar-plus-storage project in Palau, to meet 1/4th of the its energy needs, and a 2MWh batter energy storage system (BESS) in Tonga commissioned by Tonga’s Power Limited (TPL).
[note] Sunfunder: From Beverage makers to international hotels: commercial solar takes off in the Pacific.
[note] SMA: SMA and Solar Pacific Energy Corporation build the largest solar plus storage project in the western pacific region in Palau.
[note] Energy Storage News: Solar-plus-storage system commissioned in Tonga with 2MWh capacity.

TIDES have a developer led approach to generating pipeline and have signed MoUs with nine developers in the region and look to increase this further. TIDES have shared a pipeline of projects which gives us an indication of absorption capacity and pipeline readiness. Currently TIDES’ proposed pipeline is estimated at over $85 million across several PICs and market segments.

Across market segments, TIDES current pipeline distribution is in C&I (78%), on grid connection (28%), and Mini grids (3%). TIDES will ensure full due diligence is carried out on all Development Partners (“DP”) once funding has been secured to minimise reputational risk as it requires significant DP input. Most of the pipeline is in Fiji (90%) with the remaining in Vanuatu (10%) and Soloman Islands (>1%). Camco believe this due to relatively easier regulatory environments and support for renewable energy projects. A desire focus on less challenging PICs is sensible to build pipeline and demonstrate viability, however, FCDO will work with Camco to balance equity consideration and ensure diversification quickly by setting limits on total funding amounts to each jurisdiction.

Pacific Planned Pipeline

To illustrate the type of activity, TIDES planned pipeline in the Pacific includes:

Superfly (DP) plans to develop a ‘build, operate, transfer’ of a 60kW solar-hybrid power system for Atoifi Hospital in the Soloman Islands to provide near 24/7 power to the site. The genesis came from discussions with the Pacific Centre for Renewable Energy and Energy Efficiency (PCREE).

GreenCo plan to develop an 8mw solar power for the Water Authority of Fiji Tamavua Water Treatment Plant. The Solar Power system would help provide power for the plant and sell power back to the grid during the day, generating and income and reducing the Water Authorities overall energy Bill.

United Hydro Pacific is proposing to be registered as an Independent Power Producer and enter into a Power Purchase Agreement (PPA) with the local utility UNELCO. As part of this they plan to develop several micro hydropower plants in EFATE.

The market development facility as part of the project will help originate projects with targeted technical assistance. FCDO experience suggests that the fund manager is more likely to accept project origination from an integrated facility. Initial analysis also suggests that FCDO does not currently have the capacity to establish a separate market development facility. For these reasons, option 2 above is recommended.

What type of financing?

1. Option 1: Recommended, First loss equity
2. Option 2: Equity
3. Option 3: Debt
4. Option 4: A combination of the above

RCEIF will be a blended finance fund incorporating first loss equity, equity, and debt. First loss equity is the riskiest tranche of financing, and its presence in the fund’s capital structure reduces the risk of other tranches. The main factors which will determine what type of financing is most appropriate for FCDO to make are FCDO’s risk appetite and the importance of first loss equity for attracting other investors. Initial analysis of the riskiness of TIDES and PEAF suggests that providing first loss equity is within FCDO’s risk appetite. While there is currently no financial return proposed for first loss capital investors, Camco indicates a return of up to 3% could be incorporated into the structure.

There is a trade-off, to a certain extent, between catalysing private capital and securing financial returns for FCDO. Recent research from Convergence, a global network for blended finance, highlighted that blended finance transactions have on average a 4:1 leverage ratio and stress the importance of governments, DFI’s, and MDBs, in taking junior and/or first-loss terms to ensure maximum catalytic impact.
[note] Convergence Finance, Blended Finance and Leveraging Concessionality.

Therefore, further analysis is needed on the extent to which other investors require first loss equity, and the balance between the financing tranches will be negotiated with the preferred fund manager. We will also explore the possibility of adding restrictions to the terms of the first loss equity so that its benefits are targeted at certain investor categories which are assessed to require it (e.g. only private sector investors). Also important for attracting other investors is the degree of concessionality in the terms of the first loss equity, and this too will be negotiated with the preferred fund manager. FCDO will assess the fund managers success in raising private capital at first close and keep open the option of financing lower-risk tranches (Equity and Debt) to maximise the returns.

What type of CDEL?

1. Option 1: Fiscal CDEL
2. Option 2: Recommended, Non-fiscal CDEL

The two main factors for determining what type of financing are most appropriate is FCDO’s ownership of the investment and the expected return. If none of the investment is expected to be returned, yet there is a strong development rationale for support, then fiscal CDEL should be used. If the full or partial investment is expected to be returned, then non-fiscal CDEL should be used. Even if all, or part of, the investment could be returned, purely fiscal CDEL could still be used if FCDO’s investment is structured in a way whereby it is not returned, for example by using a special purpose vehicle mandated to reinvest profits and make alternative investments. If FCDO retains the legal right to the asset, then it is non-fiscal CDEL.

There are 4 potential delivery options with different types of CDEL associated with each and relative pros and cons to each. At the time of the Amendment, we propose to use option 1. Our initial assessment was that option 2 provided FCDO the most VFM route, however IPRD does not currently have an allocation to use non-fiscal CDEL and as we cannot guarantee capital preservation this route alongside options 3 and 4 are currently non-viable.

Table 3: Potential Delivery Options
CDEL	Description	Assessment	Pros/Cons
Fiscal / (option1)	FCDO makes Limited Partner investment with the economic interests transferred to an unspecified third party. A decision on which third party receive the funds will be made closer to the point at which the returns are available.	Preferred. This is judged to be a viable CDEL option at this stage. The asset would not sit on FCDO’s balance sheet. At the end of the investment period the returns would either be recycled into a second fund, or transferred to a third party. A default third party has been identified to ensure viability of this option (see Annex G).	FCDO have tested elements of this option with Hogan Lovell’s legal teams who have deemed this route viable. It would allow us to progress both programmatically and meet other donors’ timelines. FCDO would cede legal ownership of the asset and returns, thus we would not need to guarantee capital preservation. Returns would be recycled by a third party to meet wider development objectives. / This option requires legal costs and other fees which will need to be borne. FCDO would lose the right to any returns from RCEIF.
Fiscal / (option 2)	BII invests directly using additional Fiscal CDEL provided FCDO	At this stage non-viable as BII have said they are not actively investing in the Pacific and are prioritising BIP countries in the Indo-Pacific. Discussions with BII continue and they are providing very valuable support to the FCDO team. It requires BII internal approval which will take considerable time. Ultimately this option is unlikely to meet FCDO’s timelines.	BII has the necessary capacity to manage and monitor an investment of this nature. BII would not require additional oversight from FTSB. / On discussion with BII, the transfer of assets is ruled out as it skews BII’s results towards middle income countries and transferring an asset (rather than selling it to BII) has significant legal complications.
Non-Fiscal / (option 3)	FCDO makes Limited Partner investment with partial or full returns returned to HMT.	Given the first loss nature of the investment capital preservation cannot be assured. This option has a clear exit route with the returns going back to HMT.	IPRD’s options appraisal concluded an FT investment is the best option for FCDO in terms of value for money and control. FT allows FCDO to make a direct investment in TIDES and would have greater control and influence over the asset and legal ownership of the returns. It also affords FCDO with simpler exit options and the potential to transfer the asset to BII in the future. / However, IPRD do not currently have an allocation of FT and given the nature of the investment cannot guarantee capital preservation (though our ex ante expectation is of partial/full capital preservation).
Non-Fiscal / (option 4)	FCDO makes Limited Partner investment using an existing central fund managed by FCDO India.	Any potential losses from the Pacific fund would be managed within the overall portfolio of the India programme and deals with preservation of capital concerns. India has demonstrated capability to manage investments of this kind. A Financial Transaction allocation would need to be given to IPRD.	FCDO India have the necessary capacity to manage and monitor an investment of this nature. The returns would go back to the fund of funds. Initial discussions suggest this is potentially possible but may need a bespoke structure with Indian regulators. / The fund of funds would not be based in the Pacific.

1. At exit, we are purposefully establishing the financial arrangements so that money is not returned to FCDO but rather to a third party. The innovative nature of this investment and the degree of subsidies required in the Pacific context justifies the use of fiscal CDEL grants in this instance. By using a third party we can ensure the returns can then be redeployed for development purposes.

Component 2: PNG Clean Energy Investment
The economic appraisal will look at three broad options:
1. Do Nothing.
2. Invest through DFAT. Up to £3.5m for off-grid renewable energy projects delivered through DFAT.
3. Independent delivery. Up to £3.5m for off-grid renewable energy projects delivered through a new programme.

Option 1: Do nothing. DFAT has approved up to AUD 20m, just over £11m, exclusively for grant funding under its PK programme with an option to increase this commitment. This option would mean that PK continues to operate at the existing scale with DFATs current budget and there would be no additional coverage over and above this. FCDO would not be able to influence PK and build relationships with DFAT through this programme. There is a risk of damage to FCDO’s relationship with DFAT, since they are expecting FCDO support following strong lobbying.

Option 2: Invest through DFAT. Up to £3m Fiscal CDEL to support off-grid renewable energy projects and up to £0.5m RDEL for analysis, TA, evaluation, and learning. Delivery will be through DFAT and its PK programme. On RDEL, FCDO reserves the right to commission it’s £0.5m RDEL directly through PK or through alternative delivery routes to support programme objectives, which will be agreed with DFAT where relevant. PK is an off-grid electrification programme to support access to clean energy services in rural and remote communities across PNG. CDEL will be used for off-grid renewable energy projects, this will primarily be for the purchase of household and community solar but may also include mini-grids, should regulations allow.
[note] Regulations currently prevent minigrid systems, and these would need to be changed before PCEI could support them.

Evidence: Existing evidence suggests that off-grid solar, at scale, is a product business that is best suited to the private sector, where an available market exists. This generally results in lower costs, a wider choice of suppliers, and a range of delivery models amongst the private providers. However, there are certain circumstances where NGOs or donors can play a role. For example, by leveraging existing networks, NGOs may be best placed to run distribution networks to remote communities where private providers are not operating. The private sector may not reach much beyond dense population centres, even where well developed markets are present. Therefore, the evidence suggests that subsides or non-market provision are needed for the delivery of solar systems in rural and more remote communities where access or costs may be preventing private markets from operating.
[note] A number of examples of Africa, see Greenlight Planet and the One Acre Fund.

Evidence identifies several potential benefits from providing off-grid solar, these include:
1. Savings from reduced usage of Kerosene and batteries (to charge mobile phones). Across three PK projects, residents reported savings from not needing to buy kerosene and batteries (to charge mobile phones) of between 20 – 100 kina per month (£4.50 to £23). In one PK project, these savings were between 1,000 to 1,200 kina per month (£231 to £279) when combined with additional income generated from night-time economic activity.
  [note] These estimates are based on qualitative monitoring trips undertaken by DFAT to PK grantee’s, Kokodo Track Foundation’s (KTF) Light for Learning in the Oro Province and Tenkile Conservation Alliance (TCA) in the Torricelli Mountain Range.
2. Lower risk of accidents and increased health benefits of solar compared with kerosene and biomass. This includes reduced risk of carbon monoxide and other kerosene generated harmful particulates being inhaled. Accidental kerosene ingestion is also the primary cause of child poisoning in developing countries and children are frequently injured by kerosene burns. Furthermore, it will likely result in reduced biomass use which evidence suggests exposes users to pollutants which may be detrimental to their health.
  [note] Kyayesimira and Muheirwe (2021), Health Concerns and use of biomass energy in households: voices of women from rural communities in Western Uganda.
3. Improved educational opportunities as children are able to do schoolwork throughout the evening. Monitoring from several recent PK programmes highlighted an increased ability to study in the evenings and schools reported increased academic performance as a result.
4. Evening safety, security and socialising all increase, particularly for women and girls, as do opportunities for income generating activities.

Household survey data for PNG found that most households most value lighting to “illuminate cooking areas” (27%), followed by “reading and studying” (21%), and “chatting or hanging out” (19%). Only 16 percent of the households surveyed use solar kits for outdoor activities, where flashlights are often considered more useful than solar products. The survey data also showed that households in PNG only rarely use solar lighting for income-generating activities (“productive uses”). Only 3 percent of respondents used lights to extend working hours or to run an enterprise. This might be due to a lack of income earning opportunities, the cost of electrical appliances, or because household face other, more binding, constraints to income-generating activities. Qualitative evidence from DFAT’s monitoring reports across three PK projects found that residents reported that community solar systems were of high quality, but that community consultation was not adequate. Furthermore, residents identified increased night-time activity such as the ability to socialise and conduct business activity. Residents also reported an increased sense of flexibility regarding the timing of work alongside greater safety in the evening. Villages reported less smoke was emitted from households due to a reduction firewood being burned.
[note] Survey data: Anglo Pacific Research as cited in PNG+Off-Grid+Report.pdf (ifc.org) .
[note] DFAT’s monitoring approach relies mainly on qualitative methods and tools including: gender segregated focus group discussions; semi-structured intevriews with various stakeholder groups; observations of communities during the day and night; and change story collections. The sampling approaches used include rapid random sampling and deliberate sampling to target the community leaders, women, elderly, youth, and people with disabilities.

Modelling: Whilst it is difficult to quantify many of the benefits identified above, it is possible to compare the costs and benefits of using household solar with the use of kerosene. This shows a positive benefit to cost ratio of 4.6 and a net present value (NPV) of £12.2m, without taking unquantified economic, GHG emission, environmental (from reduced biomass use), health, social, and learning benefits into account (See Annex F). These additional benefits are likely to be significant, so the quantified benefit calculated should be considered as a conservative estimate.

The assumptions are as follows: Photovoltaic (PV) kits costing £390 each are provided to 7,700 households giving an upfront cost of £3 million. It is assumed annual operational costs are 1% of the initial investment. Batteries are assumed to be replaced every 5 years at a cost of £100. The total costs over the lifetime of the programme are estimated to be £3.8 million. A discount rate of 10% is applied and the lifetime of the kits is assumed to be 15 years. 5% of solar kits are assumed to stop working each year due to failure, vandalism, theft or because the battery was not replaced. Evaluation, learning and capacity building costs are assumed to be £0.5m.
[note] We have used household solar as a base appraisal because: (i) it constitutes the majority of the existing PK pipeline and is where most of PCEI funds will likely be used; and (ii) currently regulations in PNG don't allow mini-grid installation. Should this change some PCEI fundings may be used to support mini-grids.

The household benefits are the monetary value of not having to purchase kerosene for lighting and other needs (£22.50 per month) and the avoided cost of recharging mobile phones at booths (£5.28 per month). The net present value is £12.2 million based on reaching 7,700 households. It is assumed monetary savings from reduced kerosene purchases are representative of the savings beneficiaries who use other fuels, particularly biomass, would make.
[note] The savings from kerosene are based on an assumption of an average household purchase of 30 litres of kerosene per month at a cost of £0.75 per litre.

The benefits reduce if we assume a higher attrition rate. If 10% of the solar kits stop working each year, then the benefit to cost ratio of reduces to 3.7 and the net present value of the programme is £9.1 million. This underlines the importance of CSOs focusing on mobilising the community to ensure that the solar kits are properly maintained and repaired to achieve optimum value for money. It would take an unrealistically high level of attrition (72% per year) for the programme not to generate any net benefits.
[note] There is a risk of an even higher attrition rate, for example if beneficiaries assign a low value to solar kits that they have been given for free or for only a small financial contribution. As a sensitivity, if we assume an attrition rate of 20%, 30%, and 40% the BCR drops to 2.6, 2.0, and 1.6, respectively.
[note] FCDO will seek agreement from DFAT that monitoring of risks such as attrition and the environmental management of equipment at end of life, will be included in PK established monitoring arrangements.

Similarly, if we assume both a 10% attrition rate and a lower price of kerosene, at 1 kina per litre, a 1/3 of the original price, then the benefit to cost ratio reduces to 1.7 and the net present value of the programme is £2.4 million.

A further sensitivity is run by adjusting the cost of kerosene to reflect savings estimates from several recent PK programmes. As noted above, evidence from PK projects found that households reported direct savings from reduced expenditure on both batteries and kerosene of between 20 - 100 kina per month (£4.50 to £23). Re-running the model using the lowest saving estimate, £4.50 per month, results in a net present value of -£1.3m and a benefit to cost ratio of 0.6. Direct savings of approximately £7.50 (32 kina per month) result in a positive NPV.

Opportunities to use PCEI funds to pilot new and innovative approaches will be explored. This may include approaches that leverage private capital, which could raise the BCR.

Sustainability and Innovation: One potential concern surrounding the programme is the sustainability of a grant-based model. The provision of off-grid solar paid for by donor grants may limit the development of a viable private market. However, given the scale of need, it is unlikely that donor provision of off-grid solar at the scale of this programme will substantially reduce the size of the market thereby crowding out private operators, particularly as it will be targeted at populations with low ability to pay where a market may not be present. Furthermore, initial donor support can stimulate the market during its initial stages of development which could lead to a self-sustaining private market over time. Additionally, as described above, PCEI will actively target rural and remote communities in PNG where access, financing and the availability of a functioning solar market isn’t readily available.

A potential environmental concern is the approach taken to e-waste (mainly expired batteries) in PK’s existing projects. Evidence from a recent DFAT project suggests that batteries last for approximately five years before needing replacement. Therefore, PCEI will pilot innovative new approaches, improve e-waste management and incorporate lessons learnt from other FCDO contexts, such as Africa. By doing these things, FCDO funding could help improve the effectiveness and sustainability of the whole programme. Initial consultations with DFAT suggests that they are supportive of this approach.

Current maintenance is done through a community approach whereby ‘solar champions’ are trained in solar kit installation, usage, and basic maintenance with the intention to train residents. However, reporting evidence from PK suggests that whilst the quality of products and installation was high, the level of community upskilling in maintenance was mixed. The provision of good quality solar kits may help to demonstrate the benefits of the products more widely. Such demonstration effect could help build demand and growth the market for private sector providers.
[note] These insights are based on qualitative monitoring trips undertaken by DFAT to PK grantee’s, Kokodo Track Foundation’s (KTF) Light for Learning in the Oro Province and Tenkile Conservation Alliance (TCA) in the Torricelli Mountain Range.

Option 3: Independent Delivery. The programme would likely result in similar types of benefits to those outlined in option 2, though they would be slower to achieve (since it would take more time to set up a new programme than expand the existing one) and probably also be lower since the programme would not be able to leverage DFAT’s experience and relationships in PNG. Additionally there would not be the cross-fertilisation of expertise between FCDO and DFAT and innovations piloted by the programme would be less able to influence DFAT-funded investments by PK. The secondary benefits of strengthening the UK-Aus partnership would also be missed. However, this option would provide FCDO added flexibility to independently design and deliver the programme, which could result in some differences in types of activities and locations.

There are likely to be significant cost savings from delivering through DFAT, for reasons including: avoidance of set-up costs, economies of scale (e.g. from bulk procurement), and synergies such as avoidance of duplication (e.g. certain staffing positions, and certain engagements with government and communities). Savings are also likely by leveraging DFAT’s existing approach to security and logistics which is necessary given PNG is a difficult environment to operate.

The preferred option is Option 2 because it is expected to deliver higher benefits more quickly and at a lower cost.

Theory of Change
The theory of change combines the two components of the programme and is described in Figure 1.

Figure 1: Theory of Change
Activities			Outputs		Outcomes		Impacts

Market building / Early-stage project preparation. / Technical assistance for developers, governments, and financial institutions. / Financing / Capital for construction and installation in PNG. / Capital for blended finance to fund construction. / Capital for developers to develop projects. / Stakeholder engagement / UK and international diplomacy supports programme objectives. / FCDO-DFAT collaboration. / Demonstration and learning / Lesson learning and knowledge generation. / Data collection, monitoring and evaluation.			Increased number of bankable clean energy projects developed. / Increased capacity of energy sector institutions to plan and set policy. / Increased capacity of solid waste management service providers to manage e-waste. / Lower project cost of capital. / Data, analysis and learning products on renewable energy needs and investment market in PICs produced. / Household and community solar systems installed.		Share of renewables in the national energy mix is increased. / Access to electricity is increased, particularly of poor and marginalised communities. / Intermediate Outcomes / Increased clean energy generation and distribution capacity. / Improved energy planning and engagement from local and governmental institutions. / Capable developers able to bring projects to financial close.		Primary impacts / Reduced GHG emissions. / Improved economic growth, health and poverty reduction from increased electricity use and deployment of savings from lower fossil fuel imports. / Greater private sector investment in renewables beyond RCEIF due to demonstration effects, improved risk perception and commercial understanding of the investment market. / Secondary impacts / Strengthened UK – PIC and Australia bilateral relationships in the region. / Strengthened economic security and economic partnerships across the Pacific.

			Assumptions: / FCDO maintains capability to manage programme. / Poor households without electricity access identified. / RCEIF fund manager identifies developers able to navigate the complex political economy of PICs, and they are interested in entering into a longer-term partnership. / Sufficient additional project proposals are developed to absorb the financing space created by PCEP. / The projects covered by PCEP would not have been developed and financed within the next 7 years without PCEP. / Lessons learning from previous energy programmes in PNG are applied to PCEI component. / Communities are willing to participate in maintenance of off-grid solar		Assumptions: / Adequate incentives are created for the fund manager to use RCEIF resources to invest in projects/locations targeting poor and marginalised groups. / Political will on the part of PIC governments to address critical policy or regulatory barriers to investment. / Other donors are willing and able to provide finance so the RCEIF reaches financial close. / Private investors are willing to invest in RCEIF so that it reaches financial close. / Once energy assets are operational the debt can be refinanced, new investors provide finance on the basis of the financial information generated and some projects are sold. The capital can be recycled into new projects. / Projects supported by PCEP are well-designed and successfully implemented in a timely fashion.		Assumptions: / Projects supported by PCEP deliver expected results / Diesel exporter don’t divert all the reduction in exports to PICs to other markets. / Tariffs set at affordable levels for end users. / Savings from lower expenditure on fossil fuel used productively for social or economic purposes. / The private sector is willing to learn about renewables investment performance, local geographies and governance in PICs / The investment climate in PICs improves and private investors are willing to increase financing for renewable energy in PICs. / PCEP is large enough and sufficiently well performing to strengthen UK – PIC and Australia bilateral relationships.

Cost Benefit Analysis of the Proposed Options

Based on the proposed structure and Theory of Change outlined above, the proposed options will have the costs and benefits outlined below. Most of the benefits have not been quantified, however for the PCEI component, the benefits from lower electricity costs substantially exceed project costs.

Costs
The total financial cost of PCEP will be up to £20m. The FCDO staffing requirement is estimated at around 1.5 full time equivalent (FTE) during years 1-2, falling to around 0.75 FTE in subsequent years (see Annex E).

The main cost drivers for RCEIF are the cost of solar panels and other materials for building renewables infrastructure, land rent, remuneration of construction workers, project development cost, interest on debt financing, and fund management fees. For PCEI they are predominately the procurement cost of household solar kits, staff remuneration of the CSO distributing them and MEL activities.

Benefits
Reduced emissions. A significant gross reduction in emissions is expected, mostly through households and business switching their consumption from electricity generated by diesel to electricity generated by renewables and also from them reduced use of kerosene (for example for lighting). Additionally, PCEP projects are expected to provide demonstration effects that will stimulate further investment in renewables and, in turn, further reductions in diesel and kerosene use. Some of the diesel and kerosene that is no longer demanded is likely to be diverted to other international markets, so net global savings will be lower in the short term.

Improve electricity access. Energy access is a dimension of poverty. All PCEI projects and some RCEIF projects will provide electricity access to households and communities who do not currently have it.

Lower electricity costs. Electricity can be generated at a lower financial cost from renewable sources than diesel. The financial saving from beneficiaries reducing diesel use underpins the benefit to cost ratio of 4.6 estimated for PCEI (see paragraph 84 and Annex F). For RCEIF, the benefits from lower generation costs will be distributed between consumers, utilities, and investors in the generators (including FCDO), depending on the tariff rates.

Economic opportunities and growth. Increasing the supply and reducing the cost of electricity should stimulate the creation of economic opportunities. The size of these benefits from RCEIF will depend, amongst other things, on the balance between projects targeting commercial and industrial customers and towns/larger urban areas, where there is greater potential for business clusters, and with projects targeting remote and rural areas, where the potential for private sector development is smaller. Further analysis is needed on this. Results from PK suggest that it is having little effect on economic opportunities (see paragraph 83), so it is likely that similarly small benefits of this type will be produced by the PCEI component.

Poverty. The livelihood and economic opportunities created by RCEIF should reduce the number of people in poverty. As explained in the previous paragraph, PCEI is not expected to have a substantial impact on income poverty.

Health. The health benefits from PCEP will include reduced respiratory and other health conditions linked with poor air quality, particularly from burning biomass in the home. There will be a reduced need for health spending to treat these conditions by governments and individuals. For PCEI, anecdotal evidence from recent PK projects suggests a reduction in the smoke emitted from houses where solar systems have been installed.

Social. The social benefits from PCEI include increased ability to social and hold meetings in the evening. Evidence from recent PK programmes suggest an increased perception of safety and freedom at night, particularly for women.

Education. PCEI provides children the flexibility to complete schoolwork in the evenings. Evidence from recent PK programmes suggests an increase in the time spent doing homework in the evenings.

Economic security. Dependence of imported diesel, which is characterised by periodic price volatility that can be difficult for PIC economies to manage, will be reduced.

Secondary benefits. PCEP will strengthen UK bilateral relations in PICs, Australia and donor partners, and economic partnerships across the region.

Value for Money

VFM indicators will be included in the programme’s results framework and logical framework (“logframe”) to help monitor and assess VFM performance. These indicators will need to be agreed with the DFAT and it is likely that indicators/KPIs being collected and used for the DFAT’s results framework will be used.

Economy
Much of PCEP’s work will be in remote, rural communities, which will lead to higher transportation and construction/installation cost than in more accessible locations. Project-level assessments will be done to ensure such costs are reasonable for the selected locations.

RCEIF will seek to negotiate multi-project deals with developers/construction firms which will help reduce average transport, construction/installation, legal, management and other costs.

By bundling together multiple small and medium sized projects into a large investment proposition, RCEIF reduces the average costs for finance providers of making and overseeing investments, such as due diligence and staff time. This key barrier to the provision of finance.

The fee rates proposed by Camco and Pollination to cover their cost and make a profit were assessed by PRIF, which judged them to be in line with market rates.

PCEI’s main cost driver is the cost of PV kits. Bulk purchasing will be done for these from suppliers meeting recognised quality standard with appropriate warranties, lowering the average price and ensuring quality. For example KTF, a recent PK grantee, were able to procure PV household solar kits at discount of 25% relative to market rates.
[note] Two-year warrantees on PV kits seems to be the norm.

Efficiency
RCEIF brings together complementary sub-components supporting developers during the development phase of project in order to facilitate financial close, financing for the construction of projects and capacity building for governments to address constraints to new projects. This is expected to be an efficient approach because it addresses a range of key constraints in parallel.

The facility to support project developers will be designed with the aim that the majority of the funding provided for financing and technical assistance will be recovered and recycled into support for new projects through either repayment at the financial close with a set multiple or through the conversion into mezzanine loans at the same time. This is an efficiency way of reducing risk for project developer in a sustainable manner.

Alongside grant funding for off-grid solar systems, PCEI will explore opportunities to influence how DFAT uses its funding for PK and provide MEL activities to ensure there are spill over benefits to improve future project design. The likelihood of influencing DFAT is greater in a joint programme than if FCDO were to establish a standalone one. The nature of this will depend on the activities funded through PK as well as the existing work PK have done to date. Likely areas of FCDO interest will be an evaluation of the existing PK solar projects in PNG, analysis and piloting of potential innovations to the delivery model, as well as developing approaches to sustainably dispose of e-waste generated from the solar kits.
[note] Furthermore, analysis will be funded into ways that the delivery model could leverages private finance, potentially leading to piloting promising approaches (though local conditions in PNG for leveraging private finance of this nature, such as microfinance, are challenging and so pilots may not be viable). This intention is to improve efficiency by enabling households who cannot afford a high upfront cost to sustainably access renewable energy and allow for greater household coverage with limited resources.

There are administrative efficiencies from co-funding PK through DFAT. PK has been running for 3 years and FCDO can avoid the costs of starting up a new programme from scratch and leverage lessons learnt from existing PNG programmes. There are certain recurrent costs that would be duplicated were FCDO to establish a standalone programme, such as staff time spent overseeing PK (a service DFAT will provide without charging FCDO), due diligence, and monitoring. DFAT also conducts Partner Performance Assessments (PPA) on contractor’s performances and Cardno, the managing agent for PK, has received the highest rating for the previous two years, including on value for money. Finally, the PK programme is one of several that come under Australia’s PNG ESIP, which allows FCDO to improve efficiencies by leveraging DFATs existing network and expertise in PNG.

All PK projects have been reviewed by the PK Secretariat to ensure that the percentage of project management costs against the grant funding are in the 15-18% range, which DFAT have judged to be efficient. However, recent projects have averaged closer to 18% and PK have noted that this will likely rise to 20-22% to cover appropriate gender, equality, disability, and social inclusion safeguards alongside MEL obligations. This increase looks high and FCDO will assess future PK projects to ensure any additional spend is justified.

The blended capital structure proposed for RCEIF enables capital providers with different levels of risk tolerance to participate. FCDO will explore the possibility of targeting first loss equity at private sector equity investors who require it, rather than public sector equity investors who may have lower risk-return requirements.

FCDO will negotiate a fee structure for the RCEIF fund manager’s commercial/profit making incentives with FCDO objectives of supporting projects that are both financially sustainable and deliver social and developmental benefits.

There is a market failure of investors having limited understanding of the renewable energy market and its risks in PICs, leading to an inefficiently low level of investment. PCEP will help to address this by providing pilots, demonstration effects and learning products.

PCEI will address imperfect information in the market by providing capacity building activities through training which will ensure local communities can install, service and maintain off-grid solar. Capacity building would in turn provide a secondary market for maintenance, whereby future maintenance activities could provide residents with additional income. However, qualitative evidence from several recent PK programmes suggested there was weak evidence to indicate wider training in the community on the maintenance of household solar, suggesting more work needs to be done.
[note] These are based on qualitative monitoring trips undertaken by DFAT to PK grantee’s, Kokodo Track Foundation’s (KTF) Light for Learning in the Oro Province and Tenkile Conservation Alliance (TCA) in the Torricelli Mountain Range

It is judged that PCEI will not undermine the private market in PNG for solar. A combination of high and unaffordable upfront costs, limited expertise, and a lack of information on its benefits limit it’s functioning, particularly in the rural and remote areas that PK operates in. The poor households that PK support would not be able to buy solar home systems from the private sector in PK’s absence. By improving information and understanding of the benefits of household solar, PK may strengthen the private market in the longer term.

RCEIF will address the missing market for financing of small and medium sized renewable energy projects in the Pacific. This has meant that the level of investment has been inefficiently low. There is almost no financing available for projects with capital expenditure below $10m from either the private sector or MDBs/development institutions – the problem is particularly severe for projects smaller than $2m. Reasons include high transaction costs and long investment timelines. RCEIF will perform a structuring and arrangement role for small and medium sized projects that would otherwise be unable to access such services, drawing together a wide range of existing instruments and aggregating projects to create a bankable project financial structure. Through this, RCEIF will attract private sector finance.

FCDO will seek to agree joint monitoring and evaluation of RCEIF with other donors, reducing inefficient duplication of activities in this area.

Effectiveness/Cost-Effectiveness
FCDO’s Best Buys papers provides international evidence on the cost effectiveness of certain interventions for meeting particular objectives relevant to PCEP’s objective. This evidence is summarised in Annex D and is mixed, which suggests that there significant cost-effectiveness risks. The Climate Change Best Buys paper rates: development capital for climate smart investments; developing renewable energy alternatives to diesel power; development of evidence on what works in reducing traditional biomass use; and paying for project preparation or other costs for projects that do not have a positive private return but do have high social returns all as “High Potential”. However, it rates project-specific subsidy or investment in renewable energy without spill-over benefits, as a “Bad Buy” because it finds such approaches may be poor VFM unless they lead to leverage or systemic change, and because of the risk of crowding out private capital. This only has limited applicability to PCEP because there is judged to be a low risk of crowding out private investment and because the RCEIF uses leverage and has potential spill-over benefits from demonstrating the viability of commercial investment in renewables in PICs, which could lead to future investment. The Economic Development and the Improving Incomes for the Poorest Best Buys papers rate rural/household electrification as “Mixed Evidence” because of the high cost of on-grid connections in some location, the limited enterprise opportunities in rural areas, though there are more in small towns, and the need for a sufficient level of income to afford substantial use. PCEP will support both on-grid and decentralised projects, depending on what is most cost-effective for the location. Economic development benefits are expected, particularly from RCEIF projects targeting commercial and industrial customers, however it is accepted that other types of benefits are also needed to justify PCEP.

PNG has a very low population density and in many remote communities fuel transport costs and maintenance requirements for diesel generators are high. In this context, off-grid renewable energy systems are the least-cost option for supplying electricity to rural areas when household demand for energy is low and load growth is not expected to be significant. Stand-alone diesel generators are likely to be the least-cost option when the population exceeds 500 households, but this is dependent on the number of households served and the price of diesel.
[note] Liebenthal et al, 1994
[note] An Economic Assessment of Renewable Energy Options for Rural Electrification in Pacific Island Countries Allison Woodruff, 2007

PK and project developers, under the scrutiny of DFAT and FCDO, will analyse local conditions to ensure the most cost-effective electricity supply approach is selected (e.g. off-grid household solar is generally more cost effective than mini-grids in locations where households are few and far apart).

Equity
PCEP will increase electricity access in PICs and make it more inclusive of remote areas and poor people. PCEI will target poor communities that are off-grid and particularly remote, and within those communities it will target poor households for support. PCEI will predominately operate in remote villages which at present rely on kerosene and biomass.

International evidence suggests that increasing electrification and renewable energy creates economic and livelihood opportunities and other benefits for women. It is reasonable to expect the PCEP projects will create these types of benefits in PICs for women and marginalised groups. Energy access frees up time for women, improves access to public services and security, and provides opportunities for new income-generating activities.
[note] Renewable Energy: A Gender Perspective (irena.org)
[note] For example, women otherwise may spend an average of 100 hours a year collecting fuel wood. Improved energy access also and gives them more flexibility in sequencing tasks as lighting allows them to do more at night, including productive economic and educational opportunities.

If poor people cannot afford electricity, they will not benefit from access to it. Electricity pricing and its affordability for the poor will be a considered when deciding whether to approve financing for particular projects and, at the portfolio level, FCDO will seek to negotiate performance metrics related to this which will be included in the metrics for determining the performance-related component of fees for RCEIF’s fund manager.
[note] The requirement to provide affordable electricity for the poor will be included in the funding criteria that will be negotiated with the RCEIF fund manager.

## Commercial Case

Overall Approach

Different approaches will be taken for each component. The funding for PCEI will be provided to DFAT who will implement investments on the UK’s behalf in PNG through the PK programme. FCDO will invest directly into RCEIF and will seek to agree a joint approach with other donors interested in co-investing, e.g. on financing terms, fee structure, investment objects, and management arrangements.

The procurement route of the different components is outlined in the table below alongside budget estimates, which will be revised or confirmed as agreements are put in place. The budget estimates are maximum budgets for the overall programme.

Table 3: Procurement Route of PCEP Components
Organisation	Procurement route and contract type	Estimated Value
Regional Clean Energy Investment Fund
RCEIF fund manager (not yet selected)	Limited Partner agreement with RCEIF fund manager (General Partner) for the blended finance facility and possibly an Accountable Grant Arrangements (AGA) for the facility to support project developers.	Up to £15.5 million
MEL firm	Joint procurement with other donors using a competitive approach preferred. / Commercial contract with the provider.	Up to £1 million
Capacity building or analysis providers	Test ability to put through fund manager. If not desirable, then potential option of a commercial contract or Accountable Grant Arrangements (AGA) with providers selected through mini-competition.
Papua New Guinea Clean Energy Investment
DFAT – who will implement funds through their PK programme that is managed by Cardino, and delivered by CSOs	Delegated Cooperation Agreement (DCA) with DFAT. / FCDO reserves the right to commission it’s £0.5m RDEL directly through PK or through alternative delivery routes agreed with DFAT.	Up to £3.5 million
Evaluation firm (Not needed if DFAT extend their programme to 2030)	Commercial contract with a provider selected through a mini-competition under FCDO’s Global Evaluation Monitoring Framework Agreement (GEMFA)
Total		Up to £20 million
[note] The approach will need to be discussed and agreed with other donors. An option that will be proposed is a mini-competition under FCDO’s Global Evaluation Monitoring Framework Agreement.
[note] If DFAT extends their programme to 2030 or beyond, FCDO would fund evaluation work through its DCA with them.

Component 1: RCEIF
FCDO will enter into a Limited Partner agreement with the private equity fund General Partner. A detailed and independent third-party assessment, from the Pacific Regional Infrastructure Facility, of the two proposals was carried out during business case development and a preferred fund manager is identified and ensures the proposal offers VfM. On approval, the team will enter negotiations around the Limited Partnership with the preferred fund manager around all aspects of the fund, including the investment criteria, performance management, and fees and incentives.

Using fiscal CDEL, FCDO would be the Limited Partner in the equity fund but would legally transfer its economic interest to a mutually agreed third party to be identified during the investment period. We will discuss with the General Partner the timing of when our capital will be returned and establish a decision point for deciding which third party will receive our investment returns. Depending on market conditions they may include a follow-on fund. A list of potential options is at Annex G. The General Partner will need to grant permission. As FCDO has given up the economic rights of the returns to a third party this asset would not be recorded on FCDO’s balance sheet.

FCDO guidance on use of Development Capital Grants grants flexibility to programme teams who may not have reached a conclusion on exit strategy in the design, as often it is too early to determine the best value for money option at this stage. In line with the guidance we have set out the exit options available to us (Annex G) to be monitored during implementation so a decision can be taken during delivery. We have crossed referenced this decision with MFAT who have taken a similar approach for other investment vehicles in the Pacific. The criteria for making the decision will include the costs to establish an SPV versus an existing SPV, the need for additional capital, and the maturity of the market should we recycle the money into a follow-on fund in the Pacific.

TIDES will include a Technical Assistance Facility (TAF) which will provide technical assistance (TA) grant facility for developers, financial institutions, utilities, and governments. FCDO will work with the fund manager to ensure the TAF facility, along with its core staffing, will be a separate entity from TIDES and ensure there is fully separated decision-making, accountabilities, and separation of information. This will be agreed during negotiations in coordination with commercial colleagues.

MELCB. The drawdown frameworks are established to offer good value for money by pre-identifying suppliers with the capability and geographic coverage to deliver UK priorities and programming. Standalone contracts with a MEL firm and capacity building providers would be relatively small value (no more than £1 million in total over almost 7 years) so might not necessarily attract the best quality suppliers in an open competition. However, through the central framework this expertise has already been identified and a more efficient process put in place to enable the services to begin quickly. The framework costs have already been robustly assessed. A delay in securing MELCB providers through separate competitive processes might risk gaps in our capacity to deliver the programme and gain maximum benefit.
[note] It has not yet been decided whether to put out a single contract for 7 years or a couple of contracts covering around half the period each.

Component 2: PCEI
Australia is the single largest bilateral donor to the Pacific and is one of the FCDO key developed country priority partners for BIP as set out in the International Development Strategy (May 2022). UK-Australian cooperation will support HMG’s geostrategic goals in the Indo-Pacific, where competition from China is increasing.

DFAT is an Australian government ministry with strong experience of delivering programmes and receiving and managing contributions from other donors. A DCA will be signed with DFAT for PCEI. Co-financing the established DFAT investment in PK will provide FCDO with rapid results, without expending additional resource to establish a new programme or on management fees, as DFAT will not be charging these. The fee rates for PK will be those already negotiated by DFAT. This approach delivers value for money for the UK.

The systems and procedures already established for PK will be used to assess proposals and provide funding to downstream delivery partners such as CSOs. DFAT has strong procurement capability, and its systems and procedures will also be used for other procurements, such research and technical assistance. FCDO agreement will be required before proposals are accepted for UK funding – see the Management Case for more details of the governance arrangement.

DFAT will deliver three streams of work.
1. Commission and support PK to deliver renewable energy projects.
2. Commission research, analysis and technical assistance to: (a) influence and support government to make policy decision and reforms that address constraints to renewable energy investment; and (b) inform FCDO and DFAT about local needs and approaches to address them.
3. Monitor implementation of PK and commission an evaluation of and lesson learning from the programme (see Management Case).

A set of KPIs will be agreed with DFAT during the inception phase and monitored to assess the adequacy of their performance.

FCDO would like an evaluation of the PK projects it has funded in 2030. If PK is extended and is operating then, the evaluation will be commissioned through DFAT. Otherwise, FCDO will commission a third-party evaluation directly for form an evaluation firm under FCDO’s Monitoring and Evaluation Framework.
[note] DFAT has committed funding to PK until 2026 and it will consider whether to extend the programme in future.
[note] The current Monitoring and Evaluation Framework will have expired by 2030. If it is not possible to use this, we expect to utilise another relevant FCDO framework if available.

Delivery Risks
The RCEIF fund manager and DFAT will be responsible for overall delivery of the output areas relating to the RCEIF and PCEI components respectively. The risks will sit with them as supply leads. They will be responsible for tracking and managing delivery performance through their delivery chain. This will include ensuring the capability of the delivery chain and that good partners are identified.

There is a need for clear understanding of what the roles and obligations of parties in the supply chains and wider programme relationships are and these will be set out in the commercial contract with the RCEIF fund manager and the DCA with DFAT. These will also provide clarity of expectation for all members of the delivery chain. DFAT will carefully monitor and reconcile delivery chain partners’ costs before any request for payment is submitted to FCDO. The RCEIF fund manager will account for the use of FCDO funding before new tranches of financing are released.

The RCEIF fund manager and DFAT will be required to identify, mitigate, and manage delivery risks and issues for their areas of responsibility. These will need to be monitored and reported to FCDO and discussed regularly at contract management meetings.

Individual MELCB providers will be responsible for the delivery of the services for which they are contracted.

Termination of services/arrangement for implementing partners under PCEP. FCDO will reserve the right, enshrined in the contractual agreements, to terminate funding in case the performance is not up to mark. In the event of this happening for either component, a new procurement process will be initiated to identify another implementing partner.

Other commercial considerations. The Public Contracts Regulations 2015 is not expected to apply to RECEIF as it does not apply to service contracts related to (i) ‘financial services in connection with the issue, sale, purchase or transfer of securities or other financial instruments within the meaning of Directive 2004/39/EC of the European Parliament and of the Council as amended from time to time,’ or (ii) ‘for loans, whether or not in connection with the issue, sale, purchase or transfer of securities or other financial instruments’.
[note] The Public Contracts Regulations 2015 (legislation.gov.uk)

## Financial Case

FCDO Ministers approved the Concept Note with an indicative budget of up to £20 million for 30 months (October 2022 – March 2025) in July 2022. This business case sets out the intent and justification for an allocation of up to £20 million for the period April 2023 – March 2030 (six years and 11 months). The increased timescale reflects further thinking on the time needed to establish a multi donor investment fund, for that fund to make investments and to enable the investments to have a period of operation before evaluating performance and impact.

## Value and affordability
Energy needs significantly dwarf available resources in the Pacific. A UK contribution of up to £20 million over almost seven years is recommended on the basis it will offer:

Sufficient UK influence in RCEIF and, combined with financing from other donors and the private sector, sufficient to reach the minimum amount required for the fund to be launched.

An expansion of the DFAT rural electrification programme in PNG.

An extended timeline beyond March 2025 is recommended to ensure sustained UK influencing and monitoring over the period when UK-supported investments made, particularly through the regional investment fund which will require a minimum of 4 years to implement new projects. It would also enable a more informative and useful evaluation to be done after a period of the investments being operated.

The programme and funding agreements with partners will include a break point in March 2025 in line with HMG’s spending review.

## Financial components
The UK will deliver the programme through the two components set out in the appraisal case: (i) RCEIF, and (ii) PCEI.

The table below shows the indicative financial breakdown of PCEP over 6 years 11 months under the high case budget scenario of £20 million in full. Lower case scenarios will lead to reductions to the regional investment fund allocation in the first instance.

Table 4: PCEP Budget Breakdown
Component	Partners	Fund type	23/24	24/25	25/26	26/27	27/28	28/29	29/30	Total
Regional Clean Energy Investment Fund	Private Sector Fund Manager	Fiscal C-Del	£0m	£5.2m	£5.2m	£5.1m	£0m	£0m	£0m	£15.5m
	Monitoring, Evaluation & Learning Frameworks	R-Del	£0m	£0.2m	£0.3m	£0.3m	£0.05m	£0.05m	£0.1m	£1m
PNG Clean Energy Investment	DFAT	Fiscal C-Del	£1.25m	£1m	£0.75m	£0m	£0m	£0m	£0m	£3m
		R-Del	£0.15m	£0.1m	£0.1m	£0.1m	£0m	£0m	£0.05m	£0.5m
Total			£1.4m	£6.5m	£6.35m	£5.5m	£0.05m	£0.05m	£0.15m	£20m

PCEP’s annual budget will be accurately profiled at the start of each financial year in compliance with FCDO’s Programme Operating Framework (PrOF) rules for the delivery of the UK ODA target. The programme has been designed to flex according to different budget scenarios, with scope to adjust the proposed profile and shift activity into outer years where required.

Contracts, AGAs and DCA with spending beyond March 2025 will contain a break point at March 2025.

ODA eligibility: All activities in this programme are ODA eligible.

## R-DEL vs C-DEL
Funding for PCEI will be Fiscal CDEL for investment in assets, as they will not provide a return for FCDO, and RDEL for technical assistance (TA), evaluations and other activities.

Approval is being sought to proceed using the fiscal CDEL to ensure progression and keep timeline with other donors. IPRD have identified a viable means to invest using fiscal CDEL in RCEIF and an arrangement to mutually agree which third party will receive the returns from the investment. .

Agreement would allow the team to enter negotiations with the fund manager and other donors in good faith whilst allowing the fund manager to initiate fund raising with the UK committed as an anchor investor. However, we propose a final decision on fiscal and non-fiscal CDEL is made after approval. The team will complete the discussions on all CDEL options for RCEIF (see paragraphs 77 and 78). It will take time for BII to provide a decision as any investment would need to go through its internal processes and Investment Committee.

IPRD does not currently have a non-fiscal CDEL allocation to deploy and would require approval from the Financial Transaction Steering Board. If it is agreed, FCDO can make a direct investment, hold the asset on its balance sheet either directly, or via the India Fund of Funds, and receive any returns. Given the novel nature of non-fiscal CDEL, IPRD would ensue we adhere to the additional approval processes required for Development Capital Investments, including Quality Assurance Unit, Investment Committee, Financial Transaction Steering Board, HMT, and Ministerial approval. For an assessment of the pros of cons of the main delivery options, including fiscal- or non-fiscal CDEL, see table 3.

RDEL will be used for complementary TA, monitoring, evaluation and learning.

## Funding Arrangements
Our contribution to RCEIF will be set out in a Limited Partner agreement with the fund manager (General Partner). Our contribution to PCEI will be guided by a FCDO Delegated Cooperation Agreement (DCA). The arrangement for our contribution for MEL for the RCEIF component will depend on what is agreed with other donors co-funding this. If it is not possible to fund an evaluation of the PCEI component through DFAT, direct funding of this will be needed and the approach will be guided by established framework contracts.

Specific funding agreements and disbursement schedules will be developed on approval of the business case and in coordination with FCDO commercial colleagues. Pre-identified milestones or results to be reported on through partner reporting. If payments need to be made on an input basis, an analysis will be made of the financial report and disbursement plan to avoid payment in advance of needs. Value for money considerations will apply to the process of FCDO negotiation for funding schedules and reporting requirements.

For RECEIF, draw down requirements will be agreed during implementation and are expected to be scheduled periodically based on cashflow forecasts by the fund manager and on then on a need’s basis for the agreed forecast period. A proposed schedule for all donors is included below in Table 6 on the assumption of a $100m fund, this will be refined with donors and the fund manager during negotiations. If project development progress and funding disbursements lag, the forecast cash requirement at the next drawdown will take existing cash balances into account. The LP Deed will include customary protection for investors to ensure the manager acts in accordance with its terms. In addition to agreed mechanism for drawdowns and disbursements, it will contain standard termination rights in the event of the manager’s negligence, misconduct, fraud, breach, or insolvency. FCDO may agree to sequence drawdowns to match other donor requirements.

Table 6: RCEIF Proposed Total Drawdown Schedule ($’ Millions)
Date	First Loss	Preferred Equity	Senior Debt	Percentage
Year 1	2.33	1.75	7.58	11.7%
Year 2	5.40	4.05	17.55	27.0%
Year 3	5.40	4.05	17.55	27.0%
Year 4	5.40	4.05	17.55	27.0%
Year 5	0.73	0.55	2.38	3.6%
Year 6	0.73	0.55	2.38	3.6%
Total	20.00	15.00	65.00	100.0%

Commitments and payments will be made in British pound sterling and FCDO and FCDO will not carry any FOREX risk. No payments will be made in advance of need. Where payment in advance has been agreed, a copy of justification and FCDO’s agreement should be included with each payment request. In the arrangement, these reports should clearly segregate the FCDO proportion of funding. FCDO will agree a payment schedule with partners and will set this out in the formal agreements (whether DCA, commercial contract, or accountable grant). The blend of agreements is built on Australia’s experience of the most effective mechanisms for delivery of investment in PNG; and the PRIF appraisal for the best route to address regional investment needs.

## Assessment of Financial and Fraud Risk
The overall financial and fraud risk in PCEP is assessed as Major. This is because of the risks of instability and corruption in PNG, with risks to the off-grid assets being provided to households and communities. This is still within the risk appetite of DG Indo-Pacific. Having a varied portfolio, working through trusted partners such as Australia and with a well-established fund manager for the regional fund helps balance higher and lower risks across the portfolio.

Steps will be taken to ensure that the risk of corruption is minimised by channelling resources through organisations with good fiduciary controls in place, by conducting fiduciary risk assessments of implementing partners and by monitoring risks as part of the ongoing risk and financial management. PCEP will also draw on Australia’s management which provides for continuous programme review even in the absence of access for monitoring trips. Funding will not be provided through PIC channels.

Australia’s approach to due diligence has already been reviewed by the FCDO Due Diligence Hub to assess whether there are gaps in UK and Australian approaches to due diligence assessments. Its approach was found to be adequate. Where FCDO is entering into a joint agreement as part of a co-financing arrangement DCA with another aid agency and that agency will be managing the financial agreement or delivering the programme, FCDO would require sight of the assurance that the lead donor received from its delivery agents prior to disbursing FCDO’s funds. However, no formal DD is needed for another government. The DCA covers the joint donor language on SEAH. Due diligence requirements will be confirmed and in place on the other components of the programme before funds are disbursed.

FCDO officials managing the PCEP will enforce the zero-tolerance fraud and safeguarding policy in compliance with corporate requirements and ensure that all partners confirm understanding of its conditions and their responsibilities to comply.

The delivery chain risk mapping will be mapped to highlight key financial and fraud risks, the role and costs associated with sub-grantees and the relationship of UK funds to those provided by other donors. The risk map will be reviewed periodically by the programme management team, and a full review conducted six monthly by the PRO and approved by the SRO.

### How will expenditure be monitored, reported, and accounted for?
Reporting timelines and templates will be agreed between FCDO and partners. Any advance payments will be made in line with PrOF guidance and adjusted based on the cash balance, any unspent funds from previous advances.

All partners will provide narrative and financial reporting. Disbursement will be made based on a review of progress against the log-frame, technical reports and financial expenditures statement submitted by the partners. Exceptions to this may include the DCA with Australia and the contractual obligations on the regional investment fund which will be governed by FCDO’s standard reporting agreements and payment procedures.

## Management Case

Programme Management
As part of the approved 2022 Strategic Workforce Plan (SWP) HMG will boost UK Pacific development presence in the Oceania region through
- a new Pacific Development Unit (PDU) headed by an SCS1 in Australia with two deputy Development Counsellors (one in Fiji, one in New Zealand),
- additional climate roles in the Pacific including a Regional Climate and Environment Adviser based in Fiji, and
- a new Regional Trade for Development Adviser in PNG.

These additional positions are now in place and will substantively boost FCDO’s footprint in the region, alongside existing diplomatic posts and Heads of Mission. An expanded footprint will enable the UK to strengthen our development diplomacy and engagement with Pacific countries, Australia and New Zealand (and other donors), and provide regular monitoring and influencing with key stakeholders such as our implementing partners, civil society and the private sector.

A multi-team management approach will be used, drawing on the Oceania Network at post, the Indo Pacific Regional Department (IPRD) in London and Delhi and regional experts like the Climate Advisor and the Development Advisor in PNG. Such an approach reduces staff costs and enables access to expert advice, but it does entail risks from the need to coordinate the provision of programme management and technical advice across teams, which could reduce the overall impact of the programme.

The main programme management responsibilities will be as follows (see Annex E for more details):

The Senior Responsible Owner (SRO) and the Programme Responsible Owner (PRO) will take responsibility for the overall programme including bringing together the different components to ensure coherence with HMG’s strategic objectives. At inception, the SRO will be the head of IPRD, and the PRO will be a G7 economist in IPRD in London, but this may change as the programme management needs reduce after the inception phase.

Advisory expertise and quality assurance will be led by the PRO with the support of a range of PDU posts in the Oceania network, particularly drawing on new climate advisory roles, and advisers in IPRD, the British Investment Partnerships Department and the G7 Oceania Development Adviser in the UK. Australia and Pacific desks in London will also play an important role monitoring whether the programme is on track to contribute to delivery to the new HMG Pacific Strategy and identify opportunities for additional cooperation with other likeminded donors through the Partners of the Blue Pacific grouping.

There will be regular contacts with IPRD, PDU and the Oceanic Network. The formal points of consultation between IPRD and PDU will take place around the 6 monthly calls with the fund manager as well as the annual Limited Partner Advisory Committee meeting. We will also consult with posts around any individual investment or change in the Investment Strategy. More regular informal consultation between IPRD and the Oceanic network is envisaged.

Programme management support will be provided by the IPRD Programme Management Unit. G7 and HEO programme managers based in Delhi will lead on day-to-day programme oversight, providing quality programme management guidance and support to the Oceania Network and ensuring that the programme is delivered in compliance with the PrOF.

Posts will lead on in-country liaison and monitoring, working closely with partners and donors.

There will be a 6-months inception phase to put in place all the implementation arrangements, develop a logframe and create linkages with DFAT on PK and with donors providing co-funding on RCEIF. Subject to a value for money analysis, we will recruit a country-based programme funded Investment Manager to join the Delhi Investment Team to manage the inception period and lead on financial monitoring and approval during implementation.
[note] This may need to be extended if there are substantial delays in reaching a decision on the approach to take with the RCEIF component.

We have benchmarked the resourcing requirements for the RCEIF component with BII, HC Delhi Investment Team, and MFAT. For an investment of this kind, once established BII would have an Investment Manager and Deal Support Officer, with oversight provided by a Director. The main activities would be a quarterly call with the Fund Manager and participation in the Limited Partners Advisory Committee which would meet once a year in person. Once construction commences the FCDO use its staff in the region to carry out field visits. The annual meeting of the advisory committee will be a good opportunity to deepen our relationship with other donors and investors.

Table 5. Staff resourcing benchmarking

IPCP	MFAT	BII	HC Delhi Investment Team
5% Senior Civil Servant	Unit Manager - Establishment: 5%, Implementation: Negligible	5% Director	5% Team Leader
50% Economic Advisor	Senior Adviser Energy - Establishment: less than 50%, Implementation: less than 10%	10% Investment Manager	30-50% Private Sector Adviser
5% other advisers (multiple disciplines, climate, trade, investment, M&E)	Other Advisers - Establishment: less than 10% (mostly legal), Implementation: Negligible	-	-
20% Senior Programme Manager	-	10 % Deal Support Officer	20% Senior Programme Officer
10% Programme Manager	-	-	-

Resourcing will be a 2-stage process built around what is required for successful delivery of the fund. For the period of negotiating and establishing the fund, where the resourcing requirements are greatest, IPRD will engage specialist legal and financial during this period and draw on the advisory support of BII and informal advice of the Delhi Investment Team up to 10% of a FTE. MFAT is also contracting legal and financial support and as co-financiers we will share advice. We are in discussions with MFAT around cost-sharing legal and financial contracts. The informal advice arrangement with BII is set out in an internal email. We have identified a potential gap in resourcing around financial management analysis. As an investor we will need to assess the rate of drawdown of money and whether this is in line with construction progress. Other financial report and situational analysis will be required during implementation. Much of the analysis required is similar to other investment programme FCDO manages, but some analysis would differ to other financial programmes. The options for addressing this gap will be assessed during the implementation phase. We will create a specific decision-point prior to the start of implementation to assess whether we should outsource the financial monitoring. We may deploy some of the MEL budget for outsourced financial assurance during implementation.

Governance arrangements
There will be different governance arrangements for each component in the programme, reflect the differences in requirements and delivery partners:

Component 1: RCEIF
HMG management and support for RCEIF will be led primarily by the SRO and PRO in IPRD with support from PDU. The PRO/SRO will leverage support from post in relevant PICs to inform programming, support events, support lobbying activities to unblock developer issues, and manage any risks.

IPRD will lead on financial, risk, and commercial management, while the PDU will lead on in-country monitoring and liaison. IPRD will lead on quarterly calls with the Investment Manager. The PRO will travel to the PICs periodically to support collaborative working and to engage with implementing partners. Both the SRO and PRO will attend annual Limited Partner Advisory Committees.

TIDES has a complex capital structure that increases the risk of a conflict of interest, therefore, FCDO will work to incorporate strong management and governance arrangements to mitigate against this such as ensuring that TIDES applies (FCA Regulated) procedures on conflict of interest and safeguards.

 Component 2: PCEI
HMG support for PK in PNG will be delivered primarily through DFAT. However, FCDO will have the flexibility to directly procure and manage selected complementary interventions to support PK if needed (for example an evaluation after PK’s current end date, unless PK is extended) – though this is not the preferred delivery approach. The operational-level relationship with DFAT for the implementation of the programme will be led by the SRO and PRO. The SRO will also engage with DFAT to leverage UK support for PK in the context of our wider bilateral relationship with Australia. The UK mission in Port Moresby will lead on monitoring in PNG to assess that UK funds are on track, and that agreements on UK aid visibility are delivered. Specific management, reporting and monitoring arrangements and obligations for UK funding to PK will be set out in the DCA with DFAT.

A Steering Group comprised of representatives from FCDO and DFAT will decide how to allocate UK funding, oversee performance, and take further strategic-level decision as needed. Steering Group meetings will happen on a quarterly basis, though additional meetings may be scheduled if required (e.g. for urgent decisions). FCDO will be represented on the Steering Group by the SRO, PRO and G7 Programme Manager, with other team members deputising if they are unavailable. An update from DFAT on project performance will be a standing item at Steering Group meetings. DFAT will request the Steering Group’s approval to provide funding of a specified amount separately for each proposed project. Analysis of cost-effectiveness and equity of projects will guide the decisions. DFAT will circulate documentation pertaining to proposed projects, including at least 10 working days before Steering Group meetings. For each request, the PRO will seek and collate advice from, at a minimum: a relevant adviser, the UK Mission in Port Moresby, and the PDH. The Steering Group may approve the request, give approval subject to certain amendments, or reject the request. Approvals will require consensus, which would give FCDO a veto over the use of UK funding.

Risk management
The risk appetite of FCDO in PICs in each of FCDO’s seven risk categories, the main risks faced by PCEP and the corresponding mitigating actions are set out below (see the Commercial Case for delivery risk). There are no risks assessed as exceeding the risk appetite.

The overall risk rating of this programme is Major. This is within FCDO’s risk appetite for the Oceanic Network.

Risk management will be tailored for each specific component to reflect the requirements of implementing partners and will be monitored by the FCDO team. As part of this, the FCDO team will conduct due diligence assessments where needed to assess partners’ internal control systems, performance, capacity and financial controls. Risk analysis and the risk register will be refined further during programme inception, along with detailed analysis of risk and residual risk with the reference to the FCDO Risk Management Approach. The risk register of the programme will be reviewed and updated regularly during the implementation phase of the programme.

Risk	Likelihood	Impact	Mitigation	Likelihood	Impact	Risk rating
Strategy and Context				Current Appetite:		Receptive
Political instability and conflict / This could disrupt the construction/installation of renewable energy assets and the collection of revenues.	Likely	Major	Multi-country approach diversifies this risk. / Development assistance to local communities will be an important means of gaining their support for the project and reducing security risks. / The implementing partners are used to working in unstable environments.	Likely	Moderate	Moderate
Diesel imports diverted / Diesel companies may divert diesel consumed in PICs to other export markets. This could reduce net global carbon savings resulting from the PCEP investments in the short to medium-term.	Highly Likely	Major	FCDO will continue engaging with governments around the world to influence them to reduce diesel and other fossil fuel consumption. PCEP will constitute a significant part of wider energy transition programming and contribute to reducing global diesel consumption, particularly in the longer term.	Possible	Major	Major
Investment climate / A deterioration in PIC’s investment climate could deter private investors from investing in renewable energy.	Possible	Major	Multi-country approach diversifies this risk. / RCEIF will seek to crowd-in private investors. FCDO and DFAT will engage with PIC governments if they introduce measures that will weaken the investment climate or deter private sector investment in renewable	Possible	Moderate	Moderate
COVID-19 / A substantial COVID-19 outbreak is possible and could lead to lockdown measures. This could interrupt and delay the development and implementation of energy projects.	Possible	Major	Implementing partners are experienced in operating within COVID-19 restrictions, including through remote working/meetings. NGOs distributing household solar kits and construction firms in PICs are also experienced in operating within COVID-19 restrictions. Ways of working will be adapted as required by the COVID-19 situation.	Possible	Moderate	Moderate
Natural disasters / PICs exposed to several natural hazards. The occurrence of any of these could disrupt implementation and damage infrastructure and other assets funded by the programme.	Possible	Major	DFAT is used to operating in highly challenging places, though the investment fund managers are less experienced. Both will make contingency plans for natural disasters. Natural disaster risk will be considered when choosing where to locate new assets and they will be designed to be disaster resilient.	Possible	Moderate	Moderate
Policy and Programme Delivery				Current Appetite:		Receptive
Government support, response of utilities and regulatory risk / Lack of buy-in from government or regulators, and government regulations may slow or prevent certain projects. For example installing mini-grids is not currently permitted in PNG. / Utilities hold a monopoly position and their response to competition from PCEP-funded projects is uncertain. They may seek to erect barriers to these projects and use their sway with politicians and regulators to deter investment, e.g. they may oppose licenses being granted. / Analysis by PRIF suggests that at least some PIC regulators see the status quo, with unsatisfactory performance by utilities as Nationally Determined Contribution not on track to being met, as a problem and may respond positive to new market entrants.	Highly Likely	Severe	Multi-country approach diversifies this risk. / Diplomatic engagement by DFAT and FCDO and targeted technical assistance will be used to encourage political demand for renewable energy investment and for reform to regulatory barriers to them. / The capacity of project developer will be strengthened so they are better able to engage with regulators and utilities and overcome barrier they may pose.	Likely	Major	Major
Weak investor appetite / Insufficient public or private investors willing to invest in RCEIF. This would reduce the leverage of FCDO’s investment and reduce the size of the fund, which may mean higher fee rates to cover costs.	Likely	Severe	FCDO will coordination with likeminded donors. / If the investment fund does not reach financial close, FCDO will not proceed with an investment in it. / FCDO may need to provide financing on more concessional terms to attract other investors, though this would reduce VFM.	Possible	Major	Major
Weak project pipeline / There may be a limited pipeline of investible clean energy projects. / The ability of DFAT (for the PCEI component) and the fund manager (of the RCEIF component) to identify projects (and associated interventions) which are deliverable in a timely manner, have high social and developmental impact and would not have proceeded (or only proceeded more slowly) in the absence of PCEP will be critical to cost-effectiveness. / There may be incentives for DFAT and FCDO staff to approve weak projects due to political/organisational pressure to utilise funding rapidly. / RCEIF fund manager may be incentivised to approve projects that are strong from a financial perspective but relatively weak from a development one.	Highly likely	Severe	Regular FCDO diplomatic engagement with host governments will seek to address constraints to project development. / The RCEIF model is to develop lasting, multi-project relationships with project developers, building their capacity and giving them confidence to develop a pipeline of projects. To support this, part of FCDO’s funding will be earmarked for providing technical assistance to project developers and funding for project development costs. / Proposed projects will be scrutinised by the Steering Group for the PCEI component and the [Investment Committee] for the RCEIF component to help prevent weak projects proceeding. / A proportion of RCEIF management fees will be linked to performance in projects reaching financial close and delivering developmental benefit. This will incentivise the fund manager to invest in developing a strong project pipeline.	Likely	Major	Major
Funding availability and need / For RCEIF there is uncertainty about the timing of projects reaching financial close and needing investment. This makes it difficult to know in advance how quickly financing will be used and there is a risk of a mismatch with the FCDO’s annual budget allocations. This could mean that projects are delayed if they progress faster than expected and are ready before tranches of funding are available. However if projects progress slower than expected, it could mean budget allocations are not fully used in a particular year, causing financial management challenges for FCDO.	Highly likely	Major	RCEIF portfolio approach diversifies this risk. / Forecasting will be realistic and FCDO and the fund manager will communicate regularly to update these. Where there is flexibility in FCDO’s budget, budget allocations may be brought forward or rolled into subsequent year, though this may not be possible.	Likely	Major	Major
Fee structure provides inadequate incentivises / The RCEIF fund manager may be insufficiently incentivised to deliver projects and achieve developmental objectives. / Performance metrics may be gamed.	Highly likely	Severe	There will be a substantial performance-based component to the RCEIF fund manager’s fees, to help align its interests with FCDOs. This will include linking performance fees not just to financial performance but also to: project reaching financial close, and social and developmental performance. This will help incentivise good performance and reduces the impact on FCDO by sharing the cost of poor performance. / FCDO will seek to take advice from experts at BII when negotiating the term sheet with the RCEIF fund manager.	Likely	Major	Major
Supply chain risk / Global supply chain issues may cause implementation delays and increases in the cost of materials from. Bulk purchasing from suppliers can reduce costs but increase supply chain risk compared to a more diversified supplier approach.	Likely	Major	Supply chain risk will be considered as part of the appraisal of project proposal. / The diversification provided by the multi-project portfolio approach of RCEIF will reduce the impact of the risk. / Global supply chain issues largely are outside the control of grantees and construction firms, and DFAT and the RCEIF fund manager will accommodate requests for contract extensions and possibly budget increases, where justified (subject to clear verification of the justification).	Likely	Moderate	Moderate
DFAT does not extend PK programme / PCEP will run until 2030 while DFAT has only approved funding for PK until 2026. It will not be possible to deliver the outer years of the PCEI component through DFAT if it does not extend PK.	Possible	Major	FCDO will engage with DFAT to encourage it to extend PK. / If it decides not to, activities like an evaluation of the PNG component will be commissioned directly by FCDO, and certain interventions (like e-waste management) will be done earlier, although this will have implications for their effectiveness. FCDO funding for the component is front loaded, further reducing possible impact.	Possible	Moderate	Moderate
Environmental risk / Certain renewable energy investments could pose environmental and biodiversity risks, such as through habitat loss and e-waste (e.g., from expired batteries not being disposed of properly).	Likely	Major	Environmental and biodiversity risks from projects will be carefully assessed, and UK funding will not be provided where such risk are not adequately mitigated. / PK currently manages potential environmental issues associated with the disposal of used household solar kits through education and awareness activities with grantees to ensure the appropriate disposal of expired parts. DFAT recognises that more needs to be done and FCDO will work with them and PK to strengthen e-waste management.	Possible	Moderate	Moderate
Public Service Delivery and Operations				Current Appetite:		Cautious
No risks identified
People				Current Appetite:		Receptive
Inadequate RCEIF and DFAT Staff Capacity / RCEIF or DFAT staff capacity limitations could constrain the pace of new projects being developed and implemented. This would reduce the likelihood of FCDO funding being utilised.	Highly likely	Major	FCDO will stipulate minimum staffing at RCEIF in our funding agreement with them. The fee structure will have a substantial performance component which will help incentivise adequate staffing. Paul Makumbe, Camco’s Pacific Regional Director would be difficult to replace. / There are not currently concerns about DFAT’s staffing capacity. Should a concern arise in future, FCDO will engage with DFAT to encourage rectification.	Possible	Major	Major
FCDO staff risk / The proposed staffing to manage PCEP has staff from multiple teams, multiple locations and multiple time zones. There is a risk of this weakening collaboration between staff and weakening collaboration with implementing partners, reducing the quality of programme management and reducing our influence.	Likely	Major	FCDO staff are experienced in cross team and cross location working. The PRO will travel to the PICs periodically to support collaborative working and to engage with implementing partners.	Possible	Moderate	Moderate
Financial and Fiduciary				Current Appetite:		Cautious
Fiduciary risk / Risk of UK funding being used for unintended purposes or not managed in accordance with our requirements and constraints. Reasons for this may include fraud and corruption.	Likely	Severe	UK funding will be provided to DFAT and the RCEIF fund manager. Due diligence of the former has not raised fiduciary concerns, and due diligence of the latter will be done before any funding is provided. They will be responsible for: performing robust due diligence checks of grant applicants, project developers and construction firms; performing monitoring, performance reviews, and regular audits of funding acquittals; providing capacity building to downstream partners to meet FCDO fiduciary standards; and ensuring that funds are used for intended purposes and in accordance with UK requirements as set out in our DCA and commercial contract agreement with them.	Possible	Major	Major
Additionality risk / The DFAT may divert resource it would have allocated to PK in the absence of the FCDO funding to other areas. / UK funding for RCEIF may divert public and private financing that would have been invested in renewable energy in the PICs anyway, rather than leveraging additional finance. This would reduce PCEP’s emission reduction benefits.	Likely	Major	DFAT will be asked to set out their funding plans for PK upfront and this will be monitored. / Some financing for TRCEIF could be diverted from other renewable energy projects, but this could raise aggregate social and developmental benefits due to the priority RCEIF will give to these objectives. / FCDO may place restrictions on the use of its first loss financing so that it only benefits private sector investors, whose investor is more likely to be genuinely additional than public sector investors.	Possible	Moderate	Moderate
Safeguarding				Current Appetite:		Cautious
Safeguarding Risks / Staff, consultants or contractors employed by DFAT, RCEIF or their downstream partners, including construction firms, may engage in inappropriate sexual or other forms of abusive and harassing behaviour. / This risk is exacerbated by operations taking place in remote areas and limited monitoring in them.	Possible	Severe	DFAT has high standards of safeguarding protocols that staff and consultants must follow. This is also expected by their downstream partners, and they have internal management arrangements in to ensure adherence. The DCA with FCDO will be very specific in reporting and monitoring of this risk. / RCEIF will also be required to have robust safeguarding protocols for staff, consultants and downstream partners. They will be required to ensure: ongoing clear training and guidance, compliance with safeguarding protocols, robust internal management arrangements are in place to oversee the programme, and safeguarding compliance is central to delivery.	Unlikely	Major	Moderate
Reputational				Current Appetite:		Receptive
Reputational risk / Negative perceptions arising from UK expansion in the Pacific, for example due to the context of the 0.5% fiscal constraints and PICs receiving relatively high levels of aid per capita and some being upper middle-income countries.	Possible	Minor	PCEP will be communicated carefully to UK and PIC audiences, with the targeting of poor communities emphasised.	Unlikely	Minor	Minor
PNG Government risk from delivery through DFAT / Negative perceptions arising due to the PNG Government preferring FCDO to deal with them directly rather than channelling our funds through DFAT.	Likely	Moderate	Diplomatic engagement with key PNG government officials to: (i) explain the rationale for the chosen modality in advance of announcing the PNG component; and (ii) get their views and guidance on project selection and design.	Possible	Minor	Minor
Perception of high profits / There is a risk of PCEP benefitting RCEIF’s fund manager and its financiers disproportionately, particularly if high profits are made but development benefits are limited, poor people pay a high price for electricity and FCDO gets limited returns.	Likely	Major	Part of the RCEIF fund manager’s fees will be liked to performance against development criteria. / FCDO will negotiate terms on its investment such that it will receive a higher return if returns to the equity layer in the RCEIF capital structure exceed certain benchmarks. / Electricity pricing and its affordability for the poor will be a considered when deciding whether to approve financing for particular projects and, at the portfolio level, FCDO will seek to negotiate performance metrics related to this which will be included in the metrics for determining the performance-related component of fees for RCEIF’s fund manager.	Possible	Moderate	Moderate

Monitoring, Evaluation and Learning

Different approaches to MEL will be taken for the two main components. However FCDO will seek to share lessons learned between the components after annual reviews and in discussions with our RED Transforming Energy Access (TEA) team who are supporting universities and other innovations in the region.

PCEI

DFAT will monitor and evaluate the performance of PK, disaggregating the results attributable to PCEP. DFAT already has a monitoring and evaluation system in place to do this. FCDO has reviewed part of DFAT’s monitoring and evaluation plans and judged them to be adequate. We will finish reviewing them and negotiate amendments and the addition of new indicators as needed. There will be scope for FCDO staff to engage in monitoring visits, though this is not expected to be needed frequently. FCDO will also commission studies throughout the PCEI to inform programming design and appropriate indicators for outer years, initially this will focus on e-waste and a review of the sustainability of various PK models.

DFAT will provide monitoring and performance updates at quarterly meetings and written reports annually, which will be reviewed by the PRO and programme manager and feed into FCDO’s annual reviews of PCEI. DFAT will provide an evaluate report in 2026. DFAT will be required to produce revised monitoring and evaluation plans that should be agreed by the SRO/PRO within 4 months of the DCA being signed.

DFAT is scheduled to end PK in 2026, and an evaluation will be done before this when PCEI-funded assets will be only 1-3 years old. FCDO would like there to be an additional evaluation covering a longer time period in order to evaluate how assets have been operated and maintained, how e-waste has been managed, and what longer-term impacts have been. FCDO will directly procure an evaluation in 2029/30 from an evaluation organisation unless PK is extended. If it is, the evaluation would be commissioned through DFAT.

RCEIF
The PRO and MEL Adviser will develop a results framework and monitoring and evaluations plans following approval of this Business Case. An independent M&E organisation will be procured and will have monitoring, data validation and evaluation responsibilities. FCDO will seek agreement from other development partners funding RCEIF that this M&E organisation will act jointly for us as a group, with a jointly agree terms of reference and co-funding. The PRO and MEL Adviser will collaborate with the M&E organisation, development partner representatives and fund manager to establish appropriate indicators (quantitative and qualitative) to measure performance. These will include social, developmental, financial and climate indicators. Some of these indicators will be used as the basis for part of the fund manager’s performance fee, and these will be agreed with fund manager before the contract is signed. The results framework and monitoring and evaluation plans will be living documents that will be updated over time as funding is provided to additional projects.

The fund manager will monitor and report on the financial performance of RCEIF investments, the fund overall and certain other aspects of performance. This will feed into reporting by the M&E organisation as well as being provided to FCDO. Camco have noted the collection of quarterly KPI and ESG data from its investees and annual reviews to ensure fitness of projects/investee ESMS implementation. Camco noted investors are typically provided with quarterly and annual performance reports.

FCDO will supplement the aforementioned monitoring through a mix of regular meetings with key partners (including through the UK-Australia Strategic Infrastructure and Development Dialogue), and field visits by FCDO officials from PDU and IPRD.

Logframe
A single overall logframe will be developed as a tool for FCDO to assess and manage PCEP’s performance. It will include indicators for measuring the progress of delivery partners against outputs, outcomes and impacts set out in the Theory of Change, with baselines, milestones and targets. Indicators will be disaggregated by gender where feasible. Relevant ICF indicators will be included (see Table 6). The logframe will be produced within 4 months of business case approval, however it is expected that some indicators for the RCEIF component will be added subsequently because the component will still be under development at that stage. For the PCEI component, we will draw on indicators used in DFAT’s agreed M&E framework with their PNG delivery partner.

Table 7: ICF KPIs to be included in the logframe
ICF KPI	Results level
ICF KPI 2: Number of people and social institutions with improved access to clean energy	Outcome level
ICF KPI 6: GHG emissions reduced or avoided	Impact level
ICF KPI 11: Public Climate finance mobilized (GBP)	Outcome level
ICF KPI 12: Private Climate Finance mobilized (GBP)	Outcome level

During the annual, mid- and end-point reviews, both components will be reviewed against logframe indicators, results and other criteria. Based on this, judgements and recommendations on the performance of the components will be provided. With strategic leadership from the SRO, the logframe will be reviewed on an annual basis as part of the annual review process, and amendment will be made as needed to reflect changes of context and project interventions.

The ICF spending from PCEP will be reported by the UK not Australia.

Approach to Evaluation
To support adaptations and improvements to RCEIF, an evaluation of RCEIF will be done using a “process evaluation” approach around the end of first three years of PCEP. This will feed into PCEP’s Mid-Term Review. The evaluation will assess whether the methods or ways of delivery used for implementation are being effective or not. The focus of evaluation questions will include:
[note] This is tentative; exact timing will be decided in consultation with independent MEL agent.
- What is working well, less well, and why?
- What could be improved?
- How has the context influenced delivery?

For overall effectiveness and learning, evaluations will be done on both components of the programme in 2029/30 using an impact evaluation approach. These will feed into the Programme Completion Review and look at the overall effectiveness of PCEP’s core hypotheses and whether it succeeded in achieving the intended outcome level results. This will mainly focus on:
- What measurable outcomes, both intended and unintended, occurred?
- How much of these outcomes can be attributed to programme components?
- Have different groups been impacted in different ways, how and why?
- How has the context influenced outcomes?
- How sustainable are the programme’s outcome level results?

Specific evaluation questions and methodology will be agreed jointly by FCDO and independent evaluation managing agent.

Lesson learning is a crucial element of PCEP. The evaluations of each component will identify key lessons and disseminated them publicly through reports and a public event in 2030. The SRO also will share lessons learned across HMG meetings through meetings and written review documents in 2030, at the conclusion of the programme, in line with FCDO processes for capturing and disseminating lessons learned.

The Programme Completion Review will be undertaken by the FCDO team within three months of the end of the programme in line with the PrOF.

Annex A: Development and Political Economy Context

The cultures of Melanesia are characterized by small-scale societies of related kin, numerous languages (more than 800 in PNG alone), leadership based on achievement rather than ascription, and political loyalties that remain intensely local. In PNG, Solomon Islands and Vanuatu, a sense of national identity has been slow to form, and successful politicians are those who respond not to national needs but to the demands of the members of the kin group who voted for them (their ‘wantoks’). These three Melanesian countries are states defined by territory rather than by national identity, and the result is ineffective, and in more remote locations, absent government.

The map below shows the traditional grouping of the islands into Melanesia, Polynesia, and Micronesia. The map is not to scale, and it should be noted that the Pacific Ocean covers more than a quarter of the Earth’s surface. The proposed intervention of the Pacific Clean Energy Programme will particularly focus on Melanesia (PNG, Fiji, Solomon Islands, Vanuatu), and parts of Polynesia (Samoa, Tonga, Tuvalu).

Political Economy Challenges
There are several reasons for weak governance in the PICs. The first is that the colonial history of PICs has left diverse legacies. A second and related reason is that the colonial state had a negligible presence beyond the small capital and often managed in an idiosyncratic manner. This led to weak states, particularly in Melanesia.

The third explanation for weak governance is the role of geography in state formation. The predominantly rural populations of PNG, Solomon Islands, and Vanuatu are widely dispersed across mountains, valleys, and coastlines, reflecting access to subsistence resources and historic movements of people. Many communities are only accessible along bush tracks or by boat, in countries that are groups of islands rather than single land masses. This dispersal represents a barrier to central government authority and the delivery of services. More compact countries such as Fiji, Samoa and Tonga suffer few of these problems, and their governments are consequently considered to be more effective, with greater reach and better functional political authority.

A fourth reason is that access to the best-paying jobs for Pacific islanders differs from one subregion to another. Better paying jobs are found not in the islands themselves but in the more developed economies of New Zealand, Australia, the USA, and the Middle East. Labour migration acts as a safety valve for Pacific countries that have access to employment overseas. In most cases, Pacific islanders supplement the incomes of their families back home by sending remittances, which are major sources of national income in Tonga, Samoa, Fiji, Kiribati, Tuvalu, and Vanuatu. Under the new Labour administration, Australia is currently committed to expanding access to its labour market for Pacific Islanders.

A key part of the solution for the independent PICs has to be more effective and accountable governance. Yet progression in this direction by some PICs must be negotiated within political systems that remain heavily influenced by cultures.

Annex B: Main investment, capacity building and information sharing programmes in PICs

Regional renewable energy programmes in the Pacific have concentrated on sharing expertise, capacity building and increasing levels of private sector investment. Such programmes have had limited success.

The main regional programmes include:

- The World Bank’s programme targeted at increasing the capacity of power utilities to incorporate and manage renewable energy technologies which operates in 10 Pacific Island Countries including PNG.
- Japan’s long term “Project for Introduction of Hybrid Power Generation Systems in Pacific Island Countries” which aims to scale up renewable energy while maintaining diesel generators as necessary to ensure power supply. The programme operates in Fiji, Tuvalu, Kiribati, Micronesia, and the Marshall Islands.
- The AIFFP will support renewable energy investment across the region, through up to AUD 500 million in grants and up to AUD 3 billion in loans. Major investments have focused on PNG, Palau and the Solomon Islands to date.

Programmes aimed at regional capacity building and information sharing include:
- The Global Green Growth Institute, which has operations in eight Pacific countries and is developing a Pacific Regional Strategy, including a Rural Electrification Fund in Fiji.
- The Pacific Centre for Renewable Energy and Energy Efficiency is a programme established by Pacific states to promote renewable energy and energy efficiency in the region, and to support implementation of projects.
- The Private Finance Advisory Network has recently set up a programme to scale up its operations in the Pacific and is currently assisting projects in Fiji, with plans for expansion to the Solomon Islands and Tonga.

Country specific programmes have included directly funding power plants and upgrading grids, with less focus on capacity-building and increasing private investment. The main recipients of country specific programme funding have been PNG and Tonga:
- The PNG Electrification partnership is a multi-donor program with the US, Australia, Japan and New Zealand all contributing. Japan has given a grant of 1bn yen; New Zealand has committed NZD 60m and Australia has committed AUD 250m.
- Australia has three long-term programmes on improving renewable energy access in Tonga, worth a combined AUD 18.3 million. Two are being delivered by the ADB.
- The EU has spent more than €21m over the seven years 2013-2020 on improving the Tongan energy sector.
- The World Bank is currently undertaking energy development projects in the Marshall Islands worth USD 34m and a rural electrification project in Vanuatu.

Annex C: Summary of proposals and key investment terms

Metric					PEAF	TIDES
	DevCo	YieldCo	Market Capacity Building Facilities	Investment Facility
Description	Development finance & technical assistance facility for unsolicited proposal development; and 10-20 greenfield project developments	Construction finance and holding/operating facility for 10-15 greenfield IPP projects backed by PPAs	Consists of (1) Technical assistance (TA) grant facility for developers and governments; (2) development loans, and (3) Results Based Finance (RBF) facility	Developer-focused renewable energy funding platform for construction, aggregation and capital recycling
Objective	Long-term capital preservation (rather than investor returns) to be reinvested in ongoing pipeline development	Construction, operations & maintenance of assets and delivery of returns to investors	Increase bankable projects and capable developers, TA for developers and government, early-stage financing for project development; bridge affordability gaps	Blended returns
Fund size	USD 10 million	USD 250 million	USD 30 million	USD 100 million
Structure	Zero interest loan, 10 year tenor, bullet repay	Concessional equity: USD 50 million / Common equity: USD 100 million / Debt: USD 100M (40%, Green bond)	TA facility: USD 5 million as grants Development loans: USD 7 million repaid at financial close as revolving grant / RBF: USD 18 million	First loss equity: USD 20 million / Preferred equity: USD 15 million / Debt: 65 million (65%)
Number of investments	10-20	10-15	Support for 240 mini-grids; 17 utility scale; 70 TA interventions	125 projects in first 4 years
Target returns	n/a	Equity: 11-15%	n/a	Debt: 4%, 15 year tenor / Pref Equity: 10-12% / First loss: residual up to 2%
Hold period	n/a	15-25 years	n/a	4 years operating / exit
Initial investment period	n/a	3-5 years	5 years	4 years (6 for mini grid)
Project size (Capex)	n/a	USD 2-30 million	n/a	Utility scale: USD 500k – 10m (6m avg.) / C&I: USD 500k – 3 m / mini grid: USD 300k
Fees	3-6% management fee	1-2% annual management fee / + 20% carry of excess returns with catch-up and clawback	Facility Manager fee of USD 2.14 million over 5 years	2% annual management fee on committed capital during Deployment, thereafter 1.75% of deployed capital. Plus 20% carry on excess returns, with payments indexed by a balanced scorecard

Source: PRIF summary of Pollination and Camco proposals

Annex D: International Cost-Effectiveness Evidence on Interventions Relevant to PCEP from FCDO’s Best Buys Papers

Category	Rating	Finding	Comment
Climate Change Best Buys Paper
Development capital for climate smart investments	High Potential	UK public finance needs to ensure it plays a catalytic role, filling gaps rather than crowding out private capital and having a leveraging / catalytic effect on the wider investment environment beyond the immediate project being financed, e.g. by targeting geographies where capital is constrained, and where private investors can be crowded-in by de-risking.	This is what PCEP aims to do. PICs are capital constrained, PCEP targets a particular gap in private financing and provision of renewable energy assets in rural communities, it will seek to crowd in private finance directly and indirectly through demonstration effects.
Developing renewable energy alternatives to diesel power	High Potential	Cost-effectiveness: Replacing diesel with solar-diesel hybrid systems - £385 to -£135/ tCO2. / Diesel power generation is expensive but widely available. Low carbon alternatives are likely to have higher upfront costs and lower running costs but this may require good financing packages. / Other benefits include: reduced health damages, possible extended electricity access.	Providing a renewable alternative to diesel a specific objective of RCEIF. / The households targeted by PCEI mostly do not use diesel power, so limited relevance.
Development of evidence on what works in reducing traditional biomass use	High Potential	There are significant health benefits associated with reduced biomass use. / Evidence base is on biomass for cooking rather than lighting.	Many beneficiaries, particularly of the PCEI component, use bamboo torches for lighting in the home and this is expected to be reduced. Similar types of health benefits as from reducing use of biomass for cooking are expected. / Some beneficiaries of RCEIF may reduce use of biomass for cooking – this will be monitored. The household solar kits supported by the PNG component will not provide enough energy to enable electric cooking.
Paying for project preparation or other costs for projects that do not have a positive private return but do have high social returns	High Potential	This approach is cost-effective if a small public contribution towards costs pushes a project with high social returns (i.e. substantial climate benefits) to have sufficiently high private returns to enable investment.	Donor contributions into RCEIF will seek to enable investment in projects with high social returns. However these contributions are broader than contributions to project preparation (concessional financing is also being provided), and will be substantial in size overall.
Project-specific subsidy or investment in renewable energy without spill-over benefits	Bad Buy	Such approaches may be poor VFM unless they lead to leverage or systemic change; and because of the risk of crowding out private capital. / In risker environment public investment can in principle have a greater leveraging / catalytic effect, crowding-in private investors by de-risking their investment share and /or establishing markets and a track-record of successful investment. These spill-over effects will depend on the context and needs case-by-case analysis.	PICs are a risky environment and there is judged to be a low risk of crowding out private investment, particular in the remote areas PCEP will work. / The RCEIF model involves leverage and the PNG component will export opportunities to pilot leveraged approaches. Both components will seek to demonstrate viable and sustainable models for improving clean energy access and demonstrate a track-record of successful investment. The intention is to catalyse additional future investment.
Economic Development Best Buys Paper
Rural/household electrification	Mixed evidence	Costs for on-grid connections greatly increase as you shift from urban to rural areas (with last mile connection costs being particularly high), but costs of solar off-grid connections have fallen rapidly improving the economics of de-centralised approaches like mini-grids. Low take up by poor households. / May have stronger effects for women. / Need sufficient level of income for households to be able to afford substantial use and enough population density for there to be enterprise opportunities. In general rural areas not a major source of growth even with electrification. Electrification of small towns more likely to be beneficial for growth. May be more cost-effective as a livelihoods or human development intervention than a growth one (e.g. health benefits of reduced use of biomass for cooking), especially through de-centralised approaches, though there is evidence that the poor don’t use much electricity.	RCEIF will take a mixed approach, investing in both on-grid and de-centralised/mini-grid projects. It is expected that some projects will be in small towns, while others will be targeted at commercial and industrial customers, providing potential for growth benefits. / PCEI will only invest in off-grid communities and has less potential for stimulating growth. / While economic development benefits are expected, it is recognised that the size of these benefits alone do not justify PCEP.
Large Scale Energy	Great Buy		The programme will not support large scale energy projects. It is recognised that they can generate electricity at a lower average cost per kWh and would be more cost effective in supporting economic development. However they are not a cost-effective approach for reaching the remote communities that are the target (for equity reasons) of PCEP.
Improving Incomes for the Poorest, focusing on social protection and agriculture Best Buys Paper
Rural electrification	Mixed evidence	Rural electrification is only effective where populations are sufficiently well off to be able to afford electric appliances. / The size of the impact of such investments can vary by commodity and by geographical location – where farming systems are more modern and have greater electrical requirements, the investment in electricity appears to have a greater impact.	The household solar kits supported PCEI are context appropriate, providing enough electricity for things like community and household lights as well as mobile phones – which community members have – but not enough for additional appliances that are not affordable.

Annex E: FCDO Programme Management Requirements and Responsibilities

Role	Responsibility	Time
SRO	Accountable for the successful delivery of the programme. / Oversight of programmes including all components and ensuring programme coherence across the Oceania Network. / Engage with implementing partners, government partners and DFAT and other donors to influence on priority issues and ensure strong collaboration. / Ensuring PCEP strategic fit with UK objectives. / Communicate the achievements as well as results to the Ministers and organisation.	10% FTE in years 1-2, then 5% FTE. SCS in IPRD.
PRO	Accountable to the SRO for the delivery of the programme. / Engage with implementing partners and donors to ensure strong collaboration and smooth delivery. / Coordinate provision of advisory and programme management expertise. / Ensure lessons learned are communicated and shared across the organisation. / Ensure compliance with smart rules, due diligence and safeguarding	50% FTE in years 1-2, then 15% FTE – 1 x G7 Economist in IPRD
Advisory expertise	Technical advisory support to delivery partners and Pacific governments / Support programme reviews / Support project risk management / Field monitoring, evaluation and learning	35% FTE – comprised of / 5% of regional climate advisor in Fiji; / 5% of regional trade for development adviser in PNG; / 10% of Indo-Pacific Regional Department advisory capability; / 5% of British Investment Partnerships Department advisor; / 10% of Oceania Desk
Advisory expertise / (RCEIF)	BII technical and advisory support (until the point of fund establishment) / Financial management, analysing use of proceeds and flow of finance / Field monitoring of infrastructure projects	5% FTE Director level input / 10% Investment Manager / 10% FTE HC Delhi India (TBC) / Pacific Development Unit, Fiji
Programme management	Accountable to the SRO and PRO for the delivery of the programme, ensuring compliance with all PrOF rules and upholding the accompanying principles. / Engage with implementing partners to oversee timely delivery of programme. / Ensuring that FCDO compliance are applied across all the projects / Monitor the programme’s delivery of results against the logframe / Lead review of the risk management framework and escalate where necessary / Ensure programme reviews are delivered within deadlines to high standard / Provide inputs on the technical and financial reports / Ensure timely disbursement aligned with ODA allocations and spending review / Safeguarding champion	50% FTE in years 1-2 then 20% FTE – G7 and SEO in the IPRD programme management unit
Diplomatic posts in PICs	Engage with implementing partners, government partners, communities, and other stakeholders to ensure changing local contexts influence delivery decisions. / Field monitoring, evaluation and learning.	5% FTE - diplomatic posts and Heads of Mission in PICs

Annex F: Cost and benefit options of providing £3.5m to household solar (£’s)

Year	Total Cost	Discounted costs	Discounted Benefits with Attrition	Net Present Value with Attrition	Benefit-Cost Ratio
0	1,400,000	1,400,000	1,069,530	- 330,470
1	1,121,875	1,019,886	1,701,525	681,639
2	878,281	725,852	1,999,844	1,273,992
3	126,867	95,317	1,727,138	1,631,821
4	25,524	17,433	1,491,619	1,474,186
5	74,248	46,102	1,288,217	1,242,115
6	23,035	13,003	1,112,551	1,099,548
7	21,883	11,230	960,839	949,610
8	20,789	9,698	829,816	820,117
9	19,750	8,376	716,659	708,283
10	18,762	7,234	618,933	611,699
11	17,824	6,247	534,533	528,286
12	16,933	5,395	461,642	456,247
13	16,086	4,660	398,691	394,031
14	15,282	4,024	344,324	340,300
15	14,518	3,475	297,371	293,895
Total	3,811,659	3,377,933	15,553,232	12,175,299	4.6

Annex G: Identified options for investment returns

Option	Description	Pros and Cons
Option 1: / TIDES 2 fund.	Depending on the success of TIDES, our investment is recycled into a follow-on fund. This has been the case for REPP where FCDO money has been recycled into a 2nd round fund.	This may send the wrong signal to the market that continued donor support is required hindering the deepening of the financial market. We may not want to take a first loss position in a second fund if the first fund was well subscribed and achieved demonstration impact. Further, in future years BII is more likely to have the knowledge of the market to enter.
Option 2 / Returns go to an established Investment SPV	The returns could be directed to an established investment vehicle in any region FCDO operates in. There are SPVs established for Africa and India.	Using an established SPV avoids the additional costs of establishing a new SPV and FCDO can direct the returns to an investment vehicle with a strong track record in any region.
Option 3 / FCDO creates a new SPV to receive the returns	FCDO creates a new SPV with a specific investment purpose.	There would be establishment costs and would require a solution to dissolving the SPV at some point. The geography and investment mandate would need to be established. We would not own the SPV and it would not sit on FCDO’s balance sheet as an asset.
Option 4 / Returns go to the Pacific Catastrophe Risk Insurance Company to expand disaster risk insurance	PCRIC is a segregated cell company that offers disaster risk insurance to Pacific nations. It has an insurance fund of $26 million to back its policies. It employs a fund manager to invest its capital in financial assets and is owned by a not-for profit Foundation. FCDO has capitalised the company in the past.	PCRIC has a fund manager and a developmental purpose. The returns would be recycled in the region. The FCDO is represented on the Council of Members and is an anchor investor. The company has a Board of Directors responsible for its financial management and is domiciled and supervised by the Cook Islands financial authorities.