## Annual Review Template

Title: Pacific Clean Energy Programme (PCEP)
Programme Value £ (full life): £20m		Review date: 17 May 2025
Programme Code: [AMP ID#] 400021	AMP start date: 17 May 2023	AMP end date: 31 March 2030

Summary of Programme Performance
Year	2024	2025	2026
Overall Output Score	B	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	Publication of correct version of BC in early December 2025
DevTracker Link to results framework:	Publication of revised LF is in progress

A. SUMMARY AND OVERVIEW

Description of programme

Access to affordable energy is a major challenge to the Pacific Island Countries (PICs). PICs are highly vulnerable to climate change and face amongst the most expensive electricity costs in the world.

The Pacific Clean Energy Programme (PCEP) is a £20m programme across 7 years. The objectives of PCEP are both increased and equitable access to affordable and reliable electricity, with a longer-term objective of reducing carbon emissions across several PICs. The intended impact is increased number of people and businesses with access to clean energy in Pacific Islands and reduced diesel fuel imports and lower Greenhouse Gas (GHG) emissions at the national level.

PCEP is closely aligned with FCDOs Pacific Strategy, wider activities in the region and is a 100% ICF programme. Specifically, it supports the Energy Transition and Inclusive Growth pillars. The UK and NZ funding through TIDES supports the PM’s Clean Energy Mission and is endorsed by the Pacific Community (SPC). The funding enables partnership with the private sector to finance renewable energy projects in the Pacific where energy transition is urgent.

PCEP has two main components:

  1. The UK is investing £3.5m through an ongoing Australian programme, the Pawarim Komuniti Partnerships (PKP)[1]. The aim is to scale up and reach additional poor households without access to electricity through technologies for off-grid electrification in Papua New Guinea. PKP interventions specifically targets poor, remote communities especially women and marginalised groups by improving energy access, which enhances public services, safety, and income-earning opportunities where off-grid solutions are required. PKP is managed as part of Australia’s Economic and Social Program (ESIP)[2] which is implemented by managing contractor DT Global.
    [1] Pawarim Komuniti Partnerships: https://pawarimkomuniti.org.pg/. This was previously known as Pawarim Komuniti (PK). This reflects a shift towards a broader approach, focusing on partnerships to improve livelihoods, education, health, and economic development in rural and remote communities.
    [2] Information on the Economic and Social Program: https://www.dfat.gov.au/publications/development/pngs-economic-and-social-infrastructure-program-esip

PKP is the first co-financed Pacific initiative through the UK-Australia Strategic Infrastructure and Development Dialogue and was a key AUKMIN 2022 commitment. PKP is a strong example of UK-Australia development cooperation and partnership in the region, and our aligned commitment to support the clean energy transition in the Pacific. Through working in collaboration with Australia on the programme, we have gained a better understanding of DFAT’s internal processes for programmes and gained important lessons for future UK-Australia cooperation e.g. on transparency requirements.

For PNG, the PKP makes the UK a significant partner, specifically in the energy sector. It also enables the UK to join the coordinated donor effort - the PNG Electrification Partnership (PEP) - between Australia, Japan, New Zealand, and the USA, to support PNGs electrification process.

  1. Transforming Island Development through Electrification and Sustainability (TIDES): TIDES is an innovative blended finance fund which will finance renewable energy projects in six Pacific Island countries - Fiji, Tonga, Samoa, Cook Islands, Vanuatu and Solomon Islands. The UK alongside New Zealand Ministry of Foreign Affairs and Trade (MFAT) are providing 20% of the capital for TIDES in the form of junior equity. Once launched, this fund will provide loans to developers of mini-grids (key for improving energy access in remote communities), commercial and industrial solar, and small on-grid projects.

At the Commonwealth Heads of Government Meeting (CHOGM) in October 2024 the PM with NZ PM Luxon jointly announced: “a pipeline of renewable energy schemes for the Pacific” to reduce reliance on diesel generators and cut carbon emissions. In November 2024 the FS and NZ Deputy Prime Minister Peters agreed at their Strategic Dialogue that this project (‘TIDES’) would combine multi-year funding commitments from the UK and New Zealand governments of £23.9 million to partner with further private sector investment of £80m.

Summary supporting narrative for the overall score in this review

This review focuses on the UK’s contribution to Pawarim Komuniti Partnerships (PKP). This is the only operational part of the programme and is therefore the basis for results reporting. The larger component, Transforming Island Development through Electrification and Sustainability (TIDES) is expected to be signed shortly and reach financial close by the end of 2025, the next Annual Review will capture progress across both components. The program team made a decision not to include TIDES as part of this annual review, the rationale for this is outlined in the Annex and for the decision not to include process milestones.

The programme team will conduct a post-negotiation review (‘wash-up’) for TIDES to capture lessons learned.

The programme has been assessed as having met expectations, meriting a score of A. Delays were encountered in the delivery and installation of the solar kits – primarily due to logistical and weather challenges - these setbacks did not significantly compromise the achievement of intended outputs and outcomes. The implementing partner demonstrated adaptability in managing disruptions, and progress against key milestones has remained broadly on track. Since its launch in April 2024, the project has met expectations by installing over 4,900 solar household kits, 35 community systems (in schools, health centers, churches, and halls), and 64 solar streetlights across the Namatanai District of New Ireland Province.

Beneficiary feedback captured on the Pawa Bilong Niu Ailan (PBNI) project through field monitoring visit[3] suggest that, where installation has been completed, the solar kits are functioning effectively and delivering anticipated benefits in terms of energy access and community resilience. The programme continues to perform at a level consistent with its planned objectives. Feedback suggests household expectations around solar kits are rising. There is a clear and growing demand for solar systems that can handle more energy-intensive appliances such as refrigerator or cooler to support small business.
[3] Field monitoring visit conducted in March 2025 by a team from the British High Commission to five villages in the New Ireland Province. Data collected through structured interviews with 11 project beneficiaries.

Major lessons and recommendations for the year ahead

A full set of lessons and recommendations from the previous Annual Review can be found in Annex 3.

Lessons

Effective logistics planning and sustained local engagement are critical to the success of infrastructure projects in remote regions. The project faced challenges due to limited road infrastructure and weather disruptions, which impacted the transport of materials and equipment. A key lesson is the importance of conducting a detailed logistics review with all contractor parties prior to mobilisation to ensure alignment on cost, risk, and implementation realities. Additionally, more proactive and regular engagement with provincial and district-level stakeholders could have strengthened local coordination and improved delivery outcomes.

While PCEP is not currently deploying cutting-edge technologies such as AI-driven energy management, blockchain-enabled parametric insurance, UAV-based mapping, or solar-powered hydrogen mini-grids, this is a deliberate and context-driven choice. The programme’s focus is on proven, robust, and scalable solutions that are appropriate for the Pacific context, where infrastructure, regulatory frameworks, and technical capacity are still developing. To date our focus has been on piloting of potential innovations to the delivery model, such as developing approaches to sustainably dispose of e-waste generated from the solar kits[1], and trialling pay-as-you-go models[4].
[1] Furthermore, analysis will be funded into ways that the delivery model could leverages private finance, potentially leading to piloting promising approaches (though local conditions in PNG for leveraging private finance of this nature, such as microfinance, are challenging and so pilots may not be viable). This intention is to improve efficiency by enabling households who cannot afford a high upfront cost to sustainably access renewable energy and allow for greater household coverage with limited resources.
[4] Similarly, TIDES is innovative not in the range of technologies it employs but through its model to attract private finance.

PNG’s National Energy Authority has drafted an off-grid regulatory framework, but it has yet to be approved. This has caused uncertainty amongst donor partners on the legality of certain decentralised solar systems, such as mini grids. This has resulted in slower roll out of more advanced systems.

In projects operating in unfamiliar or high-risk contexts, it is essential to treat the logframe not as a static document but as a dynamic management tool. Projects in such environments are likely to encounter unforeseen challenges (e.g. logistical and environmental) that can affect delivery timelines, outputs, and assumptions. If the logframe is not regularly revisited, there is a risk that outputs and indicators will become misaligned with the reality on the ground. This can lead to misleading progress assessments, missed learning opportunities, and ineffective resource use. Regular logframe reviews help surface early warning signs, validate assumptions, and ensure the output indicators remain meaningful and achievable.

The negotiations of TIDES, a first-of-its-kind, blended finance facility in the Pacific took longer than anticipated. It involves a high degree of technical and legal specificity, with difficult trade-off decisions (such as on resourcing vs returns). Therefore, delays are likely, and this should have been anticipated when mapping out programming timelines. FCDO lacked clear guidance on negotiating DevCap instruments and the associated timelines, much of this expertise is contracted out or delegated to programme teams. A recommendation has been included to share some of these lessons across FCDO teams once the negotiations have concluded.

Recommendations

Following from the E-waste study, regular maintenance and strong community involvement is critical to ensure the sustainability of grant funded systems. FCDO and DFAT should support wider efforts to establish a national maintenance network, and more specifically must ensure that maintenance plans are built into every installation from the beginning. FCDO should also consider whether indicators can be added to monitor the implementation of recommendations from the e-waste study and ensure that a long-term evaluation is planned to assess the sustainability of projects.

Field monitoring confirms that installed solar kits are functioning well; however, rising beneficiary expectations highlight a growing demand for higher-capacity systems capable of powering energy-intensive appliances (e.g., refrigerators, coolers) to support livelihoods and small business development. Future programming should consider scalable distributed renewable energy (DRE) solutions that align with inclusive economic growth and long-term sustainability goals. Demand forecasting should allow flexibility for increased community load.

The programme team should utilise upcoming monitoring visits to Papua New Guinea highlight existing activity and better understand the challenges of operating in PNG.

IPRD should streamline SRO and PRO reporting arrangements, and greater private sector expertise should be sourced for the running and management of TIDES. A lesson learning event will be conducted once negotiations have concluded, to share learnings across FCDO teams.

FCDO and MFAT will shift to a different pattern of engagement on TIDES now that negotiations have neared conclusion and TIDES will begin implementation. This will involve closer coordination with HMGs existing instruments, a joint plan to reach first close and more advisory, rather than legal input.

Quarterly or milestone-based logframe reviews should be institutionalised. These should involve both the programme team and implementing partners. Review discussions should focus on; i) validity of assumptions and risks, ii) feasibility and relevance of output indicators, iii) emerging contextual changes that affect delivery, iv) adjustments to indicators, means of verification, or output definitions should be made where justified, v) documentation of these reviews should be incorporated into ongoing MEL records, forming the basis for more grounded and useful output-level analysis in future reviews.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

PCEP’s Theory of Change (See Annex 1 for full ToC) is designed across four broad intervention activities to deliver two key outcomes (below). The ToC is based on a strong evidence base outlined in the programme business case:

  1. Share of renewables in the national energy mix is increased.
  2. Access to electricity is increased, particularly of poor and marginalised communities.
2. Two implementing partners will deliver on the above outcomes which will lead PCEP to deliver the programme’s overall impact across several PICs (expected impact set out below):
  1. Reduced GHG emissions.
  2. Improved economic growth, health and poverty reduction from increased electricity use and deployment of savings from lower fossil fuel imports.
  3. Greater private sector investment in renewables beyond TIDES due to demonstration effects, improved risk perception and commercial understanding of the investment market.
3. The Theory of Change as set out in the original business case remains valid. However, despite initial delays we don’t envisage timelines will need to be revised.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme continues to progress in line with the expected outcomes and impact set out in the theory of change.

The programme team took the decision not to include an assessment of TIDES as part of this annual review as it is not operational. The Business Case Amendment for TIDES was agreed in February 2024. At that point, expectations were that negotiations on the package of legal documents – including, but not limited to, a Limited Partnership Agreement (LPA) – would be completed by December 2024. TIDES has not been set-up in the timeline we had expected, and we are now nearing the finalisation of the associated documents with the fund manager, CAMCO.

The programme teams experience of negotiating TIDES is captured in the recommendations above. There is a question whether these delays are due to underperformance or improve the programmes outcomes. As a result of extending negotiations, we estimate that FCDO has made estimated savings of over £750k outlined in the value for money section below.

Under the PKP component, the Pawa Bilong New Ireland project, implemented by the Kokoda Track Foundation, is making strong progress and is well on track for completion by July 2025. Since implementation began in December 2024, the project has already achieved 52% completion within four months, a significant milestone.

To date, 4,969 solar home systems, 35 community solar systems, and 64 solar streetlights have been installed across 42 of the 105 target villages. In addition, 336 solar champions have been trained to carry out installations and provide essential maintenance support, helping to ensure long-term sustainability. These results reflect the project's momentum and the positive impact it is beginning to have in improving energy access across New Ireland.

In this calendar year, PKP will aim to complete its target of delivering at least 9,530 new renewable energy products, predominantly household solar kits, and an additional 0.14MW of off-grid electricity capacity, contributing to PNG’s target to provide electricity to 70% of the population by 2030.

The PKP component has already delivered tangible benefits across several dimensions of community life. The field interviews are providing evidence to support this conclusion.

The field visits provide significant evidence of households spending less money on energy as a result of the new solar kits. Nearly all participants reported saving money previously spent on fuel for kerosene lamps or diesel generators, as well as disposable batteries for torches and radios. Most respondents plan to use these savings to improve housing or support their business activities. There is also emerging evidence gathered from field visits that indicate people are benefiting, as intended, from extended working hours thanks to lighting availability at night and in the early morning. People in communities are able to run canteens or craft-based businesses for longer.

The most profound impact of the solar kits is observed in the social dimension. The field visit’s respondents confirmed a strong impact on daily lives where they are now able toconduct household and community activities after sunset. Children now study at night, health workers can provide care during emergencies without relying on torchlight, and families can gather, socialize, or hold church services in the evening—activities that were previously constrained by darkness. Another unexpected but critical benefit has been improved community safety. Respondents overwhelmingly agreed that solar-powered street lighting has reduced incidents of theft, nighttime accidents, and wild animal encounters. This added sense of security, particularly for women and children, is a substantial social gain that ripples through the community.

The environmental benefits of the solar programme are recognised by communities, though perceptions vary around their significance. Several respondents acknowledged that shifting away from fossil fuels has reduced noise and air pollution. They also noted a reduction in battery and fuel waste—key contributors to local environmental damage, especially in rural areas with no formal waste disposal systems. However, some participants downplayed these benefits, arguing that their villages were never heavily polluted to begin with due to the absence of industrial activities. This view reflects a real context: while urban areas may see dramatic environmental improvements from cleaner energy, remote villages with minimal prior emissions perceive the shift as more symbolic than practical. That said, the introduction of renewable energy has clearly influenced attitudes toward sustainability in the benefiting communities, fostering a cultural shift that could be important for long-term environmental stewardship.

Kokoda Track Foundation (KTF) commissioned Equity Economics2 to undertake an external evaluation of their ‘Light for Learning Project’, a previous project by the same implementing partner of FCDO’s co-financed Pawa Bilong New Ireland (PNBI) project. The evaluation highlighted increased studying time for children, household savings from alternate energy sources, and reported improved respiratory health.

Our business case expectations were that PKP would also deliver mini-grids, alongside stand-alone solar and none are being delivered. Due to several constraints particularly on the regulatory side this is not yet happening. PNG’s National Energy Authority has drafted an off-grid regulatory framework, but it has yet to be approved. This leaves companies unsure whether they’re operating legally, how to set tariffs and whether their systems will be protected if the main grid later reaches their service areas. We will continue to work with DFAT and the PNG government to support these efforts

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the findings from the field visit monitoring report, along with our assessment of progress against the programme’s planned milestones and targets, there is sufficient evidence to support the continuation of the programme. While certain areas may require ongoing attention, the overall trajectory suggests that the programme remains relevant and has the potential to generate further results if sustained.

The PKP component of the programme makes an important contribution to the HMG Pacific Strategy, the UK-Australia Strategic Infrastructure and Development Dialogue and delivers on the AUKMIN 2022 commitment.

The TIDES component was referenced in the Joint Statement[5] issued following the meeting between the United Kingdom and New Zealand Prime Ministers in London on 22 April 2025. In the statement, both leaders reaffirmed their commitment to promoting the prosperity, security, and resilience of Pacific Small Island Developing States. As part of their shared response to climate change, leaders welcomed joint efforts on the TIDES renewable energy investment fund.
[5] Joint statement between the Prime Minister of the United Kingdom and the Prime Minister of New Zealand - GOV.UK

## C.DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Increased off-grid energy access in rural off-grid communities
Output number:		1	Output Score:	B
Impact weighting (%):		60%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Additional number of renewable energy products installed by FCDO funded PKP grants.	9,501 solar household systems / 80 community solar kits / 160 solar streetlights	Partially met: / The installation of solar equipment to date includes: / 7,004 solar household systems / 47 community systems (installed in 18 schools, 3 health facilities, 11 churches, 2 community halls) / 89 solar streetlights
1.2 Additional installed off-grid clean electricity capacity (MW equivalent)	0.14 MW	Partially met: / The project has installed: / 0.1050MW in solar household systems / 0.0015MW in community systems / 0.0016MW in streetlights / A total 0.1081MW has been installed in the communities between since the commencement of installations in December 2024
1.3 Cost (AUD) per solar system installed	New milestone. No milestone for this indicator since it provides qualitative information	Household system - AUD364.29 / Community system - AUD3,042.29 / Solar streetlight - AUD3,327.51
1.4 Examples of Value for Money delivered by ESIP and partners	New milestone. No milestone for this indicator since it provides qualitative information	Several strategic adaptations were made to enhance cost-effectiveness and delivery outcomes. The project shifted to using contractor installation teams to reduce the risk of systems not being installed by homeowners, ensuring timely deployment. The solar champion model was scaled up significantly (from 38 initially planned to an estimated 840 across 105 villages) enhancing community-based maintenance capacity. Training now includes long-term basic maintenance, supporting the sustainability of installations. Bulk equipment procurement was optimised by distributing costs across two sites (Namatanai and Rai Coast), and lessons from a similar initiative in Madang Province informed improvements in rollout efficiency and effectiveness.

Briefly describe the output’s activities and provide supporting narrative for the score.

Progress against this output – the additional number of renewable energy products installed – is partially met. However, the delivery partner expects the target to be achieved by July 2025. The installation of all solar equipment including household systems, community systems and streetlights commenced 8 months after contract signing in April 2024. Between December 2024 and April 2025, the project completed an average of over 50% of the planned installations. This slower-than-planned deployment has directly contributed to Indicator 1.2 – additional installed off-grid clean electricity capacity – falling short of its expected level.

This output has been given a score of B, indicating that outputs moderately did not meet expectations. The B rating is justified as 73% of installations have been completed over five months, the delivery partner has provided assurance that the remaining will be implemented more rapidly in the coming months. Furthermore, while the cost of solar systems is not explicitly quantified in the programme’s logframe, the unit cost of a home solar system charged to the programme budget is AUD 364.29, which is significantly more cost-effective than the market price of AUD 800 (see article Electrifying PNG: Challenges and opportunities for decentralised solar – Post Courier. This cost efficiency strengthens confidence in the value for money of the intervention, reinforcing the positive outlook for full delivery by July 2025. This cost efficiency strengthens confidence in the value for money of the intervention, reinforcing the positive outlook for full delivery by July 2025.

Delays have primarily been caused by a combination of adverse weather and logistical constraints. Prolonged periods of rain and rough sea conditions disrupted transportation and delayed both delivery and quality checks. Key sections of the planned transport routes were found to be unfit for heavy loads, including bridges unable to support container side lifters. In response, the partner adapted by breaking down shipments into smaller loads, allowing deliveries to continue. Rainfall also made several roads temporarily impassable. Limited storage capacity created further delay. These issues are now being managed by the partner through improved coordination with logistics contractor.

The delivery partner was able to demonstrate value for money in this project by applying a lesson learned from implementation in the previous project. Based on that experience, the delivery partner implemented a revised model for the solar champions by employing dedicated installation teams. These teams were not only responsible for system installations but were also trained to deliver community-based training. As part of this process, they successfully trained a defined number of solar champions in each village, ensuring local ownership, sustainability, and basic maintenance for the systems after installation. This approach not only enhanced coordination and operational efficiency but also enabled installation teams to deliver the systems directly to the villages. This direct delivery mitigated the risk of equipment damage or potential resale that could arise from centralised distribution.

To verify the findings the team undertook a field visit to gather qualitative evidence, which included semi-structured interviews and site observations with beneficiaries, community leaders, and solar champions across selected villages. As this was not a structured survey, recommendations and conclusions should be interpreted as indicative rather than statistically representative. The field visits were guided by an initial set of draft questions (Annex 4) developed by IPRD’s economic adviser and MEL adviser and were conducted by two members of the embassy team. A total of 11 interviews were conducted across five different villages and cross section of participants (Age, Gender, Occupation) with each interview reflecting the unique background and perspective of the participant.

Overall, the sentiment across all interviews was overwhelmingly positive. Beneficiaries expressed appreciation not only for the practical benefits the kits bring but also for the respect and care shown in the distribution and installation process. They noted that the programme has improved living conditions, supported family well-being, and contributed to a stronger sense of community.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Two new VfM indicators (1.3 and 1.4) related to this output are being measured to better assess the effectiveness and efficiency of the output (see value for money section D). There were no changes to the output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous AR for this output.

Two new VfM indicators were introduced. However, the absence of quantitative milestones limited the ability to track progress against these indicators. In future, VfM indicators should be accompanied by clear and measurable milestones from the outset to enable meaningful monitoring and reporting.

Output Title	Sustainability of the increased off-grid energy access in rural off-grid communities
Output number:		2	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review		Progress
2.1 Number of beneficiaries trained to maintain and sustain the off-grid hardware.	38		Exceeded: / 440 (female:168, male:168)
2.2 Number of people benefiting from capacity building in grant management.	6		Exceeded: / 12 people have been trained from the capacity building activities / ESIP conducted 1x Client Mandated Conditions training with a total of 4 participants (3 females and 1 male) and 1x Contract Management session with a total of 8 participants (5 females and 3 male).

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is to ensure the sustainability of off-grid energy access, with a focus on strengthening local capacity to operate, maintain and manage installed systems. Progress against this output is on track, with both indicators exceeding their respective targets.

There has been strong uptake of training with 440 people trained to maintain and sustain the off-grid hardware. The training equipped beneficiaries with practical skills to maintain off-grid systems, reducing reliance on external technicians and creating a sense of local ownership. In parallel, capacity building for the delivery partner in grant management has strengthened their ability to oversee community-level energy funds, improving budgeting and accountability.

A factor in the programme’s success has been the focus on local capacity for maintenance. All interviewed beneficiaries knew how to contact their village's solar champion—local individuals trained to assist with technical problems. This model of community-based technical may enable long-term sustainability. It should reduce dependency on external technicians and encourage communities value the equipment. Moreover, it strengthens local leadership and enhances trust in the programme’s ability to deliver reliable services.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The training and installation approach was revised based on lessons from the ESIP Madang project, where managing 38 individuals centrally created coordination challenges. To improve efficiency, KTF engaged staff organised into two five-member installation teams, enabling direct delivery to villages and reducing the risk of damage or resale. These teams were trained in technical installation, WHS, and safeguarding, and supported the training of 8 solar champions in each of the 105 villages scaling up to an estimated 840 champions. This decentralised model enhances community capacity for long-term maintenance and ownership of the systems.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Not Applicable

Output Title	E-waste management model piloted
Output number:			3	Output Score:		A
Impact weighting (%):			5%	Weighting revised since last AR?		N/A

Indicator(s)		Milestone(s) for this review			Progress
3.1 E-waste case study developed		Number of e-waste case study			Met - a case study has been developed and presented to FCDO in March 2025

Briefly describe the output’s activities and provide supporting narrative for the score.

A study on e-waste from Solar Home Systems (SHS) and mini grids in Papua New Guinea (PNG) was commissioned and delivered by Pricewater house Coopers (PwC), a consulting company. It aims to address the challenges and opportunities associated with the disposal and recycling of solar home systems (SHS) and mini-grids, which are crucial for electrification in remote areas. Improper disposal of e-waste, such as burning, sea dumping, and burial, poses significant environmental risks by contaminating ecosystems, threatening human health, and undermining efforts towards sustainable consumption and production, The study draws on global evidence of serious health risks, such as in Ghana and Nigeria, and applying it to the PNG context.

The study involved in-country fieldwork, stakeholder consultations, and a dissemination session in PNG for FCDO and others. It outlined the scale of the issue in PNG, assessed current disposal practices, and provided practical recommendations to strengthen environmental safeguards as clean energy efforts scale up.

It is widely recognised that e-waste remains a concern for PNG and this output was welcomed by those involved in delivering energy systems. There are no simple solutions to the disposal of e-waste in PNG, but the study provides recommendations for tackling the issue for future phases of the programme.

To strengthen e-waste management in Papua New Guinea, it is recommended that FCDO and other international donors support the development and implementation of a clear labelling system for off-grid solar products. Such a system would help consumers understand safe disposal methods and associated health risks, promoting responsible end-of-life practices at the community level. Complementing this, donors should invest in locally tailored education and awareness programmes that equip communities with the knowledge and tools to manage e-waste sustainably. Partnering with government agencies, NGOs, and other local stakeholders will be essential in establishing effective, context-specific collection and recycling systems suited to the needs and realities of rural PNG.

The study was high quality, and strategically aligned, justifying a score of A.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The indicator for this output should now be updated to monitor progress on pilot activities initiated as a result of the e-waste study under this programme or by others.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous AR for this output.

Output Title	Off-grid projects funded by FCDO
Output number:		4	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of FCDO-funded off-grid projects	1	Met: 1x project being implemented / The current Namatanai project is on track for completion in June 2025

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The Pawa Bilong Niu Ailan (New Ireland) project is the only FCDO funded off-grid project managed by Economic and Social Infrastructure Programme (ESIP). The project includes distributing and installing solar systems and streetlights in Namatanai District, New Ireland Province. Achievements made by this project are mentioned in outputs 1 and 2 The project is at 45% completion (on average) with implementation over a four-month period starting in December 2024. It is on track for completion in July 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There were no changes to the output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Not Applicable

Output Title	Grantees capacity building activities delivered
Output number:		5	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of capacity building activities delivered	10	Partially met: Two capacity building training conducted / ESIP conducted: / 1x Client Mandated Conditions training with from the supplier and installer a total of 4 participants (3x females and 1x male) / 1x Contract Management training at the start of the project with a total of 8 participants (5x female and 3x male)

Briefly describe the output’s activities and provide supporting narrative for the score.

1. The Client Mandated Conditions sessions with the contractors covered areas in Health, Safety and Environment (HSE), Gender, Equality, Disability and Social Inclusion (GEDSI), CCDR (Climate Change and Disaster Resilience), Child Protection, PSEAH (Preventing Sexual Exploitation, Abuse and Harassment), Work Health and Safety (WHS), fraud and anti-corruption controls, risk management and other compliance aspects. ESIP conducted one training session and held continuous assessments and improvements to the plans that had been developed for the project from this session. The WHS plan, GEDSI plan, risk management plan and other plans continue to be revised and improved through ESIP’s engagement with the contractors. The contract management training was conducted to ensure that the contractors understood the change from a grant agreement to a commercial arrangement under a subcontractor agreement.
2. The output has not met the milestone for this period, however the amount of training delivered is meeting the requirements for the programme. Additional training is not required unless the programme is scale up.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes were made to the output. ESIP was required to familiarise the contractor with the contract terms and conditions, as these differed from previous arrangements.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The milestone target for the next AR should be set in relation to the project size as there is currently no need for additional training of contractors. The day-to-day monitoring/assessments and improvements with the contractor may be sufficient. Alternatively this output could be replaced with another indicator more relevant to the future delivery of the programme.
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

Economy:

The primary cost driver for PKP is the procurement of Photovoltaic (PV) kits. To ensure value for money and maintain quality, bulk purchases were made from suppliers adhering to recognised quality standards and offering appropriate warranties. This approach helped lower average costs despite inflationary pressures, particularly in shipping and in-country logistics. Affordability remains a key barrier, with typical home solar systems in the market costing between AUD 775 to AUD 1,075. However, through bulk procurement, the project secured household systems at AUD 364, demonstrating strong value for money. Similarly, solar streetlights were procured at AUD 3,327 each, significantly lower than the AUD 4,700 cited in public sources such as Cost Comparison Between Solar vs. Traditional Lights.

Efficiency:

Delivering this programme through an existing DFAT programme creates large savings for the UK. PKP has been running for 3 years, and FCDO has avoided the costs of starting up a new programme. There are certain recurrent costs that would be duplicated were FCDO to establish a standalone programme, such as staff time spent overseeing PKP (a service DFAT is providing without any charge), due diligence, and monitoring. DFAT also conducts Partner Performance Assessments (PPA) on contractor’s performances and DT Global, the managing agent for PKP, has received the highest rating for the previous three years, including on value for money. The PKP programme is part of Australia’s broader ESIP initiative, which enables FCDO to leverage DFAT’s established networks and expertise in PNG to improve delivery efficiency. While DT Global has encountered some engagement challenges with PKP, project delivery remains unaffected. FCDO will continue to monitor the partnership and explore ways to strengthen alignment.

The FCDO has achieved estimated savings of over £750,000 through extended negotiations with TIDES. Primarily due to the following key concessions:

  1. Management Fee Reduction:
    1. Camco agreed to a revised fee structure of 2.25% during the investment period and 1.75% post-investment. Resulting in an average fee of 2% from an initial 2.5%.
    2. Fees will be applied to committed capital rather than total capital, further reducing overall costs.
  2. Establishment Cost Cap:
    1. A $2 million cap on establishment costs has been agreed.
    2. Camco will offset costs incurred to date, with remaining costs handled on a pass-through basis.
  3. Resourcing and Return Adjustments:
    1. A floor on resourcing has been agreed, with LPAC reporting in place to ensure sufficient resourcing despite fee reductions.
    2. In exchange, FCDO accepted a lower waterfall return in the medium term.
Effectiveness:

Since its launch in April 2024, PCEP has met expectations in delivering tangible results while progressing toward its intended outputs. Over 4,900 solar household kits, 35 community systems, and 64 solar streetlights have been installed across Namatanai district, transforming daily life by reducing diesel reliance, extending productive hours, and improving safety, particularly for women and girls. These energy access gains have enabled evening activities, enhanced school and medical centre operations, and supported local SMEs. Alongside delivery, the programme has advanced energy sector policy reforms, project preparation, and pipeline development. Initiatives such as the e-waste study and planned solar product labelling demonstrate responsiveness to sustainability risks. The results framework continues to guide adaptive management and evidence-based course correction.

Several strategic adaptations were made to enhance cost-effectiveness and delivery outcomes. The project shifted to using contractor installation teams to reduce the risk of systems not being installed by homeowners, ensuring timely deployment. The solar champion model was scaled up significantly (from 38 initially planned to an estimated 840 across 105 villages) enhancing community-based maintenance capacity. Training now includes long-term basic maintenance, supporting the sustainability of installations. Bulk equipment procurement was optimised by distributing costs across two sites (Namatanai and Rai Coast), and lessons from a similar initiative in Madang Province informed improvements in rollout efficiency and effectiveness.

Equity:
The programme remains focused on ensuring benefits reach remote and underserved communities, particularly through its support for off-grid and decentralised energy solutions. Gender and social inclusion principles are mainstreamed into programme design, with capacity-building efforts targeting women and marginalised groups, especially in community-based energy planning.

Cost Effectiveness: It's too early to measure this component of VfM
In summary, PCEP continues to deliver good VfM, with evidence of adaptive programming, strategic cost management, and a focus on delivering sustainable, inclusive, and resilient clean energy outcomes across the Pacific.

VfM performance compared to the original VfM proposition in the business case

The delays in PV kit delivery has postponed some benefits of the programme by 2 months thereby reducing the programme’s value for money. The project will deliver the original business case targets, with no significant changes to the theory of change or underlying assumptions. VfM will continue to be monitored across the 5 Es, with regular reviews of the business case and partner agreements to ensure alignment.

The Business Case Amendment for TIDES was agreed in February 2024. At that point, expectations were that negotiations on the package of legal documents – including, but not limited to, a Limited Partnership Agreement (LPA) – would be completed by December 2024. TIDES has not been set-up in the timeline we had expected, and finalisation of the associated documents with the fund manager, CAMCO, is expected in June 25’.

The delay in establishing the TIDES fund has ultimately strengthened Value for Money (VfM) outcomes. By taking additional time to get the fund structure right, FCDO secured significant financial and strategic benefits. Notably, management fees were reduced from 2.5% to 2.25%, establishment costs were halved from $4 million to $2 million, and overall savings to FCDO are estimated between £500,000 and £1 million. These outcomes reflect improved financial prudence and cost-efficiency. Furthermore, the revised equity dividend structure enhances investor appeal while safeguarding UK development objectives, reinforcing the fund’s strategic alignment. In this context, the delay has proven beneficial for VfM by enabling stronger governance, better financial terms, and a more resilient fund design.
Key financial savings – TIDES fund setup

The following table summarizes the key financial savings achieved during the setup of the TIDES fund, highlighting their impact on Value for Money (VfM) for FCDO.
Area	Original Terms	Revised Terms	Estimated Savings	VfM Impact
Management Fees	2.5%	2.25%	Ongoing cost reduction	Lower operational costs improve long-term efficiency.
Establishment Cost Cap	$4 million	$2 million	$2 million	50% reduction in upfront costs enhances financial prudence.
Equity Dividend Structure	Less balanced	More balanced	—	Attracts private investors while safeguarding UK development objectives.

Assessment of whether the programme continues to represent value for money

This project continues to represent value for money.

E: RISK

Overview of risk management

In accordance with risk management best practise, the PCEP team regularly assesses programme risks, updates the risk register and checks on risk appetite. The overall risk has remained Major to date. TIDES is a frontier investment and will target new segments of the renewable energy market which traditionally struggle to attract private sector investment. Additionally, many PICs have constraints on attracting private sector investment such as smaller market size.

The identified risks are being assessed on a quarterly basis or earlier if a change in context so demands, mitigation strategies are reviewed by the team and strengthened as required. All risks are within the appetite of the Indo-Pacific Regional Department’s (IPRD) Portfolio Risk Register.

One of the key risks in the programme is ensuring there is an investible pipeline of developer led clean energy projects which meet UK requirements. For PKP, an additional risk is the end-of-life considerations when batteries die and the secondary environmental concerns, they may generate3

For TIDES, there is a risk that the time required to establish the fund goes beyond donors’ financial year affecting budget availability. This risk is currently being mitigated through regular meetings between MFAT, FCDO and the fund manager CAMCO. At present this risk is assessed as being within appetite.

The programme is aligned with the Paris Agreement, supporting Pacific Island Countries (PICs) to pursue a low-carbon development pathway. The programme contributes to emissions reduction through expanded renewable energy access, reduced reliance on diesel, and cleaner construction practices. PCEP will not fund fossil fuel investments and is committed to supporting the renewable energy transition in the region. There is also a key modern slavery risk due to the existing solar supply chain, FCDO continue to work closely with DT Global and have assessed their approach to managing this risk.

While climate and environmental risks are currently assessed as low, a potential medium-term risk relates to the generation of e-waste (e.g. expired batteries and solar components) from PCEP. To mitigate this, the programme commissioned an e-waste study and will promote environmentally sound disposal practices, including labelling, awareness campaigns, and recycling where feasible. All implementing partners are required to monitor environmental impacts and apply safeguards to avoid unintended harm. PCEP will continue to review environmental risks throughout the programme lifecycle and take action to ensure continued compliance with the Paris Agreement and FCDO’s climate and environment commitments.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Delivery

The delivery, commercial and financial performance is on track. The programme risk register is updated quarterly, and all new developments are highlighted to the senior management. The team applied for removal of exclusion restriction for publishing the documents in March 2025 and later published the Business Case, Log Frame and last Annual Review on the DevTracker in line with the Programme Operating Framework compliance.

The team has ensured regular communications and engagement with DFAT, MFAT, Camco, and FCDOs Pacific Development Unit and relevant posts across the network to review progress. The delivery partners were well-resourced and maintained strong governance structures and reporting mechanisms

The PROs visit to Papua New Guinea and UK High Commissioner to PNG to New Ireland enabled discussions between KTF and FCDO and provided visibility for the UK.

PKP has made substantial progress in delivering off-grid solar solutions to remote communities in New Ireland Province, PNG, though some output targets have only been partially met to date. As of the latest reporting period, the project has installed:
7,004 solar household systems (against a target of 9,501)

47 community systems (target: 80), installed across 18 schools, 3 health facilities, 11 churches, 2 community halls, and 89 solar streetlights (target: 160).

This represents a significant scale-up in access to clean energy, with a total of 0.1081 MW of off-grid solar capacity installed since December 2024 (comprising 0.1050 MW in household systems, 0.0015 MW in community systems, and 0.0016 MW in streetlights).

1. To enhance delivery and value for money, the project adopted several strategic adaptations:
  1. Contractor installation teams were used to reduce the risk of non-installation by homeowners, ensuring timely deployment.
  2. The solar champion model was significantly expanded from 38 initially planned to an estimated 840 across 105 villages, greatly strengthening community-based maintenance and sustainability. Training for solar champions now includes long-term basic maintenance.
  3. Bulk procurement was optimised by distributing equipment costs across two sites (Namatanai and Rai Coast), and lessons from a similar initiative in Madang Province were incorporated to improve rollout efficiency.
  4. Beneficiary feedback from field monitoring remains highly positive, with reported improvements in household finances, safety, and community resilience. However, logistical challenges and regulatory uncertainty have affected the pace of delivery, particularly for more advanced systems.

TIDES remains in the pre-operational phase, with delivery focused on establishing the fund’s legal and governance framework. The negotiation process has been more complex and time-consuming than anticipated, reflecting the innovative nature of the facility and the need to secure robust safeguards and oversight arrangements. Key milestones include the Business Case Amendment (February 2024), commencement of legal negotiations (March 2024), and the anticipated completion of Limited Partnership Agreement (LPA) negotiations in July 2025.

The decision to exclude TIDES from formal output scoring in this review was agreed at a programme team kick-off meeting, with formal Terms of Reference drafted and consensus reached. A narrative update is provided, and a post-negotiation review is recommended once the fund is operational.

Commercial performance

The project has two commercial contracts in the reported period of the Annual Review:

The Off-grid Solar E-waste study was contracted directly through the internal Expert Advisory Call Down Service (EACDS2). PwC was contracted and the activity is completed.

FCDO initiated the process to contract legal representation for negotiations on TIDES, otherwise now known as TIDES, through Framework schedule 6 Crown Agent Service Agreement. We received bids from 3 legal firms, and one firm was shortlisted, and the contract was signed.
Financial Performance

1. PCEP programme team undertakes financial management and tracks financial expenditure monthly. The forecasts and disbursements are on track against the allocated funds and monitored monthly along with the IPRD finance manager.
2. This year focused on mobilisation and the programme is profiled to reflect that. In this FY 2024-25, funds have only been disbursed for the PKP component to DFAT and PWC, as shown in the table below.

RDEL 2024-25	CDEL 2024-25	Total Contribution Paid 2024-25
xxxxx	xxxxxx	xxxxxx

To date (2023-24 and 2024-25) total spend is £xxxx including £xxxx CDEL and £xxxx RDEL. In FY 25-26, programme has a budget of £xxxx (£xxxx RDEL and £xxxx CDEL). 92% of this is forecasted under TIDES agreement expected to be signed in May/June 2025.
Assets

Solar kits were purchased by PKP as part of the programme in first year of implementation. These are non-returnable and distributed to beneficiaries.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

PCEP developed different MEL arrangements for its two core components, with FCDO ensuring regular cross-component learning, including through structured reflection during annual reviews.

Under the PKP component, DFAT leads on monitoring and evaluation for the Pawarim Komuniti programme, with results attributable to UK funding clearly identified. FCDO’s MEL advisor collaborated with DFAT to agree on a results framework that includes relevant ICF KPIs and indicators to assess environmental impacts such as e-waste from household solar kits. Data will be disaggregated by gender, disability (where feasible), and adult/non-adult, acknowledging local demographic data limitations.

DFAT will continue to deliver MEL activities under PKP, which will be reported in the next Annual Review.

For TIDES, FCDO has procured a private MEL firm in New Zealand through competitive procurement to evaluate performance of the fund. Progress against this will be assessed in subsequent annual reviews.

On completion, a single overall logframe will be developed as a tool for FCDO to assess and manage PCEP’s performance

Learning

PCEP has commissioned two studies as part of PKP. One through PWC to look at off-grid Solar E-waste in Papua New Guinea, using Pawarim Komuniti as a case study and another through DFAT on providing a qualitative review of existing community-managed renewable energy systems in consultation with the PNG National Energy Authority. Both are expected to generate programmatic evidence which will inform future activities and will be distributed widely.

FCDO will also leverage social development advisory support to commission additional GEDSI analysis where relevant.

Date of last narrative financial report	N/A	Date of last audited annual statement	N/A

Abbreviation List
AR	Annual Review
AUKMIN	Australia UK-Ministerial
CCDR	Climate Change & Disaster Resilience
CDEL	Capital Expenditure Delegated Limit
C&I	Commercial & Industrial
DCA	Delegated Cooperation Agreement
DFAT	Australian Department of Foreign Affairs & Trade
ESIP	Economic & Social Infrastructure Programme
FCDO	Foreign Commonwealth & Development Office
FY	Financial Year
GEDSI	Gender, Equality, Disability & Social Inclusion Analysis
GHG	Green House Gas
ICF	Investment Climate Fund
IPRD	Indo Pacific Regional Department
KPIs	Key Performance Indicators
KTF	Kokoda Track Foundation
MEL	Monitoring Evaluation & Learning
MFAT	Ministry of Foreign Affairs & Trade
NZ	New Zealand
ODA	Oversees Development Assistance
PCEP	Pacific Clean Energy Programme
PDU	Pacific Development Unit
PICs	Pacific Island Countries
PKP	Pawarim Komuniti
PKP
Pawarim Komuniti Partnerships
PNBI	Pawa Bilong New Ireland
PNG	Papua New Guinea
PPA	Partner Performance Assessment
PRO	Programme Responsible Owner
PV	Photovoltaics
PWC	Pricewaterhouse Coopers
RDEL	Resource Delegated Expenditure limit
SRO	Senior Responsible Owner
TEA	Transforming Energy Access
TOC	Theory of Change
UK	United Kingdom
VfM	Value for Money

Annex 1: Theory of Change
Activities			Outputs		Outcomes		Impacts

Market building / Early-stage project preparation. / Technical assistance for developers, governments, and financial institutions. / Financing / Capital for construction and installation in PNG. / Capital for blended finance to fund construction. / Capital for developers to develop projects. / Stakeholder engagement / UK and international diplomacy supports programme objectives. / FCDO-DFAT collaboration. / Demonstration and learning / Lesson learning and knowledge generation. / Data collection, monitoring and evaluation.			Increased number of bankable clean energy projects developed. / Increased capacity of energy sector institutions to plan and set policy. / Increased capacity of solid waste management service providers to manage e-waste. / Lower project cost of capital. / Data, analysis and learning products on renewable energy needs and investment market in PICs produced. / Household and community solar systems installed.		Share of renewables in the national energy mix is increased. / Access to electricity is increased, particularly of poor and marginalised communities. / Intermediate Outcomes / Increased clean energy generation and distribution capacity. / Improved energy planning and engagement from local and governmental institutions. / Capable developers able to bring projects to financial close.		Primary impacts / Reduced GHG emissions. / Improved economic growth, health and poverty reduction from increased electricity use and deployment of savings from lower fossil fuel imports. / Greater private sector investment in renewables beyond TIDES due to demonstration effects, improved risk perception and commercial understanding of the investment market. / Secondary impacts / Strengthened UK – PIC and Australia bilateral relationships in the region. / Strengthened economic security and economic partnerships across the Pacific.

			Assumptions: / FCDO maintains capability to manage programme. / Poor households without electricity access identified. / TIDES fund manager identifies developers able to navigate the complex political economy of PICs, and they are interested in entering into a longer-term partnership. / Sufficient additional project proposals are developed to absorb the financing space created by PCEP. / The projects covered by PCEP would not have been developed and financed within the next 7 years without PCEP. / Lessons learning from previous energy programmes in PNG are applied to PKP component. / Communities are willing to participate in maintenance of off-grid solar		Assumptions: / Adequate incentives are created for the fund manager to use TIDES resources to invest in projects/locations targeting poor and marginalised groups. / Political will on the part of PIC governments to address critical policy or regulatory barriers to investment. / Other donors are willing and able to provide finance so the TIDES reaches financial close. / Private investors are willing to invest in TIDES so that it reaches financial close. / Once energy assets are operational the debt can be refinanced, new investors provide finance on the basis of the financial information generated and some projects are sold. The capital can be recycled into new projects. / Projects supported by PCEP are well-designed and successfully implemented in a timely fashion.		Assumptions: / Projects supported by PCEP deliver expected results / Diesel exporter don’t divert all the reduction in exports to PICs to other markets. / Tariffs set at affordable levels for end users. / Savings from lower expenditure on fossil fuel used productively for social or economic purposes. / The private sector is willing to learn about renewables investment performance, local geographies and governance in PICs / The investment climate in PICs improves and private investors are willing to increase financing for renewable energy in PICs. / PCEP is large enough and sufficiently well performing to strengthen UK – PIC and Australia bilateral relationships.

Annex 2
Programme media and communications to date.
Papua New Guinea Clean Energy Investment (PKP)

Media article drawing the press release the PNG high commission circulated after their field visit at the end of March: UK-AUSTRALIA PARTNERSHIP BRINGS SOLAR ENERGY TO NEW IRELAND, ENHANCING COMMUNITY WELL-BEING – EMTV Online

Media announcing the partnership: Australia and UK Collaborate on Major Solar Energy Project in Papua New Guinea - Papua New Guinea Today

Project brief about the FCDO-funded component in Pawarim Komuniti Partnerships website: Pawa Bilong Niu Ailan - Pawarim Komuniti Partnerships

Flyer that features the FCDO-funded project in New Ireland.

- Social media post announcing the partnership:
  - Post by the UK High Commission in PNG
  - Post by the Australian High Commission

Regional Clean Energy Fund (TIDES)

- Why the UK’s foreign office is backing a $100m blended finance climate fund in the Pacific Islands | Netzeroinvestor
- Joint statement between the Prime Minister of the United Kingdom and the Prime Minister of New Zealand - GOV.UK
- UK secures another signatory for its ‘Shadow Fleet’ call to action as New Zealand and UK Foreign Secretaries pledge closer cooperation - GOV.UK
- NZ and United Kingdom strengthen partnership | Beehive.govt.nz
- UK and NZ pledge GBP 23.9m to support Camco’s blended finance fund for the Pacific
- Joint statement between the Prime Minister of the United Kingdom and the Prime Minister of New Zealand

Annex 3: Annual Review 24-25 Lessons and Recommendations

Recommendation 1: Agree log-frame for PKP in the two months after the AR. We will work with DFAT to include relevant VFM indicators in the proposed logframe. The PCEP progamme team should agree process milestones for TIDES in the logframe.	Actioned. A log-frame was agreed with DFAT which included VFM indicators. Delays in set-up resulted in no progress milestones for TIDES, outlined above.
Recommendation 2: DFAT should use the quarterly meetings (steering group) governance processes for approval on FCDO co-financing in future years as outlined in the business case. The PCEP programme team will work with DFAT to carry out bespoke tenders to match FCDO interests and will develop a rolling workplan. We will leverage the PROs visit to Papua New Guinea in June to agree activities for the next FY.	Actioned. These are now monthly meetings. They include DFAT, the managing contractor, IPRD and Post. FCDO now specify specific requirements which DFAT use for their call for proposal. PK’s refresh to PKP has meant that the pipeline for 24/25 was agreed in February 25.
Recommendation 3: FCDO and MFAT should continue regular bi-weekly engagement on TIDES to progress negotiations. We will assess the VFM case of conducting in-person negotiations given time zone constraints.	Actioned. In person negotiations took place in Fiji July 24’. MFAT, FCDO, and Camco have continued weekly negotiation updates to progress. PDUs climate adviser in NZ keeps in regular contact with MFATs TIDES lead.
Recommendation 4: Organise a presentation for the FCDOs Pacific network on TIDES. The PCEP team will develop several communications products for internal and external stakeholders. We will also work with our network to leverage existing donor coordination meetings.	Partially Actioned. The programme team organised a presentation for FCDOs pacific network. PDUs climate adviser in NZ keeps the network informed on latest developments. A set of communication products were developed for the launch. / The programme team aim to refresh our internal products this year. This has been captured in this year’s Annual Review.
Recommendation 5: On PKP, FCDO and DFAT should agree a joint communications strategy for a June launch event and monitoring visit to coincide with the programme PRO and Senior Economist visit to PNG.	Actioned: See details in Annex 2.
Recommendation 6: The Transforming Energy Access (TEA) platform focuses on early-stage testing and scale up of clean energy innovations provides a complementary programme to PCEP and a potential end-to-end offer for renewable energy in the Pacific. This, and other programmes, provide an opportunity for teams to create semi-formal coordination mechanisms as the blended finance facility is set up and leverage complementary activities. / Recommendation 7: A political economic analysis of renewables in Pacific Island Countries has been done and was drawn on by the business case but did not address the implementation challenges. In coordination with DFAT and PDU, the team should look to undertake some political economy analysis of the implementation challenges and risks that the programme will face.	Actioned: PCEP is formally part of the Ayrton Fund coordination mechanisms. PCEPs PRO and PDUs climate adviser are in close coordination with the TEA team on overlap and complementary activities. This is likely to increase during the setup of TIDES. / Not Actioned: Further engagement with DFAT highlighted that a bespoke analysis would not add value.

Annex 4: Questions for PBNI Field Visit

Economic Impact

1. How much did you spend on energy sources (e.g., kerosene, batteries) before receiving the solar kit? Did you spend a lot, little, or nothing?
2. How did you get electricity before the solar was installed?
3. What are the main issues or challenges with your previous energy source?
4. How much do you spend on energy sources now?
5. Have you noticed any savings in your household expenses since receiving the solar kit?

Increased Income
1. Have you been able to increase your household income since receiving the solar kit? If yes, how?
2. Have you started any new business activities or expanded existing ones due to the availability of solar energy?

Ecological Impact

1. Have you noticed any changes in your community's environment since the introduction of solar kits (e.g., reduced use of kerosene, less waste)?
2. How has the availability of solar energy affected your daily life and activities? Has the solar kit improved your ability to study, read, or engage in social activities after dark? Do you have better access to TV/radio/phone/internet?
3. Have you felt safer at night since receiving the solar kit?

Energy Access and Usage

1. How often do you use the solar kit, and for what purposes (e.g., lighting, charging phones)?
2. Does the solar power cover all your needs, or do you still use other sources of energy? For example, do you still use candles, kerosene, or generator?
3. Have you experienced any issues with the solar kit? If so, what were they and how were they resolved? Are there things you would like to use solar power for but can't right now? For example, running a refrigerator, a water pump, or more lights?

Sustainability and Maintenance

1. Have you received any training on how to maintain and repair the solar kit?
2. Do you feel confident in your ability to maintain the solar kit, or do you need additional support?
3. How do/would you dispose of the solar kit components when they are no longer usable?

Satisfaction and Suggestions

1. Overall, how satisfied are you with the solar kit provided by the project? If you could do one more thing to improve energy access, what would it be?
2. What improvements or additional features would you suggest for the solar kits?

Annex 5: TIDES Component: Coverage, Process, and Reporting

Certain elements of spend, particularly those related to the legal and set-up costs for TIDES, have not been fully scored or assessed in this review. The rationale for this approach is that TIDES is not yet operational; and therefore, it was difficult to assess delivery against output or outcome milestones at this stage. Equally, the team did not have confidence in a set of process milestones to assess 6 months prior to the annual review.

Instead, we have focused on reporting progress, challenges, and lessons learned from the negotiation and set-up phase. This approach ensures transparency about what FCDO funding has supported so far, while avoiding premature scoring of activities that are not yet delivering results.

The time taken to establish TIDES: The negotiation process has been complex, involving multiple parties and legal instruments. Key milestones in the process have included the agreement of the Business Case Amendment (February 2024), the start of legal negotiations (March 2024), and the anticipated completion of Limited Partnership Agreement (LPA) negotiations in July 2025. While the time taken to reach agreement was longer than planned, these outcomes represent a better value proposition for FCDO and strengthen the fund’s ability to deliver on its strategic aims.

The additional time allowed for thorough legal review and detailed engagement with partners, resulting in stronger governance provisions, enhanced oversight rights, and more robust compliance and reputational safeguards for FCDO. Importantly, the negotiations delivered tangible financial benefits, including a reduction in management fees (from 2.5% to 2.25%), a cap on establishment costs ($2m, down from $4m), and overall estimated savings to FCDO of £500k–£1m. The process also allowed FCDO to negotiate a more balanced preferred equity dividend structure, ensuring the fund remains attractive to private investors while protecting the UK’s development objectives.

The decision not to include TIDES in the current annual review was made following a structured process at a programme team kick-off meeting, where formal Terms of Reference were drafted and consensus was reached among team members. This ensured a transparent and collective approach to the review’s scope and coverage. In hindsight, we recognise we could and or should have included more granular process milestones (e.g., completion of legal documentation, fund manager appointment, first close) and will aim to do so as the as the fund moves towards implementation.

Future reporting will not only cover the duration of negotiations but will also assess the quality of outcomes achieved, such as the terms secured for FCDO, value for money, and the fund’s readiness to deliver on its objectives. This will ensure a balanced assessment of both process and results.

As part of the recommendations we will conduct a post-negotiation review (‘wash-up’) once TIDES LPA has completed. This will capture lessons learned from the set-up phase, inform future blended finance initiatives, and support continuous improvement in FCDO’s approach to complex fund negotiations.