## Annual Review 2024/2025

Title: UKRAINE RESILIENCE AND ENERGY SECURITY PROGRAMME
Programme Value £ (full life): £230m / (Phase 1 £80m; Phase 2 uplift of £150m approved 2024)		Review date: May 2025
Programme Code: 400024	AMP start date: April 2022	AMP end date: March 2028

Summary of Programme Performance
Year	2023/24	2024/25
Overall Output Score	A+	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004311.odt / Addendum: https://iati.fcdo.gov.uk/iati_documents/D0006332.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006960.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

1. Overview. Established in 2022, the Ukraine Resilience and Energy Security (URES) programme focuses short-term on restoring Ukrainians’ access to power and heat by providing energy companies with the equipment needed to effect repairs and provide resilience for energy infrastructure in the face of targeted strikes by Russia (Output 1).
2. Longer-term, it aims to lay the groundwork for a more resilient, independent, and cleaner energy sector post-war, leaving Ukraine more self-sufficient in energy terms and less reliant on hydrocarbons. It achieves these longer-term aims through: de-risking investments into clean energy projects in the private sector (Output 2); stimulating industrial research partnerships on clean energy innovations between Ukrainian and international academic institutions and businesses (Output 3); and supporting the Government of Ukraine (GoU) to progress reforms that can attract greater private investment in the sector and support closer integration with European energy markets as part of Ukraine’s Euro-Atlantic integration (Output 4).
3. Since its inception, the URES programme has delivered strongly, mobilising quickly in 2022 and 2023, with all four Outputs established and beginning to deliver within eight months of Business Case approval. The programme has coped effectively in dynamic circumstances – this is thanks in large part to its ability to switch rapidly between emergency response and longer-term recovery needs, maintaining a minimum level of activity in both spheres but channelling spend towards emergency repairs when needs are high.
4. Operating context. The operating context at time of writing (May 2025) is regrettably similar to 2022. Damage inflicted by Russian strikes on energy infrastructure remains considerable, though tactics have evolved. Electricity transmission (substations) was the main target in Winter 2022/23. Spring/Summer 2024 saw a shift to sustained attacks on electricity generation, with Russia also targeting electrical substations linked to Ukraine’s nuclear power plants – this served to both destabilise the grid and increase the risk of nuclear safety incidents. The approach in 2025 evolved yet again, with major damage inflicted on gas production facilities, with potential ramifications for Ukraine’s ability to heat its population in the upcoming heating season.
5. Over 2024, Russia targeted Ukraine with over 2000 missiles and drones in over 30 major attacks. Despite additional electricity imports from Western neighbours and repairs, generation fell in Summer 2024 to 2.3GW below peak demand of 12GW[1] – this resulted in severe rolling blackouts around the country. The EBRD has since reported that Ukraine’s real GDP growth in 2024 reduced from over 5% in the first half of 2024 to around 2% in the second half (overall average: 2.9%), due to electricity shortages, weak harvests and labour shortages.[2] The National Bank of Ukraine continues to observe that energy infrastructure instability is a significant source of inflationary pressure, with electricity shortages and damage to energy infrastructure acting as a drag on economic growth and driving inflation.[3]
  [1] Source: “Ukraine’s Energy System Under Attack”, IEA, 2024. Ukraine's pre-invasion installed capacity was 56.1GW in 2021, although only 36GW of this was actual, dispatchable generation that could be relied upon. In 2024, 18GW was in temporarily occupied territories and 10GW of generation capacity was destroyed, leading to an acute power deficit over Summer 2024.
  [2] Source: “Ukraine’s GDP growth seen slowing slightly to 3.3 per cent in 2025”, EBRD, May 2025.
  [3] “Inflation to Remain Moderate and Economy to Recover in 2024–2026”, NBU Inflation Report, April 2024.
6. URES exists in a crowded donor landscape. The donor coordination groupings and multilateral instruments established in 2022 to address the energy impacts of Russia’s full-scale invasion – almost all of which benefit from UK support, whether political or financial – have matured significantly over the past three years, refining their processes and deepening activities. With the grid still fragile, and attacks ongoing, Ukraine will continue to be reliant on the international community for both emergency support and early investment in long-term recovery.
7. However, despite a general trend of refinement and systematisation, the freeze of USAID operations in January 2025 shifted the context significantly. Total US support to the Ukrainian energy sector, across emergency needs and long-term reform and reconstruction, has averaged US$500m per year since 2022, accounting for almost a quarter of all support to the sector.
8. The Ukraine Energy Support Fund (UESF), the UK’s preferred multilateral channel for addressing emergency equipment needs, is reporting a significant shortfall of funds compared to the value of approved funding requests submitted to UESF by the Ministry of Energy. This is despite total pledges of over £1bn since 2022. Over the medium- to long-term, the World Bank assesses that the energy and extractives sector faces recovery and reconstruction needs totalling nearly $68bn over the next ten years.[4] Total investment needs to support the implementation of Ukraine’s National Energy and Climate Plan are estimated at US$41.5bn from 2025 to 2030.[5]
  [4] “Ukraine - Fourth Rapid Damage and Needs Assessment (RDNA4), World Bank Group, February 2022-December 2024.
  [5] National Energy and Climate Plan of Ukraine 2025-2030.
9. Should attacks on Ukraine’s energy infrastructure continue, the sector may struggle to perform repairs and return generation capacity at the pace seen in previous years. During GoU’s “winterisation sprint” of March-October 2024, an estimated 4.5GW was restored with donor support. Replicating this level of recovery would be difficult under current funding constraints.
10. URES operations in this reporting period. This review covers the period from 31 March 2024 to 1 April 2025, the programme’s second full year. The period has seen URES enter “deep” implementation – building its profile and reputation for delivery among senior stakeholders internal and external, and creating interlinkages and synergies between downstream partners and components.
11. High needs driven by an uptick in attacks required the programme to scale up in Summer 2024, with the URES team in August 2024 securing approval on a Business Case Addendum for the programme’s second phase. This approval took the programme’s headroom to a total of £230m to 2028. As of April 2025, £160m of the programme’s total headroom had been committed – this review aims to collect information and evidence that can be drawn upon in the event that another extension is required in the next year.
12. At 2025’s critical juncture, with a ceasefire under discussion and the need to attract private investment for reconstruction correspondingly rising up the agenda, the elements of the URES programme focused on decarbonisation, finance mobilisation, innovation, and reform have only grown in relevance. It is encouraging to see that the evidence base has grown for the effectiveness of Outputs 2-4 over this reporting period – thanks to a process of fine-tuning on the part of the programme team, whose members continue to work iteratively and collaboratively with partners to refine activities towards the intended outcomes and impact.
Summary supporting narrative for the overall score in this review

URES has continued to perform well in FY24/25, scoring an overall A for the period of this review. The programme performed particularly strongly in its Emergency Needs and Innovation components (Outputs 1 & 3), with both scoring A+. Over this reporting period, the programme has made significant progress:

- FCDO channeled £62.5m towards emergency needs in FY24/25, amid worsening attacks. UK spend this year has translated into contracts for generation capacity equal to 41.4MW, the equivalent needed to power approximately 20,000 homes. URES funding was allocated thoughtfully, with the programme team refining internal decision-making and prioritisation processes to cover a combination of basic needs (repairs to the transmission sector, physical protection), at the same time as identifying and supporting more complex and strategic projects, for example in the rail sector.[6]
  [6] Funding gas pistons for railways has dual benefits, both for energy security within communities – since the Ukrainian rail operator, Ukrzaliznytsia, acts as a power distribution company for a subset of regular household consumers – and for the health of the country’s transportation sector writ large, particularly with rail playing an enhanced role in connecting regions and facilitating trade following closure of the airspace in 2022.
- All support that was listed as delivered or under procurement in the previous Annual Review has now been monitored by a second third-party monitoring mission. The second mission covered £2m of UK-funded gabions for protection of infrastructure – this delivery met 25% of total high-priority physical protection needs in the energy sector in Winter 23/24. The mission also covered a £10m tranche of emergency equipment to repair the transmission system, disbursed in early 2023 – this funded the delivery of high-voltage auto-transformers, regulating transformers, and surge arresters. Monitors concluded that all UK-funded equipment monitored during this mission was assessed by interviewed beneficiaries as fully meeting the needs and technical criteria. As a rough estimate, transformers and other transmission equipment provided under the £10m tranche would have capacity to distribute power to 8075 households (a medium- to large-sized town).
- UK grant support via the International Finance Corporation (IFC, the World Bank Group’s private sector lending arm) has helped unlock lending for energy generation projects led by the private sector. These projects – two risk-sharing facilities enabling loans for medium-sized companies looking to increase energy self-sufficiency and efficiency, and a major wind power project, whose beneficiary is petrol station operator OKKO Group – received combined support of £10.3m in UK grant ODA, and could yield projects of value over £400m. This demonstrates an encouraging trend of increasingly impactful projects receiving support under this output.[7]
  [7] Only the first risk-sharing facility was wholly confirmed under this reporting period – since the other two projects were only fully confirmed in FY25/26, their full results will be captured in the programme’s next Annual Review. Nevertheless, since much of the work to agree and mobilise these projects took place in FY24/25, they have been described in this report as interim activities.
- InnovateUkraine, URES’s low-carbon innovation competition, moved its first cohort of pilots and feasibility studies into implementation in Q2 of 2024. Every project represents a partnership between (at minimum) one UK and one Ukrainian entity, with the first cohort of 13 projects comprising over 50 representatives of business, academia and civil society. Over 50% of the innovations under development by this cohort are Ukrainian-led, in the sense that the intellectual property of the innovation belongs to a Ukrainian actor. The InnovateUkraine cohort is piloting innovations and studies to address questions such as: localising the production of large-scale battery storage for renewables in Ukraine using iron rather than lithium; reducing the carbon cost of concrete for reconstruction by recycling rubble; and reducing the installation cost and temperature range of heat pumps, to drive greater uptake. This reporting period saw the Foreign Secretary announce a second round of InnovateUkraine during a visit to Kyiv in February 2025. InnovateUkraine attracted a surfeit of high-quality bids during its 2023 Round 1 application window, demonstrating the project’s potential for expansion.
- InnovateUkraine’s first round raised more match funding than expected from commercial participants during this reporting period, since businesses benefiting from InnovateUkraine funding have used their own resources to create special-purpose vehicles to capitalise on the location-specific opportunities that have arisen out of their project activities. Further, a large Ukrainian company has set aside a sum of capital expenditure with a view to investing this sum into the geothermal insights provided by the InnovateUkraine-funded Geothermal Ukraine feasibility study, demonstrating the potential of InnovateUkraine projects to attract funding for scale-up beyond the timeline and envelope of InnovateUkraine itself.
- URES funded the development – on time and on-budget – of Ukraine’s National Energy and Climate Plan in June 2024. This plan was funded by the UK and drafted by a team of Ukrainian experts and civil society representatives in a completely transparent way, opening up the process to public consultation in a way that secured confidence and buy-in from donors. Ukraine’s adoption of the UK-funded NECP was one of conditions for disbursement of the first regular payment – value €4.2bn – under the EU’s Ukraine Facility.
- URES funded the creation of Ukraine’s Green Transition Office (GTO) in October 2024. The GTO is leading an ambitious workplan to create a state decarbonisation policy for Ukraine in line with Ukraine’s climate commitments under its Nationally Determined Contribution and EU accession requirements. GTO is housed at the Ministry of Economy and was designed in collaboration between the Ukrainian government, civil society, and the UK’s Climate Change Committee.
- Also under its Technical Assistance facility, URES has:
  - Improved Ukrainian companies’ reporting on sustainability indicators: UK funding via UN Global Compact facilitated reporting from 70 businesses on progress against Sustainable Development Goals and other sustainability indicators;[8]
    [8] This reporting took the form of the Communication on Progress, a worldwide UN Global Compact initiative to benchmark and track businesses’ progress against sustainability goals. For more detail, see website: CoP Page | UN Global Compact
  - Funded consultations and development of Ukraine’s Critical Minerals Strategy, to be presented at the Ukraine Recovery Conference 2025;
  - Began cooperation with IAEA on capacity-building for small modular reactors, sending four Ukrainian nuclear experts for training in the first wave of workshops;
  - Started a new project on the development of the biomethane market with Energy Community Secretariat; and
  - Launched a project mapping Ukraine’s manufacturing capability for nuclear parts and equipment, in order to prime Ukrainian companies to participate in the supply chain for innovative nuclear technologies (and alert international businesses to Ukrainian industrial capacity and expertise) in the future.
## Major lessons and recommendations for the year ahead

Summary of recommendations for the year ahead
Theory of Change and Progress towards Outcomes
1	Tighten approach to collecting real-world results. This exercise should focus initially on the programme’s emergency needs component, as the lion’s share of spend across the life of the programme, bringing in experts from the Ukrainian energy system and around UK Government to quantify impact of URES (and international) support for the energy sector - our implementing partner for Output 1 has engaged constructively with the early stages of this process. / Continue this exercise across components, pausing and reviewing any partnerships that are not able to demonstrate impact adequately.
2	Begin planning for collection of International Climate Finance results early. The URES programme first reported results against ICF KPIs in FY24/25, after FY23/24 was too early to show results against indicators. During FY25/26, URES team should work to incorporate ICF KPIs across the logframe, scouring for opportunities to incorporate newly relevant KPIs as projects mature and agreeing approach with central ICF statisticians, potentially in tandem with BE Kyiv’s Triggering Investment, Growth and Economic Resilience (TIGER) team as that programme begins to report. The team should set targeted ICF-eligible indicators as early as possible, and communicate early that partners will need to undertake data collection and disaggregate results – suggestions for individual KPIs have been included under each output.
3	Having completed a thorough review of outputs and output indicators in FY23/24, the programme team should look now to refresh milestones against outcomes over FY25/26. Recommendations for how to update outcomes indicator milestones may be found in Annex A. To complement this process, it would be instructive to plan for a more impact-focused evaluation assessment, to be conducted in 2026. Outputs should be extended to 2028.
Output 1 (Emergency needs)
4	URES team should continue to work with the Energy Community Secretariat to tighten the approach to real-world results and measuring the impact of funding. URES programme team should ensure that targets are stretching and proportionate to spend.
5	The next phase of third-party monitoring should focus on the FCDO’s second tranche of £14m, allocated in early 2024 and delivered in large part over FY24/25. URES programme team would benefit from participating in these missions.
Output 2 (Private sector resilience)
6	FCDO should continue to keep the question of IFC’s leverage, of both its own balance sheet and of private sector finance, under review. It could be instructive to attempt a light-touch benchmarking of these ratios across comparable projects and geographies in which FCDO ODA has been blended with the IFC balance sheet. In concert with other HMG teams and with a shared approach across TIGER and URES from BE Kyiv, FCDO should define expectations for leverage ratios ahead of making any fresh commitments.
7	URES SRO should continue to work with central FCDO teams and UKDel Washington to develop a cross-FCDO view on our requirements when contracting with IFC on questions such as pipeline visibility, results tracking, and payment in advance of need. These could potentially be suggested for insertion by FCDO in the standard bilateral agreement template.
8	FCDO should wait for full reporting before committing further funding. It has been difficult to fully assess performance in this Annual Review due to a mismatch between FCDO reporting timelines/processes and those of IFC. This has been communicated clearly throughout between programme teams and every effort has been made to reconcile approaches. Nevertheless, without clearer reporting, it has been difficult to assess this output fully.
9	FCDO must negotiate the exit strategy on use of any ODA that is due back to the FCDO at the end of the 26-year lifespan of the IFC Economic Resilience Action facility.
Output 3 (Innovation)
10	FCDO should better establish and localise this component in Ukraine, to build GoU awareness of URES activities and to deepen synergies with the Ukrainian energy and innovation ecosystem. This localisation effort would aim to build the ecosystem for low-carbon innovations, with a view to creating a future Ukrainian home for InnovateUkraine, and ensure that UK programmes are shaping policy at the governmental level. This localisation effort should include the following activities: / Engaging closely with GoU (Ministry of Digital Transformation and Ministry of Energy) to update on progress and create a climate in which policy decisions are taken with UK innovation work in mind; / Comms activities to Ukrainian audiences to raise the profile of these innovations; / Policy advocacy work that communicates the legislative and regulatory changes required to adopt and scale innovations; / Anchoring Ukraine’s innovation eco-system into the wider European innovation landscape.
11	The SHIELD green hydrogen project, Output 3’s second element in addition to InnovateUkraine, has the potential to enact transformational change on GoU’s approach to recovery. By delivering open-source modelling tools and research, the project has the potential to insert innovative methodologies into both short-term resource allocation and long-term strategic planning. The URES team should develop a methodology to measure and track the realisation of this potential in FY25/26. This could build the evidence base as the team considers a possible extension to this work.
Output 4 (Technical Assistance Facility)
12	The URES team should continue to streamline and localise the Technical Assistance facility in FY25/26. By end FY25/26, this output should have fewer partners. When prioritising, teams should look for: UK USP combined with local direction-setting in a partnership of equals; ability to leverage additional finance; efficiency or catalytic potential; ability to synergise other URES components.
13	Pause new disbursements to the EBRD’s Multi-Donor Account until June 2025, when project-level reports will issue. At that point, the URES team should disburse once reporting is assessed to be adequate. Future output indicators should be set according to results reported in June 2025.
Cross-cutting
14	The URES SRO should advocate for a full-time Programme Manager as minimum for this major project. Per FCDO best practice, a programme of URES’s size would typically require a dedicated SRO, PRO, adviser and programme manager as minimum.
15	Continue to refine coordination with comms teams, flagging opportunities ahead of time and maintaining an overview of equipment deliveries and publicity opportunities to streamline public outreach.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The programme’s impact statement is “Increase Ukraine’s energy security by strengthening access to the European power grid; supporting the efficient use of energy; and decreasing reliance on hydrocarbons”. Full Theory of Change at Annex A. Under this, the intended outcomes of the components are as follows:
- Outcome 1: Ukraine's energy system remains resilient throughout the conflict
- Outcome 2: Private finance plays an increasing role in Ukraine’s green energy transition
- Outcome 3: Ukraine builds back better using the best and latest innovations
- Outcome 4: UK technical assistance supports the Government to plan for a decarbonised energy sector and progress reforms that can attract greater private investment in the sector and support integration with European, regional and Western energy markets.
There have been no changes to the outcome or impact statements during the second full year of implementation. However, additional sources of verification and stronger articulation of targets were added to the logical framework (“logframe”) in September and December 2024.

In the URES Business Case Addendum (approved in August 2024), the following assumptions were outlined – these are assessed to remain broadly valid:
- War damage increases, but not to the extent that the grid fully collapses
- Ukraine successfully resists Russia from seizing territorial control of the whole of Ukraine [updated to reflect the context in 2025]
- Ukraine’s political settlement remains stable throughout and after the invasion

The below demonstrates the synergies between components. Energy has emerged as a microcosm of the most pressing reforms facing Ukrainian society today: deoligarchisation, creating an investment-friendly environment, decarbonisation, and the geopolitical shift from Soviet-era to EU-ready systems. URES is poised to continue playing a facilitating role within these processes, aiming to create a virtuous circle between innovation, investment and reform.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

1. Broadly, outputs and projects are delivering according to their aims. The programme team, led by PRO, conducted an impressively thorough review of outputs for all partners in late 2024, refreshing all outputs and agreeing indicators – this was a time-heavy endeavour. Gains from that exercise should be preserved, by sticking to outputs as defined (rather than revising) and requesting new targets against them, absent major changes to delivery plans.
2. However, there is more that could be done within URES to align outcome statements with activities, to drive tighter and more measurable progress. This speaks to a gap between the ground-level outputs and the nationwide, transformative impact envisaged.[9]
  [9] This is compounded by the lack of availability of sensitive data due to the war (e.g. GoU stopped publishing data on grid-wide generation capacity in 2024, making it more difficult to track the cumulative impact of donor support). The team has mitigated this lack of data by engaging with Ministry of Energy working groups, IEA, civil society, and drawing on extensive energy expertise in political and trade teams around the Embassy, whose members are able to draw on export databases and contacts to plug data gaps.
3. While ambition at the impact level is useful and important when designing programmes, at the stage of delivery URES is currently in, there is a need to critically assess the level of ambition and overarching assumptions. While there is measurable progress against some of the outcomes, others are too large and broad (and affected by too many wider, uncontrollable forces) for URES to reliably track progress in meeting them.
4. Therefore, setting outcome milestones that chart a clear course from outputs to impact (and allow the team to attribute and measure success) should form the focus of the next year’s activities around the Theory of Change – suggestions for precise revisions may be found in Annex A. This milestone-setting could include a return to intermediate outcomes, which were included in the original Business Case then set to one side during the early mobilisation process. Commissioning an evaluation of the programme’s progress towards outcomes and impact would be instructive during the upcoming Financial Year (and the programme’s mid-point), FY25/26.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

1. The programme should continue. The programme is one of HMG’s most potent tools when delivering on the energy-related aspects of the UK-Ukraine 100 Year Partnership Declaration, signed January 2025. Detail on precisely which aspects of the Partnership are addressed by URES activities may be found in Annex B. The URES programme also offers clear and tangible pathways to delivery against the Minister-approved “Strategy for UK’s cooperation with Ukraine on meeting urgent needs, recovery & reconstruction - 2024-2029”. This strategy notes that, “energy is the lifeblood of the economy: all GDP growth will depend on secure and affordable energy supply, while clean transition will enable Ukraine to attract investment and export renewable energy abroad”.
2. Beyond HMG strategies, the programme makes clear sense in the context of sustained damage inflicted on the Ukrainian energy system and the need to build a more modern energy sector post-war, fit for the challenges of reconstruction. Attacks have rendered the emergency needs component indispensable when aiding GoU to meet some of its most pressing responsibilities towards the population – those of provision of electricity and heating. The remaining components have been designed in dialogue with (and often delivered in partnership with) Ukrainian government and civil society, ensuring interventions are alive to Ukraine’s unique circumstances, including the energy sector’s makeup and history pre-2022.
3. Suitability for a peacetime scenario. Should emergency needs reduce, the programme has three tested components (Private Sector Resilience, Innovation, and Technical Assistance) primed and ready to deliver on peacetime objectives. The delivery modalities, limitations and use case for these components have been defined and rigorously tested since 2022, meaning that any “peacetime URES” would simply be a slimmed down version of the original, building on lessons already learned. With three years’ experience under its belt, URES’s flexible, nexus, full-spectrum approach means it is ready to hit the ground running in the event that aerial attacks on the grid cease. Strategically, energy will be a key enabler for economic recovery in peacetime – whether to power domestic industry or export abroad.
4. Ability to catalyse external and private finance. The focus on private sector resilience (with supplementary activities focused on reform and innovation) from as early as 2022 was prescient. In 2023, the IFC judged the difference between investment yielded in a “business as usual” versus “accelerated reform” scenario for energy as mammoth: $2.2bn in private finance attracted to the energy sector if Ukraine were to stick on its current path (i.e. if the policy and investment climate were to remain broadly the same) versus $167.3bn with concerted reforms.[10]
  [10] Source: “Private Sector Opportunities for a Green and Resilient Reconstruction in Ukraine”, IFC, 2023.
5. Synergies between components. Energy stands out as a sector with a particularly high potential to attract private sector investment, as well as an area where government actions and reforms can do the most to improve the volume of finance Ukraine is likely to attract. The same is true of innovation – as innovations are stimulated, so they become closer to a stage where they can successfully attract private sector resilience and influence the design of the regulatory environment on a governmental level. This year, the programme has started to see shared successes among and between outputs, particularly Outputs 2-4, whose interlinkages are shown on Page 10. For example, the ability of Ukrainian-led innovations to attract private sector finance – a stated aim of Output 3 - could double as a success under Output 2, focused on private sector resilience.
6. Low-spend scenario: In light of the above, when assessing options to pare back UK ODA spend in the Ukrainian energy sector, priority should be afforded to projects that have the ability to catalyse external (primarily private sector) finance. In terms of modality, the top-priority interventions should combine UK USP with Ukrainian leadership in a genuine partnership of equals, per the spirit of the 100 Year Partnership. These three factors – UK USP, local presence/ownership, and potential to leverage other sources of funding – should lead the team’s decision-making, with preference afforded to interventions able to “tick multiple boxes”.

## C. DETAILED OUTPUT SCORING

Output Title	Emergency support. Full title: “Resilience of the Ukrainian energy system is maintained throughout the invasion through a contribution to the Energy Community's Ukraine Energy Support Fund & in-kind provision of gabions and generators”
Output number:		1	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	Yes – adjusted in previous AR

Indicator(s)	Milestone(s)	Progress
Output Indicator 1.1 Number of supply contracts signed for the continued stable operation of the Ukrainian electricity system for the sole benefit of TSO NPC Ukrenergo JSC	Target for March 2025: 2	Achieved: 11 / SIGNIFICANTLY EXCEEDED / This is due to two unexpected in-year uplifts to this component: £20m was originally planned for, with indicators set accordingly – URES team should update indicators early in FY25/26 to ensure targets are stretching.
Output Indicator 1.2 Number of supply contracts signed for the recovery of the heating sector	Target for March 2025: / 2	Achieved: 12 / SIGNIFICANTLY EXCEEDED / As above, this indicator was set prior to the injection of two major in-year increases in funds.
Output Indicator 1.3 Other donors join the Ukraine Energy Support Fund after receiving support on mobilising their commitment from the UK	Target for March 2025: 2	Achieved: 1 / NOT MET / This indicator is about the UK team’s government-to-government efforts to help other donors join the fund. Total number of donors to UESF increased by 11 to 31 in 2024. This year, the UK engaged directly with Australia, sharing due diligence, monitoring and governance information.
Output Indicator 1.4 856 generators distributed to uninterruptible customers in Ukraine ahead of winter 2022/23 and redistributed according to GoU prioritisation.	N/A - target achieved in previous year.	N/A - target achieved in previous year. / Indicator to be removed in next logframe refresh.
Output Indicator 1.5 Quantity of generation capacity returned to the grid thanks to UK-funded equipment (MW/GW). Measured through contracts signed via Energy Community UESF	Target: 20MW	Achieved: 41.4MW / SIGNIFICANTLY EXCEEDED / UK spend this year has translated into contracts for generation capacity equal to 41.4MW. These items will be installed in FY25/26, and subsequently monitored.
Output Indicator 1.6 Number of sites protected by gabions/physical protection. Measured via number of contracts signed	Target: 30	Achieved: 39 / EXCEEDED

Activities and supporting narrative

1. UK support for emergency needs. FCDO stepped up support significantly to the Energy Community Secretariat’s Ukraine Energy Support Fund (UESF). URES disbursed £62.5m to the benefit of Ukrainian energy companies via the UESF in this reporting period. This broke down into four separate tranches: three equal tranches of £20m each, disbursed in May, September, and November 2024, respectively, and a final tranche of £2.5m in late March 2025. The £62.5m contributed under this reporting period constitutes the majority of the UK’s £86.5m contribution to the UESF made since 2022.
2. UK support in the context of total contributions. Total pledges to the Fund since its establishment in 2022 had surpassed €1bn by the end of 2024. The UK has contributed just over €100m since 2022, meaning that (taking a broad-brush approach), approximately 10% of the Fund’s results may be attributed to the UK. However, it must be noted that this picture is complicated by donors’ individual earmarking preferences – not all donors support all of the UESF’s workstreams, and therefore it is not entirely accurate for all donors to claim credit for (a proportion of) all results. As of April 2025, the UK was the Fund’s fourth-largest donor.
3. Comms opportunities. The grid below shows several upcoming comms opportunities, particularly focused on rooftop solar for hospitals (UESF Tranche 2) and decentralised generation (UESF Tranches 4 and 5). These will be fully communicated to FCDO comms teams and external stakeholders.

Details of total UK support under this output:

Year	FY22/23	FY22/23	FY23/24	FY23/24	FY24/25	FY24/25	FY24/25	FY24/25
Tranche	In-kind 1	UESF 1	In-kind 2	UESF 2	UESF 3	UESF 4	UESF 5	UESF 6
Pledge	£7m	£10m	£2m	£14m	£20m	£20m	£20m	£2.48m
Category	Generators (£6.1m), solar pilot (£0.9m); delivered bilaterally	Support to transmission operator Ukrenergo	Gabions (delivered bilaterally)	Physical protection (£12m); Rooftop solar (£2m)	Repairs, flexibly earmarked	Decentralised capacity (£10m); repairs (£8m); physical protection (£2m)	Decentralised capacity (£10m); repairs (£8m); physical protection (£2m)	Repairs, flexibly earmarked
Delivered				75%	-	1%	-	-
Monitored				-	-	-	-	-
Allocated or contracted (February 2025)	All	All	All	82%	0%	92%	0%	0%

1. Fund operational performance. The UESF has made impressive progress over the past year. After a period of procurement and discussion with the URES team, the Fund onboarded in 2024 a project manager for rooftop solar for hospitals, meaning that a UK contribution of £2m for solar made in late 2023 began in FY24/25 translating into panels and storage for Ukrainian healthcare facilities, with requests for similar support expected to increase as the mechanism scales up. The UESF flexed impressively to situational changes, rapidly onboarding a new procurement partner for all equipment in 2025 – the UK stood ready to contribute to any additional costs, though these costs were ultimately covered by other donor funding. The Fund communicated clearly to donors on risks and challenges throughout.
2. Fund governance and transparency. The UESF continues to benefit from high fiduciary controls. The Fund provides full independent audits, plus detailed monthly and annual reports, in a timely fashion to donors, and has been extremely cooperative when designing, conducting, and disseminating the results of UK-funded third-party monitoring missions. The FCDO-funded audit of agreed-upon procedures, conducted by an independent auditor and delivered to FCDO in April 2025, identified no issues or irregularities – FCDO should continue to fund similar audits as our relationship with UESF endures. Independent third-party monitors contracted by the FCDO deemed the Fund “fully transparent”.
3. Reporting and capacity. The Fund has also spent significant time and effort engaging with URES programme team’s questions and requirements, demonstrating a methodical and constructive approach. The UESF team has been proactive in spotting and communicating issues or delays associated with UK-funded equipment. In response to increased donations and a consequent increased appetite for results and reporting, the UESF scaled up its core team, which now numbers 14. Communication has been complemented from the UK perspective by a URES team secondee, who works part-time with the Fund.
4. Efficiency of open procurement. The URES third-party monitoring mission established that the UESF’s procurement procedure is open, competitive, and highly appreciated by energy company beneficiaries as a more efficient form of aid distribution in building energy sector resilience than in-kind aid.
5. Approach to earmarking. Over this period, the UK has adopted a flexible approach to earmarking – endeavouring where possible to define ahead of time where support will be targeted, to build confidence in results and impact, but also responding to requests from the host government to reprioritise allocations or loosen earmarking when the situation is unpredictable and overly rigid earmarking from donors would create an unhelpful administrative burden for GoU and Energy Community Secretariat, as fiduciary.
Case study: Second Third-Party Monitoring mission conducted in FY24/25. Results and lessons gathered regarding the UK’s first tranche of support under UESF and bilaterally-provided gabion barriers / During the reporting period, URES conducted Third-Party Monitoring on £10m of transmission equipment provided via UESF to Ukrenergo, the Ukrainian grid operator (the first tranche of supported the UK channelled via the UESF - “UESF Tranche 1”). / Automatic transformers were a major component of UESF Tranche 1. These constitute the core of each substation and are often a substation’s most expensive piece of equipment. Without them, the station's functioning is impossible. The tranche provided other, lower-cost transmission equipment, including surge arresters, switchers, current flow transformers and voltage transformers – these are easier to repair or exchange than transformers, but equally important for the safe operation of a power substation.UK infrastructure experts gave a rough estimate that the transformers provided under UESF Tranche 1 have capacity to distribute power to 8075 households (a medium- to large-sized town). / Monitors found that Ukrenergo’s strategy towards electricity system repairs had been designed to guarantee the best use of the equipment received. Ukraine's grid operator manages rolling blackouts through advanced planning to limit the power supply in certain regions – this is designed to be less costly for Ukraine’s energy system (and therefore for the population and economy) than unplanned blackouts, though it requires skilful management. Monitors found that UK-funded equipment was used to restore power flows where most needed and as an emergency backup in case of total destruction of particular system elements. Thanks to real-time information on the functioning of the grid, items are moved (even de-installed if necessary) from warehouses to substations (and vice versa), depending on need. / One unexpected benefit of the UK-funded support provided under UESF was that, in some cases, the equipment provided had the effect of rendering substations monitored more modern and effective overall: for example, one beneficiary praised UK-funded silicon-made surge arresters (as opposed to more fragile ceramic ones) for being safer during an air strike, easier to maintain and having a longer operational life than what was in place previously. This points to cost-effectiveness of items, inasmuch as they are not simply building short-term resilience (the URES programme’s first aim) but also contributing to the long-term transformation of the grid, the URES programme’s second aim. / The monitoring mission also verified £2m of gabions provided directly government-to-government (protective wire-mesh baskets filled with sand and gravel, assembled into walls to protect from debris generated by aerial attacks). The UK was the first donor to act to meet this need, and this £2m delivery met 25% of physical protection needs in the energy sector in December 2023. / During monitoring, beneficiaries gave an overwhelmingly positive assessment of the gabion structures provided, particularly the quality of the gabions themselves. FCDO-funded gabions were found to be a stronger form of Level 1 protection compared to previous measures and were found to be of better quality than locally-manufactured and other foreign-manufactured gabions. / Monitors found that gabion walls had been constructed to protect a piece of CNI at all sites visited. In all cases, the gabions were used to protect civilian (as opposed to military) infrastructure. While the protection provided by these structures only protects from some indirect hits, falling missile fragments, and other damage, most companies still consider gabions more effective than other protective means, e.g. sandbags, and effective against the majority of threats faced. / A majority of beneficiaries had seen their facilities attacked by Russia, though all had been attacked prior to installation of the UK-funded gabions. 75% of sites had seen facilities damaged by aerial attacks (drones or missiles). Equipment such as transformers, energy installations, power lines were most commonly targeted. Monitors concluded that all UK-funded equipment monitored during this mission was assessed by interviewed beneficiaries as fully meeting the needs and technical criteria.

Projected impact of contributions that have not yet been monitored

1. Railway. In late 2024, UK allocated funding via UESF towards the supply of containerised gas piston power units to Ukrzaliznytsia (UZ), Ukraine’s national railway company. The units are designed to provide backup and decentralised power for critical railway operations, reducing dependence on an overloaded grid and ensuring continuity of cargo and passenger transport during power cuts. The UZ project features compact, rapidly deployable generation assets and represents a novel collaboration between the UESF and the transport sector. With energy outages increasingly affecting the national railway system, these decentralised units provide operational continuity, particularly in frontline or logistically important regions. The contract for the supply of the first two packages of these units (20 MW each) was finalised in early 2025.
2. Delivery of the units is scheduled throughout 2025, with technical support and installation funded through complementary contributions. Results are not yet delivered, but rough initial estimates indicate that the gas piston generators will provide power for approximately 4 electric passenger trains simultaneously. The project has been mobilised extremely rapidly - credit is due to the UESF team for engaging innovatively with the situation in Ukraine and the wider donor picture, and for working through procurement at pace.
3. Solar panels. The end of the reporting period (Q1 2025) saw UESF begin to deliver and install £2m of solar equipment funded by UK via UESF under the UK’s second tranche. This is part of a UESF-implemented multidonor effort (“Rays of Hope”) to install rooftop solar at Ukrainian hospitals, building energy resilience and reducing emissions. As of December 2024, 12 hospitals had been fitted with solar panels and evaluated; the remaining 13 are scheduled for evaluation in 2025. These 25 contracts will deliver a total installed capacity of 452.2 kW. Once fully implemented, the systems are projected to generate approximately 3,360.3 MWh annually - leading to an average reduction in electricity expenditure of around 35% per hospital. It is not possible to fully report results for the UK-funded proportion of the solar initiative until projects are fully implemented, but the above indicative results are encouraging – results derived from this funding will be reported in the next Annual Review.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

1. As mentioned above, the UESF has flexed impressively to situational changes in this reporting period. A major achievement was the rapid onboarding of a new procurement partner in 2025.
2. UK grant funding for gas pistons, in support of the rail sector, has complemented lending from EBRD, an example of a well-coordinated donor picture delivering synergies. This project has also influenced and complemented EBRD’s design of corporate governance interventions focused on the rail sector. This demonstrates complementarity between UK-provided grant ODA and EBRD lending, and additional reform benefits of providing capital for infrastructure projects.
3. This year, the UK aims to remain a close and reliable partner to the UESF and the Ministry of Energy as they conduct their repair campaign, acting as convenor and helping troubleshoot as required. The URES team will continue, as it did in the Fund’s early days, to share its positive experience of working with the UESF and provide practical advice on how the UK Government has structured our partnership with the Fund.
4. This year, URES team planned to disburse £20m to UESF, but was allocated an additional £42.5m over the same period. In the upcoming year, the team should ensure targets are appropriate for level of spend. Further, URES team should look to double down on impact reporting, including by planning an evaluation of system-wide effects of UK-funded support on grid resilience.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous Annual Review	Progress during FY24/25
FCDO should work closely with DBT to ensure that open tenders for energy support are known to UK industry representatives. / FCDO should explore incorporation of additional indicators that can monitor the efforts of DBT in promoting equipment requests to UK industry.	Achieved. URES team is working closely with DBT to socialise tender opportunities to UK companies. This has translated to moderate success for UK plc – in 2024, 4% of contracts awarded by the Fund (value: €17m) went to UK companies. / Recommendation progressed. The URES team explored tracking socialisation by DBT as an indicator for the programme, but has concluded that, while cross-Whitehall working is positive on this front, our programme’s indicators should focus on efforts of FCDO and our partners.
Further donation of generators should hinge on ensuring that spare parts and technical support from manufacturers can be made available. Access to spare parts of distributed generators should be enhanced by securing contracts between producers of the generators and Ukrainian servicing companies and look to be delivered through the UESF moving forward. The FCDO in collaboration with Energy Hub should ensure the support (e.g. translation of manuals, hot-line or training organised by producers of the equipment) for beneficiaries in Ukrainian or Russian and ensure that all the missing documents are retrieved and passed to beneficiaries.	N/A. This recommendation has not been progressed since generators have been superseded by other equipment in list of GOU priority needs. However, similar issues (lack of technical wraparound support) were noted by third-party monitors when monitoring gabions. Therefore, this recommendation will be taken forward as outstanding for next year.
Any extension of the current programme should consider in the short term a gradual replacement of the small and medium fossil fuel generators (primarily petrol and diesel) with hybrid (solar and fossil fuel) generators, similar to the ones provided through the solar pilot.	N/A. As above, generators were superseded by other equipment in lists of GOU needs
The continuation of the delivery of small mobile devices to selected beneficiaries as well as further delivery of hybrid devices could be considered. FCDO should request its partners to introduce more stringent needs assessment and beneficiary criteria. Assistance and training in Ukrainian or Russian regarding the installation and maintenance of the equipment should be implemented by FCDO partners.	N/A. As above, the programme team has opted to provide support via a multilateral fund this financial year. This approach has supplanted the more time-intensive approach of bilaterally providing in-kind support, in the spirit of streamlining.
FCDO should go further with the solar pilot by building out a consortium of partners and plugging them onto the Energy Community Secretariat’s UESF to unlock funds already earmarked by several donors to fund renewable and solar resilience projects for Ukrainian social facilities – these are restricted to hospitals at this early stage	Achieved. This process was led by Energy Community Secretariat
FCDO should share solar pilot learnings with several humanitarian actors and Ukrainian NGOs looking to use solar or hybrid solar technology to have a larger impact on the overall response. A follow-up monitoring activity could bring a more conclusive assessment of the utility of medium items delivered to social and healthcare facilities on whether they are more useful and remain functional in winter.	Achieved.
Future assistance through UESF should consider adding new types of equipment provided to energy companies, primarily special vehicles, with a continued focus on mitigations being put in place to protect against the risk of dual-use.	N/A - superseded by other GOU priorities.
FCDO needs to continue with efforts to crowd-in donors to help service the remaining gap ~60% on provision of NATO-grade gabions that can provide some important physical protection for high-priority CNI, as identified by Ukraine’s Ministry of Restoration (which is coordinating these efforts).	Achieved – FCDO funding was matched and exceeded by funding from US, Japan and UK MOD. These contributions were influenced by lessons and logistical support provided by UK FCDO.
Identify opportunities to support GoU and donors to fully understand and consider the value for money trade-off on facilitating new clean energy investments against repairing old or damaged infrastructure (and vice versa),	Achieved; recommendation nuanced. TPM has shown that beyond simply repairing the grid, donor contributions have acted to transform it, driving higher efficiency in the transmission sector. This suggests that the “trade-off” surfaced in the previous Annual Review may not be as stark as previously assessed.

Outstanding and new recommendations for FY25/26

Recommendation: URES team should continue to work with the Energy Community Secretariat to tighten the approach to real-world results and measuring the impact of funding. URES programme team should ensure that targets are stretching and proportionate to spend.

Recommendation: The next phase of third-party monitoring should focus on the FCDO’s second tranche of £14m, allocated in early 2024 and delivered in large part over FY24/25. URES programme team would benefit from participating in these missions.

Learning. The UESF has demonstrated its effectiveness over this reporting period. The third-party monitoring exercise has built confidence in UESF processes and in the suitability and effectiveness of support delivered. UESF has managed unpredictability and responded well to scrutiny through transparency and open communication with donors.

Recommendation. In an altered donor climate, the UESF will be increasingly vital. UESF team has assured FCDO that staffing and capacity is sufficient to deal with an uptick in needs – FCDO should continue to keep this under review and offer support if needed.

Recommendation. Further donation of gabions and other in-kind equipment should ensure that installation advice or videos (via QR code) are accessible to beneficiaries.

Recommendation. The Due Diligence Assessment for this partner will expire in October 2025 – the programme team should work to update in good time ahead of expiration.

Output Title	Private sector resilience. Full title: “At least £60m Investment channelled into businesses critical for Ukraine's energy sector via IFC”
Output number:		2	Output Score:	[not scored]
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – adjusted based on recommendations in FY23/24 AR.

Indicator(s)	Milestone(s) for this review	Progress
Number of businesses in Ukraine supported by IFC’s ERA Programme which benefited from UK support	[no target agreed]	IFC reported that as of December 2024, two businesses had been supported: / Oct 2023: 1 (MHP) / Nov 2024: 1 (Raiffeisen Bank Ukraine)
Number of Development Partners contributing to the ERA Ukraine Program, post UK contribution	[no target agreed]	As of December 2024, 8 Blended Finance contributors, of which 5 (EC, France, Japan, Belgium, Norway) had signed post-UK URES contribution.
The leverage ratio of the aggregated total FCDO support in FCDO-supported ERA projects to the aggregated total project cost for the entire portfolio of FCDO-supported ERA projects.	[no target agreed; no reporting]	No official reporting. This indicator will be officially reported in the next annual report. This report will cover July 1, 2024-June 30, 2025, and will be shared by end-December 2025. / However, as an interim estimate, it appears that for the single project fully signed and finalised in the FY24/25 reporting period (Raiffeisen Bank RSF), total FCDO grant funding of £4.6m (combined with a partial guarantee from the French government) appears to have contributed to the leverage of a total estimated amount of approximately £126m.
Volume of climate finance mobilised for climate change purposes as a share of the total ERA portfolio	[no target agreed; no reporting]	No reporting. This indicator is under review and pending approval. If approved, results for the period July 1, 2024-June 30, 2025 will be reported by end December 2025.

Output activities and supporting narrative for the score

Reporting. It has been difficult to fully assess performance indicators in this Annual Review due to a mismatch between FCDO reporting timelines and those of IFC. This has been communicated clearly throughout between programme teams and FCDO as donor has been apprised of the reasons for this. Nevertheless, the FCDO should wait to see full reporting on the projects mentioned in this report before committing further funding.

Agreement and disbursement. UK Minister for Europe Leo Docherty signed an Administration Agreement with IFC President Makhtar Diop at the UK-hosted Ukraine Recovery Conference in July 2023. Under that agreement, the FCDO agreed that the URES programme would commit up to £25m in grant funding to the IFC’s Economic Resilience Action (ERA) programme. This amount was disbursed by FCDO over three Financial Years: FY22/23 (£15m), FY23/24 (£9.5m) and FY24/25 (£0.5m).

Absorption. In FY23/24, FCDO funding was committed to a project for MHP, Ukraine’s largest agri-producer, captured in the previous Annual Review. Over the second half of 2024, IFC’s Board approved three projects that benefited from UK grant funding, detailed below. IFC reports that, following these approvals, FCDO’s £25m contribution under this facility is expected to be fully allocated by end-June 2025.

Projects supported in previous reporting period: As a recap, during the reporting period for the FY22/23 Annual Review, IFC signed one deal with agri-producer MHP: this was designed to support development of MHP’s biowaste to biogas production facilities. MHP is the largest biogas producer and first bio-methane fuel producer in Ukraine.

1. Projects supported in FY24/25 reporting period. In November 2024, IFC signed an agreement with Raiffeisen Bank, for the latter to act as the local bank cooperating in a risk-sharing facility (RSF) led by IFC and DFC, the US Government’s development financing agency. Approximately 30% of the RSF is expected to finance longer-term renewable energy generation and energy-efficiency projects to bolster Ukraine’s energy security. IFC’s participation is backed by a grant funding contribution of approximately £4.5m (EUR5.4m) from URES, as well as by a partial guarantee from the French government. This support is channelled via the IFC’s Economic Resilience Action instrument. Loans will be primarily targeted towards midcaps (companies with market capitalisation of medium size, i.e. between small and large). This project was signed during this reporting period, meaning that as an indicative estimate, UK grant funding of £4.5m can be said in part to have contributed to the leveraging of total project costs of approximately £126m in this reporting period.
2. By comparison, the MHP deal announced in 2023 used $15m of FCDO funding to contribute to a project of total value $52m. This demonstrates a positive trajectory, with UK grant lending via Raiffeisen Bank in this reporting period appearing to catalyse larger amounts of external lending comparted to the previous reporting period. This indicates that the leverage ratio of UK grant to IFC/external lending (and the average number of companies supported per transaction) has increased with successive disbursements via the ERA, a trend that is hoped to continue.

Case study: Two UK-supported projects under IFC that were close to signature (but not yet signed) at the close of FY24/25 / 1: Risk-Sharing Facility. In addition to the Raffeisen Bank RSF detailed above, a second Risk-Sharing Facility, implemented by UkrSibBank, was also approved by the IFC Board during this reporting period. However, this RSF was only signed after the end of the FY24/25 reporting period, and so will be reflected in the following Annual Review. / 2: OKKO Group. Another major workstream this Financial Year was the preparation of a deal to deploy £3.8m of UK grant ODA to support the construction by OKKO Group of a wind project in Western Ukraine. This grant will support a complex lending project, of total value approx. €225m plus VAT. As above, this project was board-approved but not signed at the close of FY24/25. / Leverage. As currently estimated, it is expected that UK grant funding of £3.8m towards the OKKO project has the potential to contribute to the leveraging of £210m in funding from external sources. The co-lenders were IFC (€60m), EBRD (€60m) and the Black Sea Trade and Development Bank (€37m). The UK contributed to this project £3.8m. The total cost of the project was estimated at time of signing at €225m (excluding VAT), with the remainder to be met by equity from OKKO Group. / Results: The OKKO project is promising in terms of results. It is expected to fund the construction of wind plants with a combined capacity of 147 MW – this is equivalent of what would be required to power up to 80,000 homes. The plants are expected to generate at least 380 GWh of renewable zero-carbon electricity annually, resulting in carbon dioxide emission savings of approximately 245,000 tons per year. / This project has been observed to have had a demonstrator effect, attracting interest from other industrial actors who have not typically engaged in energy projects but are looking to secure their own energy supply in the face of industrial blackouts.

Beneficiary engagement. FCDO remains eager to engage with beneficiaries under the IFC ERA instrument to assess impact of lending provided under this component. This could mean the programme team engaging with down-stream beneficiaries (medium-sized companies) of the RSF programme, who are likely to use loans enabled by UK and IFC support to install new equipment for energy generation. Alternatively, it could mean engaging with large companies that are producing energy to service their own needs (e.g. OKKO Group, MHP) under the other deals concluded thanks to support from partners, including the UK. All of these partners could be interviewed/surveyed under the Third-Party Monitoring contract, where security conditions allow.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

1. The IFC team has worked fast and creatively to identify and drive forward pipeline projects in a challenging lending climate. UK grant funding has been useful in buying down interest rates, in order to unlock larger amounts of more concessional lending for projects. In addition, FCDO’s engagement and support of IFC initiatives appears to have had convening power, with grant funding provided by FCDO acting to bring together members of the World Bank Group in efforts to improve market conditions around renewables, for example, under the umbrella of the RENEW project, a technical assistance intervention supported by FCDO under URES Output 4.
2. With all funding under the 2023 Administration Agreement nearly committed, the programme team will need to refresh the indicators for this component to reflect delivery rather than mobilisation. Milestones and results will need to be set and collected according to central International Climate Finance guidance on additionality and attribution. Recommendations for ICF KPI indicators are the following:
  1. ICF KPI 6: Tonnes of Greenhouse Gas Emissions Reduced or Avoided as a result of International Climate Finance;
  2. ICF KPI 7: Installed Capacity of Clean Energy as a Result of International Climate Finance (MW);
  3. ICF KPI 11: Public Finance Mobilised for Climate Change Purposes
  4. ICF KPI 12: Private Finance Mobilised for Climate Change Purposes

Ahead of committing further funding, the BE Kyiv team should continue to engage with IFC to define expectations on leverage ratios. This could inform the allocation of future URES funding to the ERA initiative. More generally, the FCDO could do more to cohere cross-FCDO engagement with IFC, to ensure messaging is consistent both among teams and with the strategic vision set from the top of the organisation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous Annual Review	Progress during FY24/25
FCDO should bring forward in full or in part our next tranche of financing of £10m, disbursing earlier than originally planned to enable IFC to provide further economic resilience support to companies important for energy security.	Achieved
Reinforce output 4, the programme’s technical assistance facility, by working in collaboration with IFC in support of reforms that can attract private investment into the sector.	Achieved – important to continue this synergy.
FCDO must negotiate the exit strategy on use of any ODA that is due back to the FCDO at the end of the 26 year lifespan of the IFC Economic Resilience Action for Ukraine returnable capital facility.	Not achieved – for 2025/26.
FCDO should negotiate more ambitious leverage terms – on use of IFC balance sheet, and also on leveraging private finance – ahead of making fresh commitments to the ERA.	Achieved; could be further systematised – see below.

Outstanding and new recommendations for FY25/26 for Output 2

Recommendation: FCDO should continue to keep the question of IFC’s leverage, of both its own balance sheet and of private sector finance, under review. It could be instructive to attempt a light-touch benchmarking of these ratios across comparable projects and geographies in which FCDO ODA has been blended with the IFC balance sheet. In concert with other HMG teams and with a shared approach across TIGER and URES from BE Kyiv, FCDO should define expectations for leverage ratios ahead of making any fresh commitments.

Recommendation: Going forward, URES SRO should continue to work with International Financial Institutions Directorate and UKDel Washington to develop a cross-FCDO view when contracting with IFC on questions such as pipeline visibility, results tracking, and payment in advance of need. These could potentially be suggested for insertion by FCDO in the standard bilateral agreement template.

Recommendation: FCDO should wait for full reporting before committing further funding. It has been difficult to fully assess performance in this Annual Review due to a mismatch between FCDO reporting timelines/processes and those of IFC. This has been communicated clearly throughout between programme teams and every effort has been made to reconcile approaches. Nevertheless, without clearer reporting, it has been difficult to assess this output fully.

Recommendation: URES programme team could consider adding more ICF-eligible indicators to this component, to be set and collected according to central International Climate Finance guidance on additionality and attribution.

Recommendation: FCDO must negotiate the exit strategy on use of any ODA that is due back to the FCDO at the end of the 26-year lifespan of the IFC Economic Resilience Action facility.

Recommendation: FCDO should look to reinforce IFC’s ability to monitor with use of our third-party monitoring contract. Sites are likely to be closer to a stage where they can be monitored by end FY25/26, though this will need to be kept under review.

Recommendation. Continue to work closely with IFC as adviser to GoU on attracting private investment. Use this relationship and insights gained from it to reinforce Output 4, the programme’s technical assistance facility, by working in collaboration with IFC in support of reforms that can attract private investment into the sector.

Output Title	Innovation. Full title: “Energy innovations are made available to Ukraine for building back better through a dedicated challenge fund and green hydrogen study”
Output number:		3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – adjusted based on recommendations in FY23/24 AR.

Outcome indicators	Milestone for March 2025	Progress as of March 2025
Green energy innovations and innovators are empowered to play a role in Ukraine's early recovery and reconstruction. Measured through % of Projects holding an LOI/MOU or similar with a Ukrainian organisation outlining an intent to deploy/trial technology or to develop market(s) either during or after the funded project.	Target: 10%	EXCEEDED / Achieved: 38%
Ukraine owns and drives the development of its own innovations under URES work within a partnership of equals. Measured through % of projects where either a Ukrainian organisation holds the technical IP rights for the solution or where a UK organisation holds the IP but that a Ukrainian commercial entity is either in negotiation or holds a formal agreement to exploit the technology in the territory of Ukraine.	Target: 45%	EXCEEDED / Achieved: 85%

Indicator(s)	Planned milestone (end of FY24/25)	Progress as of end March 2025
Output indicator 3.1. InnovateUkraine Round 1 competition socialised and executed	YES – activity was complete by end of FY23/24.	No further progress, target already met.
Output indicator 3.2. No. of feasibility studies fully funded as a result of succeeding in selection through Round 1 of competition	None – milestone of 4 feasibility studies was achieved by end of FY23/24.	No further progress.
Output indicator 3.3. No. of private sector pilots (demonstrators) fully funded as a result of succeeding in selection through competition	None – milestone of 9 pilots was achieved by end of FY23/24.	No further progress
Output indicator 3.4: % of InnovateUkraine pilots and feasibility studies promoted to potential investors	Planned for March 2025: 0%	SIGNIFICANTLY EXCEEDED / 85% promoted to potential investors
Output indicator 3.5: Volume of private finance mobilised for climate change purposes under InnovateUkraine as a result of International Climate Finance (KPI 12) Measure: amount of private sector match funding deployed in projects to date	Planned for March 2025: £0.7m	SIGNIFICANTLY EXCEEDED / Funding attracted: £1.2m
Output indicator 3.6: % of InnovateUkraine projects actively implementing their work plans (project survival since funding award)	Planned for March 2025: 100% of projects in implementation	ACHIEVED / 100% of projects in implementation
Output indicator 3.7: Number of geospatial and energy system models produced on green hydrogen production (SHIELD project, University of Oxford)	Planned for March 2025: 1 model	EXCEEDED / 2 models produced
Output indicator 3.8. Number of policy briefs, scenario reports and academic publications and recommendations on GH2/innovative, low-carbon technologies (SHIELD project, University of Oxford)	Planned for March 2025: 3	EXCEEDED / 4 papers produced

Briefly describe the output’s activities and provide supporting narrative for the score.

InnovateUkraine (Rounds 1 & 2)

1. Round 1. In May 2024, British Embassy Kyiv launched the Round 1 cohort of InnovateUkraine, around a month after all projects began work to pilot their innovations. The event, held in Kyiv, was attended by UK Foreign Secretary Cameron and Ukrainian Minister for Energy Herman Halushchenko. The event brought together the cohort for the first time and demonstrated senior UK commitment to Ukraine’s decarbonisation.
2. Operationally, FY24/25 focused on: building the InnovateUkraine brand through engagement; tracking the progress of the 13 projects under Round 1 progress (key successes in the box below); registering the programme as International Technical Assistance with GoU; and troubleshooting ad hoc obstacles to delivery. The programme’s accelerator component scaled up activities, developing business plans with Round 1 projects and identifying communications opportunities
3. For Round 2, InnovateUkraine team has been tightly focused on pre-competition engagement with actors in Ukraine’s innovation ecosystem, to assess how InnovateUkraine can become localised more formally in Ukraine. This has included working with the British Embassy’s governance reform programme, which has supported Ukraine to develop its WinWin Innovation Strategy.[11] Ensuring InnovateUkraine’s activities are well-integrated into GoU activities will constitute a major workstream over FY25/26. February 2025 saw the launch of the InnovateUkraine competition’s second round, announced by Foreign Secretary David Lammy during a trip to Kyiv. In London the same week, Minister for Europe Stephen Doughty hosted 80+ guests at King Charles Street, comprising partners funded under InnovateUkraine, government, business and academia, to mark and publicise the second application window.
  [11] WinWin is the Ukrainian Global Innovation Strategy until 2030, designed to empower governments and international partners to drive economic recovery, strengthen sovereignty, and win peace through breakthrough technologies, open markets, and global collaboration.
4. Overall, this reporting period has seen the relevance of the InnovateUkraine competition grow. With its ability to harness UK business, InnovateUkraine meets Growth Mission objectives, and represents a unique UK offer. Interest from investors demonstrates practical relevance of innovations supported for Ukraine’s energy future.

Case study: InnovateUkraine’s Round 1 cohort are already recording successes beyond the metrics captured in the above output indicators / 5 of the 13 projects from Round 1 already hold letters of intent from end users outside of their project consortium showing interest in deploying technologies for onward trials or on a future commercial basis. This shows both strong progress and clear alignment of InnovateUkraine projects with the needs of Ukrainian end-users. This is an encouraging milestone to have reached only half-way through the implementation of Round 1, whose projects will conclude March 2026. / 85% of projects can demonstrate that a Ukrainian project participant has or is in the process of gaining rights to deploy the technology or innovation in-country. This shows the strong positioning of local partners in projects. / Some projects are already noting additional private sector investment being committed in addition to the co-financing commitment which sits on the back of the grant funding agreement. Most notably the Geothermal Ukraine project has attracted interest from a Ukrainian company, that has provisionally planned to spend a significant sum on exploration drilling linked to a Transcarpathian project that the team is using as the practical case study in their process design. This commitment has happened as a direct result of our funded programme, demonstrating the InnovateUkraine programme’s ability to leverage additional private sector follow-on funding. / The project has had a “demonstrator” effect, building confidence in the feasibility and applicability of this model in other geographies, and increasing the implementing partners ability to deliver in more challenging contexts. This may in time yield a secondary benefit of increasing total activities under the Ayrton Fund, the UK’s pledge to commit up to £1bn for R&D for clean energy technologies and business models in developing countries.

University of Oxford SHIELD (green hydrogen and ammonia study)

This project is a standalone project distinct from InnovateUkraine. The University of Oxford-led Strategic Hydrogen Integration for Effective Low-carbon Development (SHIELD) project entered full implementation in FY24/25. The project is led by a consortium of experts from the University of Oxford, University College London, Imperial College London, and the Technical University of Munich, in collaboration with Kyiv School of Economics. The SHIELD project focuses on assessing the potential of green hydrogen and ammonia within Ukraine’s energy system. It investigates the cost-effectiveness of hydrogen developments and how they might impact the Ukrainian energy system and its resilience. The project aims to identify efficient pathways for energy use, now and into the reconstruction period.

The project has exceeded against both of its logframe indicators (the final two in the table above): both the GeoX and Detecco models for Ukraine are complete and ready to use,[12] and four publications were produced in FY24/25.[13] The project has seen successes with Ukrainian stakeholders, onboarding Kyiv School of Economics as a local partner and building a stronger relationship with the Ministry of Energy and international organisations such as the International Energy Agency, who sit on the project's advisory committee. SHIELD is demonstrating early evidence of contributing towards the URES programme’s aim of driving closer integration between Ukraine and Europe’s energy systems, included in URES's impact statement.[14]
[12] GeoX can be used to generate the levelized cost of green hydrogen or ammonia achievable at a high spatial resolution throughout Ukraine, assuming greenfield development of captive renewable energy. Detecco can be used to determine the optimal balance of different energy vectors, including hydrogen, ammonia, electricity, and others and their transmission systems, to meet a generalised energy demand within Ukraine.
[13] Paper 1: Why renewables should be at the centre of rebuilding the Ukrainian electricity system [link to paper]: This paper presents a comprehensive geo-spatial mapping of Ukraine's electricity system and its destruction during the ongoing war. Report 1: Green Hydrogen Use-Cases: Global realism and Ukrainian relevance: This report analyses potential use-cases for green hydrogen in Ukraine. Report 2: SHIELD Modelling Framework and Interlinkages: This report provides an overview of the project’s modelling framework. The framework is based on the interconnections among three models: GeoH2, Detecco, and PyPSA-Ukr. Report 3: Ukraine’s Energy Sector Outlook and Long-Term Energy Policy Priorities. This report explored Ukraine’s evolving energy landscape, providing an outlook of the sector and a critical review of domestic policy and legal frameworks and strategic energy objectives as well as a stocktake of infrastructure losses.
[14] The SHIELD project employs the Python for Power System Analysis (PyPSA) model, which integrates the energy system across Europe and Ukraine. One of the intended research outcomes using this model is a ‘Whole Energy System Model in Ukraine", to include a cost-benefit analysis of grid integration with the EU, with an emphasis on potential transmission line enhancements.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
- As mentioned, InnovateUkraine was extended for a second round this Financial Year. This more than doubled the envelope and extended the time of the project, to accommodate a second competition. This year, the URES team plans to build InnovateUkraine’s local presence by establishing a Ukrainian co-organiser of the competition that works to promote these innovations and aims to advocate for market and policy conditions innovations need to succeed.
- FY24/25 saw SHIELD mobilising and establishing the team. Over FY25/26, SHIELD plans to raise its profile, through presence at conferences such as Ukraine Recovery Conference in Rome (July 2025) or Rebuild Ukraine in Warsaw (November 2025).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous Annual Review	Progress during FY24/25
FCDO could consider funding a further competition round as part of a second phase of this programme or decide to provide the programme with additional resource. FCDO should also consider further innovation challenge funds, covering other sectors, for Ukraine to support building back better.	Achieved – second round launched.
As the projects funded by InnovateUkraine move through the stages of development (currently, projects are due to start work in March 2024) the programme team will need to work closer with colleagues building private finance and tech partnerships to expose these innovators to potential investors.	Achieved – achieved, accelerator is in train; cooperation established with HQ teams working on private finance and tech.
FCDO has an opportunity to promote pilots and feasibility studies we have supported as part of usual communications and public relations activities. Promotion of these innovations will help attract private investors for further pre-market development or attract the late-stage investment necessary to launch products and systems on the market.	Achieved – InnovateUkraine and SHIELD attracted Ministerial interest this reporting period, as a result of which the team published 5 press releases and more than 10 social media posts.
FCDO should begin now to tailor technical assistance support through the Flexible Technical Assistance component to put in place legislative and regulatory frameworks that can support the adoption of any successful industrial pilots, as needed.	Achieved. This work is in train – URES team is working with another BE Kyiv programme with an innovation workstream. URES team will continue to pursue innovation work within the correct teams.

Outstanding and new recommendations for FY25/26 for Output 3

Recommendation: FCDO should better establish and localise this component in Ukraine, to build GoU awareness of URES activities and deepen synergies with the Ukrainian energy and innovation ecosystem. This localisation effort would aim to build the ecosystem for low-carbon innovations, with a view to creating a future Ukrainian home for InnovateUkraine, and ensure that UK programmes are shaping policy at the governmental level. This localisation effort should include the following activities:

  - Engaging closely with GoU (Ministry of Digital Transformation and Ministry of Energy) to update on progress and create a climate in which policy decisions are taken with UK innovation work in mind;
  - Comms activities to Ukrainian audiences to raise the profile of these innovations;
  - Policy advocacy work that communicates the legislative and regulatory changes required to adopt and scale innovations;
  - Anchoring Ukraine’s innovation eco-system into the wider European innovation landscape.

Recommendation: The SHIELD green hydrogen project, Output 3’s second element in addition to InnovateUkraine, has the potential to enact transformational change on GoU’s approach to recovery. By delivering open-source modelling tools and research, the project has the potential to insert innovative methodologies into both short-term resource allocation and long-term strategic planning. The URES team should develop a methodology to measure and track the realisation of this potential in FY25/26. This could build the evidence base as the team considers a possible extension to this work.

Recommendation. FCDO should explore recalibrating milestones and targets, given overachievement against some indicators, and adding milestones to reflect the InnovateUkraine’s second round. Milestones were initially difficult to set against a zero baseline (as this was the first innovation competition FCDO had run in Ukraine) but with more data, these could be tweaked to be more realistic.

Output Title	Technical Assistance / Full title: “Flexible TA directed to progress efforts to: plan for a decarbonised energy sector, build capacity, support investment into the renewable energy sector, or progress regulations, reforms and legislation”
Output number:		4	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	Yes – adjusted based on recommendations in FY23/24 AR.

Indicator(s)	Planned milestone (end of FY24/25)	Progress as of end March 2025
Output Indicator 4.1. Cumulative number of energy or climate strategies, plans or policy recommendations developed (ICF TA KPI 1: Climate policies informed by International Climate Finance technical assistance)	Target (Dixi Group): 3 / Target (World Bank RENEW): 1 / Target (Energy Community Secretariat, biomethane project: 0 (revised down from 3; communicated in advance) / Total target: 4	EXCEEDED / Achieved (Dixi Group): 3 / Achieved (World Bank RENEW): 3 / Achieved (Energy Community Secretariat: Biomethane): 0 / Total achieved: 6 / Dixi Group NGO’s three documents for this reporting period were the following: / Ukraine’s National Energy and Climate Plan (NECP) was adopted by resolution of the Cabinet of Ministers of Ukraine on 25 June 2024. Cabinet of Minister adopted the resolution on Monitoring the implementation of the National Energy and Climate Plan for the period up to 2030; and analytical work was carried out and a draft methodology for calculating national weighted coefficients of greenhouse gas emissions resulting from final energy consumption were developed. The methodology is to be approved by the Ministry of Environment. / Energy Community Secretariat: Biomethane. This project is at an early stage but progressing well. The implementer (Energy Community Secretariat) is developing an analytical note which aims to demonstrate Ukraine’s potential for crop cultivation, harvesting, logistics and pre-treatment to obtain raw materials for the production of advanced biomethane in Ukraine. Once published, the implementer will organise capacity-building events, to build on and disseminate the analytical notes / Detail on World Bank Group’s RENEW project may be found in Annex C.

Indicator(s)	Planned milestone (end of FY24/25)	Progress as of end March 2025
Output Indicator 4.2. Number of drafts of priority reforms or legislation supported by this TA to attract private sector investment into the energy sector	Target (Dixi Group): 1	ACHIEVED / Achieved (Dixi Group): 1 / Dixi Group NGO’s result here was the completion and submission to Cabinet of Ministers of the resolution on the Monitoring the implementation of the National Energy and Climate Plan for the period up to 2030, agreed by all Ministries. This is both a climate policy and a reform to attract private sector investment into the energy sector, per the dual focus of this workstream.
Output Indicator 4.3. Capacity building - Public and private sector representatives reached by training on climate, energy, biomethane (ICF KPI 2: individuals and organisations supported by ICF technical assistance)	Target: (Dixi Group): 421 / Target (UN Global Compact): 2700 / Target (WB RENEW): 0 / Total target: 3121	NARROWLY NOT MET / Achieved (Dixi Group): 650 / Achieved (UN Global Compact): 2333 / Achieved (WB RENEW): 20 / Total achieved: 3003 / These results relate to dissemination of research and activities undertaken under indicator 4.1.
Output Indicator 4.4. / Capacity building: Government officials progress according to common European framework for languages (British Council)	Target (British Council): 70%	EXCEEDED / Achieved (British Council): 71% / The British Council’s English class provision yielded positive feedback from the Ministry of Energy, where senior leadership views these lessons as exceptionally high quality and a key draw when attracting and retaining staff. This was reiterated by the Ministry in a testimonial when URES was securing an extension to this project in September 2024. This project closed this year after exceeding its logframe target but continues under BE Kyiv’s cross-cutting programme for provision of English lessons to GoU. This has secured a future for this initiative, in accordance with the 100 Year Partnership.
Output Indicator 4.5. Number of Ukrainian companies reporting on sustainability indicators in regular progress report ("Communication on Progress") thanks to FCDO funding	Target (UN Global Compact): 40	EXCEEDED / Achieved (UN Global Compact): 70 / UN Global Compact Ukraine is the Kyiv-based chapter of the UN Global Compact (UNGC), an international business reform initiative. Under UNGC, the URES programme supports the Ukraine Energy Initiative (UEI) and the Climate Action Accelerator (CAA). This year, UNGC improved 70 Ukrainian companies’ reporting on sustainability indicators on progress against Ten Principles of the SDGs and other sustainability indicators. More detail in Annex C.
Output Indicator 4.6. Number of oblast with Geospatial analysis for potential RE projects suitable for auction process	Output not ready for reporting – for milestone setting in future years.	N/A
Output Indicator 4.7. Number of private sector participants / potential investors reached through market survey and investor forums.	Output not ready for reporting – milestones to be set in future years.	N/A
Output Indicator 4.8. Capacity building - Public and private sector representatives reached by training on SMRs, innovative technologies and supply chains (non-ICF).	Target (IAEA): 5	NARROWLY NOT MET – this was due to attacks on substations, meaning the relevant expert could not travel. / Achieved (IAEA): 4 / IAEA: This project is designed to build Ukraine’s capacity to develop and advance its SMR programme. During this reporting period, URES funded the participation via IAEA of four Ukrainian nuclear experts in the following workshop: “Interregional Workshop on Key Considerations regarding Infrastructure Development to Support Small Modular Reactors (SMRs) and Microreactors Deployment”. One individual was unable to attend due to an attack on the energy sector just before they were due to leave Ukraine. This reflects logistical challenges inherent to all URES activities when Ukrainian participants are required to leave the country.
Output Indicator 4.9. Number of consultants or technical experts seconded for the benefit of Ukraine's energy security and resilience	Target (EBRD): 10 / Target (NEA): 2 / Total: 12	Achieved (EBRD): [-] / Achieved (NEA): 2 / Total: 2 / NOT MET DUE TO LACK OF REPORTING. / NEA: Ukrainian secondees to the Nuclear Energy Agency (NEA). This year saw the conclusion of this initiative, which seconded two Ukrainian nuclear safety experts to the Paris-headquartered NEA. The beneficiaries of this support valued the understanding they built during their secondment of the international nuclear safety system and readiness of partners they met at NEA to more deeply understand the Ukrainian experience of managing critical nuclear systems and policies under the challenges of wartime. / EBRD: Under the EBRD’s Multi-Donor Account, FCDO supports the work of the Recovery and Reform Support Team (RST) and Rapid Response Unit (RRU) in Ukraine’s Ministry of Energy. The URES team is keenly aware of the crucial support provided under these workstreams, having discussed with the beneficiary (Ministry of Energy) and seen first-hand the important work led by individuals funded under this workstream at Government-led meetings in Kyiv. However, EBRD has not been able to report on additional indicators or outside of its reporting cycle. More detail in Annex C.

Briefly describe the output’s activities and provide supporting narrative for the score.

Table 1. Partners and indicators for which they are or will be accountable – detail in table above

	4.1	4.2	4.3	4.4	4.5	4.6	4.7	4.8	4.9
Dixi Group	X	X	X
UN Global Compact			X		X
Energy Community Secretariat: Biomethane	X
EBRD									X
British Council				X
World Bank/RENEW	X		X			X	X
NEA									X
IAEA								X

Case study 1: creation of the Green Transition Office at the Ministry of Economy / In 2024, the UK-funded Green Transition Office (GTO) was officially created at the Ukrainian Ministry of Economy. The GTO is a solely UK-funded initiative, designed in partnership with the UK Government and UK Climate Change Committee, to create the policy conditions necessary a low-carbon economic recovery. A significant achievement during this reporting period was the creation by Ministry of Economy of an internal unit of three dedicated to interfacing with GTO, building sustainability of this initiative. / GTO is working with the Ministry of Economy to implement climate and environmental considerations in Public Investment Management. The plan is to develop a methodology for evaluating and prioritising investment projects according to green criteria, amend legislation, and implement relevant considerations in the DREAM online platform. / GTO is helping Ministry of Environment develop a methodology for annual publication of emission factors. GTO has also drafted sectoral decarbonisation studies for the agriculture and cement industry sectors, finalised in March 2025, which will inform updates to Ukraine’s NECP and National Determined Contributions. / On Environmental, Social and Governance, GTO published a white paper on the EU’s Corporate sustainability reporting directive and European sustainability reporting legislation.[15]
Case study 2: Pivot to Critical Raw Materials / In early 2025, URES pivoted to supporting Ukraine to develop its first Critical Raw Materials (CRM) Strategy. This pivot was due to a gap in donor support for this work and due to increased interest in the sector in the lead-up to the signing of the US-Ukraine critical minerals deal. The Strategy is planned to be ready for presentation at the 2025 Ukraine Recovery Conference in July. / The implementing partner facilitated 10 stakeholder consultations with industry. Key challenges were a lack of industrial strategy, regulatory barriers, financing gaps, and workforce shortages. Businesses cited high electricity and logistics costs as drags on global competitiveness of their products. The implementing partner prepared analytical materials to identify gaps between Ukrainian and EU regulatory frameworks around CRM as part of EU accession, comparison of Ukrainian laws with the EU’s CRM Act and preliminary positions on EU non-binding CRM policies. / This pivot has afforded HMG insight into a sensitive political issue and enabled the UK to lean in productively to ensure Ukrainian decisions about its natural resources are data-driven. It demonstrated the programme’s flexibility and ability to respond to political shifts. This work should serve as a diagnostic tool, surfacing the most pressing or strategic areas in the field of critical minerals that would benefit from future UK support.
Case study 3: UN Global Compact – impact for local business and EU accession / Success story: decarbonisation grant awarded to Ukrainian company. In December 2024, UN Global Compact awarded a grant – with UK support – of £25,000 to a promising Kyiv company with strong climate credentials. The grant was awarded via a competitive process to Kyiv-based Green&Vitamin CityFarm to support its transition to renewable energy. were used to install a 25kW solar power system with a 50 kW inverter and 51 kWh battery storage, to reduce emissions and maintain operations during power outages. Installation was completed in February 2025. / Policy advocacy. Over this reporting period, the UN Global Compact’s Ukraine Energy Initiative (UEI) has deepened its involvement in the EU accession process by expanding its role within the working group for Chapter 15 “Energy.” This is cementing UN Global Compact’s position as a “voice for business”, both with GoU and in EU accession talks.
Case Study 4: Ukraine SMR Supply Chain Priming Initiative / This reporting period covered the early stages of a new industrial priming project for Small-Modular Reactors led by a UK implementing partner. While this project is too early-stage to report results, it is an exciting initiative whose early achievements and learnings will be reflected in the next Annual Review. / The project aims to survey the Ukrainian nuclear supply chain to identify key capabilities linked to potential future domestic and European SMR programmes and to connect potential Ukrainian suppliers to a live SMR programme. This is designed to lay the groundwork to insert Ukrainian SMR manufacturers into the supply chain, as these innovative products begin to be procured and delivered over the next decade. / This reporting period has seen the project team focus on building relationships with stakeholders, including SMR producers, so that the project is tightly aligned to producers’ needs. This will enable the project to scope and scour suppliers in Ukraine, to match them with SMR producers who might need Ukrainian companies to meet their needs.
[15] Papers: CSRD in Ukraine: Key points for Businesses; Analysis of ESG Standards for Ukrainian Businesses

Describe any changes to this output during the past year, and any planned changes as a result of this review.

- A key driver of progress under Output 4 in FY24/25 was the launch and scale-up of the GTO at the Ministry of Economy. Shifts in the donor picture this year precipitated URES’s pivot towards critical raw materials, demonstrating flexibility. URES would benefit from a political economy analysis of aspects of the energy and critical minerals sectors, to scope future TA interventions or tweaks to the current portfolio.
- In FY24/25, URES PRO led a robust assessment process for Technical Assistance bids, bringing in a wide range of team members to the consultation and communicating transparently with prospective partners. This process has strengthened the selection process for the Facility and adheres to best practice, i.e. running a competitive process where possible for the selection of all projects, even when implemented by a non-commercial partner.
- In FY24/25, URES began to shift into a more localised, streamlined posture for the Facility. This was part of plans under the second phase of URES, post-Addendum, to localise and rationalise this output, retaining only those projects that are closest linked to URES’s planned outcomes. As part of streamlining, the programme team has focused on a “one in, one out” approach, onboarding new partners only when other projects have run their course, and delivering new TA where possible via existing partners.
- The streamlining process must continue in FY25/26, with the programme team aiming to have a smaller number of partners composed mainly from local organisations, complemented by international organisations when there is a clear justification e.g. in terms of scale, reducing management burden, or representing a clear opportunity to convene and leverage funding from other partners.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead (3 paragraphs)

Recommendation from previous Annual Review	Progress during FY24/25
The energy attaché role has proven effective already and should continue to end of programme, that is, to end March 2026, to make the most of innovation partnerships funded via InnovateUkraine and support socialisation with potential private and development donor investors.	Achieved.
FCDO should explore broader partnerships to incorporate additional Ukrainian institutions including: MRTOT, energy regulatory bodies, the capital market authority, central bank, and key treaty organisations mandated to progress regional energy market integration; but maintain a heavy focus on reforms that can help attract high-quality private investment into clean energy transition	Urgency has reduced. URES has this year been complemented by the TIGER economic recovery programme, which is partnering with many of the institutions listed. URES has stayed tightly focused on achieving the final section – the programme is working to attract high-quality private investment into clean energy transition by building the business case and market conditions for green transition under the GTO.
FCDO should look to support the development of innovative climate finance to maximise opportunity for these types of social impact investors to invest in Ukraine. For example, creation of credible and transparent carbon markets - a way for fossil fuel dependent companies to offset emissions by investing in Ukraine’s clean energy transition.	Workstream being delivered under the GTO.
FCDO should continually tighten the focus and routinely refresh its strategy for use of the TA facility, focusing on critical regulatory reforms identified by IFC and Energy Community Secretariat; as well as on reform to the renewable energy feed-in tariff to realise the highest impact from this programme in driving a clean energy transition.	Achieved. Facility refreshed and call for bids completed in early 2025. Engagement ongoing with IFIs, GOU, civil society on keeping focus tight on reform.
FCDO should investigate options for lighter-touch management of the Flexible Technical Assistance Facility in a way that provides the same or better value for money.	Management remains in-house. Streamlining has begun and should continue, per the recommendation below.

Outstanding and new recommendations for FY25/26:

Recommendation: The URES team should continue to streamline and localise the Technical Assistance facility in FY25/26. By end FY25/26, this output should have fewer partners. When prioritising, teams should look for: UK USP combined with local direction-setting in a partnership of equals; ability to leverage additional finance; efficiency or catalytic potential; ability to synergise other URES components.
- Recommendation: Pause new disbursements to the EBRD’s Multi-Donor Account until June 2025, when project-level reports will issue. At that point, the URES team should disburse once reporting is assessed to be adequate.
- Recommendation: URES would benefit from a political economy analysis of aspects of the energy sector and the critical minerals sector, to scope future TA interventions or tweaks to the current portfolio, to improve the regulatory landscape and drive transparent and equitable exploitation of Ukraine’s natural resources.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

1. Output 1: All variable costs under the FCDO contribution to UESF relate to the procurement and delivery of equipment, with costs varying subject to external factors beyond the programme and partner’s direct control. Equipment is selected according to specifications set by Ukrainian operators. The main cost driver is availability of the equipment on the global market (which can vary significantly, as much equipment is highly specific to Ukraine and required in unprecedented volumes due to the frequency of attacks) – high demand and low supply drives up prices. Beyond availability on the global market, prices of equipment are also affected by overarching drivers of inflation, for example fluctuations in global energy and commodity prices, and exchange rate movements. To manage these risks, procurement is conducted through competitive tendering, with forward planning and pre-qualification of suppliers to ensure resilience and cost containment.
2. Output 2: IFC charges a management fee identical to what was charged for the other BE Kyiv programme that has partnered with IFC. The “price” of a given project – i.e. the amount of UK ODA required to unlock lending required for a given project – is specific to the sector and location of the project in question, as well as the risk appetite of lenders planning to complement UK ODA. The UK’s £25m contribution to the IFC’s ERA instrument under the URES programme, signed in 2023, has been almost fully exhausted, having funded four projects in total. These four projects were concluded at different times, against different risk backdrops, with divergent locations, modalities, objectives – and therefore leverage ratios.
3. Output 3: The implementing partner for InnovateUkraine charges a 7% standard management fee for their management of the InnovateUkraine competition. FCDO has provided additional funds to cover “Accelerator” support – helping innovators seek out and secure future funding – the implementer for the accelerator was contracted commercially via a tender carried out by the main implementing partner. This is to ensure that FCDO achieves maximum value for money, by socialising industrial research and feasibility study partnerships with institutional investors to ensure long-term impact of the UK contribution, preventing a “fund and forget” situation.
4. Output 4: The URES programme management team is deliberately choosing to manage the technical assistance facility in-house rather than subcontract the management of this facility. This is lower in cost, though does impose a higher management burden on the team. However, this decision has the advantage of enabling the team to retain control over quality and flexibility of the mechanism. Fee rates vary per individual contract, though all arrangements are non-commercial and exist under an accountable grant agreement, or other institutional administration agreement serviced and directly negotiated by FCDO.

VfM performance compared to the original VfM proposition in the business case

Output 1. As noted in the previous Annual Review, Business Case, and Addendum, Energy Community Secretariat charges no fees to FCDO to cover running costs of managing the UESF fund, improving the economy of this intervention.[16] The exception to this is that FCDO has elected to cover the costs of an independent audit of its contribution to UESF, and will continue to do so. However, to balance economy with effectiveness, FCDO stands ready to contribute further if e.g. the management burden of processing large and growing donations becomes overwhelming for the UESF team. FCDO is cognisant of the strong VfM of UESF, but keen to act as a responsible co-donor if called upon. Economy is strengthened by the fact that the majority of interest accrued on funds (less bank transaction fees and fees for audit and other services) held in UESF, including funds contributed by the UK, is repurposed for the UESF’s principal purpose – purchasing equipment for Ukraine’s energy sector. The interest accrued on the account reflects UESF’s policy of paying the supplier upon delivery, to avoid payment in advance and to incentivise smooth and fast delivery. Given items can have a manufacturing and procurement timeline of six months to a year, this means funds necessarily have time to accrue interest.
[16] The partner has confirmed that all costs associated with the FCDO contribution are directed exclusively toward the procurement and delivery of equipment and materials to Ukrainian energy companies. No portion of the FCDO funding is used for staff, operational overheads, or procurement agent fees. These administrative and coordination costs are financed from other donor sources and institutional contributions, ensuring that 100% of the UK’s support (less audit costs) results in direct, tangible assistance on the ground.

Under the UESF, the team has improved efficiency through selection and monitoring of partners (manufacturers) according to their efficiency of delivery, to achieve an effect of increased efficiency over time. In addition, the UESF team reports consolidation of similar interventions and tenders, to benefit from economies of scale. The Fund operates a centralised procurement mechanism via an international procurement agent, which aggregates demand across donors and counterparties. This approach has enabled best access to markets, economies of scale, improved pricing through competitive tendering, and reduced transaction costs for Ukrainian partners. To reduce wastage of funds through foreign exchange, UESF has concluded contracts in EUR where feasible to align with the Fund currency, and negotiated fixed-price contracts where market conditions allow.

The UESF team has worked to prevent inefficiencies and ensure effectiveness by engaging in pre-tender dialogue with vendors to assess delivery risks early and prioritising suppliers with proven in-Ukraine delivery experience, to reduce risks of delays. UESF has embedded flexible but controlled processes for emergency procurement and allocation. Decisions are taken swiftly, yet transparently, based on predefined eligibility and documented support requests, ensuring timely delivery while maintaining audit trails and accountability.

Output 1 has been assessed for equity with particular focus on environmental impact, particularly the provision of gabions, which are assessed to have limited environmental impact compared to e.g. the emissions embodied in concrete protective structures. Output 1’s ability to reach the most vulnerable is enhanced by efforts by both UESF and GoU to ensure that goods and services are targeted (geographically and/or to particular groups and institutions) where they can have most impact, based on a transparent prioritisation process. This has had the effect of increasing the resilience of public services during power cuts and supporting uninterrupted healthcare in high-risk areas. Independent monitors report that equipment is frequently redeployed based on emerging needs, showing that support is maximised to reach the most vulnerable i.e. regions already suffering severe energy shortages.

1. Output 2. Running costs have been kept within FCDO baselines established for partners, meaning the economy of this intervention is as stated in the Business Case. The amount of blended finance required for each project is subject to IFC’s internal Blended Finance policy to encourage economical use of grant ODA, and varies based on project. As other programmes have partnered with IFC from British Embassy Kyiv, the URES team is now working to streamline as far as possible to drive efficiency and ensure that where two programmes are using the same partner, FCDO efforts and communication are not duplicated.
2. To drive and evidence effectiveness, URES has worked this year to monitor UK’s leverage and additionality, for example in the context of the IFC’s ability to leverage public and private finance. Output 2 of URES has successfully leveraged other donors’ funding: as an indicative estimate, £10.3m in UK grant ODA can be said to have contributed to the mobilisation of total financing from multiple lenders of value over £400m - this is a 1:40 ratio, significantly higher than the ratio seen in the previous reporting period. The efficiency of leverage has also built confidence in its effectiveness, by contributing to key intended outcome of the programme, “Outcome 2: Private finance plays an increasing role in Ukraine’s green energy transition as part of reconstruction.” Output 2 is the largest single contributor under URES (and therefore under BE Kyiv programming) to International Climate Finance spend to date, with the programme contributing £25m in ICF-eligible spend since 2023, with high potential to contribute to emissions reduction and increase the equity impact of the URES programme overall.
3. Output 3. Economy of this output is identical to that set out in the Business Case. In terms of efficiency, over this reporting period, the URES team has re-run a second competition, building on institutional knowledge and lessons learned from the first round to target stakeholder engagement and maximise staff and senior time. Funding innovation for decarbonisation is recognised as a “Great Buy” (good evidence, strong effectiveness) for achieving climate mitigation goals by FCDO’s Economics and Evaluation Directorate. In the context of this intervention, the URES team has established outcome indicators under the innovation component, demonstrating a clear line of sight between innovation activities and the ultimate desired outcome of furnishing Ukraine with the innovations required to build back better. The programme is tightly focused on affording projects access to investors, to avoid a “fund and forget” approach, against per FCDO EDD guidance. Early successes of this approach have been evidenced by ability of InnovateUkraine projects to attract follow-on funding, demonstrating a clear multiplier effect of this spend. InnovateUkraine subprojects are beginning to report encouraging GEDSI results since projects are explicitly required to plan for and report on inclusion metrics over their lifetime.

1. Output 4. For all TA providers, the programme team has ensured economy of the costs of services provided through scrutiny of budgets and cross-Embassy benchmarking. This process has driven understanding of the level of effort and resource required, building confidence in this output’s efficiency in translating inputs to outputs. We have requested reporting on value-for-money from partners whose funding increased during the reporting period. The team should continue to put in place stretching milestones and accurately price in the level of effort expected. This year has seen the evidence base grow for the effectiveness of the URES technical assistance pillar particularly to build businesses’ access to investment (in the case of UN Global Compact) and to access other donors’ funding. Ukraine’s adoption of the UK-funded NECP was one of conditions for disbursement of the first regular payment – value €4.2bn - under the EU’s Ukraine Facility - have contributed to the evidence base for the economy of the technical assistance component. UN Global Compact and DiXi Group have provided impressively granular disaggregated reporting on groups reached when reporting on ICF indicators, demonstrating an increasingly wide geographical reach beyond solely Kyiv and a wide range of uptake in terms of gender of participants, and a demonstrable willingness and ability to integrate equity considerations into reporting.
2. Cost-effectiveness: Overall, URES interventions under this reporting period have supported the contracting of 41.4MW of energy generation under Output 1 - this will (once installed) represent a boost to productivity through enabling transport, trade and business activity, contributing to stronger growth relative to a counterfactual of no emergency repairs. Similarly, as a rough estimate, transformers and other transmission equipment provided under the first UESF contribution in 2023 would have capacity to distribute power to 8075 households (a medium- to large-sized town). While this is of course part of a larger donor effort, the URES programme can nevertheless be said to be cost-effective in that its inputs are translating to overall resilience of the grid and economy.
3. UESF prioritises procurement according to Ministry of Energy’s evolving prioritisation framework, ensuring resources are directed toward the most urgent and impactful needs. This tight coordination with GoU, which acts as the overall prioritising and coordinating body, is particularly effective in the energy sector, enhancing the cost-effectiveness of the response. The URES team has used our third-party monitoring to provide ongoing recommendations and assessment of cost-effectiveness. This could be drawn out more comprehensively through a formal evaluation, drawing on the evidence set out above.

E: RISK [1/2 page-1 page]

1. Risk management. The team continues to manage risks via quarterly reviews of the risk register, escalating when appropriate and ensuring after mitigation, risks do not exceed the centrally-set risk appetite. This is complemented by monitoring of energy-specific risks to delivery, as covered in a cross-portfolio delivery risk register. Cross-portfolio delivery risks are discussed at the monthly programme board and quarterly country board to ensure visibility for HMA and appropriate escalation.
2. The programme continues to work with partners to ensure robust risk mitigation strategies are adopted to minimise the risk misappropriation of equipment. Monitors in FY24/25 reported encouraging findings on the level of safeguards in place at energy facilities.[17] Relatedly, there is a major risk of misuse or diversion of funds - the mitigation of this risk is the structure of the UESF, with Energy Community Secretariat as fiduciary, plus an independent procurement agent. The first audit of UK funds was completed in 2024 and identified no concerns.
  [17] TPM reported that gabion walls are subject to systematic monitoring and audits both internally and by government institutions. GoU receives reports about the gabions, including when they were installed and whether they were the right type and in sufficient quantities. The State Inspectorate for Energy Supervision also conducts monitoring visits, and reports back to GoU.
3. The programme team has mitigated the risk of dual-use items being used for military purposes via earmarking, opting not to fund items that have most relevant dual uses. Third-party monitoring will continue at regular intervals, and no concerns were identified in the first or second round of checks, conducted in 2023 and 2024. Finally, there is a major risk that UK-funded assets are damaged or destroyed. This has been mitigated by adopting a dispersed approach, such that funding is spread over a large geographical region. It has been encouraging to learn that items delivered to the transmission grid operator are redeployed at different sites over their lifetime, potentially reducing the risk of targeting. FCDO will continue to work with UK MOD colleagues to understand risk of targeting when allocating funding.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of FCDO:
1. A key challenge over this year has been managing the programme against a backdrop of staff disruption: UK-based staff operate on a rotation basis with breather breaks and tours are short in a conflict zone. A positive development over the reporting period was the onboarding of two new Kyiv-based staff, who work on programme and finance management and have made a major contribution. However, these individuals split their time between URES and other elements of the portfolio, meaning URES is comparatively lean in staffing term. This report therefore includes a recommendation to advocate for a full-time programme manager.
2. Another positive staff development over FY24/25 was securing approval to recruit a full-time SRO, a role that was previously filled by an individual who double-hatted as a Private Sector Development adviser. Alongside, the programme has one full-time PRO and a full-time energy attaché in Vienna, who operates as a helpful fulcrum between the rest of the programme team (based in Kyiv/London) and major Vienna-based partners.
3. Interviews with partners surfaced concerns about the rate of churn in BE Kyiv. Nevertheless, stakeholders were appreciative of FCDO’s flexibility and respect for Ukrainian implementers and their expertise. Other HMG teams commended URES’s responsiveness and openness to collaboration, across Embassy and comms teams.
4. FCDO has managed programme finances via regular comms with partners, testing forecasts and applying scrutiny to assumptions inherent to budgets. The variance against planned budget for FY24/25 was 0.02%, significantly below the 2% threshold.
Performance of Partners:

Overall, implementing partners have provided robust and timely reporting – where reporting has not fully met expectations, this has been followed up by the team and reflected as a recommendation in this review. Audits submitted by UESF and UN Global Compact in April 2025 have provided assurance on partner governance and systems. For our other partners, audits are due to be received six months after the close of projects. More detail on Partner performance may be found at Annex D – Detailed partner performance.

A summary of expected spend for FY24/25 may be found in the table below:

Component	FY24/25 (spent or accrued)
Output 1: Emergency needs	£62.48m
Output 2: Private sector resilience	£0.5m
Output 3: Innovation	£7.8m
Output 4: Technical Assistance Facility (including TPM)	£2.3m
Totals:	£73m (of 13% is International Climate Finance-eligible)

Recommendation: The URES SRO should advocate for a full-time Programme Manager as minimum for this major project. Per FCDO best practice, a programme of URES’s size would typically require a dedicated SRO, PRO, adviser and programme manager as minimum.

Recommendation: Continue to refine coordination with comms teams, flagging opportunities ahead of time and maintaining an overview of equipment deliveries and publicity opportunities to streamline public outreach.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

1. Monitoring. The URES programme team engages with beneficiaries at minimum each quarter for check-ins and requests quarterly reports from partners covering interim results against output indicators, financial status of projects, and activity updates. This reporting period, the URES team engaged an external third-party monitor to conduct a round of monitoring in the second half of this reporting period. This partner met expectations and was responsive on ad hoc asks. The partner worked well to take onboard feedback; both in terms of methodology and analysis of results, working closely with HMG experts to refine analysis and conclusions. Ultimately, URES team was happy with the final product, the main findings of which are set out in Section C (Output 1). The reports met with a positive reception from both the Ministry of Energy and Energy Community Secretariat.[18]
  [18] Detail on monitoring exercises: FY23/24: A verification exercise of 850+ fossil fuel generators donated to the Ministry of Energy; An external assessment of the functioning of a small-scale solar pilot supporting civilian resilience. FY24/25: a verification exercise of the UK’s first £10m tranche to support the transmission sector; a verification exercise and assessment of £2m of gabions, provided bilaterally government-to-government
2. Annual Review. This Annual Review was conducted over a two-month period from March to May 2023. The process began by setting ambition, requirements and exam questions with the programme team. The review took into account stakeholder interviews, including the programme team, cross-Whitehall colleagues in the Ukraine/energy space, implementers, externals and representatives from GoU Ministries. Insights were combined with lessons and evidence provided by third-party monitors.
3. Evaluation. The programme team has not yet conducted an evaluation of this work but is engaging with infrastructure experts in the UK military to better understand the impact of support provided so far. As the team looks to refresh outcomes and milestones against outcomes over FY25/26, it will also explore delivery mechanisms for a more impact-focused evaluation assessment.
4. Evidence. GoU restricted information on repairs and generation capacity in September 2024, citing security concerns. This has made it harder to assess over all resilience and stability of the energy system. However, the programme has worked around this, drawing on reporting from within the Embassy’s political team, wider contacts, G7+ donor meetings, and inputs from programme partners such as DiXi Group. The team has also commissioned assessment from the UK’s Royal Engineers to get closer towards understanding the impact of our spend on emergency needs. The programme team is used to working bottom-up on results, given the limited nature of data in Ukraine during wartime, though it is hoped that this will improve towards the end of the programme’s life.
5. In terms of disaggregation of data for learning and reporting purposes, almost all partners have adapted well to requests from the programme team to disaggregate reporting data per HMG requirements. Partners made a first attempt at this during ICF results collection at end of Financial Year 24/25, providing impressive detail in a short period.
6. Learning. The results of the second round of third-party monitoring were presented to British Embassy Kyiv, the Ministry of Energy, Energy Community Secretariat, and cross-Whitehall partners in February 2025. The outcomes from the exercise have influenced both the recommendations found within this Annual Review and the design of future work.

Date of last narrative financial report	-	Date of last audited annual statement	UESF: April 2025 / UNGC: April 2025

## Annex A: Full Theory of Change and suggested changes to outcome milestones

Impact: increase Ukraine’s energy security by strengthening access to the European power grid; supporting the efficient use of energy; and decreasing reliance on hydrocarbons.
Outcome 1: Emergency needs: Ukraine's energy system remains resilient throughout the conflict
Output indicators: Number of supply contracts signed for the continued stable operation of the Ukrainian electricity system for the sole benefit of TSO Ukrenergo
Number of supply contracts signed for the recovery of the heating sector
At least 3 additional other donors join the Ukraine Energy Support Fund after receiving support on mobilising their commitment from the UK
856 generators distributed to uninterruptible customers in Ukraine ahead of winter 2022/23 and redistributed according to GoU prioritisation.
Quantity of generation capacity returned to the grid thanks to UK-funded equipment (MW/GW). Measured through contracts signed via Energy Community UESF
Number of sites protected by gabions/physical protection. Measured via number of contracts signed
Outcome 2: Private sector resilience: Private finance plays an increasing role in Ukraine’s green energy transition as part of reconstruction
Number of businesses in Ukraine supported by IFC’s ERA Programme thanks to UK support
Number of development partners contributing to the IFC's ERA Ukraine Program, post UK contribution
The leverage ratio of the aggregated total FCDO support in FCDO-supported ERA projects to the aggregated total project cost for the entire portfolio of FCDO-supported ERA projects
Volume of climate finance mobilised for climate change purposes as a share of the total ERA portfolio
Outcome 3: Innovation: Ukraine builds back better using the best and latest innovations
InnovateUkraine competition socialised and executed
No. of feasibility studies fully funded as a result of succeeding in selection through competition
No. of private sector pilots (demonstrators) fully funded as a result of succeeding in selection through competition
% of Pilots and feasibility studies are promoted to potential investors
Volume of private finance mobilised for climate change purposes as a result of International Climate Finance (KPI 12) Measure: amount of private sector match funding deployed in projects to date
% of projects which are actively implementing their work plans (Project survival rate since funding award)
Number of geospatial and energy system models produced on green hydrogen production
Number of policy briefs, scenario reports and academic publications and recommendations on GH2/innovative, low carbon technologies.
Outcome 4: Technical assistance: TA enables GOU to plan for a decarbonised energy sector and progress reforms that can attract greater private investment in the sector and support integration with European, regional and Western energy markets
Cumulative number of energy or climate strategies, plans or policy recommendations developed (ICF TA KPI 1: Climate policies informed by International Climate Finance technical assistance)
Number of drafts of priority reforms or legislation supported by this TA to attract private sector investment into the energy sector
Capacity building - public and private sector representatives reached by training on climate, energy, biomethane (ICF KPI 2: individuals and organisations supported by ICF technical assistance)
Capacity building - Government officials progress according to common European framework for languages
Number of Ukrainian companies reporting on sustainability indicators in regular progress report ("Communication on Progress") thanks to FCDO funding
Number of oblast with geospatial analysis for potential RE projects suitable for auction process
Number of private sector participants / potential investors reached through market survey and investor forums.
Capacity building - Public and private sector representatives reached by training on SMRs, innovative technologies and supply chains (non-ICF).
Number of consultants or technical experts seconded for the benefit of Ukraine's energy security and resilience
Changes to outcome milestone indicators could include the following:

- Outcome 1: “Ukraine's energy system remains resilient throughout the conflict”. Indicators against this outcome as designed foreground European integration – important, but not a topic over which URES has a high level of influence. Similarly, the second outcome indicator measures effects for end-users – this is possible to collect results for, but more straightforward for generation equipment (e.g. turbines) that have a MW value, and notoriously difficult for physical protection or transmission equipment. Indicators for this outcome should be tweaked to become more system-wide, tracking the system’s increased resilience across a number of fronts. This could be a rough estimate, based on generic assumptions about the type of e.g. substation supported by UK-funded transformers – as part of this review, the programme team has worked with experts to collect such estimates. But beyond that, the team could develop a deeper methodology, drawing on academic literature, insight from third-party monitors, UK experts, and discussions with the teams delivering this support at the Energy Community Secretariat (given their interaction with energy companies) and work/results from the Ukrainian grid operator. A working group composed of representatives could seek to establish system-wide outcome indicators that track the increase in resilience seen within the Ukrainian energy system thanks to our emergency support. One potential starting point for developing a methodology is this paper,[19] which acknowledges upfront the challenges of measuring impact of resilience initiatives (and therefore of prioritising them) on system-wide resilience.
  [19] One potential starting point for developing a methodology is this paper, which acknowledges upfront the challenges of measuring impact of resilience measures on system-wide resilience: “Applications of Measuring and Valuing Resilience in Energy Systems”, National Renewable Energy Laboratory, August 2023.
- Outcome 2: “Private finance plays an increasing role in Ukraine’s green energy transition as part of reconstruction.” This is a relevant outcome for the programme, but the indicators linked to it both measure private finance mobilisation (increased flows of private finance towards companies, driving either green transition or green energy production). To prevent duplication, one of the outcome indicators could be instead tweaked to capture URES’s ability to unlock local credit and therefore increase access to finance, with specific focus on the perspective of end-users. This could read: “volume of credit in Ukrainian banks unlocked via local companies’ participation in Risk-Sharing Facilities – finance accessed over life of the programme”. This is more real-world than the volume of finance that either FCDO, IFC, or the local bank contributes to the facility, and demonstrates an outcome that is both outside of FCDO’s full control but also in part attributable to grant funding FCDO has contributed.
The other outcome indicator could speak to a wider trend of leverage (public and private finance mobilised in relation to grant funding) for the low-carbon investment projects FCDO has supported. As part of the evaluation exercise, these figures and their trajectory over time could be compared to e.g. quantity of private finance leveraged by other comparable MDB-led projects in the same sector.
Outcome 3. InnovateUkraine has already worked to ensure outcomes are realistic and pitched correctly, as changes or benefits derived following directly controllable outputs. Outcome Indicator 3 speaks well to the intended outcomes of the University of Oxford SHIELD project focused on green hydrogen, the second project under Component 3.
Outcome 4. Outcomes on the Technical Assistance component are broadly measurable but could be more stretching, for example by deploying ICF methodologies for “ability to enact transformational change” – while ICF KPI 15 on transformational change is typically used as an output indicator, charting “ability”, the transformational change itself could function as an outcome.

## Annex B: Aspects of the UK-Ukraine 100 Year Partnership addressed by URES activities

  1. Pillar 5, paragraph 1: “We will promote attracting long-term investments, including from the UK, in Ukraine’s clean and renewable energy.” à Output 2 under the URES programme is actively providing capital investments in renewables infrastructure for the private sector, including to genuinely trailblazing projects such as the first major greenfield wind project to attract investment since 2022. The programme team is complementing this investment via reform work undertaken via Component 4, diagnostic work undertaken by DBT, and cooperation with the Ukraine Early Recovery and Reconstruction Department.
  2. Pillar 5, paragraph 1: “Through Ukraine adopting key reforms, we will support a more enabling environment for private sector participation in the clean energy transition”. à Under URES, Output 4 is creating an enabling environment – for example via work with UN Global Compact, the World Bank RENEW project, and the Green Transition Office – to set the regulatory framework and equip companies to attract future investment.
  3. Pillar 5, paragraph 2: “We will cooperate in the protection of civilian energy infrastructure and will counteract cyber and hybrid attacks.” àThis work is being undertaken via Output 1, which is protecting critical sites via various forms of physical protection. This is complemented by UK infrastructure experts, who are taking a hands-on approach to the sharing of best practice in the field of infrastructure protection and the training of engineers in these techniques.
  4. Pillar 5, paragraph 3: “collaborating in projects on renewable and low carbon hydrogen production, storage and transport and other renewable gases”. à This is being achieved under Output 3 - its innovative green hydrogen project, SHIELD, is furnishing GoU with the tools to plan for a smart, commercially-optimised next-generation energy sector.
  5. Pillar 5, paragraph 3: “supporting development of a Ukrainian critical minerals strategy and necessary regulatory structures required to support the maximisation of benefits from Ukraine’s natural resources”. àThis area of work has emerged as a major new area for URES over this reporting period, as Component 4 has pivoted to supporting Ukraine’s strategic approach to critical minerals.
  6. Pillar 5, paragraph 3: “cooperation in the field of nuclear energy and nuclear fuel supply; supporting the safety of nuclear facilities, adoption of best practice, and replacement of Russian technologies and nuclear fuel in Europe and other countries” the URES project, under Output 4, is anchoring Ukrainian nuclear specialists into international organisations via secondments and workshops, fostering the exchange of best practice between Ukrainian and international experts in these fields, and priming the Ukrainian supply chain to contribute to the rollout of innovative nuclear technologies in future.
  7. Pillar 5, paragraph 4: “Develop a safe and secure place for UK industry to invest in Ukraine’s energy sector, including an updated and transparent, EU-compliant regulatory environment ready to receive innovations, and a solid platform for growth opportunities for the private sector.  Ukraine will commit to implementing the National Energy and Climate Plan anchored through the Green Transition Office and for Ukraine to update its National Determined Contributions to align with the NECP and deliver Net Zero.” à This work is being undertaken under URES Output 4 – analysis and policy papers delivered under the Green Transition Office (namechecked in the Declaration) are enabling Ukraine to build its climate and decarbonisation policy, and to define its emissions targets.
  8. Pillar 8, paragraph 3: “The UK will support Ukraine to establish its innovation strategy and will explore ways in which it could facilitate its implementation.” à Component 3, particularly the InnovateUkraine competition, is a key avenue via which the UK can make progress against this commitment and support Ukraine to meet its innovation ambitions.

## Annex C: Detail on Technical Assistance facility activities.

UN Global Compact – narrative

1. UN Global Compact Ukraine is the Kyiv-based chapter of the UN Global Compact, an international business reform initiative and the world’s largest community of responsible businesses. Under UN Global Compact, the URES programme supports the Ukraine Energy Initiative (UEI) and the Climate Action Accelerator (CAA). The CAA aims to empower Ukrainian businesses to address climate change by providing comprehensive education, support, and resources for setting science-based emissions reduction targets. The programme focuses on strengthening climate capabilities, improving climate risk reporting and management, mobilising investments in low-carbon solutions, and enhancing the competitiveness of Ukrainian businesses in global markets. The UEI brings together the major players in the Ukrainian energy sector, representing them in EU accession negotiations, producing reporting and research on shared challenges (e.g. human capital), and producing learning materials and modules to upskill energy sector workers.
2. New members. At the end of the reporting period, UEI had 75 participants including national and international energy sector companies. UEI members together oversee 86 ready-to-build projects in the energy sphere in Ukraine. New participants who have joined the initiative under this reporting period include Energy Company of Ukraine, a national energy trading company, and JSC Market Operator, a fully-state-owned enterprise responsible for organisation of purchase and sale of electricity on the Day-Ahead Market and the Intraday Market.
3. Individuals reached: Over this reporting period, 2,613 people registered themselves for UEI events and received post-event reports. During the same period, 1,905 people registered for CAA events and received post-event reports. Of these, 428 people attended COP29 events organised by CAA.
4. Publications: 62,634 people were reached through UEI-published White Papers.
5. Comms: UEI was actively promoted through its own and partner social media and media channels, reaching at least 57,097 people. CAA was actively promoted through own and partnering social media and media publication reaching at least 680,076 people. The most prominent promotion the CAA received was through Forbes in the article "Global Changes: How Ukrainian Business is Adapting to European Environmental Standards," which reached an audience of 650,000.
6. Companies completing non-financial reporting assessments: over the reporting period, 70 companies completed baseline non-financial reporting assessment.
7. Design of educational materials: from December 2024 to March 2025, UEI led a working group of representatives from business and academia to design and deliver a distance learning higher education course, entitled “Power Engineering Specialist.”

EBRD Multi-Donor Account – Ukraine Recovery & Reform Architecture - narrative

FCDO has soft-earmarked to provide support to the energy-related substreams of the EBRD’s pooled Multi-Donor Account, contributing £277,065 in FY24/25. The total costs for energy-related work under this project for one year were projected to be approximately €1.8m. Since the UK funded approximately 1/5th of this amount in this financial year, we expect to fund approximately 1/5th of the 53 individuals supported to deliver this work. As a result, the target the UK has set for this workstream is 10 individuals against Output 3.8, “Output Indicator 4.9. Number of consultants or technical experts seconded for the benefit of Ukraine's energy security and resilience”.

World Bank-IFC: Ukraine Renewable Energy Scale-up Initiative Technical Assistance (RENEW) - narrative

The URES programme committed funding to the World Bank-led RENEW initiative at the end of FY23/24. The RENEW Ukraine initiative aims to create a market for grid-connected, renewable energy projects (complete with storage), at scale and at competitive tariffs. The program will aim to add 20GW of wind and solar and 5GW of battery storage by 2040. In the immediate-term, the RENEW team is working to create an enabling environment to attract investment to Ukraine’s energy sector, potentially by creating an auction system. The project is geared towards installing new renewables capacity post-war.

In this reporting period, the RENEW project team has assigned roles across World Bank Group entities, defining how IFC's transaction advisory and financing and MIGA's political risk insurance components could help RENEW meet its objectives. This demonstrates a catalytic effect of this funding, inasmuch as it is bringing to bear the unique strengths of different members of the World Bank Group on a single topic.

The reporting period has been dominated by preparatory and coordination work: the RENEW team is leading collaboration with Net-Zero World, a research outfit that was responsible for the modelling for Ukraine’s National Energy and Climate Plan. Net-Zero World’s existing technical knowledge of grid integration and resource mapping mean it is well-placed to help the RENEW compile internal and external geospatial data on renewables potential (one of the later-stage outputs listed in the table above). The team has continued to collect inputs to enable auction design, including drawing comparisons with other schemes (FODER, Contracts for Difference).

The RENEW team has coordinated impressively with EBRD, Energy Community and other major players as discussion around derisking instruments for reconstruction has intensified. The RENEW team has fully engaged with new and emerging instruments, communicating clearly and promptly throughout to FCDO on complementarity of RENEW with other instruments. Based on RENEW’s progress so far, the team has made valuable contributions to the policy discussion around any future guarantee fund for renewables projects, providing advice on governance and pricing.

In terms of results, this project is on a slower burn than others under this component, inasmuch as it is explicitly focused on delivering the majority of its results post-war. Any new disbursements would need to depend on delivery of concrete results against Outputs 4.6 and 4.7, to avoid a situation in which URES is funding activities in advance of need. Nevertheless, the project remains well-structured, sustainable in scope, and well-calibrated against a complex donor landscape. The URES team should continue to engage proactively to make RENEW a success and ensure relevant stakeholders are aware of its activities.

## Annex D: Detailed partner performance

Component 1: Emergency support (UESF) The Energy Community Secretariat procured an external audit of the UK’s contribution to their pooled fund, the UESF, during this reporting period. In January 2025, the Energy Community Secretariat. In the interim, the Energy Community has provided regular updates in the form of their procurement tracker, issued monthly. As mentioned above, the change of procurement partner was managed in a transparent and proactive manner, with regular updates to donors – FCDO was grateful for the tight grip of the situation demonstrated by UESF.

Component 1: Emergency support (gabions) Over FY2024/25, the UK bilaterally delivered gabions to the Ukrainian energy sector using MOD procurement and delivery channels. These were a success story – their high-quality and rapid delivery has been highly praised by beneficiaries and monitors. Third-party monitoring also provided confidence on the level of scrutiny applied to gabion wall construction and documented several layers of quality assurance, conducted by energy companies and local authorities. This has demonstrated that this equipment is carefully deployed and highly valued. This project is now closed and further partner management no longer required.

Component 2: Private sector resilience: IFC began disbursing FCDO funds in summer 2023 and quickly built a strong pipeline of future investments. Additionally, IFC has been collaborative in sharing any information that is not commercially sensitive and working together with FCDO on policy engagement. The result of this is that the partnership has grown, with IFC becoming a major partner for the British Embassy Kyiv’s new economic recovery programme, TIGER.

IFC has provided standard reporting products per the agreed-upon timeline. However, despite constructive engagement from the IFC team, it has not been possible to set milestones for output indicators per FCDO’s internal procedures. The indicators that were set (without milestones) were reported against only partially at the end of this reporting year. This has made it difficult to assess performance for this reporting period. Arriving at a mutually acceptable approach to reporting and results will be a top priority for the URES team this year ahead of any fresh commitment to the IFC facility.

Once the UK’s full contribution to the IFC platform has been fully disbursed, likely in either FY25/26 or FY26/27, the programme should look to request an external audit from IFC. IFC and FCDO will at that juncture be able to jointly decide on the most appropriate scope and terms of reference of such audit, upon which IFC will arrange for such external audit. Finally, FCDO should continue to make available to IFC the use of our third-party monitoring contract, to verify the everyday functioning of facilities that have benefited from UK grant funding incorporated into IFC loans.

Component 3: Innovation– partner performance. Our implementing partner for the InnovateUkraine competition has been responsive as the competition has entered deeper implementation. The partner has shown grip in managing a large number of complex projects. The programme team, including newer members, has invested time in understanding the reporting protocol from the partner and are now at a stage where financial reporting can be quickly interpreted. The working relationship between FCDO and the implementing partner has been collaborative and a true “partnership” - something the programme team should look to preserve despite anticipated personnel changes.

The forecast for FY24/25 decreased significantly between December 2024 and March 2025, amounting to a reduction of £1.1m against the December forecast. This is due to one project’s failure – a not unexpected outcome in an innovation competition – and slippage of some projects to the following Financial Year. Narrative reporting is timely and detailed. However, financial reporting indicates a slow burn rate for the project and a substantial discrepancy in forecasting, with accruals reconciled with some delay. Going forward, the programme team aims to monitor the burn rate more closely and understand its root causes.

Component 3: University of Oxford, SHIELD project. University of Oxford has been responsive and prompt in financial reporting. The SHIELD team has surfaced risks to delivery proactively to the FCDO programme team and acted collegiately to resolve these issues.

Component 4. Technical Assistance: The technical assistance strand has been well-managed from a financial and programme perspective. Dixi Group has completed work on or under budget and raised requests about changes to operational spend proactively. Dixi Group provided a full value-for-money assessment at the end of this reporting period, following a scale-up of funding. UN Global Compact has demonstrated strong financial management, reporting risks of variance early, assiduously benchmarking salaries, and providing full justification for budget lines. Dixi Group and UNGC are working closely with the BEK programme team to enhance financial reporting and streamline processes from both sides. This cooperation demonstrates high commitment, readiness for change implementation, and unity in the desire to adhere to high standards. This applies to narrative and financial reporting, as well as monitoring and evaluation, including data gathering. The rest of the open projects under this strand are financed via lump payments up-front, including to international organisations and multi-donor pooled funds, meaning financial reporting is less granular and forecasting is not required.